## Annual Review Template

Title: Exiting Poverty in Rwanda (EPR) Programme
Programme Value £ (full life): 64.5m		Review date: November 2025
Programme Code: [AMP ID#] : 204477	AMP start date: / 1.11.20219	AMP end date: / 30.06.2027

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/54145050.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Rwanda has made notable progress in poverty reduction, with new household survey data showing the national poverty rate falling from 39.8% in 2017 to 27.4% in 2024 and extreme poverty declining by 5.9%, lifting 1.5 million people out of poverty[1]. These gains are attributed to sustained investments in social protection (SP), human capital and economic growth. SP plays a critical role in protecting the poorest and most vulnerable, enhancing resilience and providing pathways out of poverty. While progress has been achieved significant challenges in coverage and adequacy remain. It is within this context that the UK Government is an established partner of the Government of Rwanda (GoR) in developing its national SP sector in line with its National Strategy for Transformation (NST2). Through two previous phases of support (2008–2013 and 2013–2018), the UK helped establish and expand Vision Umurenge Programme (VUP), Rwanda’s flagship SP programme.
[1] EICV7 - Poverty Profile Report 2023/24 | National Institute of Statistics of Rwanda

This third phase of support, the Exiting Poverty in Rwanda (EPR) programme (£64.5m, 2019-2027) is co-financed by the UK Government (£46m), the Swedish International Development Cooperation Agency (Sida) (243m SEK, approximately £18.4m)[2] and from January 2026 the German Government (via KfW) (€18 m, approximately £15 m). The EPR takes a comprehensive reform approach to support the GoR to create and scale up a sustainable, self-financed and inclusive system for supporting the most vulnerable, helping the poor manage shocks and enabling more people to sustainably exit poverty. To achieve this, the programme has a strong focus on influencing the wider policy context, strengthening systems, and building capacity to underpin the delivery of SP assistance and its sustainability.
[2] Financial commitments according to the third amendment to the MOU.

The programme is delivered through three complementary modalities: 1) Non-Budget Support Financial Aid (NBSFA) to the GoR, of which 18% is intended to be performance-based: 2) an embedded Technical Assistance Facility (TAF) to support the lead Ministry of Local Government (MINALOC) and the Local Administrative Entities Development Agencies (LODA); 3) independent monitoring, evaluation and learning (MEL) to support evidence-based delivery and accountability[3].
[3] LODA is the GoR delivery partner for financial aid, Cowater are contracted to lead the TA Facility, Oxford Policy Management (OPM) is contracted to lead the MEL component

The reduction in UK ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition focused on securing gains and leveraging new partnerships to support sustainable financing in Iine with evolving GoR priorities. Ongoing discussions with partners and the sector have further informed decision making on early closure of the monitoring, evaluation and learning sub component.
About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.

Summary supporting narrative for the overall score in this review

The programme scores an A at this Annual Review based on routine and proportionate assessment of progress over the period between September 2024 to September 2025 against output and outcome indicators. It draws on review of reporting and inputs provided by GoR, TAF and MEL Supplier. A comprehensive Impact Evaluation of VUP led by the MEL Supplier is expected in March 2026 and will provide further independent assessment of progress.

Overall, strong progress has been made despite significant challenges and changes in operating context which have continued to test the ambitious objectives and delivery timelines of the programme. This unprecedented backdrop included an outbreak of the deadly Marburg disease which constrained external engagements between Oct-Dec 2024, an escalation of the conflict in eDRC and in response UK and other development partner measures and global ODA cuts. Alongside significant operating shifts such as the new social registry targeting approach launched in July 2025 and the government of Rwanda’s SP sector reform planning – also referred to as ‘re-thinking social protection[4]’.
[4] The Rethinking Social Protection process began in early 2025 and is led by the Ministry of Finance and Ministry of Local Government (MINALOC). It is supporting reform aimed at improving impact of social protection.

Key achievements this year have included:
- Secured Major Financing and Strengthened Partnerships: Successfully established a new EPR Basket Fund modality and secured co-financing from KfW of up to £15million (€18 million), supporting development partner harmonisation, transition in UK funding and enhanced programme delivery.
- Enhanced Policy Alignment and Sector Governance: Approval of the new Social Protection Sector Strategic Plan (SP-SSP2) and strengthened alignment with the Sector Working Group through a new Procedural Manual, driving coordinated action for sector-wide reforms.
- Institutional Capacity Building and Knowledge Management: Established a national Para Social Workers (PSW) training framework and launched a community of practice, complemented by a portfolio of online training materials to ensure continuous professional development of the VUP frontline workforce.
- Inclusive Social Protection and System Integration: the Old Age Grant is now a mainstreamed national component with full integration into LODA systems and launch of the Disability Management Information System (DMIS) and provisional targeting of beneficiaries.
Major lessons and recommendations for the year ahead

These are captured throughout the following sections, but overarching lessons and recommendations include:
1. Accelerate sustainability planning: FCDO, in collaboration with all partners, to finalise an exit and sustainability plan for the programme, prioritising actions that consolidate and embed programme gains, strengthen systems, and ensure knowledge transfer [by March 2026],
2. Risk Management in Targeting Transition: LODA and MINALOC, with support of TAF, to proactively manage and monitor risk and implementation during the shift from community-based targeting to Social Registry Information System and urgently resolve systems issues causing payment delays and delivery disruptions [by December 2025]
3. Advance Evidence-Based Sector Redesign: TAF to continue strong support to MINALOC and LODA in VUP rethinking processes for poverty impact and equity-focused design choices [by March 2026]. LODA, with TAF support, to mitigate risks of design changes that could dilute equity or harm vulnerable groups and ensure carefully phased implementation in line with available resources and recent evidence including the VUP IE [by June 2026].
4. Evidence and Learning Continuity:
  1. Ensure final Monitoring Evaluation and Learning deliverables, including the Impact Evaluation, better reflect end user needs, are contextually relevant and actionable for Rwanda’s social protection priorities [OPM with FCDO by March 2026]
  2. Mitigate impact of early closure of the MEL component through sustained emphasis on learning and evidence generation through ongoing TAF activities [FCDO with TAF by March 2026]
5. Advocacy and engagement: FCDO with support of TAF to strengthen development partner coordination, particularly with the World Bank, in support of Government of Rwanda (GoR) decision-making on the future of social protection and in support of long-term sector resilience, focusing on areas like innovative financing, equity and evidence [Ongoing]

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The overall impact the EPR programme seeks to achieve is the eradication of extreme poverty and poverty levels reduced in Rwanda. To contribute towards this, the outcome of EPR is to build an effective and sustainable social protection system, which ensures basic income security and access to essential services, promotes sustainable graduation from poverty, and enhances resilience of vulnerable men, women and children.

The Theory of Change posits that this outcome can be delivered if poor and vulnerable people are effectively supported through the national social protection programme to meet their basic needs (Output 2), to better withstand shocks and crises (Output 3), and to establish sustainable livelihoods (Output 4). This does however require strengthened capacity within the social protection system to sustainably implement more effective programmes and deliver policy innovation and reform (Output 1), including through the support of technical assistance and FCDO policy engagement (output 5).

As per recommendation from the 2023/24 AR, the results framework was revised this year to enhance specificity, measurability and alignment with the new national sector strategic plan (SP-SSP2/NST2) its indicators, methodology and data sources. The comprehensive process kicked off in February 2025 and involved consultation with sector stakeholders and technical input and recommendations from MEL provider, TAF and FCDO M&E advisor. Its conclusion took longer than expected given changing delivery context, uncertainty on programme scope and need for alignment. The following changes to the logframe were discussed and approved by the Development Director in September 2025:

Log frame section	Details of change	Comment/Justification for the change
Impact	Extreme poverty eradicated and poverty levels reduced for VUP participants. / Changed to: 'Extreme poverty eradicated and poverty levels reduced'.	New and simplified indicators at impact level which ensure we are able to track impact on national poverty rate with readily available data and methodologies and more appropriate impact level indicator moved up from outcome level (food security). Removal of indicators for which there is not yet an agreed methodology in place (graduation) and cannot be compared due to changed methodologies (poverty gap)
Outcome	Updated indicators	Alignment and addition of indicators to better support outcome statement agreed in 2024. This includes new/updated indicators on coverage for vulnerable groups, adequacy of benefits, GoR financing. These better reflect SP system development measures and all of which EPR has focused on supporting since inception.
Output 1	Updated indicators	Minor revisions to language of output indicators to make more specific and clarification of methodology and a new indicator on training to better reflect contribution of EPRs capacity building efforts. MEIS focused output indicator moved up from output 3 as better aligned to institutional capacity building focus of output 1.
Output 2	Access by selected vulnerable groups to more effective and new core social security instruments enhanced / Changed to: Increased access by selected vulnerable groups to more effective and new core social protection instruments.	Minor change to output language and tightening of methodology on timeliness and a new indicator that provides insight on gender (not included in this review).
Output 3	Updated indicators	Simplification/clarification of indicators on shock response and ICF methodologies and new milestone on climate sensitive public works. Shift of MEIS indicator to output 1.
Output 4	Updated indicators	Simplification/clarification of some graduation indicators, re-focus of indicators to align with available data sources as GoR M&E around graduation has not been developed and removal of indicators that depend on client satisfaction surveys as not something that can be financed/is not regularly collected by GoR.
Output 5	Updated indicators	New indicators tracking FCDO sector engagement and contribution of M&E component for the sector.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

An assessment of revised outcome indicators is provided below and draws on recently available data from the EICV7 household survey. The upcoming Impact Evaluation will support more detailed understanding of progress and testing of intended pathways. While the programme remains largely on track to contribute positively to its higher impact objectives of poverty reduction with the national poverty rate falling from 39.8% in 2017 to 27.4% in 2024 and building the social protection system in Rwanda, some key assumptions are strained, especially in terms of reductions in domestic financing and changing GoR commitment. This is evidenced by a continued decline in share of domestic financing for social protection over the last few years, with more reliance on external financing. It is well understood that the outcome and impact will only be achieved if the overall financing, coverage and adequacy of social protection progressively and sustainably expands. However, there are financial constraints which may require GoR to prioritise & make trade-offs between these goals. FCDO will continue to engage with the government and other development partners to support progress on a sustainable financing strategy and effective prioritisation of impact driven reform to support this. The next EICV8 household survey for 26/27 will provide further clarity on trajectory of change, results are expected ahead of the Programme Completion Review (PCR).

Outcome	An effective and sustainable social protection system built, which ensures basic income security and access to essential services, promotes sustainable graduation from poverty, and enhances resilience of vulnerable, men, women and children
Indicator(s)	Outcome Milestone (s) for this review (Up to end of September 2025)	Progress towards outcome milestones (up to end of June 2025)
Outcome indicator 1: / Percentage (%) of key vulnerable groups benefiting from safety nets or lifecycle grants / Disaggregation by: / (a) Children living in poverty / (b) Poor older people / (c) Poor people with disabilities / (d) All members of poor households (disaggregated by sex of HHH) / This is calculated as the number of HH members covered by VUP as a percentage of the poor population which is 27.4% of the total population. The percentage of the population in poverty is taken from EICV7 published in July 2025 and has declined from EICV5.	15%	36% of poor vulnerable groups benefiting from VUP safety net: (1,313,184/3,629,512) / In the tables which follow DS= Direct Support, CPW=Classic Public Works, EPW-LB= Labour based expanded public works, EPW-HB= Home Based Early Childhood Development Expanded Public Works, OAG=Old Age Grant, F=female and M=Male. Disaggregation by age will be undertaken at next review. / Analysis of gender for each component / Total by scheme Female Male Total / DS 81,518 60,745 142,263 / CPW 280,486 275,312 555,798 / EPW-LB 95,991 78,152 174,143 / EPW-HB 93,991 81,157 175,148 / OAG 69,420 20,131 89,551 / Total 621,406 515,497 1,136,903 / Analysis of disability for each component / Total / No disability Minor Disability Major Disability / DS 87.7% 2.7% 9.7% / CPW 99.1% 0.5% 0.4% / EPW - LB 97.3% 1.2% 1.5% / EPW - HB 98.8% 0.7% 0.5% / OAG 90.7% 3.4% 5.8% / Analysis by disability for all components / DISABILITY TOTAL TOTAL / F M TOTAL / % WITH SEVERE DISABILITY 2.4% 2.1% 2.3% / % WITH MINOR DISABILITY 1.4% 1.0% 1.2% / % WITH NO DISABILITY 96.2% 96.8% 96.5%
Outcome Indicator 2: Average VUP benefit value as a % of the poverty line / Disaggregate by VUP component: / a) Old Age Grant / b) Disability Grant / c) Expanded Public Works / d) Classic Public Works / e) Direct Support / f) Nutrition Sensitive Direct Support	OAG: 18%	Average payment as % of the poverty line 24.9% Average payment per HH as % of the poverty line 12.2%
	DG: N/A	N/A
	ePW: 30%	Average payment as % of the poverty line 33% Average payment per HH as % of the poverty line 7.8%
	ePWs-HBECD: 32%	Average payment as % of the poverty line 35.2% Average payment per HH as % of the poverty line 7.5%
	cPW: 23%	Average payment as % of the poverty line 23.5% Average payment per HH as % of the poverty line 4.2%
	DS-Disability: 27%	Average payment as % of the poverty line 27.4% Average payment per HH as % of the poverty line 5.0%
	DS-non disability: 24%	Average payment as % of the poverty line 24% Average payment per HH as % of the poverty line 8.6%
	NSDS: 13%	Average payment as % of the poverty line 13.2% Average payment per HH as % of the poverty line 13.2%
Outcome Indicator 3: Total expenditure on social protection (excluding health) as % of GDP	0.50%	0.63%[5] where the GDP figure is reported as RWF 21.5 trillion and the total expenditure figure is reported as RWF 134.8 billion (from the Backward-Looking Joint Sector Review for 2024/25)
[5] Note that the calculation is based on the SP Sector budget provided by MINECOFIN

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The EPR programme continues to play a critical role in supporting the GoR’s efforts to implement its Social Protection Sector Strategic Plan (SP-SSP2) and NST2 priorities to eradicate poverty, malnutrition and promote socio-economic transformation. This approach continues to be supported by robust global evidence on the impacts of cash transfers, as well as national evidence on the impacts of VUP itself. It is credited by GoR and the Sector for its enabling role in the design and introduction of the range of policy innovations this year whilst maintaining and strengthening existing service delivery. Additional co-financing and establishment of the EPR Basket Fund—despite resource constraints and diplomatic challenges—underscores the value placed on EPR by the sector.

As a flagship programme within the British High Commission Kigali portfolio, EPR contributes directly to Country Business Plan goals, particularly foundations for growth, through its cross-cutting poverty reduction mandate. It aligns with the UK’s commitment to deep partnerships that advance both Rwandan and UK priorities. VUP is nationally owned, enjoys strong buy-in at all levels of government, and serves as a foundation for social cohesion. The transition to a low-ODA, expertise-driven partnership further aligns to the effectiveness of EPR’s existing innovative approach of embedded technical assistance and UK sectoral leadership in policy development and knowledge transfer.
Based on these merits, the EPR programme should continue.

We will maintain effort in the coming review period to i) encourage continued prioritisation of social protection by other partners (as per BHCK engagement plan) and ii) explore avenues within FCDO to embed a strong poverty focus and build complementarity with workstreams on climate finance and skills in particular.

## C. DETAILED OUTPUT SCORING

Output Title	Sustainable institutional capacity to deliver effective social protection enhanced
Output number:		1.1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Capacity Strengthening Plan developed and implemented according to Plan agreed timetable.	Implementation targets as per management response to institutional reform plan.	A: As per the plan, the target of setting up the Training Management Team (TMT) in LODA was met. Further achievements include i) the launch of / the Social Protection Community of Practice in January 2025 which was scaled nationally among PSWs following a methodology approved by LODA. ii) Development of distance learning to support Para Social Workers (PSWs) and Local Government, across core VUP components, and is available on the MINALOC e-learning platform.
1.2 The SWG is an effective forum for coordination, planning and mutual accountability in the social protection sector.	Forward & Backward Looking JSRs held. Leadership Committee meetings held x 2. Subcommittee meetings held x 3	A+: All SWG meetings held during FY 24/25 as required as well as additional convenings which have strengthened sector strategy and planning objectives including: (i) the high level SP Conference in October 2024 and (ii) an additional 4 sub-committee meetings and governance reform in line with SP-SSP. / A new manual was drafted for the SWG and leadership committee and is now being used to manage the SWG.
1.3. Annual training on VUP policies and standard operating procedures provided to sub-national staff	10 trainings completed (of which Training of Trainers) / 10,000 people reached	A+: A total of 20,885 people were trained in the period between July 2024 to September 2025 in over 30 training events. / This was made possible through collaborative efforts between the TA Facility funded workshops and training which hosted at least 1,072 people.
1.4 Monthly reports are produced from the MEIS for each VUP component (stored in the monthly archive) and are used to manage VUP.	- 80% of reports archived and utilisation within LODA-EPR reporting / - 4 LODA quarterly reports produced / - 4 FCDO Narrative quarterly reports produced	A: 100% of the reports were archived. The key reports which are used for decision making are (i) progress reports and (ii) payroll reports / 4 FCDO quarterly narrative quarterly reports were produced and discussed with FCDO, with reviews integrated in final document before sign off.

Output 1 focuses on strengthening institutional capacity to support the effective implementation of the Social Protection Sector Strategic Plan (2024-2029) (SP-SSP2). Progress remains strong, with two of four milestones exceeded. This year emphasized implementing the Training Framework by establishing the Training Management Team (TMT), rolling out training sessions, and supporting the reorganisation of the Sector Working Group (SWG) in line with the new SP-SSP2. During EPR’s log frame refinement, minor amendments were introduced to simplify and improve reporting on capacity-building activities.
Indicator 1.1 and 1.3: This year marked the institutionalization of the TMT in LODA. The TMT is designed to sustainably manage the design, implementation, and monitoring of training after EPR support concludes. The team received dedicated training during the year. Additionally, LODA delivered training to over 20,000 local government staff and volunteers, alongside a comprehensive three-month program for para-social workers. The new CoP is essential to guide PSWs in their support and coaching for community members
Indicator 1.2: Significant progress has been made in strengthening the SWG. Operational guidelines for the SWG and the Leadership Committee were prepared and approved by the Leadership Committee in January 2025. Following the approval of the SP-SSP2 in January 2025, subcommittees were restructured and leadership roles reviewed. A SP Retreat, financed by EPR, was held in March 2025 to present agreed targets and introduce the subcommittee structure aligned with the SP-SSP2. This Retreat is important because it is the primary meeting when Government and its non-governmental partners have an opportunity to discuss strategic policy issues. The new subcommittees— aligned with the three strategic objectives of the SP-SSP2: Prevent, Promote, Protect—reflect the latest sector framework and include cross-government stakeholders and Development Partners. During the retreat, subcommittees discussed how to organize collaboration across government, supported by development partners, to achieve SP-SSP2 priorities and targets. The year saw frequent subcommittee meetings, driven by a strategic focus on managing priority interventions, supported by the TA Facility’s assistance to the SWG Secretariat.
The TAF also organised and funded the Forward-Looking Joint Sector Review (FLJSR) on 27 June 2025. The meeting was well-attended and included active participation from all stakeholders. Targets for FY2025/26 were presented in the General Forum and a discussion on financing was held, in addition to MINECOFIN guidelines for the FLJSR, contributing to strengthened joint planning.
Indicator 1.4: All FCDO reports were produced as expected however LODA’s quarterly reports are produced for internal purposes and cannot be included in this assessment. It is also difficult to assess their utilisation. Milestone will be amended for next annual review to reflect readily available data. LODA mainly relies on MEIS for reporting on VUP schemes and the payroll processing but there is no evidence on any other form of archiving the reports.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were minor revisions to this output from “Capacity strengthening plan developed and implemented” to “Capacity strengthening Plan developed and implemented according to agreed timetable”. Relatedly, minor revisions to output indicators were made to make them more specific and clarify the methodology.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The recommendations from the last AR related to this output have been implemented, including greater use of technology with the establishment of an e-learning website and the launch of the Para Social Workers (PSWs) Community of Practice (CoP) in January 2025 following a period of one year allocated to the development of associated guidance and training materials.

Recommendations:

- FCDO with support from TAF to engage with MINALOC and LODA on EPR ‘sustainability plan’ and agree clear roadmap for capacity/organisational development priorities and knowledge transfer, with targeted TAF support to deliver on this before programme closure. [FCDO/TAF with MINALOC and LODA by June 2026]. This could consider:
  - formalising an annual training calendar and how to integrate best practice principles into all future capacity-building initiatives. There is a need to adopt a competency-based approach for PSWs and local government staff, supported by e-learning and blended learning models.
  - formalising a structured knowledge-sharing strategy that links the CoP with the MINALOC e-learning platform. Continuous engagement should also track PSWs’ performance, assess how effectively they are transferring skills to VUP beneficiaries, and document the outcomes of these skill transfers.
  - Roadmap for resourcing SWG Secretariat support from 2027.
Output Title	Increased access by selected vulnerable groups to more effective and new core social protection instruments.
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review
2.1 Total number of direct beneficiaries of the VUP’s lifecycle and safety net schemes. / disaggregated by a) scheme (OAG, DG, DS (both types), ePW and cPW); b) sex of direct beneficiary and c) Disability status.	1.3 million	A:The total number of people benefitting from VUP safety nets and categorical grants was a combined 1.3 million broken down as follows per different schemes: NSDS, DS, eDS, LB ePW, HB ePW and the OAG. / Scheme Female Male Total / NSDS 154,689 0 154,689 / DS 81,518 60,745 142,263 / CPW 280,486 275,312 555,798 / ePW LB 95,991 78,152 174,143 / ePW HB 93,991 81,157 175,148 / OAG 69,420 20,131 89,551 / Total 776, 095 515,497 1,291,689 / Referring to the table above on the household members across different schemes, analysis of LODA’s MEIS indicates that excluding NSDS, 55% of household members are female and 45% are male. / Analysis by disability showed that 96.5% of VUP household members in DS 87%, eDS *no HH without a PWD so 100% disability coverage, LB ePW 97%, HB ePW 87% and the OAG are not recorded as having a disability, 2.3% have a severe disability and 1.2% have a minor disability
2.2 Percentage of VUP payments made on time to participants	90% of payments made on time	A: According to LODA’s internal monitoring system for the year ended June 2025, the following percentage payments on the following schemes: / DS and OAG 91.1% / ePW 97% / cPW 91%

Briefly describe the output’s activities and provide supporting narrative for the score.
The focus of output 2 is to ensure that poor and vulnerable households benefit from new, more effective social protection interventions. It also aims to increase the number of households and individuals receiving assistance and ensure that beneficiaries receive timely payments. Overall, this output was met according to milestones, however delays have continued during this period affecting the roll-out of the disability grant. The timeliness of payment for components not tracked by LODA such as NSDS, were also known to experience significant delays.

Indicator 2.1: Disability Grant (DG) progress resumed this year, following postponement in the previous year to allow LODA to concentrate on the Old Age Grant. During this year, work to prepare the Disability Management Information System and integration with the social registry was completed – with TA financing the completion of enumeration in December 2024 and extensive data cleaning. The Disability Design Document was updated in September 2025, although this is pending approval. It is expected that the pilot roll out of Rwanda’s first Disability Grant will occur in FY 26/27 and is expected to benefit 62,317 poor persons with disabilities under category 1 (most severe disability), which represents 38% of poor people with disabilities.

The LODA MEIS continues to produce detailed analysis of enrolled and paid beneficiaries with analysis by component, gender and disability for household heads and household members. The disability data is from NCPD based on the current medical approach coupled with a “community assessment” of certain severe disability types where HHs have not been classified by NCPD. This will be updated during FY2025/26 when the DMIS is providing data to Social Registry Information System (SRIS) and MEIS.

Old Age Grant (OAG): Despite being launched only last year, the OAG has achieved national coverage and continues to enjoy strong political support, largely due to its simple design, which allows for relatively higher benefit levels. Following last year’s large-scale rollout, this year marked the first use of the Social Registry for targeting. The first SRIS-based payments were made in August–September 2025 to eligible households, after the adoption of revised targeting guidelines proposed by the TAF. TAF also supported the integration of SRIS with existing systems, including the Monitoring and Evaluation Information System (MEIS), to enhance data flow and improve targeting accuracy. Following OAG rollout, a process evaluation was conducted in October 2024 and OAG is now a mainstream component of VUP.

Indicator 2.2: The milestone of 90% of payments made on time was exceeded across VUP components tracked by LODA, which covers all components other than NSDS, which represents 12% of payments. According to LODA reporting during this period NSDS payments were delayed by two quarters due to SRIS integration delays

The transition from community-based targeting to the social registry has caused some delays in payments in the first quarter (July-September 2025) of FY2025/26. There have been functionality changes needed in MEIS to accommodate the SRIS system operations, these have been implemented by the TA Facility’s IT Developer. Payments were expected to improve with back logs cleared in the next quarter, backdated to the start of the financial year. There remain some data challenges in SRIS, it is expected that these will be resolved in the first half year because new targeting will be needed for KfW recipients to be added in January 2026.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
During the log frame review, this output and indicators were amended for simplification of language and combining multiple into a simpler overall total recipient indicators. The Disability Grant once rolled-out in FY2026/27 will be tracked here. Scope of timeliness data will also be reflected in future milestones.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead. There has been progress on recommendations from last year: the SP-SSP was approved with MINALOC and LODA committed to tracking coverage through an established monitoring system, roll out of the social registry concluded with continued engagement on risk management and effective systems integration (although still relevant). Evidence-based influencing was strengthened through the MEL team’s mid-term review, which informed policy dialogue with MINALOC, LODA, FCDO, Sida, and other development partners.
Recommendations for the year ahead:
- The adoption of the Social Registry for targeting in its first year has slowed down the targeting process and delayed the payments in the first quarter (July-September 2025). The transfer of data between SRIS and MEIS should be harmonised as a matter of urgency for accurate targeting and efficiency in delivery [MINALOC and LODA by January 2026].
- TAF to support LODA to continue necessary preparations for the piloting of the Disability Grant from FY 26/27, ensuring this is accompanied by effective M&E framework to support learning and improvements [LODA with TAF by June 2026]. FCDO to ensure EPR Basket budget availability for Disability Grant pilot [FCDO with LODA by Jan 2026]
- TAF to support LODA to explore options of a real-time payment tracking system through digital payment solutions to reduce delays. Set quarterly performance targets for at least 90% of payments made to recipients across all schemes.[TAF support to LODA by September 2026]
- Assess options to Institutionalise periodic independent system reviews (SRIS & MEIS) to ensure tools, guidelines, and engagement strategies remain responsive to evolving risks and programmatic priorities. This approach will strengthen long term evidence-based decision-making and reinforce accountability in social protection delivery. [MINALOC and LODA with TAF support by September 2026]

Output Title	Systems for shock-responsive social protection established
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Mechanisms in place to enable cash transfers to be leveraged for shock preparedness, response and recovery	i) Rapid assessment tool for who is collecting data agreed;	B: This is ongoing. The rapid assessment tool has been developed and is in use for SRCT household level piloting but is not yet agreed. Further harmonisation is required with MINEMA for joint use.
	ii) Payment functionality in MEIS is operational	A: Payment functionality in MEIS is operational and has been improved and tested since last year.
3.2 % of public works projects that are compliant with internationally recognised guidelines for climate smart public works	Updated guidelines for CSPW under development	B: The revision of climate smart cPW guidelines is under way with an intended completion date of February 2026. In the meantime, LODA continues to use the current version of the cPW guidelines which identifies climate projects by the project typology. LODA is now documenting the number of people protected from climatic shocks.
3.3 Number of people supported to better adapt to the effects of climate change as a result of ICF: Total direct clients (Number of individuals) of SRSP, also disaggregated by sex, disability, age, and geography	120,000 direct beneficiaries (CPW)	B: 99,407 households in the poorest and most climate vulnerable districts benefitted from classic Public Works during FY2024/25. These households contained a total of 557,798 household members. / Heads of HHs Total / FHH MHH / 42,731 56,676 99,407 / HHs members: Total / F M / 280,486 275,312 555,798

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 contributes to the efforts of the GoR to strengthen the shock-responsiveness of the SP system and of VUP. It has moderately not met expectations this year due to delays in completion of climate public works guidelines which require interministerial engagement and design and less households benefiting from cPW than expected due to funding constraints.
Indicator 3.1. SRSP redesign work continued following the pilot and process evaluation, which revealed a number of design challenges, particularly related to beneficiary identification, improved grievance mechanisms, the need to clearly articulate its purpose versus emergency relief and implement timely payments. Further testing and enhancement of the SRSP payment system took place following learning. The development of the rapid assessment tool was completed in July 2025 and is being used for piloting collection of HH levels shocks in the period July to September 2025. This further built on work done by WFP and the TA Facility in 2023 and subsequently by GIZ and UNICEF with the support of the TA Facility. Currently, LODA is in discussions with MINEMA on how to better link the assessment tools used by each institution with the intention of a joint tool. In addition, LODA has begun documenting the number of people protected from climatic shocks, which will inform future responses. LODA approved a concept note describing the approach for shock-response, preparedness and household-level shocks. During this period there was also piloting of household (HH)level shocks in two districts-Gakenke and Karongi districts with 13 HHs benefitting from a new shock responsive cash transfer.

Indicator 3.2: Revision of climate smart public works began in the period and is expected to be completed in February 2026. These will include an M&E framework which aligns with indicators from international climate funding organisations and is a vital step in future climate finance access. The process has taken longer due to the need to also develop the institutional and policy framework for collaboration across sectors, and the integration with the NDCs and Rwanda’s broader climate strategy that developing meaningful guidelines will require.  LODA is not in a position to develop or implement cPW programming without this policy and institutional integration.
Indicator 3.3: During this period there was no major climate related shocks and therefore no large scale rollout of the Shock-Response Cash Transfer. As per agreed disbursement linked indicators, funds were re-allocated to strengthening preparedness prioritising the most poor and disaster prone districts who received support through climate public works. There was also piloting of household (HH)level shocks in two districts-Gakenke and Karongi districts with 13 HHs benefitting from a new shock responsive cash transfer.

Describe any changes to this output during the past year, and any planned changes as a result of this review. There were revisions to output indicators. This was mainly for simplification/clarification of indicators on shock response and ICF methodologies and new milestone on climate sensitive public works. There was also shift of MEIS indicator to output 1.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead. Implementation of some recommendations are ongoing, including the agreement and piloting of climate responsive public works guidelines. The Global Shield Against Climate Risks[6] process this year has supported dedicated shock responsive social protection discussion and gap analysis and remains an important initiative to enhance coordination with the Climate and Disaster Risk Finance and Insurance instruments and future access to climate finance. The guidelines for climate smart public works are being revised to make them more ‘climate smart’ and also include an M&E framework. Given lack of piloting opportunity, LODA should continue preparations to support operationalisation of shock-responsive cash transfer in line with climate related risk should continue.
[6] A joint initiative launched by COP27 by the V20 and G7 to promote a demand-driven, country-led approach to scaling up financial protection against climate risks and shocks.

Recommendations:
- FCDO as SWG co-chair should develop and implement a proactive engagement strategy that fosters collaboration between government agencies, development partners, and community actors on climate sensitive social protection instruments (SR-CT and cPW), leveraging existing FCDO footprint/resources such as the Green Climate Fund and Global Shield where possible. Position these reforms within a broader narrative of resilience and inclusivity, ensuring that communication channels and advocacy efforts amplify ownership and sustainability. [FCDO by September 2026]
- Fast-track the revision and adoption of climate-smart implementation guidelines that are co-designed between MINALOC, LODA and the relevant sector agencies working on climate, environment and environmental financing [LODA, with TAF support by June 2026], embedding robust monitoring and evaluation indicators consistent with international climate finance standards. Complement this with a structured capacity-building program for local implementers, focusing on climate resilience practices and adaptive delivery mechanisms informed by MEIS insights.
Output Title		Access and linkages to improved livelihood support services enhanced
Output number:			4		Output Score:		A
Impact weighting (%):			20%		Weighting revised since last AR?		No
	Indicator(s)			Milestone(s) for this review		Progress
	4.1 Targeted graduation clients receiving all elements of the graduation package to which they are entitled according to the Graduation Guidelines i) number and ii) percentage			40,000 (per SP-SSP2)		A+: 195,110 (67%) received a full package (multiple interventions across all pillars). 96,336 (33%) received a partial graduation package based on graduation pillars. The 1st Cohort assessment carried out by the Graduation Secretariat reported that of 315,327 graduation HHs, 291,446 participants had complete data with 62.4% graduating out of poverty.
	4.2 % of VUP livelihood support clients who think support is relevant, timely, and adequate			Cohort Assessment Report completed by MINALOC		A: The “Cohort Assessment Report” was completed and awaits final approval.
	4.3 Capacities developed for effective implementation of personalised graduation support			Training framework implemented / - Priority Training designed and delivered / - 100% PSWs in post who have been trained		A: As per the Training Framework i) priority training has been designed and delivered (see 1.3) and ii) 100% PSWs in post in January 2025 have been trained. / PSW Training Programme: 17,107 participants trained, (9,668 female and 7,439 male), including 11 District staff, 410 Sector staff, 2,103 Cell staff, and 14,583 Para Social Workers (PSWs) and 94 of whom were trained as master trainers.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 seeks to enhance the access of cash transfer clients to a complementary package of support that is intended to support graduation from poverty and establish sustainable livelihoods. It met expectations but challenges remain especially in understanding client satisfaction of support received and the financing, coordination and sequencing of the ‘full package’ as per the of the National Strategy for Sustainable Graduation (NSSG).

Indicator 4.1: The NSSG requires multiple interventions to be layered and carefully sequenced to enable households to build resilience and graduate out of poverty. Targets were significantly exceeded, among 181,961 graduated households; 136,848 graduation participants received a full package while 45,113 received a partial graduation package. It is understood that most of this ‘package’ is provided through different external sources and implies likely variation in quality of provision. Additionally, graduation participants have no same baseline and needs at enrolment phase, and if their needs are met on required pillars they graduate.

Indicator 4.2: The Graduation Secretariat at MINALOC conducted an assessment of the first graduation cohort. However, it is understood that this did not directly assess client satisfaction and the extent to which clients think support is relevant, timely, and adequate. The assessment resulted in a number of recommendations to enhance the effectiveness, efficiency, and sustainability of the NSSG:

To strengthen intervention delivery, programmes should provide comprehensive graduation packages following the layering and sequencing guidelines in the NSSG, ensure productive assets are relevant and market-aligned, and implement Personal Graduation Plans tailored to household aspirations. Continuous quality coaching and mentoring throughout the two-year journey is essential to support participants effectively. Additionally, expanding financial literacy and access to services through SACCOs and MFIs, alongside promoting Village Savings and Loan Associations (VSLAs), will enhance household financial stability and resilience.

Improving employment and livelihood opportunities requires advocating for large-scale rural projects that create sustainable jobs and fostering partnerships to diversify income sources. Monitoring and accountability should be enhanced through a digital Poverty Graduation Management Information System (PGMIS), graduation contracts, and regular progress reviews. Stronger coordination via local government committees and JADF, community validation during targeting, and harmonized financial calendars will reduce errors and improve efficiency. Finally, integrating shock-responsive mechanisms and planning for Cohort II by retargeting non-graduated households and applying lessons learned will ensure long-term impact and sustainability.

Indicator 4.3: Para Social Workers have a key role in supporting clients on their graduation journey through personalised graduation support and their training and retention remain crucial. In recognition of this, MINALOC and LODA, working with Local Government undertook a review of the effectiveness of the PSW programme. It was determined that 79% of existing PSWs no longer met the required standards leading to a restructuring process that involved selecting new PSWs by local communities. These selections were done during quarter two of FY 2024/2025, in all 30 districts. Some 11,652 new para-social workers were selected and 3,067 were retained. The training programme was rolled out to all in Post and priority training programme on the NSSG was developed and delivered during quarter three of FY2024/25.

Describe any changes to this output during the past year, and any planned changes as a result of this review. There was a simplification/clarification of some graduation indicators, re-focus of indicators to align with available data sources as GoR M&E around graduation has not been developed and removal of indicators that depend on client satisfaction surveys as not something that can be financed/is not regularly collected by GoR. Once the graduation MIS is developed the indicator will be aligned but for now the focus is on graduation capacity.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead. Most recommendations have been taken forward but require ongoing attention. For example, work on a robust M&E framework and agreement on graduation metrics is still pending, with proposals under discussion and further development planned this FY through the new graduation and livelihoods SWG sub committee co-chair Village Enterprise. BRAC Graduation Secretariat is operational and initial coordination steps, including a high-level meeting with CSO partners, have been taken, but practical decentralised coordination on delivery of comprehensive support remains a gap. Rollout of graduation guidelines continues to be a priority but implementation challenges such as capacity constraints, funding and ambitious district targets remain. In addition, the effectiveness of the current asset transfer component has been evaluated during this period. The MEL Supplier has supported this assessment through international evidence synthesis which has found that substituting it with substantial cash transfers could be a more effective strategy. This approach offers simplified administration, reduced operational costs, enhanced beneficiary empowerment for sustainable graduation, and a positive multiplier effect on local economies. Government are considering this as part of its ‘re-thinking social protection’ approach.
Recommendations:
- Ongoing strengthening of M&E systems to monitor the effectiveness of graduation roll-out should continue to be prioritised, including post-graduation follow-up to assess resilience and income stability and direct client feedback.[MINALOC, LODA with support of the TAF as required, by June 2026] FCDO to further consider lesson learning within future portfolio approach [FCDO by June 2026]
- As per the Capacity Development Plan, institutionalisation of the Community of Practice and continuous capacity development program for PSWs and local government staff should continue, leveraging e-learning platforms and refresher trainings through the ToTs model [MINALOC, LODA with support of the TAF as required, by June 2026]

Output Title	FCDO technical assistance and other engagement effectively supports implementation of EPR and SP-SSP
Output number:		5	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Percentage of SP reporting is produced with a high degree of accuracy and timeliness by GoR staff	Data quality assessment of MEIS for FY2023/24 per OAG's report is acceptable / LODA produces 100% of planning, finance and other reports on time with adequate explanation of variances	B: OAG 2023/24 report – unqualified conclusion on compliance, unqualified conclusion on value for money in utilisation of public funds. No assessment of the MEIS was undertaken but TAF monitors in real time. / 85% LODA reporting on time, although there was flexibility on FCDO side
5.2 Social protection policy engagement strategy developed and implemented by FCDO in collaboration with other partners	i) # quarterly meetings between PS and DDD; / ii) # meetings between DG LODA and SRO; / iii) 3 SWG meetings held per year / iv) 2 Leadership Committee meetings per year / v) 2x meetings between PS and the FCDO BHC and/or Development Director	A: FCDO developed an engagement strategy and all expected meetings have taken place. TA facilitation has also effectively supported required convening.
5.3 Generation of robust evidence on the impact of the VUP, including on poverty reduction.	at least 2 evidence or research products finalised	A+:The TA Facility and MEL Supplier have supported x4 LODA and MINALOC requested research and evidence including: i) Rapid assessment of Graduation through testimonies from Graduation Participants (not shared with FCDO) ii) analysis and modelling of EICV7 iii) research on large cash transfers for graduation research iv) research on links between fertility and NSDS.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output mainly focuses on the contribution of evidence, strengthening of the TA Facility work and FCDO policy influencing and engagement to enable EPR delivery. There has been good progress with a step up in FCDO high level sector engagement and relevant evidence generated to support policy development and decision making, including significant research and analysis to inform the rethinking social protection process. Sector stakeholders continue to highly value the strong technical contribution of the TAF, although more could be done to ensure sustainable knowledge transfer to GoR.

Indicator 5.1: The MEIS remains a critical tool for planning, budget execution, monitoring and implementation of the SP programme by LODA and Districts. TA support continues to maintain and improve functionality and linkages including with the new social registry. However, independent assessment and data quality assurance remains a key gap and has not been taken forward as expected by the OAG. According to the last OAG 2023/24 report provided an unqualified conclusion on compliance, unqualified conclusion on realization of value for money in utilisation of public funds – this is an improvement from 22/23.

LODA reports to FCDO on the EPR have been received but a number of accommodations have been made to support extended deadlines. A slight drop in timeliness was experienced during a period of LODA staffing changes. The reports met FCDO reporting requirements but there is scope for ongoing improvements in presentation of wider progress beyond EPR. This will be revisited under the new EPR Basket arrangement.

Indicator 5.2: As outlined in output 1, it has been an active period of sector engagement with BHCK playing an important role as Co-Chair of the SWG and lead Development Partner and with strong TAF facilitation through briefing and organisation. This has taken place within the context of change for the wider UK-Rwanda bilateral relationship resulting from dual announcements of UK move to 0.3% of GDP for ODA and UK measures pausing our wider financial aid portfolio, and changes to both high level positions in MINALOC and BHCK. A dedicated engagement strategy has helped to ensure constructive and more regular engagement at all levels throughout this period, including a number of Ministerial meetings. Strong collaboration with DPs has also enabled shared advocacy including during the Sector retreat in March and in relation to emergent risks and changing priorities. This will continue.

Indicator 5.3: There were different MEL products that were generated during this reporting period; the Disbursement Linked Indicators (DLI) verification process was completed in November 2025 with a learning annex to capture key insights through out the 3 years of the DLIs period. In addition, two research pieces on Nutritional Sensitive Direct Support (NSDs) and large cash transfers, were finalized in September 2025. The Social Protection re-thinking work supported by TAF and some reflections on challenges with NSDS research are being discussed and there will be further follow up and engagement with MINALOC and LODA.

Describe any changes to this output during the past year, and any planned changes as a result of this review. There are new indicators supported to improve tracking of FCDO sector engagement and contribution of M&E component for the sector. It is suggested that output indicator milestones for 1.4 and 5.1 are looked at again to avoid any overlap and dual reporting. It is also recommended that remaining milestones ensure adequate reflection of influencing effectiveness, rather than tracking of engagement.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead. Recommendations from previous AR remain relevant. Discussions between LODA, FCDO and TAF resulted in the previously recommended GEDSI post in TA Facility to be removed and the funds re allocated. The remains a need therefore to continue to mainstream and build capacity on GEDSI.

Recommendations:
- FCDO should further develop and implement a proactive engagement strategy that fosters collaboration between relevant Government agencies, Development Partners, and community actors ensuring that communication channels and advocacy efforts emphasize local ownership and sustainability. [FCDO, with TAF support, by March 2026]
- TAF to continue strong support to MINALOC and LODA in VUP rethinking processes for poverty impact and equity-focused design choices [TAF with MINALOC by March 2026]. LODA, with TAF support, to mitigate risks of design changes that could dilute equity or harm vulnerable groups and ensure carefully phased implementation in line with available resources and recent evidence including the VUP IE [TAF with LODA by June 2026].

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

The EPR Programme continues to deliver strong VfM, with 90% of disbursed funds reaching beneficiaries. Technical Assistance costs remain within agreed rates, and administrative costs are minimised through streamlined financial flows. During this year, there were some challenges related to timely disbursement to beneficiaries resulting from delayed SRIS roll out and integration into the existing MEIS. While an interim community-based targeting was devised, this ended up delaying transfers especially to NSDs beneficiaries thus affecting nutrition outcomes. The programme delivery remains heavily reliant on the Technical Assistance Facility (TAF), raising sustainability challenges for LODA’s long term delivering of SP. There is a need to strengthen capacity in the institution so that they are still able to deliver on the programme even when the TAF ends.

In FY 2024/25, £14million was disbursed to the Government of Rwanda (GoR) to support the Social Protection (SP) transfers directly. This expenditure was allocated as follows: i) 10m transfer to districts for VUP safety net components and graduation initiatives , (ii) £1.7million was transferred to graduation coordination initiatives and (iii) £2.4million was allocated to Old Age Grant and Shock Responsive Social Protection.

An additional £1.3 million was spent on the Technical Assistance (TA) Facility, while £355,082.89 was allocated to Monitoring, Evaluation, and Learning (MEL).

In addition to the above, the TA Facility has supported significant research and analysis to inform the rethinking of the social protection sector. This required thorough analysis of ECIV7 data and historic programme data.

VfM performance compared to the original VfM proposition in the business case
Economy: The programme has maintained economy across all components. Technical Assistance (TA) consultants delivered high-quality outputs in line with performance expectations while adhering to the pre-agreed rates stipulated in the Cowater International contract. Days worked by TA consultants remained within the approved forecasts, with allocations jointly agreed upon by FCDO and Cowater to reflect GoR priorities.

The NBSFA amount went to beneficiaries with less than 1% of the disbursed amount being spent on administration for the SPIU embedded in LODA. The tables below show the number of recipients supported and average transfer received:

Individual Grants
Social Protection Instrument	Recipients (Total)	Recipients (FCDO)	Average transfer in 24/25 (RwF)
Nutrition Sensitive Direct Support (NSDS)	125,505	80,323	73,790
Old Age Grant	86,653	41,593	99,493

Support to Households
Social Protection Instrument	Households (Total)	Recipients (FCDO)	Average transfer in 24/25 (RwF)
Labour-based Expanded Public Works (ePWs)	41,311	9,088	188,175
Direct Support Coverage Expansion (DS-PwDs)	11,919	3,814	154,872
Climate-Sensitive Public Works (cPWs)	99,407	25,846	143,150

Support to graduation for skills development and provision of productive assets
Social Protection Instrument	Recipients (Total)	Recipients (FCDO)	Average transfer in 24/25 (RwF)
Skills Development	7,932	2,038	443,508
Productive Asset Transfer	8,084	1,982	168,954

Efficiency: The consolidation of FCDO and SIDA funding through a single MOU streamlined financial flows, and has continued to significantly reduce transaction costs and support timely disbursements to LODA in 4 timely tranches July 2024, November 2024, January 2025 and July 2025. Continued concerns remain on the graduation component particularly the efficiency of productive asset transfer, which accounted for 10% of EPR financing. Government are considering this as part of its ‘re-thinking social protection’ approach.

Effectiveness: The programme remains focused on implementing the most impactful, evidence-based interventions—such as DS, NSDS, OAG, cPWs, and graduation components—that directly reduce poverty among the most vulnerable. Beneficiaries from recent field visits reaffirmed the critical role these benefits play in stabilizing consumption and meeting daily needs. However, rising inflation and operational costs continue to challenge the adequacy of transfer values. In response, Technical Assistance has supported the development of a rethinking strategy for social protection, which will address transfer value adjustments going forward.

Sector coordination and alignment with Development Partners on shared priorities has been strengthened through BHCK’s leadership of the Social Protection Sector Working Group and DP Coordination group. This collaboration has attracted additional funding from KfW to the EPR programme, creating a joint financing basket with FCDO, Sida, and KfW to advance common objectives. Effective collaboration with the World Bank is also underway to ensure strong alignment with respective investments until June 2027. A single multi-annual workplan for VUP will also ensure more effective Government planning and alignment of financing from January 2026.

Equity: The VUP programme design continues to be gender- and disability-sensitive, with a majority of EPR-supported households being female-headed (see table below). And 26% of funds paid under DS and expanded DS went towards supporting people with a disability or those caring for someone with a disability.

Social Protection Instruments	% female members
Labour based Expanded Public Works (ePWs)	72%
Direct Support Coverage Expansion (DS-PwDs)	60%
Climate-Sensitive Public Works (cPWs)	43%
Total	58%

Programme instruments are intentionally designed to target poor and extremely poor households, including people with disabilities, pregnant and breastfeeding mothers, children under two, and caregivers through ePWs. This approach also addresses women’s time poverty by reducing the burden of home and childcare responsibilities. However, Government concerns relating to NSDS and its perceived links to fertility increases have emerged this year. As part of the re-thinking social protection design, it is understood that this component will close. This will have significant equity implications and any transition to existing instruments, such as expanded public works, will need to be supported through rigorous safeguards before EPR funding can be utilised.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The programme’s overall risk rating remains Major, driven by its ambitious and innovative design, which seeks nationwide coverage and targets a large population of vulnerable population through government-led delivery mechanisms involving multiple stakeholders, including MINECOFIN, MINALOC, LODA, and district authorities. This complexity requires robust mitigation strategies to safeguard continuity and impact. Risks are monitored closely by FCDO and discussed formally and informally with all programme partners, informing quarterly updates to the risk register. The key risks and mitigations are provided below:

Strategy and Context: Combined UK ODA reductions and declines in domestic financing will hamper efforts for an inclusive and effective Social Protection System in Rwanda. To mitigate this, the Programme Team and TA Facility will continue monitoring allocations and engage MINALOC and MINECOFIN when funding drops below legal thresholds. In light of anticipated budget cuts for 2026/27, FCDO is stepping up engagement on sustainable financing with GoR and other Partners, including leveraging TAF and working closely with UNICEF and MINALOC to develop a Social Protection Financing Strategy aimed at securing sustainable financing. Mitigation of UK ODA reductions and avoidance of a ‘cliff edge’ from 26/27 have included leveraging of co-financing and establishment of a Basket Fund from January 2026 until June 2027 which will maintain funding levels of financial aid. In addition, EPR was protected from UK measures given its focus on supporting marginalised groups.

Policy and Programme delivery: Early closure of the MEL component by March 2026 due to FCDO funding constraints may not allow for all deliverables to be achieved and validated, potentially affecting programme learning, accountability, and future planning. To mitigate this, FCDO, OPM and LODA have initiated an engagement process, including validation workshops and review of preliminary findings, to ensure alignment and ownership. FCDO will continue advocating for evidence-based decision-making across the sector.

Policy and Programme delivery: The New Social Registry launched in the last quarter (July-September) of the review period and at the time of this AR, has not yet achieved full integration with existing LODA management information systems, creating potential delays in beneficiary targeting and eventual payment to recipients. To help mitigate, technical enhancements to the MEIS platform are underway to address programming issues and improve accuracy. Once fully operational, the Social Registry is expected to significantly strengthen targeting efficiency and incorporate a grievance redress mechanism to reinforce transparency and accountability.

Financial and Fiduciary: The risk is that there is delayed payment to beneficiaries due to the delay in roll out of the social registry information system which has slowed Government disbursements rather than FCDO funds being held in GoR accounts. To mitigate this risk, the TAF will actively manage fund flows and support LODA in resolving social registry system issues to ensure accuracy and timely disbursements. In parallel, the team collaborated with programmes such as SPARC and the World Bank to explore alternative digital payment solutions that accelerate transactions. Future FCDO disbursements will align with LODA account balances and 90% execution rates, supported by monthly budget execution tracking.

Update on Partnership Principles (delete this section if n/a) [1/2 page]

The delivery of the NBSFA component remains contingent on adherence to the UK Partnership Principles that guide the provision of UK aid. The Government of Rwanda’s commitment to the partnership principles was last assessed in December 2021, concluding that
“Overall, we assess that the Government of Rwanda remains committed to the underlying principles of our aid partnership sufficient to continue financial aid. Rwanda continues to demonstrate strong commitment to poverty reduction, economic and social rights, anti-corruption and sound public financial management. Commitment to civil and political rights and domestic accountability is limited and we remain particularly concerned about civil and political rights.”

In February 2025, in response to the situation in Eastern DRC, the UK took measures against Rwanda, including pausing “direct bilateral financial aid to the Government of Rwanda (GoR), excluding support to the poorest and most vulnerable.”

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]

Current level of fiduciary risk and direction of travel since last ASP	A Fiduciary Risk Assessment (FRA) was conducted in December 2022. The FRA and ASP are the main way in which BHCK monitors the Rwandan government’s commitment to improving public financial management and financial accountability and fighting corruption. The FRA made the following conclusion: / “The overall fiduciary risk for Rwanda’s government systems as of December 2022 is assessed to be ‘Moderate’ with no change in risk rating and a positive trajectory compared to the previous (2019) FRA assessment. The corruption risk is also assessed to be ‘Moderate’ with no change compared to the 2019 FRA assessment. Therefore, the trajectory of change is rated ‘no change’. The GoR’s overall commitment to improve PFM, strengthen financial accountability and tackle corruption is assessed as ‘credible’. The overall assessment of the level of residual risk is assessed to be ‘Minor’ for fiduciary risk and ‘Moderate’ for corruption risk”. / Relatedly, a FRA was conducted on the financial aid support to the social protection programme in Rwanda and it assessed the risk associated with the Programme as ‘moderate’. An overall ‘positive trajectory’ from previous 2016 and 2019 ‘moderate’/’major’ scores. / The reasons for the overall ‘moderate’ risk rating given to FCDO’s FA to SP are as follows: / Government systems, according to the National FRA, continue to undergo strengthening with improvements made in recent years including: a stronger and maturing basic PFM system; an enhanced and integrated IFMIS with real-time linkages with other government databases; investments into critical PFM skillsets and professionalisation; and overall resilience built-up through successive integrated PFM reforms that have been consistently enacted in the last two decades. The risk rating for social protection FA recognises this progress but also considers well-known and documented risks associated with such a complex programme and the implementation arrangements across all districts in Rwanda. / Because national PFM systems are rated as ‘moderate’ fiduciary risk and, because LODA, MINALOC and MINECOFIN apply these systems to all vertical programmes including SP, the risk to FCDO funds using these systems is also considered moderate. / The Government of Rwanda has significant capacity and experience in managing social protection programmes gained over several years and prioritises SP in its resource allocation decision making processes each year. The partnership approach between national and district governments is also commended. / The key risks identified in this and previous VUP assessments undertaken every few years since 2016 are well known to LODA, its TA and to the development partners and are set out in detail in assessment reports, capacity assessments and in risk mapping exercises. Because they are known and repeated periodically, they find their way into various initiatives including any capacity building, recruitment, systems improvement, training, and monitoring and reporting arrangements undertaken on the programme. Risks in areas such as targeting, data collection, management of cash, reporting, the reconciliation of various the systems and capacity at districts are well documented and taken into consideration on the programme, by LODA and its very effective TA. / Significant planned and ongoing reforms to IT system (through upgrades), introduction of a Social Registry, automation of SACCOs (to be completed by the end of 2023), roll out of mobile money technology and on-going efforts to keep MEIS, HMIS, IFMIS and other systems as aligned as possible, all bode well for SP. / The overall risk rating has been determined based on evidence gathered in meetings and interactions with key staff, advisors and stakeholders working on the programme, and takes into consideration the existence of safeguards already in place, including technical assistance. At present, the TA provided to LODA is crucial in maintaining risk at ‘moderate’. An Annual Statement of Progress (ASP) is overdue but will be completed by February 2026.
Specific assessment of corruption risk and direction of travel since last ASP	In the July 2024 MINALOC FRA the overall level of fiduciary risk associated with using MINALOC PFM systems is ‘major’, but with easily achievable mitigations put in place should easily drop to ‘moderate’. The risk of corruption in the public sector in Rwanda is considered ‘moderate’ and corruption indicators remain static over the past few years, although as noted above an ASP is overdue and will be completed in February 2026.
Is a full FRA update required?	An Annual Statement of Progress will be delivered at the end of February 2026. On the basis of this, and a review of the DCA with SIDA, we will determine whether a full FRA is required going forward given UK financial aid will cease at the end of FY25/26.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

The Exiting Poverty in Rwanda (EPR) Programme is overseen by a governance structure comprising the Senior Responsible Owner (SRO), Programme Responsible Owner (PRO), and Programme Officer, with strategic leadership provided by the Team Leader and Development Director. The team effectively managed the NBSFA disbursements to LODA, the Technical Assistance Facility (TAF) contract under Cowater International, and the Monitoring, Evaluation, and Learning (MEL) component under Oxford Policy Management Limited. The Delegated Cooperation Agreement (DCA) between Sida and FCDO, originally established in May 2022, has been effectively managed and was recently extended to June 2027 to align with the programme business case. Additionally, the negotiation of the EPR Basket took place during this reporting period, a new financing mechanism to enhance the delivery of EPR.

Going forward, under the new EPR Basket, FCDO will assume lead development partner role, retain programme delivery oversight. A new Joint Implementation Agreement sets out responsibilities and was agreed with LODA and KfW in December 2025.

Delivery performance
Reporting quality for both the narrative and financial reports submitted by LODA has significantly improved during the period, driven by capacity-building support from the Technical Assistance Facility. The narrative reports now integrate gender-disaggregated data, clearly articulate FCDO’s contribution, and include lessons learned, challenges, and proposed solutions. Regular monthly meetings between BHCK and LODA, complemented by formal feedback mechanisms, have strengthened both reporting and coordination. Enhanced programme management within LODA under the oversight of a division manager and, in some cases, the Director General has further improved communication, coordination and accountability. Risk management processes are embedded in quarterly and annual reports, supported by an annually updated risk register. While formal sign-off steps remain, all identified risks are addressed within the reporting period, with updates shared during monthly meetings. Financial reporting consistently captures monthly expenditure across instruments and districts, supported by the monthly forecasts. Timely submission of quarterly reports and continued capacity-building at district level remain priorities to ensure robust data collection and compliance with FCDO reporting requirements.

Commercial performance
The Technical Assistance (TA) Facility implemented by Cowater has demonstrated strong alignment with its work plan and outputs, consistently delivering high-quality monthly and quarterly reporting. The scale-up plan has been successfully implemented, with all agreed positions now filled, and notable improvements achieved in audit compliance for the 18-month reporting period (October 2023–March 2025). A time and cost extension to the TAF was approved to June 2027 to align with the EPR implementation timeline and the forthcoming EPR basket, which includes KfW as a contributing developing partner. There is continued oversight of the programme from SRO, PRO and PO which has ensured oversight and governance. The MEL supplier, Oxford Policy Management, has maintained quarterly reporting; however, its contract will conclude early in March 2026 in line with FCDO’s resources’ prioritisation under reduced ODA spending. There were noticed delays in MEL deliverables mainly influenced by both the timing of EICV7 data availability—critical for initiating the impact evaluation—and the involvedness of engagement processes with government counterparts. These factors underscore the importance of continued collaborative efforts to strengthen strategic engagement and data-sharing mechanisms, ensuring MEL outputs are timely and effectively inform Rwanda’s social protection priorities.

Financial Performance
During the reporting period, total programme spend was close to £16 million, with the disbursements to the GoR under NBSFA £14m , £1.3 million for the Technical Assistance (TA) Facility and £0.3 million for Monitoring, Evaluation, and Learning (MEL). Disbursements to GoR continue on a triannual basis (July, November and January), while TA Facility funding is released quarterly following PRO and SRO review of work plans budgets and quarterly reports. Sida contributions, managed through third party funds account held at Crown Agents Bank, ensured compliance with the Memorandum of Understanding enabling flexibility between FCDO and Sida share of the funds required. Of the FCDO budget transferred to LODA, 90% was utilised during the review period. Audit recommendations highlighted the need for enhanced monitoring to address issues such as delayed fund transfers to beneficiaries especially for NSDS component, unutilized balances, and beneficiary database discrepancies. FCDO has continued discussions with LODA to on a clear work plan to address these concerns, and we continue to closely monitor financial management and delivery.

Asset management within the TA Facility remains consistent, with regular inventories shared with FCDO. The matter of mobile phones purchased for para-social workers has been resolved collaboratively with LODA, and these assets are now under LODA’s ownership following approval of the transfer by the Development Director. FCDO continues to encourage best practices in asset monitoring, and the TA Facility has demonstrated strong compliance and stewardship in managing assets.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
Monitoring and learning have been central to programme delivery throughout the review period. Routine monitoring confirmed that the programme remained broadly on track, while structured engagement and field visits provided critical insights for adaptation.

EPR Steering Committee Meetings

Three EPR Steering Committee meetings—held in October 2024, March 2025, and September 2025—served as critical platforms for joint oversight and strategic dialogue among FCDO, the Government of Rwanda , Sida, the TAF, and the MEL team. These sessions enabled partners to assess programme performance, ensure coherence, address emerging risks, and agree on actionable priorities. They also provided an opportunity for FCDO to discuss our future contribution to Rwanda’s social protection sector, and to formally welcome KfW as a new contributor to the forthcoming EPR basket fund. A formal ToR was developed to ensure clarity on evolving membership and role of the SC. To sustain their effectiveness, it remains essential to uphold the strategic importance of these meetings, secure high-level GoR participation, and establish forward-looking agendas that drive alignment and impact.

Field Visits and Development Partner Coordination
During this period, FCDO continued to play an active convening role among development partners (WB, UNICEF, WFP, GIZ, KfW, ILO, BRAC) through facilitation of informal DP group meetings, reinforcing joint learning and coordination. Maintaining this collaborative approach especially in coordination of investments and sector advocacy and engagement, including through joint field engagements will remain critical for strengthening programme responsiveness and coherence.

Field visits took place during this period, key observations have included:
- September 2024, Rubavu: FCDO joined the World Bank’s SPTP mission to review delivery and meet beneficiaries. Priorities identified included strengthening PSWs as community role models, improving health/SRHR/nutrition awareness for NSDS beneficiaries, and enhancing childcare and breastfeeding facilities for public works participants.
- May & June 2025, Gicumbi and Nyabihu: Joint high‑level visits with German, Swedish and WFP delegations assessed VUP impact and gathered direct beneficiary feedback.
- September 2025, Rwamagana: A joint WB–FCDO mission supporting additional WB financing highlighted operational issues in Social Registry rollout, and opportunities to improve graduation support and HB‑ECD quality.
- October 2025, Gisagara: A monitoring visit collected feedback on service delivery and programme impact. Key issues included low transfer values amid inflation, unmet needs and limited employment prospects in rural areas, the critical importance of lifecycle grants (old-age, disability, child grants), and delays in Social Registry operationalization affecting timely VUP payments.

Engagement with the Government of Rwanda
FCDO has maintained strong, high‑level engagement with the Government of Rwanda under the new engagement plan, including regular dialogue with the Minister and Permanent Secretary of MINALOC and the Director General of LODA. FCDO has also continued to serve as co‑chair of the Sector Working Group (SWG). A successful Sector Retreat was held in March 2025, and all mandated SWG meetings took place. Feedback from both Development Partners and the Government indicates that BHCK is regarded as a capable and trusted co‑chair. With expected changes to VUP, the SWG and related sector forums will remain essential platforms for strategic engagement and technical coordination to support effective implementation.

In October 2024, the sector convened a Social Protection Conference funded through the Technical Assistance Facility (TAF) and co-chaired by the UK. The event attracted a wide range of stakeholders, including representatives from central and local government, development partners, civil society organizations (CSOs), and NGOs. It provided a unique platform to enhance coordination by bringing together all actors in the SP sector, share knowledge, experiences, and results to strengthen collaboration and drive a shared vision between local and national levels, communicate the requirements of the new SP-SSP2, ensuring alignment across stakeholders as well as presented evidence and learning that demonstrated social protection as a critical investment for Rwanda’s growth and development.

Evidence and Learning

Oxford Policy Management (OPM) Ltd is delivering the MEL component of the EPR programme, structured around four core outputs: independent verification of EPR DLIs, a mid-term review, a VUP impact evaluation, and research and evidence generation. During the reporting period, the MTR report was presented to the SWG Leadership Committee for validation in March 2025, the final DLI verification process was completed in November 2025 and included a learning annex, 2 research pieces on NSDS and large cash transfers were completed September 2025 and OPM initiated data collection for the VUP impact evaluation. The IE will provide much needed evidence on the Safety Net component to assess its effects on beneficiary households and communities, as well as contextual factors influencing outcomes. There will be a dissemination of the IE findings and it is hoped that government will take forward the results for evidence based policy making and implementation.
The evaluation adopts a mixed-methods approach:
- Quantitative Analysis leverages EICV7 data (2023/24) to estimate the causal impact of VUP participation on household outcomes, comparing beneficiaries with non-beneficiaries matched on key characteristics. This enables robust assessment of Safety Net components (DS, cPW, ePW, NSDS) and financial services.
- Qualitative Analysis draws on interviews and focus group discussions conducted in August–September 2025 across five districts with beneficiaries and key informants. Data will be thematically analysed to explore how programme effects materialise at household and community levels.

All programme reporting and analysis systematically present disaggregated data by age, sex, disability status, geography, and other relevant variables. This approach ensures nuanced understanding of programme performance and equity across different population groups, enabling targeted policy responses and informed decision-making. This commitment to robust data practices is reflected in the ongoing VUP impact evaluation, which combines quantitative and qualitative methods to assess household-level outcomes and contextual factors. Furthermore, findings from recent field visits in Gicumbi and Gisagara districts underscore the importance of granular data for identifying critical challenges—such as insufficient transfer values, unmet needs for lifecycle grants, and delays in Social Registry operationalisation—that disproportionately affect vulnerable groups. By maintaining this level of disaggregation and integrating evidence from multiple sources, the programme strengthens its ability to adapt interventions, promote inclusion, and enhance accountability.

Further evidence from OPM research reinforces key programme insights. An assessment of NSDS impacts on fertility found no indication that the program increases birth rates—consistent with global literature showing cash transfers either reduce fertility or have no effect, including those targeting pregnant women or caregivers. Additionally, a study on graduation approaches concluded that large cash transfers are a viable alternative to in-kind asset transfers, offering simplified administration, lower costs, client empowerment, and positive local economic effects. When adequately valued and delivered through existing systems, large cash transfers can drive productive impacts and support sustainable poverty reduction.

Stakeholder feedback, particularly from MINALOC and LODA, underscored the need for deeper engagement by OPM to ensure findings and discussions are contextually relevant and actionable for Rwanda’s social protection priorities. Strengthening this engagement in the remaining months of the contract will be critical for translating evidence into policy and programme improvements.

Over the past year, the programme employed different learning mechanisms, including Steering Committee meetings for strategic dialogue and risk assessment, joint technical field visits for beneficiary engagement and a robust MEL framework led by OPM combining both quantitative and qualitative approaches.

Key lessons highlight the need for timely operationalisation of systems like the Social Registry and adequate transfer values to ensure programme effectiveness. For FCDO and partners, priorities include deeper contextual engagement in MEL and lifecycle grants to address vulnerabilities across age and disability groups. Looking ahead, the focus will be on strengthening evidence-to-policy linkages, maintaining joint learning platforms and leveraging VUP impact evaluation to contribute to global evidence on social protection and poverty reduction.

Date of last narrative financial report	Annual Narrative Report – 1st July 2024 – June 2025 / Annual Financial Report – 1st July 2024 – June 2025	Date of last audited annual statement	Office of the Auditor General of Rwanda / LODA Audit Report on Financial Statements for the year ended 30 June 2024 / LODA Compliance audit report on expenditure for the year ended 30 June 2024

Annex A: Progress on EPR 2024 annual review
Action	Responsibility	Timelines	RAG Rating	Progress
Following this Annual Review, FCDO should undertake a review of the EPR Logframe to ensure alignment with the results framework for the new Sector Strategic Plan, update targets and indicators in line with this, and incorporate requirements from KFW who will be joining the programme in 2025. This process will be facilitated by the MEL team, include all key stakeholders and should also inform any changes to the disbursement linked indicator (DLI) framework for future years.	BHC Kigali Programme Team with support of TA Facility	Feb-25		The logframe review kicked off in February 2025 to strengthen measurability and ensure alignment with the new national Social Protection Sector Strategic Plan (SP‑SSP2/NST2), including its indicators, methodologies, and data sources. The process involved extensive consultations with sector stakeholders, including the TAF team, as well as technical input and recommendations from the MEL provider, the Programme SRO, PRO, and the FCDO M&E Advisor. The revised log frame was subsequently approved by the Development Director in September 2025.
Strengthen FCDO policy engagement to address key challenges in the Social Protection sector, focusing on areas like financing and coverage, based on further analysis	BHC Kigali Programme Team LODA, MINALOC and with support of TA Facility	May-25		The FCDO policy engagement strategy for the Social Protection sector was developed and is now under implementation. The strategy outlines a structured approach for engaging with MINALOC, LODA, and other key sector stakeholders, ensuring coherent policy dialogue, coordinated support to Government priorities, and strengthened influence on sector reforms.
Reflect on how to use DLIs from financial year (FY) 2025/26)	SPSWG	Jun-25		Policy reforms e.g. introduction of Categorical Grants have been
Give increased focus to building sub-national capacities for effective implementation of existing VUP instruments in line with approved guidelines (including a stronger focus on gender and social inclusion (GEDSI))	BHC Kigali Programme Team LODA, MINALOC and with support of TA Facility	Ongoing
				MINALOC and LODA with support of TAF continue to prioritise capacity building at national and sub national levels. The Training framework was also approved, and the Training Management Team was appointed composed of LODA and MINALOC staff.

Support the onboarding of KfW into the EPR programme and dedicate sufficient staff time to fulfil our responsibilities in relation to development partner coordination	BHC Kigali Programme Team	Ongoing		KfW has formally joined the EPR programme. All requisite agreements, including the Joint Implementation Agreement and the Cooperation Agreement governing the basket structure, have been successfully concluded.

Engage with MINALOC/LODA on how to strengthen sector coordination, accountability, and oversight, linked to the broader review of coordination structures being undertaken by GoR	BHC Kigali Programme Team	Ongoing		The SP Sector Working Group (SWG) structure has been strengthened under the coordination of the MINALOC Social Protection SPIU Secretariat. As part of this process, the Social Protection Procedure Manual was revised and validated to ensure alignment with the new SP‑SSP. Additionally, a reinforced governance structure for the SWG was established, together with a framework to guide its effective, efficient, and transparent operation across the sector.
				The Social Protection Sector Working Group (SWG) structure has been strengthened under the coordination of the MINALOC Social Protection SPIU Secretariat. As part of this process, the Social Protection Procedure Manual was revised and validated to ensure alignment with the new SP‑SSP. Additionally, a reinforced governance structure for the SWG was established, together with a framework to guide its effective, efficient, and transparent operation across the sector.