Programme Completion Review

Title: Strengthening Public Financial Management and Revenue Collection in Rwanda (SPARC)
Final Programme Spend £ (full life): £19,064,249.37.94	Review Date:	September 2025
Programme Code: 204479	Start Date: 21st February 2018	End Date: 30th June 2025

Summary of Programme Performance

Year	2018-19	2019-20	2020-21	2021-22	2022-23	2023-24	2024-25
Programme Score	A	A	A	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	Business Case (October 2018) / Business case Addendum 1 (November 2020) / Business Case Addendum 2 (October 2021)
DevTracker Links to all logframes used during programme lifetime:	Logframe / DevTracker Programme GB-1-204479 Documents

A. Summary and Overview

Description of the programme and what it has achieved

The Strengthening Public Financial Management and Revenue Collection (SPARC) programme started in February 2018 and ended in June 2025. The initial intended impact of SPARC was to support the Government of Rwanda (GoR) to manage public resources more effectively to support delivery of GoR’s development plan, the National Strategy for Transformation (NST1). This would be achieved by improving their systems and capability to manage public expenditures and domestic revenues. SPARC initially supported three GoR institutions through financial aid: the Office of the Auditor General (OAG) to strengthen audit capacity; the Rwanda Revenue Authority (RRA) to increase institutional capacity to collect more revenues; and the Ministry of Finance and Economic Planning (MINECOFIN) to improve public financial management capacity in decentralised entities.

During the programme’s lifetime, there were two addendums to the SPARC Business Case. The first one introduced the Rwandan Technical Assistance Facility (RTAF) in response to demand from GoR institutions and a no-cost extension from the initial end date of 2023 to 2025 to allow the programme to absorb its planned funding and to deliver delayed activities. The second, also no-cost, addendum added a set of interventions to strengthen social accountability, including citizen and media engagement in policy debate, which aimed at increasing the space for dialogue between non-state actors and government partners leading to positive policy institutional changes, better development outcomes, and increased citizen voice. It also ended the support to the OAG and RRA early, in 2021.

Reflecting the business case addendums, the impact statement or goal of SPARC was modified to “More effective management of public resources and more effective policy response to complex development problems, in delivering the National Strategy for Transformation”. A second outcome statement was also introduced to reflect the added work on accountability: “Interactions between the state, private sector, and non-state actors are increasingly characterised by open and informed dialogue, critical thinking and constructive challenge”.

Overall, SPARC has scored an A. The overall programme score reflects the aggregate performance across all outputs, as calculated using the FCDO scoring calculator. Four out of five outputs met or exceeded expectations, with one output (social accountability) moderately not meeting expectations due to contextual and design challenges. The scoring is based on robust evidence from annual reviews, partner reports, and the independent 2025 impact evaluation. Changes in context, such as the early closure of some components and the addition of new outputs, were considered in the scoring and are detailed in the output assessment section.

Whilst performance varied across outputs, the programme met expectations and delivered a wide range of results across its pillars. This includes:

The investment made in digitalising tax systems, as well as strengthening RRA data analytical capabilities and institutional capacity contributed to increasing tax collections to Rwf 2,325.8 billion, surpassing the target of Rwf 1,630.2 billion by 30%, in 2023. Total collections have continued to increase to Rwf 2,990 billion as of June 2025.

Support to the OAG increased their capacity to audit Government expenditure, and by the end of our support the office was auditing 88% of total Government budget expenditure, exceeding the set target (87%) by one percentage point and the baseline (85%) by three percentage points.

Support on public financial management (PFM) has led to a significant improvement in the use of public funds by Districts and from a baseline of 0 at the start of SPARC, 27 out of 28 Districts (including City of Kigali) received clean (i.e. unqualified) audits on their latest financial statements.

The RTAF was instrumental to delivering the GoR’s five-year (2024-2029) development plan, the National Strategy for Transformation (NST2), which is a blueprint that aims to help Rwanda achieve the Sustainable Development Goals (SDGs) by 2030 and upper-middle income status by 2035. It also helped develop other key strategy documents, including the Public Financial Management Sector Strategic Plan and the Governance and Decentralisation Sector Strategic Plan.

The RTAF also supported the National Institute of Statistics of Rwanda (NISR) to carry out the impact evaluation of District Imihigo (performance contracts)[1]; recommendations from this piece of work have influenced government policies such as improving GoR’s Monitoring and Evaluation systems and integration of the Local Government Tax and Land Management Systems. The latter reform is expected to significantly increase property tax collection, which will in turn increase district revenue and therefore their capacity to deliver development.
[1] The Imihigo (performance contracts) system is a home-grown initiative aimed at fast tracking development in Rwanda. Activities included in Districts Imihigo will most likely be implemented because District leaders will be held accountable by the President if their imihigo targets are not achieved.

Support to civil society has strengthened the capacity of journalists to conduct investigative journalism (for example, see these articles on administrators stealing food allocated for students and pregnant women and children being charged to enrol in government food aid), supported the integration of farmers’ priorities into District Imihigo, and generated evidence on priority services for decentralisation in the health and agriculture sectors.

It is worth noting that a successor programme, Twiyubakire, was designed based on the lessons from this programme and has been active since November 2024 to facilitate a smooth transition. However, due to the reduction in UK ODA (to 0.3% of GDP), Twiyubakire will be closing early and have to focus on a smaller number of the most strategic and catalytic activities than initially envisioned.

Major lessons learned, evidence generated and recommendations

Building a cohesive strategy that leverages funding from centrally managed programmes (CMPs) to complement bilateral work can be an effective way to bring in additional technical expertise. This will require sufficient staff time at Post to engage in the design and adaptation of CMPs to ensure that the collective portfolio is cohesive and the whole delivers more than the individual parts, as well as that it is well tailored to the needs of the Government (or another partner).

When Financial Aid to the Office of the Auditor General (OAG) and Rwanda Revenue Authority (RRA) ended in 2021, peer-to-peer partnerships were introduced through embedded advisers from HMRC and the UK National Audit Office (NAO). These partnerships are sustaining and building on the investment that the UK made in these institutions over the last 20 years. As FCDO considers its footprint in Rwanda, this can be an effective model to maintain relationships and impact for far less funding.

High-quality political economy analysis (PEA) is critical to designing effective and well-tailored interventions. Again, as the UK transitions to delivering development with less ODA, PEA will be important in ensuring that the available UK support is directed to interventions with high development return.

Although co-creation with partners can be time-consuming, the work of the RTAF to help institutions articulate their challenges and identify ways to address them has demonstrated how important it is to ensuring interventions are relevant and that institutions have a strong sense of ownership.

In the future, FCDO needs to consider carefully the role it expects of technical assistance facilities: should they focus on traditional supply side support or play a more facilitative role bringing together coalitions of state and non-state actors to drive change; should they be responsive or strategic. Answering these questions early in design will avoid facilities being drawn in too many directions and ensure they are clear on their theory of change.

The social accountability component of SPARC was short term in nature, and it was delivered by different CSOs advocating for different policy issues at different times. This limited both the impact of the component and the sustainability of changes that did occur. Any future programming in this space should either target much more specific outcomes (that can be achieved in a short time frame) or, ideally, consist of a longer-funding period and more holistic strategy.

The management of individual grants is time consuming; FCDO should explore outsourcing this management to a grant manager (as is being trialled under the new programme, Twiyubakire).

The logframe indicators, especially those linked with the social accountability output, did not fully reflect the range of interventions and did not sufficiently measure progress. Future programmes should ensure the logframe, indicators, and milestones mirror closely the theory of change, and allow them to hold partners to account.

Future programmes should be designed from the outset to leverage complementarities between interventions (e.g. on the demand and supply side) to increase the impact of the whole portfolio.

SPARC did not fully integrate gender and disability perspectives across all components of the programme, and it may be possible to better target these particularly vulnerable populations. This should be considered for future programming.

When designing future technical assistance programmes, the value for money lessons from SPARC, particularly around balancing national/international expertise, capping consultant daily rates, and using a single provider to share overhead costs, should be integrated.

Finally, one of the largest challenges for this programme was several major revisions to the approach, with components being closed early and others added late (often due to factors outside the team’s control, e.g. ODA reductions), which led to a lack of strategic coherence. Going forward, it should be a priority to design programmes with in-built flexibility to facilitate adaptation.

How this report was conducted

This report was written by the programme team composed of advisers and programme managers and it was quality assured by the SRO (who joined the programme team in March 2025 and is an accredited Evaluation Adviser). It was informed by the 2025 SPARC impact evaluation report, progress reports from partners, and interviews with implementing partners and beneficiaries.

Actions following approval of this report

Several final payments were made in September 2025, all relating to activities completed before 30th June 2025 (or when the relevant agreements ended). This is due to the late submission of invoices or additional clarifications being required. Final payment amounts have been agreed with all partners and are reflected in the final programme spend.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£20,100,000	£19,064,249.37.94
Timeframe	Five years: 2018-2023	Seven years: 2018-2025
Outcomes	Improved systems and capability to manage public expenditures and domestic revenues	Due to the two business case addendums, which introduced the Rwandan Technical Assistance Facility and the Social Accountability components, a second outcome was introduced: “Interactions between the state, private sector and non-state actors are increasingly characterised by open and informed dialogue, critical thinking and constructive challenge. / The programme performed strongly against Outcome 1. Whilst there is a detailed analysis below, SPARC has helped to design and roll out critical system changes, including the Integrated Financial Management System (IFMIS), and has strengthened individual and institutional capacities. This directly led to impact level achievements such as the increased number of public institutions audited (from 139 to 206), the increased number of districts getting clean audits (from 0 to 27), and a large increase in tax collection (exceeding targets by 30%). / For the second outcome, there is some evidence of progress but as these components were added later in the programme and changing public policy takes time, they are less well developed than for the first outcome. Achievements here include supporting the inclusion of non-state actors in the production of key policy documents, including NST2 and Sector Strategic Plans.

Overall assessment of programme outcomes, sustainability and VfM

As described above, SPARC had two outcomes:
1. Improved systems and capability to manage public expenditures and domestic revenues, and
2. Interactions between the state, private sector, and non-state actors are increasingly characterised by open and informed dialogue, critical thinking, and constructive challenge.

The below table summarises progress against each outcome indicator; as some components of the programme closed before the end date, the relevant final milestone occurred in previous years. Overall, SPARC achieved almost all the outcomes set in the logframe and significantly exceeded expectations against some targets.

Outcomes	Outcome indicators	Milestone	Progress
Improved systems and capability to manage public expenditures and domestic revenues	Number of public entities audited.	2022 milestone: 165	Significantly exceeded expectations: By the end of OAG support in 2021, 206 public entities were audited. As of 2024/25, they are auditing more than 96% of public expenditure.
	RRA has organisational capacity (systems and capability) to manage domestic revenue collection.	2021 Milestone: / 20% of activities in the Strategic Plan that directly deliver on the four modernisation priorities are complete.	Met expectations: By strengthening its ICT systems and the new operating model, RRA enhanced internal capacities to better manage domestic revenue collection.
	Number of Local Government Districts receiving (a) 'unqualified' audit reports and (b) number of Districts receiving 'qualified' or 'except for' audit reports.	2025 Milestone: / (a) 4 / (b) 20	Significantly exceeded expectations: By the end of SPARC in June 2025, 27 out of 28 (96%) districts had received unqualified audit opinions on financial statements, from a baseline of 0 at the start of the project and 1 district got an “except for” audit report from a baseline of 5.
Interactions between the state, private sector and non-state actors are increasingly characterised by open and informed dialogue, critical thinking, and constructive challenge	Number of policies revised by GoR as a result of engagement with citizens, private sector, and other non-state actors.	2025 Milestone: / 5 policies developed/revised / (total for life of project)	Partially met expectations: 3 policies were developed/revised, including the National Strategy for Transformation (NST2); The Public Financial Management Sector Strategic Plan (PFM SSP); and The Governance and Decentralisation Sector Strategic Plan (G&D SSP). / Additionally, the programme supported work to reform the Rwanda Media Policy and the expropriation law, but these have not yet been adopted by government.
	Number of instances when feedback from citizens and businesses were incorporated into government policies.	2025 Milestone: / 9 instances / (cumulative target)	Met expectations: In total, the programme has captured 10 instances, including the mainstreaming of climate and gender in NST2 and the relevant sector strategic plans; the adaptation of the Governance and Decentralisation Monitoring and Evaluation (M&E) Plan to better capture citizen experience; the utilisation of the Decentralisation Assessment Framework (DAF); recognition of priority sectors identified for decentralisation in the health and agriculture sectors; and the incorporation of farmers’ priorities in District Imihigo.

In terms of sustainability, results which were in line with GoR’s interests, such as digitalising PFM and revenue collection systems, will continue to be sustained after the programme as they are important to delivering the government’s development agenda and will receive continued investment. However, other interventions, such as strengthening the PFM capacity of staff in decentralised entities, will be difficult to sustain given the high turnover of staff, who often leave for better opportunities after acquiring marketable skills. Additionally, there is a risk that progress under the social accountability component will be lost, as it was both short term (making sustainability more challenging) and there has been a significant decrease in funding for civil society organisations (CSOs) in the last 6 months, with several donors (including the UK) significantly withdrawing from the sector.

Whilst there is a more detailed discussion on value for money (VfM) in Section D, overall SPARC provided better VfM than outlined in the business case. It not only delivered against the originally envisioned outputs and outcome but also added two additional pillars of work for less than the original budget.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

As discussed above, the theory of change and outcome indicators have evolved substantially over the lifetime of the programme. Figure 1 presents the original Theory of Change, which was focused on Outcome 1 and the use of financial aid to deliver impact. The Business Case posited that Rwanda’s PFM sector was broad but there were three catalytic investments that had the potential to significantly impact the effectiveness of service delivery and government investment. These were: (a) Creating incentives for service delivery agencies and local government to improve their financial management by supporting the Office of the Auditor General (OAG) to increase audit coverage and quality; (b) Increasing funding to service delivery agencies and local government by supporting the Rwanda Revenue Authority (RRA) to improve tax revenue collection; and (c) Directly targeting the area of greatest weakness by supporting local government financial management to get clean audits. The key assumptions (shown in figure 1) were tested in the early years of the programme and held true.

Figure 1: The Original Theory of Change from the SPARC Business Case

In 2020, there was a major update to the theory of change (see figure 2); the most significant change was the inclusion of broader technical assistance aimed at improving government’s capacity and resources to implement second generation reforms. The transition away from a top-down, state-driven model towards a more open and adaptive system required overcoming a number of bureaucratic barriers such as coordination failure, performance incentives that are suitable to the new challenges, and more effective systems to get (and act upon) feedback from service users.

Figure 2: The updated 2020 theory of change

Finally, in 2021, a further business case addendum was approved, which added the social accountability component, and introduced a second outcome statement: “Interactions between the state, private sector, and non-state actors are increasingly characterised by open and informed dialogue, critical thinking, and constructive challenge”. While a new pictorial theory of change was not formally diagrammed at the time, the logic underpinning this component was that supporting civil society organisations (CSOs) would increase the space for dialogue between non-state actors and government, leading to more responsive policy and institutional change. Key assumptions included: (i) CSOs would have sufficient capacity and access to influence policy; (ii) Government stakeholders would be receptive to engagement; and (iii) Short-term interventions could yield measurable policy change. In practice, assumption (iii) did not fully hold, as advocacy processes required more time than the programme allowed.

Strong and autonomous state institutions have supported sustained development since 1994, but mid-term goals are becoming more ambitious, and the nature of the challenges is changing, involving more complex policy decisions and trade-offs. A more detailed theory of change, particularly outlining these assumptions, would have allowed the programme to more systematically check and challenge them, and may have identified the reason for the more limited progress against this outcome. It also could have supported greater coherence between the components and a clearer strategy on where work was interlinked.

Given these major changes to the theory of change and challenges with certain indicators, there were major changes to the logframe over the lifetime of the programme. Whilst these are captured in the individual output assessments, Table 1 summarises the changes to output weightings and indicators (a full change log is available).

Table 1: Summary of changes to outputs

Outputs:	Changes to weighting:	Changes to indicators:
1. OAG capable of carrying out all types of audit assignments (financial and compliance; performance; special; and IT) to international standards	2018 - 2019: 30% / 2019 – 2022: 20% (↓) / 2022 – 2024: 0% (↓) / For PCR (lifetime): 10%	The most important change was the removing of outer year targets when the programme was closed early. Other revisions reflected agreed changes in work plans.
2. RRA 'modernisation priorities' implemented	2018 – 2021: 30% / 2021 – 2022: 20% (↓) / 2022 – 2024: 0% (↓) / For PCR (lifetime): 10%	The most important change was the removing of outer year targets when the programme was closed early. Other revisions reflected agreed changes in work plans.
3. Local government PFM systems and practices strengthened	2018 - 2021: 40% / 2021 – 2022: 30% (↓) / 2022 – 2023: 44% (↑) / 2023 – 2024: 50% (↑) / For PCR (lifetime): 40%	The indicators evolved over the life of the programme to reflect changes in government priorities and in some areas make the targets more stretching to reflect faster than expected progress (e.g. the roll out of SDMS in schools).
4. High-quality demand-driven technical assistance delivered	2018 - 2019: 0% / 2019 – 2021: 10% (↑) / 2021 – 2022: 20% (↑) / 2022 – 2023: 41% (↑) / 2023 – 2024: 35% (↓) / For PCR (lifetime): 25%	This output was added in 2019 to track the new 'public sector reform' component of SPARC; the initial output was “Selected GoR institutions supported by specialist advisers”. This evolved, as did the indicators, to reflect the technical assistance offer and the identified priorities and approach.
5. Non-state actors are effectively supporting citizens’ engagement in policy making, especially in key service delivery sectors	2018 - 2021: 0% / 2021 – 2022: 10% (↑) / 2022 – 2024: 15% (↑) / For PCR (lifetime): 15%	This output was added in 2021 based on the business case addendum and addition of the civil society work. The most significant change was that there was an initial vision to message the number of citizens that directly benefitted but this proved to be impractical to assess, so the indicator was modified in later years.

## C: Detailed Output Assessment

Output Number and Title	1. OAG capable of carrying out all types of audit assignments (financial and compliance; performance; special; and IT) to international standards
Output Score	A+
Impact weighting (%)	10%	Impact weighting revised since last AR?	Yes – as this output was not active for the lifetime of the programme, the weighting has been amended to reflect the total contribution.

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Audit coverage (value as a % of GoR budget)	87% by 2023	87% by 2021	Met expectations: / 87.8% in 2021.
Team Leaders rated effective in carrying out (a) non-complex audits and (b): repeat complex/special audits.	In 2019: / 10 / 7	This target was suspended in 2020 as it relied on reporting that was no longer available.	Met expectations: In the last year of assessment (2019), the target was met.
Number of audits (including projects) completed independently (without Technical Assistance support) by OAG.	101 in 2023	101 in 2021	Significantly exceeded expectations: In 2021, OAG carried out 208 audit assignments independently, including: all 175 financial and compliance audits; all 9 performance audits; 19 out of 20 special audits; and all 5 IT audits.
IT infrastructure supports efficient audit operations	Internal OAG review of systems to test effectiveness in 2023	52% of KPIs for 2020-21 identified in the OAG ICT Strategic Plan achieved.	Moderately exceeded expectations: The OAG achieved all ICT-related KPI targets (100%) in 2021.
Percentage of Strategic Plan Key Performance Indicators (KPIs) achieved	66% in 2023	64% in 2021	Met expectations: The OAG fully achieved 65% of the KPI targets in 2021 (16% of the KPIs were in progress and 19% not met).

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Overall, this output has scored an A+ as it met or exceeded expectations across all indicators. Impact weightings for outputs were revised only where there was a formal, approved logframe revision, in line with FCDO guidance. For example, following the early closure of the OAG and RRA components in 2021, their weightings were adjusted and documented in the revised logframe. All changes to output weightings and indicators are summarised in Table 1 and fully explained in the narrative. Each output score is underpinned by evidence from annual reviews, partner progress reports, and the 2025 impact evaluation. Any limitations in data availability are noted in the output narrative.

SPARC funded a successful partnership with the Office of the Auditor General (OAG), based on a long-standing relationship (which started in 2011), that helped the organisation meet or exceed its targets. Most importantly, OAG more than doubled the target for the number of independent audits and met the target for the percent of the government budget covered. Additionally, over the last decade, the audit mandate increased both in scope and complexity, creating a need for OAG to upgrade information and communication technologies (ICT). The most recent ICT plan started in 2020 and focuses on improving performance and efficiencies through a combination of reconstruction, standardisation, and upgrading. The Deputy Auditor General noted particular thanks to the UK for procuring critical IT equipment that supports this agenda. Finally, the wider Strategic Plan was driven by three needs: (1) to improve people’s lives through better public services, while delivering its constitutional mandate to scrutinise government expenditure and ensuring those entrusted with the management of taxpayer money are brought to account; (2) to support the implementation of the government’s medium term priorities in the National Strategy for Transformation; and (3) to stabilise perennial staff turnover by restructuring and reinvigorating the HR function. OAG made consistent progress against these targets, and its mandate, throughout the funding period.

Whilst SPARC’s support to OAG ended in 2021, it has continued to make progress in its audit function. Currently, audit coverage of total budget expenditure has increased to 96%, up from 85% at the start of SPARC in 2018. Since 2023, support to OAG has evolved from the direct financial support under this programme to peer-to-peer support through the UK National Audit Office (NAO). NAO and OAG signed a 5-year partnership agreement, which goes up to 2027.
Overall, this output has scored an A+ as it met or exceeded expectations across all indicators.

Lessons learned through this output, and recommendations for future programming

The programme of financial support to the OAG through the PFM Basket Fund scored consistently well, exceeding expectations year after year. Despite the UK’s relatively small investment, it resulted in significant improvements in the conduct of external public sector auditing and in stronger financial accountability in Rwanda. It was a very well-designed intervention, driven by the strong leadership of the Auditor General.

Staff turnover at OAG was a challenge throughout the funding period and continues to be an issue. Competition between public and private sector organisation to recruit from a relatively small pool of certified auditors is undoubtedly one of the main reasons. The key recommendation to the OAG is to strengthen its internal training unit to reduce the impact of high turnover among senior auditors.

Finally, the shift from financial aid to a peer-to-peer partnership has allowed the UK and Rwanda to maintain a relationship in this critical space whilst funding has become more limited. The initial investment in building the holistic capability of OAG means they can take full advantage of the deep technical, but more limited, expertise on offer from NAO.

Output Number and Title	2. RRA 'modernisation priorities' implemented
Output Score	A+
Impact weighting (%)	10%	Impact weighting revised since last AR?	Yes – as this output was not active for the lifetime of the programme, the weighting has been amended to reflect the total contribution.

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Future Operating Model designed and implemented	75% of Transition Plan Phase 2 activities implemented by 2023	Significant areas for investments on RRA transformation have been identified by 2021.	Moderately exceeded expectations: RRA moved to implementation of the new operating model and associated structure in 2021.
Strategic HR function designed and implemented	HR Department activities are 33% strategic by 2023	Changes to the FOM project organisation design and changes to the HR function implemented, succession plans in place for the Senior Management Team (SMT) and targeted operational plans for potential SMT successors are operational by 2020.	Met expectations: Direct support on Strategic HR ended in 2020 when a new design for the function was captured in the approved operating model. At this point, HR was equipped with extra resource and skills (they had completed a restructure) and had conducted a talent assessment for senior management and developed succession plans.
IT systems meet the future requirements of the organisation (RRA users and taxpayers)	All IT activities implemented by 2023	Implementation of key IT investments started by 2021.	Moderately exceeded expectations: By 2021, all IT projects funded by SPARC had been completed and were enhancing the tax and customs systems.
Data Analytics capability developed and embedded in RRA	Independent evaluation of RRA Data Analytics function completed	HMRC interventions to support delivery of RRA's data strategy are on track.	Moderately exceeded expectations: By 2021, the Data Science Team (DAT) was embedded in the new organisational structure and led by an RRA employee who replaced the programme-funded consultant. The Data Strategy was in place, and its implementation was overseen by a committee.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

As with output 1, financial support to the Rwanda Revenue Authority (RRA) delivered concrete results and demonstrated the value of long-term support to these fundamental institutions. Overall, investment in digitalising tax systems, strengthening RRA data analytical capabilities, and institutional strengthening contributed to increasing tax collections to Rwf 2,325.8 billion in 2023, surpassing the target of Rwf 1,630.2 billion by 30%. This was delivered by meeting, or exceeding in most cases, expectations across all five pillars of work:

In 2017, RRA embarked on a journey to review its operating model and design a new one for the future. The concept for the new operating model was inspired by a visit to the HMRC headquarters in the UK. The design phase was completed in 2020. Full implementation of the new operating model and associated structure started in May 2021. The model has enabled RRA to rationalise business functions and staff grading, improve working methods, and enhance capacity in key areas. There is effective ownership of the model by RRA staff and thus sustainability of the investment.

Since 2016, the UK have been supporting the RRA HR team in their ambition to transform into a more strategic (less transactional) HR function; to change structure and ways of working; and to develop a new HR strategy. The changes that have been made in HR during the review period, including introducing the business partnering model, reflect recommendations made by HMRC to increase strategic activity and efficiency. During the final year of funding (in 2021), RRA introduced a Talent Management and Succession Planning process to improve talent identification, differentiate between performance levels of staff, and help line managers to have honest conversations.

SPARC supported efforts to strengthen RRA’s IT systems by funding three activities: the enhancement of the Local Government Tax Management System (LGTMS); the enhancement of the Data Warehouse, Risk Management and Business Intelligence (DW-BI) system, which is a Microsoft tool that collects and analyses operating system data; and an IT Adviser to the Commissioner General (though they were quickly appointed by cabinet to be the Deputy Commissioner General). The LGTMS project was completed in 2020 and simplified the process for filing and paying local taxes and fees, thereby increasing district revenue. The DW-BI integration project was completed in 2021 and improved efficiency by bringing together data from all the IT systems of RRA into one central repository. It has quickly become the main reporting tool that informs management’s decisions; reports are now generated twice a day compared to the previous two weeks/one month. The compilation of data has also increased tax fraud detection, improved tax compliance, and increased tax and customs audit revenue. As of 2021, the RRA IT department had doubled in size to take more responsibility for system development and reduce reliance on contractors. Digitalisation is still a core pillar of RRA’s strategy.

RRA has been focused on becoming an organisation that uses data, evidence, and technology to drive decision-making and inform revenue collection. The data science capacity building project started in 2017 with HMRC’s support and was funded by SPARC from 2018 to 2021. By June 2018, the RRA had created a Data Analytics Team (DAT) within the Electronic Billing Machine (EBM) division, to use the extensive data collected by the VAT electronic billing machines. The DAT was recruited, led, and coached by a data expert from HMRC during the first half of 2018. In October 2018, the RRA recruited a Data Scientist to lead the team. In 2020, RRA approved the Data Strategy and established a Data Science Committee to oversee its implementation. DAT transitioned from a ‘project team’ staffed with consultants to a unit fully integrated into the RRA’s new organisational structure (outside the EBM division). In September 2021, the contract of the head of the data science team ended and team leadership passed on to an employee of the RRA. The DAT ran a large variety of data projects, 11 in 2021 alone; for example, they developed a COVID-19 dashboard to track the impact of the virus on the Rwandan economy.

Finally, SPARC also funded the taxpayer accounts reconciliation and update. This addressed the critical issue of a high number of unreliable taxpayer accounts (due to challenges with migrating data to the e-Tax system) and large balances held in the suspense account. In 2019, RRA contracted KPMG to update and reconcile taxpayer ledgers. At the start of the project RRA had 85.8 bn Rwandan Francs recorded in suspense accounts between 2008 and 2016. The project has traced over 90% of transactions recorded on the suspense accounts and reconciled 135 large and medium taxpayer accounts (confirming tax compliance with RRA records). Covid-19 delayed implementation, and the contract was extended to May 2022.

There was initially a programme-funded adviser embedded in RRA as a Strategic Adviser to the Commissioner General; however, since 2021, the Strategic Adviser has been a member of HMRC staff funded by the HMRC Capacity Building Unit programme. They provide advice and practical assistance to the RRA senior leadership team on how to strengthen overall system of tax administration to become more efficient and effective. Whilst the direct financial aid to RRA ended in 2021, this peer-to-peer partnership with HMRC has continued, in addition to other short- and long-term embedded technical experts from HMRC.

As with output 1, this output has scored an A+ as it met or exceeded expectations across all indicators.

Lessons learned through this output, and recommendations for future programming

The log-frame, output indicators, milestones, and targets were hard to measure and, therefore, essentially failed to usefully support project monitoring. A more balanced basket of quantitative and qualitative measures would be more useful.

RRA believes the most useful aspects of FCDO support were the reliability of funding (despite the ODA cuts), that initiatives were demand-driven, the focus on knowledge sharing and learning, that there was direct and clear communication, and that it supported more adaptive management.

HMRC and RRA have continued their bilateral relationship, but going forward FCDO and HMRC should consider how to more closely align their work, which will be on a much more limited scale, on both tax and PFM to maximise the UK’s offer to Rwanda.

A discussion should be convened across the British High Commission on how to most effectively support better data management and use across the GoR, as multiple programmes are supporting siloed initiatives.
Output Number and Title		3. Local government PFM systems and practices strengthened
Output Score		A
Impact weighting (%)		40%	Impact weighting revised since last AR?	Yes – this was revised to balance weightings across the lifetime of the programme where other components were not active across all years.

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Level of satisfaction of PFM staff capacities by their supervisors, the district executive secretaries.	Original indicator: District PFM staff supported by specialist advisers. / Target: MINECOFIN evaluation of effectiveness of TA support completed by 2023. / *Changed in 2024.		At least 70% of district executive secretaries satisfied with PFM staff performance by 2025	Met expectations: / Executive secretaries interviewed had an average satisfaction rate of 76%.
Quality of citizen participation in the planning and budgeting process	Original indicator: Sectors recoding and reporting financial transactions through IFMIS. / Target: 250 sectors (60%) using IFMIS to produce annual financial statements for 2020/21 / *Changed in 2019.		Approved district action plans and budgets reflect at least 50% of citizens priorities by 2025	Exceeded expectation: Approved district action plans reflect 80% of citizens priorities.
Public schools recording and reporting financial transactions through automated accounting system.	Original indicator: Secondary and Technical Vocational Education and Training (TVET) schools recording and reporting financial transactions through automated accounting systems. / Target: 337 Secondary and TVET schools using the accounting system to produce annual financial statements for 2020/21 / *Changed in 2019.		2,927 public schools use the SDMS accounting system to produce annual financial statements by 2025	Partially met expectations: 2,401 public schools use the School Data Management System (SDMS).
Increased % of district audit report recommendations implemented.	60% by 2025 / *Added in 2022.		70% by 2023	Met expectations: 72% of audit recommendations were implemented
Number of people supported to better adapt to the effects of climate change as a result of digitalising SACCOs	100,000 / *Added in 2024.		100,000	Moderately exceeded expectations: 118,836 people were supported to better adapt to effects of climate change / Note: this figure is the number of beneficiaries that received transfers from automated SACCOs in 2024/25. This reform has helped vulnerable communities to respond to climate change related issues (disasters) in a timely manner.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output covers our support to the Ministry of Economic and Financial Planning (MINECOFIN) to improve the capacity and systems to manage public financial resources at the subnational level, where capacity is weakest, but most services are delivered. The support provided through this programme consisted of financial aid targeted at core activities in the financial decentralisation strategy, combined with ‘technical assistance’ (though this was also provided as financial aid) to the local government.

Over the lifetime of the programme, SPARC has supported a wide variety of activities that have strengthened both individual and systemic capacities. This includes:

15 PFM technical specialists/coaches were deployed to provincial government offices to strengthen the capacities of staff at district level and non-budget entities (such as sectors, schools, and health centres). Each of Rwanda’s four provinces and the city of Kigali had three PFM specialists, one in charge of planning and budgeting; one in charge of procurement; and one in charge of accounting and reporting. Two specialists/coaches were also deployed in MINECOFIN to build capacities of district internal auditors. Interviews with district executive secretaries, the supervisors of PFM staff, provided evidence that the programme had been effective in strengthening the capacities of PFM staff, with a high level of satisfaction with the observed improvements.

  - This support has helped deliver significant improvements in PFM, as reflected by the increased number of clean audits, discussed in Sections A and B.

  - However, district executive secretaries pointed out that PFM specialists/coaches would have done their job better if they had been embedded in districts instead of sitting in provinces and MINECOFIN. Coaches spent much of their time filling staffing gaps, limiting the time they were able to dedicate to training of district staff.

SPARC supported the Government to design the School Data Management System (SDMS), an online system which records students' profiles, school infrastructure, and has an in-built accounting module which helps schools in requesting and accounting for budget for the two main expenditures (capitation grants and school feeding). Before the start of the project, public Secondary, Training and Vocational Education, and Primary, schools were planning, budgeting and accounting for expenditure using excel sheets. This resulted in inefficiencies and fraud (e.g. allocating capitation grant funds and school feeding budget to ghost students). SPARC supported the rollout of SDMS to all public secondary schools (1,766), all TVET schools (161), and recently successfully piloted and rolled out a simplified SDMS module to 474 out of 1,698 primary schools. Rollout of the simplified SDMS accounting module to all public primary schools was not possible due to Government of Rwanda budget constraints. This has led to some key efficiency gains:

  - For schools, the process of requesting and receiving the capitation grant is now down from 90 days to 7 days.

  - The automated school fees payment model has also made it easier for schools to ensure timely financial contributions from parents.

  - School capitation grants are now calculated on the basis of accurate enrolment data reducing risks of inflated student numbers.

  - Budget forecasting is also more accurate.

  - MINECOFIN was unable to quantify overall financial savings made as a result of introducing SDMS but value for money of both school capitation grants and the national school feeding programme are said to have improved.

SPARC supported the digitalisation of Saving and Credit Cooperative Organisations (SACCOs) in all the 416 sectors (entities below districts). This is an important reform that has made financial service delivery to people, especially those benefitting from social protection direct cash transfers and public works payments more efficient. Before digitalising SACCOs, transactions were manual and recorded in ledger books which increased fiduciary risks. In some instances, money (people’s savings) went missing and services were very slow. With the introduction of the core banking system in SACCOs and integrating depositors’ accounts with their mobile phones, access to financial services has significantly improved. SACCO members are now able to withdraw or deposit money using their mobile phones, which are linked to their accounts.

  - This support had an International Climate Finance element, as it indirectly addressed adaptation, as social protection beneficiaries can access timely cash transfer payments, which help them to adapt to climate shocks.

In order to strengthen citizen participation in planning, SPARC trained district and sector councillors on consultation mechanisms, how to oversee the implementation of district plans and hold district executives to account, and how to provide feedback to citizens. Data collected by MINECOFIN indicates that district action plans now reflect 80% of citizen priorities. However, there is a gap in providing feedback to citizens on activities not considered in district action plans, which leads to citizen participation fatigue, especially when citizens keep identifying needs which end up not being funded due to budget constraints[2]. Districts, especially those located in rural areas, get more than 80% of their budget from central government (line ministries), which is earmarked for specific activities which don’t necessarily address citizen priorities.
[2] On average, 57% of citizen priorities sent to Districts are not funded due to budget constraints.

Whilst the scores against indicators are slightly mixed, overall progress has been strong and in line with expectations. There is clear evidence of this output achieving its overall objective of strengthening district level PFM, and hence the score of an ‘A’.

Lessons learned through this output, and recommendations for future programming

The high turnover rate of district PFM staff was a challenge. Whenever PFM staff acquired skills, they became more competitive and moved to either central government jobs or to the private sector. To address this challenge, GoR needs to come up with a comprehensive staff retention strategy. FCDO should explore options to support the GoR on this important reform.

Expertise and capacity could be more effectively transferred by embedding expertise directly in beneficiary offices; for example, PFM specialists would have performed better if they had been deployed in districts, rather than managed centrally.

There is still a clear challenge in terms of citizen feedback loops; the lack of mechanisms for providing feedback to citizens on why their priorities are not reflected in final district action plans lead to citizen participation fatigue. Districts should prioritise putting such mechanisms into place.

While there has been significant progress in rolling out PFM systems, especially accounting systems, decentralised entities still face planning and M&E challenges, which if not addressed, will continue to affect Rwanda’s development. With ODA reducing, planning and M&E is an area that the UK could explore supporting with technical expertise. This would support sustaining the gains made under SPARC, and predecessors, in Rwanda’s PFM systems.

SPARC, particularly this output, benefitted from a centrally managed programme (CMP), the Public Finance and Tax Department (PFTD). Over £ 600,000 was mobilised from PFTD to complement the bilateral budget. Leveraging CMPs will continue to be even more important in the world of reduced ODA.

Output Number and Title		4. High-quality demand-driven technical assistance delivered
Output Score		A+
Impact weighting (%)		25%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
% of TA interventions assessed as executed satisfactorily (as planned) by beneficiary MDAs with regard to: / 1) Perceived relevance / 2) Timeliness and responsiveness / 3) Performance of TAF & TA experts / 4) Engagement with stakeholders / 5) Institutionalisation potential	Technical assistance interventions completed and exit strategy approved (note that the initial indicator was “ / *Added in 2019.		80% satisfaction rate for each intervention by beneficiary MDAs	Moderately exceeded expectations: / 100% satisfaction rate by MINALOC (2025) / 88% satisfaction rate by MINECOFIN (2025) / 95% satisfaction rate by NISR (2023) / 100% satisfaction rate by GMO (2023)
MDA staff capacity to analyse, develop and implement policies, strategies and plans	70% of staff assessed report improvement in capacity / *Added in 2021.		70% of staff assessed report improvement in capacity	Moderately exceeded expectations: 86% of staff assessed report improvement in capacity

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

In response to changing needs and a revised theory of change, the technical assistance component was expanded in 2019 from its initial focus on tax, audit, and local government, to support wider transformational change, including on improved coordination across government, reforms in Imihigo, and mechanisms for citizen feedback. Ultimately, the Rwanda Technical Assistance Facility (RTAF) supported Ministries, Departments and Agencies (MDAs) as follows:

National Institute of Statistics of Rwanda (NISR):

  - RTAF supported NISR to evaluate the impact of the Imihigo (performance contracts) system across districts in the last 10 years. One of the major findings of the evaluation was that districts’ Imihigo focused on delivering outputs rather than outcomes. The evaluation challenged districts to focus on these higher-level deliverables (e.g. in the education sector, going beyond construction of more classrooms to focusing on interventions that improve the quality of education). This has influenced the way districts plan their annual Imihigo targets.

Gender Monitoring Office (GMO):

  - Community dialogues on gender accountability were held, where citizens discussed their concerns and priorities relating to gender equality with the aim of informing district and province planning and priorities. Bringing grassroot level voices to these discussions proved to be an effective way to influence policy and programmatic changes at a local level. For example, all districts in the Southern Province incorporated gender responsive indicators in their Imihigo and District Development Strategies (DDSs). However, the project was too short to ensure long-term policy impact and institutionalisation of the process across districts, but GMO and other parts of GoR are now looking to scale up some of the experience based on UK programme support.

Ministry of Finance and Economic Planning (MINECOFIN):

  - As the largest recipient of support, the RTAF has provided targeted assistance to developing: guidelines for integrating National Strategy for Transformation (NST2) priorities in sector strategic plans; guidelines for mainstreaming gender and climate in NST2 and across sectors; NST2 itself, including its costing and macroeconomic framework; the Public Financial Management Sector Strategic Plan (PFM SSP); and Integration of Local Government Tax Management Systems with Land Information System (LAIS).

Ministry of Local Government (MINALOC):

  - They have supported MINALOC to develop several key policies and approaches related to decentralisation, including: the Governance & Decentralisation Sector Strategic Plan (G&D SSP); the Monitoring and evaluation (M&E) framework for the G&D SSP; and develop District Development Strategies (DDS) for all 27 districts, as well as the City of Kigali (28 in total).

Rwanda Association of Local Government Authorities (RALGA):

  - Finally, they also supported RALGA to develop their new Strategic Plan for 2025 – 2029.

In addition, they provided direct support to FCDO by developing policy briefs on planning, PFM and citizen participation, commissioned the SPARC impact evaluation, and conducted the fiduciary risk assessment.

Overall, the MDAs expressed high levels of satisfaction with RTAF’s delivery, with scores of 5 (very satisfied) and 4 (satisfied). MINECOFIN and MINALOC reported that all interventions met their expectations. They expressed a willingness to institutionalise the TA solutions and products, as they align with each MDAs’ respective mandates and needs. MINALOC emphasised that RTAF has significantly strengthened its institutional strategic orientation, assuring that future results are likely to be positive. The transfer of TA knowledge and skills to MINALOC staff was facilitated through on-the-job training, following a “learning by doing” approach. Furthermore, MINALOC highlighted that RTAF solutions and products are being integrated into institutional deliverables, which will support sustainability and continuity. MINECOFIN mentioned that RTAF's support in developing key chapters of the NST2 enhanced the Ministry's coordination of NST2 implementation across sectors.

RTAF conducted a post-training evaluation to assess the impact of trainings on the NST2 costing tool, hands-on costing, gender mainstreaming in the NST2, and climate change mainstreaming in Sector Strategic Plans (SSPs) and District Development Strategies (DDSs). Overall, most participants reported significant improvements across all measured skills. Before the training, most interviewees rated their confidence as limited (Score 1). In contrast, after the training, participants reported a substantial increase in confidence levels. Many described themselves as either moderately confident (Score 2) or confident (Score 3). Participants shared that they now utilise NST2 frameworks to assess project alignment with national priorities, track fund disbursement delays, and recommend corrective actions. This approach has significantly contributed to ensuring better budget efficiency and timely project execution.

Overall, this output has scored an ‘A+’, as the RTAF has exceeded expectations across both indicators. However, both indicators are highly subjective and monitoring of similar projects in the future would benefit from including more concrete measures.

Lessons learned through this output, and recommendations for future programming

A central element of the RTAF scoping and design process involved active engagement with the Government MDAs to understand the challenges that RTAF could meaningfully support. RTAF used its technical expertise to help MDAs articulate the challenges and identify ways to address them. Although this was a time-consuming process, it ensured interventions were relevant and responded to a clearly defined and evidenced problem. This early investment also helped build stronger relationships and fostered a stronger sense of ownership among beneficiary institutions.

It is important to conduct timely and well targeted political economy analysis (PEA) to ensure understanding of specific issues and inform the design of interventions. An unanticipated benefit was that PEAs strengthened the co-creation process by generating a shared understanding of what was driving the problem and how RTAF could support the beneficiary to tackle it.

The RTAF’s agility in responding to MDA’s requests increased overall trust, which made it easier to deliver other assignments. In some cases, Government counterparts tasked TA experts to carry out activities that were not directly relevant to the TA intervention. Nonetheless, TA proceeded, recognising the value of these actions in building soft power and opening entry points.

RTAF’s pragmatic approach meant designing and delivering interventions in a way that adapted to context and realities on the ground. For example, intervention delivery schedules reflected the fact that it took time for TA to understand the delivery landscape and best ways to engage and work with the range of stakeholders.

The project leveraged both formal (such as formal meetings, roundtables, sector working groups) and informal stakeholder engagement to work with different stakeholders. Informal engagements enabled RTAF to build trust with decision makers and receive tacit support that might not have emerged in formal consultations. Informal engagement strengthened the team’s understanding of personal motivations and political sensitivities that formal processes were less likely to identify.

The TAF was government-centric, and it was not obvious that there was good join up between supply-side support being provided by TAF and demand-side engagement from non-state actors.

Output Number and Title		5. Non-state actors are effectively supporting citizens’ engagement in policy making, especially in key service delivery sectors.
Output Score		B
Impact weighting (%)		15%	Impact weighting revised since last AR?	Yes

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Number of policy engagement events undertaken by non-state actors to influence public policy	Initial indicator and target: 7 (annual) non-state actors supported by the programme (first and second tiers) / *Added in 2021 and amended to the current indicator in 2022		2 in the final year	Exceeded expectation: In total, over 50 (cumulative) policy engagement events were undertaken by non-state actors to influence public policy at both District and national levels
Number of public policies influenced by non-state actors	Initial indicator: Number of citizens (direct beneficiaries) reached by the programme, with no targe set / *Added in 2021, amended to ‘number of commitments made by local or national authorities in response to issues raised by citizens and non-state actors’ in 2022, and then the current indicator in 2023		2 in the final year	Did not meet expectations: Whilst partners have engaged with key policies, there has been no actual change in public policy, as a result of work under this programme.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

This output was added in 2021 after a business case addendum to align SPARC with the UK’s evolving goals in Rwanda, which added this component to strengthen social accountability, including citizen and media engagement in policy debate. Over the last 4-years, the following projects were supported:

Strengthening farmers’ participation in Imihigo planning and budgeting through social accountability tools, led by Transparency International Rwanda (TI-RW, November 2021 – December 2022)

Mainstreaming gender equality and social inclusion in accountability mechanisms (gender budget statements and Imihigo), led by Rwanda Men’s Resource Centre (RWAMREC, November 2021 – December 2022)

Towards Just and Effective Expropriation Practices, led by the Legal Aid Forum (LAF, November 2021 – December 2022)

Promoting International Standards on Freedom of Expression in Rwanda through Media Policy Reforms, Media Ethics and Self-Regulation, led by the Thomson Foundation and the LAF (October 2022 – March 2025)

Supporting Accountability to Policy Commitments on Unpaid Care Work (UCW), led by ActionAid Rwanda (August 2023 – March 2024)

Protecting and enabling journalists’ freedom to work and ensuring compliance to the access to information law, led by the Great Lakes Initiative for Human Rights and Development (GLIHD, September 2023 to March 2024)

Indi Ntambwe mu kwiyubakira Igihugu (INKI, ‘An extra mile in state-building’), led by Norwegian People’s Aid (NPA, April 2024 - May 2025).

Across the projects, partners participated in a wide variety of activities to forward their respective agendas, including over 50 policy engagement events. Examples include:

In 2023/23 RWAMREC organised quarterly CSO forum meetings and four policy engagement events advocating for the integration of issues raised by marginalised people, youth, women, and the elderly in planning and budgeting processes.

TI-RW supported farmers committees to engage in the development of District Development Strategies (DDSs), so that they better reflect their bottom-up needs. During a field visit to Kamonyi, authorities confirmed that they found TI-RW’s approach to be an effective was of engaging citizens in planning processes.

NPA, consortium members, and downstream partners organised six workshops on sectoral decentralisation for civil society representatives, as well as a high-level workshop with MINALOC to share their findings and the Decentralisation Assessment Framework (DAF) that they had developed.

Under INKI, a citizen awareness campaign on policy literacy and environmental safeguarding was also delivered through 24 community awareness sessions, 20 radio campaigns, 15 quarterly dialogue sessions, and the establishment of five policy literacy desks in the districts of Rutsiro, Musanze, Karongi, Ngororero, Gisagara, Gasabo and Bugesera.

Whilst there was significant variation in the performance of individual projects, this output did support civil society and citizen engagement in policy making, with achievements including:

In Nyaruguru district, among nine citizen-led issues that were submitted through support from RWAMREC, district authorities committed to considering seven in the planning of Imihigo 2023/2024; while for the 2 remaining issues they committed to working with other partners to find solutions. Similarly, in Gatsibo District, among 30 issues that were raised, the district authorities committed to considering 10.

Findings from LAF’s research on how expropriating entities comply with expropriation laws, policies, procedures, and practices were used to engage stakeholders, government and CSOs in dialogues on the improvement of the implementation of expropriation practices and fed into the review of the expropriation law.

15 journalists were provided with training on investigative journalism and digital security, and afterwards a grant to produce a piece of investigative journalism. This led to the production of some high-quality reporting, including on school feeding, social protection, illegal mining, environmental degradation, and illegal expropriations (for example, administrators stealing food allocated for students and pregnant women and children being charged to enrol in government food aid). According to those interviewed for the SPARC impact evaluation, they became more aware of their responsibilities and were now able to write investigative articles “without bringing their profession into disrepute”.

LAF collated the views of more than 90 stakeholders to inform development of the new Media Policy and also supported the drafting of the accompanying cabinet paper that was submitted to the Rwanda Governance Board (RGB), the custodian of the draft policy, for onward transmission to the Cabinet.

INKI improved the capacity of 128 representatives from 91 civil society organisations to review policy, legislative, and local governance practices against principles of decentralisation and good governance.

It also developed a Decentralisation Assessment Framework (DAF) that was validated and owned by relevant government institutions and non-state actors, in particular MINALOC and RGB. It helped identify eight priority functions for decentralisation in health and agriculture, and key government stakeholders have endorsed piloting six of these.

Finally, 46,551 citizens were reached with information on government policy choices and environmental safeguarding issues, via INKI’s public awareness campaign.

However, unfortunately, this has not (yet) translated into actual change in any public policies. The programme has supported the incorporation of civil society views and priorities into the design of the new draft expropriation law and media policy, but neither of these have been approved/adopted by government and it is unclear what the final versions may look like (i.e. whether they will reflect the engagement by civil society). There has also been positive reception to the DAF, but as it was only completed a few months ago, this has not yet changed government policy within a specific sector or on decentralisation more broadly. There have been several challenges to delivering this output that may have contributed to the lack of successful delivery:

Time constraints: Advocacy is a protracted process, and it takes time to realise policy change. The majority of targets were over ambitious when you consider the limited time and scope of the individual projects. For example, the INKI project generated multiple policy recommendations, but their implementation will only be realised beyond the project’s lifespan and if the organisations secure other funding.

Contextual challenges: Successful policy reform is always dependent on having an intricate understanding of the incentives and power dynamics of decision makers. This requires having a robust PEA and influencing plan, but the quality of this underlying analysis has been variable. For example, LAF and the Thompson Foundation were both unclear on the factors delaying the approval of the media policy.

Internal structural challenges: Effective advocacy requires specific capabilities and some implementing partners struggled to hire individuals with those skills. Additionally, the consortium model trialled by INKI ended up causing significant delays to implementation when one member withdrew.

Overall, whilst some progress was made, the engagement with civil society was too short-term and unfocused to deliver significant change. The most important indicator – number of public policies influenced – was missed, and therefore this component has scored a ‘B’.

Lessons learned through this output, and recommendations for future programming

In the Rwandan context, it is critical to engage key government stakeholders early in advocacy interventions. For example, the early involvement of relevant ministries (MINALOC, MINECOFIN, RGB, and the Ministry of health) during the design and validation of the Decentralisation Assessment Framework (DAF) led to a high indicative uptake of the proposals.

Regular feedback mechanisms between citizens, CSOs, and government institutions should be encouraged to ensure that policies remain adaptive and responsive to local needs.

Programme/project success is dependent on being able to adapt. As political contexts shifts and partners face different realities on the ground, the project’s ability to adjust is essential to remaining relevant and delivering impact.

Given the reduction in ODA funding, the UK can still harness its technical expertise and convening power to support CSO advocacy and accountability interventions, as well as work with other development partners to coordinate support. It should be a priority to develop a new strategic approach to CSO support by the end of the financial year.

Any future advocacy initiatives must be informed by rigorous PEA during both selection (to ensure there is a window for influence) and throughout the lifetime of the project to inform timely adaptation. There must also be clearer theories of change, so it is easier to measure progress and test which assumption(s) has failed if/when a project does not deliver as expected.

Future work should prioritise influencing the sustainability and institutionalisation of citizen engagement not only at the local but also central level.

Work on ‘accountability’ should more closely align work on the push and pull factors to ensure that both the capacity for citizens to engage with government, and the latter’s capacity to respond are built in tandem. For example, SPARC would have benefitted from a closer alignment between the work under this pillar and the RTAF (e.g. the work of RWAMREC and RTAF with the Gender Monitoring Office were similar but occurred in isolation).

D: Value for Money

The SPARC programme demonstrated reasonable Value for Money (VfM) that remained in line with the original business case proposition and, arguably, even exceeded it given the growth in scope for the same budget. While cost-effectiveness in governance programmes is hard to quantify, the programme’s design and delivery demonstrate a commitment to VfM throughout.

Economy

SPARC achieved economy through cost-conscious implementation. The main cost driver was the buying of expert time, though infrastructure (e.g. IT equipment) investments were also made.

Much of the programme was delivered through financial aid and therefore utilised government systems for recruitment and procurement, reducing costs compared to private sector contracting.

The Rwandan Technical Assistance Facility (RTAF), managed by DAI, engaged 79% national experts and 24% international experts, enhancing contextual relevance and lowering costs.

The RTAF also capped consultant rates, saved £2,832 annually in office rent, and benefited from the closure of another FCDO-funded project by acquiring its assets, resulting in estimated savings of £5,500.

On CSO grants, programme budgets were utilised by partners as per agreed work plans.

All partners adhered to appropriate procurement policies that favoured lowest-price bids.

Efficiency

Efficiency remained high and even improved over the lifetime of the programme.

Financial aid continued to be an efficient mode of delivery in the public financial management sector, as the entire budget is spent on programmatic results aligned to the GoR’s priorities.

The provision of technical assistance was consolidated under one service provider (DAI) to share management costs over a larger number of projects, and to streamline recruitment and management processes. This tended to be more efficient when completing well-scoped work, as opposed to responsive (though the latter was often more appreciated by government).

Budget execution under LGPFM rose from 58% (2019) to 91% (2022).

Staff turnover undermined efficiency across all institutions where SPARC was building human capacity, as senior staff had to be retrained or skills were quickly lost.

Finally, the programme was extended from 5 to 7 years, and two additional pillars of work were added for no additional budget. Given the targets for the original pillars were all achieved (with additional achievements under the later years and outputs), this supports that funding was more efficiently converted into outputs and outcomes.

Effectiveness

Effectiveness is discussed in detail in sections B and C at the outcome and output level respectively. As the programme has scored an ‘A’ and achieved, or even exceeded, most of its objectives, this supports that the programme has delivered on the original VfM case.

Equity

Equity was central to the programme design and reflected in many of the outputs.

RWAMREC and GMO interventions led to gender indicators in district plans.

CSO grants targeted marginalized groups (women, youth, elderly, and people with disabilities) and promoted environmental and social safeguards.

SACCO automation improved financial inclusion, with female loan uptake increasing by 61% and increases in female membership (+24%) outpacing male membership (+20%) between 2022 and 2024.

CSO-led media training empowered journalists to publish responsibly, reducing legal risks.

The RTAF mainstreamed gender and climate across national and sectoral strategies.

.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
Throughout its implementation, SPARC maintained a moderate residual risk exposure, with a stable risk profile across its components. Risk management was proactive and adaptive, supported by quarterly updates to the risk register and revisions to the risk appetite document. These mechanisms enabled timely identification and mitigation of emerging risks, contributing to programme resilience and delivery. Below summarises some of the major risks over the programme’s lifetime.

Policy and Programme Delivery Risks

Delivery risk was acute in the Technical Assistance Facility (TAF), where success hinged on political processes and government buy-in. Civil Society Organisation (CSO) advocacy efforts encountered institutional resistance, limiting influence on policy reform. The INKI component faced delays due to partner withdrawal and RGB pre-authorisation requirements, highlighting the need for stronger contingency planning. Consultants were at times tasked beyond their Terms of Reference (TORs), and Monitoring, Evaluation, and Learning (MEL) systems struggled to capture outcome-level results, limiting evidence of impact.

Key mitigation strategies included:

Senior-level engagement with the Government of Rwanda (GoR) to secure commitment.

Strategic alignment of programme objectives with national priorities.

Use of TAF’s adaptive delivery model, which enabled responsiveness but occasionally compromised coherence and clarity of outcomes.

People Risks

Staffing capacity remained a persistent and high-impact risk. High turnover in Public Financial Management (PFM) institutions, driven by low public sector pay and private sector competition, posed sustainability challenges. Staffing levels declined from 82.8% to 58.6%, exacerbated by internal recruitment delays and the UK aid pause.

Mitigation efforts included:

Deployment of locally recruited coaches, who demonstrated higher retention and contextual understanding.

Recommendations for tailored recruitment strategies and capacity-building investments to ensure continuity and institutional strengthening.

Fiduciary Risks

Three components of the programme were delivered through a financial aid modality, which presented challenges in fund traceability and accountability. Mitigation measures included:

Use of separate bank accounts for programme funds.

Quarterly progress reports and compliance reviews.

Strengthened financial reporting aligned with government systems.

There was also a high-risk of fraud in the work with civil society. Appropriate mitigations were put in place, including due diligence assessments and close monitoring, but unfortunately fraud cases were detected. To respond to the cases, the programme team commissioned audits which led to all funds being recovered.

Reputational and Safeguarding Risks

The main reputational risks stemmed from changes in the Government of Rwanda’s commitment to the Partnership Principals (see discussion below) and the delivery of poor-quality outputs, particularly on high-profile initiatives like the new National Strategy for Transformation (NST2), undermining the credibility of the UK. Mitigations for the latter included:

Feedback loops with stakeholders.

Quality assurance mechanisms to ensure delivery standards.

The only component of this programme that worked directly with more vulnerable beneficiaries was the social accountability element. Safeguarding risks were managed through:

Spot checks

Due diligence assessments

Contractual safeguards

No safeguarding incidents were reported during implementation.

Update on Partnership Principals

SPARC’s financial aid components (OAG, RRA, and LGPFM) were subject to consideration of the Partnership Principles. The Rwandan government’s commitment to these principles was last formally reviewed in 2021 with the following conclusion:

“Overall, we assess that the Government of Rwanda remains committed to the underlying principles of our aid partnership sufficient to continue financial aid. Rwanda continues to demonstrate strong commitment to poverty reduction, economic and social rights, anti-corruption and sound public financial management. Commitment to civil and political rights and domestic accountability is limited and we remain particularly concerned about civil and political rights.”

In February 2025, in response to the situation in Eastern DRC, the UK took measures against Rwanda, including pausing “direct bilateral financial aid to the Government of Rwanda (GoR), excluding support to the poorest and most vulnerable”. As this pause came in after this programme’s final payment to the GoR, it did not impact the activities under SPARC. However, it has impacted the follow-on programme (Twiyubakire) and means that no further financial aid has been provided to any of the government departments previously supported by SPARC.

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Moderate / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Moderate / Stable

The latest fiduciary risk assessment (FRA) was completed in February 2023.  It concluded that: “The overall fiduciary risk for the Rwandan government systems as of December 2022 is assessed to be ‘Moderate’ with no change in risk rating and with a positive trajectory compared to the previous (2019) FRA assessment. The GoR’s overall commitment to improve PFM, strengthen financial accountability, and tackle corruption is assessed as ‘credible’. The overall assessment of the level of residual risk is assessed to be ‘Minor’ for fiduciary risk. It also assessed the corruption risks to be ‘Moderate’, with no change compared to the previous 2019 FRA assessment.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Programme coordination and oversight was challenging and absorbed a lot of FCDO programme management and advisory staff time because of a fragmented delivery chain that included a multitude of delivery instruments, projects, and organisations. This complexity largely emanated from the desire to make limited funds respond to wider governance issues after ODA reductions in 2020/21. During the lifetime of the programme, the FCDO team managed a portfolio of Financial Aid, a commercial contract, and accountable grants. Between 2018 and 2025, £19,064,249.37 (or 95% of the original budget) was disbursed across three modalities and 11 funding agreements.:

Total Financial Aid to GoR: £11.9M (62.3%)

  - MINECOFIN: £8.1M (42.4%)

  - RRA: £2.0M (10.5%)

  - OAG: £1.8M (9.4%)

RTAF (Commercial Contract): £5.0M (26.2%)

CSO Grants (Accountable Grants): £2.2M (11.5%)

The programme team worked closely with all partners to ensure financial management requirements were accurate and timely. The team held monthly meetings with partners, and scrutinised reports to ensure compliance with FCDO requirements. Partners provided FCDO with quarterly invoices, financial, and narrative reports. The reports showed detailed spend breakdown and projected expenditure for each quarter. As a safeguard, the programme team scrutinised progress reports in conjunction with annual workplans, budgets, and milestone schedules and discussed progress with partners prior to disbursement of funds or payment of invoices. While quality of reporting improved over time, timeliness varied, particularly during transitions and staffing changes. Regular monitoring visits were also conducted to all programme components

Whilst there were fraud cases, these were quickly identified by the FCDO programme team, and all misappropriated funds were recovered.

DAI, the commercial partner delivering the RTAF, consistently scored well against their key performance indicators, including sufficiently to have their contract extended for one additional year under the follow-on programme, Twiyubakire.

As mentioned above, this programme required significant FCDO oversight, including advisers having to engage more heavily than expected with all delivery partners to ensure high-quality PEA and well-tailored programming. In general, partners could have been more proactive in their programme delivery, with FCDO often having to step-in and suggest adaptations.

FCDO could, and should, have brought more strategic coherence to the programme, which often felt fragmented with the late addition and early closure of components. Forecasting over so many components was a challenge throughout the programme’s lifetime and underspends and delays were common.

There is a full discussion on VfM in section D, but partners generally performed well across both economy and efficiency metrics. For example, consultant fee caps and cost-sharing mechanisms enhanced economy, whilst the programme delivered more than initially envisioned for less budget (i.e. improved efficiency).

Programme-level approach to monitoring and evaluation

SPARC had sufficient monitoring in place to provide performance and financial oversight, manage risks, and support decision-making at appropriate levels. The monitoring strategy had to evolve substantially over the lifetime of the programme, as new objectives, scope of work, and implementing partners made monitoring more complex, unwieldy, and difficult to manage. Monitoring information was received quarterly from all active partners, though internal monitoring methods, protocols, capacities, and resources (including costs) varied substantially across partners. Partners’ logframes and theories of change were designed to be aligned with the overall programme documents, though further work could have been done to ensure indicators provided accurate and useful information about each partner’s progress.

The 2021 annual review was conducted by an accredited Governance Adviser from outside the officer to provide quality assurance and challenge; their findings were largely in line with reviews conducted by the programme team.

In 2025, an independent impact evaluation was commissioned, which has provided the basis for this Programme Completion Review, particularly at the outcome and impact level. It involved both document reviews and stakeholder interviews to provide a holistic view of the programme. It did recommend that future programming consider the use of outcome mapping and real-time feedback to improve the adaptability and therefore impact of the work.

Date of last narrative financial report	18/07/2025: DAI Annual Report / 19/04/2025: LAF Project completion report / 09/072025: NPA/ INKI Project completion report	Date of last audited annual statement	31/12/2024: OAG Audit report for MINECOFIN. FY 2023/24 / 03/09/2025: LAF Audit report / 25/08/2025: NPA/ INKI Audit report