Programme Completion Review
Title: TradeMark Africa (TMA) Rwanda Country Programme (RCP)
Final Programme Spend £ (full life): £25 million	Review Date:	June 2025
Programme Code: 204495	Start Date: December 2017	End Date: March 2025

Summary of Programme Performance
Year	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Programme Score	A	A	A	B	B	A	A	A
Residual Risk Exposure Rating	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/programme/GB-1-204495/documents
DevTracker Links to all logframe used during programme lifetime:	https://devtracker.fcdo.gov.uk/programme/GB-1-204495/documents

A. Summary and Overview (1-2 pages)
Description of the programme and what it has achieved [1/2 page]
Trademark Africa’s (TMA) Rwanda Country Programme (RCP) launched implementation of the Strategy 2 (S2) in December 2017. RCP had a budget of US$57.7million which was committed by donors at different times; FCDO was the largest donor, contributing £32 million, committed in December 2017. Belgium committed US$2.3 million in February 2018; USAID committed US$5 million in January 2018 and EU/IOM committed US$8.8 million in December 2018. The FCDO’s TMEA Rwanda programme budget, which funded the FCDO’s contribution to TMA S2, was initially £32m, however this was reduced to £25m in 2020 (see 2020/21 Annual Review for details).
The S2 programme aimed to contribute to reducing barriers to trade, improving business competitiveness and creating employment opportunities. The programme Memorandum of Understanding between TMA (then TMEA) and the Government of Rwanda (GoR) was officially signed in March 2018, providing a framework to kick start mobilisation and implementation of the proposed interventions. The programme was initially planned to run from July 2017 to June 2023. However, given the delayed commencement to December 2018 and other interruptions in implementation that mostly resulted from the COVID-19 pandemic, budget cuts, supply chain disruptions, regional conflicts and climate-related incidents, the programme received an extension to June 2025.
The RCP under S2 had 13 outputs, of which nine were earmarked to financing from FCDO. This programme completion review (PCR) focuses its assessment on these nine outputs. The programmes work on supporting SMEs for trade, improving customs efficiency, implementing crossover trade mechanisms, and supporting women in trade, were all delivered in line with expectations at baseline. Two components did not deliver in line with expectations at outset, the Harbour Trade Facilities and the National Trade policy alignment workstream.
Activities were aligned to Rwanda’s National Strategy for Transformation (NST 1) 2017–2024 priorities, especially the economic transformation pillar, RCP’s S2 was underpinned by two intervention pillars, namely:
Reducing barriers to trade: Through five outputs, TMA supported the GoR to develop water transport infrastructure with two harbour facilities at Rusizi (currently finalizing construction) and Rubavu (operational November 2024) on Lake Kivu. The programme improved the volume and efficiency of trade through improving the quality of infrastructure used in trade, training businesses and individuals who maintain their livelihoods through trade and raising standards and practices across Rwanda.
Improving business competitiveness for trade: Through four outputs TMA supported local enterprises to enhance their compliance with local and international standards and requirements, created market linkages to export markets, and facilitated advocacy to address challenges faced by local businesses. The programme was also instrumental in boosting cross-border trade by supporting operationalisation of cross-border markets and increasing participation of vulnerable groups in cross-border trade (CBT), especially women, people with disabilities (PWD) and young people.
Through various strategic interventions TMA has contributed to growth in total trade for Rwanda from $674 Million in 2017/18 to $6,766 Million in 2024/25. By focusing on facilitating regional trade, TMA contribution to export trade from Rwanda to EAC saw this trade grow from $193 Million in 2017/18 to $1048 Million in 2024/25. While support to overall export trade by TMA contributed to growth of Rwanda’s exports to non-EAC states from $721 Million in 2017/18 to $5719 Million in 2024/25.

Major lessons learned, evidence generated and recommendations [1/2 page]
Regional political climate is critical for programme success and commercial viability of investments. Protracted tensions and escalation of armed conflict between Rwanda and the DRC, as well as impasses with Uganda and Burundi affected project investments, especially in border towns.
Trade Efficiencies in Rwanda are co-dependent on neighbouring countries trade facilitation systems and infrastructure: Efficiency of CBT operations at for example Rubavu port largely rely on unmethodical systems on the DRC-side of the lake.
Adaptive contract management can unlock significant hurdles in project implementation. In uncertain times, flexibilities in contract design and management are necessary to ensure projects remain adaptive to contexts.
Automation of processes contributes to compliance: Digitisation of processes reduces costs of doing business and lessens time of processes. As a spin-off of automation, increased compliance is seen in businesses because of eased engagement with concerned trade management systems and institutions.
Enhanced sustainability by leveraging organisations’ own resources works: In addition to TAs provided to support systems’ development, most integration and upgrades used staff in public institutions to work closely with TAs. This contributed to enhanced technical capacities and ensured staff are capable of system maintenance in the long run.
TA to public institutions focusing on delivery of policies and strategies or policy influencing that require approval of entities not in control of supported MDAs is not as straightforward as development programmes anticipate. Diagnostic studies and PEAs are necessary to understand how change happens.
Market systems approach to support businesses enhances competitiveness and sustainability: Support to value chains development rather than individual firms and market linkages indicates more effectiveness and sustainable results.
Focus on vulnerability enhances inclusive trade: Support to vulnerable and groups most at risk such as youth and people with disabilities demonstrates wider impact regarding job creation as opposed to solely focusing on women in trade.

How this report was conducted [1 paragraph]
This PCR was conducted by an independent evaluator and the British High Commission Kigali Green Growth Team in May and June 2025. The review focused on nine FCDO-supported outputs delivered by TMA’s RCP from December 2018 to June 2025. Data was collected through detailed review of programme documents including but not limited to all annual review reports, annual reports, the business case and project progress reports. For outputs that were still active over the last two years, stakeholder consultations were conducted. The consultations focused on the harbour facilities, the Kigali wholesale market for fresh produce and women in cross-border trade projects. For the other projects, where data was not readily available, virtual consultations were conducted with stakeholders in implementing partner institutions.

Actions following approval of this report [1-2 paragraphs].
TMA provide final audit report within 18 months following programme end date to determine whether all FCDO funds have been spent and used as intended before the project can be fully considered closed.
## B: Theory of Change and Outcome Assessment (1-2 pages)

At the outcome level TMEA has two outcomes, with five outcome indicators applicable to Rwanda. The table below summarises the outcomes, there is additional detail on each in Annex B. The programme is mainly on track although significant challenges have affected delivery of the infrastructure projects over the years.

Outcome one “reduced barriers to trade” has two outcome indicators and is assessed as partially on track. Outcome two “business competitiveness” has three outcome indicators but due to lack of sufficient data, progress towards the outcome is assessed as partially on track.

	Starting point	Final result
Budget	£25 million	Final spend £24.2 million
Timeframe	July 2017	June 2025
Outcome 1: Reduced Barriers to trade	Outcome indicator 1.a “Cost to trade in goods (per twenty-foot equivalent unit (TEU)) aggregated across nodes, routes and process points of TMA intervention (calculated as weighted average and variability of cost) (disaggregated by imports/exports and route)”: / Baseline 2021: / Central corridor: US$ 5,418 / Norther corridor: US$ 5,711	End Project Target 2023: / 10% reduction in the weighted average trade costs of key trade routes that support Rwanda / Actual 2023 Achieved: / Central corridor: US$ 3,480 / Norther corridor: US$ 2,700 (US$ 2.25/Km)
	Outcome indicator 1.b “Aggregate time (per TEU) to traverse determined nodes, routes and process points after discharge of cargo from a vessel to its final delivery at the inland destination for import cargo; or from acceptance by carrier to when the cargo is loaded on board a ship for export cargo (disaggregated by imports/exports and route”): / Baseline 2021: / Central corridor: 4.3 days / Norther corridor: 5.5 days	End Project Target 2023: / 15% reduction in weighted average trade times of key trade routes that support Rwanda / Actual 2024 Not Achieved: / Central corridor: 4.1 days / Norther corridor: 5.4 days (129 Hours)
Outcome 2: Business competitiveness	Outcome indicator 2.a “Change in total trade in goods in selected value chains in Rwanda (disaggregated by exports and domestic trade)”: / Baseline 2021: …… / No baseline due to insufficient data	End Project Target 2023: / $2m / Actual 2023 Achieved: / $3m in recorded Sales
	Outcome indicator 2.b. “Total value of additional investment leveraged in Rwanda as a result of TMEA funding (disaggregated by public investment, private investment, project)”: / Baseline 2017: / No Baseline set due to insufficient data	End Project Target 2023: / $62m / Actual 2023 Achieved: / Through the EDP investments $3m have been realised and an additional $2.1m was in the pipeline by end of 2022/23. / $30m has been leveraged for the development of the Rwamagana Industrial Park which $30m has been leveraged for the development of Kigali Wholesale Market..
	Outcome indicator 2.c. “Total number of new jobs created in Rwanda (disaggregated by direct, indirect, gender of jobholder, disability)”. / Baseline 2020: / 0 jobs created in Trade Logistics Clusters	End Project Target 2023: / 11,699 jobs created (YiW) / Status 2025 Not Achieved: / 8,471 jobs created (YiW)

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]
While changes in the outcome indicators cannot be wholly attributed to the programme activities. These indicators demonstrate a significant reduction in the cost and barriers to trade for Rwanda. Of which the programme has played a significant role.
TMA’s contribution to reduced barriers to trade (outcome 1) is primarily measured through the cost and time reductions of moving goods to and from Rwanda (Kigali) through the ports at Dar es salaam via the central corridor and Mombasa via the Northern corridor. As summarised in the table above, from the baseline in 2021 to when most of the FCDO funded outputs concluded in 2022/23, the cost and time to move goods along the central corridor dropped by 36 percent and 5 percent respectively. While the cost and time along the Northern corridor dropped by 53 percent and 2 percent respectively. Based on these reductions TMA has been able to exceed its target of 10 percent cost reductions but did not meet the target of cutting time by 15 percent. These improvements in trade efficiencies are primarily attributed to TMA’s investments in automation of trade management systems and facilitation of processes that have aimed to address non-tariff barriers (NTBs) such as monotonous check points along the corridors. Notably, in S2 the RCP has not invested much in infrastructure development along the corridor, however other country programmes such as in Tanzania and Kenya have implemented key projects, especially at their ports that have substantially contributed to the observed cost and time reductions along both corridors. However, the RCP investments from S1, especially the one stop border posts (OSBPs) are assessed as key contributors to these reduced barriers to trade. Additionally, as summarised in annex 1, all intermediate outcome indicators that align fully with RCP interventions demonstrate the positive performance seen at the outcome level. For example the 65% reduction in time it takes to test and issue certificates of conformity to exporters, the 24% reduction in cost of border compliance and the removal of 45% of restrictions to movement of goods, all reflect the contribution of the RCP to reduced barriers to trade mostly through outputs 1.2.1: standards, 1.3.2:Trade systems and 1.3.3:customs efficiencies that were all FCDO funded.
There is limited clarity on the extent to which TMA contributed to the business competitiveness outcomes. This is firstly because most baselines were benchmarked at zero and no final year targets are documented for two of the outcome indicators, apart from job creation which missed the target by 28%. This was due to insufficient data at programme outset, meaning no baseline could be established. Moreover, the target for job creation in the logframe is drawn from strategy three interventions. However, there is evidence that TMA has made substantial contributions, both financial and through training inputs, to enterprises benefiting from the Export Development programme (EDP) where such firms exported goods worth over USD 2 million and accessed market deals worth over USD 2 million. Also, women in trade (WIT) interventions have benefited several women-owned businesses, especially those in cross-border trade and others organised under women’s umbrella organisation. Nevertheless, this outcome was affected severely by budget cuts that did not allow for the programme to venture into planned investment catalyst projects such as the work in the trade and logistics clusters in special economic zones that would have made a huge difference for outcomes such as job creation. Also, relevant projects such as the Kigali wholesale market for fresh produce (KWFP) were substantially delayed by changes in GoR policy positions, not allowing for investments to materialise. This has meant that most of the substantial contributions of the programme went to interventions like pre-feasibility studies and project plans for industrial parks in Bugesera and Rwamagana, and preparatory works for the wholesale market which have all not materialised by completion of the programme.
Although performance and progress to outcomes was affected by budget cuts during implementation, TMA has been very intentional about continuity and ensuring responsible conclusion of projects. The programme has managed to onboard new development partners towards the tail end of the S2. The likes of Finland and Mastercard Foundation have enabled the programme to continue strategic interventions in areas such as women in trade and other business competitiveness activities. This is not only ensuring sustainability but also provides good value for money (VfM) to the investments made by FCDO
The programme’s VfM mostly accrues from TMA not only focusing on addressing trade challenges but also ensuring equity in its deliverables, sustainability through for instance tackling climate-resilience of its projects and partnering with public institutions in design and delivery. Although TMA is primarily seen as a trade facilitator, the programme touches all components relevant to Rwanda’s national priorities under economic transformation, focusing on boosting domestic, regional and international trade. This was complemented by high-level legal and regulatory work through support to policy and national strategy development. To ensure businesses can navigate these regulatory frameworks, TMA intervened in ensuring public authorities responsible for facilitation of trade and transit have the capabilities to effectively deliver the services needed to trade. This synergistic approach to delivering outcomes has provided good value for money.
Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]
TMA’s overarching goals are regional. S2’s goal was to contribute to sustainable inclusive prosperity in Eastern and Southern Africa through increased trade by reducing barriers to trade and improving business competitiveness. The overarching impact has remained unchanged from the business case across TMA, including the RCP. The rationale of change was that increased intra and extra regional trade would increase exports, mostly, which would in turn contribute to GDP growth, employment creation, additional net government revenue and lift Rwandans out of poverty.
Following commencement of the RCP in December 2018, the programme’s theory of change (ToC) has undergone two iterations, with the first in 2019/20 and the second in 2020/21. The first alteration to the ToC in business case included a reduction from eight to six intermediate outcomes, contributing to the two unchanged outcomes. As part of this change, two intermediate outcomes (Trade Logistic Clusters (TLCs) and Public-Private Dialogue (PPD)) were reformulated as enablers of two outcomes in the ToC (trade and competitiveness). The changes in the ToC are illustrated in Annex 2. The second change to the ToC in 2020/21 involved the introduction of a new intermediate outcome that introduced the concept of safe trade to address the challenges posed by the COVID-19 pandemic.
With the change in ToC results at outcome level, various changes were made to the outcome and impact indicators from the programme’s business case. As shown in the Annex 3 the changes were at all results’ levels. At impact level, the indicator measuring change in government revenue was replaced with one measuring TMA’s contribution to climate change. Outcome 1 indicators were not changed but refined for more clarity and disaggregated to give more detail of trade costs, volumes and transit times. Outcome 2 indicators were also refined to enhance clarity and introduce new variables to be monitored, such as changes in incomes and job creation that were not included in the business case.
## C: Detailed Output Assessment

Output RW 1.1.2		Harbour facilities for Rubavu, Rusizi, Karongi and Nkora constructed
Output Score		B
Impact weighting (%)		10%	Impact weighting revised since last AR?		No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
RW 1.1.2.a. Progress towards completion of harbour facilities	1.MOU signed with RTDA.		100% completion of the Rusizi harbour facility (by March 2025)	Achievement as of June 2025 / Moderately did not meet expectation: Rusizi port construction was at 88.23% completion as of end May, with substantial completion slated for July 30, 2025.
	2.Procurement of the Supervision consultancy completed.		No final year target as a onetime procurement	Achievement as of June 2025 / Achieved / The consultant was hired in 2019/20 and is currently still operating under contract.
	3.Procurement of the transaction advisory services completed.		No final year target as a one time procurement	Achievement as of June 2025 / Achieved / No milestone was set for the final year. However, the transaction advisor was hired in 2019/20 and his contract expired in this year.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Output Status: FCDO Components Concluded but other Donors Contributions Ongoing
Final year milestones: 2024/25
Development of transport and trade connectivity on Lake Kivu in Western Rwanda, shared with the DRC, is a strategic national priority for the GoR. TMA initiated the project to construct harbour facilities in 2018, with TMA funding initially going to developments in only Rubavu and Rusizi districts. The scope was increased by the GoR in 2020 to include ports in Karongi and Nkora in Rutsiro districts when additional funding was secured from Netherlands Enterprise Agency (Invest International). This project is part of the broader agenda to develop a passenger and cargo transport system on the lake capable of high-speed access between main Rwandan trading centres in Rubavu, Rusizi, Karongi and Rutsiro. The project will ultimately facilitate cross-border trade (CBT) across Lake Kivu to DRC. The project is funded by FCDO (50%), Invest international (45%) and GoR (5).
Output 1.1.2 has one milestone for this final year 2024/25, which moderately did not meet expectation and is therefore scored B.
Although the initial financing in the business case was for the four ports mentioned above, in 2022 the scope was reduced to two ports (Rusizi and Rubavu). This is mostly attributed to escalation in costs of the ports from USD 24.1m to USD 38m due to unforeseen geo-technical challenges that increased the increased costs for Rusizi and Rubavu ports. A consultant was hired to re-run the original cost benefit analysis for two ports instead of four. The analysis showed that delivering two ports still represented vfm, and the programme proceeded with two ports. The GoR is currently in negotiations with development partners including Invest International for the financing of the other two ports with Government stakeholders consulted optimistic for negotiations to conclude in the next financial year 2025/26.
Following completion of Rubavu Port on 01 November 2023 and hand over on 01 December 2023, a pilot phase operated by the Rwanda Transport Development Agency (RTDA) was launched in June 2024. This was followed by an interim operations phase that commenced in April 2025 run by MAGERWA, hired by RTDA. This decision to use MAGERWA as the port operator is largely because the procurement of a private ports’ operator is still on-going. Status updates indicate the process is in its final stages of selection and negotiations at the Rwanda Development Board (RDB), responsible for initiation and approval of Public Private Partnership (PPP) models for government-owned assets.
[note] MAGERWA is a government-owned warehouse and logistics centre responsible for the import, storage, and distribution of goods, helping to streamline customs procedures and improve the efficiency of goods movement within the country. It plays a key role in facilitating trade and ensuring that imported goods are handled securely and efficiently in Rwanda.
Regarding usage of the completed harbour facilities at Rubavu, traffic statistics indicate that over the first two months of the interim phase the port was used by 1,203 trucks and 51 vessels that shipped over 23,989 tonnes of cargo. The human traffic at the port is still very low with no more than 20 persons per week, attributed mostly due to the under-development of passenger water transport facilities.
[note] April ‘25: 659 trucks; 24 vessels; 12,407 tons. May ’25: 544 trucks; 27 vessels; 11,581 tons
Works at Rusizi port commenced in July 2023 with almost 7 – 8 months spent on soil improvement works. Substantive construction commenced in January 2024 with a target to complete by the end of the year. However, due to various issues including prolonged rainy seasons and contractor cashflow constraints, among others, project completion has been significantly delayed, with anticipated substantial completion (96.52%) date set for 30 July 2025. Stakeholders anticipate port operations to commence in the last quarter of 2025.
 TMA were extremely proactive and flexible by approving the decision to make payments directly to suppliers of critical materials, once the issue of cashflow with the contractor arose. This eliminated further delays and has expedited near completion of the Rusizi port construction.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Traffic at the ports will be largely affected and could be determined by the port usage tariffs. During the Pilot operations phase run by RTDA, operators report daily traffic averages of 40 trucks per day and handling over 35 tonnes of cargo daily. However, following commencement of the interim phase, new tariffs approved by MINECOFIN were introduced, and there has been a noticeable drop in traffic of approximately 50%. This is mostly attributed to the fact that most of the users, especially cement exporters, were used to using under-developed water transport facilities for free and are yet to appreciate the value-add of the port.
Regional political climate is critical for the success and commercial viability of the ports. Protracted tensions and escalation of armed conflict between Rwanda and the DRC did contribute to reduction of traffic at the port in the latter half of 2024. However, this has substantially subsided in the first half of 2025 given the improved relations with the leadership in the Lake Kivu shoreline areas on the DRC side.
Efficiencies of the ports on the Rwanda side of lake Kivu are co-dependent on the DRC side’s trade facilitation systems and infrastructure: Efficiency of current cross-border trade operations at Rubavu port largely rely on unplanned and unnotified incoming vessels from the DRC-side of the lake. Similarly, port users (exporters) consulted explain how clearing of goods on the DRC side of lake Kivu is quite tedious and disincentivise use of water transport as a preferred mode of exporting and importing goods.
Adaptive contract management can unlock significant hurdles in contract execution. TMA worked with the contractor and introduced the element of paying the suppliers and other sub-contractors directly on the Rusizi Port project. This relieved the cash strapped contractor of the burdens of contract delays.
Recommendations
- Given the limited awareness and low appreciation of the value proposition presented by the harbour facilities in Rwanda’s business community, especially those involved in export of goods, there is need for TMA to invest in communication and marketing strategies targeted at especially medium and large exporters, such as those in the industrial parks and special economic zones.
- For TMA to further development of water transport on Lake Kivu should adopt a regional approach to address cross-border trade inefficiencies and leverage exports and imports from both countries. This development would not only optimise the current investments of in-land water transport but also enhance the commercial viability of the concluded and future harbour facilities on lake Kivu.
- For future complex and novel projects, especially in infrastructure, prior to commencement of financing, FCDO should execute comprehensive appraisal of implementing partners technical expertise, staffing and other necessary institutional capacities required to effectively and efficiently plan and deliver the projects.

Output RW 1.2.1	Standards and conformity assessment services for key exports strengthened and availed to SMEs
Output Score	A+
Impact weighting (%)	12%	Impact weighting revised since last AR?			No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
RW 1.2.1.a Upgrade of RSB Lab Information Management System (LIMS)	7 Days		Testing turnaround time of samples sent to Rwanda Standards Board (RSB) laboratory reduced from 7 days to 6 days (2020/21)	Achievement as of June 2021 / Data Not Available: Although the LIMS is fully operational, the turnaround time was not yet estimated by the end of the project. A ToR for a “baseline and endline data collection for ICT for trade projects” in Rwanda was developed to respond to this need.
RW 1.2.1.b. Number of total trained traders through TMEA support on priority standards. (disaggregated by gender)	Standards and SPS PAR approved		Additional 15 traders (cumulative 80) trained on priority standards (ISO 22000 and RS HACCP 184) in selected categories (D, E & G).	Achievement as of June 2023 / Substantially exceeded expectations. An additional 38 traders (cumulatively 118) trained on priority standards (category D, E & G). / The number of traders (Enterprises) trained during this phase of the project was 67 of which 13 were women led/owned and 54 were male led/owned
RW 1.2.1.c. Percentage of total trained traders through TMEA support on priority standards certified (disaggregated by gender).	Standards and SPS PAR approved		25% additional of total trained (45% cumulative) traders certified on priority standards. (Category D, E & G)	Achievement as of June 2023 / Substantially exceeded expectations. 47% (18) additional of total trained (6 women owned/led 12 Male led/owned) (92% cumulative) traders certified on priority standards (category D, E & G).
RW 1.2.1.d. Number of total Independent Local Consultants trained through TMEA support on priority standards. (disaggregated by gender).			30 enterprises supported by local consultants to attain high priority standards	Achievement as of June 2023 / Moderately exceeded expectations. 38 enterprises supported by 8 local consultants to attain high priority standards

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2022/23
Final year milestones: 22/23
This output focused on TMA’s support to the Rwanda Standards Board (RSB), primarily towards strengthening the organisation’s capacity in handling standards and certification to enable timely and quality service delivery to exporters and producers. Two projects were implemented. The LIMS upgrade project interfaced RSB’s laboratory instruments and integrated with the MIS certification and quality assurance units. The other project supported SMEs in food value chains to acquire capacities and certification in food safety. This was initially funded by FCDO. Government of Finland provided funding for completion following FCDO budget cuts in 2020. For its final year, the output 1.2.1 had three milestones. All substantially exceeded expectation scoring an A+.
The LIMS project was concluded in June 2021 while the support to SMEs in food chains to acquire capacity and certification in food safety concluded in June 2023. The second project benefited young professionals, working select SMEs to achieve certification in food safety. Also, local consultants were trained to support SMEs and RSB staff were trained in the related standards.
This project also involved disseminating standards for 3 value chains (animal feeds, catering, and transport/storage of perishable food commodities). Training in food safety management standards was oversubscribed, with 38 trainees (against a target of 15). Following the capacity building of enterprises 16 catering firms and two feed processing enterprises received certification on HACCP and/or ISO certification.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Support to staff training for compliance to standards enabled at least 18 firms obtain the required certifications in food safety and others. However, leaving business owners out of the training and sensitisation process affects traction and rate of achievement of targeted outcomes
Recommendations
Standards and conformity support needs to be widened to focus on support to compliance with continental and global standards rather than only national requirements. This direction will enhance focus on export markets and regional trade in line with TMA and FCDO’s broader visions and mandates.

Output RW 1.3.2		Integrated Trade Management Systems (ITMS) established
Output Score		A
Impact weighting (%)		6%	Impact weighting revised since last AR?			No

Output Indicator	Starting Target			Final Logframe Target	Final Result Achieved
RW 1.3.2.a. Progress towards Rwanda Electronic Single Window Phase 2 (ReSW II) operationalization.	1. The ReSW II Single Transaction Point Portal: 0 % progress towards completion.			RW 1.3.2.a.i. The ReSW II Single Transaction Point Portal (STP) and the ReSW II Commodity-Based Single Application Services Rolled Out and Operational.	Achievement as of June 2022 / Moderately did not exceed expectations: The ReSW II STP was developed but was not operational as integration of institutions was not yet complete.
	2. The ReSW II Commodity-Based Single Application Services: 8% progress towards completion (Concept note, Financial Agreement and project Charter, Mand E-Process mapping and baselines and Quarterly results reporting).			RW 1.3.2 a.ii. At least 10 Stakeholders’ Sensitization/Training Engagements Conducted	Achievement as of June 2022 / Met expectations: More than 10 stakeholders from institutions integrated in the ReSW STP have been trained in use of the system.
	3. The ReSW II Cargo Community System: 0% progress towards completion			No final year targets set	No progress reported since completion of the scoping and preliminary assessments for the ReSW II commodity-based single application service
RW 1.3.2.b. Number of additional SWIFT Portals operationalization for Government Trade Agencies - RURA and Traders' Online Portal for RSB	1. NAEB II at 5% progress towards completion (A concept note /PAR, Financial agreement and project charter Quarterly result reporting).			RW 1.3.2.b.i. 1 SWIFT at 100% progress towards completion (rolled out and operational) – NAEB.	Achievement as of June 2022 / Met expectations: The NAEB swift was developed, rolled out and operationalised.
	2. RSB II at 3% progress towards completion (A concept note /PAR, Quarterly reporting).			RW1.3.2.b.iii RSB – 30% reduction in time by traders to acquire licences/ permits/ certificates	Achievement as of June 2022 / Substantially exceeded expectations: The RSB II Swift rolled out in 2020/21 is fully operational and reportedly reduced transaction times by 80%.
	3. RURA at 2% progress towards completion (A concept note /PAR)			RW 1.3.2.b.ii 1 SWIFT at 100% progress towards completion (rolled out and operational) – RURA	Achievement as of June 2022 / Met expectations: The RURA license convergence system was rolled out and is fully operational.
	4. RMB at 2% progress towards completion (A concept note /PAR).			No final year targets set	Due to budget constraints integration of the Rwanda Mining Board (RMB) minerals export management systems was not included in the ITMS projects.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2021/22
Final year milestones (21/22)
The purpose of the ITMS is to enable real-time exchange of information between public agencies involved in trade-related transactions to reduce time and costs of trade. In the RCP, this focuses on the Rwanda Revenue Authority (RRA), Rwanda Utilities Regulatory Agency (RURA), RSB and National Agriculture Export Board (NAEB). FCDO and Finland funded the ReSW II and RURA while USAID funds the other SWIFTs.
The output 1.3.2 had five milestones in its final year, 2022. Four milestones met the final year targets, and one narrowly missed the target. The output is Scored A as it mostly met expectations.
The ReSW provides a single sign-on that enables submission of a single declaration containing all information required by the various agencies responsible for facilitating export and import trade for Rwanda. The ReSW II integrated four key agencies’ client-services entry points into a web-based single transaction point (STP). The STP was completed along with integration of RURA and RSB systems. However, the NAEB and RICA systems were not fully integrated by project end. Delayed integration was mostly attributed to the development of a parallel Agriculture Inspection and Certification Support System (ICSS) by the Ministry of Agriculture and Animal Resources (MINAGRI). The ICSS created a single portal for all agriculture sector inspection and certification services that inherently includes the NAEB and RICA systems. Nevertheless, stakeholder sensitisation and training for users of the STP reached at least 10 stakeholders.
The RSB II SWIFT developed in 2021 was upgraded by integration of RDB’s business registration system. The SWIFT was launched in 2022/23 after project conclusion. The final evaluation of the RSB II SWIFT indicates that since its launch, time to purchase Rwanda standards dropped by 67% from 21 to 4.1 hours, application for laboratory designation dropped by 79% from 9.1 to 1.9 hours, and application for metrology licenses dropped by 87% from 10.2 to 1.3 hours.
The NAEB SWIFT was launched in 2021 and is fully functional for all exporters’ licenses, certificates of origin and required analysis. Only integration to the ReSW STP remained pending by the end of the project. The NAEB swift contributed to time reductions for certificate application by 40% from 5 to 4 hours, commodity inspection by 75% from 4 to 1 hour, approval and issuance of certificates by 95% from 4 hours to 12 minutes.
RURA convergence license management system (CLMS) went live in 2020/21 and is operational. The CLMS digitised various services including online access to licences, inspection, enforcement of electronic import permits and consumer complaints. Further enhancements to the system in the final year integrated mobile money payment services, RRA customs systems, and AC Groups public transport fare system for collection of regulatory fees and a statistics reporting module was developed. The CLMS increased digitisation of RURA’s services from 30% to 85%. The digitisation resulted in an 88% reduction in time taken to acquire a licence, certificate or permit from 16 to 2 hours. Additionally, the cost of acquiring certification and permit services dropped by 83% from an average of 36 to 6 USD.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Automation of processes at RURA contributing to compliance: The digitisation of licensing processes and other services has resulted in an observed increase in the numbers of providers of utilities such as public transport now complying to all RURA requirements for operation. The increased compliance is mostly explained through the eased processes as well as increased transparency and accountability that has facilitated enforcement by RURA, for example, it is now easier to track service providers that have not renewed their licenses or certificates of operation, which was difficult through manual processes.
Enhancing sustainability by using organisations’ resources: Apart from technical advisors that were provided in some institutions to support system development processes, most integration to the ReSW II has used staff in public institutions to work closely with some consultants throughout the process. This has not only contributed to enhancing public institutions technical capacities, but also ensured staff are capable of system maintenance in the long run. This is a sustainable approach to technical assistance.
Recommendations
Any future support to trade facilitation should prioritise leveraging of digitisation and other emerging technologies such as artificial intelligence (AI) if they are to add substantial value to existing trade facilitating institutions and processes. Moreover, these systems should focus mostly on digitisation of regional interfacing systems rather than in-ward focused national systems, in the interest of boosting regional integration and continental trade.

Output RW 1.3.3		Customs efficiency enhancements implemented
Output Score		A
Impact weighting (%)		5%	Impact weighting revised since last AR?			No

Output Indicator	Starting Target			Final Logframe Target	Final Result Achieved
RW 1.3.3.a. Progress towards implementation of Customs efficiency enhancements.	1. CMS Upgrade at 5% progress towards completion (CN/PAR; FA/PC; Quarterly result reporting)			No final year target as Output completed 2022	Achievement as of June 2022 / Met Expectations / All planned upgrades to the customs management system were completed and are fully operational including: AEO II, API, e-Manifest and CDM
	2. RECTS II at 2% progress towards completion (Needs Assessment Report)			No final year target	No progress reported on the phase II of the electronic cargo tracking system.
	3. AEO II at 3% progress towards completion (FA/PC; Quarterly result reporting)			RW 1.3.3.a. iii. Authorised Economic Operators (AEO) digitalisation development completed and operationalised	Achievement as of June 2022 / Met expectations: The AEO II digitisation was completed and is operational.
				RW 1.3.3.a. iv. At least 4 Stakeholders Sensitization engagements Conducted for AEO II and Advance Passenger Information (API) Modules	Achievement as of June 2022 / Met expectations: Following operationalisation of the AEO II and API modules was integrated into the single transaction portal and activated. Trainings were completed for relevant stakeholders.
	4. Advance Ruling (AR) at 3% progress towards completion (FA/PC; Quarterly Results Reporting)			No final year target	Achievement as of June 2022 / Met Expectations: The AR and International Air Transport Association (IATA) e-manifest modules were complete and are operational.
	5. Advance Passenger Information at 3% progress towards completion (FA/PC; Quarterly result reporting).			RW 1.3.3.a. ii. Advance Passenger information (API) module completed and operationalised.	Achievement as of June 2022 / Met expectations: The API module was operationalised on the STP and is only activated for flagged passengers.
	6. SEZ Digitization at 2% progress towards completion (FA/PC; Quarterly result reporting)			No final year target	Achievement as of June 2022 / The project reports the SEZ module as completed but no details on operationalisation are available.
	7. Commodity Description Manual at 3% progress towards completion (FA/PC; Quarterly result reporting)			RW 1.3.3.a.i. Commodity Description Manual (CDM) developed.	Achievement as of June 2022 / Met expectations: The commodity description manual was developed and is available online.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2021/22
Final year milestones (21/22)
Upgrade of the Customs Management System (CMS) ASYCUDA at the Rwanda Revenue Authority (RRA) was the main project under this output. The CMS continues to be part of RRA’s broader ambitions of automating all its processes and customer service interfaces. TMA targeted enhancing customs efficiency by rendering customs transactions more predictable and proactive and reducing point of entry formalities conducted by RRA. The targeted processes this year included AEO II, API, AR and the IATA e-Manifest. This output was funded by FCDO and the Government of Finland.
The output 1.3.3 had four milestones in its final year, 2022. All four milestones met the final year targets. The output is Scored A as it met expectations.
The API, AEO and Commodity description manual development and operationalisation were completed in 2022. Following operationalisation of the API on the STP, the Directorate General of Immigration and Emigration (DGIE) raised concerns around confidentiality of passenger information. A decision was reached to only provide flagged passenger information to the API system. RRA was developing the business rules for passenger selection in the API by the completion of the project. This has since been finalised and is being used in operationalisation of the API. For all other modules in the CMS, training and sensitisation workshops were completed for all types of system administrators and users including exporters and clearing agents.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Effective and wider stakeholder engagement prioritisation from project conceptualisation: Considerable project implementation time was lost mostly due to lack of clarity and/or consensus between the public institutions involved in the trade systems integration process. This has highlighted and reemphasized the need for top level engagement from the on-set of projects to ensure and sustain commitment throughout development and operationalisation of IT projects.
Recommendations
See recommendation above under 1.3.2.

Output RW 1.4.1	Framework for the review, formulation and implementation of a responsive National Trade Policy developed and implemented
Output Score	B
Impact weighting (%)	10%		Impact weighting revised since last AR?			No

Output Indicator		Starting Target		Final Logframe Target	Final Result Achieved
RW 1.4.1.a. Progress towards alignment of national policies to EAC Commitments / (4% of total output weighting) / EoP milestone: Improved trade regulatory environment in Rwanda.		Trade Policy PAR approved		National Trade Policy review completed by the TA and validated by MINICOM and other key project stakeholders.	Achievement as of June 2021 / Moderately did not meet expectation: The TA completed reviewing the National Trade Policy, but the final validation by MINICOM was not completed.
				National Export Strategy III completed by the TA and validated MINICOM and other key project stakeholders.	Achievement as of June 2021 / Moderately did not meet expectation: The TA completed review of the National Export Strategy III, but the final validation by MINICOM was not completed.
				Industrial Policy completed by the TA and validated by MINICOM and other key project stakeholders.	Achievement as of June 2021 / Moderately did not meet expectation: The TA completed review of the draft industrial development policy for Rwanda, but the final validation by MINICOM was not completed.
RW 1.4.1.b. Progress towards implementation of selected WTO TFA project components funded by TMEA (addressing Category C measures) / (4% of output weight)		5 NTFC Project proposals approved		30% implementation of selected TMEA-funded WTO TFA project components (addressing Category C measures) by June 2021 (i.e., enquiry points – TA for the enquiry point hired)	Achievement as of June 2021 / Moderately did not meet expectation: Completed WTO TFA Category C measures supported by the programme including operationalisation of AR and the one stop centre enquiry point, as well as training of the joint risk management committee (JRMC). Hiring of a TA for the enquiry point was not achieved due to budget cuts.
				AR: Procedure manual for AR developed; 2 awareness campaigns conducted on AR for traders and clearing agents.	Achievement as of June 2021 / Met expectation: An AR procedures manual and training user manual were produced. Two awareness raising sessions were conducted with importers, manufacturers, freight forwarders, NTFC, RRA and members of RWAFFA.
RW 1.4.1.c. Number of Young Professionals (YPs) Graduates recruited and coached that are demonstrating improved readiness capability to support the mainstream functions of MINICOM and RDB - in the areas of trade and industry. / (2% of total output weighting).		Young Professionals Program (YPP) Terms of Reference Completed		85% of TMEA supported YPs in MINICOM and RDB demonstrate improved capacity readiness through capacity improvement evaluation.	Achievement as of June 2021 / Met expectation: 83% of the young professionals situated in MINICOM and RDB demonstrated improved capacity readiness by scoring above the final assessment tool minimum score.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2020/21
Final year milestones (20/21)
The objective of this output was to support the GoR to adopt a trade policy framework of laws, regulations, international agreements and negotiation positions to enable domestic enterprises to achieve legally binding access to regional and international markets. Herein the project focused its support on the review and formulation of strategic documents, policies, and strengthening trade facilitation coordination structures and functions to especially deliver Rwanda’s trade facilitation commitments to the WTO. This output was funded by FCDO and Finland.
Output 1.4.1 had six milestones in its final year of support. Two met expectations while four moderately did not meet expectations. The output score is B because although most deliverables were met, external validation processes were not concluded by project completion, limiting full delivery, hence the ouput moderately did not meet expectations.
Reviews of the National Trade Policy, National Export Strategy III and Industrial Policy were completed by TMA-supported technical advisors (TA) at the Ministry of Trade and Industry (MINICOM). The two policies and one strategy were approved by a previous minister and permanent secretary, but validation was delayed. With the transition to a new minister and permanent secretary in 2022, the documents went through another review and approval process by the new senior management team. This review resulted in changes in strategic direction with decisions to merge and/or drop some of the policies. The industrialisation policy was approved by cabinet and adopted in 2024 after closure of the project, while the other two have since been merged into one trade policy that is still being drafted. Rwanda has not updated its trade policy since 2019.
WTO TFA projects were all implemented to address category C measures, including operationalisation and sensitisation of the AR module, establishment of a one stop centre enquiry point and training of the JRMC. However, the hiring of the TA planned for the enquiry point was not achieved because of budget cuts to the programme.
The YP project that concluded in 2022 benefited 12 young professionals assigned to MINICOM (4) and RDB (8). Following a final employment readiness assessment of the YPs at the end of the project, all eight YPs in RDB scored above the 70% pass mark, while of the four in MINICOM two scored above the pass mark and two failed. At least two of the YPs have since been retained in MINICOM with one coordinating the National Trade Facilitation Committee (NTFC) work and the other leading the trade in services work at the ministry. Another YP from RDB has since joined TMA as a project officer.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
TA to public institutions focused on delivery of policies and strategies that require approval of entities not in the control of the supported ministry, department or agencies (MDAs) is not necessarily as straightforward as development programmes anticipate. Basing on adoption of strategic documents as the measure of success of TA does not necessarily depict the programme contribution to intended objectives.
Recommendations
Future technical assistance could focus more on strengthening institutional functions, capacities, processes and structures, or any other elements within the control of the leadership collaborating directly with the programme. This TA should also prioritise regional, continental and other global trade facilitation aspects, such as the African Continental Free Trade area (AfCFTA) over local or national focused trade.

Output RW 2.1.1.	Export capacity at firm level upgraded (support through Market Linkages, Specialised business Development and standard certification)
Output Score	A
Impact weighting (%)	18%	Impact weighting revised since last AR?			Yes, revised downwards as the total weighting was exceeding 100%

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
RW 2.1.1.a. Progress towards linking targeted TMEA supported firms to export markets (Disaggregated by gender, sector, market) / (5% of total output weighting)	1. Standards PAR approved		40 local firms supported in accessing export markets (30% new exporters) by June 2023.	Achievement as of June 2023 / Met expectations. 40 local firms were supported in accessing export markets through the export development programme (EDP) (15% new exporters).
			4 more (8 cumulative) market linkages (such as sales mission, business match making, and B2B) concluded.	Achievement as of June 2023 / Met expectations. 8 cumulative market linkages concluded, resulted in realisation of export sales valued at 2,002,424 USD. With another 1,000,000 USD in the pipeline as of June 2023.
RW 2.1.1.b. Progress towards influencing Export oriented reforms through PPD platforms / (3% of total output weighting)	1. Procurement initiated (Tendering Launch)		No final year target	Achievement as of June 2022 / 12 technical and 4 high-level meetings organised and conducted by the Rwanda Private Sector federation (PSF) which identified and resolved 50% of issues affecting businesses.
	2. PPD PAR developed and approved		No final year target	Achievement as of June 2018 / A public private dialogue (PPD) project appraisal report (PAR) was developed and approved by the TMA board for implementation in strategy II.
RW 2.1.1.c Number of farmers demonstrating improved knowledge of best practises (such as Post harvest handling, warehousing & grain grading standards) / (1% of total output weighting)	1. Procurement initiated (Tendering Launch)		No final year target	Achievement as of June 2019 / Procurement of an export advisor to be deployed at RDB was launched and the consultant hired and served from 2019.
	2. PPD PAR developed and approved		No final year target	Achievement as of June 2022 / 11,473 farmers were trained in various post-harvest handling technologizing, warehousing and grain grading standards to enhance their competences and quality of produce.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2022/23
Final year milestones (22/23)
The objective of this output was to improve Rwandan firms’ capability to access export markets. The three projects under this output focused on enhancing the private sector’s competitiveness and capacity to generate higher quality and quantities of products and have better production processes. Projects under this output were funded by FCDO, Government of Finland and USAID.
The output 2.1.1 had two milestones in its final year, 2023. Both milestones met the final year targets. The output is Scored A as it met expectations.
The export development programme (EDP) aimed to enhance firm level export capacity and provide export market linkages to international and regional markets. By project completion the EDP has provided support 40 local firms in IT services, horticulture, agro-processing and emerging value chains. Of the 40, six were new to exports – which was lower than the target – while the others looked to scaling up. Companies had challenges in financing certification process gaps – only three companies had export quality certifications – and thus were slow to reach export-readiness by project completion. The EDP TA also provided technical and market access support to the enterprises. This included addressing the firms’ financing gaps, especially through linkages to banks and access to Rwanda Development Bank’s Economic Recovery Programme. The firms were also supported to design business plans and to prepare export plans. Consequently, exports valued at over USD 3 million were realised by companies supported by the project.
The integrating public-private sector dialogue (PPD) for trade and investment project implemented by PSF concluded in April 2022. The project aimed to influence policy reforms and compliance with common market protocols at provincial, national and regional levels. This was done mostly through enhancement of advocacy capacities of the private sector. In this final year of the project, 12 technical and 4 high-level dialogues were conducted to identify and resolve issues affecting business. Project records indicate 50% of the issues identified were resolved by project completion. Notably, the project also produced a research paper on the impact of COVID-19 on the economy in October 2021. As a result of adoption of the recommendations from this paper, the “support to PSF business Transaction Advisory Services for Economic Recovery” was established at PSF. TA services were provided to 505 enterprises by the end of the project.
The Rwanda staples project implemented by East Africa Exchange (EAX) was concluded in 2020. The project aimed to increase maize farmers’ productivity, quality of produce and EAX’s handling capacities. Over three years, the project trained a total of 11,473 farmers in good farming and post-harvest handling practices, electronic warehousing and standards. Three EAX warehouses were upgraded, two of which have since been certified. The project has also built a network of 16 extension agents across the country. Consequently, the project realised 26,000 MT traded through EAX, against a target of 15,000 MT. Grains worth Rwf 89 million were exported against a target of Rwf 14 million. Loans worth USD 60,000 were acquired by farmers against a target of USD 50,000. Most importantly, grain rejection rates dropped to almost zero by project end, indicating improved knowledge and good agricultural production and post-harvest handling practices among farmers.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Adaptive programming is critical for success. The projects under this output were affected extremely by the COVID-19 pandemic given most of the workstreams were export oriented. From blockages of inputs to challenges in accessing external markets due to disruptions in supply chains and movement restrictions, most of the work under this output had to be adapted to the context of implementation. This flexibility in programming enabled TMA to deliver on targets in complex situations.
Firm level support is required for enterprise competitiveness. Even with TMA moving to focus on upstream support to trade facilitation with a more continental focus, the need for strengthening competitiveness of local enterprises remains critical for trade to work and impact to be realised at the individual and national levels.
Recommendations
Future technical assistance should continue to include export development support, but more from a value chain and market systems approach rather than individual enterprise competitiveness and development. Focusing on for example value chains’ capacities to participate in the AfCFTA would be a more viable approach to ensuring upstream support to regional and continental trade facilitation systems, processes and infrastructure is leveraged by the enterprises in the supported value chains.

Output RW 2.1.2		Logistics hub upgraded
Output Score		A
Impact weighting (%)		15%	Impact weighting revised since last AR?			Revised downwards as the total was exceeding 100%

Output Indicator	Starting Target			Final Logframe Target	Final Result Achieved
RW 2.1.2.a. Progress towards upgrade of Logistics Hub	Procurement of industrial park development framework contractors concluded			Tender documents for construction of KWMFP developed and approved by the project steering committee.	Met expectations: Tender documents for the construction of KWMFP were developed and approved by the project steering committee.
				Environmental and Social Impact assessment for Kigali Wholesale Market concluded and approved by RDB & REMA	Met expectations: Environmental and Social Impact assessment for Kigali Wholesale Market was concluded and approved by RDB & REMA.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2022/23
Final year milestones (22/23)
This output focuses on support to development of industrial parks and related trade infrastructure under TMA’s Trade and Logistics Cluster (TLC) programme. Interventions include market and value chain analysis, regulatory assessments, feasibility studies, investor attraction and facility development. The interventions under this output were funded by FCDO and Invest International.
The output 2.1.2 had two milestones in its final year, 2023. Both milestones met the final year targets. The output is Scored A as it met expectations.
The Kigali wholesale market for fresh produce (KWMFP) is the only project that was retained under this output following funding cuts in 2020. The KWMFP aims to support fruits and horticulture supply chains by providing a modern facility that will enable product aggregation and linkages to regional and international markets. The TMA only supported preparatory studies and construction design of the market. From project support the concept design and detailed designs of the facility were completed. The market linkages studies were also conducted, and operational model options were provided and adopted by the project’s oversight committee.
Following reassignment of land that had been demarcated for the KWMFP in the Special Economic Zone (SEZ) by the GoR to another investment project, the project supported the redesign of the construction facility to fit the new premises. Given that the reassigned land was occupied by different landowners and had to be expropriated with the support of the City of Kigali, the project supported the finalisation of an environmental and social impact assessment (ESIA) and developed the land acquisition and resettlement plan (LARP) for the project affected persons in the area. Following completion of the project support, NAEB has been able to acquire 95 of the 101 plots on the site with all but one of the landowners compensated. The plots remain to be consolidated for the project site to be fully secured in line with the detailed designs.
The detailed design and project concept are currently being used by the GoR to mobilise resources from various development partners and potential investors. With a budget of $51.6M, the GoR has committed to finance 50% of the project and is looking to Invest International that is in the process of completing its project appraisal to finance the remaining balance. Stakeholders anticipate a financing decision to be reached in 2025/26.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Multi-stakeholder projects are prone to cross-sectoral coordination challengers. The KWMFP still faces coordination challenges as its objectives cut across various entities. MINICOM views it as trade project, MINAGRI considers it as a food security opportunity, while NAEB is largely focused on exports. Meanwhile the land acquisition process was managed by the CoK. To address this challenge, steering and technical committees have been created to bring together leadership and technicians, respectively, from all the concerned institutions. This has helped streamline communication and coordination, issues notwithstanding.
Recommendations
The KWMFP provides an opportunity for development partners whose international development policies are transitioning to prioritise “trade instead of aid”. The opportunity lies in leveraging this project as an investment to engage in the export markets by for example participating in operating the facility and linking producers and exporters to importers in foreign markets. There is currently very limited local expertise in operating this first of a kind facility in Rwanda.

Output RW 2.1.3		Cross-border market (CBM) constructed and operational
Output Score		A
Impact weighting (%)		8%	Impact weighting revised since last AR?		No

Output Indicator	Starting Target			Final Logframe Target	Final Result Achieved
RW 2.1.3.a. Progress towards operationalisation of CBM (Disaggregated by CBM)	1.2 CBMs constructed (Rusizi and Rubavu)			70% (100% cumulative from previous year) Karongi and 50% (100% cumulative from previous year) Burera operational. (Operational means having all operationalisation instruments ready: business plan, management model, roadmap, selection criteria).	Met expectation: All cumulative targets have been realised, with both Karongi and Burera CBMs fully operational with all the required operationalisation instruments validated and in place.
	2.Completion of Management model and business plan for Rubavu			Strategic Plan for the CBMs developed.	Met expectation: Strategic plans for the Burera, Karongi, Rubavu and Rusizi CBMs developed.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2020/21
Final year milestones (20/21)
The objective of this output was to enhance Cross Border Trade (CBT) between Rwanda and DRC. TMA supported construction of Rusizi and Rubavu CBMs in Strategy 1. Under Strategy 2, TMA supported operationalisation of Rusizi and Rubavu CBMs, as well as Karongi and Burera CBMs built under the WTO’s Enhanced Integrated Framework (EIF) programme. This project was financed by FCDO.
The CBMs are considered operational once all the supporting operationalisation instruments are availed to the four districts managing the operations of the markets in partnership with the private sector. By end of the project, all CBMs had received their business plans, management models, rental guides, management structure, ToR for CBM board and CBM managers, roadmap for operationalisation of CBMs, and selection criteria for occupants. Additionally, strategic plans for all CBMs were delivered as well as capacity building for CBM managers.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Although occupancy of Rubavu is at 100%, utilisation usually fluctuates to less than 40%: The low levels of activity were mostly attributed to the precarious situation at the border town of Rubavu. From the COVID-19 pandemic, through the 2021/22 volcanic eruption, to the protracted conflict between Rwanda and DRC, utilisation of the market facilities continues to be disrupted. Moreover, informal traders in surrounding trading centres continue to compete unfavourably with the market facilities.
Recommendations
Given the heavy investment in cross-border markets, any future programme support should focus on leveraging them as market infrastructure to support trade in specific value chains that represent each of the neighbouring countries’ niches.

Output RW 2.2.1	Women Traders capacity enhanced including skills and knowledge on Business development, STR and CBT awareness.
Output Score	A+
Impact weighting (%)	16%	Impact weighting revised since last AR?		Yes, revised downwards as the total was exceeding 100%

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
RW 2.2.1.a. % of WCBT demonstrating good knowledge on the STR and other CBT issues (E.g. Procedures and Processes, GBV, Traders' rights etc) disaggregated by sex and location. / (5% of the total output weighting).		Procurement for baseline study launched	Additional 2,405 CBT traders sensitized (cumulatively 13,289). 80% demonstrate good knowledge of STR and other CBT issues).	Exceeded expectations: Additional 5,410 CBT traders sensitised (cumulatively 16,314). 80% demonstrate good knowledge of STR and other CBT issues).
RW 2.2.1.b. Number of women traders/SMEs trained, disaggregated by training topic, by age; by urban/rural. / (4% of the total output weighting)			830 (380 F & 450M) Rusizi CBT traders trained on STR and other CBT issues	Exceeded expectations: 950 Women traders and 450 M spouses (Total 1,400) were trained on STR and other CBT issues.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score. [1/2 page]
Completed: 2022/23
Final year milestones: 22/23
This output aimed to make trade more inclusive by focussing on addressing challenges women face in participating in trade by improving the capacity of women to partake in trade through enabling access to information, finance, and markets; facilitating implementation of cross-border policies; capacity building in taxation and financial management; skills and business development across value chains; and tackling gender-based violence (GBV) and human rights challenges. This output is funded by FCDO, EU and USAID, with some regional funding from Canada.
The Women in cross-border trade (WICBT) project is implemented through a local women’s umbrella NGO, Profemme Twese Hamwe (PFTH). The project has worked on the trade environment, focusing on GoR policies and EAC trade regulations, business formalization e.g., financial literacy training, governance of cooperatives, business planning, and women’s rights and GBV. It covered nine districts on Rwanda’s borders, working with 143 cooperatives, with over 7,000 members.
Although FCDO support to WICBT concluded in 2023, TMA has continued to work in this area with the same implementing partners through other donor funded initiatives such as the VIBE programme financed by the Mastercard Foundation.
Visits to four women-owned cooperatives and one run by persons living with disabilities (PWDs) in Rubavu district indicate that following at least four years of continued disruption to their cross-border trade activities, there has been substantial improvement since March 2025. Some of the women’s businesses were adversely affected during the intensification of armed conflict in January 2025, with one of the supported cooperatives loosing programme-financed equipment in their tailoring workshops.
Following the de-escalation of violence in March, women traders report improvements to cross-border trade and increased revenues from sales. This is mostly attributed to the fact that many of the traders can now operate till 10:00PM, as opposed to 3:00PM as it was in previous years. Additionally, traders from Rwanda were previously restricted to Gahembe market in Goma but have since March been permitted to access any markets in the province. There is also reportedly cessation of persecution and bribery at the border posts since change of security and management on the DRC side at the border posts.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]
Market systems approach to support businesses enhances competitiveness and sustainability: All the women consulted confirm that PFTH and TMA supported them with the fundamentals to start their cooperatives and businesses three to four years ago. This focused on for example compliance with standards and awareness of local and regional trade policies. Thereafter they are now supporting them with more market access rather than production activities. Through interventions such as support to participate in trade fairs and linking them to large exporters through other facilities such as the VIBE programme. The women report to have been able to secure more markets for their processed goods and even been enabled to access credit facilities in financial institutions.
Focus on vulnerability enhances inclusive trade: Much as the WICBT component focused on inclusion of women in trade, the project also supported PWD to participate in CBT regardless of gender. PWD Cooperatives’ members consulted are mostly involved in the transport sector. They report having benefited substantially from the programme, especially through technical assistance in areas such as awareness of the simplified trade regime (STR), that enabled them to participate more effectively in CBT.
Recommendations
Future support to women and other vulnerable groups in cross-border trade should adopt a regional approach to facilitating trade across the neighbouring countries. The support should not focus on only one side of the border but should look to develop and strengthen linkages between markets across the borders and could reorient to focus outcomes on specific challenges between countries rather than only trade. For example, support to trade between Rwanda and DRC needs to integrate peacebuilding aspects for sustainable cross-border trade.

D: Value for Money [½ - 1 page]

VfM performance compared to the original VfM proposition in the business case

Design
Several elements of the programme’s design introduced inefficiencies that persisted throughout its lifecycle, ultimately weakening its overall Value for Money (VfM) proposition. The delivery model was caught between two competing principles. TradeMark East Africa (TMEA) approached the programme through the lens of its internal strategy, positioning itself as a coordinator among various donors contributing to a unified strategic vision. However, the programme’s management structures, reporting mechanisms, and funding arrangements were not aligned with this model.
For instance, there was no consistent or coherent management structure. The National Oversight Committee (NOC), intended to provide strategic direction and oversight, met irregularly and was often absent from the programme calendar for extended periods. Moreover, the NOC lacked the granularity required to effectively oversee FCDO-specific components. TMEA also failed to provide regular or formalised reporting on these components, limiting transparency and accountability.
The programme’s outputs lacked the necessary complementarity to justify their inclusion under a single programme umbrella. Best practice in programme design ensures that outputs are interlinked and mutually reinforcing, creating synergies that enhance overall impact. In contrast, this programme leaned toward a fragmented model, with multiple independent outputs delivering separate outcomes. This siloed approach diluted the programme’s strategic coherence and reduced its transformative potential.
Additionally, several outputs were affected by principal-agent problems. In multiple cases, FCDO funded the design phase while implementation was left to other donors. While this model can work in theory, in practice, the implementing donors were not engaged early enough. As a result, they often requested redesigns to align with their own priorities, leading to delays, inefficiencies, and duplication of effort.

Economy
The programme’s economy was significantly impacted by external shocks, particularly in the procurement of inputs for infrastructure projects such as the port construction under Output 1. The COVID-19 pandemic and the Russian invasion of Ukraine triggered global supply chain disruptions and input price inflation. TMEA and its downstream suppliers managed these shocks as effectively as possible, but the resulting cost increases altered the VfM proposition compared to the original Business Case.
A critical issue arose in the feasibility studies for the port construction. These studies significantly underestimated the depth of Lake Kivu, necessitating a fundamental redesign of the port infrastructure. This led to substantial cost overruns and project delays. This error could have been mitigated by sequencing the project timeline to allow for more rigorous and time-intensive feasibility assessments before committing to design and construction.

Efficiency
TMEA demonstrated efficiency in areas where it had direct control, particularly in delivering training and technical assistance. For example, training in food safety management standards was oversubscribed, indicating strong demand and effective delivery. Similarly, trade policy support was translated into tangible outputs, aided by TMEA’s strong relationships with the Government of Rwanda (GoR).
However, efficiency was compromised in areas requiring coordination among multiple partners. In components such as the Harbours and the Logistics Hub, partners were brought on board late in the process, resulting in suboptimal contractual arrangements. TMEA, acting simultaneously as portfolio overseer, donor, and implementing partner, struggled to adapt to the diverse requirements of different donors. This lack of role clarity contributed to inefficiencies and avoidable delays. A clearer delineation of responsibilities and better coordination mechanisms would have improved delivery.

Effectiveness
The programme was effective in delivering training and technical assistance. SMEs and women traders who received support reported reduced trading costs and improved ease of doing business. The logistics hub and trade management systems also contributed to lower transaction costs and reduced time burdens associated with cross-border trade.
However, the effectiveness of the harbour infrastructure remains uncertain. The conflict in eastern DRC has disrupted trade flows, undermining the VfM of the intervention. Moreover, the complementary ports on the DRC side, which were essential to the success of the Rwandan ports, have not materialised. This has limited the functionality and impact of the Rwandan infrastructure, regardless of the conflict.
While support to traders and SMEs was impactful, the programme’s failure to adopt a full value chain approach limited its potential. Treating firms in isolation, without integrating them into broader market systems or linking them to other programme interventions, reduced the scale and sustainability of impact.
Policy changes by the GoR also affected effectiveness. For example, land initially designated for the logistics hub was rezoned, and key agencies (NAEB and RICA) opted out of the digital systems initiative. These decisions undermined the programme’s ability to achieve cross-government efficiencies and economies of scale.

Equity
The programme performed well in targeting specific groups, particularly women traders. Component 12 successfully supported over 5,000 female traders, enhancing their economic agency and livelihoods. This is a notable achievement in terms of gender equity.
However, equity considerations were largely concentrated in this single output. It is unclear how equity was mainstreamed across the broader programme. For instance, the harbour infrastructure lacked targeted informational campaigns to raise awareness among local populations about potential benefits. This is reflected in the low human foot traffic—fewer than 20 persons per week—suggesting limited community engagement and uptake.
Furthermore, the programme lacked robust analysis of how national trade policies and export facilitation measures affected different population groups. Disaggregated reporting on who benefited from the interventions would have strengthened the equity dimension and informed more inclusive policy design.

E: Risk [½ - 2 pages]

The programme risk in the Business Case was assessed overall as moderate and aligned with FCDO’s risk appetite for this portfolio. Since then, the risk level has increased from moderate to major due to factors such as regional instability (particularly the conflict in the DRC) and procurement risks related to large-scale infrastructure inputs for port construction and ferry operations. These have heightened fiduciary and reputational risks, including social and environmental impact risks. The situation was further exacerbated by a challenging operating context, including a significant budget reduction, the Ukraine-Russia war which disrupted supply chains, and high inflation rates that increased input costs. However, the overall risk remains within BHC Kigali’s risk appetite and reflects the difficult operating environment in which the programme has been implemented.

The programme’s expected contextual, reputational, fiduciary, delivery, operational, and safeguarding risks were captured in the programme risk register, which was regularly updated on a quarterly basis following reviews of the TMEA risk register. The main risks were discussed quarterly at pre-National Oversight Committee (NOC) meetings and during the NOC itself. The four most significant residual risks (with moderate or high probability and/or impact) were: Regional instability, primarily due to the conflict in the DRC, affecting cross-border trade;
Delivery risk associated with delays in large procurements and the supply of materials for infrastructure projects, impacting implementation progress; Environmental and social safeguards risks linked to infrastructure projects, such as environmental damage or the potential abuse or exploitation of communities by contractors; Fiduciary risk stemming from exchange rate fluctuations and high inflation, which affected contractors’ cash flow and implementation progress.

These risks were addressed during implementation and were reduced to minor or moderate levels. However, the key risk that has materialised is the conflict in eastern DRC, which has disrupted cross-border trade and carries the potential to escalate into broader regional conflict. As a result, the overall residual risk remains major.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Delivery Performance

TMA’s work in Rwanda is delivered through the Rwanda Country Programme team, based in Kigali, with support from TMA’s regional team, based in Nairobi. At the start of Strategy 2 (S2), more processes were centralised, including finance, procurement, and technical oversight. The Rwanda team has been working in collaboration with the regional team on finances, procurement, and mobilisation. TMA Rwanda Country Programme implementation between 2019/20 and 2020/21 faced a number of challenges due to (i) COVID-19, (ii) budget reductions, (iii) the Russia-Ukraine conflict affecting global supply chains and causing procurement delays, and (iv) limited oversight by the regional team, which resulted in inefficiencies. These challenges led to significant delays that affected project performance, resulting in the programme receiving consecutive B scores (2020 and 2021). This impacted the original Business Case timelines. As a result, No Cost Extensions (NCEs) were implemented, extending the programme’s end date from 30 June 2023 to at least the end of 2024/25, with a further extension into 2025/26. Additionally, as FCDO funding to TMEA in Rwanda was reduced in 2020, support was narrowed. From 2021/22, FCDO only funded two outputs (down from nine in 2020/21): the work on ports on Lake Kivu and the preparatory work for the Kigali Wholesale Market for Fresh Produce (KWMFP).

Considering the context and the risks posed by delays and poor performance, the programme team at the British High Commission Kigali and other partners implemented improvement measures: (i) the programme was placed on a Performance Improvement Plan (PIP) in 2021/22, (ii) programme monitoring was strengthened, including weekly and monthly catch-ups and field visits, and (iii) TMEA HQ enhanced oversight and monitoring of country projects, including tracking procurement to avoid delays and inefficiencies. As a result, delivery of Rubavu port significantly improved compared to previous years, with some output indicators exceeding targets. For example, the construction of Rubavu Port has been completed, and Rusizi Port is meeting set targets despite earlier design challenges.

Commercial Considerations

TMA is a Kenyan-incorporated not-for-profit company limited by guarantee—a special purpose vehicle created in 2010 by DFID (now FCDO) and other participating development partners to implement joint donor support for regional integration in East Africa. FCDO funding to TMA’s Strategy 2 was underpinned by a Memorandum of Understanding signed in December 2017. This set out expectations across disbursements and progress reporting, due diligence, audit and assurance, communication and branding, reporting suspicions of fraud, bribery and corruption, and managing programme assets. TMA has complied with these provisions. National Oversight Committee (NOC) meetings have taken place quarterly and are attended by development partners, representatives from the Government of Rwanda, and other key stakeholders from the private sector and civil society. The NOC has played an important role in supervising and monitoring national-level programmes.

Quality of Financial Management

At the start of Strategy 2 (S2) and considering the context mentioned in the delivery performance section—especially the impact of COVID-19—there were challenges in financial performance, with high variances due to underspending. TMA underwent reforms, including the introduction of a new finance system software in July 2023 to improve financial management. This system changeover initially affected reporting timelines, but improvements followed. A new tailored financial monitoring and tracking tool implemented from July 2023 helped enhance the quality of financial management and reporting. TMA has been submitting financial reports to FCDO on a monthly basis and through end-of-year progress reports. These reports provided an overview of expenditure compared to the budget for each project, alongside forecasts for the remainder of the financial year. The reports also highlighted key financial issues such as foreign exchange rate fluctuations and the level of working capital. Variances in financial reports were reviewed by the FCDO Programme Manager together with the SRO. Major variances were discussed with TMA during monthly catch-up meetings, and decisions were agreed upon to ensure that overall forecasts aligned with budgets.

The programme’s initial total budget was £32 million. Due to the impact of COVID-19 on the UK economy, the UK Government had to make tough but necessary decisions, resulting in an overall FCDO budget reduction of £7 million for TMEA S2 in Rwanda. As a result, from 2021/22, FCDO only funded two outputs (down from nine in 2020/21): the work on ports on Lake Kivu and the preparatory work for the Kigali Wholesale Market for Fresh Produce (KWMFP). At the time of this PCR, all the budget had been spent except £120,000, which TMA reserved for monitoring port liability defects until June 2025.

Programme Monitoring and Evaluation

The logframe (or results framework) has been the main tool for monitoring progress annually. The annual review process has also been part of FCDO’s monitoring approach to assess progress against the logframe. These processes helped identify progress made, challenges encountered, and lessons learned in the previous year to guide implementation in the following year. Field visits have been undertaken by both FCDO and TMA. FCDO intensified field visits as part of efforts to strengthen monitoring, particularly given the significant delays in infrastructure projects. TMA has been sharing field visit schedules in advance to facilitate joint planning and joint visits by FCDO, TMA, and other partners.

TMA has a Monitoring, Evaluation and Learning (MEL) Strategy that was approved in June 2020. This comprehensive document outlines theories of change for each intermediate outcome and identifies monitoring, evaluation, and research priorities to better understand these theories and the results achieved. Strategic reviews for each programme assessed project progress and targets, tracking outputs quarterly, outcomes biannually, and conducting an annual overall portfolio and theory of change review. TMA has increasingly focused on improving learning from its activities to position itself as a knowledge institution on Aid for Trade programming in Eastern and Southern Africa.

For every TMA-funded project, the implementing organisation is required to form committees to oversee project implementation. These include the steering committee, which provides strategic direction; the project coordination committee, which supports overall implementation activities; and the project implementation team, which manages day-to-day operations. TMA provides technical oversight on project activities and participates in all project management structures. Implementing agencies submit quarterly reports, which are uploaded onto TMA’s Management Information System, from which progress reports are generated. Quarterly review meetings are held between TMA staff and partners. Technical experts from TMA’s regional team also provide support. However, TMEA relies heavily on project-level reporting, which limits visibility into broader programme outcomes.

Evidence

TMA has an evaluation strategy and an Evidence and Results department that monitors and evaluates performance and impact. Monitoring data is expected to be disaggregated wherever possible to effectively track results for girls and women (i.e., by gender and age) and for the poorest and most vulnerable (i.e., by income quintile and defined vulnerable groups where relevant). An internal endline evaluation report conducted in May 2023 revealed that 80% of targeted women traders reported improved social and economic empowerment in Rwanda.

Learning

TMA has developed a knowledge management strategy that guides how to promote knowledge sharing by integrating knowledge and learning into programme and project activities. This includes, among other processes, sharing best practices across all country offices, the regional office, and with partner organisations. Lessons are also identified through regular reporting, mid-term reviews, and end-of-project evaluations. Feedback from these engagements supports the articulation of key results that are monitored during programme delivery. These results are included in various programme documents such as the Project Appraisal Reports.

TMA has been using a variety of approaches to ensure learning is captured and applied in its operations. These include knowledge exchange sessions with staff, quarterly strategic reviews with programme teams to capture implementation lessons that can be shared across TMA, quarterly meetings with partners, stakeholder satisfaction surveys, and the collection of lessons learned, best practices, and success stories from partners. TMA also commissions evaluations and incorporates learning from independent evaluations.

During programme implementation, field visits and the annual review by an independent evaluator were part of the mechanisms used to gather lessons that informed adaptations in other projects. These visits provided opportunities to interact with beneficiaries and other stakeholders and collect feedback. Lessons learned were captured and documented in back-to-office reports. Some of these lessons formed part of recommendations that informed adaptive and future programming. For example, one of the major lessons from the independent annual review evaluator was that marine infrastructure projects require a demonstrable track record of both offshore and onshore expertise. These projects are highly specific and technically sensitive, requiring hands-on technical experience to address challenges that are uncommon in onshore engineering projects. This insight has triggered a major recommendation for future infrastructure projects. Key lessons have been captured in this final review report and will be shared during one of the FCDO’s quarterly programme board.

Date of last narrative financial report	24th May 2025 (financial report) and 19th May ( progress report focusing on infrastructure projects)	Date of last audited annual statement	November 2023, for the year ending June 2023

Annex
Annex 1: Performance of intermediate outcome indicators
	Starting point	Final result
Intermediate Outcome 1.1. Sustainable and efficient transport infrastructure	Indicator 1.1a “Throughput of key links and nodes on the main trade routes in East Africa”: / Baseline 2017: / Central Corridor: 1,649,575 MT / Northern Corridor: 201,133 MT	End Project Target 2023: / No end project target / Actual 2024: / Central Corridor: 46,837 MT(Exports); 1,630,669 MT (Imports) / Northern Corridor: 25,164 MT (Exports); 495,037 (Imports)
Intermediate Outcome 1.2. Improved trading standards and SPS measures	Indicator 1.2.a “Average time (Days) to test and issue certificates of conformity in Rwanda”: / Baseline 2020: / 7 days	End Project Target 2023: / 6 days / Actual 2023: / 6 days (65%-time reduction)
	Indicator 1.2.b “Number of companies certified through TMEA interventions with NSBs and SPS agencies in Rwanda”: / Baseline 2019: / RSB System certified Companies: 43 (HAACP- 23, FSMS- 8, QMS - 12) / RSB Certified Companies with S-Mark - 157)	End Project Target 2022: / 3 companies certified to comply to trading and SPS measures under the project. / Actual 2023: / 4 companies certified (2 for HACCP: RS184: 2017 and 2 for SPS FCM & PVY Control).
Intermediate Outcome 1.3. Effective trade systems and procedures.	Indicator 1.3.a “Time and cost associated with the logistical process of exporting and importing goods in Rwanda” / Baseline 2019: / Border Compliance: / Time to export/import: 83hrs/74hrs / Cost to export/import: 183 USD/282 USD / Documentary compliance: / Time to export/import: 30hrs/48hrs / Cost to export/import: 110 USD /121 USD	End Project Target 2022: / Border Compliance: / Time to export/import: 63hrs/69hrs / Cost to export/import: 161 USD /239 USD / Documentary compliance / Time to export/import: 35hrs/59hrs / Actual 2021: / Border Compliance: / Time to export/import: 83hrs/74hrs / Cost to export/import: 183 USD/282 USD / Documentary compliance: / Time to export/import: 30hrs/48hrs / Cost to export/import: 110 USD/121 USD
Intermediate Outcome 1.4. Improved trade regulatory environment.	Indicator 1.4.a “Proportion of high priority national restrictions in the movement of goods requiring legislative alignment fully addressed in Rwanda” / Baseline 2019: / Identified high priority restrictions identified. No number provided.	End Project Target 2022: / 45% of the identified restrictions associated to movement of goods removed / Actual 2023: / 45% of the identified restrictions associated to movement of goods removed.
	Indicator 1.4.b “Rate of implementation of WTO TFA commitments by partner states (disaggregated by country notifications made under Category A, B and C)” / Baseline 2017: / Category A 26.9% / Category B 56.3% / Category C 16.8%	End Project Target 2022: / Category A Not Provided / Category B 79.0% (11/14 measures) / Category C 43.0% (3/7 measures) / Actual 2022: / Category A Not Provided / Category B 79.0% / Category C 43.0%
	Indicator 1.4.c “Change in time and cost to import/export goods from the elimination of EAC-prioritised NTBs of a regulatory nature (disaggregated by time, costs, imports, exports)” / Baseline 2020: / Time / GoR participation in trade and restrictive practices tolerated by governments: 2 days / Customs and administrative entry procedures (i.e. rules of origin, taxes and levies): 2 days / Technical barriers to trade (i.e. standards, testing, packaging and labelling): 7 days / Sanitary and phytosanitary measures (i.e. policies that protect humans, animals and plants from diseases and pests): 1 day / Other procedural problems (i.e. discrimination, lack of information and complex documentation requirements): 2days / Cost / GoR participation in trade and restrictive practices tolerated by governments: USD 40 / Customs and administrative entry procedures (i.e., rules of origin, taxes and levies: USD 200 / Technical barriers to trade i.e., standards, testing, packaging and labelling: USD 500 / Sanitary and phytosanitary measures i.e., policies that protect humans, animals and plants from diseases and pest: USD 250. / Specific limitations (i.e., export taxes, quotas, local content requirements and import licensing: USD 200	End Project Target 2023: / Reduce NTB cost by 10% / Reduce NTB related time/delay by 15% / Actual 2023: / No progress reported
Intermediate Outcome 2.1. Increased trade capacity of East African businesses	Indicator 2.1.a “Change in turnover of TMEA supported firms in Rwanda (disaggregated by sector, business size, gender of business’s major shareholder)” / Baseline 2021: / 1,000,000 USD	End Project Target 2025: / Value of exports for firms supported by TMA reach $0.6 M by June 2025 / Actual 2025: / Value of exports for firms supported by TMA reached $ 4.8 M by June 2025.
	Indicator 2.1.b “Proportion of TMEA supported firms in Rwanda accessing new business in export markets (disaggregated by sector, business size, gender of business’s major shareholder)” / Baseline 2020: / 0	End Project Target 2023: / 73% (11 out of 15) of supported firms accessing new businesses in export. / Actual 2023: / 25%. 10 out of 40 supported SMES (6 in horticulture, 2 in handicrafts, 1 in agro-processing and 1 in IT) accessed markets in the Middle East, Europe, West Africa and USA.
Intermediate Outcome 2.2. More inclusive trade	Indicator 2.2.a “Change in the value of trade by supported women in Rwanda (disaggregated by type of trade, age, disability)” / Baseline 2020: / Formal Route--> USD 119, / Informal Route--> USD 126, / No-disability--> USD 126 / With-disability--> USD 61 / 18-25 years--> USD 39 / 26-35 years--> USD 57 / 36-45 years--> USD 104 / 46-55 years--> USD 422 / 56+ years--> USD 261 / Overall sales (USD/Month) --> USD 119	End Project Target 2023: / End of project target: 50% increase in value of trade for targeted women traders. / Actual 2023: / No end project survey was undertaken to assess target achievement
	Indicator 2.2.b “Social and economic empowerment of supported women traders in Rwanda (weighted average index score” / Baseline 2020: / No-disability_45% / With-disability_42% / 18-25 years_46% / 26-35 years_43% / 36-45 years_43% / 46-55 years_51% / 56+ years_45% / Overall_scores_45%	End Project Target 2023: / 70% of TMEA supported women traders reporting Social and economic empowerment (weighted average index score) / Actual 2023: / No country specific surveys on the Index were undertaken at the end of Strategy 2

Annex 2: Changes to the TMA Strategy II Theory of Change

Business case TMEA S2 results chain	2019/20 Revised TMEA S2 results chain

Annex 3: Changes to outcome indicators through S2 programme implementation cycle
Business case log frame 2017/18	Log frame at Programme Completion 2024/25
Impact: Sustainable, inclusive prosperity
1.5 Total government revenue, excluding grants (US$ billion, constant prices) {Removed}	1.5 Change in greenhouse gas emissions on the Northern and Central Corridors (disaggregated by corridor and routes) {New}
Outcome one: Reduced barriers to trade
1.1 Trade costs (road, rail) in the East Africa Trade Network (EATN) at an average $x/tonne x km (US$ billion, constant prices) (% change)	1a Cost to trade in goods (per 20-foot equivalent unit (TEU)) aggregated across nodes, routes and process points of TMEA intervention (calculated as weighted average and variability of cost) (disaggregated by imports/exports and route)
1.2 Average transport time (road, rail) in the EATN (days) (% change)	1b Aggregate time (per T) to traverse determined nodes, routes and process points after discharge of cargo from a vessel to its final delivery at the inland destination for import cargo; or from acceptance by carrier to when the cargo is loaded on board a ship for export cargo (disaggregated by imports/exports and route)
Outcome two: Improved business competitiveness
2.1 Total exports in targeted sub-sectors (free on Board (FOB)) value (US$ millions, constant prices) and growth rate (%)	2a Change in total trade in goods in selected value chains (disaggregated by country, exports and domestic trade)
2.2 Investment catalysed (US$, constant prices	2b Total value of additional investment leveraged as a result of TMEA funding (disaggregated by public investment, private investment, country, project)
2.3 Evidence of crowding-in, copying and replication	2c Total number of new jobs created (disaggregated by direct, indirect, gender of jobholder, disability, country) {New}
	2d Change in incomes of TMEA supported beneficiaries (disaggregated by country, gender, disability) {New}