Programme Completion Review

Title: Work and Opportunities for Women (WOW)
Final Programme Spend £ (full life): / £10,638,841.94	Review Date:	June 2025
Programme Code: [AMP ID#] 204531	Start Date: 02 October 2017	End Date: 01 April 2025

Summary of Programme Performance

Year	2017	2018	2019	2020	2021	2022	2023	2024-25
Programme Score	A	A	A	A	A	A	A	A+
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	http://iati.fcdo.gov.uk/iati_documents/52504007.odt
DevTracker Links to all logframes used during programme lifetime:	http://iati.fcdo.gov.uk/iati_documents/51541885.xlsx

A. Summary and Overview

Description of the programme and what it has achieved
The Work and Opportunities for Women (WOW) programme was a seven and a half-year initiative (2017 to 2025) designed to advance women’s economic empowerment in global supply chains. Launched by the UK’s Department for International Development (DFID) in response to the UN High Level Panel (UNHLP) on Women’s Economic Empowerment (2015-17), the programme adopted a multi‐output approach. These Outputs were:
- Output 1 – Partnerships with multinational companies to help reduce the barriers preventing women from securing dignified, equal and economically empowering work.
- Output 2 – Working with businesses to improve data and transparency on women’s work in supply chains.
- Output 3 – A Helpdesk to enhance UK government policy and programme design and increase knowledge and support for delivering women’s economic empowerment.
- Output 4 – The WOW Fund for NGOs, to support initiatives that progressed the Action Agenda of the UNHLP.

Across all its Outputs, WOW sought to focus its efforts on the difficult structural barriers to women's economic empowerment including unpaid care, gender‐based violence and the impacts of climate change.

For the final two years WOW acted as part of the Foreign, Commonwealth and Development Office (FCDO)’s Green and Inclusive Growth Centre of Expertise (GIG COE), which works with partners to deliver economic transformation. This includes thematic focuses on growth sectors, supporting the enabling environment for green and inclusive economic transformation including land governance, sector-specific regulatory reform, women’s economic empowerment and economic inclusion. The learnings from this PCR should be built into the design and delivery of the second phase of the GIG COE, which will continue efforts to work in partnership with the private sector, academia and civil society to advance gender equality. The approach to women’s economic leadership and empowerment that this phase will incorporate follows three core objectives:
1. Increasing women’s access to quality, rewarding jobs and work.
2. Promoting partnerships that drive global efforts to recognise, reduce and redistribute unpaid care work, and reward and represent paid care workers.
3. Mobilise public and private resources to close the gender financing gap, and drive reforms for a more equitable and gender responsive International Financial System (IFS).
These still speak to the finding of the 2017 UNHLP, which proved a robust and clear underpinning for our strategy and programming, as set out in the WOW Business Case.

The programme was designed when the UK spent 0.7% of Gross National Income (GNI) on Official Development Assistance (ODA), which meant DFID had the budget to work with small scale enterprises, achieving scale while directly impacting women in communities. WOW adapted incredibly well to the changed context and budget cuts by maintaining the commitment to working with communities, while achieving impact at scale, with much lower budgets per year than initially expected. To replicate this success, phase two of the GIG COE should use relevant, quality data to demonstrate both the business case for investing in women, and pathways to do it effectively; pilot new initiatives through large firms who will take approaches to scale themselves; and amplifying the message using business networks and trade press. Where this can hook onto zeitgeist issues for business (such as climate sustainability and supply chain resilience) will be a demand for this by the private sector.

The programme was delivered by a consortium led by PwC in partnership with CARE International and Social Development Direct. Business for Social Responsibility (BSR) and the University of Manchester were members of the alliance between 2017 and 2020. The programme was implemented through 13 formal business partnerships, ranging from major retailers, agribusiness, and ethical trading organisations, as well as partners across supply chains, such as local and international NGOs (e.g. Farm Africa, WIEGO), industry bodies (e.g. Sedex, ICVCM), and business networks. The programme’s activities spanned across the following countries:
- Bangladesh
- India
- Kenya
- Malawi
- Mozambique
- Pakistan
- Indonesia

External contexts significantly shaped the evolution of the programme including the COVID-19 pandemic, the merger between DFID and the Foreign Commonwealth Office (FCO), cuts in official development assistance (ODA) and resulting in an unplanned and difficult to predict spend profile, and two no cost extensions of the WOW programme. Consequently, the programme was not able to fully implement the ambitions as captured in the original Theory of Change and contract. For example, early partnerships, which had the potential to reach large numbers of women, had to be concluded prematurely reducing the overall impact and reach of the programme. By remaining adaptive, flexible and cognisant of the evolving regulatory and corporate landscape and using the WOW Alliance and individual team members networks and reputation, WOW has consistently scored ‘A’s in its Annual Reviews and has achieved significant impacts.

Key achievements
The intended impact of the WOW programme was increased numbers of women employed in higher productivity jobs and roles in supply chains, with improved working conditions. This was achieved by empowering marginalised women, engaged men and institutions to shift norms, and used data and partnerships with the private sector, academics and both local and international civil society to drive systemic change. Its legacy is one of sustainable impact, where women’s contributions are recognised, valued, and central to economic and environmental progress. This is true both for the individual women involved in the programme and others in the supply chains of companies influenced directly or indirectly by the work of the programme – including for example those that are members of the Business Fights Poverty network, who have engaged in lesson sharing by WOW and whose website hosts key resources, and those that are part of sector specific groups sharing good practice on addressing environmental, social and governance (ESG) issues. By pivoting to focus on the intersection of gender and climate, WOW was able to keep gender equality part of the ESG discussion amongst these groups, even as broader trends amongst businesses narrowed focus on the environmental aspect. Across all of this work WOW maintained a focus on fairness, inclusion, and systemic change.

The intended impact of the programme was also to contribute to the achievement of Sustainable Development Goal (SDG) targets on ending poverty, reducing economic inequalities between women and men, and improving poor women’s access to economic resources and decent jobs (SDGs 1, 5 and 8). WOW successfully contributed to each of these, as well as SDGs 4 (quality education), 7 (affordable and clean energy), and 13 (climate action).

Major lessons learned, evidence generated and recommendations:
Clarity on targeting large numbers of women vs reaching the most vulnerable. WOW was initially established with a target of reaching 300,000 women through 10 partnerships. However, most of the early partnerships were in Asia, where it was easier to reach women at scale through factory and manufacturing settings. In contrast, pivoting to operate more in African countries in the latter part of the programme, and towards the agricultural sector, made reaching large numbers of women at scale more difficult given the dispersed nature of agriculture, of which quite a substantial part is smallholder agriculture. However, the profile of women reached was generally poorer and more disadvantaged. Overall, the programme managed to reach around 250,000 women across the range of work implemented. Future programming should be clear from the outset the exact profile of intended beneficiaries.
- Local engagement drives sustainable impact: Co-creating solutions with local partners (including suppliers and governments) enhances the reach of the programme and the long-term sustainability of the programme. Interventions for economic development should ensure local partners and expertise are involved and leading design and implementation to build capacity, buy in and sustainability.
- Talking the language of risk gets business to the table, but the language of opportunity inspires business action at scale. Companies were interested in addressing issues in their supply chains that posed material (e.g. climate) or reputational (e.g. GBVH) risks to their business. Given the challenging nature of addressing some of these issues, business preferred to test and refine gender-responsive initiatives on a smaller scale before embarking on large-scale implementation that had the potential to reach large numbers of women. However, it is the ‘opportunity’ of achieving a solution to a challenge that can ultimately convince the business to invest its own resources and time to addressing the challenge. For example, Business D saw the opportunity of investing in the Famers’ Voice Radio for improving tea leaf quality, climate change responses and the livelihoods of the smallholder farmers on whom they rely. They are now interested in adopting it themselves in other geographies and supply chains.
- Adaptability and resilience are critical: WOW’s ability to pivot during the COVID-19 pandemic, ODA cuts and organisational changes demonstrates that programmes must remain agile and responsive to unanticipated external shocks. Agility, in this context, includes regularly reviewing and updating Theories of Change and assessing different entry points that lead to the desired impact. Other critical factors include a strong working relationship between the Senior Responsible Owner (SRO) and core team, and a strong network of relationships between the core team and businesses (and business networks).

Recommendations for maximising the impact of future programming
- Focus business partnerships on a narrower set of issues in a specific thematic (e.g. gender and climate change) area aligning with businesses priorities (e.g. ESG reporting and Net Zero commitments) to leverage existing corporate momentum and co-create programmes with them from the start: Work with companies, ideally for five to seven years, that are members of wider networks and alliances to increase reach. Ensure that local suppliers are front and centre of any new programmes to improve reach and depth.
- Move away from ‘buying results’ and shift towards ‘systems’ and policy change for more lasting and sizeable impact. Given the many structural challenges that affect women in global supply chains, including low pay, lack of social protection, irregular market access and prices, future programmes should consider how to harness businesses voice as a partner to influence corporate governance and national legislation in the countries they are operating in. This collaboration would be invaluable, especially in programmes that are five to seven years in scope, as this allows time to shape and influence local, national and global processes.
- Make policy change central to the programme: Address structural challenges in supply chains by working with companies and governments together to change policies. Consider aligning future programmes to respond to emerging international standards, regulations or legislation, to help businesses to adapt and implement changes accordingly.
- Amplify data systems that identify and measure women’s economic empowerment: Consider working with a data provider or auditing/reporting agency used by the private sector and harness emerging AI tools to maximise data disaggregation and analysis for businesses, their supply chains and business networks in order to identify areas of success and bottlenecks for action.
- Enhance the uptake of information and learning through regular and strategic communications channels: Create dedicated online platforms with specific audience in mind and design appropriate online channels and content to reach the audience. Therefore, design a website and social media account (i.e. LinkedIn) to amplify learning and increase the uptake of tools and guidance. Monitor metrics to measure reach and impact. Consider working with a business-orientated communications partner to leverage contacts with relevant trade press.
- Enhance local capacity and collaboration: Invest in enhancing the capacity of local organisations and experts to ensure that interventions are context-specific, scalable and sustainable over time.
- Allocate resource to enhance the monitoring, evaluation and learning (MEL) capacity of both NGO and private partners: Allow for sufficient resourcing within the programme’s budget, for both human resource and data collection, to support MEL activities and mentoring engagement with both NGO and private partners. This will build MEL capacity and capability so that they can upgrade their internal systems, institutionalise the improved capabilities and continue to track progress on impact and sustainable change.
- Ensure outputs are designed to complement each other and interact in ways that capitalise on natural synergies when they pop-up: Outputs (such as a business partnerships, Helpdesk and Grant Fund) should dovetail rather than work in isolation, as originally intended by the WOW Theory of Change which envisioned that each WOW output will be delivered separately and target different stakeholders. Where possible, they should all work to the same key impact indicators to provide better value for money (VfM) and enhance the systemic impact created.

How this report was conducted
This report has been compiled by the WOW SRO and PRO, using detailed evidence from programme delivery partners; WOW beneficiaries including partner businesses, NGOs and supply chain workers; conference organisers and participants; and past programme officers and SROs. It includes evidence from monitoring visits in 2024 to three partnerships (two in Kenya, one in Malawi), discussions at regular governance board meetings and a range of closure events realised in early 2025.

Actions following approval of this report
Action 1: Communications: Continue to track and measure online interaction with WOW learning products. Continued monitoring of engagement with the WOW website and, specifically, engagement with WOW learning products will enable FCDO to identify which women’s economic empowerment topics are of most interest to online users. This will then enable FCDO to shape future offerings (such as toolkits and research reports) accordingly.
Action 2: Lessons learned: Disseminate WOW lessons amongst HMG colleagues to inform new initiatives and Inclusive Growth Diagnostics. The lessons learnt will be shared with relevant HMG colleagues who are working on related programmes including the FCDO Economic Centres of Expertise, to deliver greater economic empowerment and opportunities for women. An internal summary of WOW resources should be consulted as part of all FCDO Inclusive Growth Diagnostics and integrated into the development of economic development portfolios at a central, regional and country level.
Action 3: Partnerships: Maintain relationships and dialogues with WOW programme partners. Since its inception in 2017, the WOW programme has engaged with five consortium partners, 13 business partners and 24 delivery partners, and brought together representatives from across the private and public sectors and civil society. The Economic Development Department (EDD) should maintain relationships with these partners to build on their expertise, amplify their experience and maintain a network of partners in the Women’s Economic Empowerment space.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Up to £12.38 million	£10,638,841.94
Timeframe	01 October 2016 to 30 September 2021	02 October 2017 to 01 April 2025

Outcomes:	Final target		Achievement
1.1 Number of women who have improved or protected agency and/or access to higher productivity and higher-return jobs (including climate-smart/resilient jobs and/or roles) and/or improved working conditions in supply chains due to WOW interventions.	115,000		245,588: Met and exceeded. / Through Output 1, WOW reached 196,899 women. 87,054 were reached directly. 109,845 were reached indirectly by the Farmers’ Voice Radio programme under WOW’s partnership with Business D in Kenya. Through Output 4, 48,689 women were reached. This includes those women reached via COVID-related activities.
1.2 Number of partnerships (with companies/business initiatives) supported by WOW that are: (i) improving or protecting visibility and/or reducing barriers and/or creating opportunities and/or improving conditions for women in global supply chains, (ii) implementing policy and practice change that focus on both climate resilience and women’s economic empowerment, (iii) demonstrating more advanced thinking/engagement on unpaid care considerations.	8		10: Met and exceeded / The WOW programme successfully supported multiple partnerships with companies and business initiatives
1.3 Number of FCDO and HMG programmes reporting plans for improved design or to reach higher number of women beneficiaries.	35		38: Met and exceeded / Throughout the lifespan of WOW, the Helpdesk responded to a total of 106 requests for support. Of these 106 requests, 42 were programme facing.
1.4 WOW funded grantees generate new knowledge and/or influence practice in the areas of: (i) improving conditions of informal workers, (ii) recognising, reducing and redistributing unpaid care work, (iii) improving tenure security for WEE.	Sept’ 2018 - Sept’ 2019	Sept’ 2020		Sept’ 2021	Sept’ 2022	Sept’ 2023 – Mar’ 2025
	-	WOW-funded projects generate learning materials including COVID-19 specific learning materials (e.g. toolkits, briefs, public engagement materials).		WOW grantee projects show evidence of engagement, response and/or commitment from relevant government or institutional bodies, or civil society organisations, or other stakeholders to advance WEE in their respective thematic area.	WOW grantee projects show evidence of uptake, changes in practice amongst relevant stakeholders, or of new campaigns, partnerships or other initiatives established to support improvement in WEE for the relevant thematic area.	N/A – WOW Fund work concluded
	Too early to report progress	31 learning materials including COVID-19 specific learning materials generated through direct and indirect support and contribution from WOW.		Cumulative number of learning products (including COVID-19 related learning products) produced and shared is 45. This is an increase by 14 learning products (of which 9 are produced by SEWA) compared to Y3.	Cumulative number of learning products produced and shared is 51 (of which 6 were achieved in Year 5)​	N/A – WOW Fund work concluded

Overview
The WOW programme was a catalyst for transformation, advancing gender equality, economic empowerment, clean energy adoption and climate resilience across global supply chains. Of the 13 partnerships with corporate partners[1] and business organisations, 10 had positive outcomes whereas the remaining three had to be closed early due to budget cuts. WOW reshaped opportunities for women by breaking systemic barriers, increasing visibility in the workplace and positioning women as leaders in climate-smart economies. The programme’s achievements contributed to the following SDGs:
[1] Anonymised for this report: - Business A: A multinational retailer specialising in clothing, home products and food items - Business B: A multinational beauty and personal care company specialising in ethically produced and environmentally friendly products - Business C: A major multinational retailer specialising in affordable fashion - Business D: A multinational company with historic roots specialising in the sale of tea and other hot beverages - Business E: An international not-for-profit organisation which works to promote sustainable cotton farming practices and improve working conditions in the cotton industry - Business F: An international not-for-profit organisation which works to promote fair trade practices, and ensure better prices, working conditions and terms for farmers and workers in developing country contexts - Business G: A multinational agribusiness operating across the supply chain - Business H: A multinational fashion company which manages a range of popular and affordable clothing brands - Business I: An international not-for-profit organisation which works to improve the sustainability and ethical standards of the global tea industry - Business J: British supermarket retailer known for its high-quality offerings - Business K: A major multinational corporation producing a wide range of consumer goods, including food, beverages, cleaning agents and personal care products

SDG 4 – Quality education: Ensure inclusive and equitable quality education, aiming to ensure all learners acquire the knowledge and skills needed for employment, decent jobs and entrepreneurship.
SDG 5 – Gender equality: Achieve gender equality and empower all women and girls.
SDG 7 – Affordable and clean energy: Ensure access to affordable, reliable, sustainable and modern energy for all.
SDG 8 – Decent work and economic growth: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all.
SDG 13 – Climate action: Take urgent action to combat climate change and its impacts.

Economic participation
WOW directly contributed to enhancing women’s economic participation, promoting gender-sensitive work environments, and reducing structural barriers, allowing financial independence for many women. Through its partnership with Business E, addressed gender imbalances related to training and roles available to women workers and tackled entrenched perceptions around women’s role in the value chain, leading to increased recognition of women’s contributions in cotton farming, in agricultural labour, for 33,000 women. It also supported systemic change by ensuring gender-disagregated data collection, which helped to identify disparities and target interventions more effectively.

Through its partnership with Business D, on the delivery of Farmers’ Voice Radio, WOW supported smallholder tea farmers in Kenya to improve the quantity and quality of their yields, to diversify income-generating activities, such as beekeeping and agroforestry, and change gender norms around care giving and household decision making. As one woman shared, “My husband now consults me before making financial decisions. Before, he would decide alone, but now we plan together.”

Through its partnership with Business J, WOW supported smallholder farmers and farm workers, particularly women, working in horticulture supply chains in Kenya, by providing technical expertise and resources to enhance climate resilience while promoting clean energy use and sustainable agricultural practices. The WOW partnership trained 75 lead farmers, including 50 women and 25 men, to support gender-responsive climate resilience efforts. Climate-smart techniques were adopted by 98% of participants, including intercropping, agroforestry and drought-resistant crops. These methods increased crop yields by 30% on average, improving food security and surplus for sale. As one woman shared, “I used my savings to buy chickens, and now I earn enough to pay school fees for my children.”

Sustainable energy solutions
Beyond economic participation, WOW worked with companies to identify corporate social responsibility initiatives that would benefit women workers in supply chains. For example, sustainable energy solutions that significantly improved women’s quality of life. WOW’s partnership with Business J’ Climate Resilience Programme in Kenya saw 92% of participating households transition to renewable energy. This dramatically reduced household exposure to harmful smoke, resulting in improved health outcomes. It also cut down on time-consuming labour traditionally undertaken by women. One woman said, “I used to spend hours collecting firewood. Now, I cook faster and cleaner, and I have time to work on my business.” Women also trained as cookstove artisans and began producing and selling these stoves, earning KES 1,200–2,000 (GBP 7.22 – 12.04)[2] per unit. One participant shared, “I now earn enough to support my family while helping my community transition to clean energy.”
[2] This is as per XE Exchange on 10 March 2025.

Climate change resilience
The environmental impact of the WOW programme extended beyond cleaner cooking solutions. Women also played a leading role in climate resilience initiatives. In Malawi, WOW’s partnership with Business I led to the planting of over 135,000 trees, representing a vital effort in combating deforestation and improving soil quality. WOW demonstrated the intersection of climate action and economic empowerment. One farmer reflected on this shift, saying, “We now plant trees not just for today, but for future generations.”

Lasting change
Through its integrated approach, WOW empowered over 245,000 women (directly and indirectly), however the programme’s success is not measured solely by statistics but by the shifts in how women are perceived, valued and supported in their professional and personal lives. As one participant explained, “Before WOW, I was just a tea farmer. Now, I am a businesswoman, a leader and an advocate for change.”

Following Business I’s Family Management Training in Malawi, 79% of male participants expressed strong support for their wives in leadership roles, compared to just 12% before. Men, who once adhered to rigid gender roles, actively began to share household responsibilities. One female participant said, “We now cook together, and my husband even takes the children to the hospital, which was never the case before.”

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
The initial ToC (2017/18) provided a broad overview of the WOW programme’s goals but did not fully reflect the complexity of change processes. It did not clearly illustrate the causal linkages between interventions, Outputs and Outcomes, making it less effective for tracking progress and impact. Stakeholder roles were presented at a high level, without detailing the distinct contributions of supply chain companies, multinational corporations and policy influencers. Moreover, this ToC did not explicitly incorporate climate resilience or address systemic barriers such as unpaid care and informal work. In part, this was because the WOW programme did not initially focus on climate resilience and was not designed to implement unpaid care as a cross-cutting theme. The approach to institutional change was also less defined, limiting insights into how policy shifts occur. The simplified ToC therefore served as a useful starting point. However, it became clear that it needed greater detail and nuance.

The revised ToC (2022) provided a more structured and interconnected framework and introduced greater specificity regarding the changes expected for different stakeholders in order for the programme to contribute to women’s economic empowerment. A key improvement within this ToC was the integration of climate resilience, embedding policy and practice changes within supply chains to enhance sustainability. This ToC also established stronger links between different levels of change, explicitly connecting interventions to measurable outcomes. It took a systemic approach to describing how, by addressing barriers, the programme could implement activities that would influence shifts in societal attitudes and practices around unpaid care and informal work.

These refinements made the ToC more actionable, evidence-driven and effective in guiding sustainable systemic change. They also enhanced clarity, depth and adaptability, providing a more comprehensive roadmap for achieving women’s economic empowerment.

Results Measurement Framework: Key changes
Over the course of the WOW programme, the Monitoring, Evaluation, and Learning (MEL) approach evolved significantly in response to practical implementation challenges and learning.

1. Evolving MEL Support for Partnerships (Output 1)
- Initially, MEL for partnerships with multinational companies was designed to be light-touch, with the expectation that partners would lead on data collection and reporting. However, this assumption proved unrealistic. Many partners lacked the internal capacity, resources, or clarity around MEL responsibilities. In response, WOW:
- Introduced clearer MEL roles and expectations in partner agreements.
- Allocated dedicated MEL budgets and personnel to each partnership.
- Developed guidance documents to support consistent MEL practices.
- Adopted a more integrated approach to partnership design post-2022, ensuring MEL was embedded from the outset.
- These changes reflect a shift from decentralised, partner-led MEL to a more structured and supported model, improving data quality and accountability.

2. Streamlined MEL for Research and Helpdesk (Outputs 2 & 3)
- Outputs 2 and 3 required less intensive MEL intervention:
- For research activities (Output 2), MEL was minimal as academic partners provided their own quality assurance.
- For the Helpdesk (Output 3), the MEL team focused on developing tools and templates to support feedback collection and follow-up, aligned with logframe requirements.
- These outputs demonstrated that not all programme components require the same level of MEL investment, and that tailored approaches can be effective.

3. Strengthening MEL for the WOW Fund (Output 4)
- The WOW Fund required more robust MEL support than initially anticipated. Frequent revisions to logframe indicators necessitated updates to MEL processes. To address this:
- WOW developed comprehensive MEL guidance for grantees.
- Additional MEL resources were brought in to mentor and support grantees in designing tools and aggregating data.
- This experience highlighted the importance of flexible MEL systems that can adapt to evolving programme frameworks and the value of hands-on support for grantees.

Sharing learning within HMG
Alongside reports, evidence digests and guidance produced for HMG officials by the Helpdesk (Output 3), learning was shared from other outputs with colleagues across government to increase capability related to women’s economic empowerment. Example engagements included:
- Safeguarding Learning and Development webinar for FCDO Heads of Profession and Private Sector Development advisors, 18 November 2024. The WOW Safeguarding Expert delivered this session which covered findings from the WOW safeguarding risk assessments and provided case studies of both effective and ineffective safeguarding practices. The webinar materials were uploaded to FCDO’s internal learning portal.
- Cookstoves webinar for FCDO staff (and others), 9 December 2024. WOW team members outlined key findings from an investigation into the impacts of improved cookstoves on farmer and farmworker households, particularly in terms of expenditure on fuel, time savings for women, stove stacking and improved health and safety. Recommendations were provided on the design and structure of future improved cookstove projects.
- Integrating gender into the design, implementation and monitoring of carbon credit projects webinar for the Department for Energy Security and Net Zero, 11 March 2025. WOW team members delivered two sessions on: the gender issues and gaps that exist in the voluntary carbon market; why gender inclusive approaches matter; Ways to embed gender inclusive approaches; gender-related criteria to be aware of as investors/buyers; and case studies of gender best practice in carbon crediting and climate mitigation projects. A recording of the session was uploaded to an internal learning portal for other DESNZ colleagues to access.

Logframe
The initial WOW logframe was agreed during programme inception (2017/18). It was designed so that each workstream/Output was separately represented at both the Outcome and Output level. It also included at least one Output that measured programme performance and efficiency. To improve clarity, adaptability, and strategic alignment clarifications and explanatory notes were added to make indicators easier to interpret and report on, while the number of indicators was reduced and streamlined to enhance focus and manageability. The logframe was also adapted in response to external shocks like COVID-19, with revised targets and milestones to reflect programme pauses and budget constraints. Strategic shifts introduced new priorities such as climate change and gender, along with new partnership indicators to support scalable pilot projects. Timeline and impact weightings were adjusted to reflect programme extensions and the reduced number of active outputs, ensuring continued relevance and effectiveness throughout the programme’s lifecycle.

## C: Detailed Output Assessment

Output Number and Title	Output 1 – WOW pursues effective partnerships with companies to improve women's participation in supply chains.
Output Score	A
Impact weighting (%)	35%	Impact weighting revised since last AR?	Yes, down, to give average weighting for programme lifecycle

Output Indicator	Final Target	Achievement	Narrative
1.1.1 Number of partnerships (with companies, business initiatives) implementing agreed WOW partnership activities to address issues related to WEE in selected supply chains.	12	13	Met and exceeded target. / WOW established 13 partnerships with companies/business
1.1.2 Number of learning products, resources, public documents and tools produced and disseminated and/or events and/or convening led by WOW to support information sharing, industry uptake and/or building the evidence base on WEE reaching targeted stakeholders – e.g. companies, policy makers, relevant academics and donors.	27	41	Met and exceeded target. / WOW produced 41 learning products, resources, public documents, tools and/or events (see the List of Annexes). Materials were disseminated via webinars and events and were hosted online on both the UK Government webpage and the Business Fights Poverty website.
1.1.3 Number of organisations engaged by WOW on gender-sensitive climate-smart policy and practice change.	N/A – No target, qualitative reporting only.	See below for details.
1.1.4 Key activities undertaken by WOW to influence unpaid care considerations in global value chains	N/A – No target, qualitative reporting only.	See below for details.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output indicator 1.1.1 – Number of partnerships (with companies, business initiatives) implementing agreed WOW partnership activities to address issues related to WEE in selected supply chains.

Key activities
- Business A: A multinational retailer specialising in clothing, home products and food items (2018 to 2021): Implemented a worker-management training programme to increase and improve women's leadership in garment factories in Bangladesh.
- Business B: A multinational beauty and personal care company specialising in ethically produced and environmentally friendly products. (2019 to 2021): Piloted a commercially viable pricing model to account for unpaid work and care undertaken by women in the hemp mitt supply chain in Bangladesh. Also integrated a checklist on hidden labour and care provision in country framework assessments. This checklist is still in use. This pilot was not continued due to budget cuts.
- Business C: A major multinational retailer specialising in affordable fashion (2019 to 2022): Research into the unpaid work and care burden for female garment workers in Bangladesh, and research into impacts of climate change on women cotton pickers in Pakistan.
- Business D: A multinational company with historic roots specialising in the sale of tea and other hot beverages (2020 to 2025): (1) Improved the visibility of women and GBVH awareness in their estates in India. (2) Supported climate-smart agriculture Farmers’ Voice Radio programmes for women tea farmers in Kenya.
- Business E: An international not-for-profit organisation which works to promote sustainable cotton farming practices and improve working conditions in the cotton industry (2019 to 2022): Delivered a Training of Trainers and capacity building programme in Pakistan to raise awareness of gender inequality and harmful gender norms that prevent women’s participation in agronomy training.
- Business F: An international not-for-profit organisation which works to promote fair trade practices, and ensure better prices, working conditions and terms for farmers and workers in developing country contexts (2020): Contributed to the design of a new gender standard and planned to address GBVH on tea estates in India with a Training of Trainers programme to support implementing partners. This work was not continued due to budget cuts.
- Business G: A multinational agribusiness operating across the supply chain (2021): Undertook an assessment to better understand the constraints and opportunities for women farmers in the sesame value chain in Northern Nigeria, to inform the design of multinational agribusiness operating across the supply chain’s sustainability programmes.
- Business H: A multinational fashion company which manages a range of popular and affordable clothing brands (2021): Assisted garment workers in Pakistan to cope with the COVID-19 pandemic, including broadcasting messages across factories.
- Business I: An international not-for-profit organisation which works to improve the sustainability and ethical standards of the global tea industry (2022 to 2024): Conducted and published research on the impacts of climate change in Kenya and Malawi. Implemented a payment-for-ecosystem-services project with tea smallholders in Malawi.
- Business J: British supermarket retailer known for its high-quality offerings (2022 to 2024): Conducted and published research on potential Scope 3 emissions impacts on workers in horticultural supply chains. Implemented a project in Kenya focused on climate change impacts on women farmers and farmworkers.
- Business K: A major multinational corporation producing a wide range of consumer goods, including food, beverages, cleaning agents and personal care products (2021 to 2024): (1) Undertook a situational study of women workers and farmers in the sugar value chain in India to understand women’s exposure to GBVH in the sector and help implement the Global Women’s Safety Framework in Rural Spaces. This work was not continued due to budget cuts. (2) Undertook research on informal waste pickers in the recycled plastics value chain in Indonesia, with learning shared via the Fair Circularity Initiative[3], and gender technical assistance provided to The Circulate Initiative (TCI) [4].
  [3] The Fair Circularity Initiative (FCI) brings businesses together, with the aim of ensuring that the human rights of workers within the informal waste sector are respected and their critical role in circular value chains is recognised. FCI was convened by NGO Tearfund with founding members major multinational corporation producing a wide range of consumer goods, including food, beverages, cleaning agents and personal care products, Nestle, PepsiCo, the Coca-Cola Company and TetraPak, with other members planning to join soon. FCI’s work is founded on the Fair Circularity Principles which have been informed by the perspectives of rights-holders, and apply the expectations and responsibilities outlined in the UN Guiding Principles on Business and Human Rights to the informal waste sector.
  [4] The Circulate Initiative (TCI) is a global non-profit organisation working to solve the plastic pollution challenge and build circular and equitable economies across emerging markets. TCI delivers cutting-edge research and tools, builds high-impact programmes, and drives collective action with industry stakeholders including businesses, investors, and policymakers.

In addition to the above, it should be noted that WOW undertook extensive work to integrate gender indicators into Sedex[5]’s audit process, which now reaches more than 86,000 companies. WOW also worked with Acorn (a subsidiary of Rabobank) to develop guidance on gender-sensitive carbon credits. These collaborations did not follow the same contractual processes as the partnerships listed above and therefore are not classified as partnerships. Nonetheless, their impacts have been included in the outcome total.
[5] Sedex is a global technology company that specialises in data, insights and professional services to empower supply chain sustainability.

Key achievements
- Business C: WOW collaborated with them to produce The Double Day report, which explores unpaid work and care for female garment workers in Bangladesh. This research reinforced the need for Business C to include unpaid care work as a critical element of its broader sustainability initiatives. An internal working group on unpaid care has since been developed to identify suitable entry points to address these issues.
- Business D: After the closure of WOW, they will continue to invest in, and expand the use of, Farmers’ Voice Radio across their markets, including in Sri Lanka and Nigeria. Inspired by WOW’s focus on gender and climate-smart agriculture topics Business D is now establishing a partnership with the Tea Research Institute to pilot carbon emission reduction activities through tree planting, organic farming and further biogas expansion.
- Business B: At WOW’s suggestion, they incorporated into their standard country assessment framework a checklist on hidden labour and care provision which they have continued to use.
- Acorn: Acorn is a Rabobank programme which is developing high-integrity carbon credits that seek to benefit smallholder farmers across Africa, Asia and Latin America. WOW’s support, via the Integrating gender into the design, implementation and monitoring of carbon credit projects report, has helped Acorn to ensure that their projects have a strong gender lens. As an Acorn environment, social, governance (ESG) monitoring and reporting specialist explained, “The guidance provided by WOW has been invaluable in supporting our efforts to achieve our goals. Specifically, the guidance has empowered local partners by providing practical information to them on how to improve gender equity in their projects. The guidance also enhanced project design, implementation and strengthened the M&E of our projects.”
- Business J: The WOW supported Climate Resilience Programme was recognised with the edie Just Transition to Net Zero award. As a result of WOW’s cookstoves research, They are reviewing their approach to procuring and distributing cleaner cookstoves, adopting WOW learnings regarding the distribution and implementation of different stoves for different recipients (namely, out growers versus farm workers). They hope this work will lead to a more effectively implemented and environmentally positive cookstove programme which benefits farm workers, communities and the environment.
- Business E: WOW’s partnership with Business E ended earlier than expected in 2021. Nonetheless, Business E used their own funds and partnered with CARE to continue to deliver the work originally planned with WOW, ultimately reaching 14,000 community members in Pakistan. This work included training on gender inequality, budgeting and decent work, in order to enable more women to access and participate in cotton farming. Business E has acknowledged that WOW’s initial engagement helped to broker their continuing partnership with CARE. Moreover, since WOW’s involvement, Business E has integrated gender equality into their standards, which must be met by all participating farmers. Furthermore, since WOW’s involvement, Business E has set a target of ensuring 25% of field staff are women, which they are halfway to achieving. They have also set a 2030 goal to reach one million women with resources and tools in the cotton sector and have increased their own resourcing to achieve this.

Lessons learned through this output
- Companies want to work on data and pilots rather than large-scale reach. Whilst WOW initially tried to engage companies to reach large numbers, the overwhelming preference from companies was to focus on smaller pilots and innovative projects that could help build the case for larger scale up. For this reason, the offer from WOW to provide data on where women were in their supply chains (Output 2) was a ‘door opener’ when it came to convincing companies to work with WOW.
- Companies see benefit in partnering with FCDO, but relationships were tested. WOW lost time, numbers and goodwill when it had to end early partnerships prematurely due to ODA cuts. These included the Business A women’s leadership project and the Business E project on women's recognition in the cotton value chain. Relationships were damaged: none of the original partnerships were subsequently continued by WOW. Nevertheless, and in part due to the strong relationships individuals within the WOW team had with private sector partners and wider networks, companies were positive about the added value and innovation that WOW brought them. Companies welcome the additional technical support as well as the ‘brand’ recognition of working with HMG – which brings leverage for social impact teams inside the company.
- Companies were willing to work on the difficult issues. Some of the companies WOW worked with were arguably ‘usual suspects’ that had some degree of existing commitment to gender equality – but this enabled WOW to move faster and further with them on addressing ‘difficult’ barriers to women’s economic empowerment including GBVH, social norms and climate change. These companies did not want to just work on increasing women’s agency (e.g. skills training).
- Collaboration between FCDO and companies takes time. Establishing the contacts, building the trust required and identifying potential activities/draft concept note can take six months. Early implementation and inception periods take around a year – to finalise concept notes, identify and secure local partners, agree MOUs with companies/business initiatives, identify and secure the appropriate experts, complete due diligence and gain FCDO sign off. So, a two-year window is an absolute minimum to enable implementation and MEL to occur. This suggests that in future, FCDO should consider working with fewer companies (especially if the funding is relatively low) but with greater depth and longer timeframes if the aim is to reach as many women as possible. Where timeframes are limited, the ambition should shift to supporting innovation and trialling new approaches, accepting that reach will be limited, though the potential long-term impact can be significant.
- A tighter thematic focus can help direct – and align with – business priorities and programmes. Women’s economic empowerment is multifaceted: some companies wanted to work on leadership, others GBVH, etc. In the early days, WOW was focussed on the 300,000 target and was willing to work with companies on a variety of issues related to women’s economic empowerment to achieve the bigger numbers. However, in the later stages, WOW focussed more intentionally on the theme of gender and climate change. This provided an opportunity to build evidence and expertise in a particular area and respond effectively to issues business were already starting to address in their supply chains. This meant WOW could ‘piggyback’ onto existing work streams which was vital given the tight timeframes.
- Working through industry bodies and business networks offers the chance to scale. Given WOW’s focus on women’s economic empowerment and global value chains, companies were a critical partner. Engagement centred on relationships with multinational corporations in the UK and leveraging multinational corporation involvement with industry networks. For example, WOWs work with Business A on women’s leadership in garment factories enabled WOW to develop a relationship with the auditor Sedex. WOWs work with major multinational corporation producing a wide range of consumer goods, including food, beverages, cleaning agents and personal care products also enabled WOW to leverage their membership of the Fair Circularity Initiative, with research on women waste pickers reaching five other major companies. The gender support provided to TCI will potentially benefit hundreds of smaller companies active in the plastics recycling sector. WOWs initial engagement with Acorn Rabobank, led to influence and work with a major standard setting body, the ICVCM, ensuring the work on gender and the voluntary carbon market was spread further. Establishing contact through companies not the Secretariats of these bodies is key.
- Localisation gets results and more co-creation is needed with suppliers not just at headquarters, but throughout the supply chain. Reaching the poorest and improving upstream supply chains requires a localised approach. WOW prioritised this in its later years including organising in-country events with the Malawian Government and HMG on the voluntary carbon market. This enabled those with most ability to respond with the right tools and information and led for example to the tea Association of Malawi commissioning a carbon market feasibility study. Local engagement also enabled cross fertilisation, which is why a new agreement to work together between Sasini PLC (Kenyan tea producer) and Sistema (Kenyan biodigesters company) is so promising.
- Looking only at the number of WOW business partnerships originally agreed can be deceiving and does not capture the wider impact. While WOW formally had 13 partnerships and MOUs signed, it is worth noting that activities sought to involve a much larger set of companies and organisations along the value chain. The initial Business D project in India engaged 22 local tea companies and global company, major multinational corporation producing a wide range of consumer goods, including food, beverages, cleaning agents and personal care products. WOW also contributed to building the skills and resources of local implementing partners, which was not recorded but was – and should be – a key part of any future programme. WOW helped strengthen Farm Africa’s knowledge and skills on gender risk analysis and gender transformative MEL approaches. WOW also provided Farm Africa and Business I with gender and social norms resources which they plan to continue using in future work with other partners.

Recommendations for future programming
- Ensure timeframes are realistic, and objectives are focused. In order to achieve targets that include large numbers of beneficiaries, a minimum five-year partnership is required. Innovations can be tested in two years, but longer-term impacts still need to be measured, and companies need to commit to continuing the work in some capacity once FCDO support has finished. In future, more narrowly defined programmes of work should be co-created with business. Data and insights methodologies and practitioners (as per WOWs Output 2 offer) should be engaged from the beginning to build the business case and help achieve internal and external scale.
- Work with companies to get traction with Industry bodies. Industry bodies or standard setting organisations are heavily influenced by the wishes of their members. If a large corporate partner suggests an action or work stream, then the membership body is far more likely to act quickly and rally other parts of the network behind the issue than if a donor organisation approached the industry body directly through its secretariat.
- Move away from ‘buying results’ and shift towards ‘systems’ and policy change for more lasting and sizeable impact. Given the many structural challenges that affect women in global supply chains, including low pay, lack of social protection, irregular market access and prices, future programmes should consider how to harness businesses voice as a partner to influence corporate governance and national legislation in the countries they are operating in. This collaboration would be invaluable, especially in programmes that are five to seven years in scope, as this allows time to shape and influence local, national and global processes.
- Try to reach beyond working only with the company’s social impact or corporate social responsibility teams. WOW predominantly worked with social impact or sustainability teams. These teams are the obvious entry point. However, future programmes might consider requiring companies to also engage other core functions within the business, potentially including procurement departments, human resources departments or corporate affairs departments.
- Prioritise working with local suppliers and strengthening local partners. Any future work with multinational corporations should prioritise working with national suppliers that act as “aggregators” where these exist. These firms they tend to operate as a gateway to a range of international brands and buyers and have wide reach to numerous smaller local firms and smallholders whose products they “aggregate” to provide the scale of exports required. They also often have less capacity and funds to deliver all the ESG requirements buyers are requesting. FCDO should also require programmes to intentionally take the lead from local implementing partners.
- Align programming with ESG reporting requirements for greater engagement with business. All sustainability teams in large companies are concerned with the new ESG reporting requirements. WOW has developed guidance for its most recent company partners to report on WOW activities against these frameworks and hosted activities on this topic to encourage more companies to follow suit. Future FCDO-business programmes should consider aligning around preparing, or supporting business to adapt to, regional or global standards as it provides a timely springboard for action. FCDO programmes should ensure consortia members include staff that have worked, or do work, inside companies to be part of the team.

Output indicator 1.1.2 – Number of learning products, resources, public documents and tools produced and disseminated and/or events and/or convening led by WOW to support information sharing, industry uptake and/or building the evidence base on WEE reaching targeted stakeholders – e.g. companies, policy makers, relevant academics and donors.

Key activities
Reports and tools: WOW exceeded its original target in terms of the number of tools and reports that were developed and disseminated. The target was increased in 2021/22 due to uncertainty over the funding available for project implementation with business: there was a recognition that developing tools and guidance with appropriate partners had the potential for greater reach and impact beyond the life of the programme. The breadth and depth of WOW’s resources is extensive, but a shortlist of some of the programme’s most recent products is provided below:
- 2025 – Aligning gender-related activities to EU Regulations. This report provides an overview of how organisations, based in, or trading in, the European Union (EU), can report against their gender-related activities in line with current and emerging EU regulations.
- 2024 – Investing in women’s economic empowerment to strengthen supply chain resilience: A toolkit for multinational companies with supply chains in low and middle-income countries. This was produced in collaboration with IDH (The Sustainable Trade Initiative) and Invest Africa. This was a Helpdesk initiative and therefore is not included as part of the total achieved number reported against this indicator. However, it is listed here due to its relevance for companies.
- 2024 – Integrating gender into the design, implementation and monitoring of carbon credit projects: Practical guidance for project developers in the voluntary carbon market. This was produced with support from the ICVCM.
- 2024 – Promoting cleaner cooking in Kenya through the Climate Resilience Programme. This report is not published on the WOW webpage. However, it was disseminated within FCDO.
- 2024 – An assessment of the promotion of improved cookstoves in the Climate Resilience Programme in Kenya. This report is not published on the WOW webpage. However, it was disseminated within FCDO.
- 2024 – Business Fights Poverty Gender Resource Kit. This is a dedicated webpage which hosts some of WOW’s key reports produced for a business audience. It also hosts WOW-funded interviews with John Lewis Partnership on Managing Gender Inequalities in Supply Chains and with Sedex on Ethical Supply Chain Management.

Events: A shortlist of some of the programme’s most recent events and/or engagements:
- 2025 - Wilton Park Dialogue: Productive sectors for green and inclusive growth. This event brought together brought together 43 participants across Africa’s private sector, investors, government, civil society and multilateral institutions to discuss how the private sector can best be supported and harnessed to support sustainable and inclusive economic development, including through the empowerment of women, young people and economically excluded populations and green growth models. Of the 25 attendees who filled out the post-event survey, 72% scored the event 5/5, and 28% 4/5 overall; with 96% reporting the event ‘encouraged networking and helped foster new relationships’, 96% that it achieved ‘Knowledge/idea sharing’, and 84% that it ‘encouraged open and frank discussions’.
- 2025 – How can we report on women’s equality in the new and evolving EU regulatory landscape? This hybrid workshop was co-hosted with Business Fights Poverty as part of their annual Global Equity summit. The workshop was attended by ~40 guests, including representatives from a variety of major organisations, including Cemex, Diageo and the International Sustainability Standards Board.
- 2025 – Farmers in Focus: A photography exhibition showcasing an innovative radio series supporting smallholder tea farmers in Kenya to adapt to climate change. This in-person event was co-hosted with Business D. The event was attended by 28 guests, including representatives from a variety of major organisations such as Associated British Foods, Invest Africa and the Kenya High Commission.
- 2025 – Informal women waste pickers in Indonesia. This online webinar was co-hosted with Business for Social Responsibility (BSR) and the Fair Circularity Initiative (FCI). The webinar was attended by 48 guests, including representatives from major organisations such as Astra Zeneca, Carlsberg and The Coca-Cola Company.
- 2024 – Beyond carbon claims: Spotlight on the wider social and ecological benefits of Natural Climate Solutions. This in-person event was co-hosted with the Natural Climate Solutions Alliance (NCSA). The event was attended by ~50 guests, including representatives from major organisations including the World Business Council for Sustainable Development, IFC and Nestlé.
- 2024 – Member webinar: WOW supply chain decarbonisation. At the request of Business I, this online webinar was conducted for Business I members. The webinar was attended by 10 guests, including representatives from major tea brands such as Bettys and Taylors of Harrogate, DAVIDsTEA, A.C. Perchs Thehandel, Whittard of Chelsea and Business D.
- 2024 – Integrating gender into carbon credit projects. This online webinar was co-hosted with the ICVCM. The webinar was attended by 50 guests, including representatives from major organisations such as United Nations, Global Green Growth Institute, BioCarbon Cert and NatuRe Capital.
- 2024 – Exploring equitable agricultural carbon finance opportunities in Malawi. This in-person conference was co-hosted with the Government of Malawi, the UK High Commission, and the USAID/UK Aid co-funded Modern Cooking for Health Forests programme. The event was attended by 111 guests, including representatives from organisations such as the ICVCM, Tea Association of Malawi, Africa Carbon Markets Initiative, United Nations Development Programme, and Tetra Tech.
- 2024 – Business roundtable: Empowering women for resilient global supply chains. This in person roundtable was co-hosted with Invest Africa. The roundtable was attended by 25 guests, including representatives from organisations such as Sainsburys, De Beers and Anglo American.
- 2024 – Wilton Park Dialogue: Building Women’s Economic Empowerment into Climate Transitions. This event brought together 53 participants from across governments, the private sector, academia, civil society and multilateral institutions. The conference objectives included to build a common understanding of gender inclusive climate transitions, share best practice, identify the roadblocks to achieving a gender inclusive green economy and agree on how these can be overcome. Of the 38 attendees who filled out the post-event survey, 53% scored the event 5/5, and 39% 4/5 overall; with 97% reporting the event encouraged networking and helped foster new relationships (and 3% ‘to some extent’), 84% that it achieved knowledge/idea sharing (and 16% ‘to some extent’), and 89% that it encouraged open and frank discussions (and 11% ‘to some extent’).

Lessons learned through this output
- WOW ensured that its tools aligned with emerging business priorities, policy developments and standards. The programme’s agenda was at the cutting edge of women’s economic empowerment debates. This was particularly the case for gender and climate change mitigation, adaptation and resilience where there was strong interest from companies to explore this agenda but very little practical guidance prior to WOW’s tools. WOW was able to respond quickly and fill knowledge gaps. This built WOW’s visibility and opened up conversations with potential new partners to work on climate and gender. WOWs final piece of work sought to ensure that gender activities undertaken by companies could be reported against in the new EU regulatory reporting landscape. WOW’s strong ‘political antennae’ helped WOW secure buy in from organisations it wished to work with and influence.
- Partnering with business dissemination networks is key to reaching the target audience. The WOW programme was unable to have a dedicated social media presence, and only a gov.uk website with limited options for formatting however, WOW built a strong relationship with the business network Business Fights Poverty which has 30,000 members, to widen the reach of its resources. This included the development of a tailored micro-site on gender for a business audience (profiling WOW’s tools), online and in-person events and webinars, blogs and social media activity. There were also significant collaborations with other organisations to promote co-created research and guidance building WOWs identity, visibility and credibility externally.
- The process of developing a learning tool or event is often as valuable as the output itself. WOW developed some excellent relationships and networks through approaching people to either co-author reports or inviting them to contribute to key reports. These partnerships also enabled wider dissemination.
- Rapid research with business partners can provide a great basis for future project implementation work. Developing research throughout the project cycle can also help to build buy in. For example, when funding was uncertain, WOW developed research partnerships with three companies to assess the impact of climate change on women in their supply chains. This research topic was co-created with the company and undertaken by local researchers identified by WOW. Once the research was completed it provide an excellent base from which to develop the subsequent projects when funding did again become available.
- Launches and events ‘in-country’ can help ensure findings lead to more action from local businesses (and engage HMG posts). Too often, reports and events are designed and delivered at global fora or in countries where companies are head quartered. WOW was keen to deliver more research and tools to relevant actors in the countries where projects were happening. For example, the Voluntary Carbon Market conference in Lilongwe Malawi, hosted with the Government of Malawi, FCDO and Tetra Tech, inspired the Tea Association of Malawi to conduct a feasibility study of carbon credits in tea sector across Malawi. Engagement by the High Commission in Malawi meant the event targeted appropriate business partners and enabled subsequent local follow up.
- Tools and guidance documents work well for a business audience. WOW worked closely with designers at Business Fights Poverty to ensure that its guidance and lessons were in formats that would work well for business audiences. This meant ensuring that the documents looked professional and well-designed but crucially included a clear business case for action and appropriate business relevant insights and recommendations that could be easily used by sustainability staff to include in presentations to senior leaders. A variety of formats were harnessed including video interviews and highlights clips from WOW events, all of which can more easily be shared on LinkedIn. Overall, the outputs need to be timely, relevant and short to be of value to an audience that is often time poor and results driven.

Recommendations for future programming
- Undertake MEL activities to track the impact, reach and influence through guidance and events. MEL activities should be woven into the planning of events e.g. Mentimetre polls or Survey Monkey feedback surveys should accompany all online webinars and events. Additionally, follow up interviews with a small group of attendees or research partners should occur at six month and annual intervals to assess what impacts might have resulted from the report findings or use of the guidance tools.
- Align tools and guidance with emerging corporate or regulatory agendas to secure buy in and increase uptake and interest. Do not allocate all the programme’s research budget straight away. Keep some funding available to respond reactively throughout the programme.
- Include strong learning partners and business communications channels in consortia. This could include a university or research partner and a business network or communications consultancy. This will enable both robust research and increased likelihood of business buy-in (if they are hearing it from a business organisation). Wherever possible these should be local/nationally relevant organisations, not solely global organisations.

Output indicator 1.1.3 – Number of organisations engaged by WOW on gender-sensitive climate-smart policy and practice change.

Overview
The WOW programme engaged with a variety of networks, standard setting bodies and other organisations on gender and climate change including (but not limited to): 2x Challenge, Business Fights Poverty, Endeavour Mining, Farm Africa, Fair Circularity Initiative, Harvard Kennedy School’s Corporate Responsibility Initiative, IDH, Natural Climate Solutions Alliance, TCI, U3 Agrinet, United Nations Global Compact, USAID WEE Community of Practice, World Business Council for Sustainable Development and Women’s Safety Accelerator Fund.

Integrating gender into the design, implementation and monitoring of carbon credit projects report case study
Through WOW’s engagement with key market stakeholders, the team discovered a lack of guidance outlining the ways in which project developers could practically embed gender-inclusive approaches into carbon crediting activities, so developed a pioneering piece of guidance to fill this gap, supporting project developers, such as those within the WOW programme, to incorporate gender considerations into their activities.
A number of organisations supported the dissemination of this report, both via social media (e.g. LinkedIn) and articles. Such organisations include Gold Standard, the ICVCM, IndigoAg, the NCSA, Permian Global, Plan Vivo, Pollination, Save the Children, Southpole, UN REDD+, Voluntary Carbon Markets Integrity Initiative, Verra and W+. Ahead of New York Climate Week in September 2024, WOW provided briefings to PwC attendees of the ICVCM’s Accelerating Climate Action: Delivering High-Integrity Carbon Markets event, as well as the United Nations’ Gender Equity and Climate Change event. Similarly, ahead of COP29 in November 2024, WOW provided briefings to PwC panellists at the Women in Sustainability panel which sought to highlight the invaluable role women play in driving environmental innovation, addressing climate challenges and fostering equitable and resilient communities.

Output indicator 1.1.4 – Key activities undertaken by WOW to influence unpaid care considerations in global value chains.

Reports:
- The Double Day: Exploring unpaid work and care for female garment workers in Bangladesh was based on 70 interviews with garment workers to understand how much time they spent working outside the factory.
- Unpaid and unrecognised: How business can realise the benefits of tackling women’s invisible labour, was a guidance tool.
Partnerships: Both the Business I and Business J partnerships designed specific resources to encourage a focus on gender norms. - Business I’s ‘Family Business Management Training’ encouraged couples to work together to share caring responsibilities and make financial decisions together. One of WOW’s first partnerships, with Business B, specifically aimed to develop a commercially viable pricing model to account for unpaid work and care that women were undertaking in hemp mitt supply chains in Bangladesh.
Output Number and Title		Output 2 – WOW pursues effective partnerships with companies to improve data and information on women's work in the supply chain
Output Score		A
Impact weighting (%)		11%	Impact weighting revised since last AR?	Yes, up, to give average weighting for programme lifecycle

Output Indicator	Final Target		Achieved	Narrative
2.1.1 Number of partnerships (with companies/business initiatives) with improved collection and reporting of gender-disaggregated data in their supply chain as a result of WOW recommendations/influence.	3		3	Met target. / (Business A, Business B, Business C) / Results are as of 2021 when work on Output 2 stopped due to WOW budget cuts
2.1.2 Number of country-level supply chain mappings conducted (through deep dive cases).	3		3	Met target. / Results are as of 2021 when work on Output 2 stopped due to WOW budget cuts

Key Activities
Output 2 of the WOW programme sought to collaborate with multinational companies, industry bodies and research institutions, to improve gender-disaggregated data collection and transparency in global supply chains to drive systemic change. The focus was on developing methodologies, providing technical assistance, and ensuring businesses had the tools to identify and address gender disparities in their supply chains. WOW bridged the gap between research and corporate action, ensuring businesses had the necessary tools and insights to embed gender-sensitive practices into supply chain management.

Between 2019 and 2021, WOW engaged with several companies to conduct research to better understand the risks and opportunities related to women in supply chains – with resulting publications listed under ‘achievements’ below. This research was undertaken at three levels:
- Macro-level: global supply chains. WOW worked with Sedex, the Ethical Trading Initiative (ETI), OECD and International Trade Centre (ITC), to influence how gender-disaggregated data is incorporated into global compliance frameworks and ethical sourcing initiatives. WOW played a critical role in influencing Sedex’s Supplier Assessment Questionnaire, ensuring that gender indicators were integrated into ethical trade compliance for over 60,000 member companies worldwide (over 86,000, as of 2024). The programme also engaged with the International Labour Organization, World Trade Organization and ITC to advocate for the inclusion of gender data in global supply chain governance frameworks.
- Meso-level: company supply chains. WOW collaborated with companies to conduct research, pilot gender mapping methodologies and improve company-level data collection processes. For example, Business A adopted a new gender-sensitive framework to track supply chain worker demographics, and Business B incorporated WOW’s unpaid care and hidden labour tool into its Sustainable Sourcing Charter.
- Micro-level: country-specific supply chains. WOW conducted sector-specific research on garment workers in Bangladesh, agricultural workers in Kenya and personal care value chains. These case studies highlighted key gaps in assessing women’s roles in supply chains and provided recommendations for improving visibility. The findings were used to develop guidance documents, training materials, and recommendations shared with both companies and policy stakeholders.

Year 1 (2018 to 2019): In its first year, WOW laid the groundwork for improving gender data transparency in supply chains, with a primary focus on developing a structured methodology and building partnerships with companies for Output 1. The first major priority in 2019 was piloting gender mapping methodologies and testing research approaches with multinational companies. Preliminary discussions were held with Business C, Business A and Business D, laying the foundation for deeper collaboration.

Year 2 (2019 to 2020): By 2020, WOW had deepened its engagement with corporate partners while expanding its influence on global policy discussions. The onset of COVID-19 required a shift in priorities, leading to rapid-response research on the pandemic’s impact on women workers in supply chains. Despite the pandemic’s challenges, WOW maintained momentum in corporate engagement and policy influence.

Year 3 (2020 to 2021): The COVID-19 pandemic necessitated a shift in research focus, leading to rapid-response assessments on its impact on women in supply chains.

Year 4 (2021 to 2022): By 2022, WOW had established itself as a leading programme in gender-responsive supply chain governance. The focus shifted to scaling impact, disseminating findings, and ensuring sustainability beyond the programme’s lifecycle. Given the WOW budget cuts, no new Output 2 deliverables were planned for 2022. Final research outputs were shared with industry bodies, academic institutions and corporate partners, ensuring that WOW’s methodologies remained in use beyond the programme’s duration.

Output 2 successfully met and/or exceeded its targets, becoming a key asset for businesses seeking better data and understanding of women's roles in their global value chains.

Key achievements
- In April 2018, the Women Workers in Global Value Chains research brief was published, providing an overview of WOW's research. A second WOW research brief, offering an overview of available macro data on women in global value chains across priority sectors, was signed off by DFID and published in November 2018.
- A World Economic Forum (WEF) policy paper on the System Initiative on Shaping the Future of International Trade and Investment, Global Value Chain Policy Series: Gender, was completed and disseminated at the WEF Sustainable Development Impact Summit in September 2018. The paper draws on research from WOW, focusing on garments and horticulture, and examines the gender profile of work in global value chains, challenges in accessing better information on women workers, opportunities and challenges for women, and related strategies being pursued by companies and policymakers.
- In July 2019, WOW conducted a deep-dive study in the Bangladeshi garment sector with Business A. This research tested the WOW Research Guidelines, expanded understanding of women's leadership roles within the sector, and served as a pre-baseline for the Business A partnership under Output 1.
- In January 2020, WOW hosted a convening workshop – “Women in Global Value Chains: Enhancing Visibility and Influence.” This workshop brought together 29 companies, practitioners and researchers all actively engaged in data-related initiatives on gender and global value chains, with a view to enhancing the collection, recording and reporting of gender data in global value chains.
- Business C published a comprehensive study on the unpaid work and care carried out by garment workers in Bangladesh, highlighting the significant contributions of women in the supply chain that were previously invisible. Notably, this report found that women work a “double day,” averaging an additional seven hours per day on unpaid work and care, compared to less than three hours a day for men. By bringing attention to the unpaid labour of women, Business C set a precedent for other companies to recognise and value the hidden contributions of their workers.
- In 2020, Business B. tested WOW’s unpaid work and care tool – which helps to identify and address hidden labour within supply chains – in Chhattisgarh, India. This test was successful, and Business B. subsequently began the process to incorporate this tool into their Sustainable Sourcing Charter.
- In response to the COVID-19 pandemic, WOW reallocated resources to conduct rapid research on its impact on women workers in global value chains. This research provided timely insights into the challenges faced by women during the pandemic.
- WOW developed case studies and received feedback from partners, such as Royal Holloway College, University of London, which used WOW's Building Back Equitably report to frame their own research on the impact of COVID-19 on Cambodian women garment workers.

Lessons learned
- Corporate engagement requires sustained effort and trust. Companies are often hesitant to change data collection practices due to confidentiality concerns and operational complexities. WOW’s experience with Sedex showed that working through industry platforms, rather than individual companies, was more effective in driving gender data transparency and broader industry change.
- Accessing and using company data can be challenging due to delays in securing agreements and poor data quality. Data on women workers in global value chains was often unreliable, with social audits failing to capture issues like gender discrimination, harassment and abuse. These challenges caused delays in research and project timelines.
- Handling sensitive company information should be planned into programme design, monitoring and implementation. FCDO programmes should anticipate the delays and special handling required to maintain corporate trust, especially when using NDAs and confidentiality agreements.
- Workforce data on unpaid work, hidden labour, and leadership roles was difficult to capture, and firms were often hesitant to invest in better data collection. Engaging social compliance platforms was key to driving change, but building relationships and securing buy-in from member firms required time and long-term commitment.
- Early engagement with companies helped shape the programme. Involving businesses from the start allowed for better planning of data collection and ensured the research methodology was relevant and actionable.
- Output 2 targets were not only met but often exceeded, making it a significant selling point for businesses seeking better data and understanding of women's roles in global value chains. Partnerships with companies like Business C and Business A proved to be highly impactful, leading to significant improvements in the visibility and quality of data regarding women's roles in supply chains. However, resource constraints sometimes limited the ability to fully capitalise on these partnerships, underscoring the need for adequate resources to sustain and expand such initiatives.
- The programme was highly adaptable to external challenges like COVID-19. Resources were reallocated to conduct rapid research on the pandemic’s impact on women workers in global value chains, ensuring WOW remained relevant and able to support informed decision-making.
- WOW research provided strong value for money. Partners made efficient use of resources, delivering both credibility and actionable insights for businesses. The research played a dual role, offering immediate support to firms while also strengthening partnerships for future collaboration.
- Budget constraints brought along challenges, limiting the ability to recruit external reviewers – in particular those with high rates – and fully implement planned activities. Despite these limitations, WOW continued to produce valuable research and toolkits, highlighting the importance of efficient resource allocation and cost-effective impact measurement. WOW introduced mechanisms to capture additional, unplanned impacts of its work, such as insights, learning and challenges. This approach facilitated continuous improvement and adaptation based on real-time feedback and evolving circumstances.

Recommendations for future programming
- Incorporate contingency funds or co-financing mechanisms into programmes. This ensures continuity and allows critical research and partnerships to proceed even when financial constraints arise. Budget constraints posed challenges for Output 2, limiting the scale of planned partnerships and delaying additional supply chain mappings. The cancellation of research partnerships with Business D and Global G.A.P. due to funding shortages underscored the need for more flexible funding models. This contingency funding can be difficult for a donor-funded programme at the time of budget cuts/uncertainties. However, if the donor programme had anticipated potential co-funding with other donors or the private sector, some of the funding needed for the research or supply chain mapping could have been raised.
- Enhance quality assurance in programmes as a priority. The WOW programme primarily relied on private sector stakeholders for feedback. To strengthen verification and research credibility, future initiatives should consider appointing an External Reviewer to assess data collection quality, provide an independent challenge function, and advise on research and intervention priorities. Additionally, integrating academic quality assurance would add another layer of scrutiny, ensuring that findings are not only robust but also contribute to valuable, evidence-based decision-making in policy and programme development.
- Invest in research pieces that drive action and commitments from the private sector. Research outputs should be strategically designed to encourage private sector commitments and action. Developing a research, learning and output plan will help future programmes identify collaboration and research opportunities that can be advanced once funding becomes available. A well-considered plan will help to maintain momentum and engagement from key stakeholders.
- Expand research partnerships to include diverse organisations. Initiatives with similar research components to Output 2 should include more national and regional expertise to provide new perspectives and contextually relevant insights. This diversity in research partnerships can lead to more innovative findings and enhance the overall impact and applicability of programme outcomes.

Output Number and Title		Output 3 – WOW provides effective knowledge, advice and support for delivering WEE through DFID and HMG programmes through a Helpdesk
Output Score		A
Impact weighting (%)		23%	Impact weighting revised since last AR?	Yes, down, to give average weighting for programme lifecycle

Output Indicator	Final Target		Achieved	Narative
3.1.1 – % of Helpdesk queries delivered receiving positive feedback from the support recipient (regarding satisfaction, responsiveness and timeliness)​.	80%​		96%	Met and exceeded target.
3.1.2 – % of Helpdesk support requestors that report positive change related to improved confidence, knowledge or 'know-how' on issues related to WEE.​	80%​		91%	Met and exceeded target.
3.1.3 – Number of ‘Targeted Guidance’ documents produced and proactively disseminated to improve information sharing and knowledge about best practices on WEE.​	5​		5​	Met target.

Overview
The WOW Helpdesk’s mandate was to increase knowledge and support for delivering women's economic empowerment through DFID/FCDO and HMG economic development programmes so they could reach larger numbers of women beneficiaries and improve global knowledge on how to deliver results for women and girls through economic development interventions. The Helpdesk outputs were divided into three main activities: Evidence Digests, Targeted Guidance and Helpdesk Queries.

Throughout the lifespan of the programme, the WOW Helpdesk completed two pilots and responded to 106 requests for support. Of these 106 requests, 42 were directly programme facing. These included those that shaped the design of new programmes, such as a programme funded through FCDO Turkey, targeting refugees (from Syria and other countries) residing in Turkey. They also included those that improved delivery of existing programmes. For example, Query 48 Global Future Cities Southeast Asia – Gender and Inclusion Impact Assessments and Action Plans reported, “This product has helped us to improve the participation of women and excluded groups in the projects that the delivery partner is running by getting them to reconsider the design of parts of the project to include better consultation. We are better able to track this through our MEL systems.” 38 of the 42 programme facing queries reported plans for improved design or to reach higher number of women beneficiaries after receiving support from the Helpdesk.

Over the course of the WOW programme, the WOW Helpdesk produced 13 Evidence Digests. These communications were distributed across the DFID/FCDO network and uploaded onto the UK Government’s WOW webpage to broaden their reach. These Digests typically included summarised findings and recommendations from WOW Helpdesk work that was of interest to a broader audience, as well as collated news and lessons from other activities across the WOW programme. Whilst the aim was to write and distribute Evidence Digests on a quarterly basis, lack of WOW Helpdesk team availability during busy periods, as well as FCDO budget cuts, resulted in less regular distribution than was envisaged.

Five Targeted Guidance documents were produced throughout the duration of the programme:
- Targeted Guidance 1: Promoting economic empowerment for women in the informal economy (2019)
- Targeted Guidance 2: Measurement of women’s economic empowerment (2020)
- Targeted Guidance 3: Women’s economic empowerment and climate change: A primer and Women in the net zero economy: On changes in garment, agriculture and energy supply chains (2021)
- Targeted Guidance 4: No such thing as a free lunch: Investing in and addressing unpaid care and domestic work – the missing component of equitable development (2023)
- Targeted Guidance 5: Investing in women’s economic empowerment to strengthen supply chain resilience (2024).
These are proactive guidance and support on priority themes for women’s economic empowerment across the FCDO’s Economic Development portfolios. The WOW consortium and FCDO teams collaborated on the choice of themes and aimed to address ‘gaps’ across FCDO central and country teams. The methodology largely consisted of desk-based, secondary research, however, there were several desk-based interviews most notably for the Targeted Guidance on Supply Chain Resilience. This topic lacked evidence online, a gap which was filled with information from interviews with businesses. The Helpdesk collaborated with IDH and Invest Africa for these interviews and conducted a business roundtable. For the Targeted Guidance on Measurement of Women’s Economic Empowerment, the Helpdesk received three days of pro-bono support from Mayra Buvinic, one of the world’s leading experts on women’s economic empowerment data.

DFID/FCDO was the primary audience for the first four Targeted Guidance. The first three were presented to DFID/FCDO staff to discuss the implications of the findings, how to convert recommendations into practice and how to measure subsequent improvements. The WOW Helpdesk also reached secondary audiences though blog posts, social media posts and newsletters. There was no official dissemination event of the Targeted Guidance 4 on Unpaid Care and Domestic work, as there was not sufficient capacity amongst a broad audience at FCDO to absorb this much detailed evidence on the issue. The fifth Targeted Guidance was aimed at a business audience to avoid targeting an FCDO audience without capacity to engage once again. Written as a toolkit for multinational companies with supply chains in low and middle-income countries, it leveraged the ‘added value’ of the learning that emerged from WOW Programme Output 1 and capitalised on growing interest in FCDO in responsible business. The toolkit was launched at the UN Global Compact UK Network Annual Summit 2024, which was attended by 500 people in London and several hundred online.

The Helpdesk was an on-demand service available to DFID/FCDO and HMG staff working in international economic development policy and programmes in ODA eligible countries. It drew on a wide pool of expertise to provide rapid, flexible, tailored and specialist analysis guidance and ‘know-how’ on women’s economic empowerment. The Helpdesk process was adapted throughout the programme to respond to feedback from users. The nature and complexity of requests for support changed during implementation, which led to larger and longer queries, as well as collaborations with other FCDO Helpdesks such as the Disability Inclusion Helpdesk and Social Protection Technical Assistance, Advice and Resources Facility. The majority of the support provided by the Helpdesk (55%) was not geographically specific, around a quarter related directly to Sub-Saharan Africa. Thematically, there were three main areas of support: general support on women’s economic empowerment; climate change, environment and green growth; and infrastructure, investment and trade. Other themes included health, humanitarian emergencies and conflict situation, and agriculture and land, amongst others.

In December 2018, the WOW Helpdesk and Prosperity Fund entered a Framework Agreement that allowed the WOW Helpdesk to support Prosperity Fund programmes. The overall goal of the WOW Helpdesk support was to build capacity and strengthen the Prosperity Fund’s approach to women’s economic empowerment for inclusive growth and poverty reduction. The Helpdesk completed 21 queries for the Prosperity Fund, comprising of 20% of overall Helpdesk Query service. From the engagement with Prosperity Fund, the Helpdesk found there is less evidence available from middle-income countries and used data from high-income countries where relevant. Feedback from Prosperity Fund advisers noted the high quality of the work, timeliness and improved design for impact and/or reached higher numbers of women beneficiaries.

Satisfaction levels of quality of work and responsiveness work was high. 92% of respondents scored 4 or 5 out of 5 for the question “How satisfied overall are you that the WOW Helpdesk response to your request is likely to be useful for the purpose intended?” 99% of respondents scored 4 or 5 out of 5 for the question, “How satisfied are you that we responded to your query in a timely fashion?” 83% of the Helpdesk users that responded to the endline survey scored 4 or 5 out of 5 on Knowledge/ overall satisfaction: The Helpdesk support has increased my awareness of evidence to design and /or implement programmes that improve WEE outcomes. 70% scored 4 or 5 out of 5 to Planned or Actual application of knowledge: I plan or have already made changes to a programme around: Design; Outcomes around WEE; targets for women’s participation or empowerment; MEL systems that capture changes in WEE; Other. This represents a solid achievement given the unexpected disruption resulting from COVID-19 response, whilst acknowledging some room for improvement. There were also external factors that affected the opportunity to translate Helpdesk products into programme outcomes. For example, some programmes were affected by budget cuts and unable to implement recommendations made by the Helpdesk.

Lessons learned
- Measures should be put in place to manage peaks and troughs in demand. It is challenging to predict changes in demand and therefore workload, but any Helpdesk team should have mechanisms to manage these fluctuations in advance and communicate any challenges with Helpdesk staff availability to FCDO. During busier times, the WOW Helpdesk did not always meet the challenge of managing peaks in Helpdesk demand, delivering outputs much slower than initially drafted timelines, with unsatisfactory communication on why this was and when drafts could be expected. This lowered trust in the service from requesters.
- Evidence Digests effectively disseminated the latest evidence to time-constrained FCDO staff and increased demand for Helpdesk support. According to FCDO advisers, the short nature of this product meant that it was more likely to be read, keeping women’s economic empowerment on the agenda. The examples of demand-led Helpdesk work also inspired others to submit requests for support: the Helpdesk often experienced a surge in demand after the Evidence Digest was circulated.
- Targeted Guidance and on-demand Helpdesk queries are most effective when tied with an event as a useful ‘hook’. For example, The Women’s Economic Empowerment and Climate Change: A Primer was 'timely’ as it provided key messaging for the UK Government that could be shared at the Women Deliver conference in March 2021 and at COP26 in October and November 2021. It was also presented during Earth Day on 22nd April 2021. Targeted Guidance 5 was presented at the UN Global Compact UK Network Annual Summit 2024.
- WOW Helpdesk work has greater reach and impact when it has the engagement of a senior FCDO official. For example, FCDO Chief Economist, Director of Economic Development and Chief Statistician participated in the Women’s Economic Empowerment Measurement Targeted Guidance which resulted in high attendance at the presentation of findings and recommendations from this research.
- FCDO staff changes can affect the ownership and impact of WOW Helpdesk work. When staff move posts, the original objectives of the request can become unclear, and momentum can be lost. This can delay the process – and the output – and impact dissemination and engagement with the work. To mitigate this risk, the WOW Helpdesk identified secondary points of contact in the ToRs and concept notes, who could commit to taking the work forward should the original requestor leave their post.
- Helpdesks can make useful inputs into the UK Government’s policy influencing work (even though they are not designed in this way). The WOW logframe only captured the number of programmes that report plans for improved design or reach higher number of women beneficiaries. However, 60% of support delivered by the Helpdesk was categorised as ‘policy influencing’ and therefore did not contribute to the indicator target. The merger between DFID and FCO in September 2020 and the ODA cuts likely contributed to an increase in the proportion of queries on policy influencing over the course of the programme.
- It is useful to complement the written reports with briefing meetings. Detailed written products are most helpful to the requestor and staff working in different geographies and times zones. However, to engage a wider audience, short meetings to present findings and recommendations were valuable. They gave the attendees an opportunity to ask questions and provide comments. There was also demand for shorter designed and practical products with infographics to increase uptake of evidence.
- Brief and early discussions on the objectives of the work ensures clarity on deliverables. Helpdesk users sometimes approached Helpdesk with an outline idea of the purpose of their request and its nature and looked for support in shaping their idea into a focused and achievable piece of work. When it became clear that written requests could not always be sufficiently detailed or nuanced, the Helpdesk introduced an early call with the requestor, to ask questions and clarify the information necessary for a ToR.
- For country-level or regional-level requests, it is important to engage experts from that geography. This ensures that there is a contextual understanding of women’s economic empowerment and that local networks can be used. For example, on Ukraine queries, a Ukrainian team member was able to suggest individuals who could be interviewed and advised on the appropriate language to use (e.g. the word ‘conflict’ is a contentious word among Ukrainians who instead prefer ‘war’ or ‘full-scale invasion’). For another query, an Afghan team member provided guidance on sensitive topics and language (e.g. ‘De Facto Authorities’ rather than ‘Taliban’). She also provided advice on the ethics of conducting research with representatives from women’s rights organisations and women activists.
- A crucial role for any Helpdesk is to raise awareness of the services. While there is strong interest among FCDO staff for using a centrally funded Helpdesk, many FCDO (and other UK government staff) were not aware of its existence. Evidence Digests and presentations prompted staff to contact the Helpdesk. The SRO and Programme Responsible Owner (PRO) played crucial roles in ensuring that the Helpdesk was regularly advertised and signposted to staff internally, and to channel requests to the Helpdesk team. Before presentation of the Informal Work Targeted Guidance, FCDO’s publicity worked well in raising interest and securing high-level participation.
- Writing for a non-technical audience will lead to greater reach and impact of Helpdesk work. Many readers are not experts of women’s economic empowerment so it is important not to assume much prior knowledge. The Helpdesk found these users often valued talking through the report.
- Using case studies and examples allows Helpdesk requestors to think about ways they could be adapted for other contexts. For country-level requests, the most useful case studies are those from other countries in the region. Presentations can be a useful way to discuss with Helpdesk requestors how case studies from other contexts might be adapted. One Helpdesk requestor noted that the Targeted Guidance on Measurement of Women’s Economic Empowerment was well used as it had a menu of suggested indicators, which is often a request from FCDO advisers. These indicators can be tailored, depending on the context and the remit of the programme or policy.
- Demand for the Helpdesk is slower after a period of budget cuts and significant marketing needs to occur after any pauses in operations. The Helpdesk had to stop operations in August 2021 due to budget cuts. FCDO teams had been informed of the Helpdesk closure, leading to uncertainty about whether the Helpdesk was still available as a pre-paid service to HMG staff. It took time to raise awareness that the Helpdesk was open to responding to requests again.

Recommendations for future programming
- Refine the feedback mechanisms. Feedback is important for providing data for logframe targets and to allow the Helpdesk to adapt to maximise potential outcomes. It was often challenging to gain feedback from the Helpdesk users who did not always have the time to provide in depth responses or fill in feedback forms (there was a degree of ‘feedback fatigue’) and due to staff turnover at FCDO. As a result, the Helpdesk streamlined the feedback process by eliminating the need to answer baseline information. They also highlighted that feedback was a mandatory part of the request process. However, the Helpdesk has still had to rely on the PRO to chase feedback on ‘quality and timeliness of work’ and the ‘use of the service’. Providing feedback at a late stage is challenging due to memory loss, so a Helpdesk may consider a cut off period. After collection of feedback, the WOW Helpdesk could also consider offering further support to an HMG requestor. Feedback on Targeted Guidance did not happen in a systematic way during WOW implementation: any Helpdesk should consider how attendees from dissemination events intend to use the findings and recommendations.
- Impact of AI: It is important to consider the impact of AI Technologies on Helpdesk demand and type of services it can provide in the future. Given the availability of advanced AI Models and availability of fit for purpose data, we should be able to produce evidence summaries at a much lower cost and at much greater speed. This has the potential to reduce the demand for services which look to summarise or reframe pre-existing information in general terms for a non-technical audience. Whereas, research demand for complex or niche areas is likely to increase, especially in those areas which are emerging with lack of evidence. Similarly, future Helpdesk may focus more on providing technical and tailored advice to programmes. It is important to note that AI can disrupt engagement metrics for Helpdesk site. As people move away from using web browsers to access information and use AI chat bots instead. Chatbots present the same information as web browsers but they do not lead a user to the content site, thereby reducing visibility of the site.
- Opportunities to custom build AI Chatbots: A future Helpdesk function could explore building an AI Chat bot which is trained on published Helpdesk materials – either built in house or by external experts. This could be released for public use pending appropriate quality assurance.
- Set up institutional mechanisms and incentives for use of a Helpdesk at the start of the programme to improve impact on women’s economic empowerment outcomes. When women’s economic empowerment is integrated into a programme’s business case, theory of change or logframe from the start, the potential for impact is maximised. The SRO and PRO could alert the Helpdesk team to any other programmes that are being designed, facilitate a connection and offer their support in the development of the business case, theory of change or indicator review. This is particularly true for non-women's economic empowerment experts at FCDO who are less likely to be aware of the Helpdesk and may not be aware that their designed programme does not (and should) have a gender, disability and social inclusion focus.
- Broaden outreach to new FCDO users and to other UK government departments. Departments beyond FCDO can require the support of a Helpdesk on women’s economic empowerment in low and middle-income countries. The Helpdesk team could present in key departmental meetings, platforms or at international events where many staff will be present who may not describe themselves as ‘gender advocates’. For further outreach, a Helpdesk could consider having monthly ‘drop-ins’ for individuals to discuss women’s economic empowerment – to answer immediate questions and/or develop a Helpdesk request. These monthly drop-ins could be rotated across different regions to accommodate different time zones and play a role in marketing the Helpdesk more widely.
- Have a strong focus on dissemination beyond FCDO. The Helpdesk produced over 100 demand-led queries, 11 Evidence Digests and five Targeted Guidance. Many of these reports are relevant beyond FCDO and could inform the policies and practices of other institutions focusing on women’s economic empowerment. There is an opportunity to disseminate them further at conferences, international events and in social media campaigns.
- Integrate broader social inclusion in all Helpdesk requests. In initial discussions with Helpdesk requestors, team members can encourage requestors to consider broader inclusion beyond gender wherever possible, referencing women with disabilities, adolescent girls and women internally displaced persons and refugees.
- Cultivate close working relationships with other FCDO-funded Helpdesk services. Increasingly, FCDO advisers requested work that incorporated a deeper understanding of disability and gender, so collaborations with the Disability Inclusion Helpdesk took place. Other Helpdesks can also help with marketing. Future collaborations with other Helpdesks or organisations are not without risks, however, as there is less control over the work carried out for individuals contracted elsewhere and any Helpdesk should alert the requestor early on if a collaboration is not feasible.
- Reduce the length of time between the first request and the kick-off meeting with the WOW team that will implement the work. The WOW Helpdesk used the development of detailed ToRs to agree the scope of work, timelines, audience and quality with all parties. However, drafting ToRs can take time (especially if there is a surge in demand for Helpdesk services). In future, Helpdesks could consider short calls with requestors, followed by a bulleted summary of the request which everyone can agree. It is also important that first drafts of deliverables also reach requestors according to agreed timelines.
- Set up meetings to discuss recommendations in a WOW report, to ensure they are practical, actionable and contextually relevant. There was often demand from FCDO advisors to have a question on recommendations in any ToR for an evidence review. However, it was challenging for consultants to understand priorities, budgets and context within FCDO and to know which recommendations could be taken up. Therefore, once draft recommendations were written up by WOW authors, it was useful to set up a meeting to discuss and refine the recommendations, including who could take them forward, by when and how. This approach ensured buy-in, as the recommendations were built together.
- For larger, slower paced and non-confidential queries, include paid, in-country Reference Groups in the shaping, reviewing and dissemination of the deliverables. The WOW Helpdesk often incorporated voluntary interviews with key stakeholders. However, Reference Groups, comprised of diverse members, could be formed with a higher level of involvement and would ensure that WOW deliverables are better tailored to the context. Members could include representatives from civil society, women’s business networks, organisations of people with disabilities and government. This would help to ensure that these groups benefit from and use the research provided. It could also help to create strong and mutually beneficial relationships with FCDO.
- Consistently ensure that local experts are included in teams responding to country/regional-level based requests. Working with local consultants or a Reference Group could mitigate any risk of misunderstanding the local and national dynamics, including the political economy. During inception, any Helpdesk could look to increase the number of local experts in its roster across FCDO priority countries that could be mobilised at short notice. In exceptional cases, an international expert could be embedded in a Country Office (although this could be costly).
- Consider using logframe indicators that capture outcomes on policy influencing, capacity building as well as programme design/implementation. The WOW Helpdesk received increasing demand for policy influencing work (see lessons learned section) and this is likely to continue in the future. Helpdesk teams should work closely with MEL advisers on suitable indicators to capture capacity building and political access and influence. Collection of feedback for policy influencing should take place after at least a year has passed, as policy change can take longer to occur. The SRO and Helpdesk team should agree the balance between FCDO capacity building, programme-facing work and policy influencing.
- Agree criteria to determine which requests to prioritise. When there were surges in demand for the Helpdesk, queries had to be prioritised. The WOW Helpdesk often asked the SRO for advice on how to prioritise, but objective criteria could be valuable. These could include the expected level of impact (e.g. a business case or logframe review at the start of a programme) or queries from countries with the lowest income or the lowest female labour force participation.
- Ensure long-term access to the Helpdesk and prevent ‘stops’ and ‘starts’. In August 2021, the WOW Helpdesk was asked to pause all billable work, with operations resuming a year later. In 2022, FCDO staff were not aware that funding and Helpdesk support had resumed and, initially, there was slow demand.
- Seek and create synergies with other technical assistance facilities or events where WOW outputs and findings can be shared. The WOW Helpdesk is listed as a technical assistance facility that provides support on climate with a gender, disability and social inclusion lens on FCDO’s Climate, Environment and Nature (CLEAN) Helpdesk. In future, the CLEAN Helpdesk website will feature WOW products relevant to climate justice, which will maximise reach and will continue to be shared beyond the end of the WOW programme. WOW resources have also been included in the FCDO’s Promoting Equalities Regional Programme (PEP-R) website, which lists a range of gender, disability and social inclusion reports from FCDO-funded programmes and beyond. In addition, WOW’s Team Leader discussed WOW’s work on driving economic empowerment for women in supply chains in a video interview featured on the PEP-R website.

Output Number and Title	Output 4 – WOW purses effective partnerships and initiatives that respond to DFID priorities from UNHLP agenda through the WOW Fund
Output Score	A+
Impact weighting (%)	15%	Impact weighting revised since last AR?	Yes, down, to give average weighting for programme lifecycle

Output Indicator	Final Target	Achievement	Narrative
4.1.1 – WOW fund grantees deliver project activities as per the agreed workplans which contribute towards improving unpaid care work, informal work and land tenure.	On average, WOW grantees score at least green (i.e. score above 80% as per the WOW RAG rating) in implementing the annual workplan.	WOW achieved green status in Year 5 (i.e. WOW year September 2022)	Met target
4.1.2 – Number of women reached by interventions supported through WOW Fund grants with increased awareness, information and/or knowledge on issues related to unpaid care work, informal work and land tenure that expand economic opportunities/choices.	5,239	48,689	Met and exceeded target. / The WOW Fund engaged with a total of 48,689 women. Of which: / 32,879 were reached directly through WOW Fund core activities. / 3,666 women were reached indirectly through Promundo-US / 12,144 women were engaged directly through COVID-19 response activities in 2022.

Overview
From 2018 to 2022, the WOW Fund supported civil society organisations working on strategic initiatives to promote long-term change in women’s economic empowerment and progress the Action Agenda of UNHLP. These initiatives focused on three areas.
1. Enhancing land tenure security for informal women workers delivered by implementer SEWA Bharat alongside SEWA Delhi, SEWA Bihar, SEWA Grih Rin and the Indian Institute of Human Settlements.
2. Recognising, reducing and redistributing unpaid care and work for women delivered by lead implementer Promundo-US, alongside Rwanda Men’s Resource Center and Sonke Gender Justice in South Africa.
3. Improving outcomes for women in informal work delivered by lead implementer WIEGO, alongside HNSA and HNSEA.

Key activities
Enhancing land tenure security for informal women workers
The aim of the project was to increase informal women workers’ awareness of their land tenure rights and security, and increase informal women workers’ access to infrastructure services and housing finance. The women engaged by this project lived in a variety of informal settlements in Delhi and Patna and engaged in a range of informal work, most of which was connected in some way to their homes. For example, the women were homeworkers doing piece work in the garment sector, or street sellers who used their homes to store their goods for sale. Key activities undertaken by the SEWA Bharat team, alongside SEWA Delhi, SEWA Bihar, SEWA Grih Rin and the Indian Institute of Human Settlements:
- Conducting situational analysis: In the early months of the grant, the team conducted a situational analysis to shortlist potential sites and assess the barriers faced by informal women workers at these sites. Through this analysis, the team selected 14 blocks in six settlements across two cities.
- Delivering Training of Trainers: The team delivered a total of eight training sessions and a series of refresher trainings, both online and offline, to community leaders across Delhi and Patna on topics including infrastructure improvements, tenure security and housing finance.
- Conducting an external evaluation: The team partnered with Sutra Consulting to conduct an external evaluation. This resulted in a baseline report, with both quantitative and qualitative findings.
- Producing learning outputs: The team developed a series of learning materials on topics such as: improving land tenure security; increasing access to housing finance; improving infrastructure; and identifying women’s economic empowerment pathways for women workers in the informal sector. The team produced six articles, ten case studies, a video, training modules, brochures and posters. The team also produced a Tenure Security Roadmap, which depicts the de-facto and de-jure strategies which can be employed to secure tenure for different types of informal settlements.
- Advocating on behalf of informal women workers: The team lobbied government officials to prioritise infrastructure service delivery and land tenure.

Recognising, reducing and redistributing unpaid care and work for women
The aim of the project was to support and facilitate the redistribution of unpaid care work responsibilities between women and men and increase women’s decision-making power within the domestic relationship. The project promoted thoughtful and consistent dialogue with individuals and institutions, challenging gender stereotypes that perpetuate social and economic inequality. The project also supported select government ministries and civil society actors in both countries to incorporate women’s economic empowerment initiatives into existing systems and institutions. This included providing training and ongoing support to community health workers and social work personnel. Key activities undertaken by the Promundo-US team, alongside Rwanda Men’s Resource Centre and Sonke Gender Justice:
- Adapting and strengthening Program P curricula: Program P is Promundo-US’ flagship fatherhood programme. It is a proven, evidence-based model for positively changing gender norms, and men’s associated behaviours, around fatherhood and caregiving. With this grant, the team developed and adapted two existing Program P curricula, to strengthen their focus on unpaid care work and women’s economic empowerment. This work resulted in a 17-session “Bandebereho” curriculum in Rwanda, and an 8-session “MenCare 50:50” curriculum in South Africa.
- Equipping service providers to deliver Program P curricula: The team trained service providers, across Rwanda and South Africa, to deliver Program P. These service providers ranged from village-based community health workers to government-employed social service professionals, such as social workers and youth development workers.
- Scaling-up Program P: The team liaised with officials at district, provincial and national level to institutionalise Program P within existing government structures.

Improving outcomes for women in informal work
The aim of the project was to empower leaders of home-based worker groups to negotiate better outcomes for their members working in precarious conditions in the garment sector. The project also supported alliance building between home-based worker organisations and wider civil society groups working for change in women’s working conditions in the garment industry. The project emphasised the importance of organising at both the national and global level to enable positive change for women. Key activities undertaken by the WIEGO team, alongside HNSA and HNSEA:
- Increasing capacity building for women homeworker leads: The team developed the “Working in Garment Supply Chains: A Homeworkers’ Toolkit South Asia” toolkit. They then collaborated with home-based worker organisations to deliver training on this toolkit across Bangladesh, India, Nepal and Pakistan. The team also launched “Pocket Tools for Homeworkers Working in Garment Supply Chains.” These were designed to provide practical information to home-based workers in an accessible format, on topics such as awareness raising and information recording.
- Engaging existing and new allies and partners to support home-based workers in global value chains: The team participated in the event “Money Heist: COVID-19 wage theft in garment global supply chains” to discuss, alongside key players in the sector, emerging strategies for holding global apparel brands responsible for wage theft. WIEGO, HNSA and HNSEA also banded with Asia Floor Wage Alliance to call on brands to extend a one-time Supply Chain Relief Contribution to all garment workers in their supply chains during the COVID-19 pandemic. The team also engaged the Clean Clothes Campaign, contributing to their publication “Fashioning Justice: A call for mandatory and comprehensive human rights due diligence in the garment industry.”
- Strengthening collective voice and representation: In 2021, the International Working Group facilitated the virtual launch of HomeNet International – the home-based worker’s global network. Alongside regional networks and emerging platforms, both WIEGO and HNSA played a key role in this launch as a result of WOW support. WIEGO also built the Fundraising and Sustainability for MBOs platform, which is an online resource for membership-based organisations of informal workers.

Key achievements
1. Enhancing land tenure security for informal women workers
This grant significantly over-achieved against its original targets. Communities benefited from improved infrastructure, tenure security, and the availability of housing and livelihood finance. Moreover, impact analysis conducted at the time suggested that they also saved time and money, which could then be used for enhancing livelihoods and leisure. Specific achievements were as follows:
- Against a target of 17,000, 18,426 informal women workers were sensitised about infrastructure improvements, strengthened tenure security and access to formal financing. The team subsequently identified a direct linkage between awareness generation and infrastructure improvements, as communities were better able to map services to providers.
- Against a target of 5,000, 29,951 informal women workers benefitted from infrastructure improvements[6]. In Delhi, interventions led by the team focused on repair, maintenance and upgrades, such as the installation of streetlights and improved frequency of drain cleaning. In Patna, interventions led by the team resulted in major infrastructure improvements (e.g. roads and drains) which otherwise may have taken years to accomplish.
  [6] SEWA proposed a target of 5,000 prior to completing their work to conduct site mapping and sensitisation activities. This target was included in the WOW logframe, as the WOW team was not yet confident in SEWA‘s approach to collate these numbers. However, when SEWA started their implementation, they saw a tremendous response in both Delhi and Patna. When they subsequently implemented the MEL tools they had co-designed with WOW, it was clear they had far surpassed the original estimated target.
- Against a target of 500, the team strengthened the tenure security of 614 informal women workers. This was achieved via de-jure strategies, such as supporting informal women workers to apply for formal state policies, as well as de-facto strategies, such as supporting informal women workers to access formal electricity connections.
- Against a target of 200, the team distributed 413 livelihood loans to informal women workers. Distributed during COVID-19, these loans proved to be critical to enable women to access formal financing in order to regenerate their livelihoods and improve/buy houses. Specifically, these loans enabled women to buy goods and return to work. Some were even able to start new businesses.

2. Promundo-US: Recognising, reducing and redistributing unpaid care and work for women
This grant made significant progress towards the redistribution of unpaid work and care in the target communities in Rwanda and South Africa. Specific achievements were as follows:
- In both countries, the Program P curricula received formal approval/ratification. In Rwanda, the curriculum was officially approved by the Rwanda Biomedical Centre. In South Africa, it received accreditation from the Construction Education and Training Authority.
- Across both countries, a total of 268 service providers were trained to be able to facilitate Program P training sessions (110 in Rwanda and 176 in South Africa).
- Across both countries, significant progress was made to embed Program P within national health and social services. In Rwanda, “Bandebereho” was scaled across the entire health system in one district. Moreover, policymakers gave full commitment to scale the programme nationally. In South Africa, the Department of Social Development in the Free State implemented “Men Care 50:50” across three out of five districts, and incorporated Program P reporting into their routine reporting at national level.
- Across both countries, Program P contributed to significant changes in men’s and women’s attitudes. This was most notable in Rwanda, where post-session findings indicated: men began to take on more unpaid care work within the home; women were increasingly involved in household decision-making; men were less dominant in decisions about women’s work participation and women had more opportunities to participate in paid work.

3. Improving outcomes for women in informal work
This grant made significant progress towards improving outcomes for women in informal work in the target regions across Southeast Asia. Specific achievements were as follows:
- In 2021, the International Working Group facilitated the virtual launch of HomeNet International. Alongside regional networks and emerging platforms, both WIEGO and HNSA played a key role in this launch as a result of WOW support. 36 home-based worker organisations from 20 countries became the first affiliate members to join the global network, representing more than 600,000 home-based workers. Over 300 people attended the virtual launch over two consecutive days, including 80 home-based workers delegates. The first “Congress” took over five hours and was translated into 14 languages. Within this time, 36 affiliates adopted the Constitution, presented regional reports, appointed a Working Committee and confirmed the International Coordinator.
- In 2021, the learning product "Working in Garment Supply Chains: A Homeworkers' Toolkit South Asia” was launched and translated into five languages. In the first year of its publication, it was downloaded 610 times and viewed 1,346 times.
- By 2021, despite challenges caused by the COVID-19 pandemic, the grant team had trained a total of 103 home-based workers across six organisations. The grant team had also successfully engaged 15 existing partners and three new partners. In Kenya, the grant team had delivered training to 36 home-based workers enabling them to better understand different types of home-based work, how to map supply chains and where home-based workers fit within domestic and global supply chains.
- In 2021, the grant team collated inputs from 12 home-based worker organisations and from HNSA and HNSEA. The team submitted these on their behalf to the European Union Stakeholder Consultation on Sustainable Corporate Governance in Global Supply Chains. This represented a strategic approach towards joint advocacy and marked the first time that home-based worker organisations had specifically targeted the EU.

When WOW’s activities were put on hold during the COVID-19 pandemic, WIEGO’s implementation was stopped, impacting the results that WOW could achieve. Promundo had already concluded its work, and a decision was made to continue the work with SEWA. For each grantee, the MEL plan included an internal impact projection for ‘number of women reached’. The table below summarises the projected impact and results achieved against them.

Lessons learned

1. Enhancing land tenure security for informal women workers
- Tailored financial solutions can enhance economic empowerment in communities but require grassroots efforts. Although demand for housing and livelihood loans is high, these resources are often inaccessible to community members due to barriers such as lack of documentation, low credit scores and limited awareness of formal financing options. As such, community members tend to rely on informal loan sources with high interest rates. Addressing this requires extensive grassroots efforts to raise awareness, build trust and assess individual needs and repayment abilities.
- At the grassroots level, a multi-pronged approach is often more effective than a singular pathway. Responding to complex problems often requires a multi-faceted approach. Activities such as advocacy, research, policy review and community mobilisation should therefore not be seen in isolation, but rather as complementary activities. For example, SEWA successfully repaired and reopened a community toilet in the B1 Jhuggi settlement in Delhi. This could not have been achieved without social media advocacy, extensive engagement with elected officials and wide-reaching community mobilisation.

2. Recognising, reducing and redistributing unpaid care and work for women
- Continuous engagement with local and national Government is necessary to scale programmes like Program P. Experience across Rwanda and South Africa demonstrated the necessity of working simultaneously with local and national government to obtain the permission needed to embed Program P throughout public institutions.
- Public service providers are more than capable of delivering gender-transformative programming, as long as they receive the right support. Experience across Rwanda and South Africa demonstrated that, with tailored training, service providers (including community health workers, social workers and other social service professionals) are capable of facilitating participatory and impactful gender-transformative group sessions, with little or no previous gender facilitation experience.
- Exploration of innovative, low-cost recruitment and retention strategies is essential. Experience across Rwanda and South Africa demonstrated that training participants were highly motivated. However, they faced challenges in being able to attend all sessions, which impacted the effectiveness and sustainability of the training they received.

3. Improving outcomes for women in informal work
- Intentional investment in digital tools for grassroots organisations is critical. The COVID-19 Fund for devices and data plans enabled home-based worker organisations and leaders to adapt project activities to be online/virtual. This helped to maintain the momentum and impact of the grant. Ongoing investment in digital tools is therefore required to ensure that grassroot organisations can adapt activities as needed, even beyond the context of the COVID-19 pandemic.
- Informal networking can be a helpful tool to track home-based worker groups. In Ethiopia and Kenya, the team found that the concept of home-based work is only just emerging. As such, most workers view themselves as micro-entrepreneurs or producers. This makes it difficult to identify these workers and map their links to supply chains. Moreover, the team found that it was difficult to collect data on these workers using formal research methods. As such, informal group networking may present a more viable alternative.

Recommendations for future programming
- Grant programme should be contextually relevant and address the needs of the community: There should be continuous engagement with NGOs/CSOs to ensure we understand the relevant context and work together with NGOs/CSOs to ensure funds are directed towards the specific needs of the community and where we can have the greatest impact.
- Streamline the grant application process: We should consider how we can streamline the grant application process to ensure we enhance the quality of the applications received and can also build capacity amongst bidding organisations. For example, providing MEL expertise at no cost to guide applicants in the development of a robust Project Results Chain and/or MEL plan.
- Streamline the initial proposal stage: Small CSOs/NGOs can find the initial proposal stage to be onerous. To ensure participation from a wide range of CSOs/NGOs, we should consider streamlining the initial proposal stage process by relaxing some of the initial requirements such as the requirement for a lengthy literature review.
- If the proposal stage does take longer than planned, ensure that grant start dates reflect the time needed for contracting and fund disbursement.
- Establish a project steering committee with a diverse group of experts, including FCDO representatives, external gender specialists, economists and local community leaders.
- A proportion of funding, for example 20% to 30%, could be used to support the improvement of the grantee’s internal systems, such as support to the grantee’s funding strategy, or to strengthen the grantee’s MEL capability, or to help communicate the impact of the project.
- Continue to maintain a high level of adaptability in funding priorities, considering ongoing global crises, such as climate change, conflict and economic shocks.
- Plan for more structured peer-learning sessions among grantees (on themes like policy influence and scaling strategies) to enhance impact. These were initially planned under WOW but were cancelled due to the pandemic.
- If funding is cut, provide notice and consider providing bridge funding to support the civil society organisation to transition away from the funding.

WOW’s continuing impact with SEWA Bharat case study
During the inception phase of the SEWA Bharat grant, key members of the WOW team travelled to India to meet the SEWA Bharat team. During this visit, the WOW team delivered essential capacity building support to the SEWA Bharat team, including grassroots researchers and community leaders. Specifically, WOW collaborated with SEWA to co-create the Theory of Change, logframe, targets and indicators that would guide the MEL approach for the grant. In 2023, years after the grant had closed, the SEWA team informed WOW that they continue to apply the MEL knowledge they gained from WOW on a regular basis. Specifically, SEWA continues to use the WOW-supported MEL Framework across all ongoing projects, irrespective of specific donor requirements. This enduring practice highlights the broader legacy of the WOW programme, and illustrates the impact of delivering the right type of training (in-person co-creation) at the right time (during inception) to the right people.
Output Number and Title	Output 5 – WOW delivers good Value for Money as per the WOW VfM Framework
Output Score	A
Impact weighting (%)	15%	Impact weighting revised since last AR?	Yes, up, to give average weighting for programme lifecycle

Output Indicator	Final Target	Achieved
5.1.1 – WOW delivers good Value for Money (VfM) as per the WOW VfM framework. ​	Annual VfM targets met as per the WOW VfM framework	Most targets met, with the exception of two which were only partially met.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
A variety of procedures and processes have been designed and implemented to ensure that Value for Money is maximised across all WOW Outputs, as well as WOW’s wider programme management systems. The WOW VfM Framework was set up, using DFID’s 4Es VfM approach[7] to create a common understanding of VfM across WOW so that processes could be continually reviewed and refined over time, and the relevant data could be identified and captured.
[7] Economy, Efficiency, Effectiveness and Equity

An initial WOW VfM Framework was developed in 2018/19 and provided the basis for the development of the WOW VfM Reporting Tool, which was used to consider VfM both on an ongoing basis, and as part of the annual programme reporting cycle. It was implemented until the budget cuts that started in December 2020. WOW continued to report on VfM in 2021 and 2022, using only a few indicators (that were agreed with FCDO) given the limited budget. When the WOW budget was fully reinstated in 2023, the WOW team updated the original Framework in agreement with FCDO reflecting the changes to the programme that had taken place within this time.

For example, the initial WOW logframe included four active Outputs. However, work under Output 2 concluded in September 2020 and work under Output 4 concluded in September 2022. When WOW formally resumed, after the budget uncertainty, focus shifted to Output 1 and Output 3, and the overarching programme strategy underwent an internal review. By September 2023, the VfM Framework was revised (both in terms of indicators and processes) to better align with the updated WOW Strategy and logframe.

WOW was guided by a set of principles to ensure that the VfM Framework met the needs of the programme:
- The WOW VfM Framework was designed to be fit for the size and scope of WOW, and to be highly resource efficient. All VfM indicators aligned closely with existing WOW MEL structures to minimise duplication and ensure the administration of the Framework itself represented good VfM in terms of time and resource.
- The WOW VfM Framework set targets which were ambitious, while recognising the limited resources available for VfM. To support this, the Framework not only proposed indicators (and methods for measuring these), but also ways for embedding VfM into the programme.

Economy
Daily rates, overall budget and expenses: Daily rates target was exceeded; overall budget target was met; and overall expenses targets were met each year except year 3, when was not met when expenses exceeded the total expense budget for the year by 11.2% (or £4,310). This was because the proportion of budget paid to grants that year was higher than anticipated, in light of the wider budget cuts. It should be noted however that the increased expense spend was more than offset by underspend on fees for the year.
Cost saving: Amount of savings from contributions from corporate partners (both in-kind and in-cash contributions) met or exceeded except year 4 where businesses C and F provided less than 5 days, and year 6 where business K provided less than 5 days; and amount of savings from contributions from grantees (both in-kind and in-cash contributions) target was met.

Efficiency
Output 1: Partnerships with business target exceeded; Output 2: Evidence target met; Output 3: Helpdesk targets exceeded; Output 4: WOW Fund targets met or exceeded; Output 5: Timeliness of delivery target met;
‘Accuracy of forecasting’ target partially met: The WOW programme was within variance limits for 18 of 30 reporting quarters. This equates to 60% of reporting quarters, as opposed to the target of 75%.

Equity
Output 1: Partnerships with business included the development of profiles of women reached through the partnerships to assess their socio-economic characteristics and see that the programme targeted poorer more marginalised women – this was monitored but no target set; Output 4: profiles of women reached through the WOW-funded projects also monitored but no target set.

Effectiveness
Output 1: Partnerships with business target exceeded; Access for women to higher productivity jobs, diversified roles and improved working conditions target exceeded; Output 3: Helpdesk target exceeded; Output 4: WOW Fund grantees generating new knowledge and/or influence practice in the areas of: (i) improving conditions of informal workers, (ii) recognising, reducing and redistributing unpaid care work, and (iii) improving tenure security for WEE monitored but no target set.

Lessons learned and Recommendations for future programming
By articulating the value of programme activities and developing a standard for what economy, efficiency, effectiveness and equity look like for each Output, the WOW team was able to make better decisions about future activities, track progress over time and understand how their work contributes to good value for the WOW programme as a whole.
Output Number and Title		Output 6 – Gender Smart Investing Summit contributes to the sphere of gender-smart investing
Output Score		A
Impact weighting (%)		1%		Impact weighting revised since last AR?	Yes, up, to give average weighting for programme lifecycle

Output Indicator	Final Target		Achieved
6. GSIS team demonstrate effective delivery of Gender Smart Investing Summit(s)	Preparations for the second Summit are timely, well communicated and in line with expectations. The Summit demonstrates its contribution to the gender smart investing field.		Target met – The global Gender Smart Investing Summit which took place from 18-19 October 2022, brought together over 325 asset owners, institutional investors, fund managers, gender experts, and investment intermediaries from over 40 countries. The Summit was designed to explore how to integrate gender and intersectionality across the value chain and move capital at scale with a gender lens. Areas targeted for in depth discussion were how to move capital to climate-smart transport, buildings, care infrastructure and energy.

Gender Smart Investing Summit (GSIS)

Overview: GSIS took place from 18-19 October 2022, brought together over 325 asset owners, institutional investors, fund managers, gender experts, and investment intermediaries from over 40 countries. The Summit was designed to explore how to integrate gender and intersectionality across the value chain and move capital at scale with a gender lens. WOW’s aim was to ensure that preparations for the second Summit were timely, well communicated and in line with expectations.

GSIS Results: GSIS was delivered on time and with strong attendance. It raised awareness of the enormous potential of gender lens investments to address the links between gender and climate change, and the care economy. It also exposed the need for more to be done to identify pipeline investment deals, link investors to female business leaders and entrepreneurs, and to increase the number of female Investment Fund managers.

GSIS Impact: GSIS highlighted that “[a]t an aggregate level, an estimated $20bn has been identified and allocated for gender smart investing as of the end of 2021. For example, UBS Global Gender Equality ETF, launched in 2018, reached $1.6 billion at the end of October 2022. In the private markets context, the 2X Challenge significantly surpassed its original 2018-2020 target to mobilise US$3B in gender lens investments,. At the 2021 G7 Summit, a new collective 2021-2022 target of US$15B was announced”.

The call to action over the course of the GSIS was to integrate gender and intersectionality across the value chain and move capital at scale with a gender lens. The GSIS also explored what it means to bring gender and climate together from an investment perspective, and the risks of not applying a gender-lens into climate-smart transport, buildings, care infrastructure and energy. For these projects to be a success, gender and diversity needs to be embedded into the design stage.

Gender Smart merged with 2X Collaborative in January 2023 to create 2X Global for global sustainability and equal opportunity, powered by inclusive, equitable, and gender smart systems of finance. 2X’s criteria for eligibility of gender lens investment was frequently mentioned as the floor, not the ceiling in terms of future gender-lens investment ambition. Due to this merger, there was no Gender Smart Investment Summit in the subsequent years.

D: Value for Money

 The WOW programme already includes a Value for Money discussion under Output Indicator 5.1. This indicator was created to support annual monitoring and measurement of key performance indicators covering Economy, Efficiency, Effectiveness and Equity. Further details below:

Cost Drivers and Performance

Output 1: Partnerships with companies to improve women’s participation in supply chains
The primary cost drivers under this output were consultancy fees and technical assistance, which were milestone-based and benchmarked against FCDO-approved rate cards. This ensured that inputs were procured at competitive rates while maintaining quality. The WOW programme also secured pro-bono contributions from PwC and alliance partners, as well as in-kind support from corporate partners, which helped reduce the overall cost burden. These contributions were tracked and reported annually, with narrative justifications provided where savings targets were not met.

The programme’s partnership model was designed to be lean and responsive. The average number of WOW team days spent per prospective partner was monitored quarterly, with significant variances requiring explanation. This approach ensured that resources were allocated efficiently and that partnerships were pursued only where there was clear potential for impact. Due diligence processes, including integrity and safeguarding checks, were applied to all partners, ensuring ethical and strategic alignment.

Output 2: Improving gender data transparency in global supply chains
Output 2 focused on improving the availability and use of gender-disaggregated data in global supply chains, with cost drivers primarily linked to research design, stakeholder engagement, and the development of technical tools and methodologies. The programme worked across macro, meso and micro levels, engaging with multinational companies, industry bodies and research institutions. At the macro level, costs were associated with influencing global compliance frameworks—such as integrating gender indicators into Sedex’s Supplier Assessment Questionnaire. At the meso level, WOW collaborated with individual companies to pilot gender mapping methodologies and integrate gender-sensitive tools into corporate sourcing frameworks. These engagements required tailored technical assistance and iterative research support. At the micro level, country-specific research in sectors such as garments and agriculture involved fieldwork, data analysis, and the production of guidance materials.

Despite the onset of COVID-19, which necessitated a pivot to rapid-response research, the programme maintained delivery momentum and adapted its outputs to remain relevant. By 2022, WOW had transitioned to a dissemination and sustainability phase, ensuring that its tools and methodologies continued to be used beyond the programme’s lifecycle. All activities were delivered within budget, and the programme exceeded its targets, becoming a key resource for companies seeking to embed gender-responsive practices in their supply chains.

Output 3: Helpdesk support to FCDO and HMG programmes
The Helpdesk operated on a demand-driven basis, with consultants selected from a pre-approved pool. VfM was a key criterion in consultant selection, with hybrid teams (junior and senior experts) used to balance cost and expertise. Feedback was collected from support recipients to assess satisfaction and knowledge gains, and this data informed future support prioritisation. The average cost per Helpdesk intervention was tracked, with explanations provided for year-on-year variances.

Helpdesk resources were strategically targeted at programmes with the potential to reach large numbers of women or influence design improvements. Six-monthly reviews of Helpdesk spend ensured that support remained aligned with strategic priorities and delivered tangible benefits for women and girls.

Output 4: Supporting women’s economic empowerment through targeted technical assistance
The key cost drivers for this output were the design and delivery of context-specific training, the development of learning materials, and the engagement of local partners across multiple geographies. For example, in the SEWA-led project in India, costs were driven by the need to conduct situational analyses, deliver community-based training, and facilitate infrastructure improvements in informal settlements. In the Promundo-US project, costs were associated with adapting and scaling Program P curricula across Rwanda and South Africa, including training government and community service providers. Meanwhile, the WIEGO-led initiative incurred costs related to regional coordination, toolkit development, and alliance-building across South Asia.

Implementing partners leveraging existing networks and institutional knowledge to maximise reach and minimise duplication. The use of local expertise and co-creation with community-based organisations helped ensure that interventions were both cost-conscious and contextually grounded, contributing to strong VfM performance under this output.

VfM Performance Compared to the Original Proposition
Economy
The WOW programme maintained strong cost control mechanisms. All consultancy and technical assistance costs were tied to milestone achievements, with quality assurance checks in place before payments were authorised. Daily rates were competitively priced and aligned with FCDO rate cards. Travel and subsistence costs were governed by strict policies, with efforts made to book in advance and use cost-effective options. These measures ensured that the programme delivered economy in line with the original business case.

Efficiency
Efficiency was enhanced through rigorous monitoring of outputs and forecasting accuracy. The programme aimed to maintain a variance of less than 5% between forecasted and actual spend for at least nine months each year. Partnerships were selected based on criteria such as additionality and scale, and the number of partnerships implementing agreed activities was tracked against logframe targets. The Helpdesk’s responsiveness and impact were also closely monitored, with feedback mechanisms in place to ensure continuous improvement.

Effectiveness
The WOW programme demonstrated strong effectiveness in converting outputs into outcomes. It supported partnerships that improved women’s access to higher-productivity jobs and better working conditions in global supply chains. The number of women benefiting from these interventions was tracked, and qualitative data was collected to capture changes in agency and opportunity. The Helpdesk influenced the design of FCDO and HMG programmes, increasing their reach to women beneficiaries. These outcomes aligned with the programme’s impact-level goals of contributing to SDGs 1, 5, and 8.

Equity
Equity was embedded in the programme’s design and delivery, targeting low-income women, informal workers, and those in precarious employment across sectors such as agriculture, garments, and waste management. The programme recognised that reaching these groups might incur higher costs, valuing the transformative potential of inclusive economic empowerment. The programme recognised the intersecting barriers these women face—unpaid care responsibilities, gender-based violence and harassment (GBVH), and climate vulnerability—and sought to address them through tailored interventions. The programme’s design was inclusive and participatory. It co-created solutions with local partners, ensuring that interventions were context-specific and culturally appropriate. Equity was embedded throughout the programme’s lifecycle—from design to implementation and evaluation. The programme considered relative need, counterfactuals, and displacement risks to ensure that its interventions did not inadvertently increase inequalities. It used gender-disaggregated data to inform programming and developed tools to identify and address hidden labour and systemic exclusion.

Partnerships were selected based on their potential to benefit marginalised and vulnerable women, and profiles were developed for each partnership to track who was being reached. The Helpdesk supported 42 FCDO programmes, with 38 reporting improved design to better reach women, and included considerations of women with disabilities in many reports. The final product was a checklist for gender equality, disability and social inclusion across FCDO economic development programmes, to support colleagues to improve equity across different stages of programming and maintain this legacy.

The MEL efforts disaggregated data by gender to track progress throughout the programme lifecycle, and produced learning products and case studies that highlighted the experiences of marginalised women to give more detailed qualitative evidence of its outcomes.

Cost-Effectiveness
Overall, the WOW programme offered strong cost-effectiveness. It combined rigorous financial controls with a strategic focus on systemic change. By leveraging corporate partnerships, influencing donor programming, and embedding gender equality into economic development, WOW achieved impact at scale. The use of milestone-based payments, in-kind contributions, and adaptive management ensured that each pound spent delivered maximum value. The programme’s ability to influence both direct beneficiaries and broader systems positioned it as a high-performing, cost-effective intervention in the women’s economic empowerment space.

Conclusion
The WOW programme represented strong value for money across VfM pillars:
VfM Pillar	WOW Performance	Comparative Advantage
Economy	High	Milestone-based payments, cost-sharing
Efficiency	High	Real-time monitoring, adaptive management
Effectiveness	High	Systemic impact, strong MEL
Equity	Very High	Gender, poverty, and inclusion embedded

WOW’s design and implementation reflect a mature, evidence-based approach to VfM.

The significantly reduced programme budget compared to the original business case did reduce the scale of WOW’s operations and had knock on effects on the value for money it was able to deliver, however despite this WOW has successfully identified alternative opportunities to influence actors with greater budgets, through knowledge sharing events and new partnerships with businesses. VfM was also increased by two no cost extensions to the programme.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

WOW was successful in managing risk across the programme through the following ways:
- Political and economic change and instability: Adapted workplans to align with changing political environments, maintaining continuous engagement with stakeholders and managing disruptions in India and Kenya by supporting local partners.
- Funding and budget constraints: Acclimated to funding delays and budget constraints by designing modular and scalable activities, building clear breakpoints into the agreed ToRs with the programme partners. Having regular check points with FCDO and the programme partners and working together to do no harm when projects had to be closed due to budget constraints also helped manage this risk.
- Health and climate response: Responded rapidly to the COVID-19 pandemic and modified project work plans. Integrated climate-related risk mitigation strategies into project planning.
- Reputation of programme and partners: Strengthened safeguarding protocols with partners and implemented a media monitoring system to track and respond to emerging risks.

WOW operated in a dynamic and evolving global environment, so risk management was a critical component for the programme. Throughout its lifetime, WOW and DFID/FCDO maintained a rigorous approach to risk identification, assessment and mitigation to safeguard partners and beneficiaries, maintain programme integrity and mitigate reputational risks for FCDO and delivery partners. Over its seven and a half years of operation, WOW developed and maintained a comprehensive risk register covering programme and Output delivery risks, including uncertainties around funding, safeguarding and reputational risks. As part of its risk management process, a Conflict-of-Interest register, and an Ethical Wall policy were established to ensure transparency and accountability. Regular media monitoring was conducted to identify and mitigate reputational risks associated with WOW and its partners.

Political and economic change and instability risk: detailed overview
UK: Shifts in UK election periods and changes in government threatened the priority status of the WOW programme. A new or reformed government had the potential to deprioritise the women’s economic empowerment agenda, which could have impacted WOW's long-term goals. To manage this, WOW adapted its workplans and delivery models to align with the changing political and economic environments. The programme closely monitored policy changes and their implications for WOW activities. WOW also raised its profile and achievements through ongoing virtual events, positioning itself as the FCDO’s flagship women’s economic empowerment programme.
India: In India, SEWA Bharat’s WOW-funded project was significantly affected by the Citizenship Amendment Act protests (2019-2021), which caused widespread political unrest and violence. The situation was particularly tense in Muslim-majority areas such as Rajeev Nagar and New F Block in Raghubir Nagar, where SEWA Bharat conducted fieldwork. There was frequent violence and protests that halted SEWA Bharat’s work in affected areas, increased police presence in the areas, and community tensions over citizenship rights. WOW played a critical role in helping SEWA Bharat mitigate these disruptions by maintaining active communication with field teams to monitor risks and adjust plans as needed and by developing a media response strategy to prepare for potential negative press coverage, and alignment with FCDO messaging was ensured to prevent reputational damage. WOW supported SEWA Bharat in launching community meetings, awareness camps and door-to-door mobilisation to reassure communities and clarify their work's purpose.
Kenya: In Kenya, the mid-2024 riots posed significant risks to WOW’s partnerships with Business D and Business J. The unrest threatened to disrupt WOW’s work, including Farmers’ Voice Radio recordings and research trips, which highlighted the concerns around the safety of WOW’s delivery partners traveling to Kenya. To mitigate these risks, WOW monitored local news and government alerts to stay informed about the situation and maintained regular communications with local teams and FCDO. The plans for recordings and research trips were kept flexible. In addition, the team postponed planned trips until the situation stabilised to ensure the safety of team members.

Funding and budget constraints: detailed overview
- Funding uncertainty (2022 and 2024): WOW faced significant risks due to funding delays and budget constraints, which threatened programme delivery, reputational stability and the programme’s ability to achieve its intended impact. These risks were particularly pronounced between 2022 and 2024. The reduced funding meant that most planned activities had to be postponed to WOW’s final years, impacting the programme’s ability to reach its goal of 300,000 women. In light of the financial constraints, FCDO re-assessed the initial impact target for WOW.
- Impact on business partnerships: For the business partnerships, the uncertainty around WOW’s budget made it difficult to commit to long-term business partnerships, discouraging some corporate partners from engaging, which was a reputational risk for WOW. To mitigate this, WOW designed all activities to be modular and scalable and proactively communicated funding risks to partners to prevent reputational damage and misaligned expectations.
- Do no harm: In the event of budget cuts midway through a partnership, there was a do no harm risk, where beneficiaries (particularly women in supply chains) could be negatively impacted by a sudden withdrawal of support. To mitigate this, WOW built clear breakpoints into partnerships to allow for structured exits if needed and made do no harm a priority.
- Impact on the WOW team: Budget constraints created challenges in retaining core team members and securing necessary expertise for programme delivery. There was a risk of losing institutional knowledge if key team members left due to funding uncertainty (this was the case with the initial WOW Team Leader during the budget cuts). The WOW consortium maintained continuous dialogue with DFID/FCDO SRO on the budget and tried to motivate the team and incorporate proper handover when experts decided to move on.

Health and climate risk: detailed overview
COVID-19: In March 2020, the COVID-19 pandemic posed significant risks to WOW’s implementation, affecting programme delivery, partnerships and financial sustainability. WOW team members faced health risks during in-field research and engagement, leading to strict adherence to UK Government and local travel policies. Some staff had to work remotely, delaying field-based activities. Travel bans prevented scoping visits in key regions, affecting projects in India and Mozambique. To mitigate this, WOW shifted to virtual engagements and modified work plans to sustain programme momentum. The economic slowdown also impacted WOW’s corporate and alliance partners, affecting their financial commitments. In response, WOW worked to identify alternative funding strategies and adapt work plans.
Climate change: Climate-related incidents posed risks to WOW’s work on women’s economic empowerment, particularly in agricultural supply chains. Extreme weather events, such as the cyclone in Bangladesh in 2019, disrupted supply chains. A WOW team caught in the cyclone prompted the development of the Security and Travel Protocol for high-risk areas. Prolonged droughts in East Africa and South Asia affected women’s income security in the tea, coffee and garment industries. The WOW team and partners liaised closely with on-the-ground implementing partners to offer support during natural disasters or extreme weather events.

Reputation of programme and partners risk: detailed overview
- The WOW Programme operated in a complex landscape where reputational risks posed challenges to both corporate partnerships and programme delivery. These risks stemmed from media scrutiny, business partner practices and funding constraints, which required a proactive risk management approach to safeguard WOW’s credibility and ensure alignment with DFID/FCDO priorities. This was especially pertinent in relation to the carbon credits sector, which has seen significant public attention relating to environmental and social integrity issues created from some project activities.
- Corporate partners in high-risk sectors: A significant reputational risk arose from corporate partnerships in high-risk sectors such as the tea sector. Some media articles and reports covered topics such as sexual exploitation in Kenyan tea plantations and the poor living and working conditions for tea pickers in Sri Lanka. As WOW worked with corporate partners in the tea sectors, WOW has engaged with those partners when these articles/reports came to life and tried to understand whether they also worked with those tea plantations and what procedure and policies they had in place.
- Corporate engagement and relationships: Funding constraints and budget uncertainties also posed a reputational risk to WOW and FCDO, particularly in Year 4 (2022/2023) when delays in financial commitments led to uncertainty about project continuity. Corporate partners expected long-term collaboration and stability, and the lack of clarity on future funding impacted WOW’s ability to secure sustained business engagement. To mitigate this, WOW maintained transparent communication with partners, set realistic expectations regarding funding limitations while actively engaging FCDO in discussions to prioritise resources for women’s economic empowerment initiatives. To address reputational risks for the programme, WOW implemented a structured media monitoring system to track emerging threats and a timely response to potential crises, such as conducting regular reviews of media sources to assess risks related to WOW corporate partners and grantees.

Lessons learned
- A strong, agile risk management approach including regular risk assessments and adaptive planning were essential in responding to evolving challenges, particularly during the COVID-19 pandemic, funding uncertainties and shifting FCDO priorities.
- The reputational risks associated with corporate partnerships highlighted the importance of enhanced due diligence and stronger safeguarding measures in all business partnerships.
- Given the unpredictable funding environment, WOW’s modular approach to partnerships allowed for scalability and contingency planning, so the funding fluctuations did not completely disrupt programme activities.
- Maintaining open and honest communication with corporate partners, grantees and FCDO helped manage expectations, strengthen relationships, and helped with continuity despite financial and operational challenges.
- Proactive media tracking and crisis communication planning were key to managing reputational risks, particularly in politically sensitive contexts and corporate engagement.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The WOW team has produced high quality narrative and financial reporting. Quarterly reports were produce on time every quarter clearly outlining: i) summary of progress; ii) updates on partnership work; iii) cross-output activities; iv) financial performance and value for money overview; and v) key risks and issues. Quarterly reports critically captured lessons learned and how programme is adapting to changing circumstances. Alongside this, the team also produced a comprhensive Annual Report to analyse these topics in more detail and at a higher level to provide a strategic vison for the next year of programming.

A proactive risk management approach was adopted with regular risk review meetings scheduled alongside ah-hoc meetings to discuss urgent risks. The WOW team was transparent in their risk management approach which ensured risks were identified, reported and managed on time.

The WOW team worked closely with the FCDO, to ensure that an Asset Management Plan was in place. This plan aligns our asset management approach with the objectives of the WOW Programme and ensures that assets continue to serve their intended purpose, thereby maximising developmental impact and sustainability.

Financial forecasting was mostly accurate with one accounting error which affected some workstreams for the last year of the programme. Once identified, this error was quickly raised and steps were taken to ensure that the impact of this error is minimised. Moving forward, FCDO to develop relevant expertise in this area to identify accidents.

Audited financial statements and audit reports were provided to FCDO on time.

During uncertain economic climates, flexibility in budget management is essential. The WOW programme highlighted the importance of maintaining flexibility in budget management, particularly in uncertain economic climates. Despite facing multiple budget cuts and reallocations, the WOW team successfully navigated financial
constraints by adopting proactive measures such as developing budget scenarios and implementing a phased approach to partnerships.
Strong communication with stakeholders is essential to maintain programme activities. Close collaboration and open communication with stakeholders, particularly between the FCDO and WOW team, proved essential in adapting to budget changes and ensuring the continuation of key activities. The WOW team's ability to work closely with FCDO facilitated timely decisions and approvals that were crucial for programme adjustments.

Implement contingency planning. Future programmes, in particular multi-year programmes, should incorporate robust contingency planning from the outset, with clear strategies for responding to potential budget adjustments under different funding scenarios. Such contingency planning should include (i) designing multiple phases for each intervention, and (ii) preparing alternative intervention designs which can address potential budget fluctuations without doing harm or compromising the programme's core objectives.

Strengthen stakeholder engagement and communication. Establishing a structured communication strategy with key stakeholders (in particular donor organisations and programme partners) from inception is essential. Regular meetings and transparent dialogues can garner stakeholder support during challenging times, in turn helping to facilitate approvals for necessary programme adaptations, maintain programme momentum, manage risks and minimise reputational damage.

Budget variance per quarter: On the tenth working day of the final month of each quarter, WOW was required to submit the quarterly forecast to FCDO. WOW was expected to adhere to best practice guidelines, which included maintaining a target maximum variance of 5% between forecast and actual quarterly expenditure. Although this was not formally designated as a key performance indicator (KPI), it served as an important benchmark for operational accuracy. In totality, the programme was within variance limits for 18 of 30 quarters. A justification has been provided for occasions when the variance sits outside 5% target. For example, variance was attributable to the COVID-19 pandemic in 2020, which brought uncertainty to on-the-ground activities. As a result, it was difficult to accurately forecast Output 1 and Output 4 activities.

Summary of the Strategic Relationship Management scorecard assessments: The WOW team has consistently scored high (80%+) on the Strategic Relationship Management scorecard assessment in the last two years. With the most recent score being 100%. This is because the implementing partner has managed programme priorities for the last year of the programme exceptionally well with clear focus on learning, dissemination and comms whilst exploring new opportunities for work packages and activities which are practical, realistic and provide most value for money given the timeframe available and considering uncertainties around the election cycle, budget and contract amendments. WOW team’s industry relationships and expertise have been key factors in the successful delivery of high-profile programme closure events, visits, and webinars. They have ensured that: i) FCDO secures good value for money (i.e. securing venues at competitive rates), ii) there is clear planning of event objectives, iii) excellent briefs are provided for senior staff, iv) overall event management is effective (i.e. sending and tracking invites, maintaining clear communication with the FCDO team on event status), and v) industry experts are included on panels for webinars and events.

Programme-level approach to monitoring and evaluation
Alongside data collected and referenced above, the programme team mean monitored progress through regular meetings with Output leads, and for the final stage of delivery (once Outputs 1 and 3 were up and running after their pause during Covid-19) held a regular 6-weekly governance Board attended from FCDO by: Economic Development Deputy Director, Jobs and Inclusive Growth Team Leader, Senior Social Development Advisor for Economic Development and Partnerships, WOW SRO, WOW PRO, and WOW Programme Officer. This was an opportunity to align WOW’s work with wider FCDO strategy developments, and make sure those strategies are learning from WOW.

The Programme SRO and Programme Officer carried out a monitoring visit to the partnership with Business D in March 2024 in Malawi, and the Programme SRO and Jobs and Inclusive Growth Team Leader carried out a monitoring visit to the partnerships with Businesses I and J in November 2024 in Kenya, attending and participating in the Business I annual conference. Further meetings with beneficiaries either bilaterally, or through invitations to FCDO and WOW events and discussions took place throughout the programme.

Date of last narrative financial report		Date of last audited annual statement