## Nested Logframe
Aawaz II Programme Nested Logframe
Version Date: 14 April 2025
PROJECT TITLE: Aawaz II
IMPACT |  | Impact Indicator 1 |  | Region | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
A more inclusive, tolerant and peaceful Pakistan, with less modern slavery |  | Country ranking in Global Slavery Index (GSI): Global Prevalence Score | Planned | Punjab, KP, Sindh, Federal | 8th out of 167 countries | TBD | TBD | 10th out of 167 countries | 10th out of 167 countries
Achieved
Impact Indicator 2
|  | Worldwide Governance Indicators (WGI): Voice and Accountability score | Planned | Punjab, KP, Sindh, Federal | -0.8 | TBD | TBD | -0.75 | -0.75
Achieved
Impact Indicator 3
|  | Country ranking in International Gender Gap rank | Planned | Punjab, KP, Sindh, Federal | 151/153 | TBD | TBD | 149/153 | 149/153
Achieved
Impact Indicator 4
|  | Percent (%) change in prevalence of child labour, early marriages and GBV in Punjab and Khyber Pakhtunkhwa | Planned | Punjab, KP, Sindh, Federal | Children in labour: ? Early marriage <18 years: KP 33.8%; Punjab: 4.7% Pakistan: 26.4% GBV: 23% | TBD | TBD | 2% reduction | 2% reduction
Achieved
Sources: GSI Ranking, WGI Ranking, Country ranking in International Gender Gap, provincial government data sources
OUTCOME |  | Outcome Indicator 1 |  | Region | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Pakistani society and government institutions support increased voice, choice and control for women, girls, boys, youth, religious minorities and other marginalised groups, protect them from exploitation and prevent discrimination and intolerance at all levels |  | Number and type of significant initiatives adopted and scaled up by the provincial and federal government for protection and response to survivors of GBV and child marriage to which the programme made a major contribution. (data disaggregated by scope of intervention (national/ provincial), and nature of intervention) | Planned | Punjab | N/A | UNICEF: 4 DCPUs to be established and strengthened | UNICEF: DCPUs established and strengthened | UNICEF: DCPUs established and strengthened | UNICEF: DCPUs established and strengthened | • Pakistan’s overall political, economic and security context does not deteriorate • The release of programme funds from funding partners remain consistent to achieve project deliverables • The programme succeeds in highlighting the scale of violence against and exploitation of women and children in Pakistan • Change in Aawaz II-targeted communities will result in positive change in other communities not directly targeted by Aawaz II • Aawaz II can develop and adapt its model for supporting and sustaining change agents and community forums, promoting wider replication • Pandemics and natural disasters do not have serious effects • Programme priorities are embedded in the media discourse to sustain interest and commitment of stakeholders • The government stays committed to localising SDGs and working to achieve them • Development partners continue to invest in Pakistan
Achieved
|  |  | Planned | KP | N/A | UNICEF: 4 DCPUs to be established and strengthened UNFPA: Multi-sectoral Coordination Mechanism for Prevention and Response to GBV Task Forces (in KP) action plan available and regular meetings conducted. | UNICEF: DCPUs established and strengthened | UNICEF: DCPUs established and strengthened | UNICEF: DCPUs established and strengthened
Achieved
|  |  | Planned | Sindh |  | UNICEF: 3 District Child Protection Units established and strengthened UNFPA: Sindh multi-sectoral sexual violence response action plan available | UNICEF: DCPUs established and strengthened UNFPA: GBV case management curriculum is institutionalised in one service provider institution/an academic institution (at least one) | UNICEF: DCPUs established and strengthened | UNICEF: DCPUs established and strengthened
Achieved
Sources: UNJP Initiatives Tracking Sheet validated by actual evidence, independent assessments/verification, studies, policy documents, dissemination events, minutes from government meetings, anecdotal evidences and news and press clippings
|  | Outcome Indicator 2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Level of progression on legislation (amendments, new laws and delegated legislation) proposed and supported for implementation to protect rights of children, girls and women at risk or victims/survivors of GBV and child marriage. (data disaggregated by scope of intervention (national/ provincial), and nature of intervention) | Planned | Punjab, KP | UNICEF: Violence Against Children (VAC): KP Child Protection and Welfare Act 2010 exists and needs amendment to align with the CRC; Draft Comprehensive child protection legislation exist in Punjab and KP | UNICEF UNICEF contribution to CP Policy and Legal reforms has shifted to advocacy for endorsement. | N/A | UNICEF Punjab: Comprehensive CP Bill finalised and readily available for approval process | Comprehensive CP Law finalised and implemented in both KP and Punjab
Achieved
|  |  | Planned | Sindh | UNFPA: Gender based violence: Anti-rape law and rules notified. Child Marriage: The Sindh Medicolegal Act, 2023 is available. | UNICEF: Juvenile Justice System Act (JJSA) is finalised SCPA Rules finalised and submitted for approval to SWD UNFPA: Roadmap and Costed Action Plan for the implementation of Sindh DV Act 2013 is developed | UNFPA: Clinical Management of Rape curriculum institutionalised in Sindh An oversight and monitoring mechanism available for the implementation of the child marriage law in Sindh | UNICEF: Finalised CP policy Finalised SCPA Rules Finalised BR rules for more inclusivity | UNICEF: JJSA finalised and implemented. Finalised CP policy Finalised SCPA Rules Finalised BR rules for more inclusivity
Achieved
Sources: Legislative and Policy Reform Data Sheet using a Legislative Scale validated by records of ministry of law, justice and human rights department, national and provincial assembly records of bills, cabinet minutes, news and media clippings
|  | Outcome Indicator 3 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Estimated number of individuals (communities and state institutions) reached (services and awareness) by programme's support in focus areas (data disaggregated by level of national/provincial government, location, nature of support/services) | Planned | Punjab, KP | UNICEF: Punjab: Capacity of 48 SSWF strengthened . | UNICEF: 100 members of the social service workforce have strengthened capacity to engage on child protection issues 780 children (girls/boys) at risk and survivors of child protection violations receive services via a case management approach British Council Direct: 0.15 million Indirect: 1 million | UNICEF: Strengthening Capacity of SSWF British Council Direct: 0.15 million Indirect: 2.5 million | UNICEF: Strengthen the capacity of 100 SSWF (50 Punjab and 50 in KP) individuals reached by UNICEF VAC programme. British Council Direct: 0.02 million Indirect: 0.5 million | UNICEF: Strengthened the capacity of SSWF. British Council Direct: 0.32 million Indirect: 4 million
Achieved
|  |  | Planned | Sindh | 0 | UNICEF: Capacity of 100 SSWF in Sindh strengthened Capacity of 30 judiciary and law enforcement agencies on JJSA 2018 strengthened | UNFPA: 400 Nikah Registrars, Nikah Khawan & UC officials and other relevant stakeholders, including the child commission trained UNFPA: 150 Criminal Justice and related professionals (investigation Officer, SSIOU, MLOs, Police, Prosecutors, Lawyers, Judges and GBV services providers) and administrative actors (DC, magistrate) trained on GBV, ARA, Rules, Guidelines and SOPs for an inclusive and sensitive responses to GBV survivors | UNICEF: Strengthened the capacity of SSWF and judiciary and law enforcement agencies on JJSA 2018 UNFPA: 1 million of relevant stakeholders including government officials) reached out on consequences and redressal for Child Marriage | UNICEF: Strengthened the capacity of SSWF and judiciary and law enforcement agencies on JJSA 2018
Achieved
|  |  | Planned | Federal | UNDP: HSDP/SDEP Phase I &II • A minimum of 83 policymakers and experts engaged • 264 government officials, experts and media representatives trained • 1479 students trained by engaging • Media campaigns reached 34.4 million unique users in Phase I and 11.85 million in Phase II. | UNDP • A minimum of 25 policymakers and experts engaged and at least 40 government officials, experts media representatives and 60 young ACAs trained. | UNDP • A minimum of 60 policymakers and experts engaged and at least 70 government officials, experts and media representatives trained. • At least 1 million people reached through influencer and podcast campaigns. | UNDP • A minimum of 50 policymakers and experts engaged and at least 90 government officials, experts and media representatives trained. • At least 1 million people reached through influencer and podcast campaigns. | UNDP • A minimum of 135 policymakers end experts engaged and at least 200 government officials, experts, media representatives and 60 young ACAs trained. • At least 15 Influencers reach out to 2,000,000 impressions. • At least 2 million through influencer and podcast campaigns.
Achieved
Sources: Aawaz II database, programme progress reports, baseline, midline and end line assessments.
|  | Outcome Indicator 4 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Percent (%) change in knowledge and attitudes of individuals in target communities (data disaggregated by level of sex/age/ location, religion and disability) | Planned | Punjab, KP, Sindh | NA | UNJP: 20% increase in individuals (disaggregated by sex, age, location, religion and disability) reporting i) knowledge of MS and harmful practices ii) less acceptance of child labour, early/forced marriage and gender-based violence iii) improved tolerance British Council: N/A Baseline available (June 2024) i) Knowledge of GBV, child marriage a) 11 % identified the legal marriage age for girls as 16 years (KP & Punjab) b) 10% aware of laws addressing violence against women c) 10% aware of government services ii) Less acceptance of child marriage and gender-based violence a) 13% believe there is no justification for child marriage b) 22% do not justify spousal abuse iii) improved tolerance towards religious minorities a) 28% willing to interact with individuals from a faith other than their own b) 36% willing to take action if they see a person from a religious minority experiencing discrimination or abuse | UNJP: 20% increase in individuals (disaggregated by sex, age, location, religion and disability) reporting i) knowledge of MS and harmful practices ii) less acceptance of child labour, early/forced marriage and gender-based violence iii) improved tolerance British Council: N/A | UNJP: 2% increase in individuals (disaggregated by sex, age, location, religion and disability) reporting i) knowledge of MS and harmful practices ii) less acceptance of child labour, early/forced marriage and gender-based violence iii) improved tolerance British Council: 2% increase in individuals reporting i) knowledge of GBV, child marriage ii) less acceptance of child marriage and gender-based violence iii) improved tolerance towards religious minorities (disaggregated by sex, age, location, religion and disability) | British Council: 2% increase in individuals reporting i) knowledge of GBV, child marriage ii) less acceptance of child marriage and gender-based violence iii) improved tolerance towards religious minorities (disaggregated by sex, age, location, religion and disability)
Achieved
[5 empty] | Sources: Baseline and Perception Surveys, KAP survey, Aawaz database, case studies, programme progress reports, midline and end line assessments. |  |  |  |  | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) |  | FCDO (FTEs)
Output 1 Impact Weighting (%) |  | Output Indicator 1.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Strengthened government institutions with effective legislative frameworks, evidence based policies, strategies and sustainable child protection system [Output 1: Child Protection; Lead: UNICEF] |  | Number and type of UNJP's supported legislation, policies, strategies, and actions for child protection (child justice and right to legal identity) in alignment with international standards | Planned | Punjab, KP | 2021 CRVS Rules does not have comprehensive provisions for health-integrated and interoperable mechanism | Birth Registration: Draft birth registration rules for the integration of birth registration and its interoperability within health and related sectors | Birth Registration: Established Integrated Birth Registration (BR) model in 04 health facilities across two provinces, ensuring interoperability and inclusive registration of newborns, including those from minority and vulnerable groups. | Birth Registration: Professionals from LG, Health, NADRA, child protection, and Commissionerate for Afghan Refugees capacitated to implement integrated BR model. | Recommendations on Birth Registration Rules addressed and draft Birth Registration Rules prepared for KP and Punjab. Government counterparts trained on Birth Registration Interoperable Model in targeted health facilities. | • Adequate time and resources of the government are allocated for seeking the commitment of political leadership to the programme • Government counterparts recognise the importance of data generation and use as evidence to inform interventions that promote the rights of marginalised groups – including those subjected to economic exploitation- as essential to fulfilling Pakistan’s national and international commitments • The UNJP generates information to influence policy makers and public representatives that eliminating gender-based violence and violence, abuse and exploitation of children is necessary for poverty reduction, development, and social cohesion • Government priorities and policies do not shift in a major way to compromise programming activities • Public representatives are willing to set aside political differences and work jointly to improve the domestic legal and policy framework • Security situation remain stable, allowing programme activities to roll out as planned • Online/virtual programme delivery do not significantly affect the effectiveness of programme interventions
Achieved
|  |  | Planned | Sindh | Two consultations held for CP Policy (Sindh) with SCPA/ SWD. draft SCPA Act 2021 amendment rules available Sindh CRVS bylaws 2017 available and notified by Local Government No State of Children Report produced by NCRC | Birth Registration: Draft birth registration rules for the integration of birth registration and its interoperability within health and related sectors Justice for children: Juvenile Justice Systems Act rules drafted for Sindh NCRC: Finalised and launch of State of Children Report in Pakistan 2024 | Birth Registration: Established Integrated Birth Registration (BR) model in 02 health facilities in Sindh, ensuring interoperability and inclusive registration of newborns, including those from minority and vulnerable groups. Evidence based draft costed strategic plan available on child online protection Judiciary and other law enforcement agencies capacitated on JJSA 2018 | Birth Registration: Professionals from LG, Health, NADRA, child protection, and Commissionerate for Afghan Refugees capacitated to implement integrated BR model. Judiciary and other law enforcement agencies capacitated on JJSA 2018 | Recommendations on Birth Registration Rules addressed and draft Birth Registration Rules prepared for Sindh. Government counterparts trained on Birth Registration Interoperable Model in targeted health facilities. Justice for Children rules drafted and staff sensitised on JJSA SCRP report launched
Programme Target revised. Additions in blue text. 3 end-to-end service delivery pilots would be delivered in year 4. programme will directly deliver 2 pilots and its replication in one additional LG will make a total of 3.
Achieved
Sources: Draft Policy Documents validated by provincial government records of bills, cabinet minutes, website and news clippings
|  | Output Indicator 1.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Number and type of UNJP's supported actions for child protection systems implemented at provincial level | Planned | Punjab, KP | 4 DCPUs are functional Coordination Mechanism functional at provincial level Consultations held to align Child Protection and Welfare Act 2010 (KP) with CRC | Punjab: 4 District Child Protection Units (DCPUs) strengthened for effective implementation of integrated case management and referral services for children. ** KP: 4 Child Protection Units (DCPUs) strengthened for effective implementation of integrated case management and referral services for children. ** | District Child Protection Units in Punjab (4 DCPUs) and KP (5 DCPUs) strengthened through technical support to the provincial government. Punjab and KP: Draft plans developed for strengthening of social service workforce Punjab and KP:Draft plan developed child protection case management scalability and sustainability. Punjab and KP: Social work education curricula reviewed for the enhancement of the quality of the Social Services Workforce. | District Child Protection Units in Punjab (4 DCPUs) and KP (5 DCPUs) strengthened through technical support to the provincial government Strengthened the capacity of the existing child protection workforce to deliver quality and timely services including on justice for children Punjab and KP: Social work education curriculum revised. | Strengthened 9 DCPUs: (4 in Punjab and 5 in KP) by 2027. Strengthened provincial and district level technical CP Committee (TWG/coordination mechanism for CP-CMRS) Developed scale up and sustainability plan for CP-CMRS for both KP and Punjab Developed social work education curriculum.
Achieved
|  |  | Planned | Sindh | 0 | 3 Child Protection Units (DCPUs) strengthened for effective implementation of integrated case management and referral services for children. ** Sustainability, scale-up plan and interdepartmental coordination action plan in consultation with stakeholders developed. Strengthened the existing child protection workforce's capacity of 100 social service workforce to deliver quality and timely services Secondary data (literature review and DHS analysis) on child marriage completed Capacity-building package for community-based child protection committees (CBCPCs) to prevent child abuse, including child marriage and violence against girls and boys finalised | Provincial government capacitated to strengthen 3 existing District Child Protection Units and establish 2 new DCPUs Sustainability and scale up plan finalzied Capacity of the existing child protection workforce strengthened to deliver quality and timely services including on justice for children Life Skills Framework for adolescents developed and finalised Validation of the findings of the participatory qualitative research on child marriage. Finalisation and launch of the participatory qualitative research on Child Marriage | Provincial government to strengthen 5 existing District Child Protection Units, Social work education curriculum reviewed and revised for enhancing the quality of the incoming Social Services Workforce. | Strengthened 5 DCPUs: (03 existing and 02 new) by 2027. Strengthened provincial and district level technical CP Committee (TWG/coordination mechanism for CP-CMRS) Developed scale up and sustainability plan for CP-CMRS Developed social work education curriculum. Validation and launch of the findings of the participatory qualitative research on child marriage. Life Skills Framework for adolescents finalised and launched.
Achieved
Sources: Pilot Initiative Tracking Sheet validated by progress reports, field monitoring / verification
|  | Output Indicator 1.3 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | UNJP PMU level Programme Management, financial management and Reporting support | Planned | Punjab, KP, Sindh | No PMU support 0 UNJP Annual Report and biannual report 0 Human Interest Story 0 Financial report | Provide overall coordination and quality assurance support for the UNJP, ensuring alignment with objectives and standards. Submit the first UNJP biannual and annual Report, summarizing progress, outcomes, and achievements for the year. Produce one communication product or human-interest story that highlights key successes and impacts of the project. Submit Quarterly Financial Reports, providing an overview of financial expenditures and budget alignment for the quarter. | PMU Supports UNJP part for overall coordination and quality assurance Submission of 1 UNJP Annual Report Submission of 1 Bi-Annual Report Communication Product or Human-Interest story will be produced Quarterly Financial Report will be submitted | PMU Supports UNJP part for overall coordination and quality assurance Submission of 1 UNJP Annual Report Submission of 1 Bi-Annual Report Communication Product or Human-Interest story will be produced Quarterly Financial Report will be submitted | PMU established and fully functional Timely submission of Annual and Bi-Annual Report Development of Human Interest Story Quality Quarterly Financial Report submitted
|  |  | Achieved | [6 empty] | Risk Rating
[5 empty] | Sources: TBD |  |  |  |  | Major
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR)
Output 2 Impact Weighting (%) |  | Indicators on Sexual Violence |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Strengthened government institutions with effective policies and action plans for protection of women and girls’ rights and prevention and response to gender-based violence and ending child marriage. [Output 2: GBV and Child Marriage; Lead: UNFPA] |  | Indicator 2.1: Number and type of UNJP's supported legislation, policies and action plans in place at federal and provincial level for supporting actions for protection of women and girls' rights and prevention and response of gender-based violence and ending child marriage | Planned | Punjab, KP | Draft Sexual Violence response framework available | KP Sexual Violence Response Framework developed Punjab Sexual Violence Response Framework developed | KP & Punjab Sexual Violence Response Frameworks endorsed by the government | Improved regulatory frameworks (draft Rules) and institutional capacities (SOPs and guidelines) enable a coordinated, inclusive and gender sensitive prevention and response to sexual violence in KP and Punjab | Improved regulatory frameworks, draft Rules, curriculum, SOPs and guidelines available in line with minimum standards and principles of survivor centred care in KP and Punjab | • Adequate time and resources are allocated for seeking the commitment of the government officials and political leadership to the programme • Government counterparts recognise the importance of data generation and use as evidence to inform interventions that promote the rights of marginalized groups – including those subjected to modern forms of slavery – as essential to fulfilling Pakistan’s national and international commitments • The UNJP generates information to influence policy makers and public representatives that eliminating gender-based violence and violence, abuse and exploitation of children is necessary for poverty reduction, development, and social cohesion • Government priorities and policies do not shift in a major way to compromise programming activities • Public representatives are willing to set aside political differences and work jointly to improve the domestic legal and policy framework • Security situation remain stable, allowing programme activities to roll out as planned • Online/virtual programme delivery do not significantly affect the effectiveness of programme interventions
Achieved
|  |  | Planned | Sindh | 0 | Two actions in line with the Sexual Violence Response Framework Sindh implemented. | 3 actions implemented aligned with the Sexual Violence Response Framework | 3 actions implemented aligned with the Sexual Violence Response Framework | Improved regulatory frameworks, draft Rules, curriculum, SOPs and guidelines available in line with minimum standards and principles of survivor centred care in KP and Punjab
Achieved
|  | Indicator 2.2: Number and type of initiatives to support and strengthen GBV prevention and response mechanism and systems | Planned | Punjab, KP | Draft Sexual Violence response framework available | Two ARCCs established, one in KP and one in Punjab 100 Criminal Justice and related professionals (Police, Prosecution, MLOs, and Judges) trained on inclusive and sensitive responses to GBV survivors Learning and sharing conference conducted among CJS and other actors on sexual violence response. | 100 Criminal Justice and related professionals (Police, Prosecution, MLOs, and Judges) trained on inclusive and sensitive responses to GBV survivors | Improved capacities through the ARCC model and institutionalisation of trainings of CJS for inclusive and gender sensitive response to GBV in KP and Punjab | Informed by ARCC models established, costed action plan and draft PC1 available. Institutionalisation of trainings of CJS for inclusive and gender sensitive response to GBV in KP and Punjab
Achieved
|  |  | Planned | Sindh |  | Baseline assessment for one ARCC completed for selected district of Sindh 100 Criminal Justice and related professionals (investigation Officer, SSIOU, MLOs, Police, Prosecutors, Lawyers, Judges and GBV services providers) and administrative actors (DC, magistrate) trained on GBV, ARA, Rules, Guidelines and SOPs for an inclusive and sensitive responses to GBV survivors Clinical Management of Rape curriculum developed for institutionalisation in an academic institution | 150 Criminal Justice and related professionals (investigation Officer, SSIOU, MLOs, Police, Prosecutors, Lawyers, Judges and GBV services providers) and administrative actors (DC, magistrate) trained on GBV, ARA, Rules, Guidelines and SOPs for an inclusive and sensitive responses to GBV survivors | Clinical Management of Rape curriculum institutionalised in at least one academic institution Capacity building plan developed and recommendations provided for longer-term sustainability and scale up | Clinical Management of Rape Curriculum institutionalised.
Achieved
|  | Indicator 2.3: Available evidence on GBV and Child Marriage | Planned | Punjab, KP | Draft Sexual Violence response framework available | 500,000 persons including CJS and other actors are reached through an awareness campaigns (disability inclusive) on redressal mechanism related to Gender Based Violence (including TFGBV) and child marriage Initiate a study on technology facilitated GBV (prevention and response) with focus on women and girls | Report available on the improved service delivery to GBV survivors and shared with relevant stakeholders for programme design in KP and Punjab | Improved evidence (03) reports on Disability Audit, Mapping of CJS services and Improvement of Service delivery) available in KP and Punjab to inform inclusive and gender sensitive policies and programmes for GBV prevention and response | Evidence (03) reports on Disability Audit, Mapping of CJS services and Improvement of Service delivery) available in KP and Punjab to inform inclusive and gender sensitive policies and programs for GBV prevention and response.
Achieved
|  |  | Planned | Sindh |  | Developed a bench book for judges, incorporating case laws, legislation, and SOPs on sexual violence Qualitative study on sexual violence hotspots initiated, with methodology and tools finalised . | Qualitative study conducted on the hotspots for sexual violence and domestic violence | Launch of the study on the hotspots for sexual violence and domestic violence | Improved evidence base available on the issue of sexual violence and related legislative and implementation mechanisms
Achieved
Sources: UNFPA Policy Reforms Scale Sheet validated by provincial government records of bills, cabinet minutes, website and news clippings
|  | Indicators on Domestic Violence |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Indicator 2.1: Number and type of UNJP's supported legislation, policies and action plans in place at federal and provincial level for supporting actions for protection of women and girls' rights and prevention and response of gender-based violence and ending child marriage | Planned | Punjab, KP | Domestic Violence Act enacted in Punjab and KP | Dar-ul-Aman's SOPs reviewed and aligned with Interagency GBV Case Management Guidelines (KP) Dar-ul-Aman's SOPs presented to the Technical Committee of MSCM KP Consolidated draft of SOPs for Punjab Women Protection Centres available Technical Committee of MSCM (KP) notified and action plan available 30 stakeholders (Women protection officers, lawyers, district administration) in five priority districts of KP and Punjab trained on domestic violence legislations | The SOPs for DAU notified by SWD KP Consolidated draft for the Women Protection Centres SOPs notified | Improved institutional capacities (SOPs and Guidelines) for multi-sectoral GBV prevention and response mechanism operational in KP and Punjab | Improved institutional capacities ( SOPs and Guidelines) for multi-sectoral GBV prevention and response mechanism operational in KP and Punjab
Achieved
|  |  | Planned | Sindh |  | Roadmap of DV Act 2013 is launched and a Costed Action Plan for the implementation of Sindh DV Act 2013 is available Model One Stop Protection Centre is established in one district of Sindh OSPC Implementation Plan and guidelines are available | Implementation of the Sindh DV Act 2013 roadmap and action plan (at least 3 actions) supported Monitoring & Accountability Framework for implementation of DV law in Sindh is available | Implementation of the Sindh DV Act 2013 roadmap and action plan (at least 2 actions) supported | Improved institutional capacities ( SOPs and Guidelines) for multi-sectoral GBV prevention and response mechanism operational in Sindh
|  | Indicator 2.2: Number and type of initiatives to support and strengthen GBV prevention and response mechanism and system |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  |  | Planned | Punjab, KP | Domestic Violence Act enacted in Punjab and KP GBV Case Management curriculum available | GBV case management curriculum institutionalised in an academic institution in at least one province | Functional (formation, notification of meetings) multisectoral coordination at Planning and Development Department level and SWD level (for GBV prevention and response) in KP and Punjab | Improved institutional capacities (coordination mechanism, trainings and GBV case management) for a multi-sectoral inclusive and gender sensitive prevention and response to GBV in KP and Punjab | GBV Case Management Curriculum institutionalised in KP and Punjab with faculty trained and teaching GBV case management curriculum including TFGBV
Achieved
|  |  | Planned | Sindh |  | GBV helpline database is standardised and aligned with VAW indicators framework. Disability inclusive GBV referral pathway (TFGBV) available for DuAs, Helplines and OSPC Guidelines for integrating GBV helpline with police helpline developed | GBV helpline, Dua and WSS staff trained on SOPs, referral pathways, psychosocial support and ethical and quality response to GBV survivors Users' feedback mechanism for Helpline is developed and functional Guidelines for integrating GBV helplines with police helpline endorsed | GBV helpline integrated with Police Helpline 15 Develop longer term plan for capacity building and strengthening of GBV helpline | Standardized and quality GBV data bases (shelter home and helpline) available to informing evidence based policy making and programming
[6 empty] | GBV Case Management (including TFGBV) capacity building initiative launched in partnership with the Government of Sindh. 25 GBV service providers (DuAs, GBV helplines, WPC, Police Helpline, prosecutors, GBV investigation officers) are trained on GBV basic concepts, principles, handling GBV disclosure, responsible referrals | GBV case management curriculum is institutionalised in one service provider institution/at least one academic institution in Sindh A pool of master trainers on GBV case management available in Sindh | Plan for the sustainability and scale up of GBV case management is available GBV Case Management Curriculum available for in service and educational institutions as a course work | GBV Case Management Curriculum institutionalised in KP and Punjab with faculty trained and teaching GBV case management curriculum including TFGBV
[6 empty] | GBV Data safety and sharing protocols developed and notified SOPs/guidelines of Helplines, DuAs and Women Safe Houses are updated in line with GBV Inter-Agency guidelines | Monitoring & Accountability Framework for implementation of DV law in Sindh is developed SOPs/guidelines of Helplines, Dua's and Women Safe houses are endorsed Monitoring framework in line with interagency GBV case management guidelines is available for GBV helpline and DUA |  | Standardized and quality GBV data bases (shelter home and helpline) available to informing evidence based policy making and programming
Achieved
|  | Indicator 2.3: Available evidence on GBV and Child Marriage | Planned | Punjab, KP |  | Study (baseline) on the barriers in accessing/uptake of GBV services (health, social services, police and justice/ legal) is available for KP | Report on improvement in prevention, protection and response services for GBV cases including for PWDs in KP and Punjab 2000 government officials reached/informed through an awareness on the findings of costing study | Improved evidence (reports on barriers in accessing GBV services and cost of GBV social services, improvement of service delivery) available in KP and Punjab to inform inclusive and gender-sensitive policy and programmes for GBV response | Improved evidence (reports on barriers in accessing GBV services and cost of GBV social services, improvement of service delivery) available in KP and Punjab to inform inclusive and gender-sensitive policy and programs for GBV response.
Achieved
|  |  | Planned | Sindh |  | Disability accessibility assessment of government GBV response services initiated (tools developed, partnership secured) in Sindh Study (baseline) on the barriers in accessing/uptake of GBV services (health, social services, police and justice/ legal) is initiated Comparative analysis (study) on different GBV services delivery models (One Stop Protection Centre, DuAs or any other) to assess efficiency, effectiveness initiated | Disability accessibility assessment of government GBV response services report findings disseminated. Study on barriers for the survivors in uptake/accessing existing GBV services (health, social services, police and justice/ legal) is available and findings disseminated. Operational/Comparative Study on different GBV services delivery models (One Stop Protection Centre, DuAs or any other) to assess efficiency, effectiveness is available and findings disseminated | Implementation of recommendations (at least 4) of evidence products(disability audit, barriers study and operational study) supported | Improved evidence (reports on barriers in accessing GBV services and cost of GBV social services, improvement of service delivery) available in Sindh to inform inclusive and gender-sensitive policy and programs for GBV response.
Achieved
Sources: UNFPA Initiatives Tracking Sheet validated by actual evidence, independent assessments/verification, studies, policy documents, dissemination events, minutes from government meetings, anecdotal evidences and news and press clippings
|  | Indicators on Child Marriage |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Indicator 2.1: Number and type of UNJP's supported legislation, policies and action plans in place at federal and provincial level for supporting actions for protection of women and girls' rights and prevention and response of gender-based violence and ending child marriage | Planned | Punjab, KP | No national framework on Child Marriage (CM) PEA studies on CM available in Punjab and KP | Final draft of legislative instruments (amended CMRA, Rules and by-laws) provided to relevant government department for the prevention and response to child marriage in at least one province National framework to end child marriage available. Provincial action plans aligned with National Framework on Ending Child Marriage developed and available in KP and Punjab | N/A | Improved policy and legal frameworks (draft CMRA, rules and by laws) and capacities (criteria for Nikah Registrars and oversight mechanisms) enable a coordinated, inclusive and gender sensitive prevention and response to Child Marriage in KP and Punjab | Improved policy and legal frameworks( draft CMRA, rules and by laws) and capacities (criteria for Nikah Registrars and oversight mechanisms) enable a coordinated, inclusive and gender sensitive prevention and response to Child Marriage in KP and Punjab.
Achieved
|  |  | Planned | Sindh | TBD | Consensual draft of CMRA 2013 rules developed and shared with SWD Nikah Registrar certification criteria developed in Sindh for prevention of child marriage | Nikah Registrar certification criteria piloted in at least two districts in Sindh for prevention of child marriage | N/A | Improved policy and legal frameworks( draft CMRA, rules and by laws) and capacities (criteria for Nikah Registrars and oversight mechanisms) enable a coordinated, inclusive and gender sensitive prevention and response to Child Marriage in Sindh
Achieved
|  | Indicator 2.2: Number and type of initiatives to support and strengthen GBV prevention and response mechanism and systems | Planned | Punjab, KP | No national framework on Child Marriage PEA studies on CM available in Punjab and KP | Capacities of 1200 NR & UC officials built through training and engagement in Punjab and KP for marriage registration strengthening and effective implementation of the law Oversight mechanism for Nikah Registrars rolled out in at least two districts (one in each) of Punjab and KP Capacity building of 100 oversight cadre (ADLG) in Punjab and KP completed on laws, amendments, policies and reporting mechanism etc | Capacities of 1000 NR & UC officials built through training and engagement in Punjab and KP for marriage registration strengthening and effective implementation of the law Capacity building of 100 oversight cadre (ADLG in Punjab and Supervisors in KP) in KP and Punjab | Improved institutional capacities (trainings of nikah registrars and oversight mechanism) of UC officials in KP and Punjab for inclusive and gender sensitive response to Child Marriage | Improved institutional capacities (trainings of nikah registrars and oversight mechanism) of UC officials in KP and Punjab for inclusive and gender sensitive response to Child Marriage
Achieved
|  |  | Planned | Sindh | TBD | Training curriculum for Nikah Registrars, Nikah Khawan & UC officials contextualised for Sindh 100 Nikah Registrars, Nikah Khawan & UC officials and other relevant stakeholders, including the Child Protection Authority trained on Child Marriage Restraint Act and its implementation A provincial narrative (concept note) on health consequences of CM through engagement with parliamentarians, ulema and other stakeholders to change discriminatory social norms at institutional (multisectoral) level initiated | 600 Nikah Registrars, Nikah Khawan & UC officials and other relevant stakeholders, including the Child Protection Authority trained on Child Marriage Restraint Act and its implementation Capacity building of 100 members of oversight cadre in Sindh An oversight and monitoring mechanism developed for the implementation of the child marriage law in Sindh | Periodic reports produced by the oversight and monitoring mechanism for the implementation of the CM law in Sindh | Improved institutional capacities (trainings of nikah registrars and oversight mechanism) of UC officials in Sindh for inclusive and gender sensitive response to Child Marriage
Achieved
|  | Indicator 2.3: Available evidence on GBV and Child Marriage | Planned | Punjab, KP | No national framework on Child Marriage PEA studies on CM available in Punjab and KP | 700,000 persons - including government officials- reached through an awareness campaign on consequences and redressal for Child marriage A policy brief- situational analysis on child marriage developed and disseminated Advocacy note on CM (including latest case laws and Islamic Jurisprudence interpretation that supports ending CM) available and shared with stakeholders Profiling Study for Nikah Registrars, Nikah Khawan's and VC Secretaries/UC available in Khyber Pakhtunkhwa and Punjab | Report on pilot UCs for increased and accurate marriage registrations available to LGCD for future interventions | Improved reach (1 million of relevant stakeholders including government officials) on consequences and redressal for CM | Improved reach (1 million of relevant stakeholders including government officials) on consequences and redressal for CM
Achieved
|  |  | Planned | Sindh | TBD | A qualitative study on intersectionality of child marriage (persons with disabilities, ethnic and religious minorities, urban-rural and marginalised groups) is initiated in Sindh Evidence informed value-based discussions conducted to promote cross sectoral learning, awareness-raising and coordination for social norm change on CM and GBV | Launch of qualitative study on intersectionality of child marriage (persons with disabilities, ethnic and religious minorities, urban-rural and marginalised groups) in Sindh Alliances with (faith leaders, media, women-led orgs, PWDs, adolescents and youth) developed for joint lobbying on addressing discriminatory social norms on CM An awareness campaign informed by the discussions on CM prevention and response through intersectional lens | 1 million of relevant stakeholders including government officials) on evidence documentation reached out on consequences and redressal for CM | Improved reach (1 million of relevant stakeholders including government officials) on consequences and redressal for CM
Achieved
|  |  | Sources: Policy Advocacy Data Sheet validated by necessary policy evidences, minutes of meetings, pictures, campaign material and tools, communication strategy document | [6 empty] | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%) |  | Major
INPUTS (HR) |  | FCDO (FTEs)
Output 3 Impact Weighting (%) |  | Output Indicator 3.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Enhanced citizen information, voice and actions to address child marriage, GBV and social exclusion (Output 3 Lead: British Council) |  | Number of Aagahi Centres and Village, District and Provincial forums Operational | Planned | Punjab, KP | 0 | 452 VFs, 226 AACs and 15 DFs operational 15 Village Networks formed and operational 40 demands from communities delivered to DF/relevant stakeholder 4 policy recommendations from PFs delivered to relevant stakeholders Transition of British Council from commercial contract to MoU (responsibility FCDO) | 60 demands from communities delivered to DF/relevant stakeholder 6 policy recommendations from PFs delivered to relevant stakeholders | Communities experience sharing Forum Lessons learned document from VF Networks | 452 VFs, 226 AACs and 15 DFs operational 15 Village Networks formed and operational 100 demands from communities delivered to DF/relevant stakeholder 10 policy recommendations from PFs delivered to relevant stakeholders Communities experience sharing Forum Lessons learned document from VF Networks | • Funding is not interrupted or reduced significantly • Access to the field areas is not hampered by security concerns and/or unavailability of NOCs • There is political stability enabling implementation of Aawaz II interventions • Political polarisation and economic downturn has no impact on programme delivery • Communication and internet connectivity in the country is available and accessible • The selection of communities, civil society partners and ACAs is inclusive and ensures the representation of women, men, youth, religious minorities, PWDs, transgender and other marginalised communities • Spaces for community mobilisation are not subject to elite capture and allow marginalised voices to be heard • Discussions on sensitive issues are managed in a conflict-sensitive manner and do not raise social tensions • Spaces for hearing voices for change are available. Community forums are managed effectively to channel and amplify the voice of marginalised groups in a conflict-sensitive way • Voices are not silenced by fear and community forums remain safe spaces • There is parallel support under Aawaz Outputs 1 and 2 (UNJP) to build the awareness, motivation and capacity of duty-bearers to listen to community demands and respond effectively • The government is supportive of and actively participates in spaces for constructive citizen-state interaction • Referral mechanisms are developed and effective • Online/virtual programme delivery do not significantly affect the effectiveness of programme interventions in the short term • Provincial and District governments have priorities and resources aligned with Aawaz thematic areas
Achieved
Sources: Aawaz II database, case studies, programme progress reports and assessments
|  | Output Indicator 3.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Number of community members benefitting from actions taken to address child marriage, GBV and intolerance | Planned | Punjab, KP | 0 | 1,000 ACAs trained 12,000 individuals aware and have knowledge of child marriage, GBV, rights of vulnerable groups 500 actions taken by community members/forums and ACAs 12,000 community individuals benefit from actions taken by community members/ forums and ACAs 7,000 individuals aware of services available 5,000 individuals access services | 1,000 ACAs trained 30,000 individuals aware and have knowledge of child marriage, GBV, rights of vulnerable groups 850 actions taken by community members/forums and ACAs 32,000 community individuals benefit from actions taken by community members/ forums and ACAs 10,000 individuals aware of services available 7,000 individuals access services | 2 case studies on behaviour change Youth engagement forum showcasing youth led initiatives for behaviour change | 2,000 ACAs trained 42,000 individuals aware and have knowledge of child marriage, GBV, rights of vulnerable groups 1,350 actions taken by community members/forums and ACAs 44,000 community individuals benefit from actions taken by community members/ forums and ACAs 17,000 individuals aware of services available 12,000 individuals access services 2 case studies on behaviour change Youth engagement forum showcasing youth led initiatives for behaviour change
Achieved
Sources: Training attendance sheets and Community Action database, SAPs database, programme progress reports, training reports
|  |  | Planned | Sindh
|  | Output Indicator 3.3 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Evidence Generated of behaviour change and citizen - state engagement | Planned | Punjab, KP | 0 | 2 case studies on Aawaz II thematic areas Number of accelerating social change projects initiated 1 national experience sharing and learning forums 1 impact video and testimonials of beneficiaries | 2 case studies on Aawaz II thematic areas Number of research and assessment studies initiated Number of accelerating social change projects completed 3 impact videos and testimonials of beneficiaries 1 national Aawaz II learning and experience sharing forum 2 provincial learning forums | Number of research and assessment studies reports Number of papers and lesson learnt documents completed Recommendations and policy asks from 2 provincial consultations | 4 case studies on Aawaz II thematic areas Number of accelerating social change projects completed 4 impact videos and testimonials of beneficiaries 2 national Aawaz II learning and experience sharing forum 2 provincial learning forums Number of research and assessment studies reports Number of papers and lesson learnt documents completed Recommendations and policy asks from 2 provincial consultations
|  |  | Achieved | [6 empty] | Risk Rating
|  |  | Sources: Research studies and reports | [6 empty] | Moderate
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) |  | FCDO (FTEs)
Output 4 Impact Weighting (%) |  | Output Indicator 4.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Citizens and communities better able to ensure social cohesion and tolerance (Output 4 Lead: British Council) |  | Number of initiatives on social cohesion and tolerance and number of community members benefitting | Planned | Punjab, KP | 0 | 800 early warnings received 30 early warnings focusing on social cohesion and tolerance addressed 300 actions taken to promote social cohesion and tolerance 4,800 community individuals benefit from social cohesion actions | 1,500 early warnings received 45 early warnings focusing on social cohesion and tolerance addressed 850 actions taken for social cohesion and tolerance 18,000 community individuals benefit from social cohesion actions | Study on EWS/ERM initiatives | 2,300 early warnings received 75 early warnings focusing on social cohesion and tolerance addressed 1,150 actions taken for social cohesion and tolerance 22,800 community individuals benefit from social cohesion actions Study on EWS/ERM initiatives | • The selection of communities, civil society partners and ACAs is inclusive and ensures the representation of women, men, youth, religious minorities, PWDs, transgender and other marginalised communities • Spaces for community mobilisation are not subject to elite capture and allow marginalised voices to be heard • Discussions on sensitive issues are managed in a conflict-sensitive manner and do not raise social tensions • Spaces for hearing voices for change are available. • Community forums are managed effectively to channel and amplify the voice of marginalised groups in a conflict-sensitive way • Voices are not silenced by fear and community forums remain safe spaces • ACAs operate to high ethical standards and respect the principles of safeguarding; • Community-based monitoring mechanisms are established by government to enable communities to monitor the effectiveness of services and legal protections. • Online/virtual programme delivery do not significantly affect the effectiveness of programme interventions in the short term. •Communities are open and willing to accept excluded populations and change behaviours • Individuals view social cohesion as important for community building • Community members and stakeholders are willing to report and address conflict within their communities. • Public services and structures (complaint mechanisms, vigilance committees) are functional and responsive
Achieved
Sources: EWS/ERM record, Programme progress reports, case studies
|  | Output Indicator 4.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Knowledge products produced on social cohesion and tolerance | Planned | Punjab, KP | 0 | 1 case study on social cohesion and tolerance Conflict sensitivity assessment | 1 case study on social cohesion and tolerance 1 brief on social cohesion and tolerance | Lesson learnt document on social cohesion and tolerance | 2 case studies on social cohesion and tolerance Conflict sensitivity assessment 1 brief on social cohesion and tolerance Lesson learnt document on social cohesion and tolerance
Achieved
|  |  | Sources: Social cohesion sessions document, case studies, briefs, and lessons learnt report | [6 empty] | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%) |  | Moderate
INPUTS (HR) |  | FCDO (FTEs)
Output 5 Impact Weighting (%) |  | Output Indicator 5.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Enhanced citizen information, voice and actions for reducing violence, abuse, exploitation and intolerance (Output 5 Lead: CARE International) |  | Number of AACs, village forums, district and provincial forums initiated by communities and local partners | Planned | Sindh | 0 | Baseline study completed 75 villages identified for programme implementation. 1 Induction training completed for local implementing partners Accountable grant competition and inception for CARE International (Sindh Community Engagement Component) Responsibility FCDO | 75 Village Forums formed 5 District Forums formed 1 Provincial Forum formed 15 AACs established & Operational | 100 SALT facilitators trained 15 AACs established and operational At least 60% of all forums become fully functional and effective | 30 AACs 75 Village Forums 5 District Forums 1 Provincial forum
Achieved
Sources: Aawaz II database, TORs, profiles of the forums, training record, pre and post test
|  | Output Indicator 5.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | 60% of community forums take actions to address child marriage, gender-based violence (GBV), religious disharmony, disability exclusion and social intolerance. | Planned | Sindh | 0 | 5 Technical Working Groups operational 150 ACA identified from the villages | 81 Action Plans developed and executed by each VF, DF, PF and SIGs | Number (#) of issues taken up at district forums and provincial forums 60% of actions taken by DFs in support of VFs 60% action taken by PF in support of DFs and VFs. Number (#) of policy recommendations from VFs and DFs delivered to relevant stakeholders. | 60%
Achieved
Sources: Aawaz II database, SAPs, training record, ACA profiles, and list of recommendations
|  | Output Indicator 5.3 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Number (#) of people of all genders actively participating in formal (government-led) and informal VF, DF, PF (disaggregated by sex, gender, age, wealth and disability status) | Planned | Sindh | 0 |  | 880 members actively participating in VF, DF and PF forums 50% female membership in all forums | 3600 requests for information/referral received by AACs from male, female and transgenders 60% of requests fulfilled. | 4590
Achieved
[5 empty] | Sources: Aawaz II database, profiles of forums, ACA, AAC data and files |  |  |  |  | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) |  | FCDO (FTEs)
Output 6 Impact Weighting (%) |  | Output Indicator 6.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Citizens and communities better able to prevent conflict and demonstrate acceptance of all (Output 6 Lead: CARE International) |  | Number of people benefitting from the actions on social cohesion and tolerance -disaggregated by sex, age, wealth and disability status | Planned | Sindh | 0 | District and provincial services' and stakeholders' mapping completed | 5 referrals pathways tracking system developed 80 Early Warning Systems established at Village and District levels | Number (#) of early warnings reported 9180 community individuals benefitting from timely action on social cohesion and tolerance | 9180
Achieved
Sources: Aawaz II database, pathways documents, EWS documents, and database of early warning systems
|  | Output Indicator 6.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Number and types of evidence generated | Planned | Sindh | 0 | 1 Pre-KAP Survey Completed 1 Participatory Conflict Sensitivity Analysis completed 1 Gender Equality and Social Inclusion (GESI ) analysis completed | 1 Social Analysis and Actions Plan developed Number (#) of Youth fund recipients selected | 1 compilation of case studies on Aawaz II thematic areas produced 10 participatory research conducted by ACAs 1 impact video of beneficiaries developed 1 Compilation of 25 Family & Change Agent Ethnographies published 1 Lessons learned document produced and widely disseminated 1 Post-KAP Survey Completed Final Evaluation Completed | 12
Achieved
[5 empty] | Sources: List of evidences and final documents produced; meeting minutes; compiled case studies, etc. |  |  |  |  | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) |  | FCDO (FTEs)
Output 7 Impact Weighting (%) | Output 7 (a) | Output Indicator 7 (a) 1.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Safe Digital Environment Programme (SDEP) (April 2025-March 2027) Lead UNDP | A multi-stakeholder platform established by the programme actively facilitates a community of practice to inform and support the Government of Pakistan in tackling online hate speech and disinformation against vulnerable groups while protecting freedom of speech and expression | Evidence of policymakers and experts engaged in bilateral and interministerial meetings, workshops, and consultations aimed at creating buy-in and interest from key stakeholders to tackle online hate speech and disinformation at a policy level | Planned | Federal | By the end of HSDP phase II (March 2025):A minimum of 170 policymakers and experts engaged (through inter-ministerial, several needs-based bilateral meetings and 5 workshops) to encourage responsible digital citizenship policy and practice | A minimum of 25 policymakers and experts engaged (through at least 1 bilateral and/or multilateral (inter ministerial) meetings and 1 advisory council meeting | • A minimum of 60 policymakers and experts engaged (through at least 3 bilateral and/or multilateral (inter ministerial) meetings and 4 advisory council meetings. •At least 3 parliamentary National/provincial workshops held on online safety and legal dimensions and readout available." •Technical support provided for PIPs E-Learning platform 2 courses" | • A minimum of 50 policymakers and experts engaged (through at least 2 bilateral and/or multilateral (inter-ministerial) meetings and 3 advisory council meeting. • At least 2 parliamentary National/provincial workshops on online safety and legal dimensions held and readout available. | • A minimum of 135 policymakers and experts engaged (through at least 6 bilateral and/or multilateral (inter ministerial) meetings and 8 advisory council meetings and 5 workshops to encourage responsible digital citizenship policy and practice • At least 5 parliamentary National/provincial workshops held on online safety and legal dimensions and readout available. | • The Government of Pakistan is committed and ready to improve the policy regime on Hate Speech and Disinformation • The Government is open to holding constructive dialogue with the Advisory Council • Political interference and the influence of Government of Pakistan counterparts does not affect actions of targeted stakeholders to tackle hate speech and disinformation • The Inter-Ministerial Steering Committee is formed and has the mandate to act on the recommendations provided • Experts engaged by the programme, including from the Advisory Council through their work, gain wider endorsement with Government of Pakistan representatives • Commitment is an HSDP led intervention based evidence of an initiative conceived, developed and/ or implemented by the key stakeholders for the purpose of tackling hate speech, misinformation and disinformation
Achieved
Sources: Narrative reports, testimonials, meeting minutes, event readouts, partner reports, project quarterly report
Output 7 IMPACT WEIGHTING (%) | Output 7 (b) | Output Indicator 7(b) 1.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Safe Digital Environment Programme (SDEP) (April 2025-March 2027) Lead UNDP | A fact-checking tool (iVerify), a social media listening tool (eMonitor) and technical training (implemented through the programme) enhance the capability of the Government of Pakistan, experts, Civil Society Organisations (CSOs) and tech/media companies to detect and manage harmful disinformation and digital content. | Numbers of fact-checked content reported through the iVerify platform that detected harmful digital content or disinformation (disaggregated by vulnerable groups targeted) | Planned | Federal | By the end of HSDP phase II (March 2025): At least 10 social media listening reports and 14 insight based digital products/posts produced and disseminated | Readout on iVerify fact checked available for SDEP Phase II PCR At least 50 content examples fact checked using iVerify platform | • At least 200 content examples fact checked using iVerify platform. • At least 20-30 individuals trained as iVerify advocated for community based fact checking. At least 60 community notes submitted to platforms by iVerify advocates. | • At least 150 content examples fact checked using iVerify platform. • At least 180 community notes submitted to platforms by iVerify advocates | • At least 400 media stories fact checked using iVerify platform. • At least 20-30 individuals trained as iVerify advocated for community based fact checking. At least 240 community notes submitted to platforms by iVerify advocates. | • Training is effective and delivers against its objectives. Specialised expertise necessary for training and tool development is available and accessible • Government institutions and identified experts are receptive to the training and show willingness to take up the issue as a long-term feature of their institutions and curriculum • Identified trainees have capacity to be changemakers, i.e. they carry influence and can take decisions
Achieved
Sources: iVerify platform website, testimonials, narrative report, IP reports
|  | Output Indicator 7 (b) 1.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Analysis and learning generated from eMonitor social media listening reports produced and disseminated to a wide policy, civil society and media audience that promotes responsible digital citizenship. | Planned | Federal | By the end of HSDP phase II (March 2025): Total 250 individuals (215 government officials, 25 experts and 10 media representatives) trained + Government Engagement and Lesson Learnt Report (phase I & phase II cumulative) | Final social media listening reports and readouts on insight based digital product/post available for SDEP Phase II PCR At least 6 bi-monthly social media monitoring reports and 3 monthly analysis reports produced, targeting specific harmful content and disinformation affecting vulnerable groups such as women, religious and ethnic minorities, PWDs, transgender, and Pakistani diaspora in UK | • At least 24 bi-monthly social media monitoring reports and 12 monthly analysis reports produced. | • At least 18 bi-monthly social media monitoring reports and 9 monthly analysis reports produced. | • At least 48 bi-monthly social media monitoring reports and 18 monthly analysis reports are produced using social media platforms, targeting specific harmful content and disinformation affecting vulnerable groups such as women, religious and ethnic minorities, PWDs, transgender, and Pakistani diaspora in UK. • eMonitor social media lessons learnt readout produced.
Achieved
Sources: eMonitor tool, eMonitor social media Lessons Learnt Report, social media listening report, Insight based digital products/posts report, quarterly and annual reports, dissemination data for digital products that shows unique visitor clicks.
|  | Output Indicator 7 (b) 1.3 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Number of government, independent expert and media officials trained on identifying disinformation, hate speech and how to do fact-checking (disaggregated by gender, government department and role type/job grade). | Planned | Federal | By the end of HSDP phase II (March 2025): Total 250 individuals (215 government officials, 25 experts and 10 media representatives) trained + Government Engagement and Lesson Learnt Report (phase I & phase II cumulative) | At least 40 government officials, experts and media representatives trained through 2 workshops | At least 70 government officials, experts and media representatives trained through 2 workshops on online safety and legal dimensions. | At least 90 government officials, experts and media representatives trained through 2 workshops on online safety and legal dimensions. | At least 200 government officials, experts and media representatives trained through 8 workshops on online safety and legal dimensions.
Achieved
Sources: Lessons Learnt Report, pre and post assessments, quarterly and annual reports, MOUs with newsrooms, Testimonials, Story of Change.
Output 7 | Output 7 (c) | Output Indicator 7.3.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Safe Digital Environment Programme (SDEP) (April 2025-March 2027) Lead UNDP | Young digital media users (students engaged through a youth empowerment and behavioural change campaign) are more aware of online harms of mis/disinformation/hate speech and demonstrate responsible behaviour in online information-sharing and language usage. | Evidence that individuals trained on fact-checking are sensitised to the harmful effects of hate speech and demonstrate a change in their capacity and sensitivity towards inclusive rights, especially of vulnerable groups (disaggregated by gender and province) | Planned | Federal | By the end of HSDP phase II (March 2025): 1479 students trained by engaging 21 universities (University Training and Learning Outcome Report) (phase I & Phase II cumulative) Media campaigns reached 34.4 million unique users in Phase I and 11.85 million in Phase II. | At least 2 Responsible Digital Media Engagement Workshops completed reaching at least 60 young Aawaz Community Advocates (ACAs) from 2 universities. | • At least 1 workshop to train PTV digital teams on fact checking techniques and readout available. • At least 1 TOTs held with at least 1 universities to pilot online course. • Pilot online course done in at least two school systems • At least 4 training sessions held for regional collaboration - Support to AAWAZ networks • Joint messaging and BCC campaigns in collaboration with telecom companies and PTV/PTA launched. • Atleast 30 episodes of podcast series on: First person accounts of Victims of Online Harms, TFGBV and Online Harassment and Online Dis/Misinformation in Pakistan – Emerging Trends produced and released. | • At least 2 TOTs held with at least 2 universities to deploy online course. • Digital literacy workshops conducted in at least 8 schools. • At least 1 training session held for regional collaboration - Support to AAWAZ networks • At least 4 initiatives with private partners supported. • At least 90 products developed and released by 15 influencers. | • At least 2 Responsible Digital Media Engagement Workshops completed reaching at least 60 ACAs from 2 universities. • At least 3 TOTs conducted to deploy online course in 3 universities and learning document is available on deployment. • At least 1 workshop organized to train PTV digital teams on fact checking techniques and readout available. • At least 10 secondary schools engaged on digital literacy course. • At least 5 training sessions held for regional collaboration - Support to AAWAZ networks. • At least 15 Influencers reach out to 2,000,000 impressions. • At least 2 million people reached with approx. 500,000 individuals engaged through the podcast campaign. | • Universities are receptive to the training and show willingness to take up the issue as a long-term feature of their institutions and curriculum • Students and advocates are interested and willing to take part in the training - and complete it • The training delivered at universities effectively uses localised language to ensure clarity and relevance for diverse student populations
Achieved
|  |  | Sources: University engagement reports, Online course, meeting minutes, Quarterly report, Story of Change Document, pre and post assessments | [6 empty] | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) |  | FCDO (FTEs)
Output 8 Impact Weighting (%) |  | Output Indicator 8.1 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027) | Assumptions
Independent Feedback, Operational Reviews and Monitoring (I-FORM) for Aawaz II Programme |  | Operational Reviews and Assessments, Monitoring Visits and Project Level (I-FORM) VfM | Planned | Punjab, KP, Sindh, Federal | 1 spot check report, 3 operational reviews/assessments and VFM framework and report available from phase 1 | 3 Monitoring visit (qualitative and quantitative data on selective interventions to assess their effectiveness) reports 1 operational review reports/ assessment reports (according to OECD-DAC criteria) Updating the VFM Framework 1 VFM updates as per the agreed VFM framework Procurement and Inception of Third-Party Monitor (I-FORM) Responsibility FCDO | 9 Monitoring visit (qualitative and quantitative data on selective interventions to assess their effectiveness) reports 3 operational review reports/ assessment reports (according to OECD-DAC criteria) 2 VFM updates as per the agreed VFM framework | Final VFM assessment report as per the agreed VFM framework | Final VFM assessment report as per the agreed VFM framework | • There is political stability enabling implementation of Aawaz II interventions • Access to the field areas is not hampered by security concerns and/or unavailability of NOCs • There is willingness on the part of IPs to collaborate and create synergies amongst them for positive outcomes of Aawaz II • Timely availability of data from IPs for IFORM deliverables • Timely availability of data from IPs for the annual review • Timely and effective IP support with regards to primary data collection for IFORM deliverables • FCDO and Aawaz II implementing partners use knowledge products effectively to feed into design of new programmes and review of existing programme • There is willingness on the part of key users to switch to using digital platforms and online data sources
Achieved
Sources: Project M&E Records (strategic documents, TORs for assessment reports, field visit reports, meeting minutes, dashboards, periodic reports)
|  | Output Indicator 8.2 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | End-User Perception and Feedback | Planned | Punjab, KP, Sindh, Federal | 2 beneficiary feedback survey reports available from phase 1 | Baseline survey for Sindh completed Qualitative assessment round 1 completed to enhance end-users' understanding regarding programme operations | Qualitative assessment round 2, 3 & 4 completed to enhance end-users' understanding regarding programme operations | Endline survey report consolidating progress achieved and early outcomes during programme implementation | Endline survey report consolidating progress achieved and early outcomes during programme implementation
Achieved
Sources: Project M&E Records (MEL and VfM strategies, MEL plans, annual VfM analyses reports)
|  | Output Indicator 8.3 |  |  | Baseline (2018/19) | Milestone (June 2025) | Milestone (June 2026) | Milestone (March 2027) | Programme Target (March 2027)
|  | Technical Review, Coordination and Alignment | Planned | Punjab, KP, Sindh, Federal | Aawaz II phase 1 static dashboard repository FCDO Aawaz II Annual Review Report 2024 | Aawaz II dashboard updated for result tracking and reporting progress Annual Lesson Learning event held to synthesise and disseminate generated evidence and offer recommendations 1 QTRs convened and report disseminated 1 SSC meeting held | Aawaz II dashboard updated for result tracking and reporting progress Aawaz II event Decade event focused on the broader Voice and Accountability agenda. 6 QTRs convened and report disseminated 3 SSC meetings Annual Review 2025-26 | Project Completion Report with recommendations | Project Completion Report with recommendations
Achieved
|  |  | Sources: I-FORM Reports and FCDO documents | [6 empty] | Risk Rating
INPUTS (£) |  |  |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) |  | FCDO (FTEs)

## Glossary
List of Abbreviations
1 | ARA | Anti-Rape Act
2 | ARCC | Anti-Rape Crisis Centre
3 | BR | Birth Registration
4 | CAR | Commissionerate for Afghan Refugees
5 | CBCPC | Community-Based Child Protection Committees
6 | CLS | Child Labour Survey
7 | CP | Child Protection
8 | CPCMRS | Child Protection Case Management and Referral System
9 | CPIMS | Child Protection Information Management System
10 | CRVS | Civil Registration and Vital Statistics
11 | DCPUs | District Child Protection Units
12 | DV | Domestic Violence
13 | EWS/ERM | Early Warning System/Early Response Mechanism
14 | GSI | Global Slavery Index
15 | JJSA | Juvenile Justice System Act
16 | KPCPWC | KP Child Protection and Welfare Commission
17 | LG | Local Government
18 | MLO | Medico-Legal Officer
19 | MS | Modern Slavery
20 | NCRC | National Commission on the Rights of Child
21 | PMU | Programme Management Unit
22 | SCMRA | Sindh Child Marriages Restraint Act, 2013
23 | SCPA | Sindh Child Protection Authority
24 | SSIOU | Senior Superintendent of Investigation Unit
25 | SSWF | Social Sector Workforce
26 | SWD | Social Welfare Department
27 | UC | Union Council
28 | VAC | Violence Against Children
29 | WGI | Worldwide Governance Indicators
30 | GBV | Gender Based Violence
31 | CRC | Child Registration Certificate
32 | SDGs | Sustainable Development Goals
33 | SOPs | Standard Operating Procedures
34 | CJS | Criminal Justice and related professionals
35 | TFGBV | Technology facilitated Gender Based Violence
36 | CM | Child Marriage
37 | GESI | Gender Equality and Social Inclusion

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, i.e. is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality e.g. use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets disaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed i.e. consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Proposed Interventions
Outputs | Proposed Interventions
Output 3 (CARE) | Indicators
Enhanced citizen information, voice and actions for reducing violence, abuse, exploitation and intolerance | Indicator 3.1 | Indicator 3.2 | Indicator 3.3
| 3.1.1. Establishment of Village, UC, Taluka, District and Provincial Forums 3.1.2. Establishment of Community Spaces - Aawaz Aagahi Centres (AACs) 3.1.3. Capacity building on project Themes (GBV, IFH, , SI), and SBCC Strategy by Resource Organisations and Technical Partners 3.1.4. Introducing Community Life Competency Process (SALT) to IPs, VFs, DFs, ACAs, SIG leaders | 3.2.1. Identifying and engaging Aawaz Change Agents and Special Interest Groups 3.2.2. Citizen engagement at village, district and provincial levels through forums-people of all genders actively participating in formal (government-led) and informal (civil society led) decision-making spaces. | 3.3.1. Terms of references of VF, DF, and PF 3.3.2. Initial community mobilisation meeting and sessions 3.3.3. Nomination of members for forums 3.3.4. Selection of members 3.3.5. Action planning and progress of each forums
Output 4 (CARE) | Indicators
Citizens and communities better able to prevent conflict and demonstrate acceptance of all | Indicator 4.1 | Indicator 4.2
| 4.1.1. Referral Systems Strengthening and Tracking 4.1.2. Early Warning Systems established at Village, UC, Taluka & District levels to identify and pre-empt conflicts 4.1.3. Supporting Social Innovation and Participatory Action Research & Analysis on Programme Themes, through a Youth PAR Fund and Scholarship Program | 4.2.1. Carry out KAP Survey 4.2.2. Conduct Participatory Conflict Sensitivity Analysis (PCSA) Policy Analyses 4.2.3. Development of impact videos and change testimonials based on SALT learnings on social cohesion and conflict pre-emption 4.2.4. 1 Compilation of case studies/ success stories on each Aawaz II thematic areas published, translated and widely disseminated 4.2.5. 1 Compilation of at least 25 Family and Change Agent Ethnographies published (collaboration with academia) 4.2.6. 1 Lessons learned document produced, translated and widely disseminated 4.2.7. Third-party baseline study 4.2.8. Annual Reviews

## Sheet1 (hidden)
Outcome | Original description | Revised description
Indicator 1 | Local government spending | No Change
Indicator 2 | Citizen satisfaction with basic services | Generation of evidence base on the effectiveness of SNG-II initiatives and verification of short to medium term results to inform endline evaluation of SNG-II Programme’
Output | Original description | Revised description
Output 1 | Plans and budgets are more evidence-based and executed as planned | PFM systems are strengthened for effective planning and budgeting
IMPACT WEIGHTING | 35% | 30%
Output 1, Indicator 1.1 | Planning capabilities in provincial and local government institutions | Provincial planning capability
Output 1, Indicator 1.2 | Budget preparation process | Provincial budget preparation capability
Output 1, Indicator 1.3 | Budget execution in government | Provincial budget execution capability
Output 1, indicator 1.4 | This indicator was removed, and work related to A&I is now captured in other indicators across Logframe
Output 2 | Institutions are better organised to deliver (with a focus on Covid recovery and climate adaptation) | Institutions are better organised to deliver
IMPACT WEIGHTING | 20% | 20% (No change)
Output 2, Indicator 2.1 | Institutional capacity to plan and deliver post Covid recovery | Institutional capacity to deliver, including social protection, climate change etc.
Output 2, Indicator 2.2 | No longer part of output
Output 3 | Fiscal Space is increased with more resources available for service delivery | Fiscal capacity is strengthened to enhance revenue and expenditure efficiency'
IMPACT WEIGHTING | 30% | 25%
Output 3, Indicator 3.1 | Provincial own source revenue capacity | Own source revenue capacity
Output 3, Indicator 3.2 | Efficiency savings in government expenditure | Capacity to ensure expenditure efficiency
Output 4 | Innovative approaches developed and piloted | Local governance is improved
(Output 4 (new output added from year 5)
IMPACT WEIGHTING | 15% | 25%
Output 4, Indicator 4.1 | New Indicator "Local Governance and PFM systems"
Output 4, Indicator 4.2 | New Indicator "Local level service delivery"