## Logframe
Pakistan SNG-II Logframe | Version: May 23 2024
PROJECT TITLE: Pakistan Sub-National Governance (II)
IMPACT | Impact Indicator 1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Year 7 Milestone (March 2026) | Programme Target (2019-25)
Strengthened democracy in Pakistan and reduced poverty | Performance against Democracy Index (EIU) | Planned | National | 4.17 (Overall) 5.36 (Government Functioning) (2018 Score) | Data not available | 4.17 (Overall) 5.40 (Government Functioning) | 4.31 (Overall)** 5.36 (Government Functioning) | To be updated at the time of the AR
Achieved
Sources: Economist Intelligence Unit (EIU) Democracy Index (https://www.eiu.com/topic/democracy-index)
| Impact Indicator 2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25)
| Performance against Multidimensional Poverty Index (MPI) | Planned | Punjab, KP, National | Existing Baseline* Punjab: 0.152 KP: 0.250 National: 0.197 | Data not available | UNDP plans launching the new MPI report soon (based on 2018-19 PSLM data). Figures would be added, when available. These would become a baseline for setting year 4 milestone as PSLM data is collected once in two years. | Punjab: 0.123 KP: 0.258 National: 0.198 | To be updated at the time of the AR
Achieved
Sources: *UNDP MPI Score (derived from the PBS 2014-15 PSLM data and published in 2017) https://www.undp.org/content/dam/pakistan/docs/MPI/MPI%204pager.pdf Year 3 MPI score derived from PBS DHS 2017-18 **EIU Democracy Index, February 2022
OUTCOME | Outcome Indicator 1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | Assumptions
Improved provision of basic services, and strengthened perception of government performance | Local government spending | Planned | Punjab | PKR 345.5 billion (2018-19) | N/A | DDMAs established in three pilot districts and comprehensive contingency plans developed in consultation with district line departments and community representatives’ | 18% increase in local government spending in real terms over the baseline. | X% increase in local government spending in real terms over the baseline. To be updated at the time of the AR |  |  |  |  | • Government continues to make committed funds available and releases them for LG service delivery according to the agreed PFC Award/formula • LG representatives agree with new LG subordinate legislation • Data timely available from UNDP perception surveys
Achieved
|  | Planned | KP | PKR 199 billion (2018-19) | N/A | N/A | 09% increase in local government spending in real terms over the baseline | X% increase in local government spending in real terms over the baseline. To be updated at the time of the AR
Achieved
Sources: Finance and LG Departments of Punjab and KP
| Outcome Indicator 2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25)
| Citizen satisfaction with basic services | Planned | Punjab | UNDP perception survey (2021) | N/A | N/A | satisfaction rates: Public School: 96% Public Health Facility: 93% Sanitation Services: 68% | X% increase in citizen satisfaction with basic services against 2021 baseline. To be updated at the time of the AR | Two (02) Thematic Reviews and Results Verification undertaken to generate evidence on the effectiveness of SNG-II initiatives and verification of short to medium term results to inform endline evaluation of SNG-II Programme’
Achieved
|  | Planned | KP | UNDP perception survey (2021) | N/A | N/A | satisfaction rates: Public School: 95% Public Health Facility: 92% Sanitation Services: 79% | X% increase in citizen satisfaction with basic services. To be updated at the time of the AR
Achieved
Sources: UNDP perception surveys
The endline wave of perception survey substantially captured the change in citizen satisfaction and impact of SNG-II work for provision of improved services in social sectors of Water and Sanitation, Health, Education. Instead of undertaking another survey, thematic revies and results verification will be conducted. This will generate new evidence on the effectiveness and uptake of technical assistance and sustainability of various reform initiatives undertaken during the SNG-II programme in KP and Punjab. Short to medium term results and outcomes of specific reform initiatives will be verified to inform endline evaluation of the programme.
| Outcome Indicator 3 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | Assumptions
| Aggregate expenditure outturn | Planned | Punjab | 89% of approved original budget of FY 2018-19 | 87% of approved original budget of FY 2019-20 | 96% of approved original budget of FY 2020-21 | 99% of approved original budget of FY 2021-22 | 94% of approved original budget of FY 2022-23 | X% of approved original budget of FY 2023-24 | X% of approved original budget of FY 2024-25 |  | X% of approved original budget of FY 2025-26 | • Government continues to remain committed to revenue and fiscal efficiency reforms. • There is political stability and the governments remains committed to budget discipline and expnediture efficiency • Government remains accessible and amenable to reform suggestions.
Achieved
|  | Planned | KP | 84% of approved original budget of FY 2018-19 | 74% of approved original budget of FY 2019-20 | 88% of approved original budget of FY 2020-21 | 96% of approved original budget of FY 2021-22 | 84% of approved original budget of FY 2022-23 | 80% of approved original budget of FY 2023-24 | X% of approved original budget of FY 2024-25
Achieved
Sources: PEFA Assessments; Government fiscal data of KP and Punjab
| Outcome Indicator 4 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25)
| Additional Fisal Space (additional revenue and expenditure savings combined) in UK£ million (absolute) | Planned | Punjab | UK£ 0 million | N/A | N/A | UK£29.3 million | UK£130 million (cummulative) | UK£1,078 million (cummulative) | UK£X million (cummulative) |  | UK£485 million (cummulative)
Achieved
|  | Planned | KP | UK£ 0 million | N/A | N/A | UK£187.7 million (cummulative) | UK£461.1 million (cummulative) | UK£476 million (cummulative) | UK£X million (cummulative) |  | UK£470 million (cummulative)
Achieved
Sources: Government budget and fiscal data
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 1 IMPACT WEIGHTING (30%) | Output Indicator 1.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | Assumptions
PFM systems are strengthened for effective planning and budgeting | Provincial planning capability | Planned | Punjab | All 8 institutions (out of 15) identified by the government as high priority have a Public Investment Management Assessment (PIMA) rating of ‘medium’ or ‘low’ depicting weak planning capabilities at the provincial level Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | ADP guidelines ensuring institutionalisation of consultative process issued/notified and consultative process initiated in 2 departments Organisational structure and job descriptions of PPP Authority notified Framework for the prioritisation of ADP projects for mid-year review developed and approved by the P&D (to be used for the review of ADP 2019-20) Planning guidelines for LGs developed and endorsed by LG-RWG and draft planning manual developed Design of the inspectorate of Inspections and Monitoring developed and endorsed by LG-RWG LG transition related rules developed and endorsed by LG-RWG (at least 3) | ADP formulation process strengthened through adoption of mid-year ADP review framework and participatory sectoral planning Planning Reform Strategy (PRS) – focused on strengthening institutional design and effective planning – developed and endorsed by the P&D-RWG 50 new local government officials in pilot districts trained on planning, budgeting and monitoring process for LGs An end-to-end service delivery pilot initiated (service identified, provincial buy-in secured, need assessment undertaken) | At least 2 PIMA institutions (reform areas) identified by the government as high priority have a PIMA rating of ‘medium’ to ‘high’ End-to-end service delivery pilot rolled out in at least 1 LG in a pilot district | PIMA rating of one reform area further improved End-to-end service delivery pilot delivered in 2 LGs, and lessons shared for wider uptake | P&DB has moderate in-house capacity to conduct project appraisal and risk assessment | PIMA rating for 'effectiveness' of Project Appraisal and Risk Assessment improved. |  | PIMA rating of 3 reform areas (cumulative) sustained | • Planning reforms remain high on government agenda • Change in the P&D leadership does not affect planning reform priorities • Government makes necessary resources available, including the needed staffing
Achieved
|  | Planned | KP | Low planning capabilities in key government institutions – project formulation is deficient owing to the lack of development of complete and robust proposals & PC-1s (WB Report 2017) Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | Draft analytical review of the ADP completed for the priority sectors ToRs agreed and at least 4 departments identified for the assessment of planning capabilities Key recommendations of the LG study and gap analysis approved by the LG-RWG | Analytical review of ADP finalised, and recommendations approved for implementation (actions initiated on 4 out of 7 key recommendations) Assessment completed for 6 departments and recommendations presented to the P&D for action Local government performance Scorecard developed and approved by the LG Department for piloting in select LGs An end-to-end service delivery pilot initiated (service identified, provincial buy-in secured, need assessment undertaken) | Agreed recommendations of planning capability assessment implemented in 2 departments and PC-1 quality criteria developed Performance Scorecard tracking initiated in 4 LGs on PFM and planning regulations Two end-to-end service delivery pilots (cumulative) rolled out in at least 2 LGs in pilot districts | Effectiveness of strategic mandate of 2 Planning Cells internally assessed, and the planning capability reforms rolled out to 4 departmental Planning Cells Lessons learnt from 02 end-to-end service delivery pilots shared with provincial government and other LG for wider uptake. | Planning capabilities improved in P&D and 4 departmental planning cells; planning reforms rolled out to12 departments.(cumulative) | Project Appraisal and Risk assessment standards developed and assessment initiated based on these standards |  | Planning and monitoring function are better integrated leading to improved quality projects in 12 planning cells. |  | Programme Target revised. Additions in blue text. 3 end-to-end service delivery pilots would be delivered in year 4. programme will directly deliver 2 pilots and its replication in one additional LG will make a total of 3.
Achieved
Sources: PIMA assessment 2020; Government notifications & minutes; PRS document; ADP analysis reports; Sector strategies & plans; RISE & PGS documents; Analytical reports on the use of ADP prioritization framework; P&D capability meta-analysis report; World Bank report 2017; Planning capability assessment 2020; LG engagement strategy/assessment report; KP institutional assessment report 2018; LG departmental reviews; LG performance Scorecard; LG administrative data; LDP monitoring reports
| Output Indicator 1.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Year 7 Milestone (March 2025) | Programme Target (2019-25) | • Government’s appetite for reform exists • Formal authorising environment improves • Political environment remains stable • The WB and UNDP can commission the assessments promptly, ensuring that the results are available before the end of the relevant evaluation period.
| Provincial budget preparation capability | Planned | Punjab | Pillar 4 of PEFA – 12 out of 18 dimensions with a rating of C or D (6 each) demonstrating weak policy-based fiscal strategy | PFM Reform Strategy (PFMRS) developed and approved by the Finance Minister and first donor coordination meeting held Rules developed for Punjab Local Government Finance Commission (PLGFC) and approved by the Finance Department | PFMRS published with inclusion of disaster risk financing and evidence generated of its use in the design of World Bank PRIDE programme Budget call circular for 2020-21 issued with inclusion of aggregate budget ceilings (PEFA dimension 17.2) Interim need-based transparent and equitable formula for transfer of resources to local governments developed and approved by PLGFC | Joint P&D and FD budget proposal review process adopted in Primary Health and Primary Education | Budget better aligned in 04 provincial departments through joint P&D and FD reviews | Joint P&DB and FD reviews institutionalised for better budget alignment | Assessment initiated on the joint budget review process and its impact on service provision | Assessment completed on the joint budget review process and its impact on service provision | Select interventions under the PFM Reform Strategy implemented resulting in improved PEFA rating in agreed/relevant areas |  | dimensions included in the definition sheet
Achieved
|  | Planned | KP | Pillar 4 of PEFA - 8 out of 18 dimensions with a rating of C or D (3 and 5, respectively) | Budget ceilings developed and issued for recurrent and development budgets for enhanced integration and linkages (PEFA dimension 16.2) Essential PFM related subsidiary rules identified and agreed with the LG Department LG Fiscal transfer rules development in accordance with amended LGA | Integrated and strategic budgeting in the Finance Department, and at least 2 departments based on SAP system (PEFA dimension 16.2) Essential PFM rules developed and endorsed by RWG in accordance with the LGA amendment Needs based transparent PFC Award developed based on 2017 census data with analysis, details and guidelines for KP (and NMDs) | Joint Priority Committee (JPC) review of development and recurrent budget proposals for improved alignment, in 6 key departments | Budgets better aligned through review of development and recurrent budget proposal by JPC in 4 provincial departments | PFM Act implementation roadmap developed and tracking initiated | Assessment initiated on the joint budget review process and its impact on service provision | Assessment completed on the joint budget review process and its impact on service provision | Select initiatives under the PFM law/strategy implemented resulting in improved PEFA ratings in agreed areas |  | Dimensions added in the definition sheet
Achieved
Sources: Punjab & KP PEFA reports; SNG PEFA relevant assessments; Government budget documents; Notifications & letters; Budget analysis of LGs; PFC formula; PFC reports; Government meeting minutes & letters; Mini evaluation report on budget reforms
| Output Indicator 1.3 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | • Government commits to the fund release policy during the budget implementation irrespective of political patronage • There is macroeconomic stability throughout the year (no external shocks to the economy) • All administrative departments agree to prepare evidence-based cash plans • Ownership of planning and budgeting reforms in central and line departments • The WB can commission PEFA assessmnt promptly, ensuring that the results are available before the end of the relevant assessment period.
| Provincial budget execution capability | Planned | Punjab | Absence of cash plans and fund release policy | Fiscal Monitoring Committee notified to monitor utilisation of the provincial budget, and first meeting held | Cash plans of the provincial government for FY2020-21 developed and reviewed quarterly Funds Release Policy for FY2020-21 developed based on cash plans of FY2020-21 and endorsed by FD-RWG | Mid-year and end-year budget execution reports developed | Budget execution reports developed and reviews conducted by the Finance Department in line with government priorities | Budget execution review process institutionalised and legal framework for downstream budget execution strengthened | Budget execution reviews at departmental level strengthened for improved service delivery |  | Improved PEFA ratings in agreed areas relevant to budget execution |  | added in the definition sheet
Achieved
|  | Planned | KP | Absence of year-end budget execution reporting, weak cash management and forecasting mechanisms | Gap analysis of KP PFM system conducted and first draft of PFM Law submitted to the Finance Department | PFM Law finalised and submitted to the Finance Department for promulgation Cash management policy and TSA framework developed and shared with the Finance Department | Mid-year and end-year budget execution reports developed Downstream budget execution reforms under implementation in 2 line departments | Budget execution review conducted of actual releases against the Fund Release Policy Downstream budget execution reforms implemented in 2 line departments | Annual Performance monitoring mechanism initiated for three departments (Cumulative Target) | Budget execution reviews at departmental level strengthened for improved service delivery |  | Improved PEFA ratings in agreed areas relevant to budget execution. |  | Definition sheet is updated accordingly. The team suggest to keep the no of depts to 2. as it will fit well with the overall trajectory of targets. However, there is room to identify that some of the key downstream reforms are still to be institutionalise and out of 2 departments these are mature in one and at a initial stage in other.
Achieved
Sources: Notified release policy & cash plans of government; PEFA internal assessments; Government notifications; Meetings minutes; Cash management policy; Funds release policy; KP PFM Law
| Output Indicator 1.4 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | • Select provincial and local governments are willing to meaningfully engage citizens • Select provincial and local governments are responsive to citizen needs and demands
| Citizen engagement in planning and budgeting | Planned | Punjab & KP | No guidelines for citizen engagement in place in provinces Punjab: PI-5 of PEFA Assessment 2019 is scored C (depicting weaknesses in disclosure of financial information in budget documents) KP: PI-9 of PEFA Assessment 2017 is scored C (public access to fiscal information) | Citizen engagement guidelines developed and notified Plan for improvement in PI-5 of PEFA (budget transparency) developed and agreed with the Finance Department | Mechanisms for inclusive planning agreed with the provincial government 90 LG staff trained on citizen engagement in pilot local governments ToT module developed for citizen engagement, and handed over to AAWAZ for further roll out Information on contingent liabilities published in the budget documents Mid-year budget execution report developed and shared with the Finance Department | A&I recommendations under implementation in at least 1 provincial department in Punjab and A&I review of the planning processes in 2 departments in KP | Evidence of consideration of citizen needs in planning and budgeting of 2 government departments | No milestone for the year | No milestone for the year |  | Evidence of consideration of citizen needs in planning and budgeting in 04 provincial departments and 3 Local Governments
Sources: LG citizen engagement guidelines; Notification & circulation letters of citizen engagement guidelines; Orientation session reports with CSOs & MPAs; Summary analysis of budget documents vis-à-vis citizen needs and gender; Joint reporting framework; Sector strategies for inclusive planning; Inclusion assessment reports (for provincial governments); Stakeholder consultation reports
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 IMPACT WEIGHTING (20%) | Output Indicator 2.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | Assumptions
Institutions are better organised to deliver | Institutional capacity to deliver; including social protection, climate change etc. | Planned | Punjab | Weak institutional capacity (critical shock responsive systems) to manage the impact of Covid | Agenda on social protection agreed with the government | Strategy for enrolment of informal/laid off workers developed and options for their registration and employment approved for implementation Provincial social protection policy developed and presented to the government | Provincial government establishes at least two systems (out of the six systems proposed in the RISE Strategy / SP Policy) to achieve post-Covid recovery | Provincial government implements 4 initiatives (out of 6 initiatives proposed in the RISE Strategy / SP Policy) to achieve post-Covid recovery. | PSPA has strengthened institutional capacity to deliver social protection Punjab has a provincial green financing strategy | Government of Punjab has strengthened institutional capacity to deliver social protection Implementation of Green financing strategy initiated |  | Government of Punjab has strengthened institutional capacity to deliver social protection Institutional arrangements for the implementation of Green financing strategy in place | • Fiscal resources are available to implement social protection initiatives • Provincial Cabinet (and its relevant sub-committee) timely convenes to approve the provincial social protection policy | already in the definition sheet
Achieved
|  | Planned | KP | Weak institutional capacity (critical shock responsive systems) to manage the impact of Covid | N/A | Roadmap for instituting a post-Covid recovery approved and launched by the government | Social Protection Policy finalised and shared with government Social Protection Roadmap implementation tracked | N/A | Assessment of local level flood response completed; results disseminated for uptake and implementation initiated Governance mechanism for Social Protection service delivery in KP developed | Institutional arrangements for integrating and coordinating social protection in place |  | Policy and institutional arrangements for social protection in place
Achieved
Sources: Provincial socio-economic registry; Social protection concept papers; PSPA annual progress; ADP analysis; Labour department data; BISP/NSER data; KP social protection Roadmap; PC-1s; Donor reports; Government meeting minutes
|  | Planned | Sindh | Weak risk governance arrangements in key government institutions-interdepartmental coordination is deficient owing to the lack of mechanisms and frameworks. Weak institutional basis for disaster preparedness at provincial and district level (undelineated roles, absence of contingency planning and implementation, no budget allocations for disaster preparedness) | N/A | N/A | N/A | N/A | Gap analysis of existing provincial and district level governance arrangements completed SOPs developed for improved coordination between PND, PDMA and line departments” Centralized dashboard developed to establish linkages between different administrative tiers and departments for informed decision making DDMAs established in three pilot districts and comprehensive contingency plans developed in consultation with district line departments and community representatives |  | Institutional frameworks developed for PDMA's DRR Wing and District DRM units in 3 pilot distrricts DMIS updated to capture contingency plans for 3 districts Capacity building sessions held on DMIS for officials of PDMA and line departments at the district levels Exit strategy developed for handover of RGF work to the government
Achieved
| Output Indicator 2.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Year 7 Milestone (March 2026) | Programme Target (2019-25)
| Institutionalization of performance management system in Federal government for improved performance | Planned | National | Zero | N/A | N/A | 41 Performance Contracts signed between the Prime Minister and Federal Ministries | Evaluation of performance agreements initiative conducted, learnings documented and disseminated; Toolkit on performance agreements developed and shared with Planning Ministry and PMO; Strategic Roadmap for critical policy areas, including energy and economy, launched in PMO | Stocktakes and follow up meetings held for focused implementation of priority areas identified under the government's economic revival plan. |  | PM Office workstream transitioned to National Governance Programme (Output 3 of NGP Log frame) in agreement with FCDO | Effective performance management system implemented and evaluated at Federal government level
Achieved
Sources: Government meeting minutes, Government notifications, PM Office generated progress reports, Performance Agreement Toolkit
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 3 IMPACT WEIGHTING (25%) | Output Indicator 3.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | Assumptions
Fiscal capacity is strengthened to enhance revenue and expenditure efficiency | Own source revenue capacity | Planned | Punjab | No systematic reform initiatives in place for collecting additional revenues | Revenue mobilisation plan developed and endorsed by the E&T-RWG | Implementation initiated on 2 out of the 6 initiatives supported by SNG with evidence of progress on the implementation | 4 out of the 6 initiatives supported by SNG implemented and evaluated with evidence of contribution to increase in fiscal space | 05 out of 06 initiatives supported by SNG delivered, and 2 of them internally assessed. | Punjab has improved capacity to mobilise own-source tax revenue | Revenue mobilisation strategy implementation progress tracked |  | Punjab has an improved capacity for own source tax revenue mobilisation | • Provincial governments willing to adopt revenue mobilisation efforts • Provincial governments develop their capacities to conduct periodic system-based tax audits • No exogenous shocks impacting revenue realisation (including prolonged impacts of Covid) | added in the definition sheet
Achieved
|  | Planned | KP | No systematic reform initiatives in place for collecting additional revenues | Potential areas for revenue mobilisation identified and approved by the E&T Department | Revenue mobilisation plan agreed with the E&T Department and under implementation – 2 (out of 8) initiatives of the Plan under implementation | 5 (out of 8) initiatives of the revenue mobilisation plan supported by SNG under implementation | 7 out of 8 initiatives of E&T revenue mobilisation plan delivered and at least 2 of them internally assessed. | Options for an Ad-valorem UIPT regime developed and considered by the Taskforce | Strategic Plan to transition to Ad valorem UIPT developed and endorsed by the Task force |  | KP has an improved capacity to mobilise own- source tax revenue |  | Definition sheet include the list of 7 initiatives of E&T plan. In KP the focus was on E&T. we have now added 2 for LGs.
Achieved
Sources: Provincial government budgeting & financial management data; Revenue mobilisation plans; Government meeting minutes & letters; Summary analysis on SNG’s contribution to increase fiscal space
| Output Indicator 3.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | • Provincial governments able to priorities initiatives targeted at efficiency savings • Provincial governments approve relevant legal/regulatory frameworks
| Capacity to ensure expenditure efficiency | Planned | Punjab | Inefficient budgetary expenditures (no budget rationalisation/ pension review conducted in the past) | Plans for efficiency savings agreed with the Finance Department | Implementation initiated on 2 out of the 5 initiatives supported by SNG with evidence of progress on the implementation | 3 out of the 5 initiatives supported by SNG implemented with evidence of contribution to efficiency savings | 4 out of 5 initiatives supported by SNG delivered, and internal review conducted for at least 2 completed initiatives. | Regulatory framework for implementation of DC Pension scheme developed | Implementation of DC Pension scheme is at an advanced stage |  | Punjab has an improved capacity to ensure expenditure efficiency |  | The 2 to be internally assessed are from the 4 to be delivered. While the four are specified in the definition sheet the 2 to be assessed are yet to be finalised.
Achieved
|  | Planned | KP | Inefficient budget expenditures (no budget rationalisation; salary and pension audit conducted during the recent past) | Plans for efficiency savings agreed with the Finance Department | Implementation of the agreed efficiency savings plan – 2 out of 6 interventions implemented | Implementation of the agreed efficiency savings plan – 4 out of 6 interventions implemented | 05 out of 06 interventions under the agreed efficiency savings plan delivered, 2 internally assessed. | Fiscal risk framework developed and first annual fiscal risk statement prepared | Development of Fiscal Risk Framework and Fiscal Risk Statement institutionalised |  | KP has an improved capacity to ensure expenditure efficiency |  | list of 5 is specified in the definition sheet. The 2 for assessment are also proposed with subject to FCDO agreement.
Achieved
Sources: Provincial government financial management & budgeting data; Budget & expenditure data analysis; Policy reviews; Government letters & meeting minutes; Government efficiency saving plans
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output x (discontinued from year 5) IMPACT WEIGHTING (15%) | Output Indicator 4.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | Assumptions
Innovative approaches developed and piloted | Number of AR projects implemented and evaluated | Planned | Punjab & KP | N/A | Ideas for AR identified and approved by the relevant RWGs 2 AR studies commissioned | 6 AR studies completed, and findings approved by the relevant RWGs | X AR studies completed, and recommendations taken up for consideration by the relevant RWGs (cumulative) | N/A | Completed and closed | Completed and closed |  | Recommendations from X AR studies taken up for consideration by the relevant RWGs | • Government receptive to AR results
Achieved
Sources: PSC/RWGs minutes; Learning papers & products; Action research reports
| Output Indicator 4.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) |  | Programme Target (2019-25) | • Quality proposals received based on relevant thematic areas • Government open to adopting innovation reforms
| Number of ICF pilots implemented and evaluated | Planned | Punjab & KP | N/A | 1st Round of ICF launched 4 ideas for Partnership Opportunities Fund (POF) identified and approved by the relevant RWGs | 8 innovative pilots (ICF and POF) approved by the PSC commissioned | 15 innovative pilots (ICF and POF) approved by the PSC commissioned (cumulative) | Innovation Challenge Fund (ICF) process reviewed, learnings documented and disseminated. | Completed and closed | Completed and closed |  | At least 4 completed innovative pilots internally assessed, learnings documented and disseminated
Achieved
Sources: PSC/RWGs minutes; Evaluation reports; Case studies; M&E reports of pilots
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 4 (new output added from year 5) IMPACT WEIGHTING (25%) | Output Indicator 4.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Year 7 Milestone (March 2026) | Programme Target (2019-25) | Assumptions
Local level governance is improved | Local governance and PFM systems | Planned | Punjab | Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | N/A | N/A | N/A | N/A | Modern PIFRA accounting system introduced at the local government level | Local OSR pilots rolled out in 6 districts | Data driven stocktakes conducted at district level to problem solve and optimize OSR Local Government Financial Management Information System (LGFMIS) integrated with the SAP-IFMIS | SNG supported reforms taken up by local governments | • Government's commitment to LG reforms remains strong • There is clarity among stakeholders on the governing local government law
|  |  | KP | Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | N/A | N/A | N/A | N/A | LUBC committees operationalised in two districts. | LUBC committees operationalised in 6 out of 7 SNG districts (cumulative) and its oversight by Land Use Authority strengthened. |  | The Land Use Building Control Authority (LUBCA) established and ensuring compliance with relevant regulations
Achieved
Sources: PSC/RWG meeting minutes; LG reforms lessons learning report; LF financial reporting and budget analysis report; IFMIS/SAP data; government/LG meeting minutes; progress review and internal assessment reports PSC/RWGs minutes; Learning papers & products; Action research reports
| Output Indicator 4.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Year 7 Milestone (March 2026) | Programme Target (2019-25) | • Partner local governments are receptive to SNG approach • Lessons from the pilot are disseminated in time and engagement with stakeholders effectively managed • UNDP can commission the evaluation promptly, ensuring that the results are available before the end of the relevant evaluation period.
| Local level service delivery | Planned | Punjab | Absence of systematic approach to local service delivery | N/A | N/A | N/A | N/A | End-to-end service delivery management approach replicated in 2 additional LGs | Evaluation framework developed to assess the end-to-end service delivery pilot and its impact on service delivery | Evaluation to assess the end-to-end service delivery pilot and its impact on service delivery completed Workshop on dissemination of evaluation findings | End-to-end service delivery pilots evaluated with evidence of impact on service delivery and the management approach endorsed by the provincial Local Govt Department for wider adoption.
|  |  | KP | Absence of systematic approach to local service delivery | N/A | N/A | N/A | N/A | End-to-end service delivery management approach replicated in one additional LG | Evaluation framework developed to assess the end-to-end service delivery pilot and its impact on service delivery | Evaluation to assess the end-to-end service delivery pilot and its impact on service delivery completed Workshop on dissemination of evaluation findings | End-to-end service delivery pilots evaluated with evidence of impact on service delivery and the management approach endorsed by the provincial Local Govt Department for wider adoption
Achieved
Sources: LG engagement strategy; SWM assessment reports/briefs; citizen perception survey; LG-RWG meeting minutes; LG reform lessons learning report; LG financial data
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note: The Business Case has been extended to 2026 to allow for the completion of activities which could not be completed due to COVID and ODA pauses/ uncertainty. The logframe will be extended by two years and will have new milestones to measure progress towards the completion of the final programme targets after the 2023 AR. The current version incorporates new activities as part of the two pivots (COVID and floods).

## Change Frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Outcome Indicator 3 | new indicator added | Amala Najeeb | 2024-11-04
2 | Outcome Indicator 4 | new indicator added | Amala Najeeb | 2024-11-04
3 | Output 1, Indictor 1.2 | The milestone has been revised due to delay in the procurement of evaluation firm. The onboarding on MEL firm is in process and should be finalised by february 2025. This milestones will be readded to Y7 log-frame. | Amala Najeeb | 2024-11-04
4 | Output 4. Indicator 4.2 | The milestone has been revised due to delay in the procurement of evaluation firm. The onboarding on MEL firm is in process and should be finalised by february 2025. This milestones will be readded to Y7 log-frame. | Amala Najeeb | 2024-11-04
5
6
7
8
9
10
11
12

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Pb - definition sheet
|  | Definition | MOVs/Evidence
Output 1 | PFM systems are strengthened for effective planning and budgeting
Indicator 1.1 | Provincial planning capability
Milestone March 2025 | PIMA rating for 'effectiveness' of Project Appraisal and Risk Assessment improved. | PIMA conducted as part of the Punjab Planning Reform Strategy (PRS) assigns medium score to Project Appraisal both for 'institutional design' and 'effectiveness', with score for sub-criteria on 'risk assessment' being low on both dimensions. Improvement in the effectiveness would mean: (a) PIMA score for the risk assessment sub-criteria is improved. (b) Overall rating for effectiveness of Project Appraisal Improved. | PIMA Assessment
Indicator 1.2 | Provincial budget preparation capability
Milestone March 2025 | Assessment initiated on the joint budget review process and its impact on service provision | This will include: • Finalisation of the scope of work or ToRs. • Approach and methodology agreed including a stakeholder engagement plan • All relevant data and evidence sources identified and made available to the evaluation team | ToRs, methodology document, data/evidence sheet
Indicator 1.3 | Provincial budget execution capability
Milestone March 2025 | Budget execution reviews at departmental level strengthened for improved service delivery | (a) Budget execution reviews through fiscal discipline committee continue and engage relevant departments. (b) There is evidence of course correction resulting from the reviews; and, (c) All relevant rules related to budget execution drafted and endorsed by FD for approval. | Budget execution reports/draft rules and endorsement from FD of the rules
Output 2 | Institutions are better organised to deliver
Indicator 2.1 | Institutional capacity to deliver; including social protection, climate change and DRM etc.
Milestone March 2025 | Government of Punjab has strengthened institutional capacity to deliver social protection | Strengthened institutional capacity means: (a) PSPA reforms/initiatives institutionalised. These include: (i) Bahimmat Buzurg/Elderly Pension Programme (ii) Nayee Zindagee/Acid Burn Victim Rehabilitation Programme (iii) First Phase of PSER (system design and pilot registration process) (iv) M&E system (b) wider government reforms in SP domain implemented. These inlcude: (i) workers' repository and job centres under labour department (ii) Conceptual framework for provincial social protection. (c) New reforms initaited and under implementation. These inlcude: (i) MOU for federal-provincial data sharing on poverty and economic status of hoouseholds in Punjab (ii) Phase-II of the Punjab Socio-economic registry and (iii) Design of an integrated welfare project for persons with disabilities | Progress tracking of initiatives alreay implemented at PSPA, design documents for new initiatives, Final MOU document
Milestone March 2025 | Implementation of Green financing strategy initiated | Implementation initiated means (a) a dedicated climate finance unit established (b) at least one project proposal prepared for the government focused on accessing climate/green finance submitted to accredited agencies for approval. | Design of Climate Finance Unit, implementation progress reporting, Project concept/proposal document
Output 3 | Fiscal capacity is strengthened to enhance revenue and expenditure efficiency
Indicator 3.1 | Own source revenue capacity
Milestone March 2025 | Revenue mobilisation strategy implementation progress tracked | Tracking of RMS implementation will include: (a) status of businsess plans by tax collecting agencies/departments (b) scale up and replication of the SNG-delivered pilots (c) uptake of RMS recommendations in budget proposals (d) adoption and institutionalisation of key policy and administrative reform recommendations of RMS (f) audit and enforcment processes for Sales Tax on Services (g) changes to legal framework for regulation of excise duty, UIPT and Sales Tax on Services | Progress tracking using an SNG developed predefined template.
Indicator 3.2 | Capacity to ensure expenditure efficiency
Milestone March 2025 | Implementation of DC Pension scheme is at an advanced stage | Advanced stage means at least 5 out of 8 SNG- supported actions under the DC scheme are delivered and under implementation. These include: (1) Drafting and finalising the Pension Scheme Rules (2) Amending the Punjab Pension Fund (PPF) Rules, 2007 for withdrawal of profits to support employer contributions (3) Engaging with SECP for amendments in VPS Rules to support employer Pension Funds (4) Drafting and negotiating Standard Agreement with SECP-registered Pension Fund Managers for DC Pension Scheme management (5) developing processes for automated transfer of contributions to Pension Fund Accounts (6) formalising cooperation agreement / MOU with MUFAP (7) developing a monitoring and oversight mechansim for DC Pension Scheme (8) developing a communication strategy for the DC Pension Scheme | Implementation/progress tracking
Output 4 | Local level governance is improved
Indicator 4.1 | Local governance and PFM systems
Milestone March 2025 | Local OSR pilots rolled out in 6 districts | Local OSR pilots rolled out means: (a) analysis conducted of LG receipts/financial data (b) OSR roadmaps developed for six districts (one LG each) and targets discussed and agreed (c) Roadmaps are under implementation with regular stocktakes being conducted | Budget/receipt analysis, OSR roadmaps/presentation, stocktake notes/reports
Indicator 4.2 | Local level service delivery
Milestone March 2025 | Evaluation framework developed to assess the end-to-end service delivery pilot and its impact on service delivery | The evaluation framework will include: • The overall approach to evaluation discussed and agreed • Indicative tools developed including Interview Guides; Survey Instruments; FGD Guides • Timelines for implementation of the evaluation agreed | Evaluation framework, Interview and FGD guides, Survey Instruments
Milestone March 2026 | Evaluation to assess the end-to-end service delivery pilot and its impact on service delivery completed | Endline evaluation of SNG-II Programme implemented by OPM, conducted by MEL firm | Evaluation Report
Milestone June 2026 | Workshop on dessimination of evaluation findings | Dissemination workshop conducted to share findings of the SNG-II endline evaluation with key stakeholders, ensuring ownership and uptake of recommendations | Workshop Concept note & Workshop Report

## KP - definition sheet
| Milestone (March 2025) | Definition | MOVs/Evidence
Output 1 | PFM systems are strengthened for effective planning and budgeting
Indicator 1.1 | Provincial planning capability
| Project appraisal and risk assessment standards developed and assessment initiated based on these standards | The embedded support team will work on the developemnt of risk assessment standards and an assessment of select PC-Is will be condcted using these standards. | Risk Assement standards; PC-Is assessment report based on these standrads; embedded team progress reports
Indicator 1.2 | Provincial budget preparation capability
| Assessment initiated on the joint budget review process and its impact on service provision | This will include: • Finalisation of the scope of work or ToRs. • Approach and methodology agreed including a stakeholder engagement plan • All relevant data and evidence sources identified and made available to the evaluation team | ToRs, methodology document, data/evidence sheet
Indicator 1.3 | Provincial budget execution capability
| Budget execution reviews at departmental level strengthened for improved service delivery | The word 'Strengthened' refers to the performance reporting and in year course correction made by the 3 pilot departments and roll out of the reform to all departments in line with the PFM Act 2022. As part of the exit strategy, the team will also carry out an assessment in Health Department, where the reform was piloted. | Performance Monitoring Report for 3 departments, Performance Monitoring reporting Framework for other departments
Output 2 | Institutions are better organized to deliver
Indicator 2.1 | Institutional capacity to deliver; including social protection, climate change
| Institutional arrangements for integration and coordination of social protection in place | Institutional arrangements' refers to an approved SP Policy that support and inform the designing of single entity for coordinating all SP inetrventions in the province. | SP Policy, HR structure for the single entity, Amended RoBs
Output 3 | Fiscal capacity is strengthened to enhance revenue and expenditure efficiency
Indicator 3.1 | Own source revenue capacity
| Strategic Plan to transition to Ad valorem UIPT developed and endorsed by the Task force | The word "endorcement" refers to govt commitment to move towards ad valorem UIPT and the transition plan is approved for implemantion. | Transition Plan, Government Meeting Minutes, Options paper on UIPT reforms
Indicator 3.2 | Capacity to ensure expenditure efficiency
| Development of Fiscal Risk Framework and Fiscal Risk Statement institutionalised | The word 'institutionalised' refers to the endorsement and publication of the Fiscal Risk Statement by the Finance Department in line with the PFM Act 2022. | Fiscal Risk Framework and Statement of Fiscal Risk
Output 4 | Local level governance is improved
Indicator 4.1 | Local governance and PFM systems
| LUBC committees operationalised in 6 out of 7 SNG districts (cumulative). and its oversight by Land Use Authority strengthened. | The word "Strengthened" referes to improved operationalisation of LUBC Authority i.e. HR structure in place; new Master Plans/land use plans approved ; and convening of Land Use Council. Land Use and Building Control district committees will be operationalised in a total of 6 districts in SNG's ambit (Central + North) which includes 2 district from the North Cluster and 4 districts from the Central Cluster. The word 'operationalized' refers to committees notified, regular meetings held and corrective measures being taken. | Notifications, Meeting Minutes of Land Use Committees
Indicator 4.2 | Local level service delivery
2025-03-01 | Evaluation framework developed to assess the end-to-end service delivery pilot and its impact on service delivery | The evaluation framework will include: • The overall approach to evaluation discussed and agreed • Indicative tools developed including Interview Guides; Survey Instruments; FGD Guides • Timelines for implementation of the evaluation agreed | Evaluation framework, Interview and FGD guides, Survey Instruments
Milestone March 2026 | Evaluation to assess the end-to-end service delivery pilot and its impact on service delivery completed | Endline evaluation of SNG-II Programme implemented by OPM, conducted by MEL firm | Evaluation Report
Milestone June 2026 | Workshop on dessimination of evaluation findings | Dissemination workshop conducted to share findings of the SNG-II endline evaluation with key stakeholders, ensuring ownership and uptake of recommendations | Workshop Concept note & Workshop Report

## RGF definition sheet
| Milestone (March 2026) | Definition | MOVs/Evidence
Output 1 | Institutions are better organized to deliver
Indicator 2.1 | Institutional capacity to deliver; including social protection, climate change etc.
| Institutional frameworks developed for PDMA's DRR Wing and District DRM units in 3 pilot distrricts | Development of institutional frameworks that define the structure, functions, and coordination mechanisms of the PDMA's Disaster Risk Reduction (DRR) Wing and the District Disaster Risk Management Units (DDRMs) in the three pilot districts. It includes drafting organizational structures, staffing plans, functional mandates, SoPs and reporting lines | Institutional framework documents for the DRR Wing and DDRM Units endorsed by PDMA
| DMIS updated to capture contingency plans for 3 districts | Enhancement of the DMIS to include modules and data fields that record, store, and track district-level contingency plans for three pilot districts. | Updated DMIS interface reflecting contingency plan modules for 3 districts
| Capacity building sessions on DMIS held for officials of PDMA and line departments at the district levels | Completion of training sessions aimed at strengthening the capacity of PDMA and relevant line department officials in operating and maintaining the Disaster Management Information System (DMIS). | Training reports
| Exit strategy developed for handover of RGF work to the government of Sindh | Preparation of a structured exit and sustainability plan outlining the process for transitioning the RGF work from UNDP to the Government of Sindh. | Approved Exit Strategy Document

## Sheet1 (hidden)
Outcome | Original description | Revised description
Indicator 1 | Local government spending | No Change
Indicator 2 | Citizen satisfaction with basic services | Generation of evidence base on the effectiveness of SNG-II initiatives and verification of short to medium term results to inform endline evaluation of SNG-II Programme’
Output | Original description | Revised description
Output 1 | Plans and budgets are more evidence-based and executed as planned | PFM systems are strengthened for effective planning and budgeting
IMPACT WEIGHTING | 35% | 30%
Output 1, Indicator 1.1 | Planning capabilities in provincial and local government institutions | Provincial planning capability
Output 1, Indicator 1.2 | Budget preparation process | Provincial budget preparation capability
Output 1, Indicator 1.3 | Budget execution in government | Provincial budget execution capability
Output 1, indicator 1.4 | This indicator was removed, and work related to A&I is now captured in other indicators across Logframe
Output 2 | Institutions are better organised to deliver (with a focus on Covid recovery and climate adaptation) | Institutions are better organised to deliver
IMPACT WEIGHTING | 20% | 20% (No change)
Output 2, Indicator 2.1 | Institutional capacity to plan and deliver post Covid recovery | Institutional capacity to deliver, including social protection, climate change etc.
Output 2, Indicator 2.2 | No longer part of output
Output 3 | Fiscal Space is increased with more resources available for service delivery | Fiscal capacity is strengthened to enhance revenue and expenditure efficiency'
IMPACT WEIGHTING | 30% | 25%
Output 3, Indicator 3.1 | Provincial own source revenue capacity | Own source revenue capacity
Output 3, Indicator 3.2 | Efficiency savings in government expenditure | Capacity to ensure expenditure efficiency
Output 4 | Innovative approaches developed and piloted | Local governance is improved
(Output 4 (new output added from year 5)
IMPACT WEIGHTING | 15% | 25%
Output 4, Indicator 4.1 | New Indicator "Local Governance and PFM systems"
Output 4, Indicator 4.2 | New Indicator "Local level service delivery"