## Logframe
Pakistan SNG-II Logframe | Version: Sep 2025
PROJECT TITLE: Pakistan Sub-National Governance (II)
IMPACT | Impact Indicator 1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022)** | Year 4 Milestone (March 2023)*** | Year 5 Milestone (March 2024)**** | Year 6 Milestone (March 2025) | Programme Target (2019-25)
Strengthened democracy in Pakistan and reduced poverty | Performance against Democracy Index (EIU) | Planned | National | 4.17 (Overall) 5.36 (Government Functioning) (2018 Score) | Data not available | 4.17 (Overall) 5.40 (Government Functioning) | 4.31 (Overall) 5.36 (Government Functioning) | 3.25 (Overall) 4.29 (Government Functioning) | 2.84 (Overall) 4.29 (Government Functioning) | Data not available
Achieved
Sources: Economist Intelligence Unit (EIU) Democracy Index (https://www.eiu.com/topic/democracy-index) **EIU Democracy Index, February 2022 *** (EIU Democracy Index Final Report Published February 2024) ****(EIU Democracy Index Final Report Published March 2025)
| Impact Indicator 2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022)** | Year 4 Milestone (March 2023)*** | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26)
| Performance against Multidimensional Poverty Index (MPI) | Planned | Punjab, KP, National | Existing Baseline* Punjab: 0.152 KP: 0.250 National: 0.197 | Data not available | UNDP plans launching the new MPI report soon (based on 2018-19 PSLM data). Figures would be added, when available. These would become a baseline for setting year 4 milestone as PSLM data is collected once in two years. | Punjab: 0.123 KP: 0.258 National: 0.198 | Punjab: 0.141 KP: 0.236 National: 0.191 | Data not available | Data not available
Achieved
Sources: *UNDP MPI Score (derived from the PBS 2014-15 PSLM data and published in 2017) https://www.undp.org/content/dam/pakistan/docs/MPI/MPI%204pager.pdf **Year 3 MPI score derived from PBS DHS 2017-18 ***PSLM 2019-20, MPI in Pakistan 2019-20, Ministry of Planning, Development & Special Initiatives
OUTCOME | Outcome Indicator 1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | Assumptions
Improved provision of basic services, and strengthened perception of government performance | Local government spending | Planned | Punjab | PKR 345.5 billion (2018-19) | PKR 413 billion | PKR 413 billion | PKR 442 billion | PKR 517 billion | PKR 591 billion | PKR 784 billion | Increased nominal LG expenditure over FY2018-19 baseline by endline; progress assessed against FY2024-25 expenditure and percentage increase over baseline. | • Government continues to make committed funds available and releases them for LG service delivery according to the agreed PFC Award/formula • LG representatives agree with new LG subordinate legislation • Data timely available from UNDP perception surveys
|  | Achieved | [8 empty] | Achieved/exceeded nominal spending benchmark: PKR 784bn in FY2024-25 vs PKR 345bn baseline (+127%). However, real/inflation-adjusted LG expenditure capacity remained broadly unchanged.
|  | Planned | KP | PKR 164billion (2018-19) | PKR 170 billion | PKR 204 billion | PKR 236 billion | PKR 233 billion | PKR 295 billion | PKR 302 billion | Target: Increased nominal LG expenditure over FY2018-19 baseline by endline; progress assessed against FY2024-25 expenditure and percentage increase over baseline.
|  | Achieved | [8 empty] | Achieved/exceeded nominal spending benchmark: PKR 302bn in FY2024-25 vs PKR 164bn baseline (+84%). However, real/inflation-adjusted LG expenditure was 19% below baseline.
Sources: Finance and LG Departments of Punjab and KP
| Outcome Indicator 2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26)
| Citizen satisfaction with basic services | Planned | Punjab | UNDP perception survey (2021) | N/A | N/A | Satisfaction rates: Public School: 96% Public Health Facility: 93% Sanitation Services: 68% | Satisfaction rates: Public School: 97% Public Health Facility: 94% Sanitation Services: 68% | Two (02) Thematic Reviews and Results Verification undertaken to generate evidence on the effectiveness of SNG-II initiatives and verification of short to medium term results to inform endline evaluation of SNG-II Programme’ | NA | Revised target: Evidence generated on effectiveness, uptake and sustainability of SNG-II initiatives, including verification of short- to medium-term results, to inform the endline evaluation.
|  | Achieved | [8 empty] | Partially achieved/indicator approach revised: CPS showed high satisfaction in 2021-23 (schools 96-97%, health 93-94%, sanitation 68-62%), but findings were judged unreliable for assessing progress. Programme therefore stopped reporting on this indicator and used thematic reviews/results verification and the SDPI endline evaluation to strengthen the evidence base.
|  | Planned | KP | UNDP perception survey (2021) | N/A | N/A | Satisfaction rates: Public School: 95% Public Health Facility: 92% Sanitation Services: 79% | Satisfaction rates: Public School: 99% Public Health Facility: 94% Sanitation Services: 96% | Two (02) Thematic Reviews and Results Verification undertaken to generate evidence on the effectiveness of SNG-II initiatives and verification of short to medium term results to inform endline evaluation of SNG-II Programme’ | NA | Revised target: Evidence generated on effectiveness, uptake and sustainability of SNG-II initiatives, including verification of short- to medium-term results, to inform the endline evaluation.
|  | Achieved | [8 empty] | Partially achieved/indicator approach revised: CPS showed high satisfaction in 2021-23 (schools 95-99%, health 92-94%, sanitation 79-96%), but findings were judged unreliable for assessing progress. Programme therefore stopped reporting on this indicator and used thematic reviews/results verification and the SDPI endline evaluation to strengthen the evidence base.
Sources: UNDP perception surveys
The endline wave of perception survey substantially captured the change in citizen satisfaction and impact of SNG-II work for provision of improved services in social sectors of Water and Sanitation, Health, Education. Instead of undertaking another survey, thematic revies and results verification will be conducted. This will generate new evidence on the effectiveness and uptake of technical assistance and sustainability of various reform initiatives undertaken during the SNG-II programme in KP and Punjab. Short to medium term results and outcomes of specific reform initiatives will be verified to inform endline evaluation of the programme.
| Outcome Indicator 3 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025)* | Programme Target (2019-26) | Assumptions
| Aggregate expenditure outturn | Planned | Punjab | 89% of approved original budget of FY 2018-19 | 87% of approved original budget of FY 2019-20 | 96% of approved original budget of FY 2020-21 | 99% of approved original budget of FY 2021-22 | 94% of approved original budget of FY 2022-23 | 81% of approved original budget of FY 2023-24 | 89% of approved original budget of FY 2024-25 | Target/benchmark: Improved budget credibility, assessed through PEFA aggregate expenditure outturn. PEFA A-level benchmark is expenditure outturn between 95% and 105% in at least two of the last three years. | • Government continues to remain committed to revenue and fiscal efficiency reforms. • There is political stability and the governments remains committed to budget discipline and expnediture efficiency • Government remains accessible and amenable to reform suggestions.
|  | Achieved | [8 empty] | Mixed progress: Punjab improved to PEFA A-level performance in FY2021-22 (99%) and FY2022-23 (94%), but fell to 81% in FY2023-24 during the caretaker/election period and recovered to 89% in FY2024-25. Endline performance remained below the A-level benchmark but recovered to baseline level.
|  | Planned | KP | 84% of approved original budget of FY 2018-19 | 74% of approved original budget of FY 2019-20 | 88% of approved original budget of FY 2020-21 | 96% of approved original budget of FY 2021-22 | 84% of approved original budget of FY 2022-23 | 80% of approved original budget of FY 2023-24 | 89% of approved original budget of FY 2024-25 | Target/benchmark: Improved budget credibility, assessed through PEFA aggregate expenditure outturn. PEFA A-level benchmark is expenditure outturn between 95% and 105% in at least two of the last three years.
|  | Achieved | [8 empty] | Mixed progress with endline recovery: KP declined from 84% baseline to 80% in FY2023-24, largely linked to caretaker government and fiscal transfer constraints, but recovered to 89% by FY2024-25. Endline performance remained below the A-level benchmark.
Sources: *PEFA Assessments - Final results awatted; Government fiscal data of KP and Punjab
| Outcome Indicator 4 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26)
| Additional Fisal Space (additional revenue and expenditure savings combined) in UK£ million (absolute) | Planned | Punjab | UK£ 0 million | N/A | N/A | UK£29.3 million | UK£130 million (cummulative) | UK£1,078 million (cummulative) | UK£1,281 million (cummulative) | UK£485 million (cumulative)
|  | Achieved | [8 empty] | Exceeded: Punjab generated UK£1,351m cumulative fiscal space by June 2025 vs UK£485m target (278% of target; +UK£866m). This comprised mainly expenditure savings (£1,231m; 91%) and additional revenues (£120m; 9%).
|  | Planned | KP | UK£ 0 million | N/A | N/A | UK£187.7 million (cummulative) | UK£461.1 million (cummulative) | UK£476 million (cummulative) | UK£616 million (cummulative) | UK£470 million (cumulative)
|  | Achieved | [8 empty] | Exceeded: KP generated UK£616m cumulative fiscal space by June 2025 vs UK£470m target (131% of target; +UK£146m), through a combination of expenditure savings and additional revenues.
Sources: Government budget and fiscal data
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 1 IMPACT WEIGHTING (30%) | Output Indicator 1.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | Assumptions
PFM systems are strengthened for effective planning and budgeting | Provincial planning capability | Planned | Punjab | All 8 institutions (out of 15) identified by the government as high priority have a Public Investment Management Assessment (PIMA) rating of ‘medium’ or ‘low’ depicting weak planning capabilities at the provincial level Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | ADP guidelines ensuring institutionalisation of consultative process issued/notified and consultative process initiated in 2 departments Organisational structure and job descriptions of PPP Authority notified Framework for the prioritisation of ADP projects for mid-year review developed and approved by the P&D (to be used for the review of ADP 2019-20) Planning guidelines for LGs developed and endorsed by LG-RWG and draft planning manual developed Design of the inspectorate of Inspections and Monitoring developed and endorsed by LG-RWG LG transition related rules developed and endorsed by LG-RWG (at least 3) | ADP formulation process strengthened through adoption of mid-year ADP review framework and participatory sectoral planning Planning Reform Strategy (PRS) – focused on strengthening institutional design and effective planning – developed and endorsed by the P&D-RWG 50 new local government officials in pilot districts trained on planning, budgeting and monitoring process for LGs An end-to-end service delivery pilot initiated (service identified, provincial buy-in secured, need assessment undertaken) | At least 2 PIMA institutions (reform areas) identified by the government as high priority have a PIMA rating of ‘medium’ to ‘high’ End-to-end service delivery pilot rolled out in at least 1 LG in a pilot district | PIMA rating of one reform area further improved End-to-end service delivery pilot delivered in 2 LGs, and lessons shared for wider uptake | P&DB has moderate in-house capacity to conduct project appraisal and risk assessment | PIMA rating for 'effectiveness' of Project Appraisal and Risk Assessment improved. | Improved PIMA ratings in priority reform areas and strengthened planning systems in provincial and departmental institutions. | • Planning reforms remain high on government agenda • Change in the P&D leadership does not affect planning reform priorities • Government makes necessary resources available, including the needed staffing
|  | Achieved | [8 empty] | Achieved and exceeded target. Four priority PIMA reform areas improved, the Punjab Planning Reform Strategy was implemented, and Project Appraisal and Risk Assessment (PARA) standards were institutionalised. Reviews of major projects generated more than PKR 10 billion in savings and strengthened project appraisal and risk management.
|  | Planned | KP | Low planning capabilities in key government institutions – project formulation is deficient owing to the lack of development of complete and robust proposals & PC-1s (WB Report 2017) Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | Draft analytical review of the ADP completed for the priority sectors ToRs agreed and at least 4 departments identified for the assessment of planning capabilities Key recommendations of the LG study and gap analysis approved by the LG-RWG | Analytical review of ADP finalised, and recommendations approved for implementation (actions initiated on 4 out of 7 key recommendations) Assessment completed for 6 departments and recommendations presented to the P&D for action Local government performance Scorecard developed and approved by the LG Department for piloting in select LGs An end-to-end service delivery pilot initiated (service identified, provincial buy-in secured, need assessment undertaken) | Agreed recommendations of planning capability assessment implemented in 2 departments and PC-1 quality criteria developed Performance Scorecard tracking initiated in 4 LGs on PFM and planning regulations Two end-to-end service delivery pilots (cumulative) rolled out in at least 2 LGs in pilot districts | Effectiveness of strategic mandate of 2 Planning Cells internally assessed, and the planning capability reforms rolled out to 4 departmental Planning Cells Lessons learnt from 02 end-to-end service delivery pilots shared with provincial government and other LG for wider uptake. | Planning capabilities improved in P&D and 4 departmental planning cells; planning reforms rolled out to12 departments.(cumulative) | Project Appraisal and Risk assessment standards developed and assessment initiated based on these standards | Planning and monitoring function are better integrated leading to improved quality projects in 12 planning cells. |  | Programme Target revised. Additions in blue text. 3 end-to-end service delivery pilots would be delivered in year 4. programme will directly deliver 2 pilots and its replication in one additional LG will make a total of 3.
|  | Achieved | [8 empty] | Achieved and exceeded target. Planning Cell reforms were rolled out to 12 departments, improving alignment of projects with sector strategies and integrating climate and gender considerations. New planning tools and KPIs have been institutionalised and are being used independently by departments.
Sources: PIMA assessment 2020; Government notifications & minutes; PRS document; ADP analysis reports; Sector strategies & plans; RISE & PGS documents; Analytical reports on the use of ADP prioritization framework; P&D capability meta-analysis report; World Bank report 2017; Planning capability assessment 2020; LG engagement strategy/assessment report; KP institutional assessment report 2018; LG departmental reviews; LG performance Scorecard; LG administrative data; LDP monitoring reports
| Output Indicator 1.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | • Government’s appetite for reform exists • Formal authorising environment improves • Political environment remains stable • The WB and UNDP can commission the assessments promptly, ensuring that the results are available before the end of the relevant evaluation period.
| Provincial budget preparation capability | Planned | Punjab | Pillar 4 of PEFA – 12 out of 18 dimensions with a rating of C or D (6 each) demonstrating weak policy-based fiscal strategy | PFM Reform Strategy (PFMRS) developed and approved by the Finance Minister and first donor coordination meeting held Rules developed for Punjab Local Government Finance Commission (PLGFC) and approved by the Finance Department | PFMRS published with inclusion of disaster risk financing and evidence generated of its use in the design of World Bank PRIDE programme Budget call circular for 2020-21 issued with inclusion of aggregate budget ceilings (PEFA dimension 17.2) Interim need-based transparent and equitable formula for transfer of resources to local governments developed and approved by PLGFC | Joint P&D and FD budget proposal review process adopted in Primary Health and Primary Education | Budget better aligned in 04 provincial departments through joint P&D and FD reviews | Joint P&DB and FD reviews institutionalised for better budget alignment | Assessment initiated on the joint budget review process and its impact on service provision | Institutionalised integrated budgeting, medium-term fiscal frameworks, and improved PEFA ratings. |  | dimensions included in the definition sheet
|  | Achieved | [8 empty] | Achieved. PFM reforms were institutionalised through the Punjab PFM Act 2022. Integrated budgeting was scaled to all 40 departments, Budget Strategy Papers and MTFFs are routinely produced, and fiscal risk management reforms strengthened budget credibility and fiscal discipline.
|  | Planned | KP | Pillar 4 of PEFA - 8 out of 18 dimensions with a rating of C or D (3 and 5, respectively) | Budget ceilings developed and issued for recurrent and development budgets for enhanced integration and linkages (PEFA dimension 16.2) Essential PFM related subsidiary rules identified and agreed with the LG Department LG Fiscal transfer rules development in accordance with amended LGA | Integrated and strategic budgeting in the Finance Department, and at least 2 departments based on SAP system (PEFA dimension 16.2) Essential PFM rules developed and endorsed by RWG in accordance with the LGA amendment Needs based transparent PFC Award developed based on 2017 census data with analysis, details and guidelines for KP (and NMDs) | Joint Priority Committee (JPC) review of development and recurrent budget proposals for improved alignment, in 6 key departments | Budgets better aligned through review of development and recurrent budget proposal by JPC in 4 provincial departments | PFM Act implementation roadmap developed and tracking initiated | Assessment initiated on the joint budget review process and its impact on service provision | Institutionalised integrated budgeting, medium-term fiscal frameworks, and improved PEFA ratings. |  | Dimensions added in the definition sheet
|  | Achieved | [8 empty] | Achieved. The PFM Law was promulgated, integrated budgeting applied across all provincial departments, and the Fiscal Risk Framework introduced. Budgeting is increasingly linked to performance and service delivery outcomes.
Sources: Punjab & KP PEFA reports; SNG PEFA relevant assessments; Government budget documents; Notifications & letters; Budget analysis of LGs; PFC formula; PFC reports; Government meeting minutes & letters; Mini evaluation report on budget reforms
| Output Indicator 1.3 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | • Government commits to the fund release policy during the budget implementation irrespective of political patronage • There is macroeconomic stability throughout the year (no external shocks to the economy) • All administrative departments agree to prepare evidence-based cash plans • Ownership of planning and budgeting reforms in central and line departments • The WB can commission PEFA assessmnt promptly, ensuring that the results are available before the end of the relevant assessment period.
| Provincial budget execution capability | Planned | Punjab | Absence of cash plans and fund release policy | Fiscal Monitoring Committee notified to monitor utilisation of the provincial budget, and first meeting held | Cash plans of the provincial government for FY2020-21 developed and reviewed quarterly Funds Release Policy for FY2020-21 developed based on cash plans of FY2020-21 and endorsed by FD-RWG | Mid-year and end-year budget execution reports developed | Budget execution reports developed and reviews conducted by the Finance Department in line with government priorities | Budget execution review process institutionalised and legal framework for downstream budget execution strengthened | Budget execution reviews at departmental level strengthened for improved service delivery | Improved budget execution systems, including cash planning, fund release policies, and PEFA performance. |  | added in the definition sheet
|  | Achieved | [8 empty] | Achieved. Cash planning, Fund Release Policies, budget execution reviews and reporting mechanisms are institutionalised. Progress towards Treasury Single Account arrangements and sustainable debt management strengthened budget execution performance.
|  | Planned | KP | Absence of year-end budget execution reporting, weak cash management and forecasting mechanisms | Gap analysis of KP PFM system conducted and first draft of PFM Law submitted to the Finance Department | PFM Law finalised and submitted to the Finance Department for promulgation Cash management policy and TSA framework developed and shared with the Finance Department | Mid-year and end-year budget execution reports developed Downstream budget execution reforms under implementation in 2 line departments | Budget execution review conducted of actual releases against the Fund Release Policy Downstream budget execution reforms implemented in 2 line departments | Annual Performance monitoring mechanism initiated for three departments (Cumulative Target) | Budget execution reviews at departmental level strengthened for improved service delivery | Improved budget execution systems, including cash planning, fund release policies, and PEFA performance. |  | Definition sheet is updated accordingly. The team suggest to keep the no of depts to 2. as it will fit well with the overall trajectory of targets. However, there is room to identify that some of the key downstream reforms are still to be institutionalise and out of 2 departments these are mature in one and at a initial stage in other.
|  | Achieved | [8 empty] | Achieved. Fund Release Policy, Cash Management Policy and TSA Framework were adopted, expenditure monitoring improved, and performance monitoring systems were established within key departments.
Sources: Notified release policy & cash plans of government; PEFA internal assessments; Government notifications; Meetings minutes; Cash management policy; Funds release policy; KP PFM Law
| Output Indicator 1.4 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | • Select provincial and local governments are willing to meaningfully engage citizens • Select provincial and local governments are responsive to citizen needs and demands
| Citizen engagement in planning and budgeting | Planned | Punjab & KP | No guidelines for citizen engagement in place in provinces Punjab: PI-5 of PEFA Assessment 2019 is scored C (depicting weaknesses in disclosure of financial information in budget documents) KP: PI-9 of PEFA Assessment 2017 is scored C (public access to fiscal information) | Citizen engagement guidelines developed and notified Plan for improvement in PI-5 of PEFA (budget transparency) developed and agreed with the Finance Department | Mechanisms for inclusive planning agreed with the provincial government 90 LG staff trained on citizen engagement in pilot local governments ToT module developed for citizen engagement, and handed over to AAWAZ for further roll out Information on contingent liabilities published in the budget documents Mid-year budget execution report developed and shared with the Finance Department | A&I recommendations under implementation in at least 1 provincial department in Punjab and A&I review of the planning processes in 2 departments in KP | Evidence of consideration of citizen needs in planning and budgeting of 2 government departments | No milestone for the year | No milestone for the year | Evidence of citizen engagement integrated into planning and budgeting processes.
Achieved. Inclusive planning approaches were mainstreamed through planning and budgeting systems. More than 350 officials were trained, gender and inclusion indicators were integrated into planning tools, and citizen consultations increasingly informed budget priorities and allocations.
Sources: LG citizen engagement guidelines; Notification & circulation letters of citizen engagement guidelines; Orientation session reports with CSOs & MPAs; Summary analysis of budget documents vis-à-vis citizen needs and gender; Joint reporting framework; Sector strategies for inclusive planning; Inclusion assessment reports (for provincial governments); Stakeholder consultation reports
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 IMPACT WEIGHTING (20%) | Output Indicator 2.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | Assumptions
Institutions are better organised to deliver | Institutional capacity to deliver (social protection, climate, governance systems) | Planned | Punjab | Weak institutional capacity (critical shock responsive systems) to manage the impact of Covid | Agenda on social protection agreed with the government | Strategy for enrolment of informal/laid off workers developed and options for their registration and employment approved for implementation Provincial social protection policy developed and presented to the government | Provincial government establishes at least two systems (out of the six systems proposed in the RISE Strategy / SP Policy) to achieve post-Covid recovery | Provincial government implements 4 initiatives (out of 6 initiatives proposed in the RISE Strategy / SP Policy) to achieve post-Covid recovery. | PSPA has strengthened institutional capacity to deliver social protection Punjab has a provincial green financing strategy | Government of Punjab has strengthened institutional capacity to deliver social protection Implementation of Green financing strategy initiated | Government of Punjab has strengthened institutional capacity to deliver social protection Institutional arrangements for the implementation of Green financing strategy in place | • Fiscal resources are available to implement social protection initiatives • Provincial Cabinet (and its relevant sub-committee) timely convenes to approve the provincial social protection policy | already in the definition sheet
|  | Achieved | [8 empty] | Exceeded target. PSPA expanded social protection programmes, the Punjab Socio-Economic Registry reached approximately 35 million individuals, climate finance systems were established, and institutional capacity for social protection and climate action was significantly strengthened.
|  | Planned | KP | Weak institutional capacity (critical shock responsive systems) to manage the impact of Covid | N/A | Roadmap for instituting a post-Covid recovery approved and launched by the government | Social Protection Policy finalised and shared with government Social Protection Roadmap implementation tracked | N/A | Assessment of local level flood response completed; results disseminated for uptake and implementation initiated Governance mechanism for Social Protection service delivery in KP developed | Institutional arrangements for integrating and coordinating social protection in place | Policy and institutional arrangements for social protection in place
|  | Achieved | [8 empty] | Achieved. The Social Protection Policy, Social Protection Strategy, SPETS and institutional arrangements for a Social Protection Authority were developed. Climate Change Markers and climate finance mechanisms were integrated into government systems.
Sources: Provincial socio-economic registry; Social protection concept papers; PSPA annual progress; ADP analysis; Labour department data; BISP/NSER data; KP social protection Roadmap; PC-1s; Donor reports; Government meeting minutes
|  | Planned | Sindh | Weak risk governance arrangements in key government institutions-interdepartmental coordination is deficient owing to the lack of mechanisms and frameworks. Weak institutional basis for disaster preparedness at provincial and district level (undelineated roles, absence of contingency planning and implementation, no budget allocations for disaster preparedness) | N/A | N/A | N/A | N/A | Gap analysis of existing provincial and district level governance arrangements completed SOPs developed for improved coordination between PND, PDMA and line departments” Centralized dashboard developed to establish linkages between different administrative tiers and departments for informed decision making DDMAs established in three pilot districts and comprehensive contingency plans developed in consultation with district line departments and community representatives |  | Strengthened provincial and district disaster risk governance systems through improved coordination mechanisms, digital decision-support systems, and operational disaster preparedness structures in pilot districts
|  | Achieved | [8 empty] | Achieved: Gap analysis of provincial and district risk governance arrangements completed; SOPs developed to strengthen coordination between P&DD, PDMA and line departments; DMIS dashboard operationalised; DDRMUs/DDDMAs established and operationalised in pilot districts; contingency planning supported; and institutional arrangements for disaster risk governance established and budgeted for sustainability.
| Output Indicator 2.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26)
| Institutionalization of performance management system in Federal government for improved performance | Planned | National | Zero | N/A | N/A | 41 Performance Contracts signed between the Prime Minister and Federal Ministries | Evaluation of performance agreements initiative conducted, learnings documented and disseminated; Toolkit on performance agreements developed and shared with Planning Ministry and PMO; Strategic Roadmap for critical policy areas, including energy and economy, launched in PMO | Stocktakes and follow up meetings held for focused implementation of priority areas identified under the government's economic revival plan. |  | Effective performance management system implemented and evaluated at Federal government level
|  | Achieved | [8 empty] | Exceeded target. Performance Agreements were rolled out across 41 ministries and later evolved into Strategic Reform Roadmaps. PM-led stocktakes, monitoring systems and reform tracking mechanisms strengthened government performance management and accountability.
Sources: Government meeting minutes, Government notifications, PM Office generated progress reports, Performance Agreement Toolkit
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 3 IMPACT WEIGHTING (25%) | Output Indicator 3.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | Assumptions
Fiscal capacity is strengthened to enhance revenue and expenditure efficiency | Own source revenue capacity | Planned | Punjab | No systematic reform initiatives in place for collecting additional revenues | Revenue mobilisation plan developed and endorsed by the E&T-RWG | Implementation initiated on 2 out of the 6 initiatives supported by SNG with evidence of progress on the implementation | 4 out of the 6 initiatives supported by SNG implemented and evaluated with evidence of contribution to increase in fiscal space | 05 out of 06 initiatives supported by SNG delivered, and 2 of them internally assessed. | Punjab has improved capacity to mobilise own-source tax revenue | Revenue mobilisation strategy implementation progress tracked | Punjab has an improved capacity for own source tax revenue mobilisation | • Provincial governments willing to adopt revenue mobilisation efforts • Provincial governments develop their capacities to conduct periodic system-based tax audits • No exogenous shocks impacting revenue realisation (including prolonged impacts of Covid) | added in the definition sheet
|  | Achieved | [8 empty] | Exceeded target. Revenue mobilisation reforms, legislative changes, digital tax systems, ANPR rollout and establishment of the Policy Research and Analytics Unit strengthened provincial revenue generation capacity.
|  | Planned | KP | No systematic reform initiatives in place for collecting additional revenues | Potential areas for revenue mobilisation identified and approved by the E&T Department | Revenue mobilisation plan agreed with the E&T Department and under implementation – 2 (out of 8) initiatives of the Plan under implementation | 5 (out of 8) initiatives of the revenue mobilisation plan supported by SNG under implementation | 7 out of 8 initiatives of E&T revenue mobilisation plan delivered and at least 2 of them internally assessed. | Options for an Ad-valorem UIPT regime developed and considered by the Taskforce | Strategic Plan to transition to Ad valorem UIPT developed and endorsed by the Task force | KP has an improved capacity to mobilise own- source tax revenue |  | Definition sheet include the list of 7 initiatives of E&T plan. In KP the focus was on E&T. we have now added 2 for LGs.
|  | Achieved | [8 empty] | Exceeded target. Revenue mobilisation reforms increased tax collection significantly through automation, digital payments, revenue monitoring mechanisms and strengthened tax administration systems.
Sources: Provincial government budgeting & financial management data; Revenue mobilisation plans; Government meeting minutes & letters; Summary analysis on SNG’s contribution to increase fiscal space
| Output Indicator 3.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | • Provincial governments able to priorities initiatives targeted at efficiency savings • Provincial governments approve relevant legal/regulatory frameworks
| Capacity to ensure expenditure efficiency | Planned | Punjab | Inefficient budgetary expenditures (no budget rationalisation/ pension review conducted in the past) | Plans for efficiency savings agreed with the Finance Department | Implementation initiated on 2 out of the 5 initiatives supported by SNG with evidence of progress on the implementation | 3 out of the 5 initiatives supported by SNG implemented with evidence of contribution to efficiency savings | 4 out of 5 initiatives supported by SNG delivered, and internal review conducted for at least 2 completed initiatives. | Regulatory framework for implementation of DC Pension scheme developed | Implementation of DC Pension scheme is at an advanced stage | Punjab has an improved capacity to ensure expenditure efficiency |  | The 2 to be internally assessed are from the 4 to be delivered. While the four are specified in the definition sheet the 2 to be assessed are yet to be finalised.
|  | Achieved | [8 empty] | Exceeded target. Major pension reforms, including the Defined Contribution Pension Scheme and reforms to the Defined Benefit Scheme, substantially reduced long-term liabilities and improved expenditure efficiency.
|  | Planned | KP | Inefficient budget expenditures (no budget rationalisation; salary and pension audit conducted during the recent past) | Plans for efficiency savings agreed with the Finance Department | Implementation of the agreed efficiency savings plan – 2 out of 6 interventions implemented | Implementation of the agreed efficiency savings plan – 4 out of 6 interventions implemented | 05 out of 06 interventions under the agreed efficiency savings plan delivered, 2 internally assessed. | Fiscal risk framework developed and first annual fiscal risk statement prepared | Development of Fiscal Risk Framework and Fiscal Risk Statement institutionalised | KP has an improved capacity to ensure expenditure efficiency |  | list of 5 is specified in the definition sheet. The 2 for assessment are also proposed with subject to FCDO agreement.
|  | Achieved | [8 empty] | Achieved. Fiscal risk management, debt management and expenditure efficiency reforms created a stronger foundation for long-term fiscal sustainability and management of contingent liabilities.
Sources: Provincial government financial management & budgeting data; Budget & expenditure data analysis; Policy reviews; Government letters & meeting minutes; Government efficiency saving plans
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output x (discontinued from year 5) IMPACT WEIGHTING (15%) | Output Indicator 4.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | Assumptions
Innovative approaches developed and piloted | Number of AR projects implemented and evaluated | Planned | Punjab & KP | N/A | Ideas for AR identified and approved by the relevant RWGs 2 AR studies commissioned | 6 AR studies completed, and findings approved by the relevant RWGs | X AR studies completed, and recommendations taken up for consideration by the relevant RWGs (cumulative) | N/A | Completed and closed | Completed and closed | Completed and closed | • Government receptive to AR results
Achieved
Sources: PSC/RWGs minutes; Learning papers & products; Action research reports
| Output Indicator 4.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | • Quality proposals received based on relevant thematic areas • Government open to adopting innovation reforms
| Number of ICF pilots implemented and evaluated | Planned | Punjab & KP | N/A | 1st Round of ICF launched 4 ideas for Partnership Opportunities Fund (POF) identified and approved by the relevant RWGs | 8 innovative pilots (ICF and POF) approved by the PSC commissioned | 15 innovative pilots (ICF and POF) approved by the PSC commissioned (cumulative) | Innovation Challenge Fund (ICF) process reviewed, learnings documented and disseminated. | Completed and closed | Completed and closed | Completed and closed
Achieved
Sources: PSC/RWGs minutes; Evaluation reports; Case studies; M&E reports of pilots
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Output 4 (new output added from year 5) IMPACT WEIGHTING (25%) | Output Indicator 4.1 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | Assumptions
Local level governance is improved | Local governance and PFM systems | Planned | Punjab | Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | N/A | N/A | N/A | N/A | Modern PIFRA accounting system introduced at the local government level | Local OSR pilots rolled out in 6 districts | Strengthened local governance systems, revenue pilots, and PFM reforms. | • Government's commitment to LG reforms remains strong • There is clarity among stakeholders on the governing local government law
|  |  | KP | Weak institutional basis for planning and monitoring at the local level (absence of regulatory framework, no local development plans, and capacity gaps) | N/A | N/A | N/A | N/A | LUBC committees operationalised in two districts. | LUBC committees operationalised in 6 out of 7 SNG districts (cumulative) and its oversight by Land Use Authority strengthened. | Strengthened local governance systems, revenue pilots, and PFM reforms.
|  | Achieved | [8 empty] | Punjab: Exceeded target. Own Source Revenue pilots increased local revenues, strengthened transparency and accountability, and institutionalised performance monitoring through Deputy Commissioner-led stocktakes. KP: Achieved. Land Use and Building Control governance structures were established and operationalised, strengthening urban planning, land-use regulation and local governance systems
Sources: PSC/RWG meeting minutes; LG reforms lessons learning report; LF financial reporting and budget analysis report; IFMIS/SAP data; government/LG meeting minutes; progress review and internal assessment reports PSC/RWGs minutes; Learning papers & products; Action research reports
| Output Indicator 4.2 |  |  | Baseline | Year 1 Milestone (March 2020) | Year 2 Milestone (March 2021) | Year 3 Milestone (March 2022) | Year 4 Milestone (March 2023) | Year 5 Milestone (March 2024) | Year 6 Milestone (March 2025) | Programme Target (2019-26) | • Partner local governments are receptive to SNG approach • Lessons from the pilot are disseminated in time and engagement with stakeholders effectively managed • UNDP can commission the evaluation promptly, ensuring that the results are available before the end of the relevant evaluation period.
| Local level service delivery | Planned | Punjab | Absence of systematic approach to local service delivery | N/A | N/A | N/A | N/A | End-to-end service delivery management approach replicated in 2 additional LGs | Evaluation framework developed to assess the end-to-end service delivery pilot and its impact on service delivery | End-to-end service delivery pilots implemented and scaled.
|  |  | KP | Absence of systematic approach to local service delivery | N/A | N/A | N/A | N/A | End-to-end service delivery management approach replicated in one additional LG | Evaluation framework developed to assess the end-to-end service delivery pilot and its impact on service delivery | End-to-end service delivery pilots implemented and scaled.
|  | Achieved | [8 empty] | Punjab: Achieved. End-to-end Solid Waste Management pilots improved service delivery, citizen satisfaction and cost recovery while establishing systems for sustainability and wider replication. KP: Exceeded target. The SWM model achieved high citizen satisfaction, increased local revenues and was replicated beyond pilot districts, demonstrating successful scale-up and government ownership.
Sources: LG engagement strategy; SWM assessment reports/briefs; citizen perception survey; LG-RWG meeting minutes; LG reform lessons learning report; LG financial data
INPUTS (£) | FCDO (£) |  |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Note: The Business Case has been extended to 2026 to allow for the completion of activities which could not be completed due to COVID and ODA pauses/ uncertainty. The logframe will be extended by two years and will have new milestones to measure progress towards the completion of the final programme targets after the 2023 AR. The current version incorporates new activities as part of the two pivots (COVID and floods).

## Change Frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Outcome Indicator 3 | new indicator added | Amala Najeeb | 2024-11-04
2 | Outcome Indicator 4 | new indicator added | Amala Najeeb | 2024-11-04
3 | Output 1, Indictor 1.2 | The milestone has been revised due to delay in the procurement of evaluation firm. The onboarding on MEL firm is in process and should be finalised by february 2025. This milestones will be readded to Y7 log-frame. | Amala Najeeb | 2024-11-04
4 | Output 4. Indicator 4.2 | The milestone has been revised due to delay in the procurement of evaluation firm. The onboarding on MEL firm is in process and should be finalised by february 2025. This milestones will be readded to Y7 log-frame. | Amala Najeeb | 2024-11-04
5 | Output 4 | Original Output 4 “Innovative approaches developed and piloted” discontinued and replaced with new Output 4 “Local governance is improved” to reflect programme shift in focus | Amala Najeeb | 2024-11-04
6 | Output weightings | Impact weightings revised: Output 1 reduced from 35% to 30%; Output 3 reduced from 30% to 25%; Output 4 increased from 15% to 25% | Amala Najeeb | 2024-11-04
7 | Outcome Indicator 2 | Indicator revised from perception survey approach to evidence-based assessment (thematic reviews, results verification, endline evaluation) due to reliability concerns | Amala Najeeb | 2024-11-04
8 | Output 1 Indicators | Indicators refined to better reflect focus on planning, budgeting and execution systems; definitions clarified and simplified | Amala Najeeb | 2024-11-04
9 | Output 2, Indicator 2.1 | Indicator scope expanded to include social protection, climate change, and governance systems to reflect integrated institutional capacity support | Amala Najeeb | 2024-11-04
10 | Output 3 | Output reframed from 'Fiscal space is increased' to 'Fiscal capacity is strengthened' to reflect sustainability and institutional strengthening focus | Amala Najeeb | 2024-11-04
11 | Output 4 Indicators | Two new indicators added: (i) Local governance and PFM systems, and (ii) Local level service delivery, replacing innovation-focused indicators | Amala Najeeb | 2024-11-04
12 | Multiple outputs | Milestones across outputs revised to reflect COVID, floods and MEL delays; sequencing updated for realistic delivery timelines | Amala Najeeb | 2024-11-04

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.

## Sheet1 (hidden)
Outcome | Original description | Revised description
Indicator 1 | Local government spending | No Change
Indicator 2 | Citizen satisfaction with basic services | Generation of evidence base on the effectiveness of SNG-II initiatives and verification of short to medium term results to inform endline evaluation of SNG-II Programme’
Output | Original description | Revised description
Output 1 | Plans and budgets are more evidence-based and executed as planned | PFM systems are strengthened for effective planning and budgeting
IMPACT WEIGHTING | 35% | 30%
Output 1, Indicator 1.1 | Planning capabilities in provincial and local government institutions | Provincial planning capability
Output 1, Indicator 1.2 | Budget preparation process | Provincial budget preparation capability
Output 1, Indicator 1.3 | Budget execution in government | Provincial budget execution capability
Output 1, indicator 1.4 | This indicator was removed, and work related to A&I is now captured in other indicators across Logframe
Output 2 | Institutions are better organised to deliver (with a focus on Covid recovery and climate adaptation) | Institutions are better organised to deliver
IMPACT WEIGHTING | 20% | 20% (No change)
Output 2, Indicator 2.1 | Institutional capacity to plan and deliver post Covid recovery | Institutional capacity to deliver, including social protection, climate change etc.
Output 2, Indicator 2.2 | No longer part of output
Output 3 | Fiscal Space is increased with more resources available for service delivery | Fiscal capacity is strengthened to enhance revenue and expenditure efficiency'
IMPACT WEIGHTING | 30% | 25%
Output 3, Indicator 3.1 | Provincial own source revenue capacity | Own source revenue capacity
Output 3, Indicator 3.2 | Efficiency savings in government expenditure | Capacity to ensure expenditure efficiency
Output 4 | Innovative approaches developed and piloted | Local governance is improved
(Output 4 (new output added from year 5)
IMPACT WEIGHTING | 15% | 25%
Output 4, Indicator 4.1 | New Indicator "Local Governance and PFM systems"
Output 4, Indicator 4.2 | New Indicator "Local level service delivery"