## CIPREG Annual Review 2025

Title: Capital Investment Programme for Resilient Economic Growth (CIPREG)
Programme Value £ (full life): £55.3m		Review date: 14/12/2025
Programme Code: 204712	AMP start date: 24/07/2019	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	B	A	B	B	B	A
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-204712/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-204712/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Capital Investment Programme for Resilient Economic Growth (CIPREG) was approved in 2018 for a five-year period (2018-2023). The original aim of the programme, as set out in the original business case, was to support economic growth, enhance resilience against natural disasters and promote the role of the private sector. However, over time the programme has prioritised a mix of long awaited (e.g. hospital) and urgent infrastructure projects (e.g. sewage), maximising economic benefit where possible. The overall budget is £55.3m, consisting of £52.3m for infrastructure projects and £3m for technical assistance. This includes funding for the technical consultant roles within the Programme Management Office (PMO)[1], whose role is to improve the delivery and effectiveness of programme management across the Government of Montserrat and build programme management capability across Ministries.
[1] Three roles are funded through CIPREG (Hospital Project Manager, Health Service Transformation Project Manager, Health Service Transformation Project Support Officer)

Programme Timeline

2018	The Capital Investment Programme for Resilient Economic Growth
(CIPREG) was approved for a five-year period (2018-2023).
The original approved funding for the CIPREG was £30m.
The original aim, as set out in the original business case, was to support economic growth, enhance resilience against natural disasters and promote the role of the private sector. However, over time the programme has prioritised a mix of infrastructure projects, both long awaited (e.g. hospital) and urgent (e.g. sewage), maximising economic benefit where possible.

2019	A short no cost extension was approved to align the programme’s timeline with the Memorandum of Understanding (MoU) agreed between the Government of Montserrat (GoM) and the FCDO.
2023	A cost extension of £10m (to a total of £40m) and a time extension to 2025 was approved.
2024	A further costed extension was approved by HMT in October 2024, increasing the budget by £15.3m and extending it by two years to allow the construction for the hospital. This brings the total value of the programme to £55.3m. This increase was necessitated due to increased costs for the Hospital contract following the final tendering process for the main construction. £39.9m set aside for hospital build.
The overall budget is £55.3m, consisting of £52.3m for infrastructure projects and £3m for technical assistance. This includes funding for the technical consultant roles within the Programme Management Office (PMO)1, whose role is to improve the delivery and effectiveness of programme management across the Government of Montserrat and build programme management capability across Ministries.
Construction of minor works on the hospital takes place and the refurbishment of The Margetson building is completed in October.
Creation of Utilities Working Group, to drive forward delivery on renewables
2025	The time extension to 31 March 2025 expires and the 2-year time extension	commences, with main hospital build contract signed 24 January 2025	and construction starting 7 April 2025.
2026	All projects under CIPREG except the hospital build, expected to be	completed by end of March 2026.
2027	The hospital expected completion date is end of March 2027

At impact level, CIPREG aims to support ‘increased economic activity, enhanced resilience to natural disasters and improved private sector participation in Montserrat’s development’.

CIPREG’s Business Case envisaged a strong alignment between the programme and GoM’s Economic Growth Strategy (EGS). It is noted that CIPREG would focus on establishing the foundations for economic growth and increased private sector investment, especially in the tourism sector. It would invest both in physical and human capital, increasing the resilience of public infrastructure with respect to natural disasters and maximise the benefits of approved UK-funded (UKCIF) investments in the port and geothermal exploration project.

As we approached three decades on from the eruptions which transformed life on Montserrat, much of the portfolio in this reporting period supported projects to restore basic social infrastructure as a foundation for attracting labour and driving growth, such as the hospital, energy infrastructure, social housing, school buildings, asphalt and sewage plant.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Following the assessment of the logframe outputs, the programme has scored an A, meeting expectations. The scoring reflects the projects improvements over the course of the review period with most projects completed and those still active, with clear timeframes for completion. The main remaining project, the hospital build, is on track for completion as anticipated by end of March 2027. With projects winding up, the benefits realisation period has indicated that the Theory of Change (ToC) needs adjusting. The outcomes will need to reflect the reality at this stage. With most projects completed this will be mainly focussed on the hospital build.

The scores in the last review highlighted that some assumptions upon which the programme has been built have not been realised, including the creation of a tourism offer and inward investment opportunities. Good progress has been made on sustainable energy transition, hitherto thought to be unrealisable under the previous review, however, with the formation of the Utilities Working Group (UWG) to drive forward the energy transition aims, good progress has been made in this area. Future potential investment should consider the capital projects needed further to support CIPREG’s intended outcomes and theory of change, focusing on the methods by which this can be achieved. This will provide a good foundation upon which economic development in these areas could be realised, for example, through improved access to the island (port, airport and road network upgrades), delivery of a stronger tourism offer, and a clear road map to long term sustainable energy transition, being driven by the Utilities Working Group.

Risk remains Major as there is some way to go to complete the programme, with the unpredictability that brings, but it is not trending in a higher direction as most projects are now complete and the output to support relevant assumptions of the theory of change are being realised. It will be important to review the theory of change against what completed projects have made possible and adapt accordingly.

As the programme scored consecutive B’s over the previous 3 review periods, it was subject to a performance improvement plan (PIP) to get the programme back on track. The PIP tracker and update can be found at Annex A at the end of this report. Performance has improved with projects now completed, or the 4 remaining on track against current timeframes.

Major lessons and recommendations for the year ahead [1/2 page]

Last year’s recommendations have been followed up during the reporting period and there have been several lessons learned. These can be found under the detailed output sections.

Recommendations for this reporting period

Recommendations were made under each section of the Annual Review. Below are the specific recommendations raised for this reporting period.

Recommendation 1 (OP1): With all projects under this output either completed or coming to a close, a benefits realisation analysis should be produced for each indicator and forward look plan put in place to maximise the utility of the outputs the CIPREG programme has realised. This in turn will inform forward planning, prioritisation and budgeting, including for Operations and Maintenance (O&M) to ensure upkeep of equipment and maintenance of facilities produced under CIPREG. Action: Government of Montserrat (GoM) Ministries supported by PMO

Recommendation 2 (OP1): Each ministry undertake an analysis of future needs against Montserrat’s medium term strategic vision, so that future projects and programmes can complement this and provide maximum impact against the outputs already achieved to date from CIPREG. Action: GoM Ministries supported by Project Management Office (PMO).

Recommendation 3 (OP2): MoH collaborate with PMO to ensure that the digitalisation of healthcare is optimised through sharing of planning and delivery of the Health Information Service (HIS) with stakeholders in other ministries working on digitalisation, such as the Department of Information Technology & e-Government Services (DITES). Action: MoH, PMO, DITES

Recommendation 4 (OP1/2/3, Monitoring Evaluation and Learning (MEL): PMO to strengthen collaboration with all Ministries by sharing programme updates, maintaining a lessons‑learned register, and building their project delivery skills. This will ensure all active programmes are visible, enabling better monitoring, management, and more effective delivery throughout their lifecycle. Procurement team to co-locate with PMO and teams to collaborate closely and cover any cross-team capacity gaps. PMO to take on programmes’ secretariat work, now that the governance covers multiple projects and programmes. Outreach by PMO to ministries to increase and a guidance manual on project delivery produced and shared with them.
Action: PMO, GoM, Post, CIPREG Team

Recommendation 5 (OP2): As the hospital moves further into delivery phase, the health service transformation plan with the benefits realisation and hospital operationalisation details, should be reviewed and shared within the governance system. Clear pathway for all items needed to deliver the health service transformation plan such as furniture, fittings and equipment (FFE) should be in place. Thought to be given to how processes such as visas, can be streamlined and planned well in advance for external project delivery resources.
Action: MoH, PMO

Recommendation 6 (OP2): Montserrat Land Development Authority (MLDA) to revisit the rent rates to ensure the cost of future maintenance on the upgraded units is covered and they do not fall into a state of disrepair.
Action: MLDA

Recommendation 7 (OP3): GoM to identify opportunities for private sector investment outside of internet providers, for the digital offering on island. Close liaison with hospital IT team is recommended to ensure any telemedicine or IT technology driven opportunities are fully realised. As geothermal pathway and implementation become clearer, opportunities this might present for energy/mineral use/IT benefits should be analysed e.g. opportunities for data centres. Report on the outstanding contract model should be completed as soon as possible.
Action: GoM, PMO

Recommendation 8 (OP3): As the programme comes to a close for most projects, economic benefits of CIPREG outcomes should be considered in the context of IT and green energy outputs to ensure maximum benefits, For example potential uses of green energy and IT, hospital digitalisation and fibre connectivity. These can then inform future inward investment opportunities and maximise CIPREG programme output usage.
Action: GoM, PMO

Recommendation 9 (Risk): GoM Senior Responsible Officers to present detailed risk analysis at both the monthly Programme Board and bimonthly Steering Committee using the agreed format. GoM Steering Committee Officers should also submit quarterly risk registers to FCDO using the pre agreed format to better facilitate escalation usage.
Action: GoM, SROs

Recommendation 10 (Risk): A revision to the logframe and review of the theory of change should be undertaken within 3 months of this annual review including factoring in the underlying assumptions for improved economic development now that the majority of projects have been completed and factoring changes for the key hospital build focus. FCDO internal Risk Register to continue to be updated monthly and as required.
Action: FCDO CIPREG Team

Recommendation 11 (Risk): Safeguarding Board to continue meeting regularly and FCDO safeguarding lead to advise FCDO of any risks to input into Risk Register. Board has authority to set up subgroups as required to drive tangible action as needed on emerging concerns.
Action: GoM, Safeguarding Team
Recommendation 12 (Risk): Ministry of Health (MoH) PS, Community Liaison Officer (CLO) and Project Manager (PM) to continue to deliver safeguarding and induction training for new workers.
Action: MoH PS and PM
Recommendation 13 (Risk): New OTPD Safeguarding Lead should visit Montserrat in 2026 to continue the important work on safeguarding and help deliver training sessions for any new workers on Island.
Action: MoH PS and FCDO Safeguarding Team
Recommendation 14 (Risk): New FCDO Safeguarding Lead to work closely with Deputy Governor’s Office to support development of Common Approach to Protection from Sexual Exploitation, Abuse and Harassment (CAPSEAH) approach.
Action: DG and FCDO Safeguarding Lead

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The original Theory of Change (ToC) is unchanged from that of the original Business Case.

The theory of change underlined the need to enhance both economic development through improved capital infrastructure and capacity, and private sector engagement to enable that economic dividend. Clear outcomes underpinning the timely delivery of individual capital projects alongside the realisation of robust operations and maintenance systems and gender / community-based outcomes are linked to a range of impacts that include economic growth, increased private sector engagement / investment and improved resilience through laws, regulations and building standards.

Several assumptions underpin this causal theory. These include GoM capacity including on procurement and project management, and GoM ability to attract and promote tourism and inward investment. It has become apparent over the course of this review period, that it has not been possible to achieve these assumptions, despite the best efforts of the GoM. At the beginning of the next review period, these assumptions will need to be reassessed against the feasibility of them being achieved and adjusted accordingly.

The theory of change for the next period, should also reflect the addition of the Cultural Centre which will accommodate the Montserrat Legislative Assembly and provide an important addition to Montserrat’s governance capability. As one of the main community spaces and buildings, it will also provide key tourist and on island events spaces, with the benefits of income-generating opportunities this will bring.

CIPREG’s portfolio combines projects supporting economic development and others that more strongly speak to infrastructure resilience, and the delivery of essential social services. The initial economic development aims have been key to the benefits of social development projects within CIPREG, with the positive effects this has on quality of life and living conditions. For example, airport upgrades and road improvements help island access with the increase tourism and income generating opportunities these bring as well as increasing the potential for more effective medivacs from the new hospital. Maintaining green energy sources helps lower costs and reduce energy bills on island.

CIPREG has been complemented by £22m of additional ODA funding from the Improving Essential Equipment for Aided Overseas Territories Programme. This has also supported the building blocks/preconditions for economic growth and provided much needed support for social development including through essential hospital equipment and upgrades to water and sewage infrastructure.

The Fund has also greatly assisted the aims of CIPREG though provision and support for greening energy and improved island access through additional airport upgrades. With funding limited, focussing on ways to ensure the different programme funds complement each other, when one fund does not have capacity to cover all key aims, could prove beneficial to our overall objectives.

After approval in November 2024, the CIPREG budget received an uplift of £15.3m to cover the cost of the new hospital build. Along with this, an overall extension to March 2027 was agreed to reflect the delay to the Programme. However, this extension was agreed to facilitate the completion of the hospital, other projects within the Programme should not need to use this extension and after a PIP was put in place for this year, we expect all other projects to finish within this review period or by end of March 2026 at the latest.

It has become clear over the course of the assessment period and as projects have come to completion, that the programmes’ aims, assumptions and outcomes have not been as expected. A reflection on these and on the outcomes we can achieve, will need to be completed for the remainder of the programme. Specifically, the assumptions for tourism and inward investment will need to be considered in the context of the current reality and adjusted accordingly. We can expect that, with most projects nearing completion, the logframe will be much more focussed on the hospital build and on the outcomes from the completed projects to assess their level of effectiveness.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The overall output and outcome assessments over the course of the review period would indicate that the outcomes will be achieved, however not within the timescale and budget originally planned. There are good and documented reasons for this and with an adjustment of the timeframe to end of March 2027 the indications are that the programme is on track to achieve the expected outputs. At impact level, the logframe envisaged ‘increased economic activity in Montserrat, enhanced resilience to forces of nature and improved private sector participation in Montserrat’s development’. For the completed projects, it is too soon to understand the impacts made so this will need to be considered against the theory of change adjustments needed for the changed environment the programme is working under, including tourism and inward investment constraints.

The key focus of the CIPREG programme has been re-establishment of lost or poor essential infrastructure. Although economic development has been a key output, social development has and will be just as important. It is important to flag this, as whether the programme is on track needs to consider the social outputs aspect just as strongly as the economic ones that the CIPREG title targets. (i.e. new hospital, social housing, secondary school, roads and WASH). Projects to develop key green energy infrastructure, wastewater and airport upgrades currently underway through the Essential Equipment programme, are crucial to maintaining the usefulness of completed CIPREG projects and not letting the outputs lapse. The CIPREG inputs and continuation of these initiatives are needed to both support the island and to incentivise FDI through the provision of reliable energy and improved access to the island.

The programmes strength currently is the excellent delivery being shown by many of the ministries within the GoM to complete projects within the timeframe envisaged in the PIP, as summarised in Annex A. Where this has not been possible, clear timeframes and outputs are being shared which demonstrate a commitment to achieving delivery as soon as possible. Although the Project Management Office (PMO) compliment has increased, capacity issues including the lack of a Deputy Head has continued to impact delivery. Key to remaining projects performance will be strong links with the relevant ministries to help keep timeframes and targets on track.

Outcome indicator 1 tracks percentage of FCDO-funded capital infrastructure projects meeting planned completion milestone targets. With the introduction of a PIP last year, projects were failing to meet their completion targets, so the milestone was added to stipulate that all projects, except for the new hospital build but including minor works, needed to be on track for completion by the end of FY 25/26. Currently this is on track to happen or for any residual work to be absorbed by a non-CIPREG budget, effectively completing CIPREG’s role in the relevant project.

Outcome indicator 2 relates to robust systems being in place for whole life cycle O&M and value for money (VfM) demonstrated on CIPREG-funded projects and adopted in GoM systems. The milestone for this reporting period was for ‘whole life cycle and VfM methodologies fully integrated into GoM systems, including planning maturing to demonstrate provision for hospital costs within wider health financing work. O&M to fall into the recurrent budget. For completed projects GoM has set in place O&M plans but as they are very recently completed projects it will take some time to assess if this has been effective. For the hospital, future hospital costs are part of the forward-looking strategy but with the hospital build underway, specific needs and requirements may change.

Outcome indicator 3, a new indicator, relates to the consideration of gender, disability and inclusion criteria in infrastructure development decision making, and the inclusion of needs of vulnerable groups in project design and delivery. The milestone for this reporting period has been ‘Key’ inclusion criteria included in design and delivery processes. Community and expert engagement on these areas are evident across planning and design work, particularly on hospital project, social housing and cultural centre renovation and upgrade. From our AR visit we could see first-hand the inclusion planning in place for these projects and indications are that these are on track, to be reviewed again at the next annual review (AR).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Based on the above analysis of outcome and output, the realistic position with the theory of change vision and VfM analysis, the project should continue. All but four of the projects within the programme have now been completed with all but the hospital due for completion this FY. The remaining projects will provide impactful outputs for Montserrat and as they are on track for completion should continue to be supported and funded. CIPREG has and is providing key outputs for the wider Montserrat portfolio, paving the way for greener energy, greater and safer access to the country and an infrastructure which will support outputs from the port including safer tourism through the healthcare provision the new hospital will provide.

The project improvement plan has been implemented to good effect, with some areas envisaged, such as extra personnel capacity, not needed. With most projects complete, and good project delivery teams in place for the remaining, major hospital project, delivery and outputs are on track again. We cannot yet judge the full outcomes of the CIPREG programme but do now have a better understanding of the likely parameters we can measure. In consideration of the VfM analysis the counterfactual of ceasing the programme would lead to the lack of crucial infrastructure needed for the island, half-completed projects (with reputational risk to the FCDO), which are on target to complete to new timeframes and a profound impact on the economic growth of Montserrat. Given the progress made and likely completion of the programme within acceptable time parameters, this is not an option we should currently consider.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Essential economic development and resilience projects completed on time, within budget and to required standards.
Output number:		1	Output Score:	A
Impact weighting (%):		31	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 - Upgrading A-1 road and procurement of hot mix bitumen plant	Works on roads under this project completed by July 25 and O&M phase successfully implemented to ensure maintenance of roads	A: Achieved and Closed. / Planer delivered and in use, hotmix fully operational. O&M delivery through road patching in some areas but full A01 roads resurface requires a substantial funding injection, not within scope of CIPREG to provide this.
1.2 - Rehabilitation of airport runway		N/A: Achieved and Closed
1.3 - Urgent infrastructure and support infrastructure for improved access.		N/A closed in 2022
1.4 - Fit for purpose airport control tower, to address concerns raised by ASSI	All works on Air Traffic Control Tower (ATC) completed and facility in operation by December 2025. Maintenance schedule for ATC produced by GoM and reviewed by FCDO by end of December 2025. Benefits analysis of investment produced by GoM by March 26.	A: Achieved. Fit out of lift underway whilst conducting AR and on schedule for completion by early December 2025. All rooms in tower approaching final fit out stage. Requisite aeronavigation IT systems have been installed in the new tower and are operational. Tower expected to be fully operational in December 2025. Work underway using Essential Equipment budget, to upgrade runway lighting. O&M schedule and benefits analysis for wider airport and tower, yet to be shared.
1.5 - Refurbishment of critical areas of the Montserrat Secondary School, specifically blocks L and M, and the staffroom and bathroom facilities	All outstanding works to be completed by November 2025 and O&M plan produced to ensure upkeep of facilities.	A: Achieved and closed. All Blocks completed and labs, classrooms, lavatory facilities all operational.
1.6 - Renovation of essential sewage works at Drummonds and Davy Hill	Project to be completed by July 2025 within the allocated funds and a robust O&M plan to be drawn up and implemented.	A: Achieved and closed. CIPREG funded work has now come to an end. The Drummonds facility is fully operational. Lookout will not be completed as planned as Marguerita Bay / wastewater plant, funded under the Essential Equipment programme, will be covering the load for the area, but emergency overflow system is in place in case needed before the Marguerita Bay facility is operational. Completion of Davy Hill works are being funded by GoM under a different budget and PS BUILTE reports that all equipment needed to complete the project on island. Regular maintenance is being carried out.

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 1.1 measures progress against critical roads maintenance and rehabilitation. In this reporting period, the previously installed asphalt hot mix plant continues to be utilised and has been running on occasions CPREG team has visited. The supply chain for the raw materials is holding up well, with on island supplies in use which negates concerns about overseas supply chains. A road surface planer was ordered and a delivery milestone for this AR period. It has been delivered and is in use. We were able to see the equipment during our AR visit, which looks in good condition with maintenance factored into the planning to ensure it does not deteriorate (eg through sea blast corrosion). The Public Works Department is currently patching roads but a full repair and upgrade plan for key roads would be the next step to utilise the CIPREG funded facilities. This would require further funding outside of CIPREG and the PWD are working on sources. This indicator has scored an A – meeting expectations.

Indicator 1.2 measures the progress on works related to the airport runway. All work under CIPREG has been completed, complimentary work on runway lighting is underway using the Essential Equipment fund but this indicator will be closed for future reviews.

Indicator 1.3 relates to the new airport tower and addressing the recommendations from Air Safety Support International[2]. The Steering Committee approved EC$279k to complete the upgrade works this FY. Tower has had its design completed and lift procured, delivered and was in the process of installation during our AR visit, with a target completion date of mid-December. Room fit out is underway with services works completed and items needed, procured. As such, the expected completion date is within the timeframe of this AR. The aeronavigation fibre optic IT hardware has been installed and with the additional funding this FY, this equipment is now up to regional compliance standards, operational and backed up by UPS supported power supply with adequate provision for cooling. The tower itself is fitted out with air traffic controller communications and equipment which now has all cabling installed in preparation for live operations. With the outstanding room renovation works complete, the building is capable of accommodating the required 8-person staffing provision. Given the progress made against the main reason for the B grading at the last review, namely a delayed date of being operational, primarily due to delays installing the communication system, this indicator has scored an A. However, as the works are almost complete the FCDO should have sight of a maintenance plan for the tower, as soon as possible after it becomes operational.
[2] ASSI is a not-for-profit, wholly-owned, subsidiary company of the United Kingdom Civil Aviation Authority, established under Directions from the UK's Department for Transport. The company's primary objective is to help provide a more cohesive system of civil aviation safety regulation in the UK Overseas Territories

Indicator 1.4 measures progress on refurbishing classroom blocks L and M in Montserrat’s Secondary School (MSS), as well as refurbishment of other key areas such as an on-site toilets and shower block. The project was substantially delayed due to the observation of cracking in the new structural concrete works – which have now been resolved. During the site visit on 4th November 2025, all works outstanding at the time of the last AR, had been completed. The labs were in use and equipment within the rooms functional. PS Education and the acting Headmistress of MSS reported that the upgrades had helped with study classes significantly. However, completion of the project has not been without its challenges, with delays to the cabinetry and need to change contractor, meaning there were significant issues to overcome to complete the lab works. The toilet blocks, still to be completed at the time of the last review, were completed and in use. A project closeout report was generated and the project closed under the CIPREG programme. As the project has been completed this indicator has scored an A – as outputs have now met expectations since the last review.

Indicator 1.5 relates to the renovation of wastewater works at Drummonds, Lookout point and Davy Hill. The works under CIPREG intended to ensure continuation of essential community services, and reduce operating costs for the facilities, ensuring public safety (by fencing off the sites). The works at Lookout point sewage plant have been overtaken by a £2m wastewater project at nearby Marguerita Bay, which will absorb the capacity Lookout sewage plant had been covering. The solar panels in the original plant will be moved to Marguerita Bay during the construction phase of the plant. We agree it makes sense not to carry out any further works here as the plant is at end-of-life stage and the new facility would need to be used very soon, in any case. Safety and security work still underway during the last review had been completed with all 3 sites secure. Drummonds is now running off the solar installation with a generator back up and Davy Hill although secure, still needed solar panels installing. PS BUILTE assured us these are on island and will be fitted soon. All other sewage works and regular maintenance now fall under another budget and the project has been closed under the CIPREG programme. As the CIPREG element of the programme has closed and the remaining issues highlighted above, are covered under plans in place for sewage and wastewater works, this indicator has scored an A

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Indicator 1.2 (rehabilitation of the airport runway) will now be closed in the log frame.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

There are recommendations outstanding from last year. This review has assessed progress on those recommendations while adding new recommendations for 2025.

Recommendations from 2024 Annual Review (AR):

Recommendation 1 (OP1): The economic proposition of the programme should benefit from assurances on both systems and strategic planning. It is recommended that on forward planning for infrastructure, each ministry develops a road map transition covering at least 5 years to support both energy and access transitions. To support this longer-term thinking, we further recommend that each ministry incorporates strategic operations and maintenance plans covering multiple years to allow for annual prioritisation and also retain holistic oversight of key outward O&M planning for economic infrastructure. This would help shape CIPREG and could be developed by building upon the draft outcome framework. Action – GoM supported by FCDO CIPREG Team.

Progress: ongoing, with projects nearing completion or completed, we are now entering a benefits realisation stage. It is clear that, for education the project has provided tangible benefits for students. An environment more conducive to learning will hopefully produce better results and a more skilled workforce pool for Montserrat with future benefits for the economic development of the country. Better roads will ideally lead to better access to the island for tourists and inhabitants alike with economic benefits this brings and planning underway for future O&M, should factor in the maintenance plans highlighted in this recommendation and be shared with FCDO. Facilitation of better airport access has been a success, and we are seeing further work underway to improve the flight offering and landing timeframes, with the economic benefits this will bring.

Recommendation 2 (OP1): Trade visit assessments in February 2025 should inform GoM of the road mapping of critical infrastructure in a way that can be adjusted to more closely meet the needs of inward investment. The programme should identify what these asks are and analyse the extent to which these can be accommodate through CIPREG. Action: FCDO and Governor’s Office

Progress: Ongoing, there is currently very little capacity for CIPREG to accommodate additional initiatives as a funding overcommitment has been identified and time left to run for the programme is short. Although the February 25 Trade visit did not occur, proposals from previous trade meetings resulted in Essential Equipment funds covering airport runway light upgrade proposals. complimenting work previously completed under CIPREG. Additional funding from Essential Equipment has also ensured wastewater and sewage capability is strong, through the addition of the facility at Marguerita Bay. Work through the Utilities Working Group has also significantly improved the green energy offering, with geothermal options made possible by CIPREG work on maintaining the geothermal wells. It is unlikely CIPREG will pick up significant additional project work in future as the programme is at the end of its lifecycle and the focus will be on the hospital completion for the next FY, so we will be looking at ways other programmes and projects can complement the work of CIPREG.

Lessons learned from this year

As projects come to a close, it is going to take some time to assess their impact, for example how better facilities at MSS and the airport create changes for the better. We will need to work closely with GoM to assess the benefits realised over the course of the medium term, e.g. 5 years. We need to ensure we understand what future sectors will benefit from the work under this output and focus on ensuring these sectors are supported by upcoming capital programme funds for Montserrat. For example, support for roads development and airport upgrades to improve access for tourism and education improvements to focus on areas needed for future workforce planning. Infrastructure upgrades may provide space for more accommodation on island which inward investors and tourism companies alike will want to see and a potential future area to focus on.

Upkeep and upgrades to the facilities created under this output, will be crucial for continued viability of the economic growth vision of CIPREG. O&M plans covering a medium-term period should be drawn up to ensure maximum benefits from the programme outputs.

We need to be attuned to the viability of projects over the term of the programme. Some have taken much longer than expected so early collaboration and properly drawn up and clarified timeframe plans are crucial when deciding what can and cannot be in scope.

Recommendations for the following year

Recommendation 1 (OP1): With all projects under this output either completed or coming to a close, a benefits realisation analysis should be produced for each indicator and forward look plan put in place to maximise the utility of the outputs the CIPREG programme has realised. This in turn will inform forward planning, prioritisation and budgeting, including for O&M to ensure upkeep of equipment and maintenance of facilities produced under CIPREG. Action: GoM Ministries supported by PMO

Recommendation 2 (OP1): Each ministry undertake an analysis of future needs against Montserrat’s medium term strategic vision, so that future projects and programmes can complement this and provide maximum impact against the outputs already achieved to date from CIPREG. Action: GoM Ministries supported by PMO

Output Title	Essential social development projects completed in time, within budget and to required standards.
Output number:		2	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR? Yes	[If Yes, up or down?] Down

Indicator(s)	Milestone(s) for this review	Progress
2.1 - Construction and operationalisation of new hospital on Montserrat and progress on plan to improve health services delivered	Hospital construction on target to meet new CIPREG completion date of March 2027, plan to improve future health services drawn up and pathway beyond the completion of the hospital build, clear. Strategy for implementation of health services plan including O&M, achievable.	A: Achieved - £39.9 million allocated for hospital build. Minor Works Phase 1 has been completed with Phase 2 next. Permanent power now on and foundations laid for the main new hospital building. Slight delays mainly due to wet weather. On-target for completion 7 April 2027. Ideally needs to be completed by 31 March 2027 as per the business case extension timeline. / Health service transformation has begun transferring paper records over to digital records for public service practices, this is hoped to be rolled out to include private practices. / O&M has been considered in planning for hospital after it is complete.
2.2 - Social Housing studies had been commissioned to inform GoM housing policy and now in implementation	Social Housing improvements, as a result of the study, made and completed within the constraints of the CIPREG project funding by July 2025. Proposal for O&M and use of the new policy in Social Housing activities in future, clear.	A: Achieved - the Social Housing Study led to the plan to construct four one-bedroom units at Drummonds. This has been tendered with a completion date of end of March 2026, the target date for completion of all projects under CIPREG except the hospital build. The Study also resulted in the corrective maintenance work for social housing, which was successfully completed this year.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 2.1 assesses the progress made on the development of the New National Hospital, which began construction in April 2025 after a series of delays. The development of the hospital has been long promised by successive UK governments since the volcanic eruptions; first one being 30 years ago this year and is much needed.

The hospital constitutes a key commitment for the UK Government in Montserrat, which has been reflected in the initial and final financial commitments through the programme. The initial approved budget range for the hospital was £19m - £24.6m, which sought to account for the risk of procurement and construction cost escalation. This range was underpinned following the detailed design of the hospital and a quantity surveyance of the designs. A range of values was adopted given the uncertainty surrounding the market rates for construction of this scale in Montserrat, where most of the labour, equipment and materials would have to be shipped in.

FCDO was heavily involved in the design and competitive tender processes and bids for the construction. An independent qualified quantity surveyor evaluated the bids and is content that these are reasonable reflections of construction costs for the project. GoM and FCDO agreed a 15% contingency should also be added, which is standard for a capital project of this size and scope. GoM notified the UK that the preferred bid, from CIE, would require an additional £15.3m uplift to CIPREG following the technical evaluation of the tenders. This was approved by FCDO Ministers and HMT in October 2024 and brought the total CIPREG funding to £55.3m.

Although the uplift covered the majority of the items required for the hospital, it only covered a small amount of the Furniture Fittings and Equipment (FFE) needed, which has created a critical gap in the needs of the new hospital and should have been considered in the initial project requirements or picked up at the uplift point. Reflecting back on this and lessons learned will be an important part of the review process, whilst finding the funding to complete critical items to ensure the hospital can be fully operational on time will need strict rationalisation of actual versus nice to have needs.

Some issues with delivery of laundry items for the refurbished Margetson building, were resolved in March 2025, completing this phase of the works for the new hospital build. The building, adjacent to the build site, will house core services including administration, the pharmacy and physiotherapy.

A major move forward was achieved on this project, with the signing of the contract for the hospital build with CIE 24 January 2025. Ground-breaking and construction commenced on 7 April 2025 and has been making great progress.

A key piece in the critical path was completion of the Minor Works Phase 1. This consisted of demolition of buildings no longer needed, earthworks to prepare for the main construction period, installation of the Oxygen Generator plant, the Incinerator, Low voltage facility and Liquified Petroleum Gas (LPG) storage. In a first for Montserrat, the installation of an oxygen generator plant allows supply of oxygen on island, instead of relying on imports.

In parallel to the construction works under CIPREG, health service transformation and the purchase of essential equipment are being supported under the Budget Support programme and Essential Equipment Programme respectively. There is still work ongoing within the health transformation space to determine how staffing levels (including staff training on new equipment before it can be available for service to the public) and wider needs will be met. This will have an impact on the recurrent budget, which will require explicit recognition in future budget discussions as the hospital continues construction.

MoH have transferred over paper records onto a digital Health Information System (HIS) which will be crucial for healthcare management. This electronic medical system for primary and secondary health care, is for general practices at present and hopefully can include private physicians/clinicians in the future, encompassing radiation, laboratory and pharmacy systems and mental health. Montserrat is leading the way in healthcare in the region and working with Guadeloupe to adapt systems to match the needs of healthcare delivery on island.
A long-term healthcare provision strategy is in place which will include free healthcare for children and the vulnerable. Accessibility is a key consideration as required in outcome 3 with the hospital designed for disabled and gender inclusion, through provision of large lifts, separation of wards and separate rooms for vulnerable people. A Community Liaison Officer role has been advertised to bolster community engagement and information to the public about the hospital overall and ensure safeguarding is a top priority.
The pathway to improved healthcare also includes plans for new jobs, 24/7 services in primary health care and GoM are working on an MoU for secondary health care for off-island medivacs, something that also links into work on airport accessibility plans. Working with other hospitals and universities in the future for attachment programmes is being reviewed, along with progress on telemedicine, a key area to consider with DITES, making healthcare sustainable in the longer term. An advanced healthcare offering is envisaged to link into future tourism as tourists are more likely to consider travel to Montserrat more favourable if there are advanced medical facilities on island. Strong healthcare offering could also boost population growth, particularly Montserrat Diaspora.
Governance and delivery for the project has improved markedly since the last review and a testimony to this is the current on-time delivery of the hospital build works, as was clear during the review AR visit. Monthly updates in place through committees have ensured the full range of stakeholders are aware of progress and a strong Project Manager in place to lead the delivery phase brings much added value to the project to keep it on track. The Project Manager has created a hospital build risk register which ensures we are aware of any potential problems before they arise.

The indicator has scored an A – having progressed significantly from the position the project was in during the last AR and as it is on-target for completion by end of March 2027, within budget and with a Project Manager finding cost cutting savings.

Indicator 2.2 considers the work delivered through the Montserrat Land Development Agency, a statutory body of GoM under MALHYEAS, which manages the provision of social housing for Montserrat of around 200 units.

Corrective Maintenance

MLDA is responsible for corrective maintenance, much which is reactive. Most social housing has surpassed its intended lifespan and until corrective maintenance was carried out, in a state of disrepair. Upkeep of these aging units is a burden on GoM, and the waiting list for social housing tenancy still remains long. Rent could not be increased due to the state of disrepair but after EC$1.3m of CIPREG assistance, all 38 target units have been repaired. The rent issue should be revisited to ensure the cost of maintenance of the upgraded and higher quality of units to ensure they do not fall into a state of disrepair. The corrective maintenance outputs also aimed to minimise the health and safety impacts to tenants, ensure that the repairs enable the housing units to be resilient to disaster and climate change and reduce associated liabilities to GoM. Corrective maintenance to the units successfully provided comprehensive future proofing, through replacing corrugated roofing with concrete roofs and PVC worktops that are resistant to termites and structural repairs.

Challenges have been resourcefully overcome including sourcing local labour, with tenants involved in the renovations of their properties. Supply chain and storage issues caused delays particularly for non-standard size hurricane windows. There have also been fluctuations in costs for materials due to the volatile US markets, but the corrective maintenance project came in under budget.

Drummonds New Build

CIPREG Steering Committee approved the funding for construction of two housing units in Drummonds. After design and cost limitations review, this became four one-bedroom apartments. With the funding approved, MLDA were able to relocate the tenants from the area, and earthworks started, earmarked for completion by June 2025. Delays have been caused due to site design reviews, weather and supply shortages.

At the AR visit, we observed that earthworks had been completed and electrics, water, road access, drainage and sewer pipework connection to Drummonds sewage plant were planned or underway. The retaining wall at the back of the site has been completed. Tenders for the project have been opened and the winning bid with timelines identified. The works are due for completion by end of March 2026 a target set for all CIPRG projects except for the hospital.

Through the social housing corrective maintenance and new build projects MLDA have successfully used the social housing study to deliver the outputs overcoming significant obstacles. With the target completion date of the new build within acceptable limits for project delivery and corrective maintenance now complete, the projects will score an A.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

New Logframe milestone indicators were set and agreed for Hospital and Social Housing.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Lessons learned from this year

PMO capacity and outreach has been a challenge. As laid out in the progress section from last year in recommendation 3 below, recruitment has been difficult. Reviewing the terms and conditions for roles to achieve an attractive enough package for prospective candidates may help identify someone for the role. FCDO’s own role in PMO support has been greater than it should be over the year and needs to reduce. Handing back the secretariat role to the PMO team as soon as feasible will be important and enable PMO to own the full range of programme delivery work on island. This is especially important now that the Steering Committee covers a wider remit including the Port and Green Energy programmes as well as CIPREG.

We encouraged the team to make closer links with ministries during the visit and for PMO to give project delivery training including a guidance manual for project delivery, for ministries to refer to. Delivery of this work earlier in the year, would have been beneficial, aiding project delivery and financial planning and establishing a closer working relationship between PMO and other stakeholders. In addition. procurement and project delivery work have been working apart. With the two disciplines closely related, co-location to support each other and boost capacity could have benefitted delivery through cross team cover and consultation. The Head of Procurement has indicated a desire to co-locate with PMO from December this year.

Hospital resourcing concerns have been an issue given delays to issuing of visas for foreign workers. On island capacity ensured the delivery of the project stayed on track, but a review of visa processes to streamline entry for straightforward cases, could be beneficial.

There are recommendations outstanding from last year. This review has assessed progress on those recommendations while adding new recommendations for 2025.

Recommendations from 2024 Review

Recommendation 3 (OP2): The role of a fully staffed PMO should be reviewed to enable more integration across government ministries to deliver on the capacity building, procurement and project support mandate that is required to mitigate risks and improve supply chain risk. Action: FCDO and GoM to consider.

Progress: PMO is still understaffed despite running recruitment rounds for a new Deputy PMO. The Head of PMO is currently off island creating some oversight pressure. PMO has yet to identify the role, structure, needs and skills they can offer to work with all GoM ministries to deliver projects and also set out a standardised PM handbook. PMO have overall awareness of programmes but engagement with ministries on project delivery are not yet in place.

During the Annual Review PMO commented on adequate staffing levels required, the challenges meeting strict CIPREG deadlines compounded by pressures to identify contractors for projects and commence work to meet deadlines, which is impacting PMO efficiency.

Solutions are such as a centralised Gantt chart and a tracking chart for all programmes and to look at what previous PMO and typical PMO’s provide and how they work with Ministries.

Recommendation 4 (OP2): The PMO should analyse the cost benefit case for on island stock of commodity supplies, against existing supply chain issues and cost of experiences delays under CIPREG.
Action: PMO to set out the vision and seek advice from FCDO Economist.

Progress: With the majority of projects closed or already tendered and agreed, this is now less of an issue. The hospital supply chain is the risk and needs to be closely monitored by PMO, to mitigate this, one of their team works from the hospital build site and provides PMO oversight to the team.

Recommendation 5 (OP2): As the Hospital project activity intensifies, the frequency of meetings with FCDO and GOM should increase to allow for early warnings of delays.
Action: FCDO CIPREG Team

Progress: This has been realised with the hospital build in the delivery stage and meetings more frequent. Weekly meetings with CIE and Article 25, now called job-site meetings, took place during the mobilisation phase with FCDO in attendance. Monthly Health Project Committee (HPC) meetings, including FCDO attendance, gave effective oversight of the hospital project delivery. As FCDO also attend month governance meetings receiving updates there, it has been agreed that only Post would attend from December 2025 but bring in the wider FCDO team if required.

Monthly finance meetings with MoFEM have allowed effective finance and funding monitoring. Monthly Programme Board meetings and bi-monthly Steering Committee meetings, latter recently increasing in frequency, provide effective senior governance oversight. FCDO are in regular communication with GOM and PM about the hospital build which allows early awareness of any issues and a chance to mitigate these early.

Recommendation 6 (OP2): As the hospital moves into the main construction phase, GoM and FCDO should be considering a benefits realisation plan and the resource cost implications for the operationalisation of the hospital.

Progress: Ministry of Health have a forward plan for effective use of the new hospital which includes charging, accessibility, use of facilities versus medivac/treatment overseas and how to effectively diagnose and treat patients. The gap in this planning is the costs for some of the furniture, fittings and equipment (FFE) which were not all factored into the original hospital project costs and will need to be covered to ensure that full benefits realisation and costs of operationalising the hospital has been covered. MoFEM are working on funding streams for this.

Recommendations for 2025 Review

Recommendation 3 (OP2): MoH collaborate with PMO to ensure that the digitalisation of healthcare is optimised through sharing of planning and delivery of the Health Information Service (HIS) with stakeholders in other ministries working on digitalisation, such as DITES. Action: MoH, PMO, DITES

Recommendation 4 (OP1/2/3, MEL): PMO to increase collaboration with all Ministries keeping a lessons learned register and upskilling them in project delivery, ensuring that all live programmes work is shared with their office, so progress can be monitored and managed across the lifetime of programmes, with delivery made as effective as possible. Procurement team to co-locate with PMO and teams to collaborate closely and cover any cross-team capacity gaps. PMO to take on programmes’ secretariat work, now that the governance covers multiple projects and programmes. Outreach by PMO to ministries to increase and a guidance manual on project delivery produced and shared with them.
Action: PMO, GoM, Post, CIPREG Team

Recommendation 5 (OP2): As the hospital moves further into delivery phase, the health service transformation plan with the benefits realisation and hospital operationalisation details, should be reviewed and shared within the governance system. Clear pathway for all items needed to deliver the health service transformation plan such as furniture, fittings and equipment (FFE) should be in place. Thought to be given to how processes such as visas, can be streamlined and planned well in advance for external project delivery resources.
Action: MoH, PMO

Recommendation 6 (OP2): MLDA to revisit the rent rates to ensure the cost of future maintenance on the upgraded units is covered and they do not fall into a state of disrepair.
Action: MLDA

Output Title	Enhanced role of private sector in digital connectivity and renewable energy generation to meet future medium to long term needs of Montserrat
Output number:		3	Output Score:	A
Impact weighting (%):		38	Weighting revised since last AR?	[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
3.1 - Adequate digital connectivity to meet future medium to long term needs of Montserrat through laying Fibre Optic Cable and operationalising it.	At completion of third anniversary of project, effectiveness and efficiency reviewed and lessons learned. Continued private sector outreach aiming to attract digital partnerships to island. Work to ensure resilience and availability of connectivity evident	A – DITES reports almost 100% fibre coverage for Montserrat population, achieved through incentivising private sector stakeholders on island (Digicel and Flow). Speeds of up to 150 mbps achieved for all customers on fibre at very low cost (£37 pm). O&M contract in place with Southern Caribbean Fibre for 50 years. Capacity to provide up to 8 terabits of data so inward investment opportunities realistic and being looked at
3.2 - Progress towards geothermal/ renewable energy generation in Montserrat	PPP Agreements completely executed and private sector partner starts implementing renewable energy development works / Surface energy development works completed and renewable energy generated.	A – PPA proved unfeasible in the short-term period which CIPREG will cover, due to high cost of quotes from potential providers. Transition to £5.9m of capital assistance from FCDO in place with additional solar due for installation before the end of FY. Work also in place to maintain and upgrade geothermal facilities for future use (including potentially power for data centres, facilitated by outputs from 3.1 above and mining of critical minerals).

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 3.1 measures progress made towards providing Montserrat with modern and reliable internet services. GoM have implemented a public private partnership agreement with both telecommunications companies (FLOW and Digicel) on the island. The fibre optic cable project, funded under CIPREG to roll out high speed connections across the island, has concluded with a project close out report completed and submitted. The DITES team confirmed that the rollout has resulted in fibre internet for the whole island (quoted almost 100%). The GoM has begun assessing the benefits the high-speed fibre can have for the island, with the new hospital coming online in April 2027, it will be important to assess how it has benefitted from the fibre upgrades. Indications from the hospital projects team is that they have put in place systems to make use of the IT offering, linking patients and records. Commercial is in discussion with possible provision of data centres and land bases for companies to supply internet from being looked at.’ Part of this offering depends on reliable green energy so linking this aim and green energy work, will be important. A key output will be the compilation of a report on the contract mode. Although the outputs have been thought through and the almost 100% coverage of the island for fibre is in place, linking this output to future inward investment strategy will be important and should be assessed at the next AR.

Indicator 3.2 relates to Montserrat’s renewable energy ambitions. In 2012 three geothermal wells were drilled, tested and capped, with the intention of proving the resource and enabling private sector engagement in the development of a geothermal power plant. Since then, one of the wells has failed, no longer being operational. Maintenance works were successful in 2022 and demonstrated a healthy flow rate from the two operating wells. An invitation to tender for development of a Geothermal Power Plant was launched in late 2022 and closed in June 2023. There was one bid. Initial analysis of the bid showed the investment would not sufficiently reduce tariffs to justify the cost of investment – in fact depending on the trajectory of energy demand it may lead to more expensive energy. In 2025, Cabinet reviewed the bid and agreed it was not possible to continue, the initiative was stopped. A green energy initiative for £5.9m was put in place, in which the FCDO funded the expansion of solar and upkeep of geothermal, keeping a focus on green energy.

FCDO funding for maintenance activities for geothermal wells has proved key to the operation of Geothermal and continued viability for future use. The Essential Equipment programme funding of green energy transition has ensured that the milestone indicator of green energy transition has been kept on track. This has provided the pathway to renewable energy planning on island, which currently is focussed on solar, but geothermal is still a key area of future energy generation, operation and maintenance is a key part of the essential activities to ensure the transition planning stays on track. The logframe indicator for this work will need to be reviewed in light of the new transition planning pathway, which is no longer focussed on PPP viability. Given the revised milestone, energy transition plan in place through the Utilities Working Group and completion of the CIPREG programme funded work on geothermal upkeep, which is as expected, the output indicator has scored an A met expectations. But key to the next AR will be a review of the milestone, removal of PPP and focus on benefits realisation planning for green energy through keeping geothermal online including securing potential critical minerals for income generation.

The FCDO-funded mission from the Department of Energy and Net Zero in May 2025 recommended outlining a medium-term programme to increase the provision and efficiency of solar. This has resulted in the formation of the Utilities Working Group and a £5.9m funding injection for this green energy transition work. Great progress has been made over the course of the reporting period with solar on track to be expanded over the course of the rest of this Financial Year and geothermal maintenance a key area for the programme. Ultimately, the green energy transition pathway should allow GoM to reduce spend on diesel fuel, which can instead be channelled towards network improvements.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

These remain the same. The role of the private sector in digital connectivity has been very much focussed on internet providers and for the upcoming AR an update of planning on wider private sector involvement will be important, including a milestone in the logframe to identify potential opportunities considering wider programme work such as green energy.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Previous Recommendations:

Recommendation 7 (OP3): GoM to undertake analysis of the most cost-effective ways to decarbonise the system (e.g. medium-large scale wind and or/solar and battery vs geothermal). This can then inform any business case and funding requests for capital investment by the UK or to help leverage funding from the private sector.
Progress: The formation of the UWG and the funding of £5.9 towards greening energy transition and dramatically increased the work on solar and geothermal provision, with Montserrat on target to increase its green energy provision by another (20%) before the end of March 2026. The challenge will be delivery and use of the full finding before time runs out at the end of the FY.

Recommendation 8 (OP3): In relation to the geothermal proposition, 2023 Recommendation 6 (OP3) from last year should be actioned to further the overall transition case for energy against the planned opportunities that will realise the wider economic proposition. The output of these can then inform any business case and funding requests for capital investment by the UK or to help leverage funding from the private sector.
Progress: UWG has taken on support work for geothermal, with a budget to maintain the remaining wells and provide replacement equipment. An energy transition pathway is in place facilitated by the UWG work and will be reviewed in the next AR period.

Recommendations:

Recommendation 7 (OP3): GoM to identify opportunities for private sector investment outside of internet providers, for the digital offering on island. Close liaison with hospital IT team is recommended to ensure any telemedicine or IT technology driven opportunities are fully realised. As geothermal pathway and implementation become clearer, opportunities this might present for energy/mineral use/IT benefits should be analysed e.g. opportunities for data centres. Report on the outstanding contract model should be completed as soon as possible.
Action: GoM, PMO

Recommendation 8 (OP3): As the programme comes to a close for most projects, economic benefits of CIPREG outcomes should be considered in the context of IT and green energy outputs to ensure maximum benefits, For example potential uses of green energy and IT, hospital digitalisation and fibre connectivity. These can then inform future inward investment opportunities and maximise CIPREG programme output usage.
Action: GoM, PMO

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

This year’s main risk factors have been labour, and capacity shortages, supply chain risks and the volatile US market. Montserrat has labour and capacity shortages for skilled workers, and this drives a need to recruit foreign labourers, which takes time and extra money required for funding visas, as was the case for the hospital build.

Due to being a small island, supplies are limited or not available, but when they do arrive on island work is generally completed promptly. However, getting supplies to the island in the first place has caused delays, including for works on the Air Traffic Control Centre and Drummonds New Build, Social Housing. Most suppliers will be engaging with the island for the first time and local contractors often lack the capability to engage with international suppliers of materials. Delays from inputs can create further knock-on effects. For example, the delay for worktops and contractor failures at MSS which led to significant delays and extra costs. The delay in procuring the new airport lift tower and timing for the company to fit it, causing operationalisation delays. Island space for storage if items were to be procured early is also an issue and then purchasing later sees price hikes due to market pricing increases.

VfM performance compared to the original VfM proposition in the business case

Economy:
Ministries have generally demonstrated a good control of costs of inputs at a project level and stayed largely within budget allocations, this control was envisaged to be led by PMO and will need to be revisited for the upcoming year. Working alongside FCDO Project Manager in post and hospital Project Manager, large projects are run through the procurements department and have dedicated cost engineers/quantity surveyors, to ensure costs remain on track or have been delivered and in the case of all but 4 projects, closed effectively. There have been significant challenges around financial reporting, partly due to capacity constraints within the PMO and partly due to slow reporting from ministries having a knock-on effect with MoFEM calculations. However, things have been improving over the review period with three claims so far and a fourth claim forecast for December, which will see the full use of the CIPREG allocation.

With most projects closed or tender amounts agreed for the remaining ones, further economy improvements will likely be limited to the hospital build, where the PM has already made significant savings to bolster the contingency reserve. Obtaining bulk stock will continue to be looked at to help with economies of scale but as most activities including supplies, have been programmed in, this is likely to be limited and only possible if FCDO can identify a funding allocation before the end of this FY, to cover these costs.

Efficiency:
The programme is generally efficiently converting inputs into outputs as envisioned in the original business case – with most projects completed within financial allocations, or on target for completion by March 2026, except for the hospital build due for completion by end of March 2027. After securing no bids within the £2M earmarked for the Parliament Building to house the Legislative Assembly, refurbishment of the Cultural Centre has now been agreed and contractors for the majority of the work secured. However, time is tight to complete the project within the remaining window of end of March 2026 and there is a risk of overrun with consequential impact on GoM to find any remaining funding outside of the CIPREG programme.

It has also been encouraging to see projects of concern at last year’s review, getting back on track or completed, specifically, MSS, the Air Traffic Control Tower and the Cultural Centre. Reflecting the hard work that the respective ministries/PMO have put into these projects to complete or deliver them during this Financial Year.

Effectiveness:
The programme’s intended outcome is resilient economic growth, with well-maintained infrastructure operating in Montserrat. To the extent that it can be, this is being effectively delivered. Projects have mostly been completed as planned; the rest scheduled to close at the end of this FY, with the exception of the hospital. This has put the infrastructure envisaged in place, but only recently, so how effective this has been, is something to review at the next AR. What will be key to the effectiveness is O&M planning and implementation, which should be assessed at this point.

Future potential investment should ideally tie into CIPREG outputs to ensure maximum utility and effectiveness. For example, through improved access to the island (airport, roads, port) and complete delivery of the clear road map to long term sustainable energy transition being led by the Utilities Working Group.

However, now that the majority of the projects have come to a close, it will be important that sufficient funding is identified from recurrent sources, to ensure they remain in good shape and operational, this is likely to include the charging for facilities use. Also, proper long-term road maps for improvements will add to the effectiveness of the outputs from CIPREG (a long-term road improvements plan for example).

Equity:
The project’s equity is potentially the least changed from the original proposition, as the needs of diverse communities have been built into the design codes of projects. Under the school buildings project, disabled access was built into the toilet blocks and fencing for the school has been included to address gender safeguarding and physical security. The new hospital design is guided by UK HBN guidance and regional building codes and has made provision for needs of more vulnerable patients. This will include safe space for mental health needs of patients, and adaptation of wards for safeguarding purposes. The hospital will have a birthing ward and a mammography suite (with the mammography unit being funded through the Improving Essential Equipment for Aided Overseas Territories Programme). Provisioning has been made available to meet disabled access needs. The refurbishment of the Cultural Centre, although a recent addition, considered this dimension, with disabled access a key focus of the design and upgrade.

Overall Cost Effectiveness:
The original aims of the programme demonstrated a clear pathway to economic growth and increased prosperity through infrastructure upgrades. This is still the case but with the addition of a social development dimension, this may be seen as a drag on cost effectiveness. Looking at the overall impact this has, the cost effectiveness remains strong. Meetings with the Health Ministry clearly demonstrated how a significantly upgraded health provision is beneficial to the population of Montserrat and income generating opportunities, such as tourism, employee wellbeing and inward investment. Additionally, the social housing upgrades have improved the quality of the housing units and lives of tenants, making them more resilient to hurricanes and pests, a valuable benefit.

Overall, the programme is cost effective, more so now that some projects have closed and we know the actual costs to CIPREG. The challenge will be longevity of the capital investments which will depend on robust O&M plans and effective equipment use. It will also be important to consider how the outputs can add maximum VfM to any future planned infrastructure programmes to ensure they deliver the maximum benefits. Governance has played an important part in overall cost effectiveness, with the Steering Committee updated on all projects progress, issues and costs, and agreeing any variances and cost implications.

Assessment of whether the programme continues to represent value for money

This year has seen a lot of progress for CIPREG. With many of the projects now completed, the potential for unforeseen costs is limited to four projects, all of which have agreed budgets so this is unlikely. Completed projects stuck to budgets agreed and generally, produced the outputs envisaged, all in all demonstrating that the programme continues to represent value for money. The remaining projects are on track for completion as planned and a clear understanding of how they will benefit Montserrat, through social and economic development, demonstrates why this is VfM. Importantly, the programme is keeping within the allocated budget, showing that it is performing as expected and good VfM. The counterintuitive to this if the project were to be stopped, is the prospect of half completed infrastructure, which would fail to fulfil the CIPREG strategy and take away tourism, health and inward investment benefits and prove very costly in the long run.

E: RISK [½ to 1 page]

Overview of risk management

The overall risk rating for the programme remains major since the last Annual Review (AR) in December 2024. The risks were reviewed on a monthly basis during the last six months of the review period and remain relevant in the current circumstances. Mitigations have been identified for each risk.

Government of Montserrat approach to risk management

The Permanent Secretary (PS) for each Ministry is the Senior Responsible Officer (SRO)/Accounting Officer, responsible for risk registers under their Ministries own project within CIPREG, and for notifying the Programme Board of any changes, which are then passed up to the Steering Committee where required. Programme Board is usually monthly and Steering Committee bi-monthly, where Accounting Officers submit a paper for information or decision and can also submit a presentation, where risks and mitigation are included, enabling mitigation or escalation where needed and giving FCDO oversight on this.

FCDO approach to risk management

The programme team continue to ensure that the internal FCDO risk register is updated monthly at present whilst in the delivery phase of the hospital. Risks are then flagged to seniors to update the departmental risk register if required.

With the closure of many of the projects under CIPREG, the main major risk relates to timeframes for completion of the Hospital, Cultural Centre and Drummonds projects. The majority of the ongoing risk is related to the hospital, where the design and build is complex. Scrutinisation of the hospital build and financial figures continues moving forward. The risk remains major given the significant initial delay to the project, the challenging two-year timeframe to complete the build and potential for unforeseen costing variations. PM, GoM and FCDO work tightly together to mitigate any issues.

Although many projects have closed, the remaining ones are set to sight timeframes and we do not have sight of O&M planning so the overall main trends in risk continue to be GoM delays in finalising projects within CIPREG, and an inconsistent approach to O&M. The current CIPREG programme ends in March 2027, but this date is set for the hospital, and all other projects were due for completion by end of March 2025. This has been extended to end of March 2026. However, there remains a live risk that the Cultural Centre refurbishment and Drummonds new build, will not complete by this FY. As recommended last year, as part of the Programme Completion Review (PCR) for each project, the lessons learned / recommendations should be looked at in detail to avoid these delays happening again for the continuing projects and any successor to CIPREG.

Staffing

Since January 2025, the FCDO Montserrat team have been fully staffed, working alongside a Head of Programmes and Programme Manager in Montserrat, however there are still gaps within the wider FCDO team, such as in the Education and Health advisory roles.

The Project Management Office (PMO) based in Montserrat remains understaffed and a key risk to effective programme delivery. There is a need for a Deputy PMO so that the full range of PMO duties, some of which are covered by the FCDO team, can be re-instated. Recruitment for this position is underway. The Head of PMO has been in position for a year but is currently working remotely, posing a potential oversight risk. However, a new Project Manager has been recruited, working alongside the existing Project Officer and increasing the staff complement from two at the last review, to three.

Safeguarding

Safeguarding within the CIPREG programme is a major risk, especially awareness of codes of conduct for workers. To mitigate this, MoH, along with help from FCDO, created an induction handbook to give to new staff on the hospital build, our major employment project, when they begin training. This will need to be translated into different languages, so it can be clearly understood. A similar handbook will be used for the workers on the port project. Safeguarding cases continue to be potentially underreported within Montserrat with few cases raised. However, with a new Safeguarding Manager in FCDO and a new Safeguarding Lead on island, , capacity for oversight has improved. Coupled with this, mitigation is in place through the Safeguarding Board which has held 2 meetings this year and is set to continue, jointly chaired by the Commissioner of Police and Acting PS of Ministry of Health. The new GoM has also brought a tangible shift in political will to tackle embedded safeguarding challenges. Evidence of this is already apparent in willingness to have challenging conversations and public ministerial support for the joint Safeguarding Board, and clear codes of conduct, established reporting channels and SEAH awareness building for construction staff. Conversations will continue with GoM on how the CAPSEAH approach can support tackling SEAH across government, where improvements are expected to have a direct impact on safeguarding within current and future CIPREG programmes.

Recommendations

Recommendation 9 (Risk): GoM Senior Responsible Officers to present detailed risk analysis at both the monthly Programme Board and bimonthly Steering Committee using the agreed format. GoM Steering Committee Officers should also submit quarterly risk registers to FCDO using the pre agreed format to better facilitate escalation usage.
Action: GoM, SROs

Recommendation 10 (Risk): A revision to the logframe and review of the theory of change should be undertaken within 3 months of this annual review including factoring in the underlying assumptions for improved economic development now that the majority of projects have been completed and factoring changes for the key hospital build focus. FCDO internal Risk Register to continue to be updated monthly and as required.
Action: FCDO CIPREG Team

Recommendation 11 (Risk): Safeguarding Board to continue meeting regularly and FCDO safeguarding lead to advise FCDO of any risks to input into Risk Register. Board has authority to set up subgroups as required to drive tangible action as needed on emerging concerns.
Action: GoM, Safeguarding Team
Recommendation 12 (Risk): MoH PS, CLO and PM to continue to deliver safeguarding and induction training for new workers.
Action: MoH PS and PM
Recommendation 13 (Risk): New OTPD Safeguarding Lead should conduct visit to Montserrat in 2026 to continue the important work on safeguarding and help deliver training sessions for any new workers on Island.
Action: MoH PS and FCDO Safeguarding Team
Recommendation 14 (Risk): New FCDO Safeguarding Lead to work closely with Deputy Governor’s Office to support development of CAPSEAH approach.
Action: DG and FCDO Safeguarding Lead

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Financial management

The CIPREG programme has been formally extended to March 2027 and given a £15.3m uplift in funding for the new national hospital with a new total of the programme it £55.3 million. The hospital build is underway and on target for completion within the CIPREG programme period which was an area of key concern during the last AR and is a very big positive step up for the performance of the programme. Keeping the spend on track and variations to a minimum will be key for the performance of the programme over the next reporting period, especially as it is envisaged that the hospital will be the main area of CIPREG work over the next AR period.

The PMO had previously been overseeing the management of the CIPREG Programme and demonstrated effective management of the programme. However, the department has faced several challenges, including the departure of the former Head of the PMO in early 2024, leaving the Deputy to manage the department independently. This resulted in significant workload pressures. A new head of the PMO was appointed in October 2024, but the deputy then resigned and the head of PMO has been working remotely for several months with return date to Montserrat yet to be confirmed. The team now has a project manager in place to help with the workload, but the DPMO position remains unfilled. Without this position, PMO are struggling to cover the full bandwidth of duties, with FCDO covering Secretariat roles for this programme. The DPMO position has been re-advertised and interviews have taken place, so it is hoped that the office will be fully staffed and able to take on the full range of duties in the near future. This including more regular liaison with ministries on project delivery work and related training, going forward.

Programme monitoring is conducted collaboratively by the GoM and the FCDO. The Programme Officer in the Governor’s Office, the Head of the PMO, and the Senior Responsible Officers (SROs) for each project carry out regular site visits. The Programme Officer compiles and issues monitoring reports to FCDO colleagues. A new project delivery trainee has been recruited by the Governor’s Office and it is anticipated that they will start shortly, taking on some of the project delivery work for CIPREG, although not specifically working on this programme. Additionally, each SRO provides monthly updates to the Programme Board, helping to track the status of individual projects.

The Infrastructure Adviser has visited Montserrat and the Programme Responsible Owner (PRO) for CIPREG made two visits during this reporting year. These visits primarily involved meetings with stakeholders within the Government of Montserrat (GoM) and other HMG staff, but they did not include direct engagement with beneficiaries which will be a key part of the next review given the anticipated completion of all projects except the hospital within the next reporting period.

With projects closing, the need for reporting has reduced. The remaining projects, the hospital build, cultural centre renovation, air traffic control tower and Drummonds new build are at key decision points, and the governance system has had to adapt to a more agile model to ensure quick decisions can be made on project scope to ensure delivery on time. On financial management, more regular discussions regarding costing and funding have been taking place to ensure that allocated funds for the programme are spent as anticipated. Budgetary reports are received on a regular basis and with fewer projects have become easier to track. Co-ordination of budget information from ministries would be beneficial and ideally sit with the PMO, who could ensure the timely submissions of all reports and documentation.

UK Monitoring

The UK based Project Officer manages forecasting. The forecasting is aligned to GoM projections when received, this is essential for FCDO to ensure the project is compliant and the spend forecasts at the GoM and FCDO ends are the same. MoFEM projections and estimates are received more frequently now and the continuation of this, will be key to managing the project to the end of its anticipated lifetime. FCDO has engaged more frequently with MOFEM over the reporting period and collaborate effectively on funding delivery, with more frequent meetings after a pause due to lack of staff in FCDO and PMO. Lately CIPREG has looked to a financial model to allow advance payments, this is to help with liquidity at the GoM end and has the benefit of helping to ensure the CIPREG allocation is fully spent. Overall, spending of allocated funds has improved during the reporting period, which is crucial to having the available funding during the programme lifetime, to cover the projected costs. Delays to the programme in previous years have resulted in underspends which has put pressure on funding in these latter years, currently CIPREG funding is not enough to cover all projected spending due to these delays in spend in earlier years.

Procurement

Procurement processes, which were recognised as strong in the last review period have been improved over the course of this review period. This includes the introduction of procurement law in October 2025 and the development of a procurement manual for all stakeholders. All procurements must go through a central system. A database to manage this and all variation proposals, is close to completion. The Government Procurement Services team have been working on increasing their compliment by three and hope to have this in place in the New Year, providing much needed support for procurement work. It is envisaged that the new team will be co-located with the PMO team, providing potential for working across the two separate disciplines in future. Procurement over the course of the review has worked well and the completion of projects and on time delivery of the hospital build is testimony to this.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

The Monitoring and Evaluation (M&E) of progress and results for CIPREG is guided by the OTPD Monitoring and Evaluation Framework. M&E is measured through the Logframe and ongoing meetings and regular project visits.

CIPREG is governed through Project, Programme and Portfolio level committees. Different project committees are in place with the Project Delivery Committee, Health Project Committee (HPC) and the Strategic Portfolio Programme Board (SPPB). The Programme Board (PB) meets monthly with FCDO Programme Manager as Secretariat. The bi-monthly Steering Committee (SC) has the FCDO Programme Officer as Secretariat. These are all governed by the Montserrat Cabinet. The Ministries have their own meetings, and the hospital have regular meetings including the job site meeting with the contractor CIE and architectural NGO Article 25.

The FCDO team continue to have regular engagement with the Governor and the Governor’s Office to support effective monitoring and evaluation of the programme. This engagement has increased since having a full FCDO UK programme team in place. The Head of Programmes and Programme Manager in the Governor’s Office play a key role in monitoring on the ground and regularly conduct site visits. The UK team visit Montserrat regularly, including the CIPREG annual review in November 2025 and Budget Support visits in 2025 to discuss programme matters and perform monitoring site visits.

The technical officers, hospital project manager and PMO provide a comprehensive report on each of their projects on progress, finances, risks and lessons learned for each monthly programme board and bi-monthly Steering Committee.

This Annual review has been conducted with the support of the GoM Ministries, PMO and Governor’s Office, which factor in the progress and challenges of each project and lessons learned, including responding to queries on milestone achievements, successes and challenges and lessons learned on completion of projects. This year there have been three visits to CIPREG projects by the UK FCDO team in this reporting period, including this review in November 2025, and as part of other programme reviews (for the Budget Support Mission in February 2025 and Mid-Year Review in July 2025), when the Head of Department visited.

Evidence

The merits of the programme are clear although have changed and evolved over time, but evidence for the wider economic impact of individual infrastructure projects (at the scale seen in CIPREG) is difficult to produce. CIPREG, as referenced before, is predicated on the delivery of critical infrastructure and economic growth for Montserrat.

GoM and technical consultants have been engaged with in the production of CIPREG output and outcome planning, clearly indicating the needs of Montserrat, providing good evidence for CIPREG and any future programmes.
Learning

The PMO previously maintained a comprehensive lessons learned register, as well as producing project close-out reports to indicate areas of success and challenge in the delivery of projects (however these were lost in the takeover transaction, and there is need for PMO to restart these). The key lessons learned are reflected in this annual review and since the last review, there has been more engagement on lessons learned through regular discussion with Post/FCDO/GoM sharing critical information about delivery.

With projects closing within the programme we are able to see the immediate effects of outputs and outcomes. It will be important to take the lessons learned from these and use them in planning for future programmes, thus ensuring their maximum efficiency.

Date of last narrative financial report	October 2025	Date of last audited annual statement	August 2023

Annex A: PIP REVIEW

CIPREG PIP TRACKING REGISTER
Detail	Action	Current position
a) The OTPD Infrastructure Adviser works with the PMO and Government of Montserrat Accounting Officers to reassert the theory of change and clearly define the assumptions needed at this stage of the programme to its completion including an explicit common understanding of where assumptions rest (i.e. with GoM and those with FCDO / other supporting actors). Action here would align with the Annual Review recommendations 1, 2, 10 and 11.	Infrastructure Adviser	Tying in with AR Recommendation (OP1) is O&M to see if GO could advocate a centralised O&M management system within MOFEM. Currently underway, need to have a copy of any backlog list from GoM.
b) Secondly, an outward multiyear vision for Montserrat should be developed to produce points (i) – (iv) below. As part of that, support from the Governor’s office to the GoM would be helpful - particularly where there is a GoM lead on CIPREG assumptions. Action here will assist with Annual Review recommendations 7 and 8.	Governor’s Office and GoM	Progressing well. Energy transitioning planning is being managed by the UWG formed during the AR period and progressing well. Tourism future vison has been considered and being developed.
i) A visible economic plan with quantifiable elements (e.g. tourism, energy) with the intention of attracting inward investment. As part of that, the CIPREG Infrastructure and Economic Advisors would be pleased to assist the Energy Ministry to work through a multi-year Energy Transition plan. / ii) Conducive policies to attract business. / iii) Access planning and development. / iv) Whilst recognising local resource constraints, encourage the PMO to optimise on island procurement and project management capability within a PMO vision.	CIPREG Infrastructure and Economic Advisors	Energy Transition planning in place through work of UWG. Procurement phase for most projects now completed and procurement now stronger with head on island from December and procurement law in place. Work on flight, sea and night operations work helping with access plans.
4) In relation to project delays and timely project reporting. Whilst little can be done about the impact of past delays, we can however drive and improve project scrutiny with the intention of reassuring stakeholders of current trajectories whilst deepening the centrally held knowledge around downstream risk. Action here will speak in part to Annual Review recommendations 3,4,5 and 6.	Action listed in I-VI below	Fully staffed PMO key, recruitment rounds have taken place for DPMO and now team numbers increased to 3. Project delivery driven through governance process with all but 4 closed and those not closed on track for delivery as anticipated under new timeframes.
a) The work that the FS has done to agree reasonable autonomy for variation needs in respect of the hospital has helped. The final model (dependant on effectiveness) could inform other CIPREG or future infrastructure programming.	No further action	N/A
We propose that to improve overall project monitoring: / i) a standardised Gannt chart is developed and maintained for each sub project to its completion / ii) PMO to aggregate each Gannt chart and supply to the Montserrat Team Leader / PRO in advance of preparing an advice note to the regular CIPREG Steering committee meetings. / iii) We propose that the Montserrat Team Leader plans for centrally based staff (particularly Infrastructure and Economic Advisers) to visit Montserrat and include within that plan ask for advisers to actively monitor progress of specific sites and (where relevant) assist ministries and / or the PMO in areas that may be a challenge.	Local Project leads working with PMO / PMO / Montserrat Team Leader to propose 2025/26 plan by 31 March 2025	Timeframe documentation in place for all remaining projects. Active monitoring by FCDO thought visits by PRO, Economic and Infrastructure adviser as well as Head of Caribbean Team.
iv) The Governor’s office has a representative of sufficient knowledge, able to personally monitor sites each week on a specific day and to report to the Infrastructure Adviser and CIPREG PRO. That person should deliver a weekly report of observed progress. In addition to that report, the representative should be supported by the UK based Infrastructure adviser and be able to relay visual site information via cell / video phone directly in real time. To support this, we see that CIPREG should make provision for a timebound programme funded role, grade to be decided based on level of need, covering from April 2025 to the end of the programme.	Governor’s Office / Montserrat Team Leader	GO completing field visits two weekly and sending reports to FCDO. As a result of majority of project completions and project managers for all remaining projects, the additional resource was not necessary.
Building on the above, to ensure capability and knowledge is maintained after the completion of the programme, a resourcing model needs to be implemented to sustainably transition operations within key infrastructure facilities over to business as usual. Examples would be Health and Education staffing.	Government of Montserrat with support from Governor’s office	Longer term vision for healthcare articulates this and MSS are managing the upgraded facilities now completed at their facility.
Specifically on access – CIPREG would apply a formalised link with the UKCIF team to receive relevant risk updates with a view to reflecting that within the Theory of Change progress on its access assumptions.	CIPREG PRO to engage with relevant UKCIF team on Port updates.	Governance process now includes Port and UWG programmes ensuring a view of the wider picture for UKCIF and energy transition work.