## Annual Review

Title: Supporting the Africa-led Movement to End FGM: Phase II
Programme Value £ (full life): £35.5m		Review date: 06/06/2025
Programme Code: 204768	AMP start date: 06/02/2019	AMP end date: / 30/09/2026

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	B	A	A	B	A	A+
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-1-204768 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006381.xlsx

# A. SUMMARY AND OVERVIEW

Description of programme

The UK is providing up to £35.5 million over seven years for a second phase of support to the Africa-led Movement to End Female Genital Mutilation programme[1] (2019-2027). Building on the foundations of Phase I (2013-2018)[2], this programme focuses on accelerating the pace of change and achieving results at scale to contribute to a world free of FGM by 2030. The programme is working intensively in four countries with high prevalence rates (Kenya, Ethiopia, Senegal and Somalia (specifically Somaliland)), as well as supporting efforts towards abandonment across 18 countries through the UNFPA/UNICEF Joint Programme on the Elimination of FGM (UNJP).
[1] The practice is known as Female Genital Mutilation (FGM), Female Genital Cutting (FGC) and (with decreasing usage) female ‘circumcision’. In this annual review we use the term FGM, to reflect the extreme harm done by the practice and the fact that it violates girls’ and women’s human rights and bodily integrity. FGM is also the term used in international negotiations. The term ‘cutting’ is used to reflect understanding that the practice is not carried out with the intention of harming girls but because in communities where it is practiced, they cannot be married – and would therefore be isolated and stigmatised - without it. The term is not intended to question that it is an extremely harmful practice; we respect this position, but we do not use it in this annual review. Practising communities all have their own words for the practice.
[2] https://devtracker.dfid.gov.uk/projects/GB-1-203024

The programme aims to change social norms and behaviours so that FGM is no longer considered necessary or desirable by communities. Fundamental to this is a shift in gender relations and how women and girls are valued in their communities and societies. The evidence, including learning from Phase I, shows that a “multi-pronged” approach is needed to bring about this change in social attitudes and norms. The programme is therefore implemented through three complementary and mutually reinforcing components:

Supporting and building the capacity of The Girl Generation-Africa-led movement (TGG-ALM) to end FGM at multiple levels and at scale. This component is delivered by a six-member consortium led by Options, whose consortium partners[3] are largely based in or have extensive networks in Africa. Operating in Kenya, Senegal, Ethiopia and Somaliland, it aims to: deliver interventions to change attitudes and practices by working directly with communities; use advocacy to encourage leaders to prioritise ending FGM; support grassroots activists and youth initiatives with small grants to lead change within their communities and hold governments to account; and integrate efforts to end FGM into existing development programmes to reinforce ending FGM efforts at scale.
[3] Consortia partners: Orchid Project, ActionAid, AMREF Health Africa, Africa Coordination Centre for Abandonment of FGM (ACAAF) and University of Plymouth

Strengthening laws, policies and systems to work effectively to end FGM through partnering with the UNJP, which is working in 18 countries in Africa. Prior to this review period, the programme has also supported WHO to strengthen healthcare systems and support doctors, midwives and nurses to help end FGM and care for survivors.

Generating the right data and evidence to guide interventions and measure change under a component led by the Population Council, working closely with partners and the UNJP.

TGG-ALM is entering its final full year, which focuses on scaling programme interventions (by encouraging other actors to adapt and take up programme approaches), synthesising and disseminating learning and evidence, and closing out direct implementation with a strong focus on ensuring sustainability of progress, taking a phased approach across countries (direct implementation of key activities ends between August – December 2025 depending on the country/workstream).

Summary supporting narrative for the overall score in this review

The programme scores A+ for this annual review (1 April 2024 to 31 March 2025).

Changing attitudes towards FGM
This year, the Girl Generation: Support to the Africa-led Movement to End FGM programme (TGG-ALM) achieved Proof of Concept (POC) for its girl-centred, multi-level, locally-driven model to accelerate positive shifts in attitudes towards ending FGM in Senegal, Somaliland and Ethiopia, following almost three years of design, implementation, learning, and adapting the model. The programme ran robust, inclusive Proof of Concept assessments, drawing on a range of data sources including stakeholder feedback and programme MEL data.

Overall, qualitative evidence and stakeholder feedback for the model’s effectiveness and relevance was largely positive. Proof of Concept assessments in all three geographies show that the programme has delivered complementary interventions at multiple levels of society that:
- empower and inform girls about FGM within a broader context of rights and ending gender-based violence;
- have resulted in positive changes in attitudes towards ending FGM among multiple target groups (parents, community/religious/traditional leaders, health workers etc.);
- integrate FGM into pre-clinical service university curricula and healthcare delivery;
- generate learning, evidence, and global goods (e.g. tools and resources that can be adopted/adapted by others working in the sector); and
- are locally-led, and strengthen local organisations and networks to end FGM.

Proof of Concept is considered achieved in all remaining three contexts (POC was achieved in Kenya in Y3). Promising approaches for shifting attitudes have been developed, interventions are valued and relevant to communities, and plausible avenues for sustainability exist.

Although there have been positive shifts in attitudes among many target groups, significant challenges remain for the abandonment of FGM. As support for ending FGM grows, FGM-related behaviours can become more secretive, and the way in which FGM takes place changes (e.g. cross-border FGM, medicalisation, shifts to different types of FGM, performing FGM on younger girls). It has been quicker to change knowledge and attitudes towards FGM, while underlying beliefs are much harder to change. This reinforces the need for ongoing, locally-led norm-changing dialogues that consistently address the deeper drivers of FGM.

Support for local organisations to end FGM
This year, the programme provided further targeted support and capacity building to activists and grassroots African organisations who are leading change from within their communities. The ALM grantee mechanism became operational in 2022 and has disbursed over £1.6m to 82 grantee organisations across the four geographies. Grantee partners have improved institutional capacity in areas such as governance and leadership, finance and procurement and programme management.

Integrating end-FGM work into health systems
In TGG-ALM integration is a structured process of integrating FGM prevention and care into existing health interventions and systems, including into education for pre-service health professionals, and within an existing health facility in Kenya. The integration workstream has achieved all targets this year, with over 1,300 students trained across all four geographies, resulting in increased confidence and knowledge to prevent and respond to FGM. A highlight was the Model Health Facility (MHF) in Narok, Kenya, which became fully functional in Y4 and served over 2,000 women and girls with specialised FGM-related care, integrated into the health facility’s service delivery points. The MHF also supported household visits and community outreach engagements to prevent FGM and enable referrals.

The MHF is a Level 4 public health facility, which is principally financed by the government. The FCDO funding has supported setting up of a “skills lab” for students, training of Health Care Workers, FGM data collection tools, a Clinical Support Officer to support students on placements and community outreach activities. Healthcare workers are trained at the facility on FGM prevention, care and response using the standardised end FGM curriculum that was developed as part of the TGG-ALM programme. During the programme field visit to Kenya, FCDO learned that the FGM medical curriculum (developed by the University of Nairobi), which mainstreamed education about FGM, was being translated into French and shared with Senegal. FCDO were impressed with the MHF, with clear end-FGM posters and messaging on display, and the acute awareness of sensitive approach needed among the trainees when caring for survivors of FGM.

Communication, Advocacy and Movement-Building
Implementation of the Communications, Advocacy and Movement Building (CAMB) Strategy has continued to amplify and strengthen the end FGM movement at all levels. Highlights from the year include:
14 activists were supported to amplify their voices: youth activists and survivors participated in various national, regional, and global events/platforms such as the Women of the World (WOW) festival, the International Confederation of Midwives 2024 in Kigali, the Kenya Midwives Association (MAK) Conference and the CSW event in New York.
TGG-ALM made a significant contribution to at least ten policy/legal advances, including approval of Somaliland’s first national anti FGM policy, drafts of County-level end FGM policies in Isiolo and Garissa, and a cross-border commitment among regional governors to strengthen monitoring and collaboration in Senegal.
34 stories catalysed by TGG-ALM featured in media platforms, ranging from local radio talk shows to global news platforms.
TGG-ALM conducted a Training of Trainers for the Survivors Leadership Initiative (SLI), for 20 survivors to strengthen their capacity to cascade SLI and integrate its approaches into their work. Of these, three survivor-led organisations have been awarded SLI grants to support roll-out of SLI-related activities.

Learning and evidence
Generating learning and evidence for future policymakers and implementers is a key part of the programme. The Population Council has been leading the FGM Data Hub, which collates data, develops practical monitoring and evaluation tools, and provides technical assistance to inform the TGG-ALM programme. In Y4, key achievements revolved around product uptake and the use of the programme dashboard by TGG-ALM partners. During the reporting period, all TGG-ALM partners began to engage with the dashboard. Over the last year, Population Council documented or tracked 11 instances of their products serving a purpose in the field, slightly exceeding expectations. For example, Population Council received requests from funders such as UNJP, GIZ and Norwegian Church Aid for their grantees to participate in the Pop Council’s Evidence and Learning Forum to sensitise them to innovative tools developed by the FGM Data Hub. For five specific products citations grew from 21 to 46 citations in Y4 – a 119% increase. There were further instances of influence and uptake, including through acknowledgement of the Hub’s evidence in influential and popular publications in the field; requests for delivering presentations before international, scientific audiences at conferences; and stakeholders requesting technical support to use tools developed by the Hub.

Overall, the UNJP showed progress in 2024, meeting or surpassing most targets on strengthening accountability mechanisms, increasing national and local capacity for the development of costed national action plans, developing a framework to end medicalisation of FGM and improving the quality of FGM services in the UNJP’s interventions. There was a significant underperformance in the target to support women and girls who have received legal services.

The FCDO was impressed by the quality of UNJP’s work observed on a field visit to Djibouti in October 2024. FCDO observed expertise, experience and commitment of the local/regional UNJP staff which proved to be a real asset during community engagement. The programme had strong links with local NGOs, religious leaders and community leaders. The programme is working in a challenging environment in several countries of the 18 it is working with, marked by growing opposition to anti-FGM laws and policies, which will require continued focus and attention in 2025. Through the field visit, FCDO noticed that backlash and rollback occur at community level, and can be threatening towards those working on the frontlines. UNJP should consider how to support survivors and activists at the community level.

The FCDO also conducted a field visit to observe TGG-ALM work in Kenya in February 2025. The team observed the multi-layer and cross-sectoral approaches used across the programme. The strong ownership by the various stakeholders (girls, mothers, community leaders, religious leaders, grantee partners) was evident. The localisation approach was clearly embedded into the interventions. The Model Health Facility (MHF) was a particular highlight of the visit (see below). There was also a strong political will from the Narok Country Government for the MHF Facility.

Major lessons and recommendations for the year ahead

Recommendation 1: Dissemination of knowledge products and global goods: TGG-ALM has generated a large body of resources for social and behaviour change, as well as significant practical, operational, and technical learning. In its final phase, the programme (including all partners) should prioritise distilling these insights into accessible global goods, ensuring timely delivery through adequate planning and mitigation of challenges, that they are inclusive (e.g. translated into relevant languages, accessible to those with disabilities) and widely distributed through various channels including prominent international fora. This builds on last year’s recommendation which was achieved (TGG-ALM to share an updated Dissemination Strategy with FCDO by end-July 2025).

Recommendation 2: Influencing potential scale partners: TGG-ALM should prioritise engagement with partners with the potential to scale up proven interventions. Key initiatives with potential for scale are the Model Health Facility, community champions and school clubs. Scaling partners include ministries of health and education, civil society networks, NGOs, and funders.

Recommendation 3: Sustainability of the grants mechanism: The grants mechanism now effectively supports over 80 frontline organisations, providing financial, technical, and networking assistance. As a result, grantee partners are reaching large populations through innovative, context-specific, locally-led interventions to end FGM. Given the limited availability of similar large-scale FGM-focused grants globally, and strong demand from communities, it is recommended that Options and FCDO collaborate (alongside civil society stakeholders) to develop a clear action plan to ensure the sustainability and future of the grants mechanism beyond the current programme. For future programming, the grants teams should develop tailored inclusion strategies to ensure equitable participation across all regions. TGG-ALM to share a Grant Sustainability Plan with FCDO by end-September 2025.

Recommendation 4: Strengthen relationships with consortia partners for effective delivery: Options should ensure that consortia partners have a clear understanding of the expectations in the final year of delivery. TGG-ALM should strengthen relationships, communication and monitoring of progress in intervention areas to ensure that any delivery issues are identified and resolved in a timely manner.

Recommendation 5: Civil society strategy in challenging contexts: In the context of shrinking global aid budgets and increasing global pushback against sexual and reproductive rights and gender equality including rollback on FGM, TGG-ALM should support its civil society networks to strategise proactively to identify approaches to accelerate positive change or, at a minimum, maintain recent gains.

Recommendation 6: UNJP strategy: In the context of reduced funding and increased uncertainty regarding future commitments from donors, UNJP should consider whether their strategy and number of priority countries still offers a sufficient depth of programming or whether this might need revising.
# B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The intended impact of this programme is a significant reduction of FGM in focus countries/regions by 2026/7. The intended outcome is: the acceleration of positive change in social attitudes towards ending FGM in countries/regions in which the programme is operational. There have been no changes to these Outcome and Impact statements.

The main sources of evidence for validating hypotheses within the Theory of Change (TOC) are baselines, qualitative case studies/stories of change, participatory community feedback mechanisms, quantitative evaluation data on changes in knowledge and confidence, social movement scorecards, and observations from programme staff. The Proof of Concept (PoC) process is also generating valuable learning that validates the TOC, while identifying areas to strengthen. All baselines have been collected and new measurement tools developed prior to this review period, which will provide a strong evidence base on the effectiveness of the multi-level approach to ending FGM once TGG-ALM endline evaluation is completed (in Y5-6; July-December 2025). This will be a priority in the year ahead.

There is no ‘assumption’ in the TOC relating to the output on ‘increased global commitments to end FGM’. The external environment has changed significantly during the review period, with coordinated efforts to undermine the gender equality movement, and significant reductions in international aid. This may affect the programme’s ability to secure its advocacy goals, such as increased funding for evidence-based FGM interventions.

The programme continues to adjust its programmatic approach within the structure of the TOC in response to community feedback/requests, such as expanding efforts to reach more target groups (e.g. the marginalised Waliwana group, and more out-of-school girls in Kenya; and targeting new duty bearers (midwives and grandmothers) in Senegal to coordinate with and support girl champions).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall output and outcome assessments: The majority of milestones (14 out of 17, or 82%) have been achieved, and the remainder have been partially achieved. There is growing evidence that expected changes are taking place in line with the TOC, despite challenges in the external environment (including environmental, conflict- and political-related disruption in all four geographies). Across all geographies, multiple forms of M&E data and community feedback suggest that TGG-ALM is leading to positive shifts in attitudes towards ending FGM. New and existing local champions and institutions (girls, young men, teachers and schools, women’s groups, religious leaders, health workers, local authorities etc.) have been strengthened and connected to one another by the programme and are well-positioned and willing to take forward the movement after the formal end of programme implementation.

Senegal, Ethiopia and Somaliland: Proof of Concept was achieved in Senegal, Ethiopia and Somaliland in Y4. The POC Assessments highlighted the effectiveness of the programme’s girl-centred and multi-level approach, and there is growing evidence of positive shifts in community attitudes toward ending FGM. Communities consistently report improved awareness, stronger commitment, and greater willingness to act to end FGM. There are strong signs of local leadership and ownership, enhancing potential for sustainability. Furthermore, TGG-ALM has contributed to eight notable policy advances, such as the Anti-FGM policy signed in Somaliland (in September 2024).

Kenya has progressed from Proof of Concept (achieved in 2024) to an intentional focus on scale and sustainability. Existing champions and networks (such as teachers, religious leaders, young people and local administrators) have been encouraged and equipped to support organised social diffusion (the process by which end FGM messaging and conversations are spread through existing social networks). For example, over 400 school manuals have been distributed (along with training) to educators to implement girl-centred approaches in school clubs. A formal pilot and evaluation of the social diffusion approach has been designed and initiated in Narok, and qualitative data is capturing social diffusion mechanisms among women’s rights networks in Garissa and Isiolo.

With an active programme of publications (18 global goods published in Y4, with another seven pending publication), and 16 sectoral knowledge sharing and/or advocacy events, TGG-ALM is actively promoting evidence and learning across the sector. Population Council and other TGG-ALM partners are in demand for their talks, products and technical assistance, with requests from a range of actors including UN agencies, civil society, and other funders.

Further quantitative data is needed to comprehensively assess and quantify the scale of TGG-ALM's impact. To address this, a mixed methods endline evaluation, supported by African Population and Heath Research Center (APHRC), will be conducted across selected programme sites during Y5 and Y6. This will involve comparisons with the baseline studies conducted earlier in the programme. The programme end date has been revised from 31 March 2027 to 30 September 2026.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

FGM is a human rights violation and an extreme form of violence against girls – ending it is critical for gender equality and improving outcomes for women and girls. Yet UNICEF estimate that 230 million women and girls alive today have undergone FGM – 30 million more girls than 8 years ago, representing a 15% increase in total survivors.3 In 2024, newly published research by the University of Birmingham1 estimated that FGM causes at least 44,000 additional deaths per year in countries in Africa, which points to FGM as one of the leading causes of death for girls and young women in these countries. In the wider global context of increasingly limited funding for ending-FGM and rollback on women’s and girls’ rights (such as the attempt to overturn the FGM ban in The Gambia), there is a real threat to the hard-won gains towards abandonment of FGM. The need for evidence of robust approaches to accelerate progress is needed more than ever.

TGG-ALM is a high performing programme that has undertaken significant work to conduct baselines and develop and refine the intervention model. Completing the baselines and disseminating the data and learning in this final 18 months will be critical for ensuring value for money for the investments made to date and generating global goods that can have a wide influence and legacy beyond the lifespan of the programme.

# C. DETAILED OUTPUT SCORING

Performance Area	Delivery
Score				A+
Impact weighting (%):		50%	Weighting revised since last AR?	N/A

Summarise overall progress on delivery in review period

This section summarises overall progress against this performance area comprising two components: (i) TGG-ALM; and (ii) the UNJP. Overall, partners have made reasonable progress delivering against the results framework despite slower than expected implementation. For the TGG-ALM component, implementation is at different stages for each country given the initial focus on Kenya in Y1 before expansion to Ethiopia, Senegal and Somalia in Y2. During year 4 (the year under review), the programme delivered the vast majority of its desired results despite a range of external challenges and in fast-changing contexts, by adopting a reflective and flexible mindset, and continuously problem-solving:
- firstly, working to change attitudes on FGM and gender equality is a highly sensitive thematic area (which, like all programmes that address violence and trauma, come with a potential psychosocial toll for staff);
- secondly, the programme requires teams to take a sophisticated technical approach (delivering while learning, adapting, and sharing, which are relatively new ways of working in the development sector), while
- thirdly, delivering this in contexts where political instability, insecurity and climate-related crises (including droughts and floods) have significantly affected operations. Although Somaliland and Ethiopia have been the most adversely affected by insecurity (road blocks, limitations on public gatherings, risks to personal safety), focal areas in Kenya have been affected by floods and increasing economic insecurity, and focal regions in Senegal are regularly affected by droughts and accompanying threats to livelihoods.
Given the above, achieving Proof of Concept across all three countries within the planned timeframe represents a significant accomplishment, requiring cross-consortium collaboration; extensive community, regional and national engagement; and the collection and analysis of a large amount of varied datasets. Other global challenges have required programme leadership and the Communications, Advocacy and Movement-building team to invest more time and energy into responding to the increase of anti-gender movements, and the increasingly hostile global climate towards women's rights. This has resulted in the need to respond rapidly to new challenges (like the threat of legalising FGM in the Gambia) and to always be alert for possible threats such as cyber attacks to TGG-ALM website.

The establishment of the Model Health Facility has been a particular achievements, showing that with a relatively small investment, corresponding specialist training in universities, and a strong partnership with the County MOH, comprehensive services for FGM survivors can be integrated into existing health services in low-resource settings, complemented by community- and clinic-based prevention activities. The MHF will now be used as a demonstration model for the approach. ACCAF will facilitate knowledge-sharing and learning exchanges among stakeholders.

Despite the challenges, the programme disseminated and encouraged uptake of various learning. For example, ACAAF’s FGM prevention and response training curriculum was adopted for use by the Senegalese higher education system. The curriculum was reviewed by the Senegalese National Ethics Committee to scrutinise all training resources to ensure they are fit for purpose in Senegal. While Population Council are in discussions with GIZ to replicate their model to support a cohort of universities to strengthen MEL action research around FGM/gender inequality interventions.

The UNJP has also been struggling with similar political instability insecurity and climate related crises and yet remains on track, showing significant improvement from last year – see comments below.

Component 1	Support to the Africa Led Movement
Score		A+

Performance Area	Delivery (50%)
Impact weighting (%):	40%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
O1. Developing, testing, scaling and sustaining context-specific end FGM models/interventions	Proof of Concept2 achieved in three countries.	Achieved / Proof of Concept achieved in three countries (Senegal, Somaliland, Ethiopia).
	Acceleration of sustainability & scaling strategies in Kenya: scaling and sustainability milestones achieved3	Partially achieved / Scaling and sustainability strategies implemented with 4/8 milestones achieved
O2. Grants reach frontline organisations to support end FGM initiatives at community level	a) 65 grantee partners implementing end FGM initiatives (by country)	Achieved / 82 grantee partners implementing in total. By country: / Kenya: 43 / Somaliland: 9 / Senegal: 24 / Ethiopia: 6
	b) At least 70% of grantee partners show improvement in at least two priority capacity building areas (governance and leadership, finance and procurement, programme management, and MEL)	Achieved / 87% show desired improvements
O3. FGM prevention and care integrated into pre-service training for health professionals	1,200 students trained with the FGM training package	Exceeded / 1,382 students trained
O4. Movement to end FGM is amplified (strategic media and campaigns)	12 stories/features catalysed by the programme in the media (print, online, broadcast), reinforcing programme messages/ framing, to support social change and/or an enabling environment for the end FGM movement	Achieved / At least 34 stories in the media
O5. Global advocacy	Seven people most affected by FGM (survivors of FGM, women and girls, and front-line activists (including men)) supported to participate in high-level advocacy spaces (including local advocacy spaces), with their participation resulting in empowerment and influence	Exceeded / 9 people supported
P1 (programme principle indicator). Girl-centred approach is operationalised	8/10 project sites meet their target for the proportion of girls participating in feedback mechanisms who feel meaningfully involved in the design, implementation and adaptation of interventions, including feedback being meaningfully taken on	Achieved / 9/10 sites met their target

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall, the programme is on track, with all milestones either fully achieved or partially achieved. POC[4] has been successfully demonstrated in Senegal, Somaliland, and Ethiopia, while the Acceleration of Sustainability and Scaling Strategies has been partially achieved in Kenya.
[4] For this programme, delivering Proof of Concept is about building, testing and refining a small-scale end FGM model which generates promising evidence and learning, giving the programme the confidence to scale and promote the model (via scaling and sustainability strategies: sharing learning, promoting tools etc) and/or evaluate it more rigorously during a longer period of implementation.

Indicator O1 targets include: (a) achieving Proof of Concept in three countries, and (b) accelerating sustainability and scaling strategies specifically in Kenya. The POC assessment process involved compiling and reviewing all programme MEL evidence, alongside a series of consultation workshops at community level (involving school children, community dialogue participants, and grantee partners), sub-national level (including government officials, journalists, elders, and civil society representatives), and at national level.

Target (a) Proof of Concept: Senegal, Somaliland and Ethiopia
All POC assessment activities were completed in Y4, except for the final national workshop in Somaliland, which took place in April 2025 (Q1, Y5) due to Ramadan in March. POC has been achieved in all three remaining contexts. Promising approaches for shifting attitudes have been developed, interventions are valued and relevant to communities, and feasible avenues for sustainability exist. Plans for Y5 have been updated to address learnings and recommendations from the POC assessment, including strengthening quantitative data for evaluation purposes, improving standardisation/documentation of social behaviour change resources, and strengthening messaging and dialogue approaches that emphasise the importance of complete abandonment of FGM.

MEL data and extensive stakeholder feedback from these assessments indicate that the programme’s approach is effective in shifting attitudes towards FGM, is locally relevant, driven by community engagement, and shows strong potential for sustainability and scaling. Nevertheless, some challenges remain, and adaptations are recommended to further strengthen the model in Y5.

Key findings from across the countries:
- TGG-ALM’s approach is different from previous end FGM interventions (and thus welcomed by local communities): initiatives are bottom-up, and activities are led by a wide range of community stakeholders, with a high degree of participation of girls and young people. There is frequent/intense and culturally sensitive engagement through a wide range of strategies.
- Positive shifts in knowledge, awareness and attitudes have become apparent reasonably quickly in most target groups. Strategies like connecting FGM to other forms of violence against women and children, and explaining its long-term impacts, were thought to help change understanding.
- In all contexts there are those who resist these changes, and in all contexts it is much harder and takes much longer to change the underlying beliefs and norms that underpin FGM. As a result, FGM behaviours adapt to a context of decreased public support, including increased secrecy around FGM and cutting girls at younger ages.
- However, with the right support (training, mentorship, networking opportunities, communications materials and ideally, some financial support to support travel and community activities), there are plentiful local champions (including girls, young women and survivors) who invest their free time and efforts into advocating for an end to FGM, who are well positioned to take on the longer term, patient work required to shift norms, beliefs and ultimately behaviours and end all forms of FGM. There is high motivation to effect positive change in their communities, despite often challenging and risky environments.
- In all contexts, partners are leveraging existing interventions and structures where possible, to promote continuity of end-FGM activities beyond the life of the programme, such as local government youth structures, and health workers.
- Areas requiring strengthening in Y5 include:
  - Fine tuning the balance of girl-centred programming: in some contexts, concerns were raised that the programme was placing too high a burden for bringing about change on girl champions, whereas in others, children and young people wanted to do more to lead change.
  - Continuing to learn and adapt to shifts in FGM that take place in response to end FGM initiatives (e.g. shifts towards different types of FGM, rather than stopping all together; shifts to cross-border FGM).
  - Continue to strengthen/systematise communications resources for programme teams and champions: for example, while a few younger participants in Somaliland talked about FGM in terms of rights and violence, most people still speak about the health harms only, and it is well evidenced that health arguments alone can lead to medicalisation and/or changes in types of cutting, rather than abandonment. More persuasive arguments/messaging (with the right people delivering these messages) are needed to tackle this challenge.

Target (b) Accelerating sustainability and scaling strategies: Kenya
Target (b), which focuses on Kenya (where Proof of Concept was achieved in Y3) has been partially achieved, with four of the eight scale and sustainability milestones met:
A champions network across programme counties (Narok, Garissa and Isiolo) has been established and is active. This is a mechanism to sustain and scale social change initiatives at community level led by champions, who have been trained to lead activities like dialogues. By linking them for support, advocacy, and learning, the aim is to expand their efforts beyond the life of TGG-ALM. The network has TORs, a leadership structure, regular online meetings, and a WhatsApp group with 80+ members.
21 new villages reached with intergenerational dialogues, against a target of five.
Women and girls receiving FGM-related healthcare at the MHF in Narok: 654 women and girls have received specialised treatment since the MHF became operational this year.
Community health promoters are sensitising, identifying and referring women and girls for the MHF: household visits by medical students with support from Community Health Practitioners and health care workers have reached 94 households (c. 322 people).
One milestone that was partially (25%) achieved is evidence that ‘scale-up/integration’ target groups (groups identified as having strong potential to amplify the programme’s key messages to their wider networks) are including ending FGM in their discussion topics. Qualitative data confirms that one of the four priority target groups (Women’s Rights Networks) is actively promoting social change in line with programme objectives. The other target groups (Village Savings and Loans Associations, Men4Change networks, and Young Women Breaking Barriers) require more evidence of uptake of FGM discussions, and these efforts will continue into Y5.

The three remaining scale and sustainability milestones, which have not yet been achieved, relate to the social diffusion pilot. This pilot aims to test whether successful social change initiatives from one ward in Narok can effectively expand into a neighbouring ward, drawing on existing local resources and expertise (such as champions, patrons, and previously developed manuals), alongside minimal inputs from programme staff. An evaluation framework has been established to test this model, which will provide valuable insights for future scaling efforts. However, the original 12-month timeline proved overly ambitious, given the extensive background research, planning, and data collection required. Despite this delay, the milestones remain on track for completion by mid-2025.

Grants
Milestones for Output Indicator 2 are: a) 65 grantee partners implementing end FGM initiatives (by country), and b) At least 70% of grantee partners show improvement in at least two priority capacity building areas (governance and leadership, finance and procurement, programme management, and MEL).

The first milestone has been achieved: this year, a total of 82 grantee partners were contracted and funded, exceeding the target of 65 (Kenya 43, Senegal 24, Ethiopia 6 and Somaliland 9). At the end of Y4, 95% of the planned grants value had been successfully disbursed (£870,390). Funds have been disbursed to young women- and girl-led organisations, currently 67% in Kenya, 58% in Senegal, 22% in Somaliland, and 50% in Ethiopia, ensuring girls’ and women’s leadership remains central to the programme.

The second milestone has been achieved, with 87% of grantee partners from the 2023 cohort reporting improvements in at least two priority capacity building areas (governance and leadership, finance and procurement, programme management, and MEL). Most grantee partners have developed or strengthened core organisational policies, including governance and leadership, financial management, human resource management, and procurement/property management. 20 grantee partners have now developed safeguarding policies through support from TGG-ALM, while the rest are in progress.

Stronger capacity among grantee partners is indicated by the fact that since becoming part of TGG-ALM, grantee partners have successfully won over £1.7m worth of grants from other funders. These skills are crucial to help them access funding and sustain activities beyond the lifespan of the programme.

Integration of end-FGM into sectoral work
The milestone for the Output Indicator 3 on integration has been exceeded: the target was 1,200 medical students trained with the FGM training package, and 1,382 have been trained. ACCAF is on track with contributing to their aim of ensuring the next generation of health care professionals are knowledgeable, skilled, and empowered to prevent FGM (including medicalisation) and to care for survivors. They are doing this in two main ways: (i) Training healthcare professionals (lecturers) with a standardised FGM prevention and response curriculum, and in turn these lecturers roll out training to their medical/health trainees in universities and colleges (with light touch support from ACCAF). (ii) They have established and are supporting a MHF in Narok County (Kenya) to promote access to holistic FGM prevention and care for girls and women.
Lecturers and trainees demonstrate improved levels of confidence, knowledge and skills demonstrated by the following improvements in scores between pre- and post- training tests:  Kenya: from 51.5% to 67.2%, Ethiopia: from 43.5% to 89.1%, Senegal: from 53% to 68%. In addition, the trainees have demonstrated acquisition of cultural competency, communication, counselling, safeguarding and presentation skills while delivering care ethically.

The MHF became fully operational during Y4. It provides students on five-week-long placements with an opportunity to practice the skills they acquired in the classroom. The MHF offers integrated FGM prevention and care services, and home/community-based FGM prevention through medical trainees with support from community health promoters. The total number of people reached through the MHF is 2013. Collaboration and partnership with stakeholders including the County Health Management Team ensured the success of the integration model including the MHF.

Challenges: The biggest challenge to integration is for the MHF to secure financial commitments for scaling and sustaining the work. ACCAF plans to engage with the Kenya Ministry of Health and County ministry of health (Narok) with a view to disseminating knowledge and learnings on FGM prevention and response work, including the MHF, to advocate for their uptake and resource allocation. ACCAF is in discussion with the National government and county government for infrastructural improvements, specifically the housing for medical specialists and medical students accommodation to make sure that the MHF can run a 24 hours services for the community including girls and women at risk of with FGM. It is anticipated that these efforts will promote sustainability and scalability of the integration model and the MHF. TGG-ALM will support ACCAF to make the case for investment in, and scale up of, this approach in wider geographies by exploring other global platforms for sharing the model, e.g. at the International Conference on Family Planning (an abstract for a panel discussion has been submitted), CSW, and via WHO (with whom ACCAF already works closely). In Y5, ACCAF are also planning to produce and publish peer reviewed publications, as well as more accessible learning briefs, on the MHF, drawing on their extensive M&E data and learning.

Separately, during awareness creation among girls in school by the medical students, girls asked where they can hide when their parents threaten to subject them to FGM, as there are no rescue centres in the area. This issue was discussed with the Country Health Management Team, the county executive management and students. It was agreed that students can seek the help of the county government in this situation, including from the local administration for child protection services. To note that while FGM prevalence is declining overall in Kenya, Narok country has a 51% prevalence rate according to the Kenya Demographic and Health Survey (2022).

Media
The milestone for Output indicator 4 is 12 stories/features in the media, which has been exceeded, with 34 stories published or broadcast[5].
[5] Notable coverage included: The Guardian UK- highlighted the unseen scars that women and girls subjected to FGM continue to contend with and spotlighted TGG-ALM’s Survivors Leadership Initiative. Interpress News Service- highlighted the role of community interventions in engaging survivors to protect their girls. More to Her Story- An online news room focused on improving the odds for women and girls, founded by Sara Little. France24  featured the power of language in ending FGM: Kenya's Citizen Digital featured the work of the programme in disability inclusion

In Narok, TGG-ALM collaborated with local media companies to document success stories that were shared both in print and on TV. Partners also engaged with local radio stations at community level, broadcasting discussions, phone-ins, etc. In Senegal, radio broadcasts about the consequences of FGM were led by and featured TGG-ALM girl champions, reaching an estimated 6,500 people.

TGG-ALM also accelerated its own communications outputs this year, with a regular e-newsletter featuring stories of change and activists, month-long cross platform social media campaigns to mark the International Day of Zero Tolerance for FGM and 16 Days of Activism against Gender-Based Violence, and the production of various audio-visual resources which showcase the programme’s work[6].
[6] The work can be found on TGG-ALM’s YouTube Channel.

TGG-ALM considers stories/features in the media as an essential part of movement building and contributor to galvanising social change at local levels (e.g. through local radio, which can support social norms change, as described in Pop Council's Evidence Synthesis on ending FGM/C). While the direct contribution of media stories to social change and movement building is difficult to quantify, there are many examples of media coverage playing an important role in supporting/strengthening social movements, through exerting ongoing pressure on duty bearers, keeping the issue at 'top of mind' and a policy priority, and helping maintain morale/relevance among activists.

Advocacy and Movement-building
The milestone for the Output indicator 5 on advocacy is: Seven people most affected by FGM are supported to participate in high-level advocacy spaces. This target has been achieved: in total, nine survivors, youth activists and frontline campaigners actively participated in various national, regional, and global events/platforms including the WOW festival, the International Confederation of Midwives (ICM) Regional Conference 2024 held in Kigali, the ten-year anniversary of TGG hosted in the UK, Summit of the Future Action days, the Zero Tolerance Day FCDO event in the UK, ECOSOC Youth Forum in New York, and the CSW69 event in New York, where grantee partner representatives participated in side/parallel events on funding and sustainability of FGM interventions and the place for girl-centred programming. Activists engaged in various activities ranging from leading poster presentations, speaking on panels, and leading conversations to increase awareness on TGG-ALM and their work to end FGM. The programme’s advocacy team amplified their voices via social media. Panellists have fed back that participation in these events is empowering and that they plan to apply learnings from the platforms in their community work.

Two girl council members participated as panellists in a webinar on Centering Girls’ Agency and Voice: Approaches for ending FGM and other forms of gender-based violence, where they discussed their experience and involvement in TGG-ALM. Six girl council members from Isiolo and Garissa counties attended an event at the British High Commissioner’s residence on disability inclusion, as TGG-ALM marked the International Day of Persons with Disabilities (3 December 2024). The participation of girls council members with disability reinforced the vital role young people living with disabilities play in ending all forms of GBV (including FGM) and empowering their communities.

Programme Indicator P1: Girl Centred Approach is operationalised
In all programme contexts, either 100% of girls, or the vast majority (89% being the lowest figure reported) of girls surveyed reported that they felt meaningfully involved in the programme. TGG-ALM operationalised the girl-centred approach in multiple ways: regular feedback sessions with girls to reflect on progress and seek recommendations for adaptations; supporting Girls’ Councils, who represent girls in various programme spaces; activities (including in- and out-of-school clubs) to inform and empower girls to understand their rights and various forms of violence including FGM; and in several contexts, there are initiatives to foster leadership among girls and young women to champion change within their social networks.

Component 2			Laws, policies, and systems working effectively at multiple levels through the UN Joint Programme
Score						A
Impact weighting (%):	10%			Weighting revised since last AR?		N/A
Indicator(s)	Milestone(s) for this review				Progress
2.1 Strengthened regional accountability mechanisms		Ind. 3111 - 4 outcome documents of global and regional intergovernmental (African Union, League of Arab States and regional economic communities, etc.) processes that integrate commitments related to the elimination of FGM			Exceeded / 7 outcome documents[7] from global and regional intergovernmental processes, integrating commitments to the elimination of FGM, were published, surpassing the target by 60%.
2.2 Increased national and local capacities for the development of costed national action plan, implement a framework to end the medicalisation of FGM and enact and implement FGM laws		Ind. 3101 – 16 countries with a multisectoral evidence-based, gender transformative FGM elimination policy or strategy that includes a plan of actions with targets, a budget, and an M&E framework, in line with human rights and the leaving no one behind principles			Achieved / The target was met with 16 countries, with the exception of Yemen and Guinea-Bissau[8], having a current national multi-sectoral policy or strategy on FGM elimination. / These frameworks include a plan of action with defined targets, an allocated budget, and a monitoring and evaluation (M&E) component. / NB: National Actions Plan are updated every 4 or 5 years. UNJP report this data as preliminary and quality assurance has yet to be conducted.
2.4 Improved availability and quality of FGM services in Joint Programme Intervention areas		Ind. 2001 – 855,612 girls and women who received prevention and protection services on female genital mutilation / Ind. 2102 – 97,270 girls (0-19 years) and women who have received health services related to FGM / Ind. 2103 - 203,937 girls and women who have received social services related to FGM / Ind. 2104 - 50,193 girls and women who have received legal services related to FGM			Partially Achieved / Ind. 2001 1,450,136 girls and women who received prevention and protection services on female genital mutilation (exceeded) / Ind. 2102 – 88,110 girls (0-19 years) and women who have received health services related to FGM (partially met) / Ind. 2103 – 470,174 girls and women who have received social services related to FGM (exceeded) / Ind. 2104 - 5,108 girls and women who have received legal services related to FGM (not met)
Evidence/M&E	Ind. 3132 – 21 in-depth analyses, research, studies and evaluations conducted during the year to fill the evidence and knowledge gaps related to elimination of FGM				Achieved / 22 in-depth analyses, research, studies and evaluations were conducted to fill the evidence and knowledge gaps.
[7] UNFPA Arab States Regional Office (ASRO)/UNICEF Middle East and North Africa Regional Office (MENARO):1. Recommendations of the regional meeting on the cost of harmful practices) convened by the League of Arab States, UNFPA ASRO, and UNICEF MENARO. UNFPA/UNICEF West and Central Africa Regional Office (WCARO): 1. Universal Periodic Review (UPR) Review Guidance Note, 2. Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) Reporting Guidance Note, 3. The African Union Convention on Ending Violence Against Women and Girls (RO has given comments/recommendations during the drafting). UNFPA/UNICEF Eastern and Southern Africa Regional Office (ESARO): 1.UPR outcome report- Eritrea, 2. UPR outcome report- Ethiopia, 3. The African Union Convention on Ending Violence Against Women and Girls (RO has given comments/recommendations during the drafting)
[8] Guinea-Bissau's strategy concluded in 2024 and a new one is currently under development; while Yemen’s strategy not developed due to the ongoing conflict shifting governmental focus towards security and humanitarian needs and away from FGM related national strategy, legal framework, or dedicated budget to address it.

Component 2

The milestones for this component have been generally met. FCDO contributed £1.1m during the review period (for UNJP this is January 2024 – December 2025).

2.1 Strengthened regional accountability mechanisms. The indicator for this milestone has been exceeded. Seven outcome documents from global and regional intergovernmental processes were published[9], surpassing the target by 60%. Through support from UNJP different regional bodies, such as African Union and its organs such as African Committee of Experts on the Rights and Welfare of the Child (ACERWC) and African Commission on Human and People’s Rights (ACHPR), League of Arab States, African Council of Religious Leaders (ACRL), East African Community (EAC), Intergovernmental Authority on Development (IGAD) were engaged in advocacy and regional coordination efforts aimed at influencing policies, strengthening legal frameworks, and increasing national budget allocations to eliminate FGM. These bodies also supported capacity development and knowledge exchange by fostering evidence-based dialogue and collaboration among a wide range of stakeholders, including governments, regional bodies, civil society organisations, and youth-led groups. For instance, the African Committee of Experts on the Rights and Welfare of the Child (ACERWC) and the African Commission on Human and Peoples’ Rights (ACHPR) jointly supported efforts to uphold anti-FGM legislation by issuing expressions of concern in response to attempts to repeal such laws.
[9] UNFPA Arab States Regional Office (ASRO)/UNICEF Middle East and North Africa Regional Office (MENARO):1. Recommendations of the regional meeting on the cost of harmful practices) convened by the League of Arab States, UNFPA ASRO, and UNICEF MENARO. UNFPA/UNICEF West and Central Africa Regional Office (WCARO): 1. Universal Periodic Review (UPR) Review Guidance Note, 2. Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) Reporting Guidance Note, 3. The African Union Convention on Ending Violence Against Women and Girls (RO has given comments/recommendations during the drafting). UNFPA/UNICEF East and Southern Africa Regional Office (ESARO): 1.UPR outcome report- Eritrea, 2. UPR outcome report- Ethiopia, 3. The African Union Convention on Ending Violence Against Women and Girls (RO has given comments/recommendations during the drafting)

2.2 Increased national and local capacities for the development of costed national action plan, implement a framework to end the medicalisation of FGM and enact and implement FGM laws. The 2024 target to strengthen regional accountability mechanisms and enhance regional and national commitments to eliminate FGM was met. Sixteen countries, with the exception of Yemen and Guinea-Bissau have a national multi-sectoral policy or strategy on FGM elimination. The UNJP engaged through advocating for FGM policies through relevant ministries (social, health, education, religious affairs), providing technical support to the lead/tasked governmental entity/taskforce responsible for the development or review or evaluation and implementation of FGM related policy, strategy, action plan including M&E to its finalisation and endorsement. For example, in Indonesia, the Joint Programme co-funded with the Ministry of Health state budget a study which results in the issuance of a circular by the East Lombok Regent prohibiting FGM. These efforts also brought to light grassroots stories and challenges, providing valuable insights to inform the development of the Ministerial Regulation on Reproductive Health to stop health workers from performing FGM. These 16 countries also have plans of action with defined targets, an allocated budget, and a monitoring and evaluation (M&E) component. In Guinea-Bissau, the previous national strategic plan concluded in 2024, and a new one is currently under development which is expected to be finalised by the end of 2025. Through support of the Joint Programme, high-level meetings were held in Yemen which led to renewed commitments and adoption of the Aden Declaration and Roadmap to eliminate FGM, which is a multisectoral action plan to be implemented in 2025. Yemen has an outdated national action plan (2020-2022), a result of adopting the United Nations Security Council Resolution 1325 (UNSCR 1325)[10]in 2019.
[10] The resolution recognizes FGM as a form of violence against women and girls and emphasized human rights education

2.4 Improved availability and quality of FGM services in Joint Programme Intervention areas.
With respect to the social sector, a total of 470,174 girls and women benefited from social services - more than double the 2024 target of 203,937. In addition, 1,450,136 girls and women received FGM-related prevention and protection services which consist of counselling, support, shelter, education, and awareness programs. This achievement surpassed the annual target of 855,612 by 69% and exceeded the 2023 results of 903,734 by 60%. The highest contributions to this cumulative result were from Guinea, Burkina Faso, Sudan, Egypt, Nigeria, and Mali which implemented capacity-building initiatives targeting healthcare workers and key service providers, established or strengthened women and girls’ safe spaces, and intensified community outreach and social norms change communication efforts.

The number of healthcare facilities having at least one staff member trained in FGM prevention, protection, and care increased to 3,642 in 2024 increasing by 28% from 2023 (2,842). The main contributors to this cumulative result were Egypt, Ethiopia, Nigeria, Eritrea, and Mauritania.

Encouragingly, the overall number of girls and women (0-19 years) across the 18 countries who received FGM-related health services increased by 45%, from 60,656 in 2023 to 88,110 in 2024. Although this achievement has increased compared to the 2023 achievement by 45%, it is below 2024 target (91% achievement). This result is influenced by the level of integration as well as quality of reporting of FGM-related indicators within existing health management information systems (HMIS). As well as the turnover of trained health professionals for instance this was observed especially in Ethiopia which had a high contribution in 2023 that was not sustained for 2024. As a way forward UNJP will continue to: (i) Advocate for and support integration and roll out of FGM content within curricula of existent government and private training institutes and continuous professional development programs to continuously generate trained health workers to address turnover of trained health workers and (ii) Advocate and support systematic inclusion and strengthening quality of reports for FGM related indicators within the national health information systems.

Only 5,108 girls and women accessed legal services, achieving just 10% of the 2024 target of 50,193 and falling below the 2023 achievement of 42,296. The main contributor to this cumulative result was mainly led by Guinea Bissau. This “low” performance is actually an improved accuracy of reporting as per the meta data as compared to over reporting in 2023 due to an inaccurate definition. Efforts continued to strengthen systems’ interlinkages such as integrating legal services or referral pathways between different sectors. For instance, in Uganda, national and regional medico-legal working groups tasked to establish comprehensive medico-legal services supported by a strong data collection system developed a multisectoral action plan. This action plan, led by the directorate of public prosecutions (DPP) and co-chaired by the ministry of health is scheduled for implementation in 2025.

Evidence and Monitoring and Evaluation
Primary, secondary, and programmatic data at various scales, from local initiatives to national assessments was used to conduct and generate 22 in-depth analyses, research, studies and evaluations on FGM (target was 21). The evidence contributions were from 12 countries in 2024 compared to 11 countries in 2023. The main areas studied included behavioural and social norms, youth and community engagement, awareness-raising initiatives as well as factors such as education and their associations with attitudes and practices related to FGM. Some notable studies at a global level, included a 2024 update on FGM prevalence trends highlighting the progress at country levels[11] . Further, a rapid review was conducted to update the 2008 - 2020 literature review of effective interventions designed to prevent or respond to FGM30 to the latest literature in 2024 as well as collate the intervention mechanisms and key implementation considerations to support programmatic implementation[12]. UNJP plans to use a range of mechanisms to disseminate the data and learning including: the new data management platform, regular reports (quarterly, internal , regional and annual reports), regular regional meetings (African Union, League of Arab States) and non-governmental partners (such as TGG-ALM and GIZ), annual technical consultation meetings and participation in international scientific and professional meetings (e.g. International Professional Conference for Paediatricians). UNJP will also develop technical guidance notes on best practices, learning and evidence.
[11] UNICEF (2024). Female genital mutilation, a global concern - 2024 update. https://data.unicef.org/resources/female-genital-mutilation-a-global-concern-2024/
[12] Matanda, Dennis Juma, et al., (2021). What interventions are effective to prevent or respond to female genital mutilation? A review of existing evidence from 2008–2020. UNFPA, UNICEF, WHO and Population Council, Kenya. https://doi.org/10.1371/journal.pgph.0001855.

Performance Area	Actionable Learning
Impact weighting (%):	30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Robust consortium learning mechanisms result in actionable learning to support adaptive management, driving programme quality	Four (4) joint consortia learning products published that synthesise learning from across programme countries/sites, contributing to a programme-wide body of knowledge and evidence	Exceeded / 11 joint consortium publications finalised
	20 citations of knowledge products synthesised/ developed by the Data Hub (e.g., FGM Evidence Synthesis Report, Global Research Agenda, measurement tools, learning briefs).	Exceeded / 46 citations during the review period
	Three (3) sectoral knowledge-sharing events (either hosted by TGG-ALM or presenting/sharing programme products), 60 attendees participating per event	Exceeded / At least 15 events held, average 85 participants

All milestones for this area have been surpassed, with TGG-ALM successfully ramping up capturing of learning, publications, and active dissemination in Y4. Learning on the programme is both used internally (supporting ongoing adaptations and improvements), and promoted externally (to share insights and learning with the wider sector). Each programme team has reflection points and spaces across the year to review and document learnings (including as part of the quarterly reporting process), and consider how these might lead to adaptations. A major moment for doing this is the Proof of Concept Assessment, which has led to a number of recommendations for strengthening the intervention model further in Y5. Examples of learnings and adaptations in Y4 include :

- In Senegal, some individuals who had participated in community dialogues reported that they felt more confident and safer discussing issues in same-gender groups. Women-/men-only dialogues were subsequently introduced in Y4.
- In Somaliland, teams observed that clear articulation of Islamic teachings in relation to FGM can help clarify that FGM is not mandatory, and to promote a zero-tolerance message. The programme worked with religious leaders to share correct Islamic teaching on FGM, to combat any misconceptions or confusion held by community members around supporting certain types of FGM. Religious leaders are being encouraged to publicly support TGG-ALM goals. In all communication materials, the programme clearly promotes zero tolerance to FGM.
- In Kenya, the grants team learned that anchoring implementation of community activities in village-level networks and groups (rather than general mobilisation) enhances social accountability among grantee partners, creating a ripple effect for the entire community.  The programme now prioritises working with leaders of village-level groups (e.g. women's self-help groups, men's animal trading groups, school/water users, farmers etc.) to structure mobilisation for activities and community action planning. The approach is to pick the leaders of the groups/committees, empower these gatekeepers, and by extension reach the households of the group members.

Milestone 1, joint publications: 15 learning products[13] were finalised in Y4, 11[14] of which were a collaboration between consortium partners. TGG-ALM website recorded more than 150 downloads of Global Goods.
[13] - Youth Advocacy Toolkit: led by Orchid with inputs/reviews by multiple other partners - Academic article on environmental stressors and FGM: led by University of Portsmouth with inputs and technical review by AA, Population Council and Options - Reframing the language on FGM: led by Options with consultations, reviews and inputs from across the consortium - Learning Brief on Girl Champions in Senegal: inputs from ActionAid, Amref, and Options (lead editor) - Learning Brief on results of community and couples' dialogues: led by Amref with technical support from Population Council and editorial support from Options
[14] 1. Stories of change booklet (Kenya) - Finalised but currently being designed prior to publication 2. Learning Brief on Integration: Educating the next generation of health professionals on FGM - https://thegirlgeneration.org/wp-content/uploads/2025/01/Learning-Brief-on-Integration_1712246.pdf 3. Academic Article: Female Genital Mutilation (FGM) in Garissa and Isiolo, Kenya: Impacts on Education and Livelihoods in the Context of Cultural Norms and Food Insecurity - https://www.mdpi.com/2075-4698/15/2/43 4. Academic Article: Assessing the Successes and Challenges of Adopting a Girl’s Centred Framework to Ending FGM - Not published yet - UoP is submitting the article to journals 5. Position paper/ guidance note on language around FGM: The transformational Power of Language in Action: - https://thegirlgeneration.org/wp-content/uploads/2025/04/Power-of-language-2025-1-3.pdf 6. Learning and Adaptation report: Developing a girl-centered approach to end FGM. Learning from a Proof of Concept assessment in Kenya. - https://thegirlgeneration.org/wp-content/uploads/2024/09/TGGALM-Report-Sept-2024-v4.pdf 7. Learning and Adaptation report: Equipping the next generation to end FGM. Learning from Somaliland - Pending publication 8. Learning and Adaptation report: The key role of girl champions in ending FGM in Senegal - in English: https://thegirlgeneration.org/wp-content/uploads/2025/02/TGG-ALM-Senegal-Learning-Brief_040225.pdf
   And French: https://thegirlgeneration.org/wp-content/uploads/2025/02/TGG-ALM-Senegal-Learning-Brief_280125-FRENCH.pdf 9. Learning and Adaptation Report: Ending FGM in Ethiopia. Community-led approaches in Amhara - Finalised, currently being designed prior to publication 10. Learning Brief: Kenya: A comparative assessment in knowledge, attitudes and beliefs among participating and non-participating households in community conversations focused on ending FGM. - Finalised, currently being designed prior to publication Learning Brief: Training the next generation of healthcare professionals on ending FGM in Ethiopia - https://thegirlgeneration.org/wp-content/uploads/2025/05/Learning-Brief_Integration-in-Ethiopia_Dec24_FINAL-1.pdf

Milestone 2 was to achieve 20 citations of Data Hub products, and 46 citations were achieved. In addition, over the last year, Population Council tracked 11 instances of products serving a purpose in the field, exceeding expectations. Five of these relate to increased citing of products within the field. For five specific products, there has been a growth in citations, from 21 to 46 citations in the last year – a 119% increase.[15]
[15] Usage metrics (derived from Google Scholar) indicate that, by the end of the reporting period, the following increases in citations of five Hub products was observed: Effectiveness of Interventions Designed to Prevent or Respond to FGM (‘evidence synthesis’): from 8 to 12 citations. Peer-reviewed journal article version of the evidence synthesis: from 8 to 24 citations. Global Research Agenda on FGM: from 5 citations to 7 citations AMREF-PC Kenya peer-reviewed protocol paper: from 0 to 1 citation Social attitudes tool evaluation report: from 0 to 2 citations

Milestone 3 was to host at least three sectoral knowledge-sharing events, with at least 60 participants on average. This target was surpassed, with at least 15 virtual and physical events and an average of 85 participants, either hosted by TGG-ALM, or with TGG-ALM playing a significant role in organising/speaking at the event.

Webinars attracted participants outside the focus countries, including across Europe, multiple African countries, UK, US, and Canada. Webinars saw a consistent rise in attendance over time with 283 attendees from just three webinars[16]. This significantly boosted external communications about the programme’s work, strategies, and tools. They have become a vital tool for online movement-building, fostering global support for efforts to end FGM.
[16] The three webinars were titled: (i) Voices from the field: Lessons, Strategies and Stories on ending FGM in Communities, (ii) Resourcing Grassroots Movements to End FGM and (iii) Girl-Centred programming in ending FGM/C: a Proof of Concept in Kenya

Other knowledge sharing events included:
As part of 16 days of activism, The Irish Consortium on GBV invited TGG-ALM to share best practices in engaging with survivors of violence (FGM). This was part of their research work ‘From Survivor-Centred to Survivor-led; Best Practices from promising survivor-led GBV initiatives’, in which TGG-ALM SLIs work was quoted as a best practice. The webinar attracted more than 200 attendees and partners from different countries.
Population Council’s November 2024 Evidence and Learning Forum: Improving Measurement of Social and Gender Norm Change related to Female Genital Mutilation (FGM).

Performance Area	Contribution to meaningful change (Scale and sustainability)
Impact weighting (%):	20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Outcome: Acceleration of positive change in social attitudes towards ending FGM in countries/regions in which the programme is operational	12 target groups showing (qualitative) evidence of positive shifts along the continuum of attitudinal change regarding FGM (including more egalitarian gender beliefs, and FGM-related beliefs and knowledge) in target communities, with at least two in every programme country	Partially achieved / Evidence from 12 target groups in Kenya and Senegal. Means of Verification (MOVs) in Ethiopia and Somaliland did not meet criteria for robust qualitative data from more than one source. However, POC assessments suggest positive shifts in attitudes in multiple target groups across all four countries.
Intermediate outcomes (IO): / IO1. Positive changes in beliefs, knowledge and agency relating to FGM in programme regions	10% of girl/boy school club participants (in new Y4 cohort) with evidence of positive changes in beliefs, knowledge and/or agency	Achieved / Average 23% points increase (with regional variation: high of 95% points increase in Somaliland, low of 14% points decrease in Garissa, Kenya)
IO2. Advances in policies and legislation, including effective financing mechanisms, that support gender equitable efforts to end FGM.	Eight policy and legislative advances achieved that support gender equitable efforts for ending FGM	Achieved / At least 9 policy/legislative advances
IO3. Stronger and more resilient civil society movements led by women, girls and survivors working to end FGM	Average increase of five points in social movement scorecard score (disaggregated by country/focal region)	Partially achieved / Social Movement Scorecard scores plateaued on average in Kenya (59 points in Y3, 57 points in Y4): / Narok: from 59 points (Y3) to 54 points (Y4) / Garissa: from 58 points (Y3) to 63 points (Y4) / Isiolo: from 62 points (Y3) to 55 points (Y4) / Social movement scorecards (first round) conducted in other 3 countries.
IO4.Evidence, learning and knowledge sharing strengthens portfolio of effective strategies and models to end FGM	Three instances of product influence/uptake among/by stakeholders	Achieved / At least 11 examples of product influence/uptake among stakeholders (see narrative below for details)
IO5. / Integration of FGM prevention and response approaches into aligned sectors	29 institutions integrating FGM prevention and response into systems and processes (cumulative)	Achieved / 36 institutions: Kenya (25), Ethiopia (1), Senegal (4), Somaliland (6)

Outcome: Acceleration of positive change in social attitudes towards ending FGM in countries/regions in which the programme is operational
The outcome indicator milestone is 'evidence for positive changes in social attitudes towards ending FGM among at least 12 different target groups across geographies'. While the gross total for this target has been achieved, with evidence from 12 target groups, robust evidence (e.g. focus group discussions (FGDs), surveys) is only available from Kenya and Senegal. A range of attitude shifts were captured across the programme sites, across a continuum of attitudinal change. For example an increase in support for equal education for boys and girls (Kenya), more open discussions within the communities about FGM (Senegal), growing respect for girls’ voices and leadership (Kenya). Enhanced quality standards for this indicator were introduced in Y4, and data from Somaliland and Ethiopia did not meet these standards (e.g. inadequate number or composition of FGDs).  While POC assessments in all countries reflect positive changes across multiple target groups, better quality evidence is required in Y5 to substantiate these results.

Evidence from grantees also suggests positive attitudinal changes, although grantee partner reports do not contribute towards this milestone. Participants have shared compelling accounts of growing openness to abandoning FGM. Notably in Kenya, there has been a significant rise in young men advocating against FGM, e.g. among motorbike riders who champion alternative rites of passage and facilitate community dialogues. Engaging local faith-based leaders has emerged as an impactful strategy for grantee partners to challenge FGM in target communities. Trusted by their congregations, these leaders hold significant influence, allowing them to effectively shift attitudes and behaviours by incorporating anti-FGM messages into sermons and outreach activities.

Intermediate outcome 1: Positive changes in beliefs, knowledge and agency
Although this target was exceeded, the average result masks variability across programme sites and target groups. Shifts in attitudes, beliefs and agency results were all positive except in one site (Garissa, Kenya). Possible reasons for decrease in Garissa may be related to a new cohort of schools and children for the programme to engage with, or that data was collected during school holidays when the practice is high, and that Garissa is one of the places with the highest prevalence rates so shifting beliefs takes longer. Disaggregating the data, and including examples of other indicators that are close to (but not directly comparable with) these indicators, reveal the following:
In Farta, Ethiopia, MEL data showed an average 18.8%-point increase in positive beliefs, and in Guna there was a 19%-point increase.
In Senegal, data comparing programme implementation areas with non-programme areas showed that more than twice as many girls and boys know about the consequences of FGM in areas where TGG-ALM is active (94% of girls and boys), than in areas where it is not working directly (46% of girls and boys).
In Kenya, ActionAid in Kenya (AAIK) worked with a new cohort of children in forums, resulting in positive changes: the belief that girls should be involved in a decision on FGM saw a significant increase, from 87.6% to 94.0% in Isiolo.
AMREF Kenya school assessments looked at whether positive changes had been maintained in school clubs over the holiday period. A survey found that “Consistent engagement and education through health club sessions resulted in maintenance of positive changes in knowledge, attitudes, agency, and beliefs regarding FGM among members, even after a three-month school holidays period. This demonstrates the medium-term effectiveness of the health club model in maintaining positive shifts”.

On wider community shifts in egalitarian beliefs in Kenya, teams are continuing to see progress, captured by focus group discussions reports and stories of change, and are seeing community leaders, duty-bearers and key stakeholders taking the next steps from awareness and knowledge, towards further action, embedding end FGM messaging into their work and starting to share beyond the bounds of TGG-ALM programme implementation.

Intermediate outcome 2: Advances is policy and legislation
The milestone for this indicator was eight advances, and at least nine have been achieved. The programme’s advocacy efforts strengthened commitments/actions to eliminate FGM at national and regional levels, resulting in advances in policies and legislation, resource commitments, and integration of FGM prevention and response in healthcare. Key achievements include:

Approval of Somaliland’s first national anti-FGM policy (September 2024): In Somaliland, TGG-ALM and wider partners influenced the approval of the country’s first-ever national anti-FGM policy. This achievement consolidated years of engagement with ministries, advocacy with women’s rights groups and civil society, and specific TGG-ALM activities such as the Y3 exchange visit to Kenya for ministry representatives, Somali MPs, and technical officials.
AA Senegal has supported a significant next step in the implementation of the third national action plan to end FGM in Senegal (2022-2026), coordinating with the Ministry of Family and Solidarity, the UN Joint Programme, and numerous civil society organisations to produce a monitoring and evaluation results framework for the action plan, supporting accountability and progress in delivering this key national commitment towards ending FGM in Senegal.
TGG-ALM and its youth cohort contributed towards FGM being included in the Outcome Document of the Pact for the Future
Signed commitment by the Midwives Association of Kenya to integrate FGM prevention and response in healthcare
Support to the Narok County Eradication of FGM Policy (Implementation Matrix)
First draft of county-level anti-FGM policy finalised in Garissa County, Kenya. AAIK has supported and at times led the development process, working with the relevant authorities, Gender Technical Working Groups, civil society, and survivors. Once approved, these policies will be crucial in ensuring the county’s budget for initiatives aimed at preventing FGM.
1. Isiolo county has also submitted a draft anti-FGM policy to the county government (with support from TGG-ALM)
2. Commitment of all authorities (Mayors, Prefects) in Kolda and Sedhiou to support the fight against FGM.
3. During the high-level advocacy meeting in Somaliland (prior to signing of the policy) there were representatives from Kenya's Anti-FGM Board, women members of parliament, and government officials and sheikhs from Djibouti and Ethiopia contributing to collective advocacy efforts that supported the approval of Somaliland Anti-FGM policy. The participants of the meeting adopted a joint declaration dubbed the Hargeisa declaration, committing to sustained action against FGM and advocating for policy reform

Intermediate outcome 3: Stronger and more resilient civil society movements
The milestone was to achieve, on average, a five point increase in the Social Movement Scorecard score, which measures the strength of different dimensions of the local end FGM social movement such as the extent to which there is a collective vision, youth movement, use of multiple strategies and produces a final overall call and “staging” for the movement. A part of the milestone was to complete baselines in countries where scorecards had not yet been done. This milestone has been partially achieved. The first round of data was collected in Ethiopia, Somaliland and Senegal. In Kenya, the average score dropped slightly from 58 to 55. Small variations in scores may be the result of several factors: differences in the configuration of participants in the exercise over time, facilitation styles, variation in length of time since memorable events or achievements etc. In Y5, analysis of numerical scores will be supplemented with deeper qualitative analysis, for greater insights into processes of change.

Programme reporting and MEL data provide further insights into strengthening of civil society movements. TGG-ALM linked networks to each other and to policy makers to engage in collective advocacy. In Kenya, TGG-ALM continued to provide technical support to COVAW, the national convenor for the Kenya CSOs-led Network on ending FGM since 2024 (which TGG-ALM established). As a result, there has been an increase in membership to the network.

In policy advocacy in both Kenya and Somaliland, there has been increased participation of young people, women and survivors, highlighting their growing influence in shaping policies. During Y4, TGG-ALM also conducted a Training of Trainers for the Survivors Leadership Initiative (SLI), for 20 survivors to strengthen their capacity to cascade SLI and integrate its approaches into their work. Of these, three survivor-led organisations have been awarded SLI grants to support roll-out of SLI-related activities. Follow-up of the trainers found that the majority are engaged in awareness creation and sensitisation endeavours in their communities, while some have established safe spaces for survivors in their communities to meet and share their experiences. In Senegal, TGG-ALM supported survivors to consolidate different networks formed by the survivors into one network, which is now integrated with anchor grantee OFAD’s survivor-led initiative.

Quarterly grassroots advocacy briefing workshops have been held, prepping partners/youth participants for participation in global convenings. This ensures that frontline partners/grantees are well equipped to navigate advocacy spaces where they will be representing the end FGM movement.

Intermediate outcome 4: Instances of product influence/uptake
The milestone for this intermediate outcome was three examples of TGG-ALM and FGM Data Hub product influence or uptake, which has been surpassed. There are at least 11 instances of influence and uptake, including via the Hub’s evidence being referred to in influential, popular publications as being a guide to the field; being selected to deliver presentations before international, scientific audiences at conferences; and having stakeholders sign up for technical support to use tools developed by the Hub[17].
[17] Reference was made to the Population Council’s evidence on what works as serving as guidance for the field in a February 6, 2024 article in The Standard. The Five Foundation invited the Data Hub to sensitise its grassroots grantees to what works, drawing on Hub evidence. The Five Foundation have put together a Resource Bank of ‘What Works to End FGM’, supported by the Hub’s evidence synthesis. Use of the evidence synthesis by Options to provide FCDO with information they had requested on FGM and its linkage with laws and religious leaders (July 3, 2024 email). Oral scientific presentation on learnings from the piloting of the social attitudes tool delivered at an international conference, the October 2024 Sexual Violence Research Initiative (SRVI) Forum. Exposure of a wide range of continental stakeholders (grantees of UNJP, GIZ, and NCA) to the Hub’s tools through the November 2024 Evidence and Learning Forum convened with UNJP. Culminated in four (4) partners signing up to receive technical support from the Hub around the use of social attitudes tool and other FGM research issues. November 2024 TGG-ALM Small Grants Mechanism Grantees Meeting, co-convened by the Hub and Options to strengthen grantees’ understanding and use of tools and templates, including tools co-created by the Hub and Options. Norwegian Church Aid and GIZ are sponsoring their grantees to learn about the Hub-UNJP’s innovative tools in November 2025. Following a November Evidence & Learning convening, five (5) institutions signed up to receive technical assistance from the Hub to use tools to track social norms. This will be offered from Q1 in Y5. These organisations include NOFYL Somalia, UNFPA Nigeria, UNICEF Nigeria, Anti-FGM Board Kenya, Migori County Government Kenya. In Y4, TGG-ALM developed the power of language position paper, a tool to influence reframing of FGM from a cultural, religious, harmful and traditional practice to a violation of human rights. In Y4, the tool was shared on various and adopted by the Global Platform who had a session on reframing the language at CSW69. ACCAF’s FGM prevention and care curriculum is being adopted more broadly in Senegal

In addition to uptake of Population Council’s Data Hub products, there has also been interest in their implementation model on TGG-ALM (technical support approach). The approach involves close support to service delivery organisations to conduct, document, and showcase MEL (including collaborative study design, study protocol and tool development, obtaining international and national ethical clearance, guidance on data collection, and support for data analysis and teasing out programme implications, etc.), drawing on their interventions.  Population Council have received requests from other donors for replicating this model of technical support. Two donors have reached out to discuss this model, and GIZ has requested that the Hub replicate this model to support a cohort of universities and implementing partners to strengthen action research and MEL around FGM/gender inequality interventions. Population Council is in discussion with GIZ on how to formalise this partnership.

The Dashboard is being used to actively share programme results and learning within TGG-ALM. During the reporting period, all partners had begun to engage with the dashboard, uploading their MOVs. One-on-one support for the use of the dashboard has been available throughout the year, with partners taking up this opportunity.

Intermediate outcome 5: Integration
The milestone for this indicator was that 29 institutions would integrate FGM, which has been surpassed, with 36 institutions taking on ACCAF’s FGM prevention and care curriculum: Kenya (25), Ethiopia (1), Senegal (4), Somaliland (6).  In addition, ACCAF’s FGM prevention and response training curriculum was adopted for use by the Senegalese higher education system. The curriculum was reviewed by the Senegalese National Ethics Committee to scrutinise all training resources to ensure they are fit for purpose in Senegal. A further validation process was undertaken by stakeholders under the approval of Ministry of Family Affairs. The curriculum also informed the training of health care workers in a high FGM burden area of Matam region. The training was a collaboration between ACCAF’s strategic partner in Senegal (GRAG) and the Ministry of Health, following training of the Regional Head in ACCAF-led training conducted in September 2024.

This scalable, integrated model has had positive results and has potential for sustainability because it is incorporated into existing structures and functions, as well as the retooling and retraining of human resources for health. It has potential for being scaled and expanded to other geographies with a high burden of FGM and related violations.

Challenges/issues/underperformance
Delays in finalising global goods against original timelines. The delays are the result of a combination of factors: the complexities of finalising publications in a consortium, with multiple perspectives, technical inputs and rounds of review; multiple competing priorities for teams’ writing-up tasks; and challenges/delays in procuring and/or working with consultants, has been a common challenge. To address this, in Y5 target for number of global goods and production schedule has been revised in line with learnings from Y4 (allowing more time for finalisation and lower target overall than in Y4). Additionally, progress towards Global Goods will form part of quarterly partner review meetings, to allow for early identification of risks, delays or support required.

In Y4 the programme has experienced some challenges of underperformance, late submissions and poor quality data from one of the delivery partners. In response Options (lead consortia partner for TGG-ALM) has been closely monitoring the issues and working with the partner to identify support needs and ensure close collaboration and the achievement of agreed targets.

Narok County now has an Anti-FGM policy, and a policy implementation framework has been developed consultatively through the Gender Technical Working Group. However, policy implementation remains a challenge, due to limited financial resources. Advocacy efforts continue towards the county government to call for more resourcing.

In the grants mechanism, disparities remain in the level of participation of persons living with disabilities, with high levels of involvement in Garissa, contrasted by very low numbers in Narok and Isiolo. This highlights the need for targeted outreach strategies and improved accessibility measures. For future programming, the grants teams’ learning aim is to develop tailored inclusion strategies to ensure equitable participation across all regions, an insight that has broad relevance for FCDO and other development initiatives.

Youth participation in global advocacy events is hampered at the global level due to restrictive visa regulations by some countries.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

2023/2024 Annual Review Recommendation	TGG-ALM programme update
Recommendation 1: Options and the Population Council should develop a knowledge sharing and dissemination strategy and annual workplan to support the wide dissemination and uptake of new learning, knowledge and tools being generated by the programme. This should be discussed and approved by FCDO by start of August 2024. FCDO will also promote programme learning and drive uptake, including through strategic engagement with Posts and with key international actors.	Completed / Finalised and shared with consortium and FCDO. Population Council led development of this strategy, and Options led on the workplan, supported by new tools such as dissemination planning templates for each new publication/global good, which have been socialised and taken up by partners. / Given the ongoing importance of dissemination in the final year, a new recommendation to ensure a focus on dissemination activities in in Y5 has been added to the recommendations.
Recommendation 2: Options should lead the development of a programme-wide advocacy workplan for 2024-5 to operationalise the new Communications, Advocacy and Movement Building Strategy. Options should set up a cross-programme advocacy working group to support delivery, drawing in advocacy expertise from across the consortium. (By start of August 2024).	Completed / This recommendation was completed, with the workplan shared with FCDO. There is an active communications, advocacy and movement building working group with representatives from across the consortium. The group meets at least monthly with the objective of supporting delivery, experience sharing and collaboration.
Recommendation 3: TGG-ALM should refine the programme log frame in discussion with FCDO to streamline the number of indicators, removing overlap and reducing the overall reporting burden. UNJP should be assessed separately through its own performance area – this will be taken forward by FCDO in discussion with UNJP. The indicators selected to measure UNJP’s performance should be revisited by FCDO to ensure they are most relevant and reflect FCDO priorities (e.g. around evidence, M&E, scale). By end of August 2024.	Completed / TGG-ALM refined and streamlined the programme log frame, which was approved and finalised by August 2024. The new programme log frame is being used for this Annual Review.
Recommendation 4: Options should strengthen measurement and communication of the programme’s results from its programming and advocacy to enable TGG-ALM to tell a compelling story about the programme’s impact.	Ongoing / Progress has been made this year with the appointment of APHRC to lead on design of the endline evaluation particularly at community level. The communications, advocacy and movement building team have strengthened their routine MEL and reporting, and there is closer collaboration between the CAMB and MEL teams to further strengthen communication of results (e.g. recent POC Kenya, grants webinars).
Recommendation 5: Following the expansion of the Small Grants Mechanism, TGG-ALM should develop and implement a plan to ensure accurate forecasting within 5% variance, working with FCDO.	Completed / The programme has moved to activity-based forecasting and is updating forecasting figures with FCDO twice a month. Additionally, regular meetings between the finance team and FCDO have been agreed to discuss issues as they arise. The 5% variance threshold remains.
Recommendation 6: Options should improve understanding of how well the programme is reaching the most marginalised women and girls, including those with disabilities, and identify concrete actions to strengthen this (by end September 2024).	Completed / The programme gender lead has conducted a mapping of which vulnerable groups are being reached and how, with recommendations on how to strengthen inclusion. A report was submitted to FCDO in October 2025. See advocacy and movement building section above for activities on working with people with disabilities.
Recommendation 7: FCDO should plan a visit to the TGG-ALM programme in 2024 to deepen understanding of the programme’s strengths and learning. This should feed into the next Annual Review.	Completed / FCDO visited Kenya (including Narok) in February 2025.
Recommendation 8: UNJP and FCDO should have quarterly meetings to track progress, risks, and other management priorities (By start July 2024).	Not Completed / Due to the way the progress is tracked it transpired that it would be more efficient to use the biannual Executive Steering Group meetings to track these.

# D: VALUE FOR MONEY

The strategic case for TGG-ALM remains intact based on the outcomes at the end of Y4. Programme partners continue to utilise the Value for Money Framework (VfM) to systematically assess VfM performance and identify areas to improve VfM going forward. The value proposition of TGG-ALM requires that the programme develops approaches that contribute to positive changes in attitudes, and social norms towards ending FGM and generates learning so these can be adopted by others.

Effectiveness:
The core model to accelerate positive changes in attitudes towards ending FGM is demonstrating effectiveness. Proof of Concept has now been achieved in all four countries, and Kenya has moved onto scaling and sustaining approaches. Proof of concept assessments were held in Ethiopia, Senegal, and Somaliland in Year 4, with all three countries showing promising early evidence of effectiveness in generating positive shifts in attitudes towards ending FGM. Kenya reached Proof of Concept stage in Year 3 and in Year 4 has focused on scaling and sustaining approaches.

Advocacy efforts by programme partners have led to stronger commitments to end FGM. At local level, activities such as the Survivor Leadership Initiative have led to survivors independently leading activities to end FGM in their communities. At national level, TGG-ALM has supported government commitments to end FGM – for example, the programme supported the government in Somaliland to prepare for and approve Somaliland’s first Anti-FGM Policy. The UNJP has increased the reach of its initiatives through knowledge dissemination, and by providing technical support to non-UNJP countries and organisations. For instance, in 2024 Liberia, Niger, Sierra Leone, and Tanzania virtually participated in the Joint Programme's annual technical consultation, a forum for experience sharing.

The grants mechanism has been strengthening the broader movement to end FGM, with 82 grantees across the four countries receiving funds. The grant mechanism targets many smaller organisations who have not previously been eligible to receive donor funding, and with support from TGG-ALM have received their first grants. As a result of comprehensive capacity-building, many grantees have subsequently secured additional funding from other sources, reflecting the longer-term sustainability and value of the programme.

Economy: The programme’s key cost drivers are staff, travel, and grants. Fee rates have been managed in line with the programme benchmarks established in the contract.  All travel by programme staff requires a clear purpose and justification. TGG-ALM uses prequalified suppliers and robust procurement processes to ensure the best prices are obtained. To date, the programme has secured £1.2m of additional funding from non-FCDO funders to expand TGG-ALM activities including expanding grants in Senegal and the Survivor Leadership Initiative training. This additional funding is primarily from Foundation for a Just Society International (FJSI), who match funded FCDO’s investment in small grants in Senegal with a total of $1.5million for 3 years covering the period October 2022- October 2025. In addition, Wallace Global Fund granted $50,000 for the 12 months up to and including October 2024 to support the Survivors Leadership Initiative.

Efficiency: Delivery has been on track against the workplan with 14 out of 15 PBR deliverables being delivered on time in Y4, however there have been some delays to the approval and publication of Global Goods, from Options, due to issues such as a lack of sufficient data, reliance on external consultants, and longer than expected review/QA processes. Options have provided assurances that these delays will be reconciled and mitigated against in Y5. The UNJP has robust and clearly defined financial and operational management practices across headquarters, regional, and country levels. Timely disbursement of funds from HQ to regional and country offices is prioritised, and the utilisation of these funds is carefully tracked and assessed to mitigate the risk of funding losses.

Equity: Performance on equity is good with continued evidence that the Girl-Centred Framework is being applied in the development and implementation of interventions to centre the voices, needs and priorities of girls. The programme actively ensures the inclusion and participation of persons with disabilities including addressing practical needs (accessible venues and caregiver support),sign language (including in webinars) and translations. Persons with disabilities are also supported to play leading roles in community dialogues and activities and the grassroots grants mechanism has encouraged and supported organisations led by persons with disabilities to apply for grants. Both the UNFPA and UNICEF have a Disability Inclusion Policy and Strategy providing inclusive strategies. TGG-ALM supports 3 small grantees which are led by persons with disabilities – 2 in Kenya and 1 in Senegal. TGG-ALM gives organisations led by people with disability priority during grantees selection process to encourage more organisations with PWDs to come on board and reduce stigmatisation. Representatives of people with disabilities have also been encouraged to participate in the Grants Advisory Committee where possible. In several countries, the UNJP has endeavoured to operate in remote and hard-to-reach areas, ensuring a commitment to providing equitable access to services and support, however in some countries this is not always as straightforward. On the Annual UNJP Field Visit in September 2024, in Djibouti, we observed that one of the groups of affected individuals that are most challenging to reach are those with disabilities, such as deafness.

Challenging geographies also create inequitable distribution of support services, as in many countries, there are regions where infrastructure is limited, and access (even by car) is difficult. For example, Djibouti is an extreme environment, with incredibly high temperatures year-round and difficult terrain, making accessing some communities incredibly hard or in some cases, impossible. Additional effort and resource is needed in these locations to ensure activities are reaching individuals across all parts of target countries.

Following recommendations from last year, Options have taken a more proactive approach to targeting hard-to-reach areas. Grantees have praised the grants mechanism for providing support in rural areas where donors do not typically fund. Community activities have also continued in conflict-affected areas in Amhara, Ethiopia, and in parts of Somaliland where the security situation has been volatile. The continuation of these activities has meant that support has been provided to some of the most vulnerable women and girls in these regions.

Cost Effectiveness: The assumptions in the business case and rationale still hold and it remains highly likely that the benefits of the programme will significantly outweigh its costs. Y4 was the second full year of implementation for the core models in all countries and the primary focus has been on working towards achieving proof of concept in the three other target countries: Ethiopia, Senegal and Somaliland (Somalia). 730,762 people have been directly supported by TGG-ALM in Y4 of the programme, though it is difficult to quantify the number of cases averted attributable to the programme. The UNJP reached 1,394,813 women and girls with various interventions.

The global landscape means UNJP are likely facing significantly reduced funding in future years, prompting UNICEF and UNFPA to explore funding management strategies. UNJP should consider whether the current number of priority countries allows sufficient depth of delivery in this context.

To strengthen coordination and reduce duplication including cost efficiency of other resources, the UNJP has developed workplans that are complementary and aligned with countries’ national FGM response plans. The UNJP has regular meetings with regional players e.g. with TGG-ALM and GIZ. The UNJP has also been offering technical support and sharing learning with UNFPA and UNICEF regional offices in Southeast Asia, to support the development of programme documents for: ‘Breaking the silence: increasing accountability on addressing FGM in Southeast Asia,’ and ‘Regional Accountability Framework for Ending Female Genital Mutilation/Cutting in South-East Asia,’ both of which are funded by the Australian Department of Foreign Affairs and Trade.

# E: RISK

Overview of risk management

FCDO maintains an overall risk register which is reviewed by the programme team on a quarterly basis. The overall risk profile remains ‘Major’ given the delivery risks and sensitivities inherent in working on ending FGM, particularly in unstable contexts.

Addressing deeply rooted social norms around sensitive, complex, and often taboo subjects, such as FGM, inherently carries safeguarding risks for the populations the programme aims to support. To mitigate these risks, the programme implements a robust 'Do No Harm and Safeguarding Framework'. A dedicated Safeguarding Lead oversees the operationalisation of this framework across the TGG-ALM Programme. FCDO have been alerted to safeguarding incidents, of which there was one case during this review period, demonstrating that the mechanism in place for reporting is working. A greater emphasis has been placed this year on ensuring that FCDO are made aware of safeguarding cases as quickly as possible, and that timely written updates are provided on the status of cases. Programme partners should continue to report any instances of safeguarding incidents as soon as possible and ensure that updates are provided promptly.

The programme works with multiple partners across different geographies and uses due diligence and delivery chain risk management to manage fiduciary risks across the supply chain. We can expect some risk given the funds are being disbursed to local grassroots organisations with relatively low levels of financial management capacity. Owing to the robust financial monitoring and management systems put in place across this programme, four cases of fraudulent activities were flagged. In two of these cases the final investigation found no wrongdoing, and in the remaining two cases, the misappropriated funds were recovered, and the mitigating strategies were strengthened to ensure the same issue could not occur again.

While the risk profile of the geographies that TGG-ALM operates in have not changed significantly over the last year, the programme continues to operate in high-risk areas. These include conflict affected areas in Amhara (Ethiopia) and Somaliland, and Garissa (Kenya) which has security risks due to its proximity to the Somali border. The programme continues to use a risk-based approach balancing the need to continue activities to support the most vulnerable in conflict-affected areas with protecting the safety and welfare of staff. For example, during the implementation of the Social Movement Scorecard Assessment in Q3, TGG-ALM faced security challenge due to the conflict that was happing inside Erigavol. They relocated participants from Erigavo to Gar-adag, the closest safe location at that time. The conflict at the time restricted TGG-ALM’s ability to travel in and out of Erigavo due to the curfew that was mandated by the government restricting movement at the time, so the adjustment was to ensure both the safety of staff and the continuation of the work. The programme has a dedicated Security Focal Point who oversees security across the programme and Options and consortium partners have security policies and procedures which are followed.  UNJP grapple with similar issues on security situations in sensitive political contexts. The leadership team and programme team continue to closely monitor context and implement adaptive programming where necessary.

The programme collaborates with a diverse range of partners, each with varying levels of management capacity. The grants mechanism presents the most significant fiduciary risk due to the distribution of funds to small organisations that sometimes have limited experience in financial management. Substantial effort has been invested in mitigating these risks. During the pre-award phase, the programme undertakes comprehensive assessments of potential grantees’ governance structures, financial management capabilities, and policies related to conflicts of interest, whistleblowing, and other critical areas. When gaps are identified (especially among smaller grantees) the grants team provides targeted training and technical support to establish or strengthen necessary systems and processes. Additionally, the programme utilises an anchor-grant model, providing a larger grant to a lead organisation in each region that also supports capacity-building among smaller local grantees.

An emerging risk in Y4 has been an increase in cyber-attacks against the TGG-ALM website. Although it remains unclear whether these attacks are targeted specifically at the programme, the timing of incidents have coincided with key FGM events. Additional cybersecurity advice has been sought, and the TGG-ALM website’s security has been improved.

Risk Name	RISK	OVERALL RESIDUAL RISK	RISK MITIGATION STRATEGY
C7	Strategy & Context: Context: security situations deteriorate in target countries undermining programme activities	MAJOR	All programme components will monitor security situations carefully and adjust their level and mode of engagement in different countries accordingly. If necessary, we can rebalance activities across target countries
C27	Strategy & Context: / Global rollback of rights and rhetoric in conjunction with pro-FGM campaigners undermining and causing significant impact on anti-FGM interventions. This includes potential repealing of anti-FGM legislation in countries which can embolden pro-FGM movements across TGG-ALM/UNJP focus countries and beyond. This may also specifically impact progress made by TGG-ALM/UNJP in the border regions of TGG-ALM/UNJP Countries.	MAJOR	In countries where TGG-ALM/UNJP does not operate, it cannot not take a lead on actions undertaken by pro-FGM campaigners. The programme will actively support where possible, reviewing communications being shared by CSOs/women's organisations and influencers in countries experiencing potential rollback. We will utilise the FCDO Post Network to monitor these kinds of threats, as well as working alongside colleagues when threats materialise to understand what support is most helpful, remaining aware of the use of anti-Western/anti-colonial rhetoric in some cases, and adapting our response in light of that. This is in line with the wider Quiet Diplomacy approach on FGM. We will also continue to work with UNJP colleagues to monitor these threats in target countries, collaborating across the Donor Group to consolidate the programme’s approach. Where this risk is heightened, the TGG-ALM CAMB team along with key stakeholders in the target country will coordinate a unified response across the consortium and key prominent activists. This can include amplification of stories and messages from activists in country.
F9	Financial & Fiduciary: / Fiduciary: Aid Diversion of FCDO funds including via small grants mechanism	MODERATE	Due diligence through procurement process provides assurance of robust financial management of successful bidders and proven experience of managing downstream partners. Explore ways to reduce FCDO's compliance impact on programme partners in a sensible way whilst remaining within the rules. We expect some risk here due to the size of the grantees, and that TGG-ALM are providing support to partners to comply with our processes. The grant mechanism also has three tiers: small (£2k), medium (~£20k) and anchor grants (~£100k) which allows TGG-ALM to use a risk-based approach to the grants. A TGG-ALM programme manager provides quality assurance of grant agreements and donor compliance, and monitors and tracks grant disbursements whilst, communications and external engagements are overseen by a communications department. The grant team and MEL components have adapted significantly as described under the learnings section below.
O1	Public Service Delivery & Operations: / Operational: Programme does not reach the poorest, most vulnerable, and hardest to reach women and girls	MODERATE	The social norms approach and reaching the most vulnerable is central to the programme theory of change and strategy. Evidence based PEA informs geographical scope and targeting. Will be reviewed through partner programme meetings and reviews. Close monitoring of partners, with robust and regular challenge. Continue to encourage Partners to disaggregate data by disability as well as age, sex and geography to ensure programme interventions capture the most vulnerable women and girls.
S2	Safeguarding: Safeguarding issues are not detected and managed, undermining a Do No Harm Approach	MODERATE	High quality evidence based Do no harm framework and monitoring approach in place. Successful bidders have a track record on the ground and base their work on a deep understanding of social norms change in ending FGM. Results will be triangulated through different measures including innovative approaches to measuring social norms change. For TGG-ALM, this should be discussed as a regular agenda item at quarterly meetings when risks are discussed. Ask Options for quarterly safeguarding reports, and to reiterate to downstream partners the importance of reporting issues to Options as soon as possible who will report them to us. For UNJP, given the nature of this component of the programme being managed by UNICEF and UNFPA, the safeguarding risk is held by the UNJP rather than FCDO.
R0	Reputational: risk of criticism of UK involvement (both in the UK and internationally) and approach.		We have proactively been monitoring this and have put together robust lines to combat criticism. UK public is consistently supportive of FCDO's work on ending FGM. Internationally this will be mitigated through our firm emphasis on supporting African leadership to end FGM, and where issues arise, we will work closely working with comms and spads on this. Programme partners have developed a communications strategy for the programme to engage key stakeholders. Have taken quite proactive steps to rebuild relationship with Five Foundation. Continue to support regional Civil Society Organisations through the UNJP, emphasising the FCDO’s work to support local activists, for example, in The Gambia.
C3	Strategy & Context: / Resources available to delivery partners are insufficient to meet level of ambition (considering population growth).	MINOR	FCDO policy team will continue to lobby other donors to support efforts to end FGM. Work with partners to review prioritisation/programme delivery. FCDO also provide learning and data from the Data Hub; these resources contribute to better use of the resources that are available. FCDO to monitor impact of the end of the TGG-ALM programme has on the ending FGM advocacy space. Ensuring that the UK does not lose the UK voice among the international community on this topic.
D6	Policy & Programme Delivery: / Breakdown of relationship between consortium lead and partners.	MINOR	Delivery via two consortia and UN partners will help ensure risk Consortium lead hold virtual meetings with partners, working groups with consortium members on each group sharing across a range of partners. Key to bring in consortium partners, but Options have been better at managing this of late. Important to continue conversations with consortium partners individually as well as through Options. Possible strategy could be to hold annual meetings to engage with consortium partners and grantees, to share learnings and build relationships etc. Annual Review 2024 recommended that Options set up a cross-programme advocacy working group to support delivery, drawing in advocacy expertise from across the consortium, this will support relationship building.
R10	Reputational: / Downstream partner organisations are also proactively advocating on anti-rights issues in direct opposition to the UK's policy position on preventing roll-back on women's girls' and LGBTQ+ rights	MINOR	We will work closely with partners on continual due diligence of downstream partners to ensure that UK funding does not fund organisations that are actively advocating on anti-rights issues. Team to meet with Options to continually assess activities of downstream partners. If some issue arises specifically to do with LGBTQ rights, team to consult with LGBT Rights Team for advice on handling.

# F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Quality and Timeliness of Narrative Reporting
Quarterly progress reports from Options were submitted in a timely manner, outlining programme targets, achievements, challenges and learnings. Justification was provided for any delayed activities and requests to move payment by results milestone deadlines were made in advance to FCDO.

Financial Management, Monitoring of Assets and Audited Financial Statements
This section focuses on the main delivery partner, Options, reflecting that it is the lead organisation for the component that received the majority of spend under the programme this year. Options and its five sub-contractors continue to provide thorough financial management through narrative and financial reporting and due diligence processes.

The small-grants mechanism is designed to be accessible and responsive to the needs of small, and/or new grassroots organisations to allow decision making and delivery closer to programme regions and be more locally-led. Options has established robust financial management processes which include strong oversight and hands on support for financial reporting, pre-grant training and due diligence processes, and appointing local “anchor” partners to help manage and monitor financial performance.

Invoices were submitted to FCDO in good time for processing. Following recommendations from last year, Options have worked with FCDO to ensure more accurate forecasting, however, there have been a small number of forecasting discrepancies this year, though they have been rectified in a timely manner. Population Council have also experienced some forecasting errors, correction of these errors led to an underspend of £100,147.

Risk and Delivery Chain Maps

Options has a risk matrix and systems for monitoring risk in place; the risk matrix is updated monthly. Options and partners developed a Delivery Chain Map for the programme, providing a comprehensive overview of downstream partners. These Delivery Chain Maps are subject to modification upon each partner’s sub-contract amendments informed by annual budgets ceiling confirmation.

Options has continued to monitor partners’ financial, delivery and contractual performance through regular bi-laterals, consortium wide meetings and quarterly reporting mechanisms. This includes ensuring the partners’ narrative reports, financial reports and the Strategic Relationship Management (SRM) Scorecards are accurate (see below section for summary of SRM scorecard assessment).

Performance of Partners, including summary of the SRM scorecard assessment for each delivery partner.

Over the past year, partners have performed as required, meeting most deliverables within their workplans and have responded to all review feedback.

Options has been designated a “Gold Contract” in FCDO and is required to publish quarterly performance assessment against 3 KPIs on the Cabinet Office website, as part of UK efforts to improve public confidence in the delivery of public services.

Component/lead partner	Budget 24/25		Actual Spend as of Apr 2025	Comments
Options	£6,458,503	£6,830,649		£ 345,146 (Anticipated overspend) / £345,146 was brought forward from future year budgets to FY24/25 - decision approved in December 2024
Population Council	£ 679,808	£ 579,661		£ 100,147 (underspend)
UNJP	£ 0	£1,100,000		No allocation at the start of the FY. Two uplifts made: / 250k in June 2024 / 850k in February 2025

Compliance with the Supply Partner Code

Options has ensured full compliance with FCDO Supply Partner Code of Conduct requirements over the past year.

Options has a robust Conflict of Interest Policy. Staff are provided with training and other materials to support them in identifying conflicts, and senior staff in the UK and overseas manage the conflict-of-interest registers. As an annual requirement, all partners will be undertaking a similar certification process this year towards ensuring full compliance.

Options routinely publishes information on IATI in line with the FCDO’s requirements. All programme partners bar one has self-certified their compliance with IATI requirements, and all subscribe to having their data published by Options under IATI requirements. In addition, Options is a current member of the UN Global Compact and require that all employees read and sign Options’ Code of Conduct which is aligned with the UN Global Compact Principles. Almost all programme partners are already members on UN Global Compact.

Options have due diligence processes to provide assurance that UK Government funding is not used in any way that contravenes the provisions of the Terrorism Act 2000, and any subsequent regulations pursuant to this Act. In addition, Options has maintained high levels of data security in accordance with the Data Protection Act 1998 and any subsequent regulations pursuant to this Act, or new Act and with the General Data Protection Regulation (Directive 95/46/EC). Options staff undertake annual GDPR Trainings as part of ensuring full compliance with GDPR regulations and Options partners have self-certified on undertaking annual training that covers the full range of ethical matters as defined in the supply partner handbook 2020 and ensure records are kept.

UNJP policies on fraud and procurement are publicly available and strictly applied. Programme countries continuously apply assurance activities through external audit firms to support spot checks, audits and micro-assessments. Regular virtual and in-person programme monitoring and follow-up mechanisms are in place, and these are being used to provide any guidance needed for programme implementation. A comprehensive programme annual report and certified financial statements are produced and shared with all donors and partners supporting the Joint Programme.

Compliance with the new cost and transparency requirements, highlighting any profit variance and challenge and use of Open Book Accounting

Over the life of the programme, Options has kept and maintained full and accurate records and accounts of the operation of this contract including the services provided under it and any sub-contracts and the amounts paid by FCDO. Options and its programme partners have been within the approved profit levels for the consortium for the period of operation.

# G: MONITORING, EVIDENCE AND LEARNING

TGG-ALM is an adaptive programme, aiming to strengthen the evidence base for “what works” to end FGM across a wider variety of contexts and to adapt approaches rapidly in response to learning and/or changes in the external environment. This year, there have been significant advancements in the programme's adaptive approach to ending FGM. The Results Framework was streamlined to focus on the most impactful indicators, enhancing the quality of evidence collected through a combination of qualitative and quantitative methods. Key achievements include the development of guidelines to strengthen data collection, capacity-building workshops for grantees, and the implementation of social movement scorecard assessments in Ethiopia, Senegal, and Somaliland. The central MEL team provided technical support and facilitated learning forums, resulting in improved data quality and insights into community attitude shifts. These efforts have informed programming decisions and contributed to the programme's proof of concept, demonstrating the effectiveness of sustained, locally led interventions in changing social norms.

Monitoring and Evaluation

As per the recommendations of last year’s Annual Review, the Results Framework was re-structured this year to streamline the number of indicators and elevate the most meaningful results for Annual Review reporting.

In Y4, The MEL team worked with partners to develop guidelines to strengthen data collection and synthesis processes. It also carried out visits to the four implementing geographies to provide MEL technical support and strengthen capacity of partner teams. The quality and breadth of evidence collected from grantee partners has notably improved as a result, providing clearer insights into community attitude shifts, enabling more informed and timely programming decisions.

The MEL team also supported partners to undertake social movement scorecard assessments in all regions of implementation in Ethiopia, Senegal and Somaliland. The MEL team enabled the movement building and advocacy workstreams to undertake an assessment of the Survivor Leadership Initiative training to establish the effect it had on the participating survivors, and an assessment of the civil society organisations network (CSO Network) in Kenya. The key areas of assessment were network coordination and collaboration, partnerships and joint initiatives as well as challenges and strengths of the network and how this could be improved.

The Population Council’s Data Hub played a pivotal role in supporting TGG-ALM by reviewing data collection plans, analysing monitoring data for ActionAid in Kenya and Somaliland, and evaluating reports from Senegal. They also gathered evaluation data for Amref and ActionAid in Kenya, facilitated meetings and forums for grassroots grantees, and co-hosted an Evidence and Learning Forum on social norms change. Their comprehensive analysis informed the programme’s proof of concept reports, refining interventions for future scale-up.

Evidence

Evaluation data generated by the Population Council’s Data Hub have provided insights into the effectiveness of various TGG-ALM intervention components in shifting key intermediate and outcome indicators, including attitudes, social norms, beliefs, behavioural intentions, and agency.  Quantitative data has been collected using surveys measuring shifts in knowledge/beliefs/agency with girls and boys in participating interventions using a PC-developed survey and has also been collected using surveys measuring changes in key indicators with a broader range of community members in intervention areas.

In Kenya, the analysis revealed that TGG-ALM interventions, such as community intergenerational dialogues and women-only reflection circles in Isiolo County, as well as community or couple dialogues in Narok County, was impactful in influencing community members to completely oppose the continuation of FGM and believe that those in their social networks hold the same belief. These interventions equally influenced participants to espouse more favourable attitudes towards girls who have not undergone FGM; enhanced their likelihood of not cutting their daughters in future; and influenced their perception that men in the community are likely to marry women who have not undergone FGM. These findings have helped provide a rationale for sustaining these intervention components as part of TGG-ALM’s programming.

Learning

Over the last year, the Data Hub has used convenings to capture and share lessons, new evidence, and know-how. This has included a regional convening for grassroots grantees under the Small Grants programme, which brought participants together to gain insights into what they were learning from their own projects, and where they needed support for reporting on these learnings. They also convened an Evidence and Learning Forum around social norms change, which brought together external stakeholders (and selected TGG-ALM partners) to share lessons and tools for capturing such change.

All TGG-ALM partners have contributed to externally facing learning products during Y4, including producing learning briefs, Learning and Adaptation reports and resources - built on programme learning – to support others in the movement to take effective action (e.g. the Youth Advocacy resource). A series of well-attended webinars has also been hosted by TGG-ALM, and this has been embedded into the core workings of the programme and will play a crucial role in Y5.

Key lessons emerging this year include the following:

Validation of existing evidence: at this stage of the programme, several clear lessons reflect the existing evidence base on ending FGM:
Sustained Interventions: Long-term, locally led efforts are crucial for changing entrenched social norms. Consistent engagement over years is key, though ongoing efforts are needed as some FGM practices persist in secretive ways.
- Multi-Level Engagement: Working across households, schools, and communities, and involving all genders, creates an environment where FGM is addressed as a societal issue, not just a women's issue.
- Involvement of Influential Leaders: Engaging health workers, women's networks, and religious leaders enhances intervention effectiveness, providing support and legitimacy to the end FGM movement.
- Safe Discussion Forums: Creating tailored forums for dialogue is essential, allowing communities to challenge deep-rooted norms. Formats should suit local contexts, such as intergenerational or household dialogues.
Emerging and less documented lessons: in addition, lessons are emerging that add to the existing evidence base:
- Transformative Role of Centring Girls and Survivors: Survivor-led initiatives can be more effective than interventions led by external actors because they tap into the lived experiences of those who have been directly impacted by FGM. This learning is apparent in several POC assessments and the evaluation of the SLI.
- Support and Safeguards: Efforts to empower girls as champions to end FGM must go hand in hand with robust support structures around them: adult champions who can support them and help create an enabling environment around them, and strong safeguarding and support structures to help them prevent, mitigate and respond to any risks relating to their work. Based on the recommendation to support emotional wellbeing of survivors, we will strengthen the capacity of SLT cohort members on basic counselling skills to be able to take care of themselves and support other survivors in their communities/interventions.
Re-framing FGM: we describe FGM as violence, a violent criminal act and abuse against women and girls that is generated by inequality and discriminatory social norms, to highlight the physical harm and also the psychological trauma survivors often endure. This re-framing can motivate community members and duty bearers to respond more urgently and effectively.
Generating data on FGM from health settings: The MHF is generating objective data on FGM that is current and in real time from the antenatal clinics. The data can be very useful for policy, programming and investment. ACCAF plan to analyse this data to demonstrate how health systems can generate accurate and objective data on FGM without compromising health care seeking behaviour in clients.
The power of innovative and small granting in building movements: TGG-ALM’s grants demonstrate the effectiveness and feasibility of an unusual and innovative mechanism for channelling support from a bilateral funder to small, often new and/or youth or women-led frontline organisations. With over 80 grantee partners, the grants mechanism is operating at scale, and reaching many thousands of community members in high prevalence contexts.

Date of last narrative financial report	22 April 2025	Date of last audited annual statement	31 March 2025