## Annual Review Template

Title: BRILHO – Energy Africa Mozambique
Programme Value £ (full life): FCDO Business Case £30 million. The Overall Programme is £38 million with Swedish SIDA contribution.		Review date: Sept 2025
Programme Code: 204837	AMP start date: 01/07/2016	AMP end date: 31/12/2026

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A+	A+	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0006865.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006862.xlsx

# A. SUMMARY AND OVERVIEW

## Description of programme
BRILHO – Energy Africa Mozambique is a UK-funded programme that promotes access to off-grid renewable energy for rural households and businesses in Mozambique through a market-based approach. It is the UK’s primary mechanism for delivering its commitments under the Energy Africa Compact, established through a partnership between the governments of Mozambique (GoM) and The United Kingdom (UK) to advance Sustainable Development Goal (SDG) 7 (to ensure access to affordable, reliable, sustainable and modern energy for all by 2030).
Implemented by SNV via a commercial contract, BRILHO has four components:
1. Market Development Fund (MDF): the programme provides start-up grants and results-based financing to help off-grid energy companies to expand and innovate into rural and underserved areas.
2. Demand activation: the programme supports consumer education and awareness on the benefits of modern energy solutions.
3. Evidence and research: the programme conducts Mozambique-focused studies to address knowledge gaps.
4. Policy support: the programme provides technical assistance and capacity building for government and energy stakeholders.
The programme has a total budget of up to £38 million over a 7.5-year period. This includes £11.3 million contributed by the Swedish International Development Cooperation Agency (Sida). As of June 2025, a combined total of £30.4 million has been disbursed by both donors, with £23.6 million coming from FCDO alone. The programme is in its sixth year of implementation, and therefor this annual review presents results and targets based on the full programme value, which includes both UK and Swedish funding contributions. The FCDO business case allows for funding up to £30 million of which £26.7 million is contracted to SNV to deliver the main component of the programme.
Summary supporting narrative for the overall score in this review
The overall programme score is A+ Outputs - moderately exceeded expectations. Three of the four programme outputs have exceeded the defined annual targets, and the four outcomes have surpassed the end-of-programme targets. To date, the programme has enabled over 3.6 million people to gain access to clean energy. Additionally, it has successfully leveraged more than £45.8 million in private sector investment into clean energy services and products.

Output 1 (A+), which assesses the support provided to off-grid energy firms, was exceeded overall, although the milestone for direct jobs created by supported firms was narrowly not met due to post-elections tensions and uncertainty. Output 2 (A++) surpassed expectations, driven by a successful pilot behavioral change campaign that led to an increased uptake of Improved Cook Stoves (ICS). Output 3 (B) was partially achieved, as the programme did not fully meet targets on studies produced and coordination activities. Output 4 (A+) exceeded expectations due to effective support provided on policy and regulation, as well as direct assistance to firms.

In addition to continued progress on energy access, this year marked significant achievements:
- The launch of Mozambique’s first private sector operated green mini-grid in Maqueze, Gaza Province, supported by the programme.
- Receipt of a prestigious award from the UN’s Sustainable Energy for All (SE4All) initiative, recognising the programme as an ‘Africa Change Maker: Energy Heroes 2025’.
- Expansion by Solar Home System (SHS) firms into the productive use of energy, including the establishment of Mozambique’s first electric vehicle taxi fleet, and the introduction of solar-powered irrigation.
These achievements were realised despite a challenging backdrop of nationwide post-election disruption, which affected sales, repayments, and progress with the new government on policy and regulatory matters. The situation improved in the final quarter of the review period, and the programme remains on track, building on the strong results and foundations laid in previous years.

## Major lessons and recommendations for the year ahead
The main lessons and recommendations from the review period are summarised in the two tables below. Given the programme will enter its final year of implementation, the recommendations are focused on ensuring a sustainable and responsible exit.

Lessons Learned
1	Programmes seeking to achieve durable regulatory and policy change should consider embedding technical experts. The use of programme funded embedded experts within ARENE (the energy regulator), was a key factor in this year’s launch of Mozambique’s first privately operated green (solar) mini-grid (operated by UK based ARC Power), for example in helping to secure the concession agreement. This approach could be used in other programmes where regulatory and policy change is needed.
2	There are opportunities beyond the area of energy access that the programme can develop further. Firstly, on local manufacturing where companies supported by BRILHO are producing cookstoves and assembling solar products, thereby capturing more value within the Mozambique’s domestic market. Secondly, the programme has helped firms diversify into productive use of energy, including electric vehicles and solar pumps for irrigation which broaden revenue streams and offer economic growth. Lastly, the programme is creating synergies with other UK programmes - such as solar-powered irrigation systems for the MAJI (agriculture) programme, and solar mini-grids which could power the community water systems supported by the T-WASH2 (rural water and sanitation) programme.
3	Financial sustainability remains a long-term goal for ICS and SHS companies in Mozambique and needs a holistic approach. This is a common challenge across off-grid energy markets in Africa. Financial sustainability is likely to depend on several factors: an improved regulatory environment, increased scale to reduce unit costs, and better access to affordable finance. It will be essential to address the barriers faced by this subsector through a holistic approach that ensures the active participation of all relevant public and private stakeholders (government, regulators, development partners, financial sector).
4	Subsidies will continue to be needed to reach ‘last-mile’ customers after BRILHO. To make energy access affordable and commercially viable, subsidies will still be required to reach the lowest income households in Mozambique after the BRILHO programme. Without these subsidies, it is likely that firms will only be able to reach higher income households. Following BRILHO, other programmes such as the World Bank’s Pro Energia can continue to subsidise firms. The UK funded End User Subsidies lab is building evidence on how the wider sector can sustainably fund last mile access.
5	Sustained UK leadership will be important to build on the programme’s success and ensure that off-grid markets continue to deliver increased energy access in rural areas. BRILHO has played a catalytic role in the evolution of Mozambique’s off-grid energy market. For example, BRILHO’s results-based financing supported half of all quality verified SHS sales between 2020 and 2024 and accounted for over 60% of ICS sales since 2021.[1] UK leadership and engagement can continue after the end of the programme through other investment, influencing, and expertise.
[1] BRILHO_Transforming-off-grid-energy-access-in-Mozambique-2024_final.pdf

The lessons learned have informed the general recommendations outlined below. Together, these recommendations aim to ensure a responsible exit as the programme moves into its last year with UK and SIDA funding. This should protect the investments and progress achieved to date, while preparing for the transition to FCDO’s next phase of support for energy access in Mozambique.

Achieving universal energy access[2] in Mozambique remains a long-term goal, and the UK should continue to play a role in this effort, given the experience and success from BRILHO which has been instrumental in growing the off-grid energy sector. However, with the FCDO expected to operate with reduced ODA resources (grants), future support should focus on delivering targeted expertise and mobilising UK investors. This approach should remain aligned with the Government of Mozambique’s Energy Transition Strategy and the multilateral development banks’ Mission 300.
[2] SDG7 progress report Tracking SDG 7 | Progress Towards Sustainable Energy

Recommendations
#	General recommendations	Responsible	Timeline
1	Recommendation 1: UK should organise Heads of Mission from development partners that have investments in the off-grid sector; to engage the newly appointed Ministers of Energy and Finance to advocate for consistent and supportive regulatory implementation. While there have been some regulatory improvements over the past year (such as the introduction import tax and VAT exemptions for certain firms) implementation remains inconsistent. This uneven application continues to drive costs and customer prices, ultimately constraining sales growth. The risk is that without policy being implemented, firms cannot expand (undermining achievement of SDG7 and the Energy Transition Strategy), and the gains to date may even be reversed.	FCDO - SRO	By end of 2025; ongoing as needed
2	Recommendation 2: SNV should assist firms to respond to the new Mozambique carbon market regulations (expected to be finalised by end of 2025). These should provide market confidence for carbon credit buyers, and opportunities particularly for ICS firms. There may also be risks depending on level of taxes applied. The programme should advise investee firms on the implications, and how they can benefit and manage any new costs. In addition, advice on how firms can benefit from the compliance markets (Article 6 trading and CORSIA).	SNV - TL	By March 2026 (after carbon market regulation enacted)
3	Recommendation 3: SNV should assess the financial sustainability of BRILHO firms, and map sources of finance available. The team should carry out an assessment of each’s firm’s financial sustainability, for example using a set of financial KPIs (drawing on work by GOGLA[3], AECF and others). Given the need for continued significant support for subsidies/ grant funding to last mile access, the programme should propose how these can continue to be provided - whether via donors, government, climate finance, or cross-subsidies, drawing on evidence from the GOGLA end user subsidy lab[4]. Future funding to the sector could include the World Bank’s Pro Energia and SIDA’s Mais Sol, and potentially UK investment from sources such as BII+. Also, BRILHO is piloting an innovative ‘receivables aggregator system’ (allowing companies to package and sell expected repayments to provide short-term working capital).	SNV - TL	By June 2026
4	Recommendation 4: The programme team should prioritise developing further green mini-grids. Having established the first private GMG, the programme can build on this and support further concessions planned in Gaza province in the rest of the year. This technology offers higher Tier access, and more potential for productive use and economic development compared with SHS. It should also explore the link with rural water access (the public fund PRONOSAR as a user for water system pumps), given SNV also manages FCDO’s TWASH2 water access programme in Mozambique.	SNV TL and FCDO SRO	Ongoing
5	Recommendation 5: SNV to measure and report indirect benefits. There are numerous benefits not captured in the formal log frame reporting, including household savings, health, environmental, security, education, and SME growth and innovation. These should be captured before the end of the programme, for example through case studies or regular reporting, to showcase the programme’s full impact, demonstrate the sector’s broader importance to rural development, and to encourage investment.	SNV -	Via quarterly reporting and; ongoing
6	Recommendation 6: Conduct an impact evaluation of the programme as it enters its final phase to accurately measure the results achieved over the implementation period. The evaluation should assess the share of household benefits due to cost savings versus income generation, including the extent to which the lowest income communities have been reached. Findings from the evaluation should be shared with the multilateral development banks to inform their Mission 300 (energy access programming) approach.	SNV TL/FCDO SRO	To start in November 2025 and end in December of 2026.
7	Recommendation 7: In final phase of the programme, SNV should launch a targeted push to strengthen safeguarding and fraud awareness among participating businesses. A plan to strengthen these mitigation risks should be developed by December 2025, including considerations on revamping messaging on safeguarding and fraud; and a refresher training to be provided to grantees and frontline staff.	SNV/FCDO Safeguarding Champion	By June 2026
[3] PAYGo PERFORM KPIs - GOGLA
[4] End User Subsidy Lab - GOGLA

# B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
BRILHO’s theory of change (ToC) describes how its activities lead to the changes necessary to achieve the intended impact of ‘improved access to clean, affordable, reliable energy – as set out in the Sustainable Development Goals, leading to money-saving, better well-being and better livelihood opportunities for poor people.’ Interventions under the programme components are designed to deliver the outcome of a “stronger off-grid renewable energy market with more private sector companies with functional business models approaching commercial viability. This leads to more rural households and businesses with increased energy access through innovative private sector provision and investment in off-grid renewables”. The theory of change as set out in the business case is added below.

Based on the current programme performance, the theory of change and the underpinning key assumptions remain valid. The set of interventions aimed at businesses, off-grid technologies, the policy environment and consumers, are largely achieving the desired impact and outcomes. No changes to the programme’s theory of change (ToC) are proposed for this review. Similarly, the evidence identified in the Business Case is still valid, reinforced by the programme's continued good performance. The programme was extended last year, resulting in an expansion of both the outcome and impact targets. Although the UK’s funding contribution for this financial year was reduced, the targets and Theory of Change were not adjusted, due to additional contributions from SIDA. This maintained the programme at the same funding level and scope as originally agreed when the extension was approved.

## Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The outputs (financial and technical support to firms, awareness, and policy advisory services) are supporting progress towards the impact and outcome results of more people and businesses with access to energy (both electricity and improved cooking services). Progress against each of the expected impacts and outcomes of BRILHO is on track and it is summarised below:

Impact 1: Number of rural households that accessed off-grid renewable energy products that improved their economic situation.
During the reporting period, 226,667 households gained access to new or improved off-grid renewable energy (of which 115,615 through SHS and 111,052 through ICS). This represents an additional 1,133,335 people with access to energy, assuming 5 persons per household[5]. BRILHO has enabled over 3.6 million Mozambicans to have access to energy, representing more than 10% of the country’s population[6]. The change in households’ economic situation was measured in the BRILHO conducted mid-term and micro economic impact study, both of which demonstrate the improvement of households’ economic situation (including financial savings resulting from using SHS and ICS compared traditional lighting and cooking sources).
[5] The assumption of 5 persons per household is based on a Mozambique demographic survey and is consistent with surveys carried out by the BRILHO programme
[6] It is possible that some households have purchased both a SHS or clean cookstove with support from the programme. However, these are expected to be relatively rare as ICS companies supported by BRILHO operate in peri-urban areas, often with grid connections, whereas SHS companies target rural areas in a wider range of provinces.

Impact 2: Number of businesses that accessed off-grid renewable energy products that have improved their economic situationDuring the reporting period, a notable portion of energy access initiatives demonstrated dual benefits. Specifically, 8.52% of customers utilising Solar Home Systems (SHS) and 5.05% or deployed Improved Cooking Stove (ICS) units served both productive uses of energy (PUE) and domestic needs (PUE is defined as where customers run their own businesses or another economic activity). This overlap highlights the growing role of decentralised energy solutions in not only improving household living conditions but also enabling income-generating activities.
Findings from a microeconomic impact study further underscore the significance of this shift. Households adopting SHS and ICS technologies reported a marked improvement in their economic situation. This positive development is primarily linked to cost savings from reducing dependence on traditional, and often more expensive, energy sources for lighting and cooking. By lowering energy expenses and enabling small-scale economic activities, such as home-based businesses or extended hours of operation, these clean energy solutions are playing a critical role in enhancing household resilience and economic empowerment, especially in vulnerable communities.
Outcome 1: Additional number of people benefitting from the use of improved cooking solutions (Cumulative)
There were 578,075 people (111,052 households) additionally benefiting during the year from improved cooking stoves, continuing the growth of previous years. The programme has now reached 1,609,275 people cumulatively who have access to improved cooking solutions, ahead of the 2025 milestone of 1,285,000. This continues the rapid growth of previous years.

Meetings with beneficiaries and independent surveys confirm significant savings on charcoal costs due to using more efficient stoves, in addition to health (reduced smoke) and environmental benefits (lower carbon emissions and deforestation). The penetration of ICS in lowest income, rural areas remain a challenge. However, most BRILHO supported firms are operating in peri-urban areas where a form of stoves is already used (rather than open fires).

Outcome 2: Number of people with improved access to off-grid renewable energy from SHS or a green mini-grid (AC or DC) (Cumulative)
Regarding access to electricity, 578,075 people (115,615 households) have directly benefited from a new or improved access to off-grid renewable energy during the period. In total, 2,051,235 people now have improved access to electricity due to BRILHO, exceeding the 2025 milestone of 1,875,000 people. This year, green-mini grids also contributed to the outcome for the first time, with the new 50kW GMG in Maqueze, Gaza province adding 349 household connections as well as for firms and two public institutions (1,745 people is currently benefiting from connections from GMGs).

The use of RBF continues to lower prices and the PAYGO model makes purchases affordable for many households. SHS firms report challenges due to availability of working capital, foreign exchange shortages, and high levels of missed repayments, which pose a risk to further expansion, particularly to ‘last mile’ rural areas.

Outcome 3: Number of businesses with access to reliable renewable energy either through an ICS, an isolated solar system or a green mini-grid (AC or DC) (Cumulative)
The programme directly reached 51,204 businesses with improved access to energy, surpassing the 2026 target of 31,500. This marks a significant increase from last year’s 35,748 businesses. The growth is partly attributed to the implementation of the first recommendation from the previous annual review, which involved revising sub-grantee agreements to ensure continued Results-Based Financing (RBF). The revised agreements included a gradual reduction of the RBF value through reverse auctions, expanded access to higher-tier products/services, and continued the use of Catalytic Grants for innovation or unexpected needs. Additionally, ARC Power’s mini grid in Gaza province is now operational, contributing to the number of firms with access.

Outcome 4: Amount of additional private funding mobilised for BRILHO interventions. (Cumulative)
Over £9.5m was mobilised during the past year. A leverage ratio of 1: 2.4 is estimated (i.e. for every £1 invested by BRILHO, £2.4 has been mobilised from private investment). This shows that, despite challenging financing conditions (for example obtaining local currency finance), the RBF and catalytic grants to firms have been effective in attracting further investment, contributing to sustainability and the programme’s value for money.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
As noted, BRILHO continues to deliver impressive results at output and outcome levels, helping to increase access to energy in rural communities in Mozambique. BRILHO is a key part of the British High Commission in Maputo Country Business Plan, contributing to the outcome on energy transition, under the climate and nature goal. It is also delivering progress on Mozambique’s Energy Transition Strategy (which aims for modern energy access for all) and it is aligned with the Mission 300 international energy access coordination effort launched this year led by the World Bank and African Development Bank.

BRILHO offers good value for money when benchmarked against other energy access programmes supported by FCDO and development partners (see value for money section below for details). The annual review process found evidence that the programme’s use of results-based finance (RBF), catalytic grants, and targeted technical assistance continue to be effective in reducing the energy access gap. Feedback from investee firms, customers, and government departments and agencies was highly positive. The programme should therefore continue into its final year to protect the investments made to date, to make further progress, and to ensure a responsible exit and the UK’s move towards other forms of UK support to the sector.

# C. DETAILED OUTPUT SCORING

Output Title	Businesses have access to finance and technical assistance (TA) to offer off-grid energy products and related services for rural households and businesses. Supported businesses have improved sustainability and have a wider impact on the local economy.
Output number:		1	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of ICS, SHS and productive energy/mini-grid businesses supported with TA, finance, or both continuing to be operational businesses 12 months after the start of support. (disaggregated by TA, Finance and both) (cumulative)	9	Milestone moderately exceeded / The programme supported 11 businesses, of which 6 SHS firms (Engie, Dynamiss, Epsilon, Ignite, Uranus, GLP); 4 ICS firms (Burn, Community Carbon, MozCarbon, Sogepal) and 1 GMG firm (ARC Power)
1.2 Number of jobs created in supported businesses (disaggregated by gender, age, business size and geography) (cumulative)	2413	Milestone moderately not met / The programme created 2401 jobs (892 women, 1509 men – based on firm reporting)
1.3 Number of MSME jobs created as a result of BRILHO interventions (disaggregated by gender, age, business size and geography) (cumulative)	44,000	Milestone moderately exceeded / BRILHO created 51,207 MSME jobs based on survey results

Briefly describe the output’s activities and provide supporting narrative for the score.
Eleven companies were supported by the programme with RBF, catalytic grants, and technical assistance by the end of the review period, which is also above the milestone. Three companies had contracts terminated due to poor performance, while two graduated from BRILHO support, having completed all targets. In addition to the financial support, BRILHO provided bespoke technical assistance on credit management, investment readiness, and matchmaking with potential investors. Feedback from firms has been strongly positive on how the technical assistance has helped to improve business models.

Companies selling solar home systems (SHS) reached 115,615 households during the year, using the PAYGO method. The programme also expanded its support to investee firms on ‘productive use’ projects, in addition to energy access, to improve accessibility and livelihoods. For example, Epsilon signed a contract extension to incorporate e-mobility (supporting local assembly of electric ‘tuk-tuk’ vehicles), and other productive use products such as solar water pumps for irrigation. By diversifying towards productive use, SHS firms can add another revenue stream to manage risks such as cashflow and non-repayments. One other innovation is Ignite’s move towards an ‘energy as a service’ payment model (i.e. a leasing approach), which has lowered consumer costs and has increased uptake compared to PAYGO.

On improving cooking solutions (ICS), companies have reached 111,052 households’ sales this year. However, compared with SHS the geographic scope is more limited, and firms have not managed to move into remote and rural areas. The affordability of ICS is also dependent on voluntary carbon markets, which have driven price reductions even further than RBF, though are volatile: at the time of the review, voluntary carbon market (VCM) prices had dropped to $1 (down from $8 or higher). The change in carbon prices has led to one ICS firm (Community Carbon) to reduce production in their factory in Maputo. If firms were able to access the compliance (formal) carbon market, with higher and more stable prices, this would be a major benefit. Firms are also concerned that the new carbon market regulation may set taxes at a level that is not affordable and introduce new requirements - another ICS firm mentioned to the review team that a decision on setting up a new Mozambique manufacturing plant is pending on the new regulation.

On green mini-grid (GMG), a first privately operated green-mini grid was launched in Maqueze, Gaza Province. This represents a major programme success and to the country, given mini-grids will be crucial for ensuring access in many areas where it is not viable to extend the national grid, alongside with SHS. RbF and grants applied to the capex have helped to bring the tariff to a level that is acceptable for the developer and affordable for SMEs and some households, though they are still above the EDM grid tariffs ($25c/ kWh) compared with $14c/kWh) due to the higher costs in remote areas. The GMG is operated by ARC Power which is planning to expand in Gaza province during the year ahead. Technical advisory support was also provided to GMG businesses, including assistance on pre-registration requirements to operate mini-grids concessions.

The number of jobs created directly last year by investee firms hiring staff (2401) have been mostly maintained, though there was no further direct job creation in BRILHO-supported businesses this year. While some firms were able to expand with current levels of staffing, it also reflects the challenging post-election political and economic conditions faced during the year, which created uncertainty and made firms reluctant to hire new staff.

The programme also measured jobs created indirectly, due to the productive use of energy (i.e. energy used for income generation activities). The estimate is based on surveys conducted, using the percentages of ICS and SHS units deployed which have mixed use (domestic as well as productive use), with one job created per each unit used for productive use. Based on this method, the programme created 26,183 jobs indirectly for the review period, with a cumulative total of 51,207 jobs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes during the past year or planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
See Annex 1 for a summary of progress against last year’s recommendations (recommendations 1 and 4 are relevant for this output). Section A contains lessons learned and recommendations for the year ahead.

Output Title	Better educated and engaged rural population with understanding of the benefits of off-grid renewables and related services e.g. mobile money and pay-as-you-go (PAYG) systems.
Output number:		2	Output Score:	A++
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Percentage of targeted household and MSMEs adopting the technology	8%	Milestone substantially exceeded / The programme reached 24% of targeted household and MSMEs

Briefly describe the output’s activities and provide supporting narrative for the score.
For the review period, the programme conducted the Vila Livre de Fumo (Smoke-Free Village) pilot campaign, which enabled to measure the uptake of ICS by households. The pilot was conducted in 4 neighbourhoods in two communities in the Boane district, Maputo Province, reaching a total of 2,131 households. This campaign consists of a behavioural change communication strategy aimed at encouraging the transition from traditional cooking methods to improved and clean cooking technologies. This included sensitisation activities, door-to-door visits, village meetings, cooking fairs, and school days. The campaign concluded during the reporting period

The campaign exceeded its milestone target, with one in four households (24%) purchasing an improved cookstove during the campaign, and 95% of these attributing this decision to the pilot. This was a much higher rate than the milestone, so this Output is scored as an A++. The success of the pilot was due to the effective campaign including the use of trusted agents and demonstrations. It also reflects that the two target communities were in peri-urban areas (Maputo province) with higher incomes than in rural settings and are therefore more able to respond to the campaign with purchases of cookstoves. It would however likely be challenging to replicate the success rate in rural areas with higher poverty levels.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes during the past year or planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
See Annex 1 for a summary of progress against last year’s recommendations (no specific recommendations for this output). Section A contains lessons learned and recommendations for the year ahead.

Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No
Output Title	Improved availability and access to relevant information about the supply and demand of off-grid renewable energy in Mozambique.

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of studies (from Mozambican institutions) completed and disseminated on improving understanding of success factors for clean energy companies in Mozambique	4	B target partially met. For this review period, 3 studies were completed: lean data insights aggregate report: round 3, transforming off-grid energy access in Mozambique: The Brilho programme contribution (2019 – 2024) and Replicating Smoke Free Villages in Mozambique – Endline report.
3.2 Number of coordination meetings, shared organisation of events, coordination on enrolment criteria or sharing of best practices held with other Mozambican programmes and other FCDO offices working on Energy Africa	25	B target partially met. For this review period, 16 coordination meetings were held. / 4 - GIZ (Quarterly) / 1 - Lessons Learnt Meeting (November 2024); / 1 - KFW (November 24); / 1 - RenMoz (April 2025); / 1 - Sub-Working Group on Technical Assistance (May 25); / 1 - Donor Coordination Meeting on Mini-Grid Country Platform (May 25); / 1 - Donor alignment on Mini grids in Mozambique (Nov 24); / 1 - Energy Sector Working Group High (ESWG) level meeting (June 24); / 1 - ESWG Country compact (June 2025); / 1 - Donor visit to Niassa (April 2025); / 1 - Country Platform donor meetings (April 2025) / 1 - Mozambique Off-grid energy sub-group Meeting (Sept 25); / 1 - Energy sector working group meeting (August 2025).

Briefly describe the output’s activities and provide supporting narrative for the score.
During the reporting period, BRILHO programme facilitated the development and completion of three studies. However, this fell short of the programme’s target of four studies. In relation to the second performance indicator, only 16 coordination meetings were conducted out of the planned 25, resulting in another unmet target. Despite these efforts and partial achievements, the overall objectives associated with this output were not fully realized.
On the first performance indicator, studies conducted included Lean Data consumer insights by 60 Decibels, where it interviewed 411 customers from 9 BRILHO-supported SHS and ICS companies. The respondents revealed that over 90% experienced improved quality of life after purchasing these products. The second study which was an analysis of BRILHO’s impact from 2019–2024 which showed its key role in shaping Mozambique’s off-grid energy market. Notably: (i) BRILHO’s results-based financing supported 50% of all quality-verified SHS sales (2020–2024) and (ii) It contributed to over 60% of ICS sales since 2021.
The third study was a pilot of Behavioural Change Model for ICS adoption, inspired by Cambodia’s Smoke-Free Village initiative. Using Behaviour Change Communication (BCC), the pilot reached 2,131 households in Boane District. A baseline survey assessed demographics, cooking habits, and attitudes. After nine months, an endline survey of 1,316 households measured changes in stove use, clean cooking behaviours, and perceptions. This demonstrated strong progress in stove adoption and usage. Household ownership of improved or clean stoves rose from 51% to 67%, while exclusive reliance on traditional stoves dropped from 49% to 33%. One in four households purchased a new stove during the pilot, with 95% attributing their decision to the intervention.
Improved charcoal stoves were the most popular. Primary stove usage shifted significantly: 33% now use improved stoves, 27% use clean stoves, and traditional stove use fell to 40%. In Eduardo Mondlane and Gueguegue, nearly half of households now use improved or clean stoves as their main cooking device. The clean cooking score increased from 29.5 to 39.1, reflecting a positive shift in cooking practices. Over 25% of households improved their energy ladder classification. Awareness of clean cooking technologies reached 100%, driven by campaign activists (87%) and sales agents (48%). Key motivators included fuel savings (44%), faster cooking (29%), and reduced smoke (14%).
However, adoption of smoke-related safety behaviours was uneven. Households using improved stoves showed improvement, while those using clean or traditional stoves saw a decline, possibly due to lower perceived risk. Cost remains the main barrier, especially in Eduardo Mondlane (61% vs. 17% in Gueguegue). Access improved significantly, with only 4% unaware of where to buy clean stoves (down from 26%). Safety perceptions of LPG and electric stoves were overwhelmingly positive.
On the second performance indicator, during the reporting period, the programme actively engaged stakeholders through both bilateral and multilateral coordination efforts. Out of the 25 planned coordination activities, 16 were successfully completed, falling short of the target.
A notable example was the RenMoz 2025 Conference, organized by AMER (Associação Moçambicana de Energias Renováveis) and held in Maputo. This event provided coaching to companies on effective pitching techniques for matchmaking sessions. Three companies from the BRILHO portfolio, Epsilon, BURN, and Dynamiss participated in these sessions. The conference served as a valuable platform for showcasing their business potential and fostering strategic connections with key stakeholders in the renewable energy sector. The following coordination meetings were held during the reporting year:
4 - GIZ (Quarterly);
1 - Lessons Learnt Meeting (November 2024);
1 - KFW (November 24);
1 - RenMoz (April 2025);
1 - Sub-Working Group on Technical Assistance (May 25);
1 - Donor Coordination Meeting on Mini-Grid Country Platform (May 25);
1 - Donor alignment on Mini grids in Mozambique (Nov 24);
1 - Energy Sector Working Group High (ESWG) level meeting (June 24);
1 - ESWG Country compact (June 2025);
1 - Donor visit to Niassa (April 2025);
1 - Country Platform donor meetings (April 2025)
1 - Mozambique Off-grid energy sub-group Meeting (Sept 25);
1 - Energy sector working group meeting (August 2025).

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes during the past year or planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
See Annex 1 for a summary of progress against last year’s recommendations (recommendation 2 is relevant for this output). Section A contains lessons learned and recommendations for the year ahead.

Output Title	Improved policy and regulatory environment for off-grid renewable energy in Mozambique. Strengthened FUNAE able to help private sector navigate off-grid regulatory environment.
Output number:		4	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of operational policies/regulations implemented	2	A+ Moderately exceeded expectation. (4) four priority policy areas have been addressed in the new off-grid regulations: i) Regulation on Access to Energy in Off-Grid Areas; ii) Concession Award Regulation; iii) Tariff Regulation, and iv) Interconnection Regulation for mini-grids in off-grid areas.
4.2 Number of private sector companies advised by / FUNAE/ARENE on / Mozambique's off-grid energy rules and regulations / (cumulative).	80	A+ Moderately exceeded expectation. The programme has advised over 80 companies through various initiatives: i) Sessions conducted by ARENE for off-grid companies, introducing the regulations and the necessity to register via the E-Lisefor platform, ii) ARENE's participation in off-grid conferences (e.g., RenMoz) and fairs (e.g., FACIM), among other events.

Briefly describe the output’s activities and provide supporting narrative for the score.
On this output the BRILHO programme has moderately exceeded expectations in its performance against key indicators. Regarding the policy/regulations implemented, the programme successfully implemented four operational policies and regulations, doubling the initial target of two. This reflects strong progress in supporting the regulatory framework for off-grid energy. On advisory support to companies, the programme also exceeded its target of advising 80 companies on Mozambique’s off-grid energy rules and regulations through ARENE and FUNAE. While the exact number was not specified due to estimation-based reporting, available evidence confirms that the milestone was surpassed.
Regarding the first performance indicator, as part of its operational plan to support the implementation of the Regulatory Framework for the Off-Grid Energy Sector, BRILHO organized a training session. This session was specifically designed for technical staff from the Fundo de Energia (FUNAE) and aimed to strengthen their understanding of the regulatory instruments governing the off-grid energy sector in Mozambique.
The training session sought to familiarize participants with the key components of the Regulatory Framework and to encourage dialogue on its practical application. It also aimed to enhance institutional capacity for effective implementation and oversight of off-grid energy initiatives. During the session, participants conducted a detailed analysis of several legal instruments, including the Regulation on Access to Energy in Off-Grid Areas, the Concession Award Regulation, the Tariff Regulation, and the Interconnection Regulation for Mini-Grids in Off-Grid Areas. These discussions provided a comprehensive understanding of the legal and regulatory landscape shaping the development of off-grid energy solutions in the country.
In addition to the legal review, the session facilitated in-depth discussions on FUNAE’s role in implementing the regulatory framework. Participants shared experiences from past rural electrification projects and explored the evolving role of the private sector in the management and operation of Green Mini-Grids (GMGs). These conversations highlighted the importance of collaboration between public institutions and private stakeholders in achieving sustainable energy access.
For the second performance indicator, the programme advised over 80 companies through various initiatives led by ARENE, including sessions for off-grid companies, introducing the regulations and the necessity to register via the e-lisefor platform and through ARENE’s participation in off-grid conferences (e.g., RenMoz) and fairs (e.g., FACIM[7]), among other events.
[7] Maputo Internationa Trade Fair which is the largest corporate and business exhibition in Mozambique, showcasing of national products and potential, covering all sectors of economic activity on both national and international level.
The advisory process included direct support for operationalizing the off-grid regulatory framework through the secondment of three additional off-grid energy specialists to ARENE. These specialists played a key role in the development and testing of ARENE’s digital platform, e-lisefor, which facilitates the submission of concession-related documents by private companies for Green Mini-Grid (GMG) projects.
The platform was enhanced to accommodate both public tenders and spontaneous applications, and it also allows companies to request information from ARENE regarding GMG site availability prior to submitting their documentation.
In addition to platform support, advisory services were provided to Arc Power/Moetse during their mini-grid concession process. This included assistance in drafting the legal response letter to the Administrative Court, which addressed the Court’s request for clarification before granting final approval of the concession.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes during the past year or planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
See Annex 1 for a summary of progress against last year’s recommendations (recommendation 5 is relevant for this output). Section A contains lessons learned and recommendations for the year ahead.

# D: VALUE FOR MONEY

Key cost drivers and performance
The table below sets out the main programme expense items to date from the total allocated budget. The largest share of costs is results based finance (RBF) payments and catalytic grant payments to firms, followed by milestone-based payments to the implementing partner. The programme’s costs here are linked to achievement of RBF targets and delivery milestones.

Budget line/ cost driver	Expenditure to date	% of expenditure
Inception costs	£0.6m	2%
Project reimbursable expenses and payments by results	£1.9m	6%
Milestone based payments	£8.7m	29%
Fund disbursements (RBF and catalytic grant payments to firms)	£19.2m	63%
Total	£30.4m	100%

VfM performance compared to the original VfM proposition in the business case
Performance against the programme’s value for money (VfM) metrics is summarised below:

Economy: BRILHO staff costs (international and local rates) remain in line with the contract, which was competitively procured. Programme expenses are below 3% of overall expenditure. The implementing partner’s overhead costs (non-project attribute costs) are capped within the limit agreed by FCDO.
Efficiency:
Analysis by the programme found that the overall cost per household with access to energy was €34 per household, which compares favourably with other energy access programmes operating in Mozambique (including EnDev, AECF, and Pro Energia) which range from €121 to €170 per household.

The costs of programme disbursements per unit have fallen over the past year for both SHS and ICS across the different Tiers (levels of access).[8] SHS unit costs fell by up to £8 and currently range between £30 and £130 per unit depending on specification (Tier 1 to 3). ICS unit costs also decreased across Tiers 1-3 by between £2-3 per unit, with a range between £11 and £27 from Tiers 1 to 3. These reductions were driven by an increase of sales which reduced the amount of support per unit.
[8] The multi-tier framework indicates the level of energy access, with a Tier 1 solar home system or cooking stove providing a more basic level of service than Tier 3

The average cost per job created directly in BRILHO-supported firms was £6,906, an increase from £6,575 per job last year. While firms have not increased staff, in part due to the economic situation, they have still been able to expand with the same number of employees (higher sales per employee). This is similar to the previous year, and, together with falling costs per unit, suggests businesses are becoming more profitable and efficient.

Effectiveness:
The ratio of private sector investment leveraged due to BRILHO support is estimated at 1: 2.4, a small increase of £0.1 compared to last year. This means for every £1 invested by BRILHO, £2.4 has been mobilised from private investment - over £9.5m was mobilised during the past year from loans and equity financing (estimate based on partner reporting).

The ratio of jobs created indirectly by businesses supported by BRILHO was 2,546 at the end of the reporting period, an increase from 1,352 jobs reported last year.

Equity:
Of the 3.6m people benefiting from improved access to energy due to BRILHO, the programme estimates that over half (53%, or 1.9m) are women. There were also 345,612 women benefiting from jobs and/or higher incomes from BRILHO interventions. Of the 2,410 jobs created directly by BRILHO portfolio companies, 892 were women (37%).

During the reporting period, the RBF GESI incentives within BRILHO’s portfolio continued to encourage grantees to hire and promote women in both technical and leadership positions, as well as to enhance their technical skills. This included implementing the Women's Economic Empowerment Initiative within BRILHO’s portfolio. BRILHO also held a graduation ceremony for 12 participants of its long-term course on Gender and Leadership, with attendees from FUNAE, BRILHO companies (Ignite, GLP, Burn), and the Industrial and Commercial Institute of Nampula.

Assessment of whether the programme continues to represent value for money
Based on the mid-term review, output performance over the review period, and performance against the value for money (VfM) metrics, the programme's overall VfM remains strong. The programme is exceeding its targets and delivering results ahead of schedule and has a lower cost per household with access to energy when compared to similar programmes in Mozambique, as noted in the efficiency section above.

# E: RISK

Overview of risk management
The overall risk level of the programme remains moderate. Both FCDO and the implementing partner continue to monitor risks on an ongoing basis. A comprehensive risk register overing a range of risk categories, is maintained and updated regularly. Written updates are provided to FCDO and discussed in detail on a quarterly basis.

During the review period, one new risk emerged (around support for mini-grids projects) in addition to two existing risks (government regulations and carbon credits) that have been closely monitored. While mitigation actions have been implemented, these risks remain unresolved and continue to pose a potential threat to the programme’s impact, particularly as it approaches to the end of the programme. During this period, no safeguarding concern was identified or reported via the verification activity, performed by BRILHO’s Independent Verification Agents via telephone and onsite visits, or through completion of the quarterly basis safeguarding forms by BRILHO´s investees.

One of the key risks relates to the Government of Mozambique’s limited capacity to fully implement regulatory measures on fiscal incentives, alongside the imminent expected introduction of new taxes on carbon credits. Although the approved regulatory framework recognises that business initiatives under mini-grids, solar home systems, and improved cooking technologies are eligible for fiscal incentives under the Mozambican tax code, the initial two solar home system companies that previously benefited from these incentives are no longer able to access them. The government has suspended these benefits, making it increasingly difficult for companies to sustain market growth. This has direct implications for the programme’s responsible exit strategy, particularly for Results-Based Financing (RBF) mechanisms, as BRILHO-supported businesses are becoming heavily dependent on them. As outlined in the recommendation table, a more holistic mitigation approach is needed. This should include the use of diplomatic channels to advocate for the full implementation of the fiscal incentive framework. Another closely monitored risk is the development of new government regulations on carbon credits, which may introduce significant taxation. This could have a rapid and substantial impact on the sector, especially for clean cooking companies that have been able to reduce end-consumer prices due to their access to carbon credits. A further mitigation plan is currently being developed to address this risk.

The emerging risk concerns the mini-grid projects. The programme may lack sufficient resources and time to support the development of the mini-grid market to the same extent as other technologies, such as solar home systems and improved cooking stoves. If socio-political instability, similar to that experienced last year, reoccurs, it could further deter private sector investment and delay government processes. As a result, the programme may not be able to adequately respond to the needs of the green mini-grid sector within the current timeline, which ends in October 2026. A mitigation plan is being considered, including exploring how other development programmes in the sector could provide complementary support.

# F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

## Summarise the performance of partners and FCDO, notably on commercial and financial issues.
SNV Netherlands Development Organisation implements BRILHO through a contract, which includes working with other downstream partners. SNV continues to receive positive feedback from programme stakeholders, including the Government of Mozambique and downstream partners. Private sector subgrantees stated that SNV’s BRILHO team has been instrumental in supporting them to be aligned with the programme objectives.

The programme remains on track and is moving forward with the implementation work for the extension phase. The total value of the SNV contract is £38M including SIDA’s contribution. The programme has spent 80% of its total approved budget, and the track record of spending according to forecasts has been excellent, for this review period SNV forecasted £7.8M of which they spent £7.1M and these variances was mostly due to the on-going socio-political situation during and after the elections with nationwide protests affecting the normal performance and pace of the programme and its stakeholders.

As part of the annual review process the SNV team have submitted an updated Delivery Risk Chain Mapping given that the programme is coming to an end. This can be seen in the BRILHO Delivery Plan 2025.xlsx

FCDO commissioned an independent audit, which was completed in April 2025 by Nexia, following a competitive tender process. Based on the audit report and management letter, it has been concluded that no financial irregularities were identified from 1 June 2023 to 31 December 2024. The management letter also states that all the financial statements were presented fairly and that all its statements of receipts and disbursements follow best practices and FCDO requirements.

During the reporting period, the Gender Equality and Social Inclusion (GESI) activities focused on continuing the implementation of RBF GESI incentives within BRILHO’s MDF portfolio to encourage grantees to hire and promote women in both technical and leadership positions, as well as to enhance their technical skills; the delivering of the life skills course to six private and public institutions; and the implementing the Women's Economic Empowerment Initiative within BRILHO’s portfolio. Additionally, the programme has developed a strategy to mainstream gender standards in E-Mobility, which aims to benefit up to 110 young women aged 18 to 35. This initiative, to be piloted with Epsilon, includes an RBF aimed at supporting lower income women in obtaining electric vehicles. The anticipated outcomes are that these women will boost their income by utilising electric vehicles for taxi services (such as Yango, Bolt, and others) and deliveries from restaurants and shops. This will not only enhance women's representation in business within the clean energy value chain but also help connect young women with technology.

The programme maintains an updated asset registry which is updated and shared with FCDO on a quarterly basis. Discussions are ongoing with FCDO Management Accounts to write-off damaged assets (office furniture damaged in storeroom due to high humidity) to the value of £1,971. An asset spot-check is conducted annually by FCDO Programme Officer. The last asset spot-check was conducted on the 15th of September 2025. As the programme is in its last year of implementation, SNV will submit an asset disposal plan for the BRILHO assets.

# G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
This annual review was carried out by BHC Maputo’s senior prosperity and economic development officer and a climate and environment adviser, with support from the BRILHO programme manager and SRO. The review team visited five ICS and SHS companies in Maputo province, including a ICS factory (Community Carbon) and an assembly plant for electric vehicles (Epsilon). They also met with ICA and SHS customers in different settings, including households displaced from flooding in Boane district. Customers were satisfied with ICS and SHS purchases and the level of service and reported financial savings (due to efficiency and reduced expenditure on charcoal, batteries, phone charging, and candles); as well as livelihood opportunities, and improved safety. However, upfront costs and repayments remain a challenge for many households despite the PAYGO plans available for SHS and relatively low ICS pricing. Meetings were also held with the SNV programme leadership and team as part of the review.

This review proposes that an impact evaluation be carried out at the end of the programme to fully capture successes, challenges and lessons learned. This would enable the UK to build on BRILHO’s impact and to inform other off-grid energy programmes in Mozambique (see recommendations section). It is expected that this would use mixed methods and be carried out by an independent third party, with SNV managing the contract.

Evidence
The BRILHO programme has supported various evidence products during the year, including Lean Data consumer insights complied by 60db. This carried out interviews with 411 customers from 9 BRILHO supported SHS and ICS companies and found over 90% had improved quality of life due to purchasing these products.

An analysis of BRILHO’s support from 2019-2024 was completed and detailed the programme’s key role in the off-grid market’s evolution in Mozambique. For example, BRILHO results-based financing was provided to half of all quality verified SHS sales between 2020 and 2024 and contributed to over 60% of ICS sales since 2021.[9]
[9] BRILHO_Transforming-off-grid-energy-access-in-Mozambique-2024_final.pdf
The programme also piloted a behavioural change model to support improved cookstove (ICS) business initiatives. Inspired by Cambodia’s successful Smoke-Free Village (SFV) model, VLF used Behaviour Change Communication (BCC) strategies to encourage a shift from traditional stoves to cleaner cooking technologies. The pilot was conducted from January to September of 2024 and reached 2,131 households in Boane District, Maputo Province. A baseline survey gathered data on demographics, cooking practices, and attitudes in each household. After nine months, an endline survey assessed changes and found that around one in four households reached by the campaign had purchased an improved cookstove.

Learning
Lessons learned in the past year are included under Section 1 of this Annual Review. Learning was collected during the field visits noted above to assess progress and verify results. The programme shared learning across the sector – for example BRILHO invited three SHS businesses (Dynamiss, Epsilon, and Uranus), and one GMG developer (ARC Power) to participate at GOGLA’s 8th Global Off-Grid Solar Forum and Expo in Nairobi in October 2024. In addition, social media posts highlighted results and learnings.

Date of last narrative financial report	June 2025	Date of last audited annual statement	April 2025

# ANNEX
## Annex 1 – Progress on recommendations from previous reviews

#	Previous recommendation	Progress – September 2025
1	Recommendation 1: BRILHO should continue its market stimulation efforts with an emphasis on RBF in the remaining two years. With an immediate effect, BRILHO team to review agreements with sub-grantees to ensure RBF continuation so that the RBF value reduces over time through the reverse auctions, increase access for higher tier products/services (including for mini-grids, and opening up electric cooking), consolidate the numbers of recipient firms in line with performance (ensuring local firms are given extra time if needed), and keep Catalytic Grant as a flexible option for specific instances of innovation, additionality or unexpected need.	Completed. The programme terminated agreements with underperforming subgrantees and amended them with partners capable of delivering greater impact and reaching a larger number of beneficiaries. The remaining funds were redirected to further stimulate the productive use of energy, including solar-powered irrigation, and to pilot e-mobility initiatives such as the use of electric vehicles.
2	Recommendation 2: By March 2025, the FCDO and BRILHO team will conduct an updated assessment of the state of the respective markets to inform how the BRILHO offer should evolve into any successor programme. Some functions or sub-sectors may be handed off smoothly to other larger programmes (see recommendation 4), and BRILHO could shift into more frontier areas and types of support (demonstrating further Productive Use technologies) – a separate note has been provided on opportunities for the evolution of BRILHO.	Ongoing. Although a preliminary assessment was conducted for the concept note of the proposed new energy transition programme, a comprehensive and updated assessment of the relevant markets is still required, particularly to determine the most effective approach in a future context with reduced ODA resources.
3	Recommendation 3: FCDO should explore opportunities to align with other UK instruments. This could fill critical market gaps that BRILHO is not well-placed to address, such as unlocking local lending from national banks or equity investment in firms (by June 2025). PIDG Facilities, Regional Energy Efficiency Programme (REPP), or BII could be relevant for the BRILHO programme.	Completed. Additional conversations and engagement with other UK-funded instruments have taken place, with mixed results. Among these, the most promising prospect relates to PIDG, which is currently designing a more holistic offer. Consideration is also being given to how posts, including Mozambique, could actively participate in this initiative.
4	Recommendation 4: The scale of RBF financing needed to reach Universal Access is significant. FCDO and BRILHO team to reach a workable cooperation agreement with the incoming ProEnergia programme (part of the World Bank’s $5bn Accelerating Sustainable and Clean Energy Access Transformation (ASCENT) regional multi-phase approach) to avoid overlap/confusion, continue market acceleration, and scale parts of the BRILHO offer. (by December 2024)	Completed. The programme actively provided support to the World Bank, although concerns remain about whether the World Bank’s interventions might distort market growth and create misaligned incentives for businesses.
5	Recommendation 5: FCDO should use diplomatic engagement to ensure the full and proper application of the off-grid regulations, enabling the start of planned mini-grid projects (by February 2025).	Ongoing. This recommendation is once again reflected in the Annual Review recommendations.
6	Recommendation 6: While scoring A+ represents a fair reflection of programme performance, with the 2-year cost and time extension in particular, the BRILHO team should update the results expectations by the end of November 2024 to ensure they are sufficiently stretching and representative.	Not completed. A full set of results and targets to be delivered by the end of the programme was previously updated and approved by the Development Director for the last year’s annual review. Discussion with BRILHO and Programme team has occurred and due to uncertainty with budget while approaching the end of the programme, it was decided to maintain the revised targets.