## Annual Review Template

Title: Title: Impact Evaluations on Urban transport, transport corridors and road safety across multilateral development banks and bilateral programmes (ieConnect)
Programme Value £ (full life): £12.25m (£14.5m)		Review date: 20/9/24
Programme Code: 204931	AMP start date: 4/11/2016	AMP end date: / 30/6/2024 (31/12/25)

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2022	2023	2024
Overall Output Score	A	A	A+	A+	A+	A+	A	A	A+
Risk Rating	Mod	Mod	Mod	Mod	Mod	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/5627325.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/90000639.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Getting transport right is crucial to poverty elimination, economic development and trade; and to ensuring optimum capital and recurrent spend for domestic budgets. Poor transport decisions can be a huge burden on domestic budgets for decades.
Reliable, accessible transport services support increased productivity, facilitate trade and enable access to economic opportunities and health and education services, thus distributing the benefits of growth. Where designed to be inclusive, transport services play an important role in empowering women and girls and vulnerable groups.
The ieConnect for Impact programme increases the availability and use of rigorous research and impact evaluation (IE) evidence for the selection, design, and implementation of transport infrastructure projects, particularly in low-income, lower-middle income countries or fragile and conflict affected states (FCAS). The IEs are particularly innovative as they are IEs in real-time so have the potential to positively inform and impact decisions (scaling up / down and changes in design) of the large-scale transport investments through baseline data collection and onwards IEs.
[note] Impact evaluations (IE) assess whether development interventions are effective and achieve the intended targets and are essential in building an evidence base on what works best, ensuring impactful interventions at scale and returns on investment to drive Value for Money (VfM) decision making.
The ieConnect programme is a collaboration between the World Bank’s Development Impact (DIME) department and the World Bank’s Transport Global Practice. It has a shared and common vision of “Sustainable Mobility for All”. FCDO was integral to the formulation of SuM4All and has held a Steering Committee seat since inception so there is alignment with FCDO on SuM4All objectives.
[note] The Sustainable Mobility for All (SuM4All) initiative is a global multi-stakeholder partnership framed around the four goals of universal access, efficiency, safety, and green mobility in transport. For more information, visit www.sum4all.org.
Prior to 2016 when FCDO raised the idea of expansion of DIME into the transport sector the World Bank undertook <1% of its IEs in the transport sector despite transport being the second largest lend sector for the World Bank at that time. ieConnect is still a cutting-edge programme within the global transport sector.
ieConnect currently focuses on four pillars: urban mobility, transport corridors, road safety, and rural infrastructure. It has cross-cutting themes of gender, female economic empowerment, fragile situations, environment, and climate change. COVID-19 response or recovery was additionally included as a program theme in 2020.
ieConnect is funded through a window within the World Bank’s (WB) umbrella Impact Evaluation to Development Impact (i2i) multi-donor trust fund (MDTF) and is managed by the WBs Development Impact (DIME) department in the WB’s Research Department (DEC). FCDO has contributed to the i2i trust fund through three programmes: (1) the Fund for Impact Evaluation (also known as i2i), managed by the Evaluation Unit in FCDO’s Economics and Evaluation Directorate, (2) through country-specific programs in Nigeria, Tanzania and the Democratic Republic of the Congo, financed by the respective FCDO country offices, and (3) the ieConnect programme under the Growth Research Team in Research and Evidence Division (RED). The i2i Trust Fund has now run to completion with any new funds to DIME for IEs being through the Development Impact TF which has near identical objectives to i2i.
[note] For clarity in this summary the Trust Fund will be called i2i TF and the programme will be referred to as i2i.
[note] i2i covers a broad set of topics to build the global use of IEs while ieConnect is strictly transport evaluations.

Summary supporting narrative for the overall score in this review

This 2024 Annual Review covers progress made during the 2023 calendar year.
Currently, ieConnect has 30 projects across 18 countries within Africa (AFR), Middle East and North Africa (MENA), Latin American and Caribbean (LAC), and South Asia (SAR) regions, of which 27 (see Annex 1) are financed by FCDO.
[note] These include Africa: 67%; South and South-East Asia: 7% and FCAS: 53%
The ieConnect programme continued to meet, exceed or significantly exceed all logframe indicators for outcomes, outputs, and value for money. In the 2023 Annual Review FCDO noted that the logframe indicators needed updating however this did not happen (detail in below section on Major lessons and recommendations for year ahead). It is for the second consecutive AR year difficult to score the project fairly due to the lack of appropriately updated logframe targets. The ieConnect team have performed strongly however some of the 2023 outcome and output targets were exceeded in 2022. Given the overall strong performance of the ieConnect team shown through the narrative and the fact that they suggested amendments to the logframe but received no response from FCDO in the course of 2023 the score of A+ is justified.
IeConnect have exceeded expectations in the programme as a whole through the generation of significant policy influence through increasing the use of evidence in policy making and generating evidence to increase the effectiveness and impact of emerging transport investments. This policy influence has also proven to be relevant for projects across countries implementing similar projects (outcome 2.1) as exemplified in case study 1.
##### Case Study 1: Measuring Gender-Based Violence in Tanzania

Measuring the extent of violence against woman (VAW) can be challenging, especially given the social stigma, lack of systematic reporting systems, and normalization of this type of violence. The ieConnect study in Tanzania aims to provide crucial insights into the extent, type and spatial distribution of violence faced by women in public spaces and evaluate whether mobile app-based reporting can improve our understanding of the prevalence of VAW. This is particularly important in relation to women’s mobility given that much of the harassment experienced by women in public can occur during their commute (whether while walking, waiting for transport or while using public transport). IeConnect research has shown how this type of harassment can limit women’s schooling and economic choices, thus decreasing their opportunities and overall welfare (Constraints to Women’s Use of Public Transport in Developing Countries, Part I: High Costs, Limited Access, and Lack of Comfort and Part II: Safety, Borker, 2022).
Intervention
The IE tests the effectiveness of providing a mobile app to bridge the reporting gap by allowing users to record incidents witnessed or experienced. The team sampled 1,151 university students, aged between 18 and 27, who are regular commuters and who own a smartphone. The IE used a randomized controlled trial where it randomly assigned two-thirds of the sample to receive the mobile app (treatment group) and one-third not to receive the mobile app (control group). Those who received the app were further randomized into a paid arm (compensated for their use of the app based on a random target for app usage) and an unpaid arm (not paid for their usage of the app). The randomization was stratified by university and the primary mode of transport used for their main activity, to have representation across space and modes of transport.
The IE conducted a baseline survey between April and July 2023 and deployed the app among treatment students for 23 weeks following the baseline survey. Eight follow-up surveys were also conducted during this period. An endline survey is planned for the summer of 2024, to finalize the data collection for this IE.
Results, outputs and impact
While the study is still ongoing, intermediate results provide interesting insights into women’s mobility and exposure to harassment in Dar es Salaam. Over 80% of the women leave their neighborhood 4 days per week or more and travel for more than 1 hour daily. Like in most cities, most women have multi-modal trips and use mostly public transport. Buses (dala dalas) are the most popular mode, being the main model of transport for almost 60% of women. The study participants who have been using the app have sent more than 2,000 incident reports and around 1,800 perception reports, within a time span of 6 months. Based on this data from the mobile app, women are harassed at least once every two weeks. This contrasts remarkably with the harassment reported to police gender desks where only 173 cases were registered in all of Dar es Salaam in 2017. Almost 3/4 of the harassment incidents are associated with traveling, with over half of that in public transport. Among the incidents of harassment recorded, 40% of them were severe forms of harassment. Finally, only 1% of the incidents recorded by victims were reported to the police, while 5% of them were reported to security personnel, conductor, or driver.
[note] Severe offenses include stalking, forceful touching/groping, intimidation, indecent exposure and physical abuse, whereas mild harassment consists of unwelcome comments, catcalling, whistling and inappropriate gestures.
When presenting this work to government counterparts, detailed discussions were held with the relevant regulatory authorities (DART and LATRA) to design a penalty structure for dala-dala drivers and conductors if they harass women and/or when women face harassment in their vehicle.
Results from this study will also inform the implementation of a similar interventions in other countries, a first pilot already being planned for Bangladesh.

Major lessons and recommendations for the year ahead
In the 2023 AR (covering calendar year 2022) it was stated that the Logframe was last updated in 2021 and some milestones for 2022 were already met or exceeded in 2021. This resulted in the 2023 AR being challenging to fairly assess the real results for 2022. The 2023 AR recommended that FCDO and ieConnect review the Logframe by October 2023 and update targets. This did not happen even though the ieConnect team suggested revised targets. FCDO did not respond and the Logframe was not updated. Although outside of this 2023 AR cycle it should be noted that the new FCDO lead and ieConnect have now finalised more stretching targets for 2024 which are detailed in Annex 2 (N.B the original targets showing as strike though). Examples of these changes include:
Outcome 2: Improved effectiveness and impact of new and existing transport interventions from FCDO, MDBs and the wider community
2.1 Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself : increased from 25% to 35%
2.3 Downloads of ieConnect research working papers: increased from high of 3,100 to high of 19,000

Output 1: Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation
1.2 Thematic knowledge reviews or technical notes for policymaking: increased from 5 to 8 (in year 2025)

Output 2: Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making
2.4 Spend on non-WB IEs or co-funded IEs where WB contribution <=25%: increased from 25% to 45%

The 2023 AR recommended a no-cost extension to enable the ieConnect team to do more dissemination to increase the uptake of research results however a re-assessment by FCDO in 2023 concluded that a costed extension of £2.25million (increasing total from £12.25m to £14.5m) until end December 2025 was good value for money. This was approved in April 2024 and is shown as bracketed budget (£14.5m) and end date of project (31/12/25) in the Programme Summary box.
The costed extension will enable the ieConnect programme to expand existing impact evaluations to generate further results and to include new areas of research focused on key transport priorities such as resilience, inclusion, accessibility and fragile and conflict affected states.
Recommendation: FCDO and ieConnect will ramp up our concerted effort on dissemination and uptake with a focus on leveraging knowledge and impact of the benefits of real-time, large scale IEs. The aim of this work will be to inform and transform the transport sector (and facilitate specific MDBs) to learn from ieConnect as a model and replicate at scale across the sector.
Recommendation: FCDO and ieConnect will engage specifically through the MDB Sustainable Transport Working Group, preparation for the UN-Decade for Sustainable Transport and SuM4All to further highlight the economic value (including in transport investment cost savings) and increased impact in undertaking ieConnect type IEs in the transport sector, including encouragement of innovative data collection methods.
Recommendation: FCDO and ieConnect will explore the potential of MDB agreement on a set of transport indicators to be measured across all MDB transport investments. This will engage with existing work funded under the FCDO High Volume Transport (HVT) programme in the SuM4All Working Group on Data and Indicators (due to report by end November 2024).
Recommendation: ieConnect will actively collaborate with both ADB and FCDO’s HVT to explore potential for joint IEs and learning events.
Recommendation: ieConnect will provide five country level summaries and two regional level summaries (Africa and Asia) of ieConnect work for sharing with FCDO country / regional offices.
Recommendation: ieConnect will produce an Action Plan which will be agreed by FCDO by end November 2024 for specific activities to achieve the above recommendations.
Recommendation: FCDO will analyse by April 2025 the positives and negatives of medium term continued IE work through (i) ieConnect or (ii) within other possible FCDO transport research programmes.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

ieConnect aims to improve the effectiveness of investments in transport infrastructure in low-income countries (increasing the use of evidence in policymaking and project development), contributing to faster, fairer and more inclusive economic development, and poverty reduction. While the eight MDBs lend about $20 billion for transport projects on average every year, the Private Infrastructure Development Group (PIDG) has committed 13.2% of their portfolio to transport infrastructure (22.5% in 2022) and British Infrastructure Investment (BII) invests about 30% of their portfolio in infrastructure, less than 1% of all impact evaluations from 2000 to 2015 were for transport projects. In short there are huge transport investments however the evidence base for decision-making in the sector is weak. Transport is also normally in the top three sectors for domestic budgets in FCDO partner countries. The United Kingdom is the second largest donor to both the WB and ADB and a major donor to other MDBs so a significant proportion of MDB transport investment funding is from UK Aid. Getting transport investment right is crucial for the use of both partner and UK government resources, economic development and trade, and ultimately poverty elimination.
[note] https://www.adb.org/documents/progress-report-2016-2018-mdb-wg-sustainable-transport
[note] https://pidg-wp.dusted.digital/wp-content/uploads/2023/06/PIDG_Annual_Review_2022-1.pdf
[note] Sabet, Shayda Mae, and Annette N. Brown. "Is impact evaluation still on the rise? The new trends in 2010–2015." Journal of Development Effectiveness 10.3 (2018): 291-304
[note] Including UK ODA resources. FCDO spends a limited amount on infrastructure investments directly, but makes significant indirect ODA investments through capital contributions and concessional fund replenishments in the MDBs.
ieConnect does this by:
1. Increasing the amount of evidence available by conducting IEs.
2. Increasing the amount of evidence available by influencing governments and the MDBs to do IEs on their projects and improving their capacity to do and use the IEs.
3. Disseminating the evidence to policymakers and programmers through workshops, journal articles, and publications.

Partners include the developing country governments as decision makers for transport projects and policies, the MDBs as the major investors in the sector and civil society as implementers and influencers. ieConnect links to FCDO offices in Tanzania, Pakistan and Ethiopia to share findings and identify ways to inform programming. ieConnect briefs the FCDO office in other countries when they conduct field visits. ieConnect also collaborates with the FCDO funded Global Road Safety Facility (GRSF) and the FCDO funded High Volume Transport Research Programme (HVT) on joint learning events, bringing together learning on road safety and innovative data collection from all three programmes.
[note] Geographic coverage of the whole programme includes Africa, Middle East and North Africa, South Asia and Latin American and Caribbean.
[note] Also hosted by the World Bank and supported by FCDO.
The nature of the transport projects being evaluated and the impact evaluations means that most evaluations are longer than the FCDO funding. The Logframe accounts for this by focusing on outputs withing the timeframe of the FCDO support. For example, there is a strong focus on data and data systems, because these need to be in place early in the life of the IE and can be completed within the timeframe of FCDO’s funding. ieConnect produces documents at various stages during the IE and not just a final report. Logframe indicators are calibrated to this, so we are confident they will meet the expected targets. The reports are shared with the relevant governments and, as demonstrated in some of the case studies, are influencing loan design, implementation, un-related projects (e.g. other countries) and government policies.
The programme continued to perform well across all indicators of programme outcomes, outputs, and value for money and generated policy influence through producing policy relevant evidence on effective transport investments and supporting dialogue.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall ieConnect is on track and has made impressive progress. The earlier mentioned issue of logframe targets or milestones needing to be revised has been further complicated by incorrect milestones being recorded in the 2023 AR (noted below). At outcome level the below table is now accurate and further details the agreed revised milestones for 2024 and 2025:

Outcome	Indicator	Milestone 2022 (incorrect in 2023 AR)	Actual Milestone 2022	Original Milestone 2023	Progress 2023	Milestone 2024 (previous and revised)	Milestone 2025 (previous and revised)
Improved awareness, demand for and use of transport evidence in decision making	REMOVED
	Proportion of transport impact evaluations with multi-arm evaluation designs to test project innovations.	41%	40%	40%	44% / (12/27)	40% 45%	40% 45%
	Proportion of impact evaluations that influence12 transport project during design or implementation.	63%	55%	55%	67% / (18/27)	55% 60%	55% 60%
	Proportion of completed transport impact evaluations that generate evidence used to support project adoption, targeting, scale-up, scale-down, continuation or cancelation decisions or that influence discussions on complementary interventions. (Phase 413 only)	45%	45%	45%	54% / (7/13)	45% 55%	45% 55%
Improved effectiveness and impact of new and existing transport interventions from FCDO, MDBs and the wider community	2.1 Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself. (Phase 3 or above)14	28%	16%	16%	33% / (9/27)	25% 35%	25% 35%
	2.2 Proportion of completed and published transport impact evaluations that are cited in the academic literature	25%	25%	25%	100% / (6/6)	75%	75%
	2.3 Downloads of ieConnect research working papers (cumulative).	Low15: 5,500 / Med: 5,650 / High: 5,800	Low: 1900 Med: 2000 High: 2100	Low: 2700 Med: 2900 High: 3100	13,224 / Significantly exceeded	Low: 15,000 Med: 17,000 High: 19,000	Low: 17,000 Med: 19,000 High: 21,000

In 2023, the program met or exceeded every logframe target. In terms of outcomes, there were increases in both outcome 1.3 and 2.1, with a higher proportion of impact evaluations that influence the project itself and that have influenced other transport projects during the design and implementation phases.
Traditionally, it takes a long time for IEs to produce results, meaning that they usually only influence future programming. However, ieConnect has been successful in using innovative data collection at baseline to identify areas for improvement within the loan project being evaluated during design and implementation (outcome 1.3). ieConnect reports and increase from last year from 63% to 67% IE baselines informing loan project design or implementation.
The proportion of completed transport projects that generate evidence used to support project adoption, targeting, scale-up, or that influenced discussions on complementary interventions (outcome 1.4) increased from 6 last year to 7 this year (now 54%), and importantly, there are now more projects that are considered for this outcome since it is only relevant for projects in Phase 4 (there are now 13 as compared to 8 last year).
At this stage, all projects are in phase 3 or phase 4. It is important to note that many of the projects considered in phase 3 have draft outputs that are currently being finalized and will be disseminated within the next few months. They are not yet considered as phase 4 because the outputs are not ready for public discussion and dissemination. The program is on track to deliver across both phase 3 and phase 4 projects by the end date.
Examples of outcome level ieConnect work include:
In Rwanda, the Lake Victoria Transport Corridor Project is studying the effects of the construction of the Ngoma-Nyanza highway in Rwanda, a 130-kilometer section of road linking southern Rwanda with border crossings to Tanzania and the Democratic Republic of Congo. The IE team has already supported the associated World Bank project in integrating a administrative data using spatial integration for project implementation (outcome 1.3).
In Kenya, the Road Safety: Matatu and Insurance Markets project measures the use of crowdsourced rider feedback on bus safety as a measure of safe driving and using objective sensor data on speed, harsh-braking, harsh-cornering, and number of crashes to test how well this new type of measurement framework works in a pilot in Nairobi and surrounding areas. Kenya’s National Transport and Safety Authority (NTSA) is building on the lessons learned from the pilot to help inform definitions of speed violations and standardized speed indicators, as well as improving monitoring of high-frequency speed data collected through national speed governors. The team is also discussing adaptation of the passenger feedback survey modules in NTSA activities to better understand passenger perceptions of safety, preferences, and the role of drivers and owners in public service vehicle (PSV) safety (outcome 1.3).
In Nigeria, under the Efficiency of Informal Transit Networks: Evidence from Lagos IE, ieConnect is supporting the Lagos state government to assess the impact of a large-scale reform of the public transit network. The team has started by studying the Bus Reform Initiative (BRI), which is now also turning to accompany the integration of light rails for a greener intermodal transit network. So far, results and policy-level findings have been shared and discussed directly with the Lagos Metropolitan Area Transit Authority (LAMATA), the Lagos State Government, the International Finance Corporation (IFC) and the World Bank country teams, the AFD and other development partners. The data collected feeds into the revision of the Lagos State Strategic Transport Masterplan (outcome 1.4) as well as complementary investments by the IFC (outcome 2.1). More details on ieConnect’s work in Lagos are in case study 2.
##### Case study 2: Measuring welfare effects of the introduction of public transportation in rapidly growing cities. The case of Lagos, Nigeria.

Transportation generates the largest share of greenhouse gas emissions and is a primary driver of pollution in cities. Dense, public transit-orientated cities tend to have fewer carbon emissions as they do not require vast amounts of driving. Lagos is known for its persistent traffic congestion challenge where an average commute takes about four hours a day (the highest in the world) and most of the vehicles on the road are over 15 years old, using old emission technologies with high sulfur levels: 200 times higher than US standards for diesel.
To address some of these challenges towards an environmentally friendly, more efficient, and safer public transit system, the Lagos state government through LAMATA launched a Bus Reform Initiative (BRI) – an ambitious city-wide reform of the public transportation services by rolling out about 820 high-capacity buses across 50 formal routes to replace the existing old paratransit buses (popularly referred to as danfo or yellow buses). The objective of the research was to deepen understanding on how Lagos can be set on a greener and better mobility path by providing analytics on passengers’ choices, public and informal transit, and evidence on how to regulate informal transit.
The research team has worked closely with LAMATA and the Lagos State Ministry of Transportation towards building data and analytical capacity. The collaboration saw LAMATA providing access to e-ticketing to the research team for analysis. This data was invaluable for assessing ridership patterns, revenue, and overall performance of the BRI. It also provided other relevant data on the BRI rollout plans, a list of motor parks, bus stops and routes for planning purposes.
Methodology
The research team is studying the direct and indirect effects of the new options and the indirect effects stemming from the change in informal transit prices and frequencies in response to the reform, and the valuation of these components by the commuters.
Estimating the effect of the new option on existing minibuses was achieved by using the panel data collected by the team on the danfo supply to measure how the informal transit operators responded to the opening of the new formal system. The team compared routes that received new formal service to control routes that were included in the government’s long-term plan for the new network but on which formal service had not commenced.
The research team also estimated the welfare effects of the rollout of the formal system, using two randomized control trials (RCTs) to estimate how commuters value the changes in informal prices and wait times. The team designed a SMS-based app to send participants random offers to wait at bus stops for a random amount of time. Analyzing the patterns of rejection or acceptance gave the team an estimate of the value of time that is specific to Lagos commuters and that will be used for future planning. Similarly, the team investigated how changing the price of the BRI would change usage leveraging the rich e-ticketing data routinely collected by LAMATA. The team elicited price sensitivity by providing 50 – 75% discounts to ride the formal bus system.
Results, Outputs, and Impact
Results from the data analysis have shown that the overall network coverage has improved - while accessibility of the services has been improved within the Lagos metro area by about 70%, with an average monthly ridership of 2,951,085 and 122,962 daily- and prices and quantities of danfos fell in response to the BRI. This is particularly true when the BRI was cheaper, benefiting mini-buses passengers on these routes. In addition, both men and women highly value the new public transit option in terms of trip safety. Safety concerns lead to 40% of women avoiding certain trips, especially for social or household activities. The welfare analysis shows that the new Blue Buses have generated a surplus equivalent to approximately 5% of wages on an average route.

Results and policy-level findings have been shared and discussed directly with LAMATA, the Lagos State Government, IFC, AFD, and other development partners at different conferences. The data collected feeds into the revision of the Lagos state Strategic Transport Master Plan. Further analytical support is being provided for update of the transport master plan, and preparation of the AFD and IFC operations on Quality Bus Corridors - an approximately a US$50 million investment from IFC, involving road infrastructure improvements and the provision of dedicated lanes for public transportation buses to reduce travel times, pollution and noise along the corridors.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

ieConnect is highly complementary to the wider FCDO Transport Research Portfolio showing impact at scale and breadth of engagement.

FCDO are currently designing a possible transport research programme. FCDO and ieConnect will need to re-evaluate the ieConnect costed extension and future IE work in the transport sector in the medium term. FCDO and ieConnect will need to rapidly explore pros and cons for IE work to be integrated within possible future transport research programmes or as a stand-alone programme in the medium term.

## C. DETAILED OUTPUT SCORING

Output Title	Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1a Number of ongoing Impact Evaluations (IEs) across key sub-sectors (total): urban mobility, transport corridors, and road safety.	Low:24 / Med:25 / High:26	27 / (exceeded high milestone)
1.1b Number of completed outputs (the sum of 1.1c-1.5)	47	53 (exceeded)
1.1c Number of grant-supported knowledge products, for example, IE papers or IE reports (excluding outputs detailed below)	30	34 (exceeded)
1.2 Thematic knowledge reviews or technical notes for policymaking	4	4 (met)
1.3 Number of cross cutting reviews in FEE and FCAS	2	2 (met)
1.4 Developed data infrastructure (with ability for scale up)	7	8 (exceeded)
1.5 Developed and validated measurement framework that is able to disaggregate impact (male/female or rural/urban).	4	5 (exceeded)
1.6 FCDO program co-financing share	<40%	36% (met)
1.7 Thematic distribution: / Gender (cross-cutting)	35%	44% (exceeded)
1.8 Geographic distribution: / FCAS	50%	59% (exceeded)
1.9 Income level distribution: / DFID focus countries	>60%	74% (exceeded)
1.10 Female Economic Empowerment (FEE): / Proportion of IEs with FEE specific intervention / Proportion of IEs disaggregated by sex and age	30% / 35%	33% (exceeded) / 52% (significantly exceeded)

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 measures progress on ieConnect’s quantity and quality of evidence, knowledge and data infrastructure – including measures of thematic and geographic coverage. The thematic and geographical coverage don’t change once the impact evaluations are selected so the latter are greyed out and not scored because the changes in percentage are related to the decrease in IEs rather than active changes to the programme.

The scored output measures 1.1 (a, b & c), 1.4, 1.5 and 1.6 all met or exceeded milestones. This Output is scored as an A+.
Research outputs during 2023 (outputs 1.1b to 1.5, see Annex 1) exceeded milestones. The programme continued finalisation of impact evaluation reports including a final report for the Liberia Road Safety impact evaluation which was formally peer reviewed in the World Bank system by Transport and Energy experts across the Bank. Overall, the portfolio has generated rigorous evidence across 53 completed outputs (output 1.1b).
In Ethiopia, the ieConnect team worked with the government and the World Bank to evaluate the Transport Systems Improvement Project (TRANSIP) which has the objective to improve mobility along selected corridors in Addis Ababa (a city with high road fatality rates). The team has been evaluating the road safety and mobility impacts with the goal of helping to improve the design, execution, and the planned outcomes of the project. It has done this through running computer vision analytics on video footage from cameras installed at road intersections, trained the image detection algorithm and used computer vision analytics to identify the speed of vehicles, traffic and jaywalker count and, most importantly, near-hits, near-collisions and accidents. This is one of the first times such an exercise has been done in a low-income country setting. This has informed the development of a road safety tool aiming to make it open source for future projects to use in other contexts (output 1.4).
IeConnect continued to develop and strengthen data systems using innovative technologies. In Mozambique, ieConnect collaborated with the World Bank’s Integrated Feeder Road Development Project to evaluate the impact of improving rural transport infrastructure on agricultural development using data from satellite imagery to detect and inform changes in land use following construction and maintenance of rural ‘feeder’ roads (output 1.5). The research is distinguishing the causal effects of the intervention from other activities that may also influence agricultural intensification.
ieConnect has enabled evaluation of over US$5.7 billion in transport investment projects to date (Value for money: Effectiveness). ieConnect’s technical assistance, capacity building, and analytical and advisory support are designed to help leverage additional financing from international financial institutions, national governments, and other development partners. FCDO’s funding has encouraged others to invest. Over the lifetime of the programme, partner governments, other parts of the WB, and other development partners have contributed more than 177% of the value of FCDO’s total investment towards the cost of delivering the IEs, bringing the share of FCDOs financing of the program down to 36% (output 1.6). One recent example of this is the French Agency for Development (AFD) agreeing to finance an additional data collection in Nigeria for a cost of approximatively Euro 200,000, as part of a lending project of Euro 78 million.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output milestone targets for 2024 and 2025 have been increased to encourage additional stretch in the latter part of the programme and reflect progress to date. Revised logframe outputs are detailed in Annex 2.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from 2023 AR were not sent to ieConnect until after their reporting for 2024 AR so have not been formally responded to in the ieConnect Reporting.

Recommendation from 2023 AR: For the final year and the programme completion review, ieConnect should disaggregate the number of peer-reviewed journal articles from other publications. Response: Annex 1 in the 2022 and 2023 ieConnect annual reports provides a list of outputs categorized by “type of output” including journal articles. Only peer-reviewed journal articles are classified as journal articles on this list; therefore, these can be directly aggregated to get the total number of peer-reviewed journal articles.

Output Title	Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making
Output number:		2	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1.a Number of MDBs involved at the operational level	5	5 (met)
2.1.b Number of bilateral donor institutions involved at the operational level	6	6 (met)
2.2 Number of IEs or projects working directly with a non-WB implementing partner	12	14 (exceeded)
2.3 Proportion of co-financed transport programmes	100%	100% (met) / (11/11)
2.4 Spend on non-WB IEs or co-funded IEs where WB contribution <=25%	25%	44% (exceeded) / (12/27)
2.5 Proportion of people participating in workshops that come from low or lower-middle income countries	80%	85% (exceeded) / (431/509)
2.6 Proportion of people participating in workshops that come from FCASs	50%	59% (exceeded) / (298/509)
2.7 Number of people trained in workshops and / or by ieConnect supported teams/ researchers.	520	661 (exceeded)
2.8 Number of workshops	15	22 (exceeded)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall the ieConnect team showed strong performance in this output and exceeded the majority of scored milestones. This output scores an A+.

Some of the indicators are fixed once IEs are selected and are kept for tracking purposes (outputs 2.1 – 2.2, greyed out and not scored). Co-funding of impact evaluations (output 2.3) and the loan projects that underly them (output 2.4) are indicators of the programme’s potential to influence the funders and policy makers. If the WB is funding a lower proportion of the underlying loan there is more likelihood of influencing non-WB funders, particularly the other MDBs. These indicators help push the WB ieConnect team to use their expertise on projects outside the scope of the WB. Output 2.3 met expectations with all IEs tied to co-financed loans projects.

Strengthening countries’ transport data systems through institutional and technical capacity building remains critical for prioritising and scaling-up evidence-based and results-driven transport investments in the long term. ieConnect continues to emphasise the importance of data and data systems to underpin the impact evaluations and has used innovative approaches to data. The team promoted innovations in data to support transport sector decision-making and stimulate discussion on how to scale these innovations. The ieConnect team has continued to build the capacity of a broad set of stakeholders to make systematic use of data and evidence through a collaborative “learning-by-doing" approach (outputs 2.5 – 2.8).
At the operational level, the team is continuing to work (Output 2.1a) with MDBs including the African Development Bank (AfDB), Islamic Development Bank, the Asian Development Bank, the European Union, the Inter-American Development Bank; and bilateral donors (output 2.1b) including FCDO, the U.S. Agency for International Development, JICA, Dutch Development Bank, EXIM Bank of China, and AFD. Examples of co-financed transport projects being evaluated as part of the ieConnect program include the impact evaluation of the Rwanda Rural Feeder Roads, which is examining the impact of a multi-donor, national feeder road upgrading program on farmers' livelihoods, financed by the European Union, the United States Agency for International Development, and the Netherlands Development Finance Company (Output 2.3).

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The output milestone targets for 2024 and 2025 have been increased to encourage additional stretch in the latter part of the programme and reflect progress to date. Revised logframe outputs are detailed in Annex 2.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendations from 2023 AR were not sent to ieConnect until after their reporting for 2024 AR so have not been formally responded to in the ieConnect Reporting.

Recommendations of 2023 AR: FCDO and ieConnect should consider how to better measure the quality of capacity building in the final year of the programme and for the programme completion review. ieConnect should target more dissemination activities at LMICs and FCAS stakeholders. Response: targets for 2024 and 2025 for output 2.5 (Proportion of people participating in workshops that come from low or lower-middle income countries) have been increased. It was agreed to maintain the same targets for 2024 and 2025 for output 2.6 (Proportion of people participating in workshops that come from FCASs) for consistency as ieConnect measure this output against an ex-DFID FCAS classification (pre 2020).

Output Title	Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of organisations participating in ieConnect workshops	200	209 (met)
3.2 Number of organisations, universities, research centers, and government agencies participating in ieConnect networks	83	87 (met)
3.3 Number of non-WB hosted dissemination events	70	91 (exceeded)
3.4 Number of presentations in high-level meetings with multi-stakeholder MDB and/or bilateral transport leadership	4	4 (met)

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focuses on Communities of Practice and knowledge platforms. All outputs were met. This output scores an A.

IeConnect continues to perform well on this output. In 2023, ieConnect continued to engage with MDBs at different levels. In October 2023, ieConnect and FCDO co-hosted a roundtable with development partners including the European Investment Bank (EIB), Agence Francaise de Developpement (AFD) and the German Development Agency (GIZ) to discuss ieConnect’s work and priority areas for future research in the transport space, this was in the sidelines of a wider SuM4All meeting. The event included presentations from Government counterparts including Managing Director of Nigeria’s LAMATA and Deputy Director of the Kenya’s NTSA detailing joint data and evidence generation with ieConnect and its impact on transport programmes and policies. The event also featured presentation of ieConnect’s research and policy impacts on topics including BRT projects, transport corridors, and equitable transport access for women.
The ieConnect team has also worked to use the existing projects as platforms of both dissemination and uptake discussing research opportunities in transport with other MDBs and bilateral institutions. For example, in Senegal, much of the data and analysis being done for the new BRT project can be useful for studying a new project funded the AFD, the EIB and others to restructure the whole bus network in Dakar.

Annex 4 shows the list of events. ieConnect (and the Development Impact Evaluation team) has continued to strengthen their identity as a leader in innovative data driven research. This has given the team more platforms to share results.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Recommendations from 2023 AR were not sent to ieConnect until after their reporting for 2024 AR so have not been formally responded to in the ieConnect Reporting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from 2023 AR were not sent to ieConnect until after their reporting for 2024 AR so have not been formally responded to in the ieConnect Reporting.

Recommendation from 2023 AR: Given strong performance on this output over several years, FCDO and ieConnect should ensure realistic end of programme targets. Response: FCDO and ieConnect added new and increased targets for 2024 and 2025 in August 2024.

Recommendation from 2023 AR: DIME to look at how the AGIL team tracks their engagement and influence on World Bank activities. Response: ieConnect engaged with the AGIL team on how they measure their activities. DIME is currently revamping the entire myIE reporting system under the leadership of the DIME analytics team; and ieConnect is working with the team to ensure learning from this conversation as well as our own experiences in monitoring projects will be reflected in the update.

## D: VALUE FOR MONEY

Key cost drivers and performance

FCDO and the ieConnect team agreed VfM indicators in 2021. The program continued to demonstrate value for money in 2023.
Economy
The average cost to FCDO of completed papers or reports ($249,958) remained below the target of $275,000, noting that ieConnect only counts one paper per impact evaluation (e.g. final peer-reviewed journal article or working paper but not both).
Efficiency
- 59% of grant activities have supported governments in using non-traditional data sources and/or disruptive technology, an increase of 3 percentage points from 2022 and 19% percentage points higher than the expected target. This target is being increased to 50%.
- On average there were 3.4 presentations per project post baseline, bringing the results to different types of audiences including government officials, operational staff in transport, and academic researchers which is above the program target of 2 but is slightly less than 3.5 which was the figure achieved in the previous year.

Effectiveness
- ieConnect has enabled evaluation of over $5.7 billion in transport investment projects to date, and this continues to meet the programme target.
- IeConnect continues to work to increase government and other operational counterparts that are included as partners in a study. The target this year was 85 and the programme has achieved 112, which is an increase of 8 from last year.

Equity
- The proportion of Impact Evaluations that either conduct gender-disaggregated analysis or study a gender-specific intervention remains constant from the previous reporting period at 44%, which is 14 percentage points higher than the target.
- The cumulative sum of government and other operational counterparts from Fragile and conflict areas has increased by 6 to 53 against a target of 35.
Cost-effectiveness
Increased crowding-in of external funds with 63.96% of financing for IEs coming from alternate sources as of the target which is greater than 60% and is 1.18% points higher than the previous annual report
Assessment of whether the programme continues to represent value for money
On the basis of the indicators agreed by FCDO and ieConnect, the programme continues to represent good value for money.

E: RISK

Overview of risk management

The ieConnect program remains a moderate risk.
The main risk areas of concern (moderate after mitigation) are as follows:
- External context: The main external risks related political instability, climatic or other shocks that could have prevented the research team from traveling or engaging in programme activities. This risk was mitigated by on the ground presence of field supervisors in many countries that closely monitored local developments and kept the entire research team informed of any noticeable developments that could impact research. Additionally, the team invested in building strong networks in country through frequent dialogue and investment in capacity building so that, if required, programme activities could continue.
- Delivery: To mitigate the risks associated with capacity constraints in partner countries the programme team collaborates closely with counterparts to build capacity and provide assistance to facilitate progress on all aspects of the IE implementation. There is a risk that the projects underlying the impact evaluations are delayed. Because of this, the FCDO Logframe for ieConnect focuses on data systems, data collection, and delivering products rather than completing full impact evaluations within the programme timeframe. The World Bank is committed to completing the full impact evaluations over the longer-term.
- Operational: Experienced management teams are in place at both FCDO and the World Bank and the programme is managed within the standards agreed between the two partners centrally.
- Fiduciary: There are no concerns over financial management within the programme as they follow standard World Bank processes. FCDO reviews all calls for funds and does not pay in advance of need.
- Reputational: The main risk in this area is related to the impact evaluations not being seen as good enough quality and not being picked up by stakeholders. To mitigate this the team works closely with government stakeholders throughout the entire project process to ensure the relevant policymakers are invested in the research and are more likely to engage with the research findings and use them to inform policy. The IeConnect team is increasing their emphasis on dissemination of results and to that end dissemination events is a large part of the programme extension which has recently been approved.
- Safeguarding: The project looks closely to mitigate the risks associated with social exclusion and the rigorous World Bank’s standard safeguards policies within the Environmental and Social Framework have been applied fully to mitigate this risk

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The World Bank has clear financial management and procurement policies in place which have been agreed centrally by FCDO and the programme follows all relevant policies.

The World Bank programme team sends financial reports to FCDO at least twice per year as agreed at the start of the programme, and at the same time as their call for funds. They also respond promptly to additional requests for information from FCDO. During the reporting period discussions were ongoing on a costed extension to expand on previous research and support integration of previous FCDO-funded research into a new generation of mobility projects led by a range of multi-lateral organisations including but not limited to the World Bank. Unfortunately these discussions have taken longer than anticipated and although the agreement has been signed by the time of writing this review.

The World Bank programme team and FCDO staff meet on a quarterly basis to discuss progress against the programme timeline, review finances and discuss any issues or concerns. This includes a face-to-face meeting in March during the World Bank Transport Week when possible. ieConnect reports are clear and consistent and the responses to ad hoc requests are quick and substantial. Both parties have found the meetings to be useful in contributing to a strong working relationship.

As this programme operates under a World Bank Trust Fund it is included in the Single Audit of all World Bank trust funds. No issues regarding this programme were highlighted in the last Single Audit.

FCDO funds are not used to purchase any assets.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
Due to discussions on the extension of the programme and the change in PRO within the FCDO team additional meetings have been scheduled to complement the regular quarterly meetings between FCDO and the World bank programme team

Evidence
Both the cross-cutting themes of gender and inclusion and the disaggregation of data has improved gender aspects and poverty focus of the evidence. ieConnect have undertaken innovative and high tech work to better access data at scale that can be efficiently used in data poor or inaccessible / FCAS regions and accurately provide baseline data on poverty. An example of this is in Cote d’Ivoire where ieConnect undertook analysis and research on use of KPIs routinely collected by mobile phone companies and overlayed with satellite data to correlate with household survey poverty data. This resulted in cheaper and faster poverty data for baselines in transport IEs.

Learning
ieConnect are prompt and responsive to both FCDO-country level and thematic summary requests. This assist with learning and dissemination. Shorter, accessible documents and presentations could be improved but are of a good standard in ieConnect. A standard format for these summary pieces will be finalised in 2024.

Key lessons from ieConnect on data and real-time IEs are crucial to impart to the wider global transport community. There are opportunities for leapfrogging of data gathering and methodologies within the transport sector and these could learn from ieConnect. This is an opportune moment for ieConnect to further disseminate and motivate with the UN Decade for Sustainable Transport starting in 2026.

Date of last narrative financial report	July 2024	Date of last audited annual statement	June 2024

Annex 1 – 2023 Key Outputs with Links
Project	Type of Output	Output
Key Knowledge Products
Efficiency of Informal Transit Networks: Evidence from Lagos, Nigeria	Final Report	Impact of Large-Scale Transit Reform: Evidence from Lagos, Nigeria**
ieConnect Program (Global)	Thematic Knowledge Review (Corridors)	Impact Evaluation of Transport Corridors: Approach from the ieConnect Portfolio*
smarTTrans: Road Safety in Kenya	Working Paper	The Unintended Consequences of Curfews on Road Safety
Liberia Road Safety Impact Evaluation	Final Report	Motivation for Reckless Driving: Evidence from a Lab-in-the-field Experiment**
ieConnect Program (Global)	Thematic Knowledge Review (Health)	Benefits and Costs of Transport and Mobility for Health: A survey of the economics literature**
ieConnect Program (Global)	Cross cutting review (Health)	The Role of Transport and Mobility for Women's Access to Health: A survey of the economics literature**
COVID19 Mobility Analytics Task Force	Journal Article	The evolution of the COVID-19 pandemic through the lens of Google searches
COVID19 Mobility Analytics Task Force	Journal Article	Scale matters: Variations in spatial and temporal patterns of epidemic outbreaks in agent-based models
COVID19 Mobility Analytics Task Force	Journal Article	A stitch in time: The importance of water and sanitation services (WSS) infrastructure maintenance for cholera risk. A geospatial analysis in Harare, Zimbabwe
Impact Evaluation of Emergency Response and Post-Crash Care in Malawi and Tanzania	Journal Article	Fall injuries in Sub-Saharan Africa: analysis of prospective injury registry from 23 health facilities in Malawi and Tanzania
Effects of Large Transportation Infrastructure Projects on Worker Well-Being	Working Paper	Conscientiousness and Labor Market Returns: Evidence from a Field Experiment in West Africa*
Measuring Violence Against Women in Public Spaces: Drawing on Experimental Evidence	Working Paper	Sexual Harassment in Public Spaces and Police Patrols: Experimental Evidence from Urban India
Policy Briefs and Blogs
Road Safety in Kenya: Matatu and Insurance Markets	Blog	How providing information can improve safety: Evidence from Kenya’s informal public transit sector
The social costs and benefits of infrastructure construction: Air pollution and bus rapid transit (BRT) in Dakar	Blog	Innovative data collection for measuring air pollution in Dakar / The History of Dakar Air Quality & How They’re Using Air Quality Technology Today
Ethiopia Expressway	Blog	Evaluating the impact of transportation investment
COVID19 Mobility Analytics Task Force	Blog	To harness telecom data for good, there are six challenges to overcome

Notes: Key knowledge products correspond to output indicator 1.1c, thematic knowledge reviews correspond to output indicator 1.2 and cross cutting reviews correspond to indicator 1.3. Blogs are not counted in the logframe indicators but are shown here as 2023 program outputs. *Select outputs are mentioned in previous annual reports, for instance, as previous working paper versions. These outputs are shown here as new publications since they were released in 2023 but they are not counted as additional outputs in the logframe indicators. **Outputs are not yet publicly available.
# Annex 2 – Revised logframe for 2024-2025

# Annex 3 – List of Transport Portfolio Projects
	Project Name	Country
1	Impact Evaluation of the Transport Systems Improvement Project (TRANSIP) in Addis Ababa	Ethiopia
2	Understanding the Impacts of CAREC Corridor Investments in Pakistan on Connectivity and Local Economic Development	Pakistan
3	Lake Victoria Transport Program Rwanda Corridor	Rwanda
4	Rural Roads and Agricultural Value Chains	Rwanda
5	Understanding and Addressing Gender-Based Violence in Public Transportation in Dar es Salaam	Tanzania
6	Impact of a fare policy change on the well-being of vulnerable groups in Bogotá	Colombia
7	Hawassa Industrial Park Community Impact Evaluation	Ethiopia
8	Guinea-Bissau Rural Transport Project: Impact Evaluation on Women's Access to Essential Services and Economic Opportunities	Guinea-Bissau
9	Measuring Violence Against Women in Public Spaces: Drawing on Experimental Evidence	India
10	Impact Evaluation of Iraq Transport Corridor Project	Iraq
11	Road Safety in Kenya: Matatu and Insurance Markets	Kenya
12	Liberia Road Safety Impact Evaluation	Liberia
13	Transport and trade facilitation at the border, trade costs and revenue mobilization	Malawi
14	Route to Development: Impacts of Road Network Improvements on Agricultural Intensification in Mozambique	Mozambique
15	Enhancing Female Participation in Household Decision-Making for Improved Impacts of Rural Roads on Factor Accumulation and Productivity in Nicaragua	Nicaragua
16	Efficiency of Informal Transit Networks: Evidence from Lagos, Nigeria	Nigeria
17	Impact Evaluation of Rwanda Rural Feeder Roads	Rwanda
18	Measuring and Enhancing Mobility in Dakar	Senegal
19	The social costs and benefits of infrastructure construction: Air pollution and bus rapid transit (BRT) in Dakar	Senegal
20	Hawassa Industrial Park COVID-19 Impact Evaluation	Ethiopia
21	COVID19 Mobility Analytics Task Force	Global
22	smarTTrans: Road Safety in Kenya	Kenya
23	Impact Evaluation of Emergency Response and Post-Crash Care in Malawi and Tanzania	Malawi
24	Effects of Large Transportation Infrastructure Projects on Worker Well-Being	Senegal
25	Experimental Evidence on Urban Transport and Mobility: Impact Evaluation of the Dar es Salaam BRT System	Tanzania
26	Impact Evaluation of Emergency Response and Post Crash Care in Tanzania	Tanzania
27	Impact of Highway Upgrading on National Integration and Local Economic Development	Tunisia

# Annex 4 – Events
Project title	Name of event	Name of host institution
Non-WB Dissemination Events
The social costs and benefits of infrastructure construction: Air pollution and bus rapid transit (BRT) in Dakar	Measuring Development 2023: Mitigating the Risks and Impacts of Climate Change / Measuring the Impact of a BRT Project in Dakar, Senegal, on Air Quality	Center for Effective Global Action (CEGA), WB
ieConnect Program (Global) and multiple projects presented, including but not limited to: / Air pollution and bus rapid transit (BRT) in Dakar / COVID19 Mobility Analytics Task Force / smarTTrans: Road Safety in Kenya	International Road Federation (IRF) Annual Conference 2023: Innovation for Better Mobility Systems / Opening remarks: Innovation for Better Mobility Systems / Session: ITS and Big Data to Meet Transportation Challenges	International Road Federation (IRF)
Understanding the Impacts of CAREC Corridor Investments in Pakistan on Connectivity and Local Economic Development	Global Evaluation Initiative gLocal's Evaluation Week 2023 / Geospatial Data and Analysis for Monitoring and Evaluation	Centre for Economic Research in Pakistan (CERP)
Route to Development: Impacts of Road Network Improvements on Agricultural Intensification in Mozambique	Planet Explore 2023 Conference: From Transparency to Action / The Marketplace Activity Index: Real-time Economic Monitoring in Remote Rural Areas	Planet Explore
smarTTrans: Road Safety in Kenya	Urban Economics Association: 12th European Meeting of the Urban Economics Association / The Unintended Consequences of Curfews on Road Safety	Urban Economics Association (UEA)
Route to Development: Impacts of Road Network Improvements on Agricultural Intensification in Mozambique	Dissemination event with Mozambique’s National Roads Administration (ANE)	National Roads Administration (ANE)
The impact of a targeted fare subsidy program on public transportation usage and labor market outcomes: a regression discontinuity analysis from Bogota	Dissemination of baseline results with the Secretaría Distrital de Movilidad (SDM) and Transmilenio	Secretaría Distrital de Movilidad (SDM)
Impact Evaluation of Rwanda Rural Feeder Roads	Partnering for Development Impact: Evidence that Transforms	EU Delegation to Rwanda, WB
Efficiency of Informal Transit Networks: Evidence from Lagos, Nigeria	Dissemination to stakeholders: / Informal transit sector data with LAMATA, Directors of Bus Service Unit, and GIS team / Presentation to LAMATA policymakers	LAMATA
Measuring and Enhancing Mobility in Dakar	West Africa Regional Conference on Road Safety	ANASER & WHO
smarTTrans: Road Safety in Kenya	National Road Safety Pre-Conference: Road Traffic Crash (RTC) Analysis for National Road Safety Action Plan Priorities	National Transport and Safety Authority (NTSA)
smarTTrans: Road Safety in Kenya	Investing in Analytics to Inform the Digitization of Traffic Fines in Kenya	NCAJ Working Committee on Traffic Reforms
Road Safety in Kenya: Matatu and Insurance Markets	Public Service Vehicle (PSV) Safety Using Telematics Data and Passenger Feedback: Results from a Pilot*	NTSA
Effects of Large Transportation Infrastructure Projects on Worker Well-Being	Dissemination with Conseil Exécutif des Transports Urbains de Dakar (CETUD) and CRBC	CETUD
Efficiency of Informal Transit Networks: Evidence from Lagos, Nigeria / Route to Development: Impacts of Road Network Improvements on Agricultural Intensification in Mozambique	8th Urbanization and Poverty Reduction Research Conference, 2024* / Public and Private Transit: Evidence from Lagos / Rural Marketplaces and Local Development	International Growth Centre, MCC, GWU, WB
Select WB Dissemination Events**
ieConnect Program (Global)	World Bank Global Road Safety Facility (GRSF) Road Safety Academy: Measuring and Monitoring Road Safety Results	WB
smarTTrans: Road Safety in Kenya	Development Data Partnership Day 2023: Using private sector data for a road safety in Kenya	WB
Route to Development: Impacts of Road Network Improvements on Agricultural Intensification in Mozambique	Poverty & Equity Global Practice Seminar: How marketplaces shape rural development: new insights using satellite imagery	WB
Efficiency of Informal Transit Networks: Evidence from Lagos, Nigeria	DEC Half-Baked Seminar: Does Public Transit Crowd Out the Private Sector	WB
The social costs and benefits of infrastructure construction: Air pollution and bus rapid transit (BRT) in Dakar	DIME BBL: Innovations in Data to Support Investments in Pollution Abatement	WB

Notes: Non-WB dissemination events correspond to output indicator 3.3. *Select early 2024 events are shown but not counted in the 2023 logframe indicators. **World Bank dissemination events are not counted in the logframe indicators but select events from 2023 are shown. These events are relevant for helping the program to disseminate knowledge within operational teams at the World Bank.