## Annual Review

Title: Sustainable Inclusive Livelihoods through Tea Production in Rwanda (SILTPR)
Programme Value £ (full life): £16.4		Review date: Aug 2025
Programme Code: 204941	AMP start date: August 2016	AMP end date: March 2029

Summary of Programme Performance
Year	2016/17	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	A	A	A	A	A	A	A+	A+	A++
Risk Rating	Major	Major	Major	Major	Major	Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-204941/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-204941/documents

A. SUMMARY AND OVERVIEW

Description of programme

Tea is an important crop that makes a substantial contribution to Rwanda’s economy. Farming tea is labour intensive and offers significantly higher incomes to farmers than traditional crops. Thanks to favourable agroecological conditions, Rwandan tea is high quality and commands high prices. The Rwandan tea sector has significant potential for growth and investment. However, the sector faces constraints, such as small and fragmented plot sizes, low agronomic skills and capacity of small holder farmers (SHFs), low fertilizer use, and lack of capital. This leads to low incomes and a limited capacity to invest.
[note] In 2022, Rwanda exported $82m of tea, making it the 15th largest exporter of tea in the world. Tea was the 6th most exported product from Rwanda (after gold, tin ores, coffee, malt, and niobium/tantalum/vanadium/zirconium). The main destinations of tea exports from Rwanda are Pakistan ($31.4m), UK ($20.2m), Egypt ($11.4m), Sudan ($5.5m), Kazakhstan ($5m), and Egypt ($4.9m). Tea accounted for around 4.6% of Rwanda’s total export earnings in 2022 (Source: https://oec.world/en).

In this context the UK, in partnership with The Wood Foundation Africa (TWFA), fund the Sustainable Inclusive Livelihoods through Tea Production in Rwanda (SILTPR) programme. The broader project is a partnership between the Government of Rwanda (GoR), Unilever/Ekaterra/Lipton/Browns Investment PLC-Rwanda, Luxmi (a major Indian tea company new to Africa), TWFA, the Gatsby Charitable Foundation (Gatsby), and the UK. Initially UK funding amounted to £11.8m over nine years (2016-25). The programme recently received a cost extension from 2024 to 2029 with additional funding of £4,6m to fund 3 new components:
[note] At the outset the partner in the project was Unilever. However, during the timeframe of this programme Unilever changed their tea business to a subsidiary called Ekaterra. Ekaterra has since been sold to new ownership of LIPTON Teas and Infusions (“Lipton”). Lipton has now been sold to Browns. All obligations were transferred in the changes to Browns; thus, no changes were made to the SILTPR programme. Throughout this document “Browns” is used, but – for ease of comparison with previous Annual Reviews – this is equivalent to previous references to “Unilever”, “Ekaterra”or “Lipton”.
1. Expansion of smallholder tea at Nshili Kivu Tea Factory (NKTF) - The aim is to bring an additional 2,500 SHFs into the tea business, cultivating an additional 2,000 Ha. This will be implemented through the Ubumwe Tea Company Ltd.
2. Installation of three (3) pilot ropeways for smallholder tea transportation at Rugabano
3. Implementation of the carbon neutral tea production and processing.

SILTPR aims to drive job creation and increase incomes by supporting SHFs to develop tea in line with best practice, becoming reliable suppliers of greenleaf tea to existing factories and two new factories. Browns and Luxmi committed to invest up to $72m to construct tea processing factories on core estates in the Western (Rugabano) and Southern (Nyaruguru) Provinces of Rwanda. This programme has the potential to have a significant impact on the Rwandan tea sector. With the scaled up of the model to Nshili Kivu, 2,500 new Nshili Kivu farmers will be supported to grow tea, bringing the total small holders supported to 21, 500 who will plant a total of 9, 400 hectares and will supply to Nshili Kivu, Rugabano (Luxmi) and Kibeho (Browns) tea factories, and will produce over an estimate of 18m kg of made tea per year at the programme’s maximum year. Already, in terms of the amount of tea in the ground (including both SHFs and Browns’s industrial block), Nyaruguru is the largest tea estate in Rwanda.
[note] For context, Rwanda’s total tea exports in 2022/23 were 39m kg (Source: Annual NAEB 2022-2023 Agriculture Exports Performance, page 13).

The programme operates through the establishment of professional smallholder service companies (SCs). Ubumwe Tea Company Ltd (UTCL), Services Company Outgrowers in Nyaruguru-North (SCON-N) and Rugabano Outgrowers Services Company (ROS) are assisting SHFs to overcome the barriers to entry into the tea sector. They provide agronomic support, farm inputs on interest-free credit, and production logistics (collection, weighing, transport, and payment). These SCs are the exclusive suppliers to the new Browns’s Kibeho and Luxmi’s Rugabano tea factories. Patient capital is provided in the form of tea seedlings, fertiliser and continuous hands-on agronomic support as well as training through farmer field schools (FFS). Farmers are also financed to cover land preparation and planting services.
[note] The service companies are registered as non-profit companies limited by guarantee and operate on a cost-recovery basis.

Summary supporting narrative for the overall score in this review

This Annual Review (2024/25) scores A++. The three programme outputs score A++, A++, A+. This has been a high-performing programme for a number of years, consistently scoring A or above, even as logframe targets have been revised upwards. Additional programme outcomes and outputs as a result of the cost extension will be added to the logframe in FY 2025/26 (once the ongoing funding scenarios are concluded). TWFA revised the Theory of Change, which was approved by FCDO in Nov 2024.

The programme outputs are structured around (1) effective learning and adaptation, (2) farmers planting high quality tea according to best practice, and (3) inclusive and effective management of tea service companies. Details of the output progress is in Section C.

SILTPR is on track to achieve the planned outcomes and impact. It has a robust method for defining and tracking indicators for outcomes and impacts. Section B outlines the progress on these annual targets. These targets have been met or exceeded. SILTPR is producing more tea than was originally envisaged (albeit with a slight drop in quality in 2024/25 due to drought). It is creating more employment opportunities – particularly seasonal – than was expected. It has brought significant FDI to Rwanda. Farmers are making more profit from their tea production than was expected and are reporting improvements in their overall socio-economic situation.

As with all programmes SILTPR faces some challenges, but these have been well-managed by the service companies and implementing partners and have had relatively limited impact on the ability to achieve programme indicators. Some challenges are very localised (e.g., poor roads and delay in delivery of fertiliser, some come from global factors (e.g., the high price of inputs, or the depreciating Rwandan Franc). Overall, the implementing partner manages risks well and the primary risk – the untested nature of the business model – has been reduced as tea has started to be harvested and the model proven to work. In 2022/23 the risk rating was reduced from major to moderate, it remains moderate in this Annual Review (see Section E).

Major lessons and recommendations for the year ahead

Lessons and recommendations are shown throughout the following sections. Some key overarching recommendations for the programme include:

TWFA and FCDO should work together to redesign the logframe for the future years, including indicators for the components under cost extension. Also given the front loading of funds, TWFA and FCDO need to review the profile of results to reflecting the profiling of funding to the project in the coming years.

TWFA and FCDO to review progress towards objectives on Greenhouse gas (GHG) reductions, and to disseminate findings of studies around lowering the carbon footprint of tea processing and transport.

BHC Kigali programme team to explore further communications products about the programme, including links to UK suppliers and markets.

All partners should ensure that a public launch of the Browns Kibeho tea factory scheduled for September 2025 happens in a way that highlights the positive impacts of the programme.

Given the success of the programme to date, TWFA to consider scaling up the model to new areas.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SILTPR Theory of Change (ToC) can be summarised as follows: “the provision of effective support to smallholder farmers (SHFs) through Services Companies (SCON-N, ROS and UTCL) will increase the capacity of SHFs to plant and maintain tea and supply high quality (and in sufficient quantity) greenleaf to tea factories. As a result, farmers will experience sustained and increased incomes and livelihoods while more private investment is attracted as the sector becomes de-risked”. A diagram showing the ToC is at Annex A.

The ToC diagram has been updated in 2024 to incorporate three new components that were added in the cost extension (see Annex B for the new ToC). Below components have been included in the ToC diagram:

Outputs incorporated;

1. R7: Farmers have access to safe, green and sustainable transport for seedlings and greenleaf (Pilot ropeways)
2. R10: Baseline assessment & inventorisation of Greenhouse gas (GHG) emissions in Nshili Kivu, Shagasha and Mulindi factories completed
3. R11: Agreed strategy/roadmap to Net Zero implemented in 3 factories
Short term outcomes incorporated:
R20: Nshili Kivu, Shagasha and Mulindi Factories reduce GHG emissions as they transition towards Net Zero.
Impact level results incorporated:
R34: Improved resilience and adaptation to, and mitigation of, climate and environmental change.
The outcome/impact statements have not changed in the past year but indicators targets in 2024/25 have been revised to capture additional results under cost extension. Very early in the programme the impact and outcome statements were both amended (slightly) from those set out in the original Business Case. In 2020 an indicator was added at the impact level (indicator 4) to capture the improvements in socioeconomic situation as perceived by farmers involved in the programme (measured through annual surveys). It is recommended that the logframe indicators be revise in line with revised ToC for cost extension.
[note] Impact statement in Business Case (“Increased sustainable incomes and improved livelihoods for farmers and wage labourers through the production of tea”) has changed to “Sustained, increased incomes for smallholder tea farmers and contribution towards enhanced macroeconomic stability.”
[note] Outcome statement in Business Case (“Tea is planted and cultivated according to target standards and farmers receive decent wages for developing tea”) has changed to “Tea is planted and cultivated according to target standards, with employment opportunities for both men and women.”

A greenfield tea development is an expensive and long-term undertaking which presents challenges and risk for all parties, especially the SHFs and private investors. It takes four years from planting tea until it reaches full commercial bearing. This creates a significant financial strain on the farmer given the loss of income from land set aside for this activity. Unless patient capital is available, tea is often an unviable proposition. Similarly, significant expertise is needed to maximise the productivity of tea bush. Technical assistance can enhance and support good agricultural practices during land preparation, planting, weeding, applying fertilizer, and plucking tea. Furthermore, large-scale investors struggle to source tea of consistent quality and quantity from SHFs and can benefit from efficient aggregation and extension services. The SILTPR SCs provide these services to secure high quality and sufficient quantity of supply which reduces the investor’s risk.
[note] Greenfield means starting from scratch, building new facilities, and farming on land which has not been used for tea previously.

In terms of capital, the SCs provide RWF I million per ha as a start-up zero-interest loan to farmers, paid in three instalments based on preparation of land and planting tea. Funds are paid into farmers’ bank accounts at local banks, hence increasing farmers’ engagement with the formal banking sector and reinforcing financial inclusion. Loan repayments start when tea bushes start bearing and farmers begin to supply tea to factories, this is generally in year 3.
[note] At the start of the programme this was approximately $900. As the Rwandan Franc has depreciated this has changed to approximately $700 (as of mid-2024). This loan amount has – of July 2024 – been increased to RWF 1m.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

SILTPR’s outcome statement is that: “Tea is planted and cultivated according to target standards, with employment opportunities for both men and women.” This is tracked by four outcome indicators with annual milestone targets. These are shown in the table below.

The programme is on track for all outcome indicators. The amount of greenleaf tea produced and the number of people with productive work are all higher than was expected at the outset of the programme. The survival rate of tea bushes has met the target, whereas tea quality has dipped slightly below the target due to drought. As production of high-quality tea is crucial to the SILTPR business model, it will be important that the SCs continue to focus on ensuring quality.

Outcome indicator	2024/25 target	2024/25 achievement
1. Amount of greenleaf tea produced annually (kg)	4, 900,000	5,882,576 (120% of target)
2. Survival rate of tea bushes per ha per year	85%	96% / (112% of target)
3. Quality of green leaf produced [measured by % of good leaf collected from SHFs]	70%	68% / (97% of target)
4. No. of individuals cumulatively engaged (Permanent and Seasonal) in productive activity under the programme	Permanent: 12, 314 / Seasonal: 40, 321	Permanent: 12, 700 (103% of target) / Seasonal: 70, 902 / (176% of target)

This year is the fifth year that outcome indicator 1 has been measured (greenleaf tea production only started a few years into the programme). The amount of greenleaf tea produced is increasing rapidly (821k kgs in 2020/21, nearly 2m kgs in 2021/22, 3.5m kgs in 2022/23, nearly 5m kgs in 2023/24 and nearly 6m in 2024/25). This is well above the target (4.9m kgs). Tea is being produced in larger quantities, and earlier, than in the original business plans: this is an impressive achievement.

Outcome indicator 2 has slightly exceeded target and it is higher than previous year where the survival rate was 85.5%. Even with the prolonged drought of 2024, the survival rates were higher than expected. This does, however, highlight the risks of increasing extreme weather events on the programme.

Outcome indicator 3 has dipped slightly below the logframe target. Again, this was due to the prolonged drought of 2024. The extreme dryness caused poorer quality in the greenleaf tea being delivered. Ensuring that tea produced is high quality, and thus can attract a premium at market, benefits both the farmers (who receive a quality bonus) and the private sector companies involved.
[note] GoR’s minimum standards for quality greenleaf is 65%. SILTPR programme has targets above this, at 70%.

Indicator 4 tracks the employment effects of the SILTPR programme, both permanent and seasonal jobs. Permanent jobs are primarily farming households – there were 988 new farming households in 2024/25 – but also captures direct employment at the service companies (SCON-N and ROS) and the factory sites. Seasonal jobs far surpassed the target, these include workers hired for maintenance and plucking, workers at nurseries supplying tea seedlings, and temporary positions at the factory sites. In terms of gender disaggregation, permanent jobs are split 50-50, yet seasonal jobs are 55% female over the life of the programme (in 2024/25 they were 55% female). For seasonal jobs only the quarter with the highest figures (usually Q3 due to land preparation and planting) is picked. The size of the seasonal employment is partly a reflection – in response to recommendations from previous Annual Reviews – of encouraging using external labour rather than just family members for land preparation and maintenance. Part of the Rainforest Alliance certification achieved by both SCs considered how labour is used on farms (hours, working conditions, etc.).
[note] This assumes that a new farming household within the programme generates permanent two permanent jobs – one male one female. The accuracy of this assumption should be further examined through the programme evaluation.

At the impact level SILTPR aims for: “Sustained, increased incomes for smallholder tea farmers and contribution towards enhanced macroeconomic stability.” This is tracked through four indicators with annual targets. These are shown in the table below.

Impact indicator	2024/25 target	2024/25achievement
1. Farmer's average net income per ha of tea cultivated (USD)	$668	$730 / (109% of target)
2. Annual Value of Greenleaf produced (USD)	$1,666,000	$ 2, 055, 734 / (123% of target)
3. Increased FDI in the Rwandan tea sector (Cumulative)	$29,061,340	$35, 128, 209.86 (121% of target)
4. % of farmers who joined the programme in previous year(s) who report improvement in their overall socio-economic situation (%)	SCON-N / 2017 cohort: 90% / 2018 cohort: 85% / 2019 cohort: 60% / 2020 cohort: 50% / 2021 cohort: 40% / 2022 cohort: 35% / 2023 cohort 30% / ROS / 2018 cohort: 85% / 2019 cohort: 60% / 2020 cohort: 50% / 2021 cohort: 40% / 2022 cohort: 35% / 2023 cohort 35%	SCON-N / 2017 cohort: 95% / 2018 cohort: 91% / 2019 cohort: 92% / 2020 cohort: 87% / 2021 cohort: 80% / 2022 cohort: 80% / 2023 cohort 93% / SCON-N ave: 86.2% / Disaggregation: / Female ave: 89.2% / Male ave: 63% / Age 18-30 ave: 86% / Age 31-50 ave: 87% / Age 51-60 ave: 83% / Age +61 ave: 89% / ROS / 2018 cohort: 71% / 2019 cohort: 90% / 2020 cohort: 69% / 2021 cohort: 60% / 2022 cohort: 75% / 2023 cohort 59% / ROS ave: 70% / Disaggregation: / Female ave: 61% / Male ave:75% / Age 18-30 ave: 50% / Age 31-50 ave: 76% / Age 51-60 ave: 68% / Age +61 ave: 65%

Again, progress against these four measures is extremely positive. Showing that the programme is having a real impact on farmers’ lives – in terms of income and perception of improved situations.

Impact indicator 1 tracks the net income for each hectare of tea. This has exceeded expectations and is now at $730ha. Over the life of the programme this target has been revised upwards substantially. To add context, an early survey in Nyaruguru (circa. 2016) found that the average net value of traditional crops was around $150/ha. Farmers are now making over four times that amount from farming tea.
[note] For SCON-N the average net income was $788/ha. For ROS, the figure was $682/ha.
[note] The original logframe has an end-of-project target of $409/ha.

Indicator 2 – the value of greenleaf tea produced – substantially exceeds expectations. As with indicator 1, the target has been revised upwards during the life of the programme to align with the SCs’ operational targets. This higher target has still been exceeded, by 23%. Over $2.1m of greenleaf tea was produced in 2024/25.

Indicator 3 exceeded target by 20%. The targets for FDI have been revised downwards from the estimates at the start of the programme as costs of factory construction have become clearer. Nonetheless, in 2024/25, $35m of FDI into Rwanda was injected by Browns and Luxmi as a direct result of SILTPR, and – in addition – a second Lipton (now Browns) factory in Nyaruguru has been agreed as part of SCON-S ($15m).
[note] The Luxmi factory in Rugabano is up and running, the Lipton factory in Nyaruguru began operations in March 2024.

Indicator 4 captures farmers’ self-reported improvements in their overall socioeconomic situation from survey data. In general, and particularly for farmers who have enrolled more recently, targets have been met or exceeded. Across the board, across age ranges, and over time (different “cohorts”) farmers are reporting improvements in their overall socio-economic situation. Farmers in the older cohorts are reporting that their socio -economic situation has improved compared to the past. Females are reporting improvements at a higher level than males.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on impressive achievement throughout the year, continued strong performance on Value for Money (VfM) and the high potential for large-scale impact this programme should continue. It is a flagship economic development programme in the British High Commission (BHC) Kigali’s portfolio delivering on both our economic (higher productivity economic activities, more investment in Rwanda, increased trade) and climate goals (helping deliver our International Climate Finance funding).

At time of writing this Annual Review, the programme has been given a cost extension to March 2029. The BHC Kigali team will work with TWFA to revise log frame targets and add new indicators to capture new components added as part of cost extension.

## C. DETAILED OUTPUT SCORING

Output Title	Programme efficiently implemented and adapted in line with emerging findings and learning
Output number:		1	Output Score:	A++
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Evidence in support of solid project design generated and project implementation adapted in line with recommendation of how to best support higher incomes of smallholder farmers while achieving commercial business sustainability	At least 1 knowledge product/evidence in support of project design (e.g. case study, documentary, success story, beneficiary story, brochure, fact sheet, annual report, articles etc.) produced and disseminated. / At least 4 adaptations to project design implemented as a result of evidence are documented by SILTPR	Two knowledge products (#1 and #2 in the list below). / At least 8 project adaptations have been documented (they are described in the list below, #3 – 11).
1.2 MRM system implemented and evaluation conducted according to agreed methodology and timeframes	Nyaruguru and Rugabano socioeconomic baseline surveys carried out / Impact assessment carried out on Nyaruguru and Rugabano farmers	Surveys were conducted. / (100% of target)

Briefly describe the output’s activities and provide supporting narrative for the score.

There are two indicators under this output. Both have met or exceeded targets. This output scores an A++. Output 1 is about ensuring that the implementation of SILTPR benefits from relevant emerging findings and lessons, including from DFID/FCDO Annual Reviews, regular quarterly performance reports, analysis and SC board meetings.

There have been various knowledge products and project design adaptations during the year.

An infographic showing the results and progress to date on the SILTPR has been developed; to show in one-page the progress being made by the programme. This infographic is shown in Annex C

Programme adaptation:

In response to evolving implementation realities and opportunities for deeper impact, the programme underwent a structured adaptation process guided by evidence, governance oversight, and strategic alignment with long-term development objectives. Key developments included:

Programme Extension and Additional Financing
A cost and time extension was approved by FCDO, with an additional investment of £4.6 million to consolidate results and integrate emerging priorities into the programme framework.

1. Introduction of Strategic New Components
   Three high-impact components were added under the expanded budget envelope:
  1. Nshili Kivu Smallholder Expansion, targeting an additional 2,500 farmers
  2. Rugabano Pilot Ropeways, aimed at reducing green leaf transport costs and losses
  3. Carbon Reduction Project, focused on decarbonization of factory operations in Nshili Kivu, Shagasha, and Mulindi

1. Financial Risk Mitigation and Policy Reforms
   In a joint decision by the Boards, two key operational shifts were adopted effective financial year 2024/25:
  1. Discontinuation of foreign exchange (forex) adjustments on Rwandan franc-denominated farmer loans from April 1, 2024
  2. Adjustment of green leaf deductions from 30% to 35% effective July 1, 2024, to reflect increased forex exposure assumed by the Service Companies (SCs)

Loan Recovery and Business Plan Alignment
The Boards mandated SCs to develop a robust loan recovery tracking matrix, aligned with the long-term business plan, to improve financial performance and sustainability.

Climate Resilience and Farmer Training-
In response to a prolonged drought (May–September 2024), SCs intensified training on climate adaptation techniques including water conservation, tree planting, mulching, and pasture establishment to build resilience at farm level.

Gender Integration and Institutional Collaboration
To strengthen gender mainstreaming, both SCs initiated collaboration with the Gender Monitoring Office Rwanda, including the completion of a gender audit and follow-up actions to close identified gaps.

Farmer Leadership Strengthening and Electoral Reform
Ahead of the upcoming SCON farmer elections, the programme revised the electoral framework to clarify roles and responsibilities of farmer leaders, introduced qualification criteria, and a capacity-building programme.

Fertilizer Procurement Risk Mitigation
In response to procurement and disbursement delays under the bulk fertilizer scheme, SCs boards approved an increase in buffer stock purchases—initially 20%, with a planned rise to 50%. Additionally, ROS and SCON established dedicated, reliable fertilizer storage facilities, while management continued to engage the Rwanda Fertilizer Fund to streamline future procurement.

For outcome indicator 1.2, 10 farmers and workers surveys were carried out as scheduled (in Feb 2025). Surveys conducted included:
    - Baseline Survey - 189 SCON farmers + 239 ROS farmers
    - Annual Socio- Economic - 313 SCON farmers + 350 ROS farmers
    - Vulnerability 1189 SCON farmers + 2239 ROS farmers
    - Casual workers Survey- 43 workers in SCON & 40 in ROS
    - Satisfaction- 313 SCON farmers + 350 ROS farmers

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations under this output from last year’s Annual Review are shown in the table below.

Recommendation	Progress
FCDO and TWFA should discuss how the lessons from surveys can be packaged and presented to best demonstrate to stakeholders the impact of the programme.	An infographic was developed – see Annex C.

Lessons from this output, in particular around the operations of SCs have informed the scale up of the model to Nshili Kivu

Recommendation for the year ahead on this output
FCDO and TWFA to consider how best to disseminate the knowledge products form the programme.

Output Title	Farmers coordinated and supported to plant quality tea
Output number:		2	Output Score:	A++
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of Farmer Field Schools (FFS) operational with defined curriculum, running fortnightly (Cumulative)	140	167 / (119% of target)
2.2 Number of farmers participating in Farmer Field Schools (Cumulative) disaggregated by gender	4, 500	4, 895 / (108% of target) / Sex disaggregation for 2024/25 (female (%) / male (%)) / ROS: 42% out of 598 farmers were female / SCON-N: 26% of 424 farmers who graduated were female
2.3 Total seedlings/tea bushes planted by smallholders (Cumulative)	46,160,380	55.43 million (120% of target)
2.4 Hectares of tea planted by smallholders (Cumulative)	3, 297	3, 408 / (103% of target)
2.5 No. of farming households planting tea with the support of the service company's extension services (cumulative)	6,042	7,052 / (117% of target) / Sex disaggregation / Cumulative female/male: 28/72 / 2024/245 / female/male: 31/69 / ROS: 33% females out of 619 / SCON-N: 22% females out of 370

Briefly describe the output’s activities and provide supporting narrative for the score.

There are five indicators under this output. All have exceeded targets. This output scores an A++. Output 2 is the core of the activity under SILTPR (reflected by the 50% output weighting), it is about ensuring that farmers are adequately supported to plant high quality tea.

Outputs 2.1 & 2.2 – farmer field schools (FFS) – were one of the main programme casualties of the pandemic in earlier years. All classes were put on hold due to restrictions on gatherings; this affected nearly 1,000 farmers. During the pandemic, training was carried out at individual farm level with agronomists and capitas travelling door-to-door (“training-by-visit” approach). Since 2021 SCs have managed to catch up with training. In 2024/25 at ROS 18 FFS were completed by 598 farmers, in SCON-N 18 classes were completed by 424 farmers. Targets were exceeded for both indicators. The FFS focus on practical lessons on agronomic issues, such as planting techniques, plucking, erosion control measures, tipping, decentering, health and safety, farm management, fertilizer application, etc. Demonstration plots have been established for this practical training.

Outputs 2.3 & 2.4 cover the number of tea seedlings and the area of tea planted: both these targets were exceeded. ROS and SCON-N planted 4.52m and 4.15m tea seedlings respectively in 2024/25, bringing the cumulative total to over 55.4m. SILTPR has now planted nearly 3,408 ha of tea of about 430 ha was planted in the past year. In terms of the amount of tea in the ground (including both SHFs and Lipton’s industrial block) Nyaruguru is the largest tea estate in Rwanda.

Output 2.5 covers the number of farming households involved in the programme. This has surpassed 7,000 – of which 988 new farmers were recruited in the past year, exceeding the target. In general, the average area of tea planted per farmer is lower than was anticipated at the outset – on average 0.4 ha per farmer in ROS.
[note] Equivalent figure for SCON-N is 0.9 ha/farmer.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to indicators.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations under this output from last year’s Annual Review are shown in the table below.

Recommendation	Progress
Important that SCs, as they expand, maintain a focus on quality of tea produced.	Maintaining quality is core to the model of the SCs. As set out in the Outcome section, adverse weather in 2024 hampered quality this year – although SILTPR is still above the NAEB quality requirement. In response to a prolonged drought (May–September 2024) which affected the quality of tea, SCs intensified training on climate adaptation techniques including water conservation, tree planting, mulching, and pasture establishment to build resilience at farm level
TWFA – working with all partners (including GoR and FCDO) – continue to work proactively to address challenges faced in operations.	Many of the programme adaptations (see Output 1) are aimed at addressing operational challenges (e.g., fertiliser buffer). A programme extension that has been approved by FCDO will also focus on addressing these challenges further.

Output Title	Efficient, inclusive and sustainable management of service companies
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Farmers' representatives trained in managerial capabilities that are successfully participating in managerial activities (Cumulative)	N/A	Not applicable. No training took place in 2024/25.Training to be done after elections due 2025/26 / Farmers elections will be held in 2025/26. / Previous year total of 115 farmer representatives trained (25% female) represents 115% of target).
3.2 Number of Farmers' representatives elected to represent smallholders (at least 50% women) (Cumulative)	N/A. No elections planned in 2024/25.	N/A. No elections planned in 2024/5.
3.3 Number of farmers' representatives trained in corporate governance (Cumulative)	N/A	Trainings will take place after elections / Previous years total of 115 farmer representatives trained (25% female) represents 92% of target).
3.4 Number of services provided by the Services Companies to their clients (Cumulative)	9	9 / (100% of target) / No other services will be introduced to the farmers.
3.5 Percentage of tea farmers satisfied with the services provided by the Services Companies	80%	97% / (121% of target) / SCON-N ave: 98% / Disaggregation / Female ave: 96% / Male ave: 98% / Age 18-30 ave: 88% / Age 31-50 ave: 97% / Age 51-60 ave: 98% / Age +61 ave: 99% / ROS ave: 96% / Disaggregation / Female ave: 96% / Male ave: 96% / Age 18-30 ave: 96% / Age 31-50 ave: 94% / Age 51-60 ave: 99% / Age +61 ave: 98%

Briefly describe the output’s activities and provide supporting narrative for the score. There are five indicators under this output. However, for this reporting year, only one is relevant (the others have seen no activity in 2024/25). The indicator on farmer satisfaction level has exceeded the target. This output scores an A+. Output 3 seeks to enhance the management of the tea service companies so that they are professional, efficient, inclusive, and sustainable. It captures work to ensure that farmers are fully represented and have the skills to govern the companies. This is in line with TWFA’s long-term aim of handing full control of the services companies over to famers in years to come.

Farmer representatives were elected and trained (on managerial activities and corporate governance) in previous years (2021/22 and 2022/23). Neither of these activities took place in 2024/25 (output 3.1, 3.2 & 3.3). Farmers elect representatives of groups of farmers and there is a pyramid of farmer leaders, with two farmers sitting as directors on the board of each SC. Farmer elections will be held in 2025/26, thereafter, training of farmers’ representatives will commence. In terms of past training, females account for 25%, which is broadly in line with gender mix in the broader population of farmers (see output 2.5) where, overall, 28% of farmers are female.

SCON-N and ROS provide a range of services to their farmer clients (output 3.4). This hasn’t changed in the past year. No more services will be introduced. As tea began to be harvested, electronic weighing was rolled out in 2020/21. This brought the number of distinct services to nine. The satisfaction level with these services is measured by Output 3.5 (through farmer surveys).
[note] The others are transportation of seedlings; provision of quality seedlings; provision of fertilizer; mentoring on tea husbandry; patient capital for investment into tea farming; financial inclusion; FFS; digitized payment for greenleaf tea.

Output 3.5 was measured in the satisfaction surveys carried out in March 2024. SCON-N overall satisfaction level was 98%, and for ROS 96%. Satisfaction is generally similar for females and males, although it is very high across both SCs, both genders and all ages.
[note] Sample size is 295 for SCON-N and 308 for ROS. Percentage refers to those answering “satisfied” or “very satisfied”.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no specific recommendations under this output from last year’s Annual Review.

For the coming year (2024/25), the indicators under this output should be revised to account for the fact that there are no upcoming planned elections for farmer representatives or further training for the current representatives. This recommendation was not implemented as it was waiting on clarity on FCDO funding for outer years and which components of cost extension would continue

## D: VALUE FOR MONEY

Key cost drivers and performance

Key cost drivers of the programme remain the same as in previous annual reviews. The costs are driven by support services to tea farmers (training, mentoring, extension services), supply of farm inputs (fertilisers, seedlings), interest-free start-up loans (for land preparation), collection and transport of greenleaf to tea factories for processing, design of ropeways transport and costs of nursery development and maintenance. Throughout the year, the SCs and TWFA continued to perform well on cost control as resources were economically managed, and inputs procured competitively ensuring the right quality at the right price as per procurement systems and practices established at both SCs.

VfM performance compared to the original VfM proposition in the business case.

The VfM proposition of the business case assumes that income generated by farmers joining the programme is significantly higher than earnings from existing means of income. This assumption combined with a gradual planting schedule of 18 years and a long-term, zero interest rate repayment schedule for patient capital, leads to a robust benefit-to-cost ratio. In line with the propositions in BC, this annual review finds that the programme continues to represent VfM at the programme and beneficiary level, and throughout the BC proposed indicators and the 5 E’s of FCDO’s value for money framework.

Economy
The review finds that economy standards are in line with the business case proposition. SCs, supported by TWFA, manage programme resources economically, buying inputs of the appropriate quality at the right price. Procurements follow competitive tenders and large orders of inputs are procured in bulk. To secure economies of scale, fertilizers were procured in bulk with other tea estates across Rwanda. SCs will continue to procure fertilizer through consolidating their order with Shagasha and Mulindi factories. SCs also continued to hire local resources (e.g., agronomists and capitas) to secure high quality extension services for farmers at a reasonable price.

As a result of these measures, the overhead cost against total cost ratio remained stable. Through controlling costs of operations by the end of the year the SCs’ overheads unit cost was RWF 406,000/ha against a budgeted amount of RWF 422, 000/ha.

Efficiency
According to the first evaluation report (completed in 2022/23), efficiency has been maintained by the programme:
- Administrative overheads, as a share of total cost are modest and have been steadily reducing over time, for both companies, which is an important measure of overall programme efficiency.
- The cost per tea seedling for instance, is being maintained at £0.04 as per the original business plan target, with all targeted seedlings having been distributed to farmers for planting. For instance, in this reporting period, the cost per seedling was RWF 66 (£0.034) due to timely planning of seedling needs, and careful management of nurseries.
- A new subcontracting arrangement means that the SCs only pay for healthy seedlings delivered. This payment by results approach passes some risk on to sub-contractors.
- Joint procurement of inputs and in bulk among SCON-N, ROS, Browns and Luxmi was a practice that keeps input costs lower.
- The cost of leasing NAEB mother bush was re-negotiated down by SCON-N from RWF17m to RWF11m. To reduce costs further, SCON-N has developed its own mother bush as a longer-term project so as not to continue to rely on the NAEB supply.
- Experimental low-bed nurseries technologies were introduced. These require a lot of training and monitoring but can push survival rates for seedlings from 85% to 97%.
- As indicated by the evaluation report, the cost of advisory per farmer has reduced from $1,242 to $141 (89%) at SCON-N and $84 to $61 at ROS (27%) due to large number of farmers recruited in recent years (approx. 1000 new farmers in each of 2021/22, 2022/23, 2023/24 and 2024/25).
Effectiveness
SILTPR is currently meeting expectations both in terms of delivery and development impact, with many of the milestone targets exceeded, including those at outcome and input level. Based on the performance so far there is good evidence that SILTPR is being effective towards achieving its intended results. Many milestone indicators for this review have surpassed the targets, including number of permanent jobs created (12,764 vs. annual target of 12,314), number of households farming (7054 vs. annual target of 6042) and the value of tea produced ($2,055,734 vs. annual target of $1,666,000). Evidence from socio-economic surveys, field visits and the evaluation report suggest that the programme is having significant livelihood gains for SHF – farmer average income is $730/ha against the target of $668/ha (compared to previous opportunities for land use offering approx. $150/ha). There is also evidence of a wider effect on the communities, such as some improved roads, greater variety of economic activity (e.g. banking and saving options), and more labour opportunities for non-farming households. These large investments, in poor, rural areas of Rwanda, are on track to make substantial positive changes in the communities at large.

Therefore, FCDO’s investment is already contributing to significant permanent/sustainable increase in smallholder net incomes. At maturity, the project is expected to help raise farmer incomes threefold. By the end of the year, close to 83,666 cumulative direct jobs (12,764 permanent and 70,902 casual jobs) had been generated in the Rugabano and Nyaruguru greenfield projects. When the project is fully developed, it will create permanent employment for at least 52,635 people directly and indirectly. The expansion of the programme in Nyaruguru (SCON-South, SCON-S) – based on the positive demonstration effect of SILTPR – is expected to create close to 19,000 additional jobs (12,138 seasonal and 6,362 permanent jobs). FCDO’s investment of $15.1m (£11.68m) has helped leverage $105m (FDI from Browns and Luxmi, and philanthropic capital from Gatsby and TWFA). Additionally, TWFA, Browns and GoR have committed to invest a further US$30m in SCON-S, raising the total public, private and philanthropic capital leveraged to $135m and confirming the replicability and scalability of the model. This means that every $1 of FCDO funding has helped leverage at least $9 from other funding sources, which is very good financial leverage.

Equity
The initial criteria for joining the programme (committing to allocating between 0.3ha and 1ha of land to tea) were set in a way to ensure that most poor SHFs who can convert part of their land to tea, and remain with additional land for other crops, are reached. However, the recent relaxation of selection criteria to include farmers owning more than 1ha for consolidation and cluster formation purposes pose important equity risks that need to be fully understood. However, to manage that risk, SCON-N developed an internal greenfield farmer prioritization schedule that clearly highlights that SCON-N priority selection criteria remains 0.3 to 1 ha (i.e., smallholder farmers), however, larger farmers who own land within the SCON-N clusters will also be considered in a second round only if annual planting targets are not met and these farmers have capacity to maintain their land. Overall, results generated by the programme are inclusive. Both men and women continue to benefit from the employment and income opportunities arising from tea related activities. At least 55% of seasonal employment created to date being female. Representation of farmers in decision making is in line with the gender split of farmers. The impact evaluation did not find any major issues around equity. An example of assessing equitability is that the farmer field school training delivery model is being reviewed and adapted to ensure that no one is left behind especially illiterate farmers and those with physical disability as recommended by evaluation report.
[note] Those farmers who choose to farm more than 1ha of land pay interest on their loans. Farmers with <1ha have interest-free loans.

Assessment of whether the programme continues to represent value for money.

Based on positive rating by the evaluation report against five OECD-DAC evaluation criteria (Relevance, Effectiveness, Efficiency, Impact and Sustainability, and the VFM), and impressive achievement throughout the year, continued strong performance on VfM and the high potential for large-scale impact this programme should continue. It is a flagship economic development programme in the British High Commission (BHC) Kigali’s portfolio delivering on both our economic (higher productivity economic activities, more investment in Rwanda, increased trade) and climate goals (through delivery of our International Climate Finance funding).

E: RISK

Overall risk rating: Moderate

Overview of programme risk

The Business Case outlines expected context, reputational, fiduciary, delivery, operational, people and safeguarding risks, which have been captured in the programme risk register. This is updated on quarterly basis following review of the TWFA risk register. SILTPR’s risk in the business case was assessed overall as “Major” with a “High” development impact. Since 2022 annual review, the overall risk rating has changed from major to moderate due to the fact that the operational model is operating successfully, the factories are operational, farmer loans are being repaid and recycled into the SCs, and tea yields and quality are high and exceeding targets.

All other types of risks (safeguarding, delivery, context (covid-19), fiduciary (budget cut) and operational (expected field and quality)), have been addressed and mitigated against and residual risk impacts are moderate (as per updated risk register on AMP). One residual risk remains major: quality of the road network. However, in this year of review, the GoR has rehabilitated Birambo to Rubengera road where 3 bridges were repaired, and the Rambura to Town road and prioritised to rehabilitate 55.8kms of roads. In addition, TWFA has submitted a proposal to FCDO to address this key operational constraint at Rugabano (ROS) through a capital investment to pilot a ropeway transport system for moving tea from farm to factory. This has been consideration by FCDO and the ropeways project is under design.

Given the progress in addressing risks and based on positive evaluation report, the programme overall risk rating is assessed as moderate.

Key risks that came up during review to continue monitoring closely include:
- The road network in the catchment area remains a challenge, especially during the rainy season when roads increasingly become slippery. Vehicles can get stuck, developing mechanical problems thus increasing maintenance costs as well as causing damage to seedlings and greenleaf during transportation. TWFA through SCs continues to lobby the local and national governments to start rehabilitation of the 55.8km that were prioritised.
- Late delivery, of imported fertiliser (NPK – Nitrogen, Phosphorus and Potassium) affected timelines for its application, potentially affecting the quantity and quality of tea. To address this, the SCs boards decided to increase bulk order purchase by 50% to boost buffer stock to help in application in the event of delay. Additionally, ROS and SCON established dedicated, reliable fertilizer storage facilities, while management continued to engage the Rwanda Fertilizer Fund to streamline future procurement.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery performance

SILTPR is delivered by TWFA in partnership with the Government of Rwanda (GoR), Browns, Luxmi (a major Indian tea company new to Africa), the Gatsby Charitable Foundation (Gatsby) and the three Rwandan professional specialised technical small holder service companies (SCs) co-owned by farmers – Services Company Outgrowers in Nyaruguru-North (SCON-N), Rugabano Outgrowers Services Company (ROS) and Ubumwe Tea Company Ltd (UTCL) at Nshili Kivu. Delivery of FCDO funding during the year of review was through the services companies (SCs) which assisted SHFs to overcome the barriers to entry in tea. The SCs provided agronomic support, farm inputs on interest-free credit, and production logistics (collection, weighing, transport, and payment). They also provided patient capital in the form of tea seedlings, fertilisers and continuous hands-on agronomic support. Farmers were also financed to cover land preparation services and for their daily labour on tea farms. These companies are the exclusive suppliers to two new factories. TWFA provides oversight and high-level and strategic perspective to ensure the project objectives are met. The programme is currently meeting expectations both in terms of delivery and development impact. The milestone targets for the year have been achieved and some targets significantly exceeded, despite the dry season which affected the production of tea.

Commercial Performance
TWFA is a not-for-profit organisation incorporated in the United Kingdom and registered in Rwanda by the Rwanda Development Board (RDB). FCDO funding to TWFA is through an accountable grant agreement (AGA) signed in September 2016. TWFA has fulfilled the key provisions within the AGA. Quarterly progress reports and monthly finance reports are provided to FCDO, in addition to an annual progress report. There has been an improved quality of the quarterly progress reports, comprehensively covering progress and challenges across key results areas as well as clear and more comprehensive financial reports with supporting narrative. Board meetings for the SCs take place on a quarterly basis where strategic performance and management related issues are discussed and progress against follow up actions are properly assessed, including on risks and safeguards. The board meetings are also attended by farmer representatives and FCDO, as an observer. The voice of farmers’ representatives in the board meetings has been very important and their views and concerns are properly addressed through open and inclusive discussions, for example the board approved farmers request to increase land preparation loan from RWF 900k to RWF 1m. During this year of annual review, FCDO approved a cost extension to the programme worth £4.6m of additional funding to (i) scale-up the model to Nshili Kivu, (ii) pilot a ropeway transport system for moving tea from farm to factory and (iii) improve sustainability in the sector by implementation of carbon neutral tea production and processing. This brings the programme total value to £16.3m with an end date of March 2029.

Financial Performance

TWFA have a tailored financial monitoring tracking tool which tracks project costs against FCDO full budget utilisation. TWFA submits financial reports to FCDO on quarterly basis and an annual progress report at the end of the year. Financial reports are reviewed by the Programme Manager and approved by the SRO before disbursements are made. During 2024/25, the UK disbursed £2,229,366 to fund activities, including £1m under cost extension for design of ropeways project to address transport challenges in Rugabano Karogi District and the funds were fully utilised. This success in financial performance is attributed to both FCDO and TWFA oversight of programme activities and improved forecasting capacity among SCs.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring

The logframe has been the main results framework used to monitor progress annually. The annual review process is also part of the FCDO monitoring, to assess progress against the logframe. Field visits are normally undertaken by FCDO, in addition to regular meetings with the implementing partner. These help to point out progress made; challenges and lessons learnt in the previous year to guide implementation of the programme in the following year.

Different Monitoring and Results Measurement (MRM) tools are in place to collect relevant data on project implementation on an ongoing basis. During the year, TWFA, factories and SCs continued to use various tools to collect data including: 1) Nursery and seedling tracking 2) Employment tracking 3) Farmer Field School (FFS) tracking 4) Farmers’ register 5) Land preparation tracking 6) Manager’s monthly progress reports 7) SCs’ board meeting reports 8) Logframe. The systems like ArcGIS also provide field data that is used by project managers. The process of digitisation of farmer records has also begun, using tablets. Land mapping using handheld GPS to capture farm coordinates and sketch map of the farms also begun, in addition to surveys.

Evaluation

TWFA has commissioned an independent external impact evaluation of SILTPR programme, conducted by TripleLine, which began in 2018/19. This evaluation uses a theory-based evaluation design to examine:
- Impact (what works, for whom, in what context).
- Sustainability (in terms of impact and institutions).
- Effectiveness.
- Efficiency.
- Relevance.
- Value for money.

The evaluation is supporting the knowledge management and learning function through a detailed assessment of the existing monitoring and results measurement (MRM) and learning systems. The evaluation faced various delays throughout the covid pandemic and the first evaluation report for phase 1 was delivered in September 2022. Overall, the report is positive about SILTPR’s performance. Recommendations have been developed for TWFA on how to improve the existing framework as well as support in collecting and processing lessons learned and encouraging cross-learning from SCON-N to ROS and vice-versa. An action plan has been developed by TWFA. FCDO will monitor its implementation going forward. As the programme has been extended, final programme evaluation report is expected in 2029.

Evidence and Learning

SILTPR was designed to be adaptive to allow for timely responses following lessons learnt throughout the implementation process. Programme learning and adaption are documented in the quarterly reports under each pillar of the programme. Output 1 (in Section C) summarises key learning and programme adaptations. Other lessons include:
- The delivery model for both ROS and SCON-N is identical following a series of lesson learnt and shared during services companies’ board meetings, which helps sharing insights and standardising best practice to improve the performance of both service companies.
- Farmer field school training delivery model is being adapted to ensure that no one is left behind especially illiterate farmers as recommended by evaluation report.
- The evaluation report noted a low adoption rate of climate-smart agriculture (CSA) practices/technologies at both ROS and SCON-N. The major emphasis would be put on increasing capacity building for smallholders on CSA technologies and increasing mobilization of farmers on climate resilience & its relevance. Environmental management has been incorporated in farmer field school curriculum. Service companies and TWFA will continue to monitor and introduce new CSA technologies/knowledge as programme implementation continues.
- The programme has undergone a structured adaption process guided by evidence, learning and strategic alignment with long-term development objectives to include expansion of the model to Nshili Kivu small holder tea farmers, piloting of ropeways transport in Rugabano Karogi District and enhancing the climate sustainability of tea sector focusing on decarbonization of factory operations in Nshili Kivu, Shagasha, and Mulindi.
- For this reporting year 10 surveys were conducted in March 2025, which included:
- Baseline;
- Annual socio-economic;
- vulnerability,
- Casual workers, and
- satisfaction survey. Analysis of these survey reports is being done which will inform futured adaption

Review process

This Annual Review was undertaken by the Programme Responsible Owner and the Senior Responsible Owner (SRO) of the programme, in the Green Growth and Trade (GGT) team, at BHC Kigali. The review was informed by desk-review of programme documents and meetings with implementing partner to verify results and discuss programme risks. It was approved by the GGT team leader, and Development Director

Date of last narrative financial report	July 2025 – annual and quarterly progress report	Date of last audited annual statement	August 2025, for the year ending 31 March 2025 (for ROS and SCON-N)

Annex A – SILTPR Theory of Change (Original)

Annex B: Revised Theory of Change

Annex B – SILTPR Infographic
Annex D – Summary of key findings from first evaluation report
What works and why?
Key success factors	Getting sufficient numbers of farmers to register, representing a sufficient number of hectares. / Delivering services to farmers. / Farmers produce high quantities of high-quality tea. / Farmer commitment to the scheme. / Anchor investors are delivering on their promises. / Government creates/maintains a beneficial enabling environment.
Additionality
initial evidence shows that there is a high degree of additionality for farmers, investors and workers.
In the absence of SILTPR would…	…farmers have planted more tea?	Unlikely
	…farmers have got access to SCON-N/ROS-type services?	No
	…farmers have seen a similar increase in incomes?	No
	…farmers have accrued similar benefits?	Unlikely
	…a similar number of jobs been created?	No
	…the communities in Nyaruguru and Rugabano benefitted to the same extent?	Possibly, but the positive effect of SILTPR is clear
	…Unilever/Luxmi have gained access to similar quantities of high-quality tea?	Not in those regions
How equitable is the programme?
Overall, SILTPR can be considered to be equitable and inclusive in terms of registration, providing services, enabling farmers to stick with the scheme, and enabling farmers to derive benefit from it, but the inclusiveness implications of land preparation loan size are worth considering going forward.
Replicability
Key success factors	A suitable crop. / Registering sufficient numbers of farmers. / Delivering services to farmers. / Farmers produce high quantities of high-quality tea. / Farmer commitment to the programme. / Anchor investors are delivering on their promises. / Government creates/maintains a beneficial enabling environment.