ADDENDUM TO BUSINESS CASE
INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Sustainable Inclusive Livelihoods through Tea Production in Rwanda (SILTPR)
Country or region targeted	Rwanda
Type of cost extension (if applicable)	Non-costed extension and no time extension. The proposal is to spend £1.64m more this FY in order to reduce outer year’s budget. Overall Budget will remain unchanged.
Original project budget	£5m
Original project start and end dates	July 2016 – March 2020
Previous extensions	Costed extension. Additional £6.83m (total budget became £11.83m). End date extended to December 2023. / No cost extension. No budget changes. End date extended to March 2025. / Costed extension August 2024, £4.624m end date extended to March 2029 (total budget £16.454m)
Cost extension value (if applicable)	Non costed extension (proposal is to spend £1.64m more this FY in order to reduce outer year’s budget) / (total budget remains £16.454m).
New reduced budget (if applicable)	-
New project end date (if applicable)	31st March 2029 (no time extension)
Business Case Quest Document No.	5518390

INFORMATION
What is the project’s purpose?
The project’s purpose is to support job creation and increase incomes by working with smallholder farmers (SHFs) to develop greenfield tea. / The UK, in partnership with The Wood Foundation Africa (TWFA), funds the Sustainable Inclusive Livelihoods through Tea Production in Rwanda (SILTPR) programme. The broader project is a partnership between the Government of Rwanda (GoR), Lipton[1], Luxmi (a major Indian tea company new to Africa), TWFA, the Gatsby Charitable Foundation (Gatsby), and the UK. UK funding currently amounts to £11.8m over nine years (2016-25). / SILPTR aims to drive job creation and increase incomes by supporting SHFs to develop tea in line with best practice, becoming reliable suppliers of greenleaf tea to existing factories and two newly constructed factories. Private sector partners have invested up to $30m to construct tea processing factories on core estates in the Western (Rugabano) and Southern (Nyaruguru) Provinces of Rwanda. The factory in Rugabano (constructed by Luxmi) began operating in 2019. The factory at Kibeho in Nyaruguru, built by Unilever/Ekaterra/Lipton[2], began operation in March 2024. TWFA have invested a further US$16m in interest-free returnable patient capital on top of the committed amount by the UK to support farmers. UK funding is specifically used for zero-interest loans to SHFs, which over time is recycled back into the service companies’ businesses. / The current project impact and outcome statements are still valid: / Impact Statement: Sustained, increased incomes for smallholder tea farmers and contribution towards enhanced macroeconomic stability. / Outcome Statement: Tea is planted and cultivated according to target standards, with employment opportunities for both men and women. / SILTPR to date has worked in two locations: / In four sectors of Nyaruguru District, Southern Province (Munini, Kibeho, Cyahinda and Mata sectors) TWFA established the Services Company Outgrowers Nyaruguru North (SCON-N) through which around 7,000 SHFs will be supported to plant approximately 3,400 ha of tea over approximately 15 years. Alongside this, Browns have built a new tea processing factory and have planted a core estate on 817ha. / Similarly, in Rugabano sector of Karongi District, Western Province, TWFA established the Rugabano Outgrowers Services Company (ROS) through which around 12,000 SHFs will be supported to plant approximately 4,000 ha of tea over approximately 15 years, while Luxmi through its subsidiary (the Rugabano Tea Company (RTC)), has built a new tea processing factory and planted a core estate on 356ha. / The Services Companies (SCs) established in Nyaruguru and Rugabano support farmers with all the necessary inputs, working capital, training as well as transportation and selling of greenleaf tea to factories. The SCs are co-owned by TWFA and the SHFs. / More detail on the operating model of the service companies is set out in Annex A.
What is the objective of the cost extension or other changes?
This is a non-costed and no time extension. The primary purpose of this extension is to increase spend by £1.64m this financial year in order to reduce outer years budgets, whilst not affecting project overall outputs. Upon approval of the addendum the programme team will work with the partner to reprofile the outer years payments and revise the timeline down. The programme team will come back to the Development Director for approval. / The additional funding this financial year will be spent on activities within the Wood Foundation eco system, on activities in the ROS site, which are within the scope of the original project agreement. The FCDO funded the ROS site under the original business case and thus has experience working here with the Wood Foundation. The evidence from annual reviews shows that Wood Foundation is a strong partner with a depth of knowledge in the sector and context. / As the FCDO will be spending more this Financial Year, the Wood Foundation will then cover outer years payments from their funding sources. This allows FCDO to frontload their commitments, reducing spending in outer years and risk to the portfolio under the alignment to 0.3% ODA. / Overall, TWFA proposes to draw a further £1.64m of FCDO commitments under the SILTPR programme, leaving £1.078m of FCDO commitment to be disbursed in future years and thus preserving the full results of the FCDO/TWFA partnership. / The August 2024 time and cost-extension in the SILTPR partnership runs from 2024 to 2029 during which period FCDO will invest a further £4.624m. This overall commitment comprised £1.583m for ROS ropeways; £2.471m for Nshili Kivu smallholder expansion; and £570k for sustainable tea production. Out of this, £1.906m has been drawn to date to cover programme expenditure for the period to March 2026. / Following discussions between TWFA and FCDO, TWFA would like to propose an increase in the drawdown for the 2025/26 financial as follows: / The Rugabano Greenfield Development (ROS) is a component of the SILTPR programme. This year, ROS is supporting 500 smallholder farmers to develop a further 250 hectares of new tea. This is in addition to 1,673 hectares already developed and which needs to be maintained through provision of inputs, agronomy and logistics services. The ROS budget for 2025/26 is $1.83m (£1.46m) which will be spent by March 2026. The summarised ROS budget is shown at Annex 1 below. TWFA proposes that FCDO funds the ROS budget this year, through a budget reallocation of £1.46m from the Nshili Kivu smallholder component of the cost-extension, while TWFA shall fund the Nshili Kivu smallholder expansion to the same extend in future years when FCDO funds have been exhausted. Therefore, TWFA requests $1.83m (£1.46m) additional drawdown for FY 2025/26 in this regard. / On the ROS ropeways, the second ropeway is now in production to be delivered in December 2025. The third ropeway is under design. It’s clear that the total budget of $2m (£1.583m) shall be exceeded by approximately $220k (£0.18m). TWFA requests to re-allocate an equivalent amount from the sustainable tea production component of the cost-extension to meet this shortfall in the ropeways budget. This reallocation also means that the expenditure on ropeways for this financial year shall increase by $220k (£0.18m). he ropeways support is within scope of the sustainable tea production objectives / Overall, TWFA proposes to draw a further $2.05 (£1.64m) of FCDO commitments under the SILTPR programme, leaving £1.078m of FCDO commitment to be disbursed in future years and thus preserving the full results of the FCDO/TWFA partnership. / Table 1: ROS summary budget FY2025/26 / Cost item Budget (Rwf) Budget (US$) / Field costs 398,569,000 274,875 / GL transport logistics 141,767,000 97,770 / Fertilizer costs 858,038,000 591,750 / Administration 384,675,000 265,293 / Mother bush expenses 38,850,000 26,793 / Nursery activities 334,657,000 230,798 / Staff M/cycle costs 10,000,000 6,897 / Land preparation advances 250,000,000 172,414 / Capital expenditure - general 236,248,000 162,930 / Total 2,652,804,000 1,829,520
What is the additional and total support the UK will provide?
The UK will provide additional £1.64m (100% CDEL). This increase will allow for outer years spend to be reduced by the same amount, meaning the overall budget for the programme remains unchanged. / Here is the indicative revised disbursement schedule for the programme. This is conditional on agreement with the partner. / Year Disbursement / 2016/17 607,037 / 2017/18 1,221,124 / 2018/19 1,245,532 / 2019/20 1,535,687 / 2020/21 1,107,518 / 2021/22 2,127,956 / 2022/23 1,910,702 / 2023/24 691,163 / 2024/25 2,229,366 / 2025/26 2,546,000 / 2026/27 578,000 / 2027/28 500,000
What are the expected results?
The additional resalts this year from the increased FCDO funding are: / 500 smallholder farmers to develop a further 250 hectares of new tea on the ROS site. This is in addition to 1,673 hectares already developed and which needs to be maintained through provision of inputs, agronomy and logistics services. / Due to FCDO’s funding being replaced by Wood Foundation in the outer years, the results to the March Addendum remain unchanged. The programme team will rework the logframe to measure and attribute results to FCDO funding: / Component A results / A detailed table is shown in Annex B. The results include: / An additional 2,500 SHFs cultivating tea. / An additional 1,940 Ha of tea. / An additional 10 permanent jobs (at factory – in addition to improved livelihoods in 2,500 SHF households). / Over 5,000 additional casual labour jobs (at least 50% female). / Increases in volume and value of greenleaf tea. / Increased income to SHFs from $2.3m to $4m, amounting to an additional $680 annual income per farmer, per year. / To note: this final result – SHF income – is an underestimate of total impact on farmer income. A substantial proportion (approx. 60%) of the 2,500 new farmers will only enter the project and begin planting and farming tea in 2027/28/29. Given that tea takes 3 or 4 years to mature, these SHFs will only begin to make substantial income from 2029/30 onwards. Incomes will continue to increase beyond the life of the FCDO SILTPR project. / Component B results / Details of the results are shown in Annex B. The results include: / A saving of $14m to GoR (through not having to rebuild/repair roads). / Green, resilient and sustainable infrastructure which saves 200,000 kms of truck movement, 50,000 litres of diesel use, and avoids 150 tonnes of CO2 emissions, per year. / Increased income to ROS SHFs, estimated at $850,000 due to increased quality and quantity of tea supplied to the factory. / Reduced cost for ROS SHFs, estimated at $160,000. / Improved life quality for SHFs and their families. Not having to head-carry tea (or employ labour) frees up significant time and resources. Benefits will be realised in terms of, for example, health, childcare, reduced safeguarding risks, and improved safety. These benefits would be disproportionally realised by women who bear the brunt of unpaid care work. Women will also experience reduced safeguarding risks, and improved safety. / Component C results / The carbon footprint of three large, well-known and important factories in the Rwandan tea sector accurately assessed. / Strategies have been implemented to reduce the carbon footprint of these factories. / Lessons have been shared across the Rwandan (and broader East African) tea sector.
What is the approach to implementation?
The new component will be implemented through (CDEL) grants to TWFA. These will be disbursed quarterly based on activity reporting, spend reporting, and financial forecasting. TWFA will manage these funds across all three components. TWFA have been a reliable and strong implementing partner to date, and the BHC Kigali programme team are satisfied with their performance and the management relationship. The programme team will investigate whether a revised Due Diligence Assessment is required for TWFA. / Internally within BHC Kigali, SILTPR is managed by a Grade 7 advisor (SRO), and an experienced SEO programme manager is PRO. Oversight is provided by the Green Growth and Trade team leader, and the Development Director. / SILTPR does not actively target female farmers. It targets SHF households. However, Rwandan women are disproportionately represented in smallholder farming: they make up 55% of the workforce but 88% participate in informal agricultural activities. Many SHF households are female-headed, and there a substantial proportion of ROS and SCON farmers are female. SILTPR has targets relating to female representation among farmer representatives and governance structures. SILTPR has taken action to address gender-specific challenges, for example, by requiring SHF households to use joint bank accounts (rather than accounts which are only in the male farmer’s name) to receive loans and subsequent income from selling greenleaf tea. / There are no concerns related to issues in the terrorism act. Standard text is included in SILTPR programme documents (e.g., MOU).
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
There is a substantial amount of learning from the programme to date which continues to inform the extension. / There are a variety of monitoring and results measurement tools already in place and these will be extended into component A of the extension (the work with SHFs). Some monitoring processes include: / Tracking nurseries and tea seedlings / Tracking employment (permanent and seasonal) / Tracking Farmer Field School (FFS) registration and attendance / Farmer registration / Tracking progress on land preparation / Monthly progress reports from SC management / Quarterly board meetings of the SC board / The programme logframe. / SCs also conduct an annual set of surveys. For example, in February/March 2024 ten surveys were completed at SCON & ROS as follows; / Baseline Survey of 383 new farmers / Annual Socio-Economic of 603 farmers / Vulnerability survey of 382 farmers / Survey of 80 casual workers / Survey on satisfaction with SC services for 595 farmers. / These surveys are used to track the socioeconomic impact of the project on farmers and workers, as well as assess satisfaction levels with SC service provision. The survey results are discussed at SC board meetings.
[1] At the outset the partner in the programme was Unilever. However, during the timeframe of this programme Unilever changed their tea business to a subsidiary called Ekaterra. Ekaterra has since been sold to new ownership of LIPTON Teas and Infusions (“Lipton”). All obligations were transferred in the changes to Ekaterra and Lipton; thus, no changes were made to the SILTPR programme. Throughout this document “Lipton” is used, but – for ease of comparison with previous programme documents – this is equivalent to previous references to “Unilever” or “Ekaterra”.
[2] See footnote 1.

Annex A – Service Company operating model

The delivery model of both SCs has developed during the project, based on lessons learnt. It can be summarised as follows:

The SC provides a fixed amount of RWF 900,000/ha[3] (which covers the full cost of land preparation and planting) as start-up loan without interest to each farmer. Farmers are paid in three instalments based on milestones: RWF 200,000 in phase 1, RWF 400,000 in phase 2 and RWF 300,000 in phase 3 for 1 ha of prepared and planted land (or the pro rata equivalent for smaller land sizes).
[3] This was increased to RWF 1m in 2024, to account for consistent depreciation of the Rwandan Franc.

The amount is paid through farmers’ bank accounts held at the Bank of Kigali (for Nyaruguru) or a range of commercial banks (for Rugabano) upon verification and approval of the quality and full completion of each phase of land preparation by the SC. There are no direct cash payments made to farmers. All payments go through bank accounts (these are opened with SC support after a farmer has registered).

As part of the financing package, farmers are supplied with good quality tea seedlings and fertilizers on no-interest credit, as well as technical guidance from SC experts to ensure application of good agricultural practices.

The contract signed between the SC and each farmer, states that the loan repayment will commence when farmers start supplying greenleaf to tea factories. Given the time it takes for tea to mature, this is usually not before year 3 or 4.

The SCs do not seek a profit and operate on a cost-recovery basis. They exist for the benefit of farmers, to enable them to successfully build their tea-growing businesses.

The SCs provide agricultural support services to tea farmers e.g., training through Farmers Field Schools (FFSs), mentoring and extension services, supply of farm inputs (seedlings, fertilizers etc.), interest-free start-up loan finance for land preparation and collection and transport of greenleaf tea to the factories. Over time the training methods in FFS have been adapted to ensure that they are inclusive of farmers who are, for example, illiterate.

The contract between a farmer and SC includes an agreement for farmers to agree to a “co-guarantor” arrangement whereby the farmer agrees to work together with a minimum of three other farmers in an adjacent growing area. These farmers agree that they will develop their greenfields together with support from other “co-guarantors” and carry out maintenance activities to the satisfaction of the SC. If any farmer becomes incapable of maintaining their farm, the co-guarantors will take over maintenance and receipt greenleaf proceeds from their farm until the farmer’s outstanding debt is repaid.

Minimum wage paid by both SCs to casual workers is currently RWF 1,550 for half-day of work; higher than the average pay for agricultural labour in both locations. To date, the seasonal workers in the programme have been 55% female. Farmers can offer work flexibly to casual workers, and – during the timeframe of the programme – the extension of the times of the day available for plucking tea has allowed for this proportion of females in the casual workforce. SCs also legally require (and closely monitor) farmers not to exploit any workers they hire, to provide them with PPE and not to engage child labour.
Annex B – Initial risk assessment and mitigations for ropeways pilot (component B)

Identified Risk	Mitigation
Permit for construction	The GoR (via the Road Transport and Development Agency, RTDA) were consulted and confirmed that, while permits are required as with any construction project, they did not foresee any circumstance which would result in a rejection of the application for a permit.
Wayleaves for the structures and rope passage	RTDA advised that where the supporting structures were to be located, including the end loading and unloading stations, the land would be purchased, and would follow all legal requirements. They have suggested that they may be able to help fund such acquisitions. The extent of the land requirement for each ropeway is about 25sqm per 250m of ropeway and 50sqm at each of the two end stations. For a typical ropeway of 2km this would mean 275sqm of land to be acquired. / Along the length of the ropeway, the ropes will be at a height not to interfere with any buildings. RTDA have advised that wayleaves will not be required for the land which the ropes cross. / Where the route crosses tall trees these will have to be trimmed or removed. The permits to do this will follow the legal process that REG use for installation of electrical cables.
Safety of goods at high level over private and public spaces	The ropeways will be fitted with steel cradles, in which the bags of tea and/or fertilizer are carried. This will minimise the risk of any goods falling.
Intersects with National electricity cables	A meeting was held with REG who advised that if there were any clashes, their power cables would be re-routed underground. There were no clashes at the time of the feasibility study in September 2022.
Climate and weather	The ropeway will be designed to accommodate high winds and heavy rain. The feasibility designer has installed systems in the Himalayas where they operate year round, including during the monsoon seasons.

Annex C – Budget

The budget from TWFA was provided in USD. This was converted (in July 2024) to GBP at an the corporate exchange rate provided by FCDO’s Systems Accounting Team of 1.26409 GBP:USD. GBP figures have then been rounded to the nearest £1,000.

USD
Component	2024/25	2025/26	2026/27	2027/28	2028/29	Total
A	375,000	625,000	625,000	750,000	750,000	3,125,000
B	600,000	1,400,000	-	-	-	2,000,000
C	90,000	135,000	360,000	135,000	-	720,000
Total	1,065,000	2,160,000	985,000	885,000	750,000	5,845,000

GBP
Component	2024/25	2025/26	2026/27	2027/28	2028/29	Total
A	297,000	494,000	494,000	593,000	593,000	2,471,000
B	475,000	1,108,000	-	-	-	1,583,000
C	71,000	107,000	285,000	107,000	-	570,000
Total	843,000	1,709,000	779,000	700,000	593,000	4,624,000

Annex D – Summary of key findings from first evaluation report

What works and why?
Key success factors	Getting sufficient numbers of farmers to register, representing a sufficient number of hectares. / Delivering services to farmers. / Farmers produce high quantities of high-quality tea. / Farmer commitment to the scheme. / Anchor investors are delivering on their promises. / Government creates/maintains a beneficial enabling environment.
Additionality
initial evidence shows that there is a high degree of additionality for farmers, investors and workers.
In the absence of SILTPR would…	…farmers have planted more tea?	Unlikely
	…farmers have got access to SCON-N/ROS-type services?	No
	…farmers have seen a similar increase in incomes?	No
	…farmers have accrued similar benefits?	Unlikely
	…a similar number of jobs been created?	No
	…the communities in Nyaruguru and Rugabano benefitted to the same extent?	Possibly, but the positive effect of SILTPR is clear
	…Unilever/Luxmi have gained access to similar quantities of high-quality tea?	Not in those regions
How equitable is the programme?
Overall, SILTPR can be considered to be equitable and inclusive in terms of registration, providing services, enabling farmers to stick with the scheme, and enabling farmers to derive benefit from it, but the inclusiveness implications of land preparation loan size are worth considering going forward.
Replicability
Key success factors	A suitable crop. / Registering sufficient numbers of farmers. / Delivering services to farmers. / Farmers produce high quantities of high-quality tea. / Farmer commitment to the programme. / Anchor investors are delivering on their promises. / Government creates/maintains a beneficial enabling environment.