## Annual Review Template

Title: Sustainable Inclusive Livelihoods through Tea Production in Rwanda (SILTPR)
Programme Value £ (full life): £11.8m		Review date: Aug 2022
Programme Code: 204941	AMP start date: Aug 2016	AMP end date: Dec 2023

Summary of Programme Performance

Year	2016/17	2017/18	2018/19	2019/20	2020/21	2021/22
Overall Output Score	A	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-204941/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-204941/documents

A. SUMMARY AND OVERVIEW
Description of programme

Tea is an important crop that makes a substantial contribution to Rwanda’s economy.[1] Farming tea is labour intensive and offers significantly higher incomes to farmers than traditional crops. Thanks to favourable agroecological conditions, Rwandan tea is high quality and commands high prices. The Rwandan tea sector has significant potential for growth and investment. However, the sector faces constraints, such as small and fragmented plot sizes, low agronomic skills and capacity of small holder farmers (SHFs), low fertilizer use, and lack of capital. This leads to low incomes and a limited capacity to invest.
[1] In 2020, Rwanda exported $54.7M in Tea, making it the 19th largest exporter of Tea in the world. Tea was the 3rd most exported product in Rwanda. The main destinations of Tea exports from Rwanda are Pakistan ($28.1M), UK ($15.8M), Kenya ($5.01M), Germany ($1.61M), and Russia ($1.25M). Tea accounts for around 6% for total export earnings in 2020 (Source: https://oec.world/en).

In this context the UK, in partnership with The Wood Foundation Africa (TWFA), fund the Sustainable Inclusive Livelihoods through Tea Production in Rwanda (SILTPR) programme. The broader project is a partnership between the Government of Rwanda (GoR), Unilever, Luxmi (a major Indian tea company new to Africa), TWFA, the Gatsby Charitable Foundation (Gatsby), and the UK. UK funding amounts to £11.8m over seven years (2016-23).

SILTPR aims to drive job creation and increase incomes by supporting SHFs to develop tea in line with best practice, becoming reliable suppliers of greenleaf tea to existing factories and two new factories. Unilever[2] and Luxmi have committed to invest up to $44m and $27m respectively to construct tea processing factories on core estates in the Western (Rugabano) and Southern (Nyaruguru) Provinces of Rwanda. TWFA will invest a further US$16m in interest-free returnable patient capital on top of the committed amount by the UK to support farmers. This programme has the potential to have a significant impact on the Rwandan tea sector. At maximum capacity, the two factories will be supplied by 19,000 SHFs who will plant tea on a total of over 10,00 hectares (Ha) of land and produce over 14m kg of made tea per year.[3] Already, in terms of the amount of tea in the ground (including both SHFs and Unilever’s industrial block), Nyaruguru is now the largest tea estate in Rwanda.
[2] During the timeframe of this programme Unilever changed their tea business to a subsidiary called Ekaterra. Ekaterra has since been sold to new ownership. All obligations of Unilever transferred to Ekaterra, thus no further risks arise. For the purposes of this document, and ease of comparison with previous Annual Reviews, references remain to “Unilever”.
[3] For context, Rwanda’s total tea exports in 2021 were 35.2m kg.

The programme operates through the establishment of professional smallholder service companies (SCs).[4] Services Company Outgrowers in Nyaruguru-North (SCON-N) and Rugabano Outgrowers Services Company (ROS) are assisting SHFs to overcome the barriers to entry into the tea sector. They provide agronomic support, farm inputs on interest-free credit, and production logistics (collection, weighing, transport, and payment). These companies will be the exclusive suppliers to the new Unilever and Luxmi factories. Patient capital is being provided in the form of tea seedlings, fertilisers and continuous hands-on agronomic support. Farmers are also financed to cover land preparation services and for their daily labour on tea farms.
[4] The service companies are registered as non-profit companies limited by guarantee and operate on a cost-recovery basis.

Alongside this Annual Review FCDO plans to submit a no-cost extension to SILTPR. This will involve extending the life of the programme from December 2023 to March 2025, but with no change in the amount of UK funding committed. This will have various benefits: it will further extend the partnership between TWFA and FCDO, allowing FCDO to maintain influence in the investment; it will allow FCDO to support a further planting season; it will deliver more results for SHFs and in terms of investments within the lifetime of the programme; and it will allow FCDO's constrained ODA budget to have maximum impact.

Summary supporting narrative for the overall score in this review

This Annual Review (2021/22) scores A. The three programme outputs score A, A, A+. This indicates that this high-performing programme continues to meet expectations, even with a logframe revision during the year which made targets more stretching. The programme is on track to achieve the planned outcomes and impact. As with all programmes SILTPR faces some challenges (some arising from the pandemic), but these have been well-managed by the service companies (e.g., mitigating cancelled farmer field schools (FFS), or working to deliver road repairs) and have had relatively limited impact on the ability to achieve output indicators. Through 2020 and 2021 agriculture was – relatively – less badly hit in Rwanda than some other sectors. Whilst covid prevented gatherings and meetings – important training, sensitisation, and recruitment methods for the tea service companies – many day-to-day farming activities could continue throughout. Nonetheless, challenges remain. These are both very localised – such as poor roads in the regions where SILTPR operates, or the shortage of labour for working on farms (which will become increasingly difficult as the programme expands) – or as a result of global factors (e.g., the high price of inputs such as fertiliser as a result of the Russia/Ukraine conflict). Many challenges SILTPR is already mitigating against, for example by ensuring that any possible delays in completion of factories does not negatively affect SHFs.

The programme outputs are structured around (i) effective learning and adaptation, (ii) farmers planting high quality tea according to best practice, and (iii) inclusive and effective management of tea service companies. Details of the output progress is in Section C.

The past two years have been when tea has started to be harvested in the two regions. This has provided an opportunity to assess how well the programme is doing on outcomes and impacts. There is very good evidence that this programme will achieve both its stated outcomes and impact. Section B outlines the progress on the annual targets. All, bar one of these indicators has been exceeded. SILTPR is producing more tea at a higher quality than was originally envisaged. It is creating more employment opportunities – particularly seasonal – than was expected. It continues to bring in significant FDI to Rwanda. Farmers are making more profit from their tea production than was expected and are reporting improvements in their overall socio-economic situation.

Major lessons and recommendations for the year ahead

Lessons and recommendations are shown throughout the following sections. Some key overarching recommendations include:
- As set out above, FCDO should extend the programme, at no additional cost in order to maximise benefits. As part of this process, TWFA and FCDO should review the logframe and risk matrix.
- As part of this review of logframe and risk matrix, TWFA and FCDO should in particular focus on equity. The data collected by the monitoring and results measurement systems are disaggregated by gender, disability and age – but this is not always reflected in the logframe (e.g., impact indicator 4, output indicator 3.5).
- It is also important that TWFA and FCDO review the activities already in place to try and drive female farmer representation (output indicator 3.2) and bring in new activities, training or sensitisation to reach this target.
- The partnership model used in this programme remains highly successful – particularly in budget constrained times. FCDO should consider how – including through the ongoing evaluation – to scale up impact and use this kind of model in other sectors. FCDO should also consider how to best share learning with other DPs, GoR, private sector and actors in the tea sector to encourage scale up and replication.
- A proportion of the UK funding for SILTPR is eligible for International Climate Finance (ICF) funding. It is likely that SILTPR could contribute to other ICF indicators. FCDO and TWFA should review the programme against the ICF results framework and agree what can be reported and review the proportion of programme finance attributable to the ICF,
- As covid restrictions lift FCDO should ensure a more regular series of field visits as well as senior interactions to lift the profile of the programme through active communications.
- FCDO and TWFA should continue to collaborate to solve some of the key issues facing the programme – not least considering programmatic options (including by linking with other FCDO programmes) to address the issue of labour shortages.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SILTPR Theory of Change (ToC) can be summarised as follows: “the provision of effective support to smallholder farmers (SHFs) through Services Companies (SCON-N and ROS) will increase the capacity of SHFs to plant and maintain tea, and supply high quality (and in sufficient quantity) greenleaf to tea factories. As a result, farmers will experience sustained and increased incomes and livelihoods while more private investment is attracted as the sector becomes de-risked”. A diagram showing the theory of change is at Annex A.

The theory of change and outcome/impact statements have not changed in the past year. Very early in the programme the impact and outcome statements were both amended (slightly) from those set out in the original Business Case.[5] [6] In 2020 an indicator was added at the impact level (indicator 4) to capture the improvements in socioeconomic situation as perceived by farmers involved in the programme (measured through annual surveys).
[5] Impact statement in Business Case (“Increased sustainable incomes and improved livelihoods for farmers and wage labourers through the production of tea”) has changed to “Sustained, increased incomes for smallholder tea farmers and contribution towards enhanced macroeconomic stability.”
[6] Outcome statement in Business Case (“Tea is planted and cultivated according to target standards and farmers receive decent wages for developing tea”) has changed to “Tea is planted and cultivated according to target standards, with employment opportunities for both men and women.”

A greenfield[7] tea development is an expensive and long-term undertaking which presents challenges and risk for all parties, especially the SHFs and private investors. It takes four years from planting tea until it reaches full commercial bearing. This creates a significant financial strain on the farmer given the loss of income from land set aside for this activity. Unless patient capital is available, tea is often an unviable proposition. Similarly, significant expertise is needed to maximise the productivity of tea bush. Technical assistance can enhance and support good agricultural practices during land preparation, planting, weeding, applying fertilizer and pesticides, and plucking tea. Furthermore, large-scale investors struggle to source tea of consistent quality and quantity from SHFs and can benefit from efficient aggregation and extension services. The SILTPR service companies provide these services to secure high quality and sufficient quantity of supply which reduces the investor’s risk.
[7] Greenfield means starting from scratch, building new facilities, and farming on land which has not been used for tea previously.

In terms of capital, the service companies provide RWF 900k[8] per hectare as a start-up zero-interest loan to farmers, paid in three instalments based on preparation of land and planting tea. Funds are paid into farmers’ bank accounts at local banks or SACCOs (Savings and Credit Cooperatives), hence increasing farmers’ engagement with the formal banking sector and reinforcing financial inclusion. Loan repayments start when tea bushes start bearing and farmers begin to supply tea to factories, this is generally in year 2, 3 or 4.
[8] Approximately $900.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

SILTPR’s outcome statement is that: “Tea is planted and cultivated according to target standards, with employment opportunities for both men and women.” This is tracked by four outcome indicators with annual milestone targets. These are shown in the table below.

Outcome indicator	2021/22 target	2021/22 achievement
1. Amount of Greenleaf tea produced annually (kg)	1,212,300	1,981,347 / (163%)
2. Survival rate of tea bushes per ha per year	85%	94.7% / (111%)
3. Quality of green leaf produced [measured by % of good leaf collected from the smallholder farmers]	65%	70.3% / (108%)
4. No. of individuals engaged (Permanent and Seasonal) in productive activity under the programme	Permanent: 7,654 / Seasonal: 20,376	Permanent: 7,164 / (94%) / Seasonal: 26, 333 / (129%)

The programme is exceeding all outcome indicators bar one, often by a substantial amount. The amount of greenleaf tea produced, the survival rate of tea bushes, the quality of the tea produced and the number of people with productive work are all higher than was expected at the outset of the programme. This is extremely positive.

The only target which is below target (permanent jobs) is so because it is a cumulative target and previous years had been low. In the reporting year (2020/21) the annual target was 1,470 and the number of permanent jobs created was 2,256 – an annual achievement of 153%.

- This year is the second year that outcome indicator 1 has been measured (greenleaf tea production only started recently). These amounts largely come from farmers who enrolled early in the programme (2016/17/18). Nearly 2m kgs of greenleaf tea was produced, more than double the amount (821k kg) from the previous year, and exceeding 1.2m kg target. This target was revised during the logframe revision in November 2021. It was increased by over 50% (from 824k kg to 1.2m kg) to better align with SCs business plans and operational targets. Hence, the overachievement of this target is impressive.
- Outcome indicator 3 was also assessed for the second time this year and exceeded the logframe target.[9] Ensuring that tea produced is high quality, and thus can attract a premium at market, benefits both the farmers (who receive a quality bonus) and the private sector companies involved. Rwandan tea continues to do well and sell at a premium at the Mombasa tea auction. In early 2022 prices averaged $3.02/kg[10], the tea produced in Rugabano (ROS) performs particularly well, selling above the Rwandan average and is second only to Gisovu (the top factory in Africa as a whole).
  [9] In the November 2021 revision of the logframe the target was increased slightly to 65% to align with the GoR’s minimum standards.
  [10] By comparison Kenyan tea sold at $2.72/kg, Burundian tea at $2.44/kg, Ugandan tea at $1.27/kg and Tanzanian tea at $1.15/kg/.
- Indicator 4 tracks the employment effects of the SILTPR programme, both permanent and seasonal jobs. Permanent jobs are primarily farming households – there were 1,128 new farming households in 2020/21 (against a target of 735) – but also captures direct employment at the service companies (SCON-N and ROS) and the factory sites (Unilever and Luxmi). Seasonal jobs far surpassed the target, these include workers hired for maintenance and plucking, workers at nurseries supplying tea seedlings, and temporary positions at the factory sites. In terms of gender disaggregation, permanent jobs are split 50-50,[11] yet seasonal jobs are 57% female. The size of the seasonal employment is partly a reflection – in response to recommendations from previous Annual Reviews – of encouraging using external labour rather than just family members for land preparation and maintenance. Part of the Rainforest Alliance certification achieved by both service companies in previous years considered how labour is used on farms (hours, working conditions, etc.). In terms of pay, the minimum wage paid by both SCON-N and ROS to casual workers is RWF 1,550 per half-day. This is higher than the average half-day pay for agricultural labour in both districts and compares favourably to previous day rates (RWF it is up from 1,000 per half-day in the previous year). Nonetheless the availability of labour remains a key challenge for the programme (see details in section C).
  [11] This assumes that a new farming household within the programme generates permanent two permanent jobs – one male one female. The accuracy of this assumption should be further examined through the programme evaluation.

At the impact level SILTPR aims for: “Sustained, increased incomes for smallholder tea farmers and contribution towards enhanced macroeconomic stability.” This is tracked through four indicators with annual targets. These are shown in the table below.

Impact indicator	2021/22 target	2021/22 achievement
1. Farmer's average net income per ha of tea cultivated (USD)	$605	$611 / (101%)
2. Annual Value of Greenleaf produced (USD)	$363,690	$457,388 / (126%)
3. Increased FDI in the Rwandan tea sector (Cumulative)	$34,411,000	$21,663,030 (63%)
4. % of farmers who joined the programme in previous year(s) who report improvement in their overall socio-economic situation (%)	SCON-N / 2017 cohort: 50% / 2018 cohort: 40% / 2019 cohort: 30% / ROS / 2018 cohort: 40% / 2019 cohort: 30%	SCON-N / 2017 cohort: 77% / 2018 cohort: 75% / 2019 cohort: 56% / 2020 cohort: 46% / SCON-N ave: 65% / ROS / 2018 cohort: 45% / 2019 cohort: 58% / 2020 cohort: 65% / ROS ave: 56%

Again, progress against these four measures is positive. Showing that the programme is already having a real impact on farmers’ lives – in terms of income and perception of improved situations.

- Impact indicator 1 tracks the net income for each hectare of tea. This has greatly exceeded expectations at over $600/ha.[12] This only slightly exceeds the target. However, this target was revised upwards substantially[13] in the logframe revision in November 2021, and the result is that farmer incomes are almost double the same measure in the previous year ($327/ha). This is still based on quite small numbers (farmers who enrolled early) but is hugely encouraging. To put this into context, an early survey in Nyaruguru found that the average net value of traditional crops was around $150/ha. Farmers are making four times that amount from farming tea that is yet to reach full maturity.
  [12] For SCON-N the average net income was $691/ha, benefitting 277 farmers. For ROS, the figures are $530/ha, and 701 farmers.
  [13] From $216/ha to $605/ha.
- Indicator 2 – the amount of greenleaf tea produced – substantially exceeds expectations. As with indicator 1, the target was revised upwards in November 2021 (from $289k to $364k) to better align with operational targets. This higher target has still been exceeded, by 26%.
- The only indicator which has not been met is indicator 3. There has been over $22m of FDI into Rwanda, but this falls short of the $34m target. This is largely a result of slower milestones towards construction of the Unilever factory but overall, both the factory and core estate are on track.[14]
  [14] The Luxmi factory in Rugabano is up and running, the Unilever factory in Nyaruguru is expected to be constructed and functioning by Quarter 4 of 2023.
- Indicator 4 is new and captures farmers’ self-reported improvements in their overall socioeconomic situation. All targets have been substantially exceeded. Across the board, and over time (difference “cohorts”) farmers are reporting improvements in their overall socio-economic status.

Using outcome and impact indicators would score this Annual Review above an A (likely A+). This is very positive news. We are seeing that efforts before and during the pandemic are bearing fruit in 2021/22 with strong outcome and impact performance. This demonstrates that the theory of change is working. One reason to remain cautious is that the impact of covid on the programme (for example, the lack of farmer field schools in 2020) may only be seen in future years (with possible lower yields), this however seems low risk.

Value for money (VfM) of the SILTPR programme is substantial. The UK investment has helped leverage a large amount of private sector investment into Rwanda. The programme has been successfully able to resolve a coordination problem between multiple SHFs and potential large-scale tea processing plants. In the absence of this programme there would be no coordination mechanism for the farmers to liaise with Unilever or Luxmi. There would have been little incentive for large firms to establish relationships with thousands of SHFs. SILTPR bridges this gap. The programme works with experienced partners who, in the past year have successfully handed over a separate tea investment – Mulindi – to farmer control. This provides lots of opportunities for learning.[15] The UK’s investment is relatively small (~$15m), but this has leveraged over $100m in private (Unilever and Luxmi) and philanthropic capital (Gatsby and TWFA). In addition, a further $30m has been leveraged with the development of SCON-S (including $10m of GoR funding). The strength of the demonstration effect can be seen in the different approaches of SCON-N and SCON-S. For SCON-N, their very first greenfield investment in Rwanda, Unilever chose to acquire 700 Ha of land for its own core estate to provide some base supply to its factory to mitigate the risks of the SHF model. The SHF model has many advantages (e.g., less expropriation, better livelihood impacts) and has proven to deliver high quality tea. Therefore, the second phase (SCON-S) is fully SHF, with no core estate required.
[15] For more information on Mulindi see here.

Evaluation
An independent evaluation of SILTPR has been commissioned. This will use a theory-based evaluation design to examine: impact (what works, for whom, in what context); sustainability (in terms of impact and institutions); effectiveness, efficiency, relevance and value for money. The evaluation faced various delays throughout the covid pandemic, meaning that the first evaluation report (some five years into implementation) was only produced in 2021/22. Thus, this report is less a “baseline”, but an assessment of initial progress of the programme. At the time of writing, this report is in draft stage and feedback is being gathered from stakeholders. As with all (good) evaluations it contains is a huge amount of detailed information – more than can be summarised here. The report contains assessments of the different aspects (impact, efficiency, etc.) for each SC. It sets out recommendations with a variety of different timelines (low-cost quick fixes, priority investments, mid-term actions, monitoring priorities, and strategic considerations). Overall, the report is positive about SILTPR’s performance across the wide range of issues it examines, as can be seen from the table in Annex B, which summarises the key findings and recommendations of the draft report.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on impressive achievement throughout the year, continued strong performance on VfM and the high potential for large-scale impact this programme should continue. It is a flagship economic development programme in the British High Commission (BHC) Kigali’s portfolio delivering on multiple objectives around resilient and productive economics, specifically by generating higher productivity in the tea sector, greater investment in Rwanda, and increased trade.
## C. DETAILED OUTPUT SCORING

Output Title	Programme efficiently implemented and adapted in line with emerging findings and learning
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Evidence in support of solid project design generated and project implementation adapted in line with recommendation of how to best support higher incomes of smallholder farmers while achieving commercial business sustainability	At least 1 knowledge product/evidence in support of project design (e.g., case study, documentary, success story, beneficiary story, brochure, fact sheet, annual report, articles etc.) produced and disseminated. / At least 4 adaptations to project design implemented as a result of evidence are documented by SILTPR	2 knowledge products / 5 project adaptations from evidence
1.2 Monitoring and results measurement (MRM) system implemented and evaluation conducted according to agreed methodology and timeframes	Nyaruguru and Rugabano socioeconomic baseline surveys and follow ups carried out	Surveys were conducted

Briefly describe the output’s activities and provide supporting narrative for the score.

There are two indicators under this output. Both have met targets. This output scores an A. Output 1 is about ensuring that the implementation of SILTPR benefits from relevant emerging findings and lessons, including from DFID/FCDO Annual Reviews, regular quarterly performance reports, analysis and board meetings.

Learning and scaling are demonstrated by the SILTPR programme substantially influencing the design of the new phase of work in Nyaruguru, called SCON-South (SCON-S). This is a $30m partnership between the GoR, TWFA and Unilever is explained in the previous year’s Annual Review (2020/21).

In the past year, many lessons have emerged from TWFA and Gatsby’s work in the handover of the Mulindi Tea Company to farmers in March 2022. They are highly relevant to SILTPR. The lessons include
- Adopting a long-term approach to strategic development beyond 10 years which allows a focus on transformational impact rather than the short- term gains. Initial signs are promising with ROS and SCON-N farmers begin to receive proceeds from tea planted in 2017 and 2018, average net income per ha is $611. This is expected to increase to $3,000/ha over the next 10 years.
- Having a shared vision with the government and other likeminded shareholders is key in ensuring buy-in and support. This is relevant for SILTPR when addressing challenges, advocating for policy review/formulation and infrastructure development around the factories. In Rwanda, the government is strongly committed to support SHFs.
- Ensuring sustainability of the intervention is at the core of the operations to ensure long-term results that will be enjoyed for generations to come as opposed to focus on short-term financial and operational goals.

In the past year other programme adaptations included:
- A thorough revision of the programme logframe in November 2021. This aligned targets with operational targets of the SCs, revised targets upwards where needed to ensure they remained ambitious and meaningful given past overperformance.
- A review of the survey and monitoring tools, especially to incorporate best practice on safeguarding.
For outcome indicator 1.2, the surveys scheduled for the previous year (Jan/Feb 2021) had to be postponed and were carried out in May 2021. For this reporting year, the surveys were conducted in February 2022. Surveys conducted included:
  - Baseline survey for 415 new farmers
  - Annual socioeconomic survey for 274 farmers
  - Vulnerability survey for 415 farmers
  - Workers survey for 80 workers
  - Satisfaction survey for 274 farmers
Some findings from the surveys are described in output 3.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

VfM is not defined by output in either the original business case or previous annual reviews. Further information on VfM is included in Section E.

This output enhances VfM by producing evidence informing programme adaptations with a view to maximizing impact. It also considers that SILTPR is based on the latest and most relevant evidence. Most evidence products, lesson learnings and adaptations were completed with limited additional cost. As set out above, key elements demonstrating strong VfM here is the extension to a second phase in Nyaruguru and the lesson learning from the Mulindi handover. The initial investment by the UK (and others) has leveraged an additional $30m investment into SCON-S, similarly the UK investments in SILTPR are benefitting from previous investments in Mulindi.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to indicators. There were no changes to 2021/22 targets in this output during the logframe revision in November 2021.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations under this output from last year’s Annual Review are shown in the table below.

Recommendation	Progress
Given that surveys happened late (May 2021) it will be important to analyse these and consider what – if any – programme adaptations are required.	Survey findings were presented to SCON-N and ROS boards. In particular the findings on the areas where farmers were most/least satisfied with the SC services were considered in decisions by Board and management.
Continue to ensure that lessons from SILTPR are used to assist the design and operation of SCON-S.	SCON-S and SCON-N continue to work very closely together and share knowledge – they essentially operate as nearly one organisation.

Recommendations for the coming year:
Important to finalise the first evaluation report and for SCON-N/ROS/TWFA to set out an action plan for responding to recommendations from the evaluation.
Output Title	Farmers coordinated and supported to plant quality tea
Output number:		2	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of Farmer Field Schools (FFS) operational with defined curriculum, running fortnightly (Cumulative)	60	63 / (105%)
2.2 Number of farmers participating in Farmer Field Schools (Cumulative)	1,500	1,827 / (122%)
2.3 Total seedlings/tea bushes planted by smallholders (Cumulative)	27,260,380	29,062,359 / (107%)
2.4 Hectares of tea planted by smallholders (Cumulative)	1,947	1,988 / (102%)
2.5 No. of farming households planting tea with the support of the service company's extension services (cumulative)	3,762	4,283 / (114%)

Briefly describe the output’s activities and provide supporting narrative for the score.

There are five indicators under this output. All have met or exceeded targets. This output scores an A. Output 2 is the core of the activity under SILTPR (reflected by the 50% output weighting), it is about ensuring that farmers are adequately supported to plant high quality tea.

Outputs 2.1 & 2.2 – farmer field schools (FFS) – were one of the main programme casualties of the pandemic in earlier years. All classes were put on hold due to restrictions on gatherings, this affected nearly 1,000 farmers. In mitigation training was carried out at individual farm level with agronomists and capitas travelling door-to-door (“training-by-visit” approach). During this reporting year (2021/22) FFS could restart as covid restrictions were eased. In ROS 12 FFS reached 360 farmers, in SCON-N 20 classes were formed with 583 farmers. Targets were exceeded for both indicators. The FFS focus on agronomic issues, plucking standards, decentering, tipping, farm preparation, soil control measures, cross-cutting matters on health and nutrition, health and safety, livestock keeping, financial management and record keeping, and COVID-19 protocols and precautions. Demonstration plots have also been established for practical training.

Outputs 2.3 & 2.4 cover the number of tea seedlings and the area of tea planted: both these targets were slightly exceeded. Each site planted over 4m tea seedlings in 2021/22, bringing the cumulative total to nearly 30m. SILTPR has now planted nearly 2,000 ha of tea, of which nearly 600 ha was planted in the past year. In terms of the amount of tea in the ground (including both SHFs and Unilever’s industrial block) Nyaruguru is now the largest tea estate in Rwanda.

Output 2.5 covers the number of farming households involved in the programme. This has surpassed 4,200 – of which over 1,100 new farmers were recruited in the past year. This exceeds the target. One consequence of this is that the average size of tea planted per farmer is much lower than was anticipated at the outset – on average 0.3 ha per farmer in ROS[16].
[16] Equivalent figure for SCON-N is 0.9 ha/farmer.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

VfM is not defined by output in either the original business case or previous annual reviews. Further information on VfM is included in Section E.

Key cost drivers here include input costs, cost of land preparations and planting, as well as cost of nursery development and maintenance. Fertiliser prices have increased hugely in the past two years due to covid and the Russia/Ukraine conflict. Fertiliser prices for the tea sector have increased in the range of 50-60% in the past year alone. This remains a challenge for the agriculture sector as a whole. To seek to ensure better input quality at the right prices, SILTPR SCs procure inputs competitively. Economies of scale are pursued through bulk procurement of fertiliser with other TWFA factories and tea operations.[17]
[17] The Wood Foundation, in addition to the greenfield sites through SILTPR, has brownfield tea estates in Rwanda at Mulindi, Shagasha, Gisovu, Pfunda & Rugabano: https://www.thewoodfoundation.org.uk/venture-philanthropy-in-africa/tea-brownfields/

Mushubi mother bush (from which tea seedlings are taken) costs have in the past been higher than anticipated, which has been a key challenge. During the year, following long negotiations, an agreement was signed with NAEB in January 2022 to lease the mother bush with the annual lease being reduced from RWF 17m RWF 11m. However, the Mushubi mother bush is located a long way from Nyaruguru – adding costs. SCON-N’s medium-term strategy is to develop its own mother bush in Nyaruguru, this will take a number of years, but will provide significantly improved VfM in the medium- and long-term.

A key challenge to delivery, and thus VfM, is the state of roads in both locations, in particular in Rugabano. The bad roads affect the transportation of seedlings to the smallholders’ farms, leading to delays in planting. It also damages the seedlings. Following harvest, farmers can resort to carrying greenleaf long distances (up to 10km), often having to hire additional labour for this task. Continued poor roads will hamper access to new areas that SCs are targeting for expansion. All of this reduces the efficiency and effectiveness of the programme model and can disincentivise new farmers from joining the project. It also may provide a real risk to achieving the scale of impact that it otherwise might. SILTPR has instigated strong mitigations to this challenge, as described in Section D.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to indicators. There were changes to 2021/22 targets during the logframe revision in November 2021, specifically:
- Output 2.1 target revised down from 100 to 60. This is a cumulative target and was revised to account for the missed FFS due to covid.
- Output 2.2 target revised down from 2,990 to 1,500. This is a cumulative target and was revised to account for the missed FFS due to covid.
- Output 2.3 target revised up from 23.8m to 27.26m to better account for previous overachievement.
- Output 2.4 target revised up from 1,700 to 1,947 to better account for previous overachievement.
- Output 2.5 target revised up from 2,990 to 3,762 to better account for previous overachievement.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations under this output from last year’s Annual Review are shown in the table below.

Recommendation	Progress
Given the poor quality of roads and the fact that tea production will increase year on year, continuing to address the rehabilitation of roads is critical.	See progress described above in VfM section.
TWFA should assess the impact of the lack of FFS and consider whether further mitigation of future risks is necessary. Important to plan – to the extent possible – for what will be feasible in terms of training in the coming year(s), given covid	Mitigation for cancelled FFS was strong, although whether there will be any knock-on effects in future years remains to be seen. FFS restarted in 2021/22 as covid restrictions eased.

Recommendations for the coming year:
TWFA, along with all partners, need to work to address the key challenges highlighted in their regular reporting and monitoring. Many of these are linked to the increasing scale of operations for the SCs (as more farmers are registered) and include: roads, maintaining high-quality greenleaf, and finding sufficient labour.

Output Title	Efficient, inclusive and sustainable management of service companies
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Farmers' representatives trained in managerial capabilities that are successfully participating in managerial activities (Cumulative)	N/A	N/A
3.2 Number of Farmers' representatives elected to represent smallholders (at least 50% women) (Cumulative)	90	100 / (31% women) / (111%)
3.3 Number of farmers' representatives trained in corporate governance (Cumulative)	N/A	N/A
3.4 Number of services provided by the Services Companies to their clients (Cumulative)	9	9 / (100%)
3.5 Percentage of tea farmers satisfied with the services provided by the Services Companies	70%	94% / (134%)

Briefly describe the output’s activities and provide supporting narrative for the score.

There are five indicators under this output. Two have exceeded targets, one has hit the target, and two were not applicable for the reporting year. This output scores an A+. Output 3 seeks to enhance the management of the tea service companies so that they are professional, efficient, inclusive, and sustainable. It captures work to ensure that farmers are fully represented and have the skills to govern the companies. This is in line with TWFA’s long-term aim of handing full control of the services companies over to famers in years to come. This is precisely what TWFA has recently achieved in another of its tea production sites at Mulindi.

There has been no further progress on outputs 3.1 & 3.3 since training for new farmers representatives is scheduled for 2022/23. Terms of Reference (TORs) to train representatives, the training programme, materials, budget and logistics have all been finalised.

In addition to the 25 farmer representatives (8 women) already in SCON-N, farmer elections took place in ROS in 2021/22. A total of 75 farmer leaders were democratically chosen to represent farmers at the sub zone, zone and mega zone levels. The indicator includes a specific target for “at least 50%” of representatives to be women. This is not being achieved, only 8/25 representatives at SCON-N and 23/75 representatives at ROS are women. Whilst employment creation is successfully achieving gender equity (see Section B), it is clear that representation is falling short.

SCON-N and ROS provide a range of services to their farmer clients (output 3.4). This hasn’t changed in the past year. As tea began to be harvested, electronic weighing was rolled out in 2020/21. This brought the number of distinct services to nine.[18]
[18] The others are transportation of seedlings; provision of quality seedlings; provision of fertilizer; mentoring on tea husbandry; patient capital for investment into tea farming; financial inclusion; FFS; digitized payment for greenleaf tea.

Output 3.5 was measured in the satisfaction surveys carried out in February 2022.[19] SCON-N overall satisfaction level was 95%, and for ROS 93%. In particular, farmers were happy with services such as transportation (SCON-N), fertilizer supply, and quality of seedlings, and least satisfied with FFS training and size of the loans. A key finding for ROS is that dissatisfaction is caused by the poor quality of roads and the need for farmers to carry greenleaf long distances.
[19] Sample size is 171 for SCON-N and 125 for ROS. Percentage refers to those answering “satisfied” or “very satisfied”.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

VfM is not defined by output in either the original business case or previous annual reviews. Further information on VfM is included in Section E.

This output looks to build capacity in managing the service companies, with the long-term aim of handing them over to farmer management. In itself this is a good demonstration of VfM: seeking to remove the need for external funding and allow the companies to operate efficiently. This has been successfully demonstrated with the handover of the Mulindi plantation in the past year.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to indicators. There were changes to 2021/22 targets during the logframe revision in November 2021, specifically:
- Output 3.1 was kept as N/A for 2021/22 but revised to 80 for 2022/23.
- Output 3.2 was revised up from 8 to 90 to better reflect the number of farmer representatives planned in the SCs.
- Output 3.5 was revised down from 80% to 70%, with the agreement that the revised methodology should only include count of farmers that are “very satisfied” and “satisfied” (and exclude “somewhat satisfied”).
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations under this output from last year’s Annual Review are shown in the table below.

Recommendation	Progress
Increase the level of representation by female farmers.	The level has remained the same during the most recent farmer elections. See further recommendations below.
Although the level of farmer satisfaction is high, TWFA and the service companies can analysis the survey information to consider whether/how to address the areas where satisfaction is particularly low	Survey findings were presented to SCON-N and ROS boards. In particular the findings on the areas where farmers were most/least satisfied with the SC services were considered in decisions by Board and management.
As part of the logframe review TWFA and FCDO should revisit what counts as “satisfied” for output indicator 2.5 and discuss whether only two (instead of three) of the five possible answers to the survey questions should count as “satisfied”.	Done – see previous section describing logframe changes.

FCDO attends quarterly board meetings of SCON-N and ROS as an observer. It is clear from those meetings, and from our interactions with farmer directors on field visits, the great value added to discussions and decisions by the farmer directors. The representation of beneficiaries in the management of the service companies is a strength of the programme’s approach.

Recommendations for the coming year:
Important for FCDO (and partners) to work with TWFA and SCs to understand the reasons behind the low level of farmer representatives who are women, and to consider how to put in place specific actions to address this in the coming year(s).

D: RISK

Overview of risk management

The programme maintains a risk register, tracking main risks along with the mitigation measures. The main risks relate to context, delivery, fiduciary and operational. The Covid-19 pandemic continued to affect programme activities especially tea plucking in quarter one and part of quarter two, due to government guidelines and restrictions that inhibited planned activities mainly farmers training, sensitization and greenleaf plucking.

However, there was relaxation of most Covid-19 restrictions by the end of quarter two which made FFS training possible and tea plucking much more efficient.

Overall risk rating: Major
Throughout the year, the programme made significant improvements across various risks notably those related to strategy and context, reputational/safeguarding and fiduciary risks which remain major. The overall risk rating for the programme remains major, with a number of mitigation measures in place to mitigate against major risks. During this reporting period, TWFA and FCDO conducted a thorough review of the risk matrix. There was discussion over whether the overall risk rating should remain as major – the initial logic for this was that this was a novel and untested model. Whilst TWFA and FCDO agreed that the model was now operating successfully and this justification was no longer the case, the existence of other types of risks (covid, financial, delivery) meant that maintaining the rating as major was prudent. TWFA and FCDO will conduct another further thorough review of risks in the coming year.

The main risk status per category is explained below:

Financial and Fiduciary:
TWFA has minimised fiduciary risk through the annual audit and quarterly financial reports that are shared with FCDO. Management accounts were generated by the service companies on a monthly basis throughout the year and reviewed by TWFA to ensure that expenditures are in accordance with the agreed budget. There is also thorough presentation and scrutiny of the SCs finances at quarterly board meetings. External audit was also conducted and presented to the boards in November for both service companies (SCON-N and ROS) as per schedule. Standard procurement guidelines are also detailed in the financial processes and procedures.

Context:
The main contextual risk related to the covid-19 pandemic with related lockdown especially in quarter one and part of quarter two. However, most of the COVID-19 related restrictions were eased at the end of Q2, which allowed FFS and tea pluckers to carry out their work smoothly. Climatic conditions mainly the changes in rainfall patterns affect tea planting; landslides in ROS along with soil erosion causing roads’ blockage, while in the dry season some seedlings dry up. To mitigate the risk SILTPR established partnerships with government to assist in reopening of roads while drought resistant seedlings and early planting are being devised for drier areas.

The road network in the catchment area remains a challenge, especially during the rainy season when roads increasingly become slippery. Vehicles can get stuck, developing mechanical problems thus increasing maintenance costs as well as causing damage to seedlings and greenleaf during transportation. TWFA through SCs continued to lobby the central and local government and leaders to rehabilitate roads, for instance in SCON-N, 23 kms of roads were rehabilitated by government while in ROS, a roads committee was set up that helped in emergency road repairs costing RWF 4.25 million ($ 4,250) and were seeking a cost share between RTC and the company. The Local Government on its part will mobilize the community to provide adequate labor. During the year, internal emergency road repair was completed with all three partners participating. Road rehabilitation by GoR was going on, all three roads had substantial grading work done but none had murram by the end of FY.

Safeguards:
The programme continued to report general improvements in safeguards following the Health and Safety (H&S) audits. SCON-N reported improvements in safeguards following the Health & Safety (H&S) consultant visit and training during the year. A Standard Operational Procedure (SOP) was in place for soil excavation works and all contractors were being supervised closely. An action plan was put in place to address all identified high risks and prevent future accidents. A consultant engineer has also been identified to address the issue of lightning risks while awareness through sensitizing staff and farmers will be initiated.

In past years the two service companies have introduced a comprehensive safeguarding framework following a comprehensive assessment of safeguarding risks. This included policies such as a Code of Business Conduct; Whistleblowing Policy; Sexual Harassment, Exploitation and Abuse Policy, Revised HR Manual – includes grievance handling & equal opportunity; and Code of Ethics. Staff awareness sessions were held to sensitize staff on the policies.

Relatedly, in ROS, a Rainforest Alliance external audit was conducted by Africert, in January 2022. Training of ROS management staff and farmers and conducting internal audits was completed. The training focused on the new standard's six standard pillars: management system, traceability system, Income, and shared responsibility, farming system, social and environmental systems. ROS was certified on behalf of ROS farmers in the new Rainforest Standards.

There is also a reported steady improvement in farmers’ income as a result of tea growing. According to the latest data from farmer payment schedules from greenleaf collected, farmers’ average net income per in 2021/22 was $611/ha which was a 114% increase from 2020/21 income of $327.5/ha. Thus, mitigating the risk of farmers’ loss of livelihoods due to the planting of tea.

Delivery:
In this reporting period, COVID-19 pandemic affected mostly the first and second quarters of the year, with Government of Rwanda (GoR) imposing stricter restrictions on movement and gatherings due to high spikes especially in June 2021, that had new virus mutations. The GoR was able to mobilise vaccines that were administered across the country with priority given to essential workers and the aged. As more vaccines were made available, more age groups were vaccinated (18 years and above) were included, and Rwanda had one of the highest COVID-19 vaccine rates in the region and beyond. The pandemic further delayed farmers training, farmers surveys and field data collection by the impact evaluation team. SCON-N and ROS continued to adhere to GoR's directives and protocols. To ensure that the programme is not adversely disrupted by COVID-19, TWFA team had to devise means of field activities continuing, mainly trained farmer in their farms in smaller groups. The farmer surveys were also eventually conducted in May 2021 while the impact evaluation team field visit was completed in Feb 2022 and a draft report has been submitted to FCDO.

The delays by Unilever in meeting the timelines for Kibeho factory construction preparations remains a concern especially in SCON. Currently, most of the preparatory work including geotechnical investigations and environmental social impact assessments (ESIAs) have been done and reports submitted to relevant authorities for review. The selection of the civil contractor was also completed. The factory commissioning is planned in the next FY (2023/24). TWFA maintains close relationship with Unilever and Luxmi, to ensure that both companies remain committed to investments promised, which helps farmers committed to tea farming as their source of livelihood.

Operational:
TWFA continued to provide timely quality reporting and communication over the course of the year. They provide detailed and clear quarterly reports with communication on challenges, logframe target achievements, financial and reports of lessons learnt, and adaptations provide a clear narrative on what the programme is doing. FCDO remains an observer at the boards of both service companies (which meet, remotely, quarterly), which provides an excellent opportunity to stay in very close contact with the progress and challenges on the ground, including hearing from the farmer representatives (who are directors of the service companies) on each board. FCDO will keep engaging with TWFA to keep the momentum of better reporting especially on improved livelihood of farmers in the target areas.

Farmers in both SCs were trained on occupational health and safety and Rainforest Alliance principles and criteria. However, there are still challenges in relation to road safety and landslides during rainy season in the catchment area. This mainly affects the transportation of seedlings to the collection centre and farms leading to delays in planting and damages to the leaf and seedlings.

TWFA also commissioned an external impact evaluation of SILTPR, conducted by TripleLine. It is envisioned that the evaluation will support the knowledge management and learning function through a detailed assessment of the existing monitoring and results measurement (MRM) and learning systems, recommendations to be developed for TWFA on how to improve the existing framework as well as support in collecting and processing lessons learned and encouraging cross-learning from SCON-N to ROS and vice-versa. The first evaluation report was delivered in quarter 2 of FY2022/23, albeit 3 months behind schedule.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

There has been an improved quality of the quarterly progress reports, comprehensively covering progress and challenges across key results areas as well as clear and more comprehensive financial reports with supporting narrative. Over the last year, noticeable progress has been made on several areas including regular reporting on lessons learnt and subsequent programme adaptations and updates of risk matrix within FCDO standards. The major economic surveys (baseline survey for new farmers, socio economic survey of old farmers, vulnerability, socio-economic survey of workers and satisfaction survey) were conducted in May 2021 and February 2022, for both SCON-N and ROS.

Regarding the financial forecasts, there is a need for improvement on monthly forecasts. It has been a challenge getting full year forecast from TWFA, instead preferring to send quarterly spend, with projections for the next quarter. On the side of FCDO, this affects effective decision making especially given the changing context in priorities. The costs in both ROS and SCON-N were driven by advisory services costs, logistics and input procurements, especially fertilizers which were affected by the war in Ukraine, with sanctions put on Russian fertilizers.

TWFA has remained extremely flexible in budgeting during the year. This has helped FCDO to address underspends elsewhere by flexing the annual budget and moving TWFA’s own philanthropic funding across financial years. This is a strong advantage of the partnership model between TWFA and FCDO and will be important in future years as we extend the lifetime of the programme (without changing the overall budget envelope).

Generally, there is evidence that the programme continues to deliver Value for Money from an economy and efficiency perspective, while FCDO investment is contributing to increase in farmers’ incomes thus contributing to better livelihoods. Regarding effectiveness and equity aspects of the programme, more females and males continue to gain employment with income being generated to meet other household needs like health insurance, education for children and nutritious food in homes.

Economy
Key cost drivers of the programme include input costs, costs of land preparations and planting, as well as cost of nursery development and maintenance. Throughout the year, the service companies and TWFA continued to perform well on cost control as resources were economically managed, and inputs procured competitively ensuring the right quality at the right price as per procurement systems and practices established at both SCON-N and ROS. To secure economies of scale, fertilizers were procured in bulk. SCs will continue to procure fertilizer in bulk through consolidating their order together with the Shagasha and Mulindi factories.

Service companies also continued to hire local resources like agronomists and capitas to secure the best quality of extension services to farmers within a reasonable price. As a result of these measures, the overhead cost against total cost ratio remained stable by the end of the year.

Efficiency
Efficiency has been maintained across various components of the programme during this year:
- The cost per tea seedling for instance, is being maintained or less than £0.04 as per the original business plan target, with all targeted seedlings having been distributed to farmers for planting. For instance, in this reporting period, cost per seedling reduced from $0.051 to $0.035 (£0.04 to £0.029) due to huge amounts of seedlings planted in 2021/2022.
- The cost per beneficiary farmer accessing extension services reduced by 10% from £625 in 2020/21 to £560 in 2021/22 due to the large numbers of new 2021 farmers recruited while extension services costs remained stable as per initial budget.

Effectiveness
The programme is on track to achieve its intended outcome and impacts, with many of the milestone targets exceeded. Some examples include:
- FCDO’s investment is already contributing to significant permanent/sustainable increase in smallholder net incomes. At maturity, the project is expected to help raise farmer incomes threefold. By the end of the year, close to 33,475 cumulative direct jobs (7,142 permanent and 26,333 casual jobs) had been generated in the Rugabano and Nyaruguru greenfield projects. When the project is fully developed, it will create employment for 50,000 people directly and indirectly. The expansion of the programme to Nyaruguru South because of the positive impact of SILTPR is expected to create close to 19,000 additional jobs (12,138 seasonal and 6,362 permanent jobs).
- Moreover, FCDO’ s investment of $15.1m (£11.68m) at Nyaruguru and Rugabano has helped leverage $105m of FDI from Unilever and Luxmi, philanthropic capital (Gatsby and TWFA). Additionally, TWFA, Unilever and GOR have committed to invest a further US$30m in a new greenfield tea project in Nyaruguru South, raising the total public, private and philanthropic capital leveraged to $135m and confirming the replicability and scalability of the model. This also means that every $1 of FCDO funding has helped leverage about $9 from other funding sources, which is very good financial leverage.

Equity
The initial criteria for joining the programme (committing to allocating between 0.3ha and 1ha of land to tea)[20] were set in a way to ensure that most poor SHFs who can convert part of their land to tea, and remain with additional land for other crops, are reached. However, the recent relaxation of selection criteria to include farmers owning more than 1ha for consolidation and cluster formation purposes pose important equity risks that need to be fully understood. However, to manage that risk, SCON-N developed an internal greenfield farmer prioritization schedule that clearly highlights that SCON-N priority selection criteria remains 0.3 to 1 ha that is smallholder farmers, however, larger farmers who own land within the SCON-N clusters will be also considered in a second round only if annual planting targets are not met and these farmers have capacity to maintain their land. Both men and women continue to benefit from the employment and income opportunities arising from tea related activities, with at least 65% of seasonal employment being female as shown in the table below:
[20] Those farmers who choose to farm more than 1ha of land pay interest on their loans. Farmers with <1ha have interest-free loans.

April 2021- March 2022[21]
[21] 2021/22 log frame results

Quarter (Q)	Seasonal jobs created	Percentage (%) female	Percentage (%) male
Q1	7,333	64%	36%
Q2	8,749	62%	38%
Q3	11,672	81%	19%
Q4	11,630	56%	44%

Date of last narrative financial report	July 2022	Date of last audited annual statement	June 2021[22]
[22] The accounts report to 31 March 2022 has not been availed yet, but quarterly financial reports availed by TWFA show robust financial management system in place.

Annex A – SILTPR Theory of Change

Annex B – Summary of key findings from draft first evaluation report

What works and why?
Key success factors	Getting sufficient numbers of farmers to register, representing a sufficient number of hectares. / Delivering services to farmers. / Farmers produce high quantities of high-quality tea. / Farmer commitment to the scheme. / Anchor investors are delivering on their promises. / Government creates/maintains a beneficial enabling environment.
Additionality
initial evidence shows that there is a high degree of additionality for farmers, investors and workers.
In the absence of SILTPR would…	…farmers have planted more tea?	Unlikely
	…farmers have got access to SCON-N/ROS-type services?	No
	…farmers have seen a similar increase in incomes?	No
	…farmers have accrued similar benefits?	Unlikely
	…a similar number of jobs been created?	No
	…the communities in Nyaruguru and Rugabano benefitted to the same extent?	Possibly, but the positive effect of SILTPR is clear
	…Unilever/Luxmi have gained access to similar quantities of high-quality tea?	Not in those regions
How equitable is the programme?
Overall, SILTPR can be considered to be equitable and inclusive in terms of registration, providing services, enabling farmers to stick with the scheme, and enabling farmers to derive benefit from it, but the inclusiveness implications of land preparation loan size are worth considering going forward.
Replicability
Key success factors	A suitable crop. / Registering sufficient numbers of farmers. / Delivering services to farmers. / Farmers produce high quantities of high-quality tea. / Farmer commitment to the programme. / Anchor investors are delivering on their promises. / Government creates/maintains a beneficial enabling environment.