## Annual Review

Title: Digital Access Programme
Programme value £ (full life): up to £82.5m		Review date: 25/07/2024
Programme code: 204963	AMP Start date: 16/07/2019	AMP End date: / 31/03/2030

Summary of programme performance
Year	FY 2018/19	FY 2019/20	FY 2020/21	FY 2021/22	FY 2022/23	FY / 2023/24	FY / 2024/25
Overall output score	A	A	A+	A+	A+	A+
Risk rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

Link to business case:	Digital Access Programme (DAP) Business Case
Link to results framework:	DAP Logical Framework

This Annual Review of the FCDO-DSIT Digital Access Programme (DAP) covers the period July 2023 until June 2024. This was the fifth year of programme implementation, following the June 2019 ministerial approval of Phase 2 (Implementation, FY2019/20-FY2022/23), which built on Phase 1 (Diagnostics and Stakeholder Engagement, FY2018/19). Following the recommendation in the DAP 2023 Annual Review (AR), and the publication of the FCDO Digital Development Strategy 2024-2030, the timeline of the Implementation Phase has been extended to March 2030. The no-cost time extension was formally approved in AMP in March 2024.

The publication of the DDS with top deliverables on last-mile connectivity and digital inclusion also requires continued implementation of this flagship initiative. Another key reason for the above extension, besides the consistently good performance of the programme and the high level of demand for DAP support in all five partner countries, was to allow the intervention adequate time to achieve its overall goals beyond the outputs and outcome levels, given the multiple events that have required the programme to adjust its plans and approaches - while still aiming for the same objectives approved in the approved business case. This process of continuous adaptation was possible thanks to the agile and flexible in-house delivery model of the DAP.

For example, at the beginning of FY2020/21, the Programme rapidly pivoted towards COVID-19 adaptation, response and mitigation – mainly through virtual delivery models, while staying closely aligned to the programme’s Theory of Change. Digital inclusion, the overall goal of the intervention, acted as a key enabler of pandemic response and longer-term resilience. Other key events driving programme adaptation were linked to HMG’s decisions on ODA allocations. The mid-2020 FCDO ODA prioritisation exercise saw the DAP budget being reduced by approximately 25% across the DAP’s three pillars in FY2020/21 and the subsequent one-year Spending Review outcomes brought a 54% reduction of the FY2021/22 budget.[1]
[1] Part of this budget reduction was offset by lower costs brought about by the adoption of virtual delivery modalities imposed by the pandemic.

Additionally, in FY2023/24 there was a pause in ODA spend mandated for the June-October 2022 period, and the end of Q3 brought a sudden cut of the programme budget of about 24%. Strategic planning for the following year (FY2023/24) was also heavily affected by the deep overall reductions in the FCDO ODA budget, which caused DAP resources to be reduced by over 46%. This volatility caused delivery, operational and reputational risks to emerge (as for many other FCDO interventions). The DAP central teams and overseas network worked seamlessly together to proactively manage such risks and managed to fill some of the most critical resource gaps by mobilising funding from key sources such as the CSSF (in relation to Pillar 2’s work on cybersecurity capacity building) and leveraging in-kind contributions of global partners and of local governments in partner countries[2].
[2] (practical examples of this proactive, dynamic approach are provided in the Outputs’ narrative).
As demonstrated in this Report (and in the previous two Annual Reviews), the Programme managed to maintain the viability and effectiveness of the three pillars in all five partner countries, and the integrated nature of the intervention, despite the significant and continued resource constraints outlined above. This enabled the DAP to stay on track with regard to its expected outcomes, at times also overachieving them thanks to innovative, catalytic approaches that have generated economies of scale and particularly good Value for Money.

The DAP 2024 Annual Review was led, as in previous years, by the DAP x-HMG (cross-government) programme team. The review benefited from in-house advisory expertise from central teams in FCDO (Foreign, Commonwealth & Development Office) and DSIT (Department for Science, Innovation & Technology), and from the five DAP country teams based in HMG missions. The whole process was conducted in close consultation with global and local implementing partners and key stakeholders, and incorporated independent inputs from accredited advisers from other relevant teams in the HMG ecosystem. The review also captured key insights and lessons from the FY2023/24 DAP Cross-Country Peer Learning Event; and further built on the DAP First-Cycle External Evaluation and its follow-ups[3].
[3] The evaluation team consulted with a wide range of internal and external stakeholders and reviewed an extensive set of programme documents and monitoring data, working closely with the central and programme teams and conducting a deep dive in South Africa.

This review is based on evidence from over sixty-five live or recently completed projects across the three pillars in five programme countries - including progress reports, completion reports and monitoring data, triangulated through the DAP country teams and multiple implementing partners. During the review period, the DAP x-HMG programme team also conducted a mid-year results stock-take (the June 2024 ‘results harvest’) to pull together quantitative and qualitative data for the most representative indicators and inform the scoring of the programme outputs and outcomes.

This Annual Review receives a score of A+ as all three programme outputs have been scored as having moderately to substantially exceeded expectations across all their indicators, despite a very challenging environment; and programme risk is rated at Moderate based on the latest update of the programme top risks, relevant trends and mitigation measures. The programme also continued to demonstrate good Value for Money (VfM), representing a significant improvement on the parameters set in the business case.[4]
[4] It should be noted that VfM could be even better if ODA allocations were confirmed more timely, and were not reduced at relatively short notice.

A. SUMMARY AND OVERVIEW

Description of programme

Digital technology is a powerful catalyst for inclusive economic growth and sustainable local development. However, developing countries and emerging markets have often struggled to take advantage of the benefits of the digital economy, because of limited or unaffordable connectivity, lack of digital skills and relevant content and services, limited trust and resilience in the system, as well as limited capacity to foster digital innovations and tech entrepreneurship for development and social impact.

The Digital Access Programme - a partnership between FCDO and DSIT with a total budget of up to £82.5m[5] - catalyses inclusive, affordable, safe and secure digital access for excluded or underserved populations in Kenya, Nigeria, South Africa, Brazil and Indonesia; and uses increased digital inclusion as a basis for more thriving digital ecosystems that stimulate innovations for local development challenges and create local skilled jobs.
[5] To note: the ODA prioritisation process in FY2020/21 saw the DAP budget for that year reduced by 25% and the SR/business planning process for FY2021/22 has caused a reduction of 54% in the yearly budget.

The above objectives represent the DAP’s ‘primary purpose’. Additionally, the DAP aims to deliver ‘secondary benefits’[6] by stimulating opportunities for business partnerships between local digital economies and the UK, and by supporting HMG digital development, technology, and cyber policy objectives. The Programme was announced by the Prime Minister at the UK-Africa Investment Forum on 20th January 2020.
[6] Based on the former Prosperity Fund’s approach, secondary benefits were expected to naturally flow from the achievement of the primary purpose, through medium to long-term pathways of improved business environment and inclusive economic growth. Shorter-term and more targeted, transactional secondary benefits (such as facilitation of UK exports like cyber expertise, or investment opportunities for UK tech firms) are exclusively supported by non-ODA spend (assessed through a separate Annual Review process). Following the closure of the Prosperity Fund, all legacy PF programmes have been working since early FY2021/22 to refresh their secondary benefit strategies and seeking further non-ODA funding from available FCDO sources, where relevant.

The Diagnostic Phase of the programme (FY 2018/19), involving in-depth country-level research and stakeholder engagement, utilised cross-government expertise and identified the key challenges and opportunities faced by our partner countries with regards to meaningful digital access and inclusive growth of their local digital economies. Introductory pilots were conducted to test and learn from relevant approaches and partnerships.

The Implementation Phase of the programme started in Q2 FY2019/20, was designed to continue until end FY2022/23, has been extended to March 2025 and subsequently to March 2030, and is articulated into three interconnected pillars:

FCDO-led[7] Pillar 1 ‘Models & Enablers’ (up to £60m) – Test and validate innovative, inclusive and scalable technology and business models in order to facilitate the sustainable expansion of affordable connectivity, digital literacy, skills, locally-relevant digital content and services for excluded or underserved communities - with an emphasis on gender, disability and broader inclusion. This is complemented by key enablers such as digital inclusion policy and regulatory reforms and capacity building of key institutions in partner countries.
[7] Led by the Digital Development Cluster in the Development Policy Department (FCDO).

FCDO-led[8] Pillar 2 ‘Trust & Resilience’ (up to £15m) - Build partner countries’ capacity to prevent and respond to cybersecurity harms affecting governments, businesses and citizens (including by strengthening basic cyber-hygiene skills of vulnerable groups at risk of online abuse or exploitation), thereby contributing to achieving international and UK cyber policy objectives.
[8] Led by the Cyber Policy Department (FCDO).

DSIT-led Pillar 3 ‘Sustainable Digital Ecosystems’ (up to £7.5m) - Stimulate local digital economies and support local tech entrepreneurs to find innovative solutions to local development challenges (‘tech for good’ / ‘tech for social impact’), create local skilled jobs, and forge partnerships between local start-ups and international businesses (including UK firms) through a Tech Hub network to drive inclusive and sustainable economic growth.

In support of the three programme pillars, a workstream on ‘Learning & Insights’ led by FCDO-led Pillar 1 (as lead component of the programme), ensures useful experience and lessons from across the programme components and countries are captured and shared with relevant stakeholders to amplify the impact of the programme. This also helps in reinforcing coherence of implementation and a consistent read-across of the three pillars (for example on business environment reforms and on digital skills development).

A small component of non-ODA activities funded by FCDO-led Pillar 2 and DSIT-led Pillar 3https://ukc-word-edit.officeapps.live.com/we/wordeditorframe.aspx?ui=en-GB&rs=en-US&wopisrc=https://fcogovuk.sharepoint.com/teams/DPCCDigitalAccessProgramme/_vti_bin/wopi.ashx/files/6e18a379fcc34a448de80f3a1efa4c9e&wdenableroaming=1&mscc=1&hid=F6E10E04-E655-47F9-87FC-2F25E8C980BF&wdorigin=Outlook-Body.Sharing.ServerTransfer.WSL&wdhostclicktime=1689442465195&jsapi=1&jsapiver=v1&newsession=1&corrid=18ed0ef9-5b6b-4498-a100-23d40fee4e85&usid=18ed0ef9-5b6b-4498-a100-23d40fee4e85&sftc=1&cac=1&mtf=1&sfp=1&instantedit=1&wopicomplete=1&wdredirectionreason=Unified_SingleFlush&rct=Normal&ctp=LeastProtected[9] identified opportunities and areas of competitive advantage for international and UK business in the digital sector of the emerging markets covered by the programme. The implementation of this component was completed in FY2022/23, however the overall DAP continues to offer a useful platform for mutually-beneficial digital and tech partnerships between programme countries and the UK.[10]
[9] (Until FY2020/21 - in terms of central non-ODA allocation from DSIT for this programme component).
[10] This component was assessed through a separate AR process for non-ODA projects.

Summary supporting narrative for the overall score in this review

This Annual Review assigned an overall score of A+ to the Digital Access Programme for its performance during the period July 2023 - June 2024, as all three outputs moderately to significantly exceeded expectations[11]. The overall programme also demonstrated excellent Value for Money in achieving its results[12], as well as significant resilience and adaptiveness in response to the post-pandemic context and to ongoing institutional constraints (e.g. ODA budget reductions, FCDO internal reorganisation, DCMS/DSIT transformation process).
[11] See details in Section C of this report.
[12] See detailed VfM analysis and indicators in Section E of this report. The Annual Review team chose to present a detailed VfM analysis in the final section of the report as there are several overlaps between pillars and also a joint approach to VfM across the Programme. This avoided repeating the same information across the different Outputs in Section C.

Despite having to significantly flex, the programme remained consistent with the overall Theory of Change and continued to operate in all five countries across its three pillars, delivering successfully on all strategic workstreams, which was supported through the Country-Level Implementation Planning (CLIP) process. All DAP country teams worked on joint strategic priorities aligned to both DAP objectives and business planning at post. The planning process in this review period required collective thinking on stakeholder engagement and cross-programme Country-level Implementation Plans (CLIPs). The DAP central and country teams collaboratively updated the plans, which enabled FCDO and DSIT teams to further improve their coordination across the programme, spot additional opportunities for joint work, optimise shared stakeholder engagement, avoid duplication of efforts, and track progress more effectively.

Below is a summary of the key achievements under each programme output assessed by this Annual Review[13].
[13] Full detail of evidence supporting output scoring is included in Section C of this report.

With regards to Output 1, the FCDO-led Pillar 1 (‘Models and Enablers’) has focused on engaging with key stakeholders and implementing partners directly and through the DAP country teams to identify, develop and roll out strategic projects to lay the foundations of key digital inclusion ‘enablers’; and test and develop the viability, scalability and sustainability of digital inclusion ‘models’ across the five programme countries. By the end of the period under review, Pillar 1 had completed 26 projects through local and global partners achieving all planned outputs and seeing evidence of outcome-level changes. All these interventions are fully aligned to the programme-wide and pillar-specific Theories of Change (ToCs) and contribute directly to the expected outcomes on the three levels of intervention identified in the Diagnostic Phase reports and in the Implementation Phase plans:

1. Systemic level: policies, regulatory frameworks and institutional capacity building for digital inclusion enablers
2. Supply-side: inclusive and affordable last-mile[14] connectivity models
  [14] ‘Last-mile’ here refers to digitally underserved communities with no access to affordable connectivity. These are rural, peri-urban or urban low-income communities, typically beyond the market frontier of mainstream connectivity providers.
3. Demand/user-side: digital skills development and locally-relevant digital content/services models for underserved communities

With regard to Output 2, the FCDO-led Pillar 2 (Trust & Resilience) continued to oversee the work of the main contract with KPMG, which entered full implementation in June 2021.The design of this programme component in each partner country was based on the initial DAP cross-pillar digital access diagnostics, and subsequently on the pillar-specific assessments (Cybersecurity Capacity Maturity Model reviews) delivered during the inception phase. The latter took into account independent assessments of national cyber security capacity and demand from key stakeholders in each country.

During the period under review, Pillar 2 completed a further round of project-level funding allocations to increase the reach and impact of successful projects. All projects delivered outputs as planned, moderately exceeding expectations. The overall effect of the project portfolio under this component also provides evidence of further outcome-level change.

Another important achievement of this programme component was the integration of Pillar 2 intervention into the wider network of CSSF/ISF-funded cybersecurity capacity building regional portfolios in Africa, Indo-Pacific and Latin America. This approach has produced the added benefit of linking DAP work more closely with FCDO’s cybernetwork at post and draw on its deep expertise and successful stakeholder engagement.
With regard to Output 3, the DSIT-led Pillar 3 (‘Sustainable Digital Ecosystems’) of the DAP had all five Tech Hubs in Kenya, Nigeria, South Africa, Brazil and Indonesia operational and delivering capacity building projects. Through its in-house delivery model, Pillar 3 is interfacing directly with the local digital ecosystems and has delivered significant results in terms of support to local digital entrepreneurs, through a wide range of activities (including training on business development, mentoring, coaching, exposure to investors and facilitation of access to finance and markets).

Pillar 3 support to local digital ecosystems has generated digital innovations to address local development challenges, strengthened local tech start-ups, and facilitated the creation of local skilled jobs. The Hubs have continued to increase their outreach across the local tech ecosystems and have undertaken work on start-up legislation, influencing national policy dialogues, achieving all planned outputs and seeing evidence of outcome-level change.

During the period under review, the DAP also implemented 11 cross-pillar projects that successfully linked three key components of digital development work, e.g. digital skills with cyber-hygiene awareness and tech entrepreneurship; as well as building capacity of key institutions in partner governments dedicated to digital, cyber and tech for their national development agendas.

Key lessons and recommendations for the year ahead

During the period under review, the FCDO-DSIT DAP team worked closely together to implement the recommendations from the 2023 Annual Review. Notably, the programme further strengthened its approach to identifying opportunities for programme-wide synergies and to design cross-pillar projects. Throughout the period under review, the programme teams continued to demonstrate exceptional flexibility and agility in dealing with resource constraints and staff shortages and in navigating the disruption and complexities caused by the post-pandemic impacts and by institutional transformation. As recommended, the programme teams also fully embedded the x-HMG coordination and knowledge management mechanisms (Programme Management Committee, Senior Governance Committee, cross-country peer-learning process); and established more direct and systematic links between DAP and the broader Digital Development policy and programming work of FCDO and wider HMG.

Below is a summary of lessons learnt and recommendations for the next annual review period (July 2023 – June 2024), focusing on programme-wide issues. Pillar-specific recommendations are included under each of the Outputs in Section C.

Joint strategic planning for DAP ‘second phase’ in view of next SR process:

This 2024 Annual Review has helped consolidate DAP results so far and provide robust evidence of the programme’s effectiveness and outcomes. With the confirmation of the ODA allocations until March 2025 and the formally approved time extension of the programme to the end of the Spending Review period, the programme team should focus on the further development of its ‘DAP 2.0’ concept focused on:

  1. further supporting the successful models demonstrated by the DAP and attracting public and private investors to scale them and invest in them for the future, thereby enhancing sustainability of outcomes;
  2. amplifying the impact of the DAP by packaging its evidence in adaptable knowledge products for the benefit of the wider regions around the five partner countries;
  3. connecting the DAP more systematically with other relevant HMG interventions, including as a knowledge platform collaborating with the emerging Centres of Expertise (in particular the Tech CoE, a deliverable of the ITS) and by creating a conducive investment climate and business environment for BIP’s work on digital and tech infrastructure;
  4. more generally, as a flagship HMG programme on digital development, supporting the implementation of the IDS[15], the ITS[16], the Cyber Strategy, the new FCDO Digital Development Strategy 2024-2030, and other relevant HMG plans[17].
    [15] FCDO led International Development Strategy
    [16] FCDO-DSIT International Tech Strategy
    [17] For example, the FCDO Women & Girls Strategy and the upcoming FCDO Digital Development Strategy

Cross-programme learning, knowledge management and regional amplification:

Evidence shows that the expertise and delivery skills of the DAP central and local teams at post are in high demand and represent the core of successful programme implementation. The DAP should therefore continue building in-house expertise at the centre and in-country through on-the job learning, advisory input from specialist teams as needed, L&D opportunities, and the delivery of more frequent cross-country peer learning events. The team should build on the positive experience of the November 2023 cybersecurity Pillar 2 conference in London and the DAP in-person learning event, to plan for further exchange opportunities, complemented by country visits by DAP central teams, to accelerate the knowledge management component of the DAP 2.0 plan. The central and country teams also need to work together to confirm plans on the regional amplification of DAP outcomes, as discussed at the latest peer learning event.[18]
[18] A plan for Tier 1 and Tier 2 country prioritisation has been drafted in line with relevant HMG priorities and existing strategies.

Enhanced cross-pillar delivery and cross-FCDO/HMG collaboration:

Cross-pillar projects have been particularly successful so far, especially in the areas of digital skills development and of policy and regulatory reforms. The DAP should therefore continue to enhance cross-pillar and cross-country delivery and strengthen further its ability to manage knowledge and disseminate evidence and models, to amplify the impact of the programme. These features would also better position the DAP to contribute as a ‘knowledge platform’ to the development of the FCDO-led Centres of Expertise, where digital and tech need to be integrated as a key enabler. This would enable the DAP to use its rich evidence from country-specific and cross-country programming on digital development in support of a wider range of HMG interventions applying digital technologies to development challenges.
Joint communication and branding strategy:

The DAP took a more coordinated approach to communication and branding during the period under review, utilising an even more joined-up narrative, and seizing more proactively multiple opportunities for shared visibility of the programme and of its results. This has enhanced internal and external stakeholder engagement, and facilitated the dissemination of knowledge and evidence.[19] The DAP should continue to take advantage of the most strategic events and platforms to make its work even more visible and amplify its impact. So far, the most notable and effective fora for the DAP’s international visibility have been the ITU[20] summits, the Internet Governance Forum, and the USAID-sponsored Global Digital Development Forum.
[19] Publishing a DAP case study in the OECD 2022 Development Cooperation Report to represent the UK’s work on inclusive digital transformation demonstrated the value of this innovative and adaptive intervention. The DAP was also featured in the most recent joint report of the World Bank and Global Centre for Cybersecurity Expertise as a trailblazer on the successful integration of cybersecurity capacity building with broader digital development.
[20] International Telecommunications Union

Integrating environmental and climate change considerations:

During the period under review, the DAP incorporated environmental and climate change considerations in the design of all its Country-level Implementation Plans (CLIPs). During the next two years of implementation to the end of the SR period, the programme team should focus on the most strategic and catalytic interventions in key areas such as promoting low-cost low-energy connectivity models, ensuring safe disposal of e-waste, and supporting digital start-ups that work on climate-tech or green-tech innovations. Evidence from this type of activity will also support FCDO’s policy and programming work on ‘digital sustainability’. The latter is a key pillar of the new FCDO Digital Development Strategy (DDS), whose implementation will be supported by the DAP as a flagship HMG programme on this agenda.

Embedding sustainability in scale-ups of tested digital inclusion models:

During the review period, DAP scaled up projects with a predominant focus on systemic-level workstreams (USF[21], enabling regulation for last-mile connectivity, government digital transformation) and demand-side workstreams on digital literacy and skills. We had robust cross-pillar engagement with public and private sector stakeholders through forums like the Pillar 2-led Chatham House cybersecurity and digital development conference and Pillar 3-led tech-hub events both centrally and in partner countries. Nationally and internationally, we have had several examples of project scale-ups across the project portfolio, which include the institutionalisation of national digital skills and literacy frameworks in Kenya and South Africa and institutional adoption of digital telehealth applications in Indonesia. The institutionalisation of last-mile connectivity models involving community networks, small-scale internet service providers and wireless internet service providers has also been evolving as a key priority in Kenya this FY. The DAP should continue to intensify engagement with government and industry in partner countries to ensure sustainability of impact and buy-in for institutionalising digital inclusion models developed and tested through DAP projects.
[21] Universal Service Fund

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The diagram below summarises the DAP’s Theory of Change. No changes have been made to outcome and impact indicators as detailed in the original business case. The key cross-programme indicators are detailed in the DAP’s Logical Framework.

Describe whether the programme is on/off track to contribute to the expected outcomes and impact.

The DAP has now completed four years of implementation, with April 2020 – June 2022 largely focused on COVID-19 adaptation, response and mitigation, in parallel with scaling up of several interventions relevant to longer-term pandemic resilience; and the period under review (July 2023 – June 2024) representing a positive reset in a post-pandemic context, however against the background of significant resource constraints and institutional volatility across HMG. The latter generated significant delivery, operational and reputational risks, which the DAP teams have so far managed proactively and successfully. The insights from the DAP external evaluation and previous reviews, and the assessments of output-level and outcome-level results in this 2024 Annual Review indicate that the programme is still fully on track to contribute to expected impact as described in the business case.

For example, the systemic changes supported by strategic projects in five programme countries under Pillar 1 and Pillar 2 on policy and regulatory reforms as well as institutional capacity building for inclusive, safe and secure digital access, and the ecosystem-level support by the Pillar 3 Tech Hubs, indicate pathways that clearly connect discrete results with catalytic processes of change leading to increased digital inclusion, as well as broader economic and social development. The on-the-ground effects of testing of scalable, sustainable models and the emphasis on cross-country learning and amplifying results, also strengthen the evidence that the programme is on a valid path to impact. For example, the reduction in the digital divide in the partner countries and the increased resilience and capacity of their digital ecosystems is showing positive effects in terms of inclusive economic growth and of more sustainable diversification of the economy.[22]
[22] For example, in Nigeria, the contribution of the ICT sector and of the broader digital economy to the GDP is growing fast in comparison with the role of the extractive economy (oil), thereby reducing the dependency of the country on one resource – besides increasing productivity in a number of other sectors through digitalisation.

The rich institutional and technical knowledge gained by the DAP global team during the Diagnostic Phase and Implementation Phase, as well as the results and lessons from all the projects across three pillars are an important asset for the achievement of programme impact. The programme demonstrated significant resilience in the face of the pandemic crisis and post-pandemic impacts, and of multiple budget reductions. It has stayed on track and its interventions are still fully compatible with the overall ToC, while gradually aligning with the evolving context of relevant HMG strategies (FCDO International Development Strategy, FCDO-DSIT International Tech Strategy, HMG Cyber Strategy, FCDO Digital Development Strategy) and establishing itself as the flagship x-HMG programme partnership on digital development.

Overall, the Programme has made a real difference for partner governments and other key stakeholders in Kenya, Nigeria, South Africa, Brazil and Indonesia, and for their digitally-underserved communities. Improved policies, regulations, licensing frameworks and standards have created a more enabling environment for digital inclusion, cybersecurity capacity and digital entrepreneurship. DAP outcomes help partner countries to build a more thriving digital economy, contributing to national GDP and creating skilled jobs, through an inclusive, responsible and sustainable digital transformation journey – inspired, where relevant. by the UK experience and benefitting from UK expertise in this field.

Importantly, better policies and institutions have relied on the evidence of several digital development models tested and scaled by the DAP, e.g. on affordable connectivity, digital skills, locally-relevant digital content and services, cybersecurity skills and systems, and tech entrepreneurship. The support to the relevant technology and business/organisational models has simultaneously generated positive outcomes for the communities and beneficiaries directly involved in DAP projects.

At June 2024, the DAP has reached directly and improved the digital inclusion of over 13.8m people in five countries. While this is a significant number and goes well beyond the expectations of the original business case analysis, it is the catalytic nature of DAP interventions, the scalability of its models and the systemic change facilitated by the programme that will continue to deliver outcomes and impact over time, multiplying the outreach to a much wider audience. Below is an overview providing quantitative details on how the DAP has so far achieved (and significantly exceeded) its key expected outcomes across the three pillars and five partner countries, using as reference the programme’s Logical Framework:

DAP outcome indicators	June 2024 milestone	June 2024 result[23]
Percentage reduction in the digital gap (catalysed by digital inclusion enablers and models) in partner countries	20%	26%
Number of digital innovations for local development generated by local start-ups	1,000	1,838
Number of digital inclusion, cyber-security and 'tech for good' policy dialogues and strategic stakeholder consultations at country level and on global platforms	100	164
Number of digital inclusion, cyber-security and 'tech for good' knowledge products for cross-country dissemination	50	116
Number of digital inclusion, cyber-security and 'tech for good' country-specific and cross-country partnerships with public and/or private sector stakeholders	50	85
[23] For the review period, there were 925 digital innovations for local development generated by local startups, 111 digital inclusion, cyber security and tech for good policy dialogues, 95 digital inclusion, cyber-security and 'tech for good' knowledge products for cross-country dissemination, 68 digital inclusion, cyber-security and 'tech for good' country-specific and cross-country partnerships with public and/or private sector stakeholders.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the insights from the external DAP Evaluation and on the assessments of programme performance in the 2023 and 2024 Annual Reviews, the DAP should continue to pursue its inclusive digital access objectives, while leveraging its adaptive delivery model to respond to emerging priorities and challenges (e.g. as done during the pandemic and during the post-pandemic rebuilding period). Below is a short outline of the DAP’s value added as an individual programme and within the wider x-HMG digital development portfolio:

The DAP has demonstrated its strategic relevance:
- for HMG in programme countries, by providing a valuable platform for high-level engagements by Heads of Missions’ in policy dialogues with partner governments and influencing major reforms (as demonstrated by MoUs and Declarations of Intent);
- during high-level ministerial visits providing a positive show-case of UK expertise and support to the local digital economies, and a basis for further bilateral cooperation;
- for HMG strategies on digital and tech, by illustrating the UK approach to digital development, providing evidence and case studies for FCDO-DSIT ITS, FCDO IDS, UK Cyber Strategy, and the upcoming FCDO Digital Development Strategy (DDS)
- for HMG’s international positioning on digital inclusion in global fora, for example through the DAP partnership with the ITU. A key demonstration of DAP’s strategic value was its role in demonstrating the commitment of HMG to digital inclusion objectives, which positively supported the election of the UK to the ITU Council in October 2022https://ukc-word-edit.officeapps.live.com/we/wordeditorframe.aspx?ui=en-GB&rs=en-US&wopisrc=https://fcogovuk.sharepoint.com/teams/DPCCDigitalAccessProgramme/_vti_bin/wopi.ashx/files/6e18a379fcc34a448de80f3a1efa4c9e&wdenableroaming=1&mscc=1&hid=F6E10E04-E655-47F9-87FC-2F25E8C980BF&wdorigin=Outlook-Body.Sharing.ServerTransfer.WSL&wdhostclicktime=1689442465195&jsapi=1&jsapiver=v1&newsession=1&corrid=18ed0ef9-5b6b-4498-a100-23d40fee4e85&usid=18ed0ef9-5b6b-4498-a100-23d40fee4e85&sftc=1&cac=1&mtf=1&sfp=1&instantedit=1&wopicomplete=1&wdredirectionreason=Unified_SingleFlush&rct=Normal&ctp=LeastProtected[24].
  [24] International Telecommunication Union.

- The Programme has adopted a blended delivery model (in-house and outsourced) and adaptive methods to flexibly respond to a rapidly changing digital and tech sector in each country, and to test partnerships and approaches before scaling up - thereby maximizing chances of success, managing scale risks, and enhancing VfM. This has led to significant results in the focus areas of inclusive connectivity, digital skills, content and services for underserved communities; country-wide cybersecurity capacity, cyber-hygiene awareness, and online safety (especially for women and girls); digital entrepreneurship and ‘tech for social impact’ innovations.
- The DAP is the only x-HMG programme that is fully dedicated to digital development and aligns through its holistic approach with all FCDO policy priorities of digital inclusion, transformation, responsibility and sustainability[25]. It has been highlighted as a unique example of FCDO-DSIT co-design and co-delivery of digital interventions. It will also play a flagship role in showcasing FCDO’s achievements in digital development in the upcoming DDS.
  [25] Four key areas of FCDO’s current Digital Development policy framework. This will be captured in a new Digital Development Strategy.

- The DAP effectively brings together the relevant technical expertise and policy mandates of three different HMG departments/teams that work on complementary aspects of digital development, with a focus on x-HMG collaboration and cross-pillar work. It actively engages with other x-HMG programmes to develop synergies and share insights[26].
  [26] For example, the Better Health Programme in South Africa; the Global Trade Programme in Indonesia; the Africa Technology Innovation Partnership in Kenya, Nigeria, South Africa; and the Inclusive Education Programme in Brazil.
- The DAP has established and developed a competent x-HMG central and multi-country team that is delivering value directly to key in-country stakeholders through technical advice, policy dialogue and capacity building - for example[[27] through its specialist digital access country advisers and its unique Tech Hub network model. The expertise of these teams will be a valuable asset for the development of the new FCDO Centres of Expertise (in particular the Tech CoE as deliverable of the ITS) and for FCDO’s digital development capability offer; and will also contribute to shaping a conducive investment climate and enabling environment for BIP’s[28] investment agenda.
  [27] Both are based in HMG missions and fully integrated with wider digital and tech work at Post)
  [28] British Investment Partnerships

Additionally, given the latest discussions within FCDO and HMG on the role of AI in the development context, in terms of both potential benefits and emerging risks, the DAP will be instrumental in ensuring that adequate foundations are in place for partner countries to contributing to shaping relevant, context-specific AI developments.

## C. DETAILED OUTPUT SCORING
Output title:	Increased digital inclusion of excluded or underserved communities in partner countries, through the support of systemic enablers and scalable models for affordable last-mile connectivity, digital literacy and skills, and locally-relevant digital content and services.
Output number:	1	Output Score:	A+
Impact weighting (%):	50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Digital inclusion policies, regulations and strategies introduced or improved	40	102[29] digital inclusion policies, regulations and strategies introduced or improved across DAP partner countries, including for example: / 1 Improved USF Strategic Plan 2023/2024 – 2027/2028 (Kenya) / 1 Improved USF Project selection Manual (Kenya) / 1 CA/USF Department Capacity assessment report and development plan (Kenya) / 1 Policy Brief on Digital Services in Agriculture and accessible government services (Kenya) / 1 Improved National digital/ICT accessibility monitoring and evaluation framework/tools (Kenya) / 1 Refined digital accessibility standards implementation framework (public sector facing) (Kenya) / 1 National digital skilling curriculum and skills development framework launched (Kenya) / 5 MoUs on development and utilisation of community networks infrastructure including establishment of village owned enterprises (Indonesia) / 1 Community Networks committee created with Anatel (APC Brazil) / 1 forum on regulation of digital platforms aimed at promoting digital rights and to combat disinformation (APC Brazil) / 1 coalition of rights on the networks (APC Brazil) / 1 Community networks service provider license issued (APC Kenya) / 1 USF 2022-2026 draft strategy launched to support 100 community networks in next 5 years (APC Kenya) / 1 National Digital Economy Policy and Strategy for 2020-2030 (APC Nigeria) / 1 Digital Rights Bill (APC Nigeria) / 1 EU-Nigeria Digital economy package (2021-2024) to support digitalisation strategy / 1 National data policy (APC Nigeria) / 1 Next Generation Spectrum Policy (APC SA) / 1 Broadband fund launch (APC SA) / 1 Electronic Communications Act amendment (APC SA) / 4 state level digital economy plans and strategy frameworks (Nigeria) / 5 action plans for adoption of the national broadband plan (Nigeria) / 4 action plans for integrating/enhancing Govtech and Civictech (Nigeria) / 5 Digital jobs playbook advocacy action plan / 1 recommendation document to strengthen Kaduna state’s digital strategy (Nigeria) / 1 Framework for developing and integrating state-level Govtech solutions (Nigeria) / 5 state level digital economy needs assessment reports developed (Nigeria) / 1 Policy dialogue on promoting digital literacy through inclusive digital training (British Council, Nigeria) / 1 policy dialogue on digital literacy and skills with Ministry of Communications and Informatics / 1 contribution to Kenya’s e-trade strategy (BSI) / 1 International standards summit at G20 (Indonesia) / 1 Child online protection roadmap undertaken and launched (ITU Indonesia) / 1 collaborative regulation for digital transformation improved (ITU Kenya) / 1 committee set up to make recommendations on and generate policy actions for sustainable operating model for school connectivity (ITU Kenya) / 1 policy recommendation on last mile connectivity from Joint ITU-APC workshop (ITU Kenya) / 1 Strategic Co-operation agreement with WISP Association in Brazil (Abrint) signed (DSA Brazil) / 1 official DSA response to the Anatel request for commentary regarding the 6GHz Spectrum submitted (DSA Brazil) / 1 DSA response to the Indonesia NRA request for commentary regarding the 6GHz Spectrum / 1 lower 6GHz band opened up as license exempt in July 2022 (DSA Kenya) / 1 response to ICASA submitted on 6 Ghz spectrum (DSA SA) / 1 response to Ministry of Communications on spectrum policy (DSA SA) / 1 lower 6GHz band opened up as license exempt in May 2023 (DSA SA) / 2 ITU roundtables on school connectivity mapping held with key decision-makers in Brazilian government (November 2022 and June 2023) / 1 regulatory research paper on challenges and opportunities for sustainable and effective connectivity policies in Brazilian schools (Brazil) / 1 USF steering committee on school connectivity (Brazil)
Awareness raising of key institutional stakeholders on digital inclusion priorities and approaches	2,000	9,998 key institutional stakeholders engaged on digital inclusion priorities and approaches / 872 (Kenya) / 107 (Indonesia) / 804 (Brazil) / 89 (Nigeria) / 134 (SA) / 5,549(APC/cross-country) / 258 (British Council/cross-country) / 159 (BSI/cross-country) / 268 (ITU/cross-country) / 565 (DSA/cross-country)
Digital inclusion models supported and tested for scalability and sustainability	160	264 Digital inclusion models supported and tested for scalability and sustainability / 14 (Kenya) / 16 (Indonesia) / 5 (SA) / 2 (Brazil) / 4 (Nigeria) / 82 (APC/cross-country) / 2 (British Council/cross-country) / 4 (BSI/cross-country) / 3 (ITU/cross-country) / 6 (DSA/cross-country)
Aggregate beneficiaries directly reached by Pillar 1 projects on digital inclusion (connectivity, skills, content, services)	5,000,000	6,656,294 direct beneficiaries reached by Pillar 1 projects on digital inclusion / 1,132,124(Kenya) of which 498,000 (PWDs) / 28,122 (Indonesia) of which 18,378 females and 438 PWDs / 222,511 (Brazil) / 1,022,228 (Nigeria) / 1,509 (SA) / 19.803(APC/cross-country) / 9,356 (British council/cross-country; 5,533 females and 1,019 people with disabilities) / 159 (BSI/cross-country) / 200 (ITU/cross-country)
Aggregate communities directly involved in Pillar 1 projects on digital inclusion (connectivity, skills, content, services)	2,500	3,282 communities directly involved in Pillar 1 projects on digital inclusion (connectivity, skills, content, services) / 90 (Kenya) / 38 (Indonesia) / 133 (Nigeria) / 848 (Brazil) / 64 (SA) / 122 (APC/cross-country) / 55 (British Council/cross-country) / 47 (ITU/cross-country)
[29] 69 digital inclusion policies introduced and improved, 8,805 key institutional stakeholders engaged, 136 digital inclusion models supported for scalability, 2,436,012 beneficiaries reached, and 1,397 communities directly involved in Pillar 1 projects in FY 2022/23.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 1 receives a score of A+, as all indicators have overachieved their relevant milestones moderately or significantly.

Output 1 is delivered by the FCDO-led Pillar 1 (‘Models & Enablers’) of the DAP, which also acts as the lead component for the overall programme. In FY 2023/24 Pillar 1 continued to test and develop the viability, scalability, and sustainability of digital inclusion ‘models’ and ‘enablers’, engaging with key stakeholders, and with local and global partners - directly and through DAP country teams - across the five programme countries. Pillar 1 activities focused on scaling up successful projects delivered in FY2022/23 and developing new projects with key country-level stakeholders based on a demand-driven approach, evolving strategic priorities and broader DAP objectives.

During the period under review, Pillar 1 initiated or scaled up 26 country-specific projects across five countries through its ‘direct delivery' component (involving primarily a blend of inhouse HMG expertise and local implementing partners). We started a new global project on international standards for digital transformation with BSI and commenced the second phase of our ongoing projects with global partners started in early 2021 (ITU, DSA, DIAL and British Council) where cross-country learning, international expertise and global institutional mandates/convening capacity were specifically required. These complement the DAP global project with Association for Progressive Communications (APC) on community networks initiated in early 2020 and the BSI global project on the role of digital standards in inclusive digital transformation, which completed its pilot phase in the previous financial year.

All projects mentioned above are fully aligned to the programme-wide and pillar-specific ToCs and contribute directly to the expected outcomes on the three levels of intervention identified in the DAP Diagnostic Phase reports and in the Implementation Phase plans:

●Systemic level: policies, regulatory frameworks and institutional capacity building for digital inclusion enablers
● Supply-side: inclusive and affordable last-mile connectivity models
● Demand/user-side: models for the development of digital skills, locally relevant content and services for underserved communities

All projects are captured within the Pillar 1 and cross-pillar strategic workstreams of the relevant DAP Country-level Implementation Plans (CLIPs), which are regularly refreshed by the x-HMG DAP team and country teams to reflect evolving needs and the dynamic nature of the digital and tech sector. Below is an overview of the key activities implemented by Pillar 1 during the period covered by this Annual Review, by programme country.

In Kenya, we have continued work with trusted local partners across the range of system-level and market-level digital inclusion activities, while also increasing the complementary engagement with the DAP global partners. We provided Technical Assistance (TA) to the Communications Authority of Kenya (CA) through the DAP country team, local partners, ITU[30], DSA[31] and APC[32] in the following areas:
[30] International Telecommunication Union
[31] Dynamic Spectrum Alliance
[32] Association for Progressive Communications

1. Developing the USF[33] strategic plan 2023/24-2027/28 based on the 2021 Data Access Gap study, use and impact study of USF services in 2022 and the school broadband connectivity project assessment study.
  [33] Universal Service Fund
2. USF Financing efficiency toolkit and Capacity building on grant making and last mile connectivity mapping.
3. Support and implementation of Government Transformational Digital Agenda
4. Technical advice and capacity building for implementing the Government of Kenya’s Digital superhighway roadmap and assessment of operating framework for small-scale last-mile connectivity providers, wireless internet service providers and community networks.
5. Review of the licensing regime for small-scale and wireless internet service providers.
We also provided TA to CA and ICTA[34] and formed multi-stakeholder partnerships to address strategic initiatives for last mile connectivity and digital accessibility of government services, in alignment with the Government’s transformational digital agenda. The first partnership with APDK, British Council and ACWICT has been instrumental in launching the National Digital skills curriculum and skills development framework and the National digital accessibility evaluation framework. In partnership with ICTA, they have held policy dialogues on digital accessibility and capacity building needs across sectors like Agriculture, Health and Education, providing recommendations for conducting capacity building programs and digital skills needs assessments across strategic sectors.
[34] Communications Authority and ICT Authority of Kenya

Our last-mile connectivity partnership with DSA, APC, ITU and ICTA is currently working on priority areas like assessment of potential community network deployment models and supporting the rollout of public wi-fi hotspots by ICTA and connectivity infrastructure to operationalise the hotspots.

The Programme has received great appreciation from the Government of Kenya, resulting in the rollout of several strategic projects by the Communications Authority, led by multiple local partners, focusing on provision of Cellular Mobile Infrastructure and service, Agricultural content digitisation and Dissemination (KALRO)[35], enhancing accessibility of educational content for learners with disabilities (KIB)[36] and establishing the Education Cloud open resources portal (KICD)[37].
[35] Kenya Agricultural and Livestock research organisation
[36] Kenya Institute for the Blind
[37] Kenya Institute of Curriculum development

All the above activities improved the sustainability of Programme initiatives launched to improved accessibility of affordable and sustainable last-mile connectivity solutions and inclusive models for digital engagement of underserved communities across Kenya.

Through multi-stakeholder partnerships with our global partners, roundtables and dialogues held with ICTA, CA and other public and private stakeholders, we have bolstered the importance of licensing community network operators and finding more sustainable operational models for them, generating policy recommendations to support them and being instrumental in bringing together an association for better representation of community networks.

With BSI, we have been able to make seminal contributions to organisational awareness and capacity building on international standards, with some key contributions to Kenya’s eTrade strategy with a policy roundtable session and subsequent dialogues and needs assessments in the thematic area of international standards and digital transformation.

In Nigeria, the DAP continued to work with trusted local and global partners on digital inclusion initiatives in challenging political economic circumstances, while building on key pieces of technical assistance and policy advice provided over time to the telecoms regulator National Communications Commission (NCC) and the Federal Ministry of Communications and Digital Economy (FMCDE). During the period under review, the programme scaled up ongoing projects with Cybersafe foundation and Initiative for Digital inclusion on online digital skills training for improving employability, tackling online harms and cyber-hygiene awareness.

We have also been working with Tech4Dev on the next phase of their digital literacy and skills development initiatives. In FY 2023-24, their traditional digital literacy model was applied to improving capability of civil servants across five Nigerian states of Lagos, Edo, Kano, Kaduna and Jigawa.

Our systemic level work continued to be enhanced in collaboration with our partner NESG[38], who provided technical advice on state-specific policy and regulatory frameworks related to digital economy and digital jobs creation, e-government, digital skills, and Right-of-Way administration.
[38] Nigerian Economic Summit Group

The scope of multi-stakeholder dialogue and engagement were expanded further in this financial year despite delays and setbacks faced due to political economic circumstances. NESG, ITU, IDI[39], APC and Cybersafe foundation have all been extremely dynamic in bringing together a wide range of public and private sector stakeholders for joint policy roundtables and workshops. The ITU-APC workshop on regulatory support for digital inclusion with NITDA[40], CITAD[41] and West Africa Governance forum and the ITU-ILO[42] workshop on boosting jobs and enhancing skills for youth in Nigeria’s digital economy have both produced key recommendations on required reforms. Cybersafe foundation’s online harms workshop is bringing together partners like Meta and Inhope as well as representatives from government and Interpol to discuss issues like online gender-based violence.
[39] Infrastructure Delivery International
[40] National Information technology agency
[41] Center for Information, technology and development
[42] International Labor organisation

With regard to digital literacy and skills, British Council made some significant strides with stakeholder engagement and policy dialogues on digital literacy among disadvantaged and excluded groups. DAP Nigeria has also continued the scoping work on spectrum management with the Dynamic Spectrum Alliance. In collaboration with local partners, the DSA has conducted analyses of the benefits of the usage of the 6GHz band for license exempt technologies to make connectivity more affordable.

In this review period, Brazil went through a change of political administration which has proved very constructive for digital development and for DAP Brazil’s strategic priorities and importance. Social development and the use of technology for promoting social inclusion have been the highlights of the new political regime. Some of the key highlights of this financial year are expected to be resource mobilisation for USF allocations and 5G auctions to promote a national school connectivity policy to bridge the connectivity gap. In this regard, ITU’s policy engagement and interventions on school connectivity mapping along with strong collaborations with local partners Lemann and MegaEdu has been instrumental in moving the dial in this policy area and shaping the approach to improving school connectivity. Acting on the ITU’s recommendations, a permanent discussion group led by the federal government, jointly with Ministry of Communications, National Telecoms Agency and Ministry of Education to address the current lack of dialogue on coherence of initiatives for improving school connectivity. The national ITU-DAP FCDO team have been providing invaluable technical assistance to this coordination process, additionally aided by a capacity building initiative on the Universal Service financing efficiency toolkit, developed by the ITU to mobilise execution of policies surrounding the use of the Universal Service Fund.

DAP Brazil has leveraged opportunities provided by the socio-political momentum and worked closely with existing stakeholders Anatel, Ministry of Management, Ministry of Communications and Ministry of Education with APC’s partnership, to support Anatel’s initiative to promote the responsible regulation of community networks, supporting Anatel’s initiatives to regulate community networks and last mile connectivity mapping.

As a result of this engagement, the telecom regulator has created its first internal Community networks committee dedicated to the promotion of open discussions on community networks. DAP Brazil will also co-host the third edition of the High-level UK-Brazil Digital & Cyber Dialogue to discuss policy challenges and propose cooperation strategies with the Brazilian Government, as one of many measures to improve the sustainability of our work on Digital Inclusion in the country.

In Indonesia, our projects continued to scale up digital inclusion models that have proved successful at pilot stage. We continued to work with SAFEnet, which resulted in two seminal publications on Online Gender-Based Violence Legal Framework in Indonesia and Online Gender-Based Violence against Indonesian Women Human Rights Defenders. English versions were disseminated widely. A handbook on handling cases of criminalisation of online expression was launched with the aim of improving beneficiaries’ capability to handle criminalisation cases against problematic articles of Indonesian Information and Electronic translation law. Policy recommendations from these publications were shared with The House of representatives of the Republic of Indonesia for consideration in the National Sexual violence bill.

There were many advancements made in strategic workstreams for enhancing last-mile connectivity with APC’s School of Community Networks, which was expanded in 10 areas of Indonesia through a series of workshops and programmes on community networks infrastructure. Innovating to adapt to geographic challenges, APC, ISIF, and the Research Center of Cultural Product and Environment – Institute Technology Bandung, set up a bamboo internet backhaul tower to respond to the need for affordable and locally available materials in Tembok Village, Bali, Indonesia.

Continuing our engagement on Telehealth and Telemedicine, Lapor-Covid 19 launched an application for Virtual Homecare Services with a community health consultation option. They also disseminated explainer publications highlighting the benefits of the service. The national award-winning service has provided free consultations for 774 patients with Covid-19, long Covid and mental health issues. Our work with Sehati Group on their maternal health application has successfully been moved to Tangerang province following a change in business model due to a Ministry of Health mandate. Using a standalone model application, the project has trained 13 community health centres and independent midwife practices.1672 ultimate beneficiaries (pregnant mothers) were monitored and received the consultations on the pregnancy risks using the results of the application.

Berdaya Bareng, DAP local partner since 2021, started work on their scale-up in this FY and conducted the first digital and entrepreneurship incubator for the best participants from the empowering women and people living with disabilities project. Three months of intensive mentoring sessions were given on business and managing social media. By the end of the mentoring sessions, the participants had the opportunity to scale up their businesses through various Berdaya Bareng networks/partners, including joining an exhibition with the Department of Cooperatives and MSMEs South Sulawesi province. The new phase of the project is targeting the expansion of digital literacy skills to improve financial literacy and entrepreneurship capability as part of post-pandemic economic recovery in several areas of Indonesia like Greater Makassar, Kendari, Manado, Balikpapan, and Samarinda.

In South Africa, the catalytic work started in 2022 continued through the review period, with an emphasis on demand side interventions with a focus on systemic levels and demand side interventions. Projects with local partners like Bellamatrix, Blind SA, CSIR and Research ICT Africa continued going strong while global partners like APC, DSA and ITU continued developing their projects in SA. Some of the key projects were:
- The Blind SA scale up which will train approximately 200 blind and partially sighted persons from 40 Community business organisations and 9 provinces in National certificate level qualifications for proficiency in information technology. Digital literacy and training in the use of computers and smartphones using adapted technology, software, hardware and smartphone apps will enable access to the internet and information networks. This will enhance their ability to access skills, employment and recreational activities.
- This FY, CSIR through C4IR is currently assessing the current implementation of open data policies by South Africa cities, establish regulatory gaps that may inhibit the large-scale implementation and co-design an open data actionable policy framework and tools that include the declaration of principles and a guideline for how local governments can develop specific policies and strategies for how data will be treated, and a network of early adopters will enable knowledge exchange and peer learning.
- Our scale up with Bellamatrix will address the digital divide which exists in the schooling community within the ICT in Education for teaching and learning. One of the key objectives of the programme is to build long-term sustainability that will enable continuity beyond the programme, and one of the main strategies to enable this is the catalysing, equipping and motivating of Communities of Practice.
- Our local project with NEMISA, started in 2022, was responsible for setting up the national digital skills framework of South Africa and is now discussing institutionalisation of digital access models with government.
- With global partner ITU, technical training sessions on specialised regulatory topics were conducted over three phases and hosted in Pretoria by ICASA. The first training on spectrum engineering fundamentals and legal and regulatory frameworks of spectrum management took place as from 15 to 16 May 2024, and was followed by the Spectrum Monitoring and Quality of service and experience regulatory frameworks training held on 25-26 May 2024. The training series concluded with sessions on International Mobile Telecommunications - 2020 systems and 5G deployment which took place from 26-27 June 2024.
- At the systemic level, the APC, along with local partner Zenzeleni, was responsible for improving the next generation spectrum policy, unlocking the broadband fund and making amendments to the Electronic Communications Act.
- The DSA made formal submissions and recommendations on the way forward for 6Ghz spectrum and spectrum policy reform. In one of the key achievements for DAP and DSA, the lower 6Ghz band has been opened as license exempt on 23rd May 2023. Following a series of strategic discussions and workshops with institutional stakeholders, a Wireless Internet Service Providers’ mentorship program is in planning stages with a view to implementation in Q3 2024/25.

At cross-country level, the FCDO Pillar 1 team across all partner countries continued to work with the Association for Progressive Communications to continue implementing the multi-country project on community networks development. Some of the main highlights for this FY include joint participation with UK government in the Partner to Connect Coalition Roundtables with a joining pledge on the national Schools, among other pledges submitted independently by each organisation. At the national level, the draft USF strategy in Kenya 2022-2026, which included support for 100 community networks, was made available for public consultation. In the next period, there is the opportunity to engage with the latest national consultation in South Africa in next generation spectrum policy, as well as regulatory training workshops with ITU in Kenya and Nigeria. The school of community networks also reached indirect beneficiaries in the villages and communities that were reached by the initiative. The number of indirect beneficiaries in partner countries were 10,000 in Brazil, 50 in Indonesia, 55,065 in Kenya, 140 in Nigeria and 94,872 in South Africa.

Additionally, the Joint APC-ITU Roundtable on last mile connectivity solutions in Kenya with ICTA and CA provided some timely momentum to the last mile connectivity priorities for the Government of Kenya’s Digital superhighway plan to set up public wi-fi hotspots around the country and set up and maintain connectivity infrastructure around them. As a result of this engagement, a new association of community network operators is being set up in Kenya to address issues with the operational environment and address challenges of sustainability and scaling up.

The Dynamic Spectrum Alliance was equally effective in pioneering alternative connectivity and digital access models by engaging on improvements to licensing regimes to accommodate the requirements of wireless internet service providers and on the benefits of opening the 6Ghz band for license exempt usage for affordable connectivity.

Some of the major milestones this year include a strategic cooperation agreement with the WISP association in Brazil (Abrint), engagement of NRAs across partner countries on 6Ghz spectrum band, e-learning platform with 7 modules on wi-fi development and the regulatory landscape. The DSA has also conducted market analysis and proposed capacity building curriculum for WISPs and small-scale internet service providers for key digital economies like Kenya.

Our long-standing association with ITU has resulted in the development of the valuable Universal service financing efficiency toolkit, and training on how to use it across all partner countries. Key highlights include a draft roadmap on Child Online Protection (COP) undertaken by the Ministry of Women’s Empowerment and Child Protection with the support of UNICEF Indonesia and the involvement of the Indonesian COP multiagency Network. Through this, project, last mile connectivity mapping of broadband networks and school connectivity has been provided to most partner governments and adequate training on mapping has been launched on the ITU academy. This has been accompanied by discussions, policy dialogues and stakeholder roundtables on improving school connectivity mapping and resource mobilisation for improving sustainable operating models for connecting schools

On digital literacy and skills development, the British Council made some key inroads with the launch of the national digital skills curriculum and assessment framework in Kenya and engaged partner governments across partner countries organising successful policy dialogues and generating recommendations on the way forward for sustainable digital literacy and skills mapping and development. Their interventions have also resulted in a large mobile global Community of Practice and sustainable impact creation with global dissemination of training toolkits and training of expert level trainers who are well equipped to be agents of transformation and change for their communities.

Our joint project with BSI on international standards has had sustainable impacts like the contribution to Kenya’s eTrade strategy and international standards summit at the G20 in Indonesia, while engaging public and private stakeholders in policy roundtables and capacity building on international standards.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.

The key recommendations for Pillar 1 from the DAP 2023 AR were all implemented within the set timelines, as summarised below:

Intensify cross-country knowledge exchange with two peer-learning events by end of FY2023/24: DAP Pillar 1 successfully organised an annual peer learning event in December 2023 with adequate attention to tracking the development of all strategic DAP workstreams in 2024. Country teams, stakeholders and partners all shared insights and noted achievements in the areas of inclusive connectivity, cybersecurity capacity building, female tech entrepreneurship and digital employability, digital literacy and digital skills, gender, disability and inclusion and engaging with key government stakeholders. Takeaways from the session included case studies and examples of successfully scaled up projects which have resulted in sustainable impact. Reflections on MREL and lessons learned formed the core of a series of follow-up sessions on digital skills, gender and inclusion and engagement with government stakeholders. The X-DAP teams' site was refreshed and re-started as a new Teams channel. Since then, programme reporting templates have been refreshed and a new cross-country activity tracker has been added to keep track of projects. This tracker has been updated regularly since the event and is being used more effectively by all country teams and country leads.

Upgrade Pillar 1 cross-country project trackers, increase focus on knowledge management by prioritising Learning and Insights workstream and strengthen the link of Pillar 1 activities with relevant strategies and policy work in digital development: Throughout the review period, frequent stocktaking sessions with country teams resulted in consistent tracking and monitoring of project progress, delivery challenges, key stakeholder engagement and achievements. All these updates were recorded in an annual activity tracker to ensure the achievement of strategic priorities and expected outcomes as highlighted in the CLIPs. The Learning and Insights workstream was strengthened by follow ups on lessons learned, shared under various strategic priority headings in the DAP peer learning event. A knowledge management ToR [43]was put in place, based on insights and demands raised by country teams, for a potential knowledge management workstream.
[43] Terms of Reference

Increase the focus on G2G (government-to-government) peer learning, building on the positive experience of Ofcom’s exchanges with telecom regulators in Kenya and South Africa during FY 2023/24: DAP Pillar 1 built on peer learning exchanges through forums organised by global partners like the Global Summit organised by the Dynamic Spectrum Alliance and other country-based stakeholder roundtables and policy discussions with the ICT Authority and Communication Authority of Kenya, and with Anatel in Brazil, in collaboration with APC and partners. Knowledge exchange priorities were also built into this FY’s strategic planning process through the CLIPs for each partner country. The DAP central team continued to build the relationship with Ofcom and to facilitate relevant peer learning exchanges with telecoms regulators and ICT authorities in partner countries, as well as coordinating on joint inputs for policy commissions and presentations in international fora (for example within the ITU, CTO and IGF contexts) attended by senior representatives of DAP countries’ governments.

Build on the demonstration of viable business models for inclusive connectivity, through direct engagement with the industry to ensure models are picked up and scaled, investors see the opportunity in last-mile markets, and financial sustainability is embedded in the process: We have had robust cross-pillar engagement with public and private sector stakeholders through forums like the Pillar 2 led Chatham House conference and Pillar 3 led tech-hub events both centrally and in partner countries. Nationally and internationally, we have had several examples of project scale-ups across the project portfolio as demonstrated in the narrative above. Some highlights include institutionalisation of National digital skills and literacy frameworks in Kenya and South Africa and institutional adoption of digital telehealth applications in Indonesia. The institutionalisation of last mile connectivity models involving community networks, small-scale internet service providers and wireless internet service providers has also been evolving as a key priority in Kenya this FY. Pillar 1 teams will continue to strengthen the focus on this recommendation in FY 2023/24.

Build on the mainstreaming of environment and climate themes in the DAP CLIPs: DAP Pillar 1 worked on spreading awareness among stakeholders and mobilising partners on the urgency of adapting to the theme of sustainability and digital awareness and developed strategic workstreams on climate change and sustainability through the CLIPs. Some of these workstreams from the partner countries are a Digital framework for better monitoring of deforestation (Brazil), Improvement of technology adoption of cross cutting efforts to reach net zero targets, Digital literacy for farmers on Climate-change adaptive agricultural practices (Kenya), Promoting sustainability through digital means (Nigeria), Strengthening national policy environment for managing and mitigating the impact of ICTs on climate change.

Lessons	Recommendations	Owners	Timelines
DAP country teams have progressed to develop successful scale-ups of evolving Pilar 1 strategic workstreams with local and global partners, while intensifying bi-lateral systemic level partnerships and knowledge exchange with partner governments.	Develop the DAP learning and insights workstream further with a focus on knowledge management and amplifying the visibility and impact of programme implementation in geopolitically relevant regions where DAP partner countries are located. Organise an annual peer learning event and a cross-HMG DevTech talk on the programme.	DAP Pillar 1 SRO/Lead Adviser/PRO	By December 2024
Environmental sustainability and climate change are being proactively developed as strategic workstreams in this FY’s strategic planning.	Link into new strategic workstreams on digital sustainability developed with the new DDS, in collaboration with Climate advisory cadre, using DAP projects to pilot innovative approaches, with focus on climate tech, e-waste management, and renewable energy connectivity solutions.	DAP Pillar 1 SRO/Lead Adviser	By March 2025
Peer to peer exchanges with governments of partner countries have continued through national and international roundtables and conferences conducted by local and global partners.	Continue engagement with DAP partner country governments and industry to ensure digital access models are scaled up sustainably, with investor buy-in, where possible; and link more directly into opportunities with BII and broader BIP offer. / Refresh the DAP Private Sector Engagement plan to prioritise additional strategic corporate partnerships.	DAP Pillar 1 country leads/Adviser	By March 2025
	Focus on implementing projects which employ digital inclusion models to tackle climate change and improve environmental sustainability in alignment with business planning priorities at post and central DAP objectives.	DAP Adviser/country leads/PRO	FY 2024/25

Output title:	Increased resilience of partner countries to cybersecurity threats through supporting effective legislation and strategies, embedding education and training, establishing industry standards, and building a culture of cybersecurity.
Output number:	2	Output Score:	A+
Impact weighting (%):	30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) / for this review	Progress[44]
Initiatives delivered to increase awareness of cybersecurity and data protection issues amongst general public, senior policy makers and law enforcement institutions	12	16 initiatives delivered to increase awareness of cybersecurity and data protection issues amongst public, senior policy makers and law enforcement institutions / 1 multi-channel communications campaign to increase awareness and uptake of the Nigerian Cyber Security Strategy (Nigeria) / 1 training of Indonesian government ministries responsible for delivering cyber security policies and regulations for critical CNI assets. (Indonesia)
Cybersecurity-related legislation and strategies developed	10	13 cybersecurity related legislation and strategies developed (annual) / 1 Cybercrime awareness and skills amongst law enforcement officers (South Africa) / 1 Improving Telemedicine cybersecurity (Indonesia) / 1 Cybersecurity regulation for the banking sector (Indonesia) / 1 ‘security by design’ framework for Ministry of Economy to use in its digitisation programme more widely where desired
Aggregate beneficiaries (individuals, businesses or institutions) directly reached by Pillar 2 projects on cybersecurity / cyber-hygiene awareness and cybersecurity capacity building initiatives	13,000	42,729 beneficiaries directly reached by Pillar 2 projects on cybersecurity / cyber-hygiene awareness and cybersecurity capacity building initiatives / 2 Cybersecurity and data protection toolkits for SMEs (SA and Nigeria) / 1 National incident response coordination activities / 1 Digital forensics training / 1 SEDA train the trainer programme and pilot trainings / 1 awareness raising of cybersecurity campaign (Brazil) / 1 national cyber security curriculum development (Brazil)
[44] Pillar 2 indicators are evaluated as cumulative numbers. Annual numbers are as follows: 2 cybersecurity initiatives delivered, 4 cybersecurity related legislation and strategies developed, and 31700 beneficiaries engaged in FY 2022/23.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 receives a score of A+, as all indicators have overachieved their relevant milestones moderately or significantly.

Output 2 is delivered by the FCDO-led Pillar 2 (‘Trust & Resilience’) of the DAP. Under Pillar 2, the main contract with KPMG entered full implementation in June 2021.The design of this programme component in each partner country was based on the initial DAP cross-pillar digital access diagnostics, and subsequently on the pillar-specific assessments made during the inception phase. The latter considered independent assessments of national cyber security capacity and demand from key stakeholders in each country. All projects have delivered outputs as planned, moderately to significantly exceeding expectations. The overall effect of the project portfolio under this component also provides evidence of further outcome-level change. Below is a summary description of project highlights and relevant results in the five partner countries:

In Indonesia, Pillar 2 worked on cyber security regulation support in the financial sector. We supported the development of a consultation paper that set out stringent data protection and cybersecurity standards and controls for banks. To better understand the impact of the proposed legislation, a test exercise was piloted with eight banks. Recommendations from the pilot were used to refine the new regulatory framework, which is expected to become law by the end of the year. We also conducted a training needs analysis to determine further training OJK staff (Otoritas Jasa Keuangan, Financial Services Authority of Indonesia) might need to perform these assessments annually, across all Indonesian banks.

We also secured Indonesia’s telemedicine services by supporting the Ministry of Health assess the cyber security and data protection capacity of healthcare facilities. Under DAP, we released a Security Outcomes Framework (SOF) which will be used as a tool to assess the capacity of the participating organisations. We also undertook a pilot project to provide the Indonesian Ministry of Health with identified lessons, recommendations on how to develop and embed the SOF in the health sector, and what is required to make it happen. As a result of the pilot project, the MOH are implementing the SOF across wider healthcare organisations, and alignment to the SOF will be a requirement of relevant healthcare legislation.

In Brazil, Pillar 2, focused on cybersecurity capacity building and awareness raising of key actors supporting Brazil’s cybersecurity maturity and resilience. DAP supported Brazil’s implementation of a Security by Design framework for newly digitised government services covering the 169 government departments. We also built the Brazilian Government’s capacity to carry out national cyber security awareness campaigns, working with the Institutional Security Cabinet of the President of the Republic (GSI) and led the development of a National Cybersecurity Curriculum for schools, indirectly benefiting 1500 students and 300 teachers.

To support the Brazilian government’s digitisation of government service programme, Pillar 2 created a Secure By Design framework which covers a set of technical controls that are to be applied when each government service is digitised. Training was provided to Brazil’s Special Secretariat of De-bureaucratisation, Management, and Digital Government (‘SGD’) using real-life government services as examples to show how the framework should be applied, and a RAG rating mechanism was created so SGD can retrospectively evaluate the security of services that have already been digitised. This framework and training provide reassurance over the safety of citizens’ personal data and safeguards services’ integrity and availability.

A project to curate a toolkit of high-quality cyber education resources was designed, comprising 40 hours of lesson plans and support materials, the toolkit design was informed by research among students and teachers into the problems surrounding cyber education in schools. The toolkit is now available to teachers nationwide and work is underway to promote its availability.

In Nigeria, Pillar 2 took on the bold task of reinforcing the critical national infrastructure (CNI) threat assessment and protection framework. Nigeria’s Office of the National Security Adviser (ONSA) wanted to rectify their understanding of the CNI system and the impact of cyber security threats. DAP Pillar 2 led on the development of a framework for 00identifying its CNI and protecting it from cyberattacks. To support ONSA, this project worked with Nigerian CNI providers and the UK subject matter experts to understand the maturity of CNI regulation in Nigeria to develop functional requirements for a new CNI regulation operating model, and to help upskill key stakeholders to implement it through regular audits of CNI security. Building this capability within Nigeria will enable effective ongoing assessment of how CNI providers are managing cybersecurity risks, to identify and address recommendations for improvement.
In 2021, Nigeria’s Office of the National Security Adviser (ONSA) launched an updated version of its National Cybersecurity Policy and Strategy (NCPS). Keen to raise awareness of this new strategy, ONSA wanted to deploy a substantial communications campaign, which was taken on by Pillar 2. The campaign highlighted what had changed within the NCPS, why this mattered, and what people might be expected to do differently as a result. A broad mix of different audiences, from other government agencies and critical industry sectors through to the general population, were targeted. The campaign reached 10% of the Nigerian population; some 20 million people under the DAP intervention. The results of the anonymous post-delivery survey indicated that after viewing the communications materials, 92% of those surveyed would take steps to protect themselves better online as a result.
In another initiative, also delivered in South Africa – a cybersecurity and data protection toolkit was developed, through which, over 150 individuals received cybersecurity training to increase awareness of cyber security threats and risks and provide guidance on good practice amongst SME owners and employees. In the post-event survey 86% ‘strongly agreed’ and 14% ‘agreed’ that the training increased their awareness of cybersecurity and 81% ‘strongly agreed’ and 19% agreed that they will recommend the toolkit to others.

In South Africa, Pillar 2 developed a Cybersecurity and Data Protection Toolkit to provide SMMEs with guidance on how to improve their cyber maturity and take the necessary steps towards being compliant with the Protection of Personal Information Act (POPIA). On DAP, we promoted engagement with the toolkit and upskilled SMMEs through a series of roadshows, trainings, and train the trainer schemes with the Small Enterprise Development Agency (SEDA).
Over 200 SMMEs participated in the Cyber Roadshow and an additional 200+ viewed our session(s) online. The sessions covered cyber hygiene basics, data protections/POPIA 101, Ransomware overview, and training on how to use the free resources in the toolkit. Through feedback reports, 95% of participants indicated they had engaged with the toolkit since the session, and 76% of those who used the toolkit found it very useful, and 24% found it useful. We will work with FCDO during the Cyber Africa Programme to agree how to collect further evidence of the toolkit being successfully used by SMMEs.
In another initiative in South Africa, we worked on a complete cybercrime training curriculum for police offices. New standard operating procedures were also developed, outlining how officers should use the powers available to them within the Cybercrimes Act.
Over 2,300 police officers have been trained on the Cybercrimes Act. Participants completed a pre- and post-training survey to assess the extent to which the training increased their knowledge of the act. Their self-reported knowledge pre- and post-training increased by 30–62 percentage points across all areas.

In Kenya, the relatively new Office of the Data Protection Commissioner (ODPC) exists to improve the security of Kenyan citizens’ and organisations’ confidential data. The DAP team worked with the ODPC to help operationalise its first three-year strategy, translating it into a sustainable framework for how data should be handled. The DAP also helped to create a national Public Key Infrastructure system, in line with international best practice guidelines. This will play a vital role in securing online transactions, delivering confidentiality, integrity and authentication services across the government’s digital platforms.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A – no changes made and no changes planned as a result of this review

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

During the period under review, the DAP Pillar 2 team addressed the recommendations outlined in the 2022 Annual Review report, as summarised below:
Strengthen partner governments’ buy-in to projects - We engaged proactively with governments of all partner countries, coordinating with key cybersecurity stakeholders like the Financial Service Authority and the Ministry of Health in Indonesia, Institutional Security Cabinet of the President of the Republic and Special Secretariat of De-bureaucratisation, Management, and Digital Government (‘SGD’) in Brazil, the Office of the National Security Adviser in Nigeria and Small Enterprise Development Agency (SEDA) in South Africa among others. The portfolio of projects in each country was balanced between those that require government buy-in as a critical success factor, and those that were delivered independently. While most collaborations with governments focused on reinforcing and strengthening cybersecurity infrastructure, other projects in the industry space focused on working with small and medium scale enterprises and adopted a train the trainers' approach to achieve expected outcomes. KPMG, the main DAP Pillar 2 implementation partner continued to work with posts to build robust relationships with relevant public and private institutions, including by communicating DAP’s achievements systematically and highlighting the programme’s added value. They used multi-channel communications (websites, social media, radio and events) for national public awareness campaigns, and reused, adapted and tailored material depending on the platform and target audience. Metrics, such as audience analysis and segmentation, enabled comparative analysis of different types of communication, leading the partner to refine their communication strategies throughout the project lifetime.

Better cross-coordination and delivery of cyber capacity building work across partner countries - The DAP programme team continued to ensure that all Pillar 2 activity is coordinated well across countries. From October 2020 to June 2024, the DAP Trust & Resilience Pillar delivered £10 million of cyber capacity-building activities across 15 projects. These projects included helping the Nigerian police force to develop its digital forensic capability; enabled Kenya’s government to better protect its citizens’ data; assisted the delivery of Brazil’s new cybersecurity school curriculum; developing Indonesia’s national cybersecurity strategy; and improved the South African police’s ability to prosecute cybercriminals and combat online child exploitation. All projects aimed to build sustained capacity, enabling partner governments to better protect their citizens online and to defend their critical national infrastructure (CNI) from cyberthreats. As a major step towards ensuring cross coordination and better delivery of capacity building priorities, Chatham House hosted the Strengthening Cyber Resilience Conference in London in November 2022, in partnership with KPMG. The conference’s aim was to share experiences and knowledge about how international cybersecurity capacity-building can support national sustainable development and cybersecurity outcomes. The conference also explored the role of international partnerships, drawing on the experience of and lessons from the DAP. More than 100 implementers, policymakers and other experts from the five DAP partner countries and from the UK shared their experiences and best practices based on DAP projects and other activities. The conference was also an opportunity to strengthen international networks and consider next steps for national and international capacity-building projects.

Continued alignment with CSSF requirements including with regard to funding of local staff, admin costs cap, and project monitoring and learning - Former DAP Pillar 2 projects have now been integrated into the CSSF Africa Cyber Programme (Kenya, Nigeria, South Africa), the CSSF Indo-Pacific Programme (Indonesia) and the CSSF Global Cyber Programme (Brazil). These programmes form part of the CSSF Cyber Portfolio, led by the Resilience Team in FCDO Cyber Policy Department. All aspects of administration spend, staffing and cost caps fall under the jurisdiction of the Joint Funds Unit (JFU) and the CSSF guidelines and rules. The Cyber Portfolio has an agreed budget for staffing with the JFU this financial year, currently standing at around 6.5% of total costs. Any new staffing slots, including for Country Based Staff will be agreed with JFU.

Lessons learned this year

- Understanding the target audience and beneficiaries through detailed needs assessments and understanding the political context throughout periods of transition (like in Nigeria this FY) is really important for effective mitigation of delivery challenges and risks.
- It is crucial to build mutual trust by gathering advice, opinions and concerns from a variety of different stakeholders in the set-up and inception phases of the project.
- It is vital to ensure that all stakeholders agree on the scope of project activities and what constitutes success. Clear communication – particularly on timescales and what delivery looks like in practice – can help align expectations in the project’s planning phases.
- Adopting a highly dynamic and responsive approach to project implementation including a significant appetite for risk and commensurate procedures for risk awareness and tolerance, with an emphasis on communication with stakeholders in project implementation.
- The main challenge in implementation was not a lack of data to measure project impact, but rather sharing data between stakeholders, even different government agencies and organisation building trusted information sharing-platforms and embracing an open approach.
- Partnering with third-party organisations, exploring self-financing models and national and international knowledge sharing and expert community building were central to ensuring sustainability of project activities and impact after formal closure of projects.
- Building trust and promoting collaborative working has been crucial in catalysing the possibility of achieving significant outcome level changes across the project portfolio and partner countries.
Recommendations for next year

- We should continue to work on scaling up sustainable projects which have been concluded in this FY by working with Posts to build robust relationships with relevant public institutions, including by communicating DAP’s achievements systematically and highlighting the programme’s added value.
- We should continue annual processes of outcome harvesting to collect evidence of outcome level changes. Since this financial year, the process is led by an external MEL provider, Integrity Global, working closely with the Portfolio Performance and Operations team. The best evidenced examples should proactively be developed into “change stories” which can be shared with FCDO Cyber Governance Boards and in wider reporting. Project level data should continue to be captured in a “repository” which will be used to track and monitor progress, and for analysis and reporting purposes.
- Lessons learned should start being captured on a quarterly basis with programme leads requesting further information from implementers on how sufficient trust and collaborative working can be embedded in project design.

Output title:	Greater access to digital services that address development challenges, and a more developed and inclusive digital entrepreneurial ecosystem will lead to poverty reduction through inclusive digital economic growth and digital development.
Output number:	3	Output Score:	A+
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of people trained	50,000	54,637[45] people trained / (including cross-country work) / 1,589 Indonesia / 801 SA / 2,163 Nigeria / 1,529 Kenya / 7,763 Brazil
Number of tech SMEs mentored	8,000	9,012 tech SMEs mentored / (including cross-country work) / 708 Indonesia / 308 SA / 130 Nigeria / 72 Kenya / 473 Brazil
Number of funders and investors engaged	1,800	1,815 funders and investors engaged / (including cross-country work) / 47 Indonesia / 312 SA / 62 Nigeria / 201 Kenya / 31 Brazil
[45] 13,845 people trained, 1,691 tech SMEs mentored and 653 funders and investors engaged in FY 2022/23

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 is delivered by the DSIT-led Pillar 3 (‘Sustainable Digital Ecosystems’) of the DAP, constituted by the DSIT-led International Tech Hub Network (ITHN), which works to stimulate innovation and technology on a local level in partner countries. The network aims to forge innovation partnerships between international tech sectors and the UK, stimulate local digital economies and build high-end digital skills.

Pillar 3 of the DAP includes the ODA-funded Tech Hubs (in South Africa, Nigeria, Kenya, Indonesia, and Brazil). These support digital entrepreneurs, SMEs and tech start-ups across their respective technology ecosystems to find innovative solutions to local development challenges, thereby driving sustainable economic growth to serve women, marginalised youth and PwDs[46] in particular. The Tech Hub approach therefore contributes to the overall DAP digital inclusion programme goals.
[46] People living with disabilities.

It built on a successful FY2022/23, expanding the breadth and results of project delivery across the network, as well as increasing the cross-pillar collaboration and synergy with Pillar 1 and Pillar 2 initiatives. All five Tech Hubs have been operational during the period under review. Through the provision of digital skills training, mentoring, connections with investors and funders, entrepreneur support and trainer development, the Tech Hubs have significantly contributed to their local tech ecosystems. Pillar 3 activities have been a mixture of piloting innovative solutions to local development challenges and scaling approaches that have proven to be successful. The Tech Hubs adopted an agile and flexible approach to design and delivery.

A significant development from previous years has been the Tech Hubs’ involvement in policy and strategy initiatives in partner countries, aligning more directly with the systemic approach of Pillars 1 and 2 of the DAP. For example, three of the hubs have worked with host Governments on start-up legislation, whilst others have been involved in relevant policy dialogues. This has ensured that we influence the local tech ecosystem more comprehensively.

As well as in-country projects, Pillar 3 delivered two cross-country projects during the past two years: the African Angel Academy and the Future Female Business School (more details below), the latter being a great example of DAP cross-pillar work through co-design and co-funding. Throughout the year, the Tech Hub teams at Post have proactively coordinated across DAP pillars to identify opportunities for collaboration on projects and connect digital innovations and tech start-ups to Pillar 1, Pillar 2, and cross-programme objectives.

Below is a summary of highlights from the work of the Tech Hubs in the five DAP countries.

Brazil

In FY2023/24, the UK-Brazil Tech Hub continued fostering innovation and collaboration between the United Kingdom and Brazil, achieving significant milestones and leaving a positive impact on Brazil's digital ecosystem. Throughout the year, 7,763 beneficiaries (with 54% women) were directly supported through 10 initiatives in collaboration with key public and private stakeholders across Brazil. The Hub focused on addressing inequality and climate objectives, with particular attention to the Northeast region of Brazil, where the highest inequality rates are observed. The Hub worked closely with government and private organisations on a national level to promote greener and more inclusive technologies and digital ecosystems, improving public services through gov-tech and citizen technology accelerators.
Strategic partnerships with cities of Belo Horizonte (Southeast), Toledo (South), Salvador and Recife (Northeast) played a vital role in developing successful cases of inclusive public policies. These partnerships aimed to provide training and inclusion opportunities to individuals from underserved areas, ensuring a continuous effort to leave no one left behind the benefits of the digital economy. The Tech Hub led policy engagements and dialogues with stakeholders at city, state and national levels, contributing to advance UK-Brazil collaborations in various areas including digital transformation, tech for good, digital inclusion, connectivity, climate, gender equality, LGBT+ rights, and development.
Two cross-pillar projects (DAP Pillars 1 and 3) were implemented, successfully offering a holistic approach to digital development in Brazil. Working in partnership with the National Telecoms Regulator ANATEL, the Campus Party Include project provided training to +450 teenagers in public schools in the cities of Toledo (state of Paraná) and Salvador (state of Bahia). This initiative established technology labs and equipped young minds with robotics and digital skills, enabling them to embrace STEM areas and explore further learning and professional opportunities. This effort was particularly significant for the region near the Iguaçu Triple Frontier (Brazil, Argentina, and Paraguay), and the community Nordeste de Amarelina in Salvador, both known for their vulnerability to criminal activities. Another cross-pillar initiative engaged the state of Bahia (Northeast) to address connectivity and climate resilience with a roadmap produced with UK expertise by the Connected Places Catapult.
The Tech Hub supported new digital innovations through a national approach. The Future Females continued to deliver strong gender equality results supporting +130 women entrepreneurs who acquired valuable knowledge, skills, and networks with two cohorts focused exclusively on Greentechs and Agritechs. The BrazilLAB GreenGovTechs Accelerator provided a platform for innovative solutions addressing environmental challenges faced by the government, thereby contributing to a greener future.

Similarly, the CitzTech program, in partnership with META and LabHacker, made a significant impact at the National Congress by supporting 50 start-ups while facilitating the government's enhancement of its services and public engagement. The Global Impact Bootcamps united 106 start-ups, predominantly from the Northeast of Brazil, fostering collaboration and knowledge exchange on a global scale, providing a platform for entrepreneurs to learn about accessing international markets and contribute to solving global challenges, with the UK serving as a natural destination for partnerships and opportunities.

Indonesia

Over the course of FY2023-24, UK – Indonesia Tech Hub projects in Indonesia have made significant strides, leaving a growing impact within the digital ecosystem. The hub’s concerted efforts have empowered 1,589 beneficiaries with essential skills of digital literacy and equipping them to navigate the digital landscape confidently. By bridging the digital divide, the hub has enabled individuals to participate actively in the digital economy, fostering social inclusion and economic empowerment. Simultaneously, our focus on entrepreneurship support has fostered a thriving ecosystem, having mentored 708 small and medium enterprises, providing them with the tools and knowledge necessary to succeed. By nurturing innovation, fostering entrepreneurial mindsets, and connecting start-ups with networks and funding opportunities, the likes of the Nurture to Scale project, we have also catalysed sustainable growth within the tech sector.
In line with the UK’s vision of gender equality, the hub targeted and uplifted 1,484 women through entrepreneurship mentoring, offering tailored digital transformation support and resources through hub’s FemTech community gathering, unlocking their potential, driving meaningful change in their lives and communities. A crucial aspect of the hub’s work has also been growth of digital innovations for local development. This year, 168 local start-ups have harnessed their creative potential, yielding transformative solutions for societal challenges through industry mentoring and business acceleration.

Recognizing the importance of collaboration, 47 funders and investors were engaged, along with the establishment of 12 partnerships with public and private stakeholders, forging strategic partnerships that fuel the growth of our projects, from government endorsement, co-funding projects to providing access to capital for beneficiaries, strengthening our ability to effect lasting change and scale impact. Additionally, the hub has facilitated six policy dialogues and strategic stakeholder consultations, elevating the importance of innovation growth, talent and suitable regulation within the national agenda like the health tech regulatory sandbox¸ which creates an enabling environment for digital development.
It has been a transformative year for the UK – Indonesia Tech Hub despite operating with limited resources, the hub kept engaged and leveraged relevant connections. The hub continuously supports a future of inclusivity, prosperity, and sustainable growth for all by nurturing the digital ecosystem in Indonesia.

Kenya

Through the UK-Kenya Tech Hub, the UK Government continues to support and increase it impact across the tech-start up ecosystem in the country. Through this year’s 8 projects, the tech hub has been able to positively impact 1500+ people from trainings to build websites in less than 30 minutes with no code to training women entrepreneurs on building their credit scores in order to access debt financing from lenders.

We have witnessed a great deal of success in continuing to build the Angel investor network pipeline, with 8 more groups created to get more individuals to diversify their investment by starting to invest in start-ups, thereby supporting local innovations to access international markets.

Through joint collaborations with other departments across the FCDO, we continue to scale innovations beyond our reach. Strong partnerships with ATIP and the RISA Fund have seen us take our programmes a notch higher, with the likes of Sasakazi going on to receive funding to scale up and support more tech entrepreneurs access job opportunities while improving their skillset. This project which initially run as the Digital Access Programme under the UK-Kenya Tech Hub banner has been able to leap a step further as a result of the cross-cutting support from such funds and supportive colleagues from the East Africa Research and Innovation Hub. As the UK-Kenya Tech Hub, we remain committed to supporting the Kenyan tech ecosystem, spurring growth by leveraging on HMG’s supportive role through the Digital Access Programme.

Nigeria

From June 2022 to June 2023, the UK-Nigeria Tech Hub made a significant impact, reaching 2,163 individuals through various initiatives. This included providing digital skills training to 1,700 people, with a focus on empowering women (680 trained). The Tech Hub also supported 168 tech-enabled SMEs, early-stage startups, and engaged with 55 investors.

The Nigeria Tech Hub collaborated with Google for Startups to award $3 million in cloud credit infrastructure to female technology founders in Nigeria.

Building upon the successful pilot, the Tech Hub scaled the Design, Product, and Developer School, now known as the DevCareer Tech Programme. This 6-month virtual training program, equipped 1,700 individuals, including 680 women, across Nigeria's 6 geopolitical zones with technical skills in software development, product design, and product management.

Additionally, the Tech Hub supported the 'Social Innovation Driven Entrepreneurship' project in collaboration with the Network of Innovators and Incubators in Nigeria (NINe), Kaduna Business School, and Microsoft. This hybrid accelerator program aided 60 commercially viable and innovative digital solutions that create more economic opportunities through identified market and sector gaps affecting Mid to low economic class demography in Nigeria.

The African Angel Academy project trained 24 aspiring angel investors (15 women, 9 men), equipping them with the knowledge needed to identify and invest in deals. The Nigeria Syndicate Legal Primer was also developed and made open source for the benefit of the tech ecosystem.

South Africa

The UK-South Africa tech hub networked 1,275 people and trained 769 programme beneficiaries, expanding access to UK networks, promoting tech inclusion, creating funding opportunities and cross-organizational collaboration. Operationally, a greater emphasis was placed on deeper interventions, resource maximization, scaling through collaboration, and the sustainability of interventions.
Expanding Access to UK Networks:
The UK-SA tech hub delivered 3 projects expanding access to UK networks for 103 beneficiaries:
A) A pilot Funders to Founders project connected 24 UK & European investors with 19 South African start-ups. Three months post-programme, 3 start-ups have expanded into the UK; with 1 more successfully raising their first round of funding.
B) Through the Global Entrepreneurship Programme (GEP) collaboration, two masterclasses were held with the GEP, to support 19 tech hub alumni in their journey to scale their start-ups to the UK.
C) The GESA awards, provided a platform for 10 ed-tech founders to showcase their businesses, with the three semi-finalists receiving travel and accommodation support to the UK for the finals.

Promoting Tech Inclusion:
The support of women, previously disadvantaged communities and beneficiaries from rural communities is built into the design of all UK-SA tech hub projects and initiatives. We delivered principally through 3 initiatives:
1. We commissioned Future Females Empowerment Initiative to research the female funding gap in Africa, drive dialogue around the gender disparities within tech, which could then provide evidence for programmatic design in future. Through this, 10 industry experts joined a roundtable event to discuss the final research report.
2. Future Females Business School (FFBS) provided training for 114 women entrepreneurs, with 22 of those beneficiaries coming from rural communities.
3. Launch League supported 16 underserved tech hubs across South Africa, through their open-licensed toolkit. 239 of the 360 beneficiaries networked came from previously disadvantaged backgrounds.
.
Creating Funding Opportunities:
Enabling a thriving fundraising environment continued to be a focus area for the UK-South Africa Tech Hub. 102 funders and investors were engaged across all programmes, connect events and interventions. Through the African Early-Stage Investment Summit we expanded our network to include 626 members of the investment community. We introduced 37 funders to businesses from the GESA Awards, Future Females Business School and Funders to Founders.

Cross-Organizational Collaboration:
We have scaled impact through collaboration both across the network of tech hubs and across the British High Commission in South Africa. Future Female Business School delivered its 13th Cohort across all 5 tech hubs. This also provided the data for the funding gap research report. Launch League remained a key collaboration between P3 and P1 of the Digital Access Program. The Tech Hub worked with the political team to open new opportunities for our partners working on The Startup Act Movement and a Policy Business Case Study, additionally the hub supported DBT’s Africa Arena event.

The UK-SA Tech Hub’s interventions have made great progress promoting sustainable, impact-driven results over a larger pool of short-term beneficiaries. Over the next 2 years we want to drive project scale by securing match funding from organisations which share our commitment to digital inclusion.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes made during the period under review, and no changes planned as a result of this Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

1. Ensure good coordination and synergy at local level and identifying potential activities for delivery by the Tech Hubs to achieve joint objectives with Pillar 1 and/or Pillar 2:
During the period under review, the Tech Hub teams have continued to work with colleagues across the DAP on cross-pillar activities that achieve joint programme objectives. This has been supported by the work of the Programme Management Committee, regular cross-pillar meetings with DAP country teams and joint updating of the CLIPs. The success of this approach has been documented throughout section C of this report.

2. Complete Tech Hub teams staffing and provide targeted support on project design and management from central teams:

During the period under review, the DAP governance structure and senior leads at post worked to complete the staffing and resourcing of the five Tech Hubs to a level commensurate with Pillar 3’s scope, and enabling a more strategic engagement with the digital ecosystems in-country. Central teams from Pillar 1 (lead) and Pillar 3 worked closely together to provide relevant steer and advice, as well as project design, procurement, implementation and monitoring support, managing the gap created in DSIT by internal restructuring and downsizing of the ITHN team. This worked very well for the achievement of the programme’s objectives and targets, and also for cross-pillar learning; however it also placed an additional strain on the already stretched lead central team, which the DAP governance structure has started to address for FY2024/25 through a revised resourcing model.

Lessons learned this year and recommendations for the year ahead.
1. During the period under review, the Tech Hubs have increased their influence in the ecosystem including at policy level. To enhance this trend, we need to coordinate across HMG more proactively and have regular engagement with relevant policy teams, in sync with the rest of the DAP to ensure a joined-up approach.
2. There is high demand for the Tech Hub offer. In order to expand the reach of Pillar 3 to further contribute to DAP goals, we need to extend our network through collaborating with other hubs across the relevant regions. This includes external stakeholders such as tech and digital development organisations, thought leaders and the UK tech community.
3. The International Tech Hub Network has shown progress against its outcomes and output measurements. Moving forward, we need to focus further on impact-level results, such as contribution to inclusive economic growth. To ensure we are supporting the development of local digital economies, we need to measure job creation, revenue generated, and sectoral impact (e.g., number of people who now have access to financial services as a result of a fintech solution).
4. To enhance the sustainability of the Tech Hubs’ interventions, the teams need to seek more proactively like-minded supporters and funders, beyond HMG, which share the DAP’s commitment to digital inclusion. This would fit well our ‘pilot & scale’ model, crowding in diverse sponsors and investors at different stages of digital innovation.
5. Working with a wide range of local partners has demonstrated the high level of growth potential in the digital ecosystems of all DAP countries. Borrowing from Pillar 1 and Pillar 2 approaches, also Pillar 3 needs to focus on building local capacity, which helps with long-term sustainability and government buy-in, resulting in credibility of UK interventions.
6. Co-creation of interventions across the programme pillars and with a range of local partners and stakeholders has ensured that we capture all relevant perspectives. The Tech Hubs should continue to apply their multi-stakeholder approach (in line with wider DAP) to ensure contextual knowledge and robust diagnostic of local challenges and opportunities are duly considered in design, delivery and learning.

D: RISK

The DAP central FCDO and DSIT teams managing Pillars 1, 2 and 3 of the programmes, and their respective SROs, are working closely and systematically through the DAP programme governance structure (Senior Governance Committee, Programme Management Committee) to jointly monitor risks and issues and put mitigation measures in place with a collaborative and agile approach.

More specifically, the DAP central teams assess risks at pillar and programme level; and the five country teams at Post in Brazil, Indonesia, Kenya, Nigeria and South Africa flag any additional country-level risks to the central DAP teams as and when relevant. Risks are discussed at fortnightly x-HMG DAP update meetings as appropriate and reviewed in detail at the quarterly Programme Management Committee meeting.

At the senior oversight level, risks are reviewed as part of quarterly as well as ad hoc Senior Governance Committee meetings by the programme SROs, who regularly liaise with the senior leaders (HoMs / DHMs / Economic Counsellors) in the five posts. A detailed cross-pillar risk register is kept up-to-date by the Pillar 1/lead team and shared with Pillar 2 and 3 colleagues at least once a quarter for their inputs. The revised version is reviewed at each quarterly meeting of the Programme Management Committee. The level of detail and assessment of DAP risks has been considered fit-for-purpose and aligned to best practice by internal departmental QA, e.g. by the FCDO and DSIT annual Statements of Assurance processes.

This Annual Review has confirmed the overall risk rating of the Digital Access Programme at Moderate, as in previous reviews. This reflects the most up-to-date risk analysis, and is in line with the full risk register (further updated in AMP in June 2024, in consultation with programme managers, lead advisers and SROs from across the three pillars of the DAP programme, and the five country teams at post).

The continued rating at Moderate is mainly the result of the coordinated effort by FCDO and DSIT staff from across the three programme pillars to mitigate risks posed by internal and external factors in FY 2023/24 (internal reorganisation following FCDO merger, development of new strategies, i.e. IDS and ITS, delays in the three-year Spending Review and subsequent BCP process), in conjunction with an established joint programme narrative for internal and external stakeholder engagement and comms. Our collaborative cross-Whitehall working practices greatly contribute to the effective delivery of the programme, and the mitigation of operational and reputational risks. Delivery risks continued to be managed by close monitoring, robust design, procurement and reporting processes, thorough due diligence assessments, and expert country-level presence (DAP teams at post) staying close to the delivery chain. There have been additional reputational risks generated by the ODA pause and ODA cuts in FY2023/24, as well as the further budget reductions in early FY2024/25. These have been particularly severe, but the DAP governance structure, through the central teams and senior leads at post, has proactively managed these risks by communicating sensitively with key stakeholders in-country and agreeing a manageable plan for project scale-downs and deferred payments, where relevant and feasible, with local and international partners. Where applicable, in-kind contribution from government stakeholders and from global partners (e.g. ITU, British Council, APC) have been leveraged to further manage both delivery and financial default risks.

COVID-19 direct and secondary impacts risks have been closed. The central team, country teams and external implementing partners make good use of technology to ensure delivery if impacted by COVID can be made virtual and follow country guidance should there be another COVID breakout. The programme resilience allows for quick change in partner activity to ensure maximum impact of ODA funds.

Below is a short summary of current top risks, and relevant mitigation measures:

Impact of challenging and deep ODA cuts generate delivery, operational and reputational costs, and damage, leading potentially to loss of stakeholder buy-in and programme impact.
The programme has gone through several cycles of SR, budget cuts, COVID and spend deferral from start of implementation. Central team work closely with wider departmental corporate team to ensure the programme is well represented at board level during SR process and ODA cuts exercise. Central team liaised regularly with country leads and explained the SR and budget cuts process and started to manage expectation from an early stage. External partners were given high level updates on these processes and what the various scenarios could look like. Overall budget cuts were managed in an agile way to ensure total spend aligned with the forecast.

Misuse of funds or fraud by implementing partners and relevant organisations in the delivery chain.
Robust financial management procedures and programme management processes adopted to prevent fraud and misuse of funds and implement a zero-tolerance approach, including robust due diligence procedures, close monitoring, and suitably hands-on oversight of programme by qualified teams, including country-level leads. From experience of first four years of implementation, and based on randomised project-level audits, the SROs are reassured that the programme is well set up to continue performing well in the management of fiduciary risks.
Full detail of risks and mitigation measures is available in the up-to-date DAP cross-pillar register in AMP.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Financial performance
Date of last narrative financial reports	June 2024[47]	Date of last audited annual statements	June 2024[48]
[47] The DAP works with several local and international implementing partners. The most recent financial and narrative reports from DAP projects have been submitted to the SROs in June 2024.
[48] The DAP works with a wide range of implementing partners through its three pillars. Audited annual statements are required for each project funded by the DAP - as specified in relevant agreements - with the most recent statement submitted in June 2022 and other statements submitted at different cut-off dates depending on project timelines.

Summary of programme finances

Timeline	Allocation and forecast/spend / (by programme pillar)	Total spend/forecast
FY2018/19 – FY2022/23 / (business case approved budget)	DFID Pillar 1: up to £60m / FCO Pillar 2: up to £15m / DCMS Pillar 3: up to £7.5m	Up to £82.5m[49]
FY2018/19 (spend) / (Diagnostic Phase)	DFID Pillar 1: £313,201 / FCO Pillar 2: £551,751 / DCMS Pillar 3: £330,824	£1,195,776
FY2019/20 (spend) / (start of Implementation Phase)	DFID Pillar 1: £2.47m / FCO Pillar 2: £1.1m / DCMS Pillar 3: £1.24m	£4,810,000
FY2020/21 (spend)	FCDO Pillar 1: £11,585,000 / FCDO Pillar 2: £2.6m / DCMS Pillar 3: £1.78m	£15,965,000
FY2021/22 (spend)	FCDO Pillar 1: £8,000,000 / FCDO Pillar 2: £4,499,217 / DCMS Pillar 3: £2.232,951	£14,732,168
FY2022/23 (spend)	FCDO Pillar 1: £5,580,637 / FCDO Pillar 2 CSSF: £4.5m / DSIT Pillar 3: £1,782,869	£11,863,506
FY2023/24	Cross-pillar ODA: £8,666,145 / Pillar 2 CSSF: £1,458,000	£8,124,145
FY2024/25 (forecast)	Cross-pillar ODA: £10,580,018 / Pillar 2 CSSF/ISF: £3,722,345	£14,302,363
[49] ‘Up to’ total as per SoS-approved Business Case. Based on current SR figures, it is foreseen that the programme will only receive and spend up to 75% of its originally allocated budget.

Financial Update at end Q4, FY2023/24

Table 1: DAP Pillar 1
Expenditure YTD	£5,580,637
Forecast spend	£5,580,637
In-year allocation	£5,580,637

FCDO Pillar 1 spent exactly 100% of the funds from the in-year allocation, showing excellent alignment to forecast, as in previous financial years. The spend was driven by: (a) accountable grant agreements and MoUs with non-commercial entities for multiple digital inclusion projects in the individual DAP countries and five cross-country projects with global partners; (b) service contracts with private sector providers to deliver TA to key stakeholders in partner countries on digital access policy and regulatory frameworks, as well as consultancy support to DAP country teams at post on project design and delivery.

The FCDO Pillar 1 central team liaised with country teams, local and global partners on a regular basis to ensure forecasting and utilisation of the funds were accurate. The reduced amount of funding meant we had to re-align projects to budgets and redouble our efforts to extract maximum VfM from limited resources. We were able to have direct control over the finances as we co-designed on project proposals and relevant budgets with partners and contributed our expertise in selecting delivery models and focusing on activities that would have the most systemic impact. The Pillar 1 team arranged quarterly project steering committees with each implementer, and worked closely with DAP country leads and relevant stakeholders to streamline and accelerate interventions.

Table 2: DAP Pillar 2 (CSSF)
Expenditure YTD	£4.5m
Forecast Spend	£4.5m
In-Year Allocation	£4.5m

The spend of Pillar 2 is driven by the contract with the main implementing partner for this component, KPMG. The remainder of the budget covered FCDO staff costs for the central programme management team and DAP advisers and country leads based at post in the five partner countries. Pillar 2 achieved 100% spend of its allocation in FY 2023/24.

Table 3: DAP Pillar 3 (Tech Hubs)
Expenditure YTD	£1,782,869
Forecast spend	£1,782,869
In-year allocation	£1,782,869

The spend of Pillar 3 is driven by the staff costs for the five Tech Hub teams at post, and by country-specific as well as cross-country service contracts and grant agreements on individual projects. Pillar 3 achieved 100% spend of its allocation in FY 2023/24.

Delivery and commercial performance
For the overall DAP (Pillars 1, 2, 3), the control of the programme budget is held at the centre (as a centrally-managed programme). Any commitments and subsequent payments are made with endorsement of the Programme Management Committee, having discussed the need for specific projects and relevant spend with country teams, in strategic alignment with the country plans.

All service contracts, accountable grants and MoUs are SRO-approved, and the majority of projects are procured, managed and overseen from the centre, with country teams working on intervention design, technical content, stakeholder management and in-country monitoring. The central teams (SROs/LAs/team leaders/advisers) provide strategic and technical QA and guidance to country teams. Due-diligence assessments (DDAs) are carried out for each partner (local or international) entering into contracts or agreements with the DAP, in alignment with current HMG rules. A few small-scale activities are handled locally, such as logistics, supplies and organisation of events. This set-up ensures a suitable level of oversight and support by the accountable teams to ensure that funds are spent economically and efficiently, and that outcomes of the spend are effective and equitable.

For cross-pillar projects, the in-house concept notes are evaluated by x-HMG central committees at programme manager and technical adviser level, and endorsed by SROs to approve co-funding across pillars. Feedback is provided to DAP country teams (including Tech Hubs) on strategic focus, technical content, delivery model and VfM; and support is provided from HQ teams for the further refining of concept notes. Once these have been finalised and the delivery model selected, the relevant procurement tender or call for proposals (CfP) processes kick in.[50]
[50] For all organisations we enter into agreements or contracts with, we carry out detailed due diligence assessments (DDAs), produce SRO-cleared reports, and keep them on record.

Pillar 1 and Pillar 2 service contracts were awarded through tender processes and accountable grants were awarded through CfP processes during the period under review. Both types of proposals were evaluated by DAP central or central/country committees on technical and value for money criteria through separate sub-teams. We further co-developed proposal(s) to ensure we get best value for the selected bids. In some cases, justified by the unique mandate of the potential implementing partner and strong fit with the current needs of the programme, the programme teams consider speculative proposals or proactive co-creation of projects with the partner. This approach is only applied to non-profits and NGOs, entails rigorous scrutiny of overall approach, narrative proposal and budget, and through co-design it provides a high level of control and influence by the DAP team over the way the project is designed and delivered. Single-sourcing rules and processes are followed closely and wherever relevant.

During the period under review, Pillar 1 has continued to apply its tried and tested blended delivery models, combining in-house expertise with direct delivery working closely with local implementing partners in the five DAP countries; and scaling up the cross-country projects with global partners (ITU, DSA, DIAL, British Council – respectively on telecom regulation, spectrum management, digital transformation advice and capacity building, and digital skills development) to complement the ongoing cross-country work by global partner APC on community networks. Pillar 1 also initiated a new multi-country partnership project on digital standards with BSI[51]. The flexibility and versatility of this blended delivery model has allowed for full and timely spend in all DAP countries for both FYs in the programme implementation period so far.
[51] BSI = British Standards Institution

Following its move from the Prosperity Fund to CSSF[52] funding in FY2020/21, Pillar 2 continued to align to CSSF guidance, including on procurement processes. Previous decisions were in most part not affected, and the team worked to sync processes and practices with CSSF rules - including with respect to results frameworks, project-level ToCs and job descriptions. Regarding the latter, Pillar 2 worked closely with Pillar 1 (DAP lead team) so that job profiles of DAP country team members could be adapted to reflect CSSF requirements while retaining the strategic thrust required by the overall DAP in-country.
[52] CSSF = Conflict, Stability and Security Fund

In Pillar 3, local procurement processes for small-scale projects that complement in-house delivery are delegated to the Tech Hub teams at Post. These identify opportunities, design ToRs and procure the services of local suppliers following FCDO commercial guidance and working with local procurement teams, with oversight and support by the DSIT team. The Tech Hubs’ business planning is a collaborative process with the central programme team members, who assess and approve projects based on concept notes that provide evidence of ToC alignment and expected outcomes.

The DAP continued to delivery multiple cross-pillar projects during FY2022/23, in order to achieve joint digital inclusion objectives across two or more components. Where applicable, one of the pillars led on the procurement, in order to streamline procedures and minimise transaction costs. For example, Pillar 1 issued accountable grant agreements with non-profit implementers for cross-pillar projects with Pillar 3, following required selection processes and due diligence assessments.

(c) Value for Money performance

This section includes a quantitative and qualitative analysis of VfM, adopting the same approach as in the last two AR reports; and uses the evidence tracked during the past twelve months at country level and per project to calculate the value of key indicators across the pillars, and provide some practical examples. To note, the overall programme VfM analysis is jointly presented here to avoid repetition of information across the three pillar-specific outputs in Section C of this report, given the shared VfM approach and the similarity of examples across pillars.

During the period under review, Pillar 1 successfully delivered on 32 country-specific and multi-country projects across the five DAP countries – all of them aligned to a clear strategy of systemic change combined with supply- and demand/user-side support (as outlined in the relevant DAP CLIPs).

Pillar 2’s main implementing partner (KPMG) started the implementation phase of key projects in June 2021, worked closely with FCDO on monitoring and VfM, and issued invoices on completion of pre-agreed milestones in each project. KPMG completed delivery of DAP Pillar 2 in Quarter 3 of financial year 2022/23 and delivered a completion report on 18 January 2023. Pillar 2 completed 15 new projects delivered through KPMG - three in Brazil, three in Indonesia, four in Nigeria, three in South Africa and two in Kenya.

Economy

Procurement

Across the DAP, service contracts were awarded through tender processes and accountable grants were awarded through CfP (call for proposals) processes in the past 12 months (as in previous years). Both types of proposals were evaluated by DAP central or central/country committees on technical and value for money criteria. For service contracts under Pillar 1 and 3, we procured through existing central HMG frameworks where possible, in order to economise on costs of direct market engagement. Selected small-scale service contracts at country level were procured through the relevant commercial teams at post or through the HMG Regional Hubs as relevant. Central teams always retained control and accountability by reviewing contracts and budgets, and providing SRO approval for relevant spend. This allowed the central programme team to verify VfM criteria before any contract was awarded.

Consultancy rates

All the DAP Pillar 1 projects during the period under review used local specialists (who bring better local-level knowledge) which led to consultant day rates being significantly contained. We have systematically contracted locally-based experts, mostly avoided international travel (also due to the pandemic) and put a cap on number of in-country trips (proportionate to project needs, and in line with country-specific COVID-19 protocols still relevant in early 2022). We have used local procurement routes wherever possible, to leverage local knowledge of the consultancy markets and sensitivity to local costs and trends.

Pillar 1 only uses an intermediary consultancy company (through an existing framework) where necessary and whenever more economical (comparing rates across an appropriately wide range of offers) and efficient from the perspective of contracting processes and transaction costs. In both cases, the Pillar 1 central team monitors closely and approves rates that are proportionate to local market conditions and justified by the seniority, experience and qualifications of the consultants, going through a rigorous screening of CVs, TA package proposals and financial offers.

Example - The total value of Pillar 1 country-specific service contracts during FY2023/24 was £411,755. The average national expert fee rate was £285/day and international expert fee rate for a comparable level of experience and qualifications was £450/day. Prioritising working with local experts - where appropriate and feasible - provided a saving of £148,231 i.e. over 36% saving in consultancy costs over one year when compared to the consultancy assignments being conducted exclusively by international experts. This was assessed as excellent VfM: besides conducting the relevant assignments at the expected level of quality, the involvement of local experts provided the added benefit of deep knowledge of the local context and established networks with relevant stakeholders in-country. The amount saved on consultancy rates was reinvested in extending ongoing projects to achieve additional results or deployed for other digital inclusion activities in the country (through other service contracts or accountable grants, depending on suitability of delivery model).

Travel and logistics costs

Travel was kept to a minimum during the annual review period as in most partner countries pandemic risks were still at a critical level. However, where applicable and as in previous FYs, close monitoring of hotel rates, allocations and guidelines for in-country as well as international travel (for example, strictly observing FCDO rules on class of travel or maximum daily rates for accommodation), choice of venues for trainings and workshops, criteria for approval of refreshments, meals and stationery costs at events, all contributed to ensuring an economical approach to the delivery, management and monitoring of activities.

Example - The initial Pillar 1 FY2023/24 forecast for international travel, logistics and accommodation was approximately £150,000 to keep in line with previous years’ travel forecast. Central and country teams liaised regularly over teams call to discuss and enhance capability of the team therefore travel was only approved if it was a critical business need. This was a saving of 46% and the overall travel and expenses for the period under review was £69,000. This resulted in further £81,000 being re-invested to project activities.

Salaries and associated staff costs

Since programme inception, programme staff have been selected in line with the DAP business case HR plan. Minor adjustments were made to adapt to country contexts and relevant labour markets, to ensure an economical approach to recruiting and retaining staff with the appropriate qualifications and experience.

Example - The total cost of staff salaries and associated costs for the DAP was £1,179,176 across three pillars. The Tech Hub network across the five DAP countries amounted to £536,563, a cost fully justified by their direct implementation role as tech specialists recruited from the industry.

Contract management

Pillar 2’s service contract with KPMG as main implementer for this DAP component includes a Value for Money strategy which sets out in detail how KPMG is expected to apply the 4 Es approach throughout the contract period, including defined roles and responsibilities, and evaluation metrics. The Pillar 2 main implementer contract is based on a payment-by-results mechanism and includes open-book data requirements. KPMG invoices FCDO once milestones are completed and approved by the DAP Pillar 2 lead team.

Delivery

During the design of Pillar 2 new projects for FY2023/24 (part of the KPMG contract), we set a limit of £800/day for any project, to incentivise allocation of staff at an appropriate level of seniority (and therefore cost). In all projects under the KPMG contract, we have reinvested unspent travel costs into additional remote delivery or delivery through local sub-contractors. We have also ensured that delivery and decision-making is managed economically within the FCDO DAP team, using relevant delegated authority limits.

Efficiency

The DAP teams have leveraged their blend of in-house and direct delivery models to increase the efficiency of project delivery: by using the skills and experience of specialist advisers at centre and country level to deliver value to key stakeholders; and by engaging directly with local implementing partners through local calls for proposals, tender processes or (in selected cases) project co-creation, always followed by a phase of design and development that would finetune project strategy and budget to maximise VfM before signing the relevant agreement. This has allowed the DAP to deliver a significant number of strategic projects and conducting policy dialogue processes, while reducing the need for intermediation and visibly increasing the efficiency of the programme.

Number of consultancy days per TA package: DAP central teams work closely with country teams in the design of ToRs for TA packages required for local projects to ensure timeframes and number of days are proportionate to expected deliverables and maximise efficiencies.

Expertise level required for project delivery: in combination with the above, efficiency is also being driven by central and country teams through systematically assessing bids (CVs, project proposals, commercial offers) to ensure qualifications and experience levels are adequate while avoiding over-qualification.

Budget design and type of costs eligible for grant-funded projects: central teams also work with country teams on both indicating clear criteria for costs eligibility in local CfPs or during project co-creation processes with local partners (for example: the DAP does not cover cost-intensive infrastructure, technology or connectivity budget items).

Project-level budgeting, reduction of overheads: Previous AR recorded maximum threshold of 5% overheads for projects implemented by external partners. For FY2023/24 there was a total of 31 Pillar 1 projects and by working with some existing partners DAP managed to reduce the overheads average down to 4.5%.

Example - While the total overheads for Pillar 1 in FY2023/24 across project budgets would have totalled £420,000, we worked closely with partners and country advisers to identify ways to reduce costs and increase efficiency of resource use. Total overheads were therefore reduced down to £235k, which generated a saving of £185K and a conversion rate of 44%[53]. The latter figure was reinvested in direct projects costs and supported additional activities and results.
[53] Rate at which savings on overheads get converted into direct project costs.

Programme-level overheads to total/direct costs ratios: Since programme inception, the overall DAP has been maintaining an excellent VfM performance in terms of ratios between overheads to direct or total programme costs.

Examples – Admin costs for the DAP Pillar 1 for FY2023/24 amounted to £119,667 (salaries, platform costs, travel and logistics). This was against £5,580,637 as the total programme spend. Based on these figures, DAP has been monitoring a basic VfM indicator for efficiency, finding the value within the set thresholds (see below).

Another example of efficiency indicator is the ratio between total overheads and total direct costs. Below are the values for Pillar 1 for FY2023/24, which also remain well within the set thresholds and demonstrate great VfM performance:

Effectiveness

The DAP continues to maximise the cost-effectiveness of its interventions using a three-step approach:
1. closely evaluating project and budget proposals and the correlation between them;
2. monitoring project spend as it progresses;
3. practicing flexible programme management, e.g. reallocating resources to different budget lines within a project if there are robust cost-effectiveness reasons to do so.
The programme does not fund infrastructure, technology or equipment costs as the emphasis is on facilitating systemic change rather than investing directly on initiatives that would be financed more sustainably by local governments or by the industry. This approach has proven to be very cost-effective over the first three years of implementation of the DAP. The main cost drivers in relation to the effectiveness of the programme are technical assistance and capacity building to develop the models and enablers of digital development in order to facilitate lasting and sustainable improvements within local eco-systems. To consolidate the impact and sustainability of spend, the central teams provide advice and guidance to country teams and implementing partners in designing activities that amplify the impact of the programme and extend the longevity of its results:

- by working on scalable models, rather than stopping at direct delivery in a limited number of communities;
- by focusing on building capacity for the future, adopting approaches such as ‘Training of Trainers’ (ToT) and coaching beneficiaries or stakeholders that can replicate useful activities within the ecosystem;
- by supporting systemic elements like regulatory reforms and institutional strengthening on crucial drivers such as affordable connectivity technology and business models that are instrumental to expand digital inclusion of underserved groups across a country.

The DAP also seeks to establish sustainable in-country ownership of projects/interventions, to embed changes within governance structures and in-country networks.

The DAP central teams have been monitoring the programme’s cost-effectiveness in terms of outreach cost per I can, a VfM indicator that is suitable to the current implementation stage of the intervention. It should be noted that types of projects and activities, as well as country or local contexts, as well as beneficiary groups, vary greatly across the DAP and even within each pillar. However, there is merit to observing how ‘cost per beneficiary’ is evolving in the life of the programme, varies across programme countries and what its average value is.
Additionally, under Pillar 2, effectiveness has been maximised through central management, the design of individual projects, and the way projects are delivered:

- An agile approach to central management of project funds allocated 70% of the total budget to projects during the inception phase, then allocated the remainder after the first months of full implementation. This allowed to extend projects that had proven particularly successful, increasing the component’s effectiveness.
- Projects that would maximise effectiveness were specifically selected, e.g. those which have a catalytic effect and can be scaled up after the end of the DAP intervention. For example, the project on cyber curriculum for Brazilian schools has scaled from one to three states and is due to be expanded nationally after the end of DAP support. During the design phase of all projects, the team considered how to enhance long-term effectiveness e.g. by ensuring local stakeholders have ownership.
- The Pillar 2 team has worked with the main supplier KPMG to select appropriate local partners to deliver projects adapted to each country’s context, support the local cyber services ecosystem and often driving better VfM.
Below is a summary analysis and some examples of VfM cost-effectiveness calculations across the three pillars of the DAP.
Cost per beneficiary in FY2023/24

DAP digital inclusion projects	Project spend (£)	Beneficiaries	Average cost per beneficiary (£)
Projects directly improving connectivity, digital skills, content and services for beneficiaries in Kenya, Nigeria, South Africa, Brazil and Indonesia, implemented through local and global partners.	5,049,646	2,246,004	2.07

The above calculation refers to projects implemented during the period under review, focused on directly reaching local beneficiaries in underserved communities to improve their digital inclusion through more affordable connectivity, digital skills development and access to locally-relevant digital content and services, tailored to the needs of last-mile low-income communities and marginalised groups. The average cost per beneficiary across the five countries (£2.07) in all digital inclusion projects directly affecting individual beneficiaries, and implemented through local and global partners, represents excellent VfM.
This is an average calculation across the five countries, but local averages differ depending on socio-economic and institutional context, the maturity and size of the project portfolio in each country, the extent to which digital outreach was effectively viable and allowed for lower unit costs and rapid scale-up (e.g. in Kenya), as well as challenges of complex geography and security costs in unstable regions (e.g. in Brazil, Nigeria). Another variable affecting cost per beneficiary is the baseline capacity of communities and consequently the appropriate different levels of training, capacity building or TA delivery. Overall, this summary analysis demonstrates great VfM and the Pillar 1 team continues to monitor both risks of fallback and opportunities for further improvement.

Equity

As stated by the DAP External Evaluation final report, “Equity is in the DNA of the DAP”, given its overall goal and results achieved so far on increasing inclusive digital access and ‘leaving no-one behind in a digital world’. Programme spend is fully targeted on supporting the digital inclusion of underserved communities. This approach is based on the analysis generated by the digital access country diagnostics carried out by the DAP team, which considered the specific challenges faced by excluded groups due to multiple factors, e.g. gender, age, disability, ethnic origin, socio-economic status, remote location. During the period under review, the DAP has consolidated this approach and achieved some robust results, as outlined below.

Gender & Inclusion in the DAP

Gender and inclusion considerations have been built into the design of each DAP intervention. Following a recommendation by the DAP external evaluators in late 2020, the DAP team systematised its G&I approach in a set of guidelines tailored to digital development interventions following a consultation across the DAP network. The guidelines are now formally adopted by the Programme and applied to each DAP intervention.

DAP projects put significant emphasis on equity, and the need to reach female beneficiaries, as well as persons living with disabilities (PWDs). The DAP central programme teams work systematically with country teams to ensure the design of projects, CfPs and ToRs for tenders, employ a fully inclusive approach, e.g. by addressing specific issues such as the gender digital divide or the gender bias in the tech sector; or the digital exclusion of PWDs; and the need for affordable last-mile connectivity to reach out to underserved rural or low-income peri-urban/urban communities.

Practical results are evident. One such example is the DAP project with the Association for Progressive Communications (APC). Following recommendations from the DAP central team, APC now has at least one woman as leader or co-leader in every community network supported by the project. Gender-disaggregated results are also being monitored through DAP MREL framework indicators. DAP Nigeria has supported the Federal Government to develop a dedicated policy to reduce the Digital Gender Gap (DGG) to 10% by 2025, which will extend meaningful digital access to more than 5 million women. The programme is also supporting a policy to extend affordable digital access to 70% of the population, with special consideration to people living with disabilities (PWDs). During FY2023/24, DAP Kenya completed projects with local organisations specialised in supporting the digital inclusion of PWDs, e.g. InAble and APDK. The latter and ICTA also worked with DAP Kenya to enhance the accessibility of government digital services for PWDs during the period under review.

The main implementer for Pillar 2, KPMG, has been working with a specialist gender and inclusion consultancy (Social Development Direct) to ensure gender and inclusion considerations were integrated into each project at design stage. Some projects specifically target gender and inclusion outcomes e.g. training female-owned SMEs in cyber essentials; and designing school-based cyber awareness training in a way that is sensitive to how different groups experience cyber harms. To strengthen SME cyber awareness in South Africa, we developed a bespoke cyber awareness toolkit and worked in partnership with South African incubator WomHub to train 10 female-owned SMEs as facilitators and disseminate the toolkits across their networks.

Equitable approaches to gender and inclusion have been built into the design of all Tech Hub interventions and into the MREL framework for Pillar 3. The DAP has supported a cross-pillar multi-country project fully focused on female entrepreneurship, following a successful pilot of this model in South Africa.[54] Since originally partnering with the UK-South Africa Tech Hub in FY2018/19, this collaboration has been scaled up.
[54] The Future Females Business School is a three-month virtual accelerator initiative, that combines a proven training methodology, with coaching, mentoring and peer-to-peer learning, to equip female entrepreneurs with the entrepreneurial skills and best practices needed to start and grow successful and sustainable businesses, that utilise technology to have a positive impact in their community and environment.

Equity VfM analysis

VfM analysis of the ‘equity’ dimension includes considering the cost effectiveness of projects with an emphasis on or fully dedicated to inclusion – e.g. gender-focused or PWD-focused interventions. The DAP’s work in Kenya is a good example of equity-related VfM, where women and people living with disabilities have been the main beneficiaries of multiple projects, e.g. the DAP Kenya initiatives with local partners ACWICT and APDK. DAP’s projects in Indonesia focusing on maternal health and women-led community radio initiatives in remote communities demonstrated great VfM from the equity perspective because of their delivery models, cost structures and results achieved.

Below is a summary VfM analysis of the equity when the project is specifically targeting female and people living with disabilities.

Pillar 1 - Cost per female beneficiary
  (based on sample of women-focused FY2023/24 projects)
Total Spend on / gender-focused / projects / components	Total female beneficiaries	Cost per female beneficiary
£ 458,500	435416	£1.05

Pillar 1 - Cost per PWD beneficiary
  (based on sample of PWD-focused FY2023/24 projects)
Spend on / PWD-focused / projects / components	Total PWD / beneficiaries	Cost per PWD beneficiary
£551,747	510,000	£1.08

The average cost of reaching beneficiaries with PWDs has been reduced by 17% thanks to economies of scale generated by the expansion of successful interventions with the same implementing partners.

________________________