## Annual Review Template

Title: Nepal Climate Smart Development Programme
Programme Value £ (full life): £58.5 Million (This includes a £8.5m cost extension via a Business Case Addendum.)		Review date: August 2025
Programme Code: 204984	AMP start date: / 6 October 2016	AMP end date: 31 March 2026 (BC addendum received 1 year time no cost extension)

Summary of Programme Performance
Year	2017	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A	A	A+	A+
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	Business Case	Addendum to Business Case
DevTracker Link to results framework:	Logical Framework

A. SUMMARY AND OVERVIEW

Description of programme
The Nepal Climate Smart Development Programme (CSD) is a £58.5 million strategic portfolio programme. The majority counts as International Climate Finance (ICF). The programme supports Nepal’s resilience to the impacts of climate change and enhances low carbon development. This is delivered through technical assistance (TA), Financial Aid (FA) and Viability Gap Funding (VGF) to support national policy reform and demonstration of adaptation and mitigation actions on the ground, as well as leveraging of public and private financing.
The programme started in October 2016 and is scheduled to end in March 2026. By March 2025, many of the original components had been closed. During this annual review period (July 2024 to June 2025), the following components were under implementation: Nepal Renewable Energy Programme (NREP both TA and FA), Nepal Green Hydrogen Market Opportunities (Green Hydrogen) project, Strengthening of Nepal Electricity Authority (NEA) Capacity on Environment and Social Safeguards (NEA’s E&S Safeguard) project, and Himalaya Resilience Enabling Action Programme (HI-REAP) manged by IIOD (India and Indian Ocean Directorate) under CARA (Climate Action for a Resilient Asia). The Nepal Climate Change Support Programme (NCCSP2) though active was in the process of closure.
Currently, implementation wise only the Green Hydrogen project and the FA component of NREP are active and are scheduled to continue until December 2025 and March 2026, respectively. The NCCSP2 completed its implementation on the 30th of June 2024 and initiated its closure from July 2024, with the contract ending in January 2025.
Nepal Climate Change Support Programme (NCCSP2) supports local governments (provincial and municipal) to mainstream climate change within development planning and investments to improve the resilience of climate vulnerable communities. This is the second phase of the programme and is implemented by local governments with TA and FA support through Pegasys and with Mott MacDonald (MM) as the downstream partner. The total programme value is £23.1m, including 16.4m FA and £6.7m in TA to support this. NCCSP2 successfully concluded implementation in June 2024, and closure occurred by 31st January 2025 with the submission of a Programme Completion Review (PCR). Some of the lessons to take forward included: reticence of government to incorporate climate financing models others than budgetary support; and benefits of using AI to tailor detailed designs for the climate change adaptation infrastructure projects could improve cost efficiencies. Achievements included submitting Detailed Project Reports (DPRs) to local governments (LGs) to help them mainstream climate adaptation, and prioritisation of adaptation plans by LGs in Karnali Province. More will be covered in the CSD PCR.

1. Nepal Renewable Energy Programme (NREP) aims to increase energy access, energy security and energy transition for improving productivity of businesses by developing the market for the small-scale distributed sustainable energy (DSE) technologies. The TA component of the programme was implemented by a consortium led by DAI Europe (DAI-E) and concluded in March 2025. The FA for the Sustainable Energy Challenge Fund (SECF) is being implemented by Nepal Governments Alternative Energy Promotion Centre (AEPC) through the Central Renewable Energy Fund (CREF). Over the lifetime of the programme, a total of £9.24 million was allocated for TA with total spend of £8.72 million at the end of the TA, while £8.76 million was allocated for FA with total spend will be estimated £4.77 million by end of the FA period. The FA component will end in March 2026.
2. Green Resilient and Inclusive Development (GRID) supports Nepal’s development agenda based on the GRID framework building on the Kathmandu Declaration signed in September 2021 to mainstream environment friendly, climate resilient and inclusive development. It is implemented by the World Bank, through an EFO (Externally Financed Output). The budget for the project was £500k. Most implemented actions under the supported GRID Strategic Action Plan (SAP) remain in effect e.g. 1% green tax on fossil fuels. Provincial coordination and GRID communication tools were also developed and are on the GRID website.
3. Nepal Green Hydrogen Market Opportunities (Green Hydrogen) project aims to enhance the green hydrogen sector in Nepal and develop key stakeholders' capacity for advancing the green hydrogen sector in Nepal. It is implemented by the World Bank, through an Externally Financed Output (EFO). The budget for the project is £1.34 million.
4. Strengthening of Nepal Electricity Authority (NEA) Capacity on Environment and Social Safeguards (NEA’s E&S Safeguards) project aims to build capacity of NEA and its subsidiary companies- the Dudhkoshi Storage Hydropower Project and Upper Arun Hydroelectric Project on E&S safeguards and develop a user-friendly Environment and Social Management System (ESMS) for NEA. It is implemented by the Asian Development Bank (ADB), through a Memorandum of Understanding (MoU) with the Asian Development Bank (ADB). The budget for the project is £500k.
5. Himalaya Resilience Enabling Action Programme (HI-REAP) is a component of the Climate Action for a Resilient Asia (CARA) programme that aims to implement a set of activities in Nepal focused on nature-based solutions for disaster risk reduction, agroecosystem resilience, and air quality improvement. The programme is implemented by the International Centre for Integrated Mountain Development (ICIMOD) and represents a £1 million contribution from the British Embassy Kathmandu (BEK) to the CARA programme. This project will be separately reported under CARA.

Summary supporting narrative for the overall score in this review:

The overall score for the CSD programme for this year is ‘A+’ (outputs met expectations).
Some of the achievements supporting the overall score in this review include:
With NREP’s technical assistance, the AEPC/CREF has fully institutionalised Sustainable Energy challenge Fund (SECF) systems and processes to provide viability gap funding to private sector-led sustainable energy projects. Since NREP’s technical assistance ended in March 2025, AEPC has continued to manage the funds effectively. The SECF received strong interest from the private sector, with over 300 concept notes received. 68 projects have been implemented, mobilizing around £10 million in private finance and £1.41 million in public finance. These projects have installed around 17 MW of renewable energy systems, 38 Electric Vehicle (EV) charging infrastructures projects and 6 innovative projects benefiting over 121,000 people and 72 Micro, Small & Medium Enterprises (MSMEs).
The Green hydrogen project, led by the World Bank and delivered with Butwal Power Company (BPC), is on target to conclude by December 2025, under an agreed extended deadline. The revision was required after some delays due to the complexity of the first private sector led - and largest - green hydrogen pilot project in Nepal and World Bank procurement. That said, government approval and tax exemption have been secured for import of the parts for a 200kW pilot green hydrogen project. The outcome will be clean energy for use in large-scale industries or hospitals. As of October 2025, construction was planned to conclude by end-December 2025. In addition, various sectoral studies - such as a demand market assessment - and capacity trainings of government have been completed.
The NEA’s E&S Safeguard project successfully developed and submitted the Environmental and Social Management System (ESMS) for NEA, including policy gap analysis, E&S safeguard policy, institutional structure, and E&S management plan. A total of 250 NEA staff were trained through the capacity building workshops and training and specialized training modules and a female-focused session was carried out to enhance inclusivity. Key documents such as the Labour Management Plan, Biodiversity Offset Plan, and Resettlement Plan were prepared for the Dudhkoshi hydropower project.

Major lessons, recommendations and actions taken from the past year:
Last year’s lessons learned and recommendations for NREP included: strengthening AEPC; manage private sector expectations, and support efforts to secure funding from development partners, climate funds, and public sources beyond the NREP period. Based on these, NREP provided TA to build institutional capacity, and successfully handed over relevant projects and processes to AEPC/CREF. Upon NREP’s technical support end in March 2025, AEPC/CREF has taken full responsibility for implementing SECF. Transparent communication regarding project timelines and budget availability ensured smooth engagement with private sector stakeholders, with no complaints reported, although further financial support from FCDO was requested. AEPC successfully influenced KfW to mobilize additional funding in support of SECF pipeline projects. KfW has committed EUR 9 million to AEPC for solar energy initiatives, and this commitment has now been extended to include SECF solar rooftop pipeline projects under the generation-based incentive (GBI) window. Furthermore, AEPC is actively engaging with development partners including the EU, GIZ, KfW, Norwegian Embassy, ADB, and the World Bank. NREP also supported AEPC in developing a $50 million concept notes for a “Green Investment Facility Nepal” to help secure funding from the Green Climate Fund (GCF).
Additionally, in line with the recommendation to raise awareness on the cost benefits of Electric Cooking (e-cooking), NREP developed evidence-based materials in collaboration with microfinance institutions, helping customers make informed decisions. Furthermore, NREP engaged with the Electricity Regulatory Commission (ERC), Nepal Electricity Authority (NEA), and Ministry of Energy, Water Resources and Irrigation (MoEWRI) to advocate for appropriate electricity tariffs. NREP and AEPC held multiple meetings with ERC, NEA, and MoEWRI to advocate for revised electricity tariffs for e-cooking and EV charging. The ERC is currently planning to revise the electricity tariff structure.
Green Hydrogen and NEA’s E&S Safeguard project work wasn’t operational last year, and so there were no lessons or recommendations to draw on.

Major lessons and recommendations for the year ahead
Lessons Learned	Recommendations	Responsibilities	Timelines
Increased and strengthened technical capacities within the local governments - specially municipalities (semi-urban areas) and rural municipalities can improve both the quality spending and delivery of climate change programmes	Work with BEK’s governance team on the Civil Service Bill to recommend required capacities within the local governments. Resourcing will be a challenge, however. / Work with RAIN partners through embedded climate experts in BEK’s priority Provinces and collaborate with Local Governments to build local capacities accordingly of existing human resources.	SRO/PRO RAIN (Resilience Adaptation and Inclusion in Nepal) team / Climate Advisor, BEK	Ongoing, subject to the Civil Service Bill / Embedding ongoing in Lumbini and Madhesh Province under RAIN (TASLU). Capacity building in FY 25/26
NREP’s support demonstrated that VGF is an effective mechanism to reduce investment risks and attract private sector participation in the DSE sector. VGF builds investor confidence by bridging financial gaps in early-stage technologies and business models. To sustain momentum in emerging DSE areas, AEPC must secure dedicated VGF resources under the SECF.	AEPC should seek additional short-term financial support from GIZ, EU, and KfW to maintain progress in the DSE sector. For long-term sustainability, AEPC must develop a SECF sustainability plan and mobilize domestic resources, climate finance, and multilateral loans. / Green Growth Nepal (GGN) or RAIN could assist in preparing the plan and proposals to access climate finance and strengthen SECF’s institutional framework.	AEPC / GGN or RAIN team	Discuss with GGN or RAIN to take this forward in FY 25/26
Affordable financing is essential for DSE companies aiming to scale. However, limited collateral often prevents these businesses from accessing bank loans. The Loan Loss Guarantees (LLG) provided by the SECF has proven effective in mitigating lending risks for banks, enabling them to support these companies. Without such financial mechanisms, these businesses will struggle to expand and sustain.	The SME Catalytic Finance Facility under Nepal in Business (NIB) could provide loan guarantees or alternative financing instruments, such as blended finance or equity support, to help DSE companies overcome collateral barriers and access capital for scaling their operations effectively.	NIB team	Discuss with NIB to take this forward in FY 25/26
Delays by NEA in implementing net-metering and providing transformers for EV charging stations, along with an unfavourable electricity tariff structure, have slowed energy transition efforts and discouraged consumers from adopting cleaner technologies, highlighting the need for timely coordination, infrastructure support, and policy reforms.	Coordinate with NEA, ERC, and MoEWRI to ensure timely infrastructure support and design affordable, targeted electricity tariffs such as time of use rates and special slabs, to accelerate clean energy adoption and ensure cost competitiveness.	GGN team	March 2026
The lack of a dedicated tariff structure for Battery Energy Storage Systems (BESS) in Nepal poses a significant challenge to their commercial viability. Although BESS is critical for managing the intermittency of renewable energy and enhancing grid reliability, the current tariff framework does not account for the additional investment required. This gap discourages adoption, despite the declining cost of battery technologies.	The ERC should develop a dedicated tariff structure for BESS to reflect their unique role in enhancing grid reliability and supporting renewable energy integration. GGN could support ERC in this process by providing technical and policy guidance.	GGN team	March 2026
Nepal’s DSE sector, supported by NREP, demonstrates strong potential to attract foreign direct investment (FDI) and funding from development finance institutions (DFIs). For example, NREP directly funded Simple Energy Pvt Ltd., a solar company that secured DFI investment (InfraCo). More broadly, British Investment International (BII), IFC, and MetLife have supported a landmark $60 million local currency green bond issued by NMB Bank to unlock investment in solar energy and EV infrastructure. To scale such investments effectively, Nepal requires a more favourable policy environment and strengthened institutional frameworks.	GGN could promote investment in distributed sustainable energy by advocating for supportive policies, strengthening institutional capacity, promoting investment readiness, supporting green financing mechanisms, and facilitating partnerships with international investors to unlock the sector’s potential and attract FDI and DFI funding for DSE sector.	GGN team	Discuss with GGN to take this forward
Affordable and targeted electricity tariffs are essential to drive the adoption of electric cooking and EV charging, thereby increasing overall electricity demand. NREP and AEPC consistently engaged with the Electricity Regulatory Commission (ERC) to advocate for such tariff structures. Although ERC agreed in principle to revise the tariffs, implementation has not yet occurred.	GGN could take this initiative forward by supporting ERC in the design of affordable and targeted tariffs, including time-of-use rates and dedicated slabs for electric cooking and EV charging stations.	GGN team	Discuss with GGN to take this forward
NEA has made initial progress in implementing E&S safeguards, but further steps are needed. Approval of ESMS, development of clear guidelines, and establishment of an institutional structure are crucial. To ensure long-term success, NEA must prioritize staff training, allocate necessary resources, and integrate ESMS into its regular training programs.	ADB should continue supporting NEA in institutionalizing the ESMS including providing technical assistance for staff training, resource mobilization, and integration of ESMS into NEA’s training programs. Furthermore, collaboration between GGN and ADB could be explored to further reinforce and advance this institutionalization process.	ADB / GGN team	Discuss with GGN to take this forward in FY 25/26
Green Hydrogen: undertaking such a project in Nepal can take longer than anticipated due to the novel and complex nature of new technologies. As such procurement routes should be considered upfront to avoid potential delays through robust systems like the World Banks. Contingency time is needed.	FCDO and World Bank to continue strongly monitoring the project, including with at least one site visit before completion of the project.	FCDO team / World Bank	By November 2025
Green Hydrogen: UK visibility and branding on such a pioneering project, with strong UK financial commitment, is low. For example, NORAD’s £74k contribution is mentioned in BPCs 2024 Annual Report.	FCDO to meet with BPC to explain the significance of the UK contribution. FCDO and World Bank to organise joint senior delegation site visit, possibly for the inauguration. This work can also be linked with GGN’s work at OIBN, given a recent green hydrogen proposal submitted to OIBN.	FCDO team / World Bank	December 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Theory of Change (ToC) for CSD is: “Increased investment and improved Government planning for climate smart development” delivers the impact of planning and investment in climate resilient and low carbon development to promote and sustain economic development and poverty reduction in Nepal with an outcome of Increased investment and improved Government planning for climate smart development. ‘Climate smart development’ is defined in the programme Business Case as economic growth that is coupled with increased resilience to climate change impacts and increased uptake of low carbon technologies. There have been no changes in the impact and outcomes - Increased investment and improved Government planning for climate smart development of the CSD portfolio. Likewise, there have been no change in outputs statement as well. No outputs were planned under NCCSP2, Green Hydrogen project, NEA’s E&S safeguard project and ICIMOD’s HI-REAP.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The CSD Business case has a single outcome: Increased investment and improved Government planning for climate smart development with NREP - contributing to it this year. The outcome is measured against 3 indicators:
1. Annual volume of public and private investment in the sustainable energy sector.
2. The MOFE and MOEWRI have fully mainstreamed climate change/clean energy into all their work including sector budget tracking, monitoring, evaluation, and learning.
3. Capacity of Sustainable Energy (SE) generated and number of people, institutions and MSMEs access to the clean energy.
Against Outcome indicator 1, in the last year the NREP programme mobilized about £ 10 million of private and £ 1.41 million of public financing for sustainable energy projects. The Green Hydrogen project has mobilised £1m of co-financing from BPC.
Against Outcome indicator 2, NREP collaborated with AEPC to support the inclusion of the CREF within the Renewable Energy and Energy Efficiency (REEE) Bill to establish a strong legal foundation for the fund. As a result, Clause 31 of the REEE Bill has proposed to establish the Sustainable Energy Fund, effectively transforming CREF into this fund as per Clause 49(4), and formally recognizing CREF as AEPC’s designated financing mechanism. The REEE Bill 2081 has been passed by Nepal’s National Assembly and is currently under review in the House of Representatives.
Against Outcome indicator 3, NREP supported the installation of about 17 MW renewable energy projects against the planned 10 MW. Likewise, 121,373 people directly benefitted, compared the planned 111,000 people. However, the number of MSMEs was not fully achieved. A total of 72 MSMEs benefited, compared to the planned target of 100. This shortfall was primarily due to limited funding availability within the SECF. Field visits and stakeholder feedback show that DSE technologies like solar rooftop systems, pellet-based boilers, solar water pumping systems and EV charging stations have helped businesses to reduce energy costs, reduce air pollution and boost productivity.
NREP has made a substantial contribution toward achieving its long-term goal of promoting climate-smart and inclusive economic development by successfully mobilizing investments from both public and private sectors. Notably, several DSE enterprises that received early-stage support have expanded their operations. However, businesses aiming to introduce new DSE technologies or innovative business models continue to face challenges. These enterprises require ongoing technical assistance and targeted viability gap funding to address perceived risks and facilitate market entry.
The Green Hydrogen project plans to have built a 200kW demonstration project by December 2025. This will likely benefit clean energy use in small amounts to large-scale industries, or hospitals. As a pilot project this will also provide valuable information to the market to help green hydrogen become a viable source of energy in the future in Nepal. A South Korean company recently signed an MoU with OIBN to explore a 20MW site.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
The CSD programme has delivered strong value for money and supported UK priorities on green growth, climate change adaptation and mitigation, climate finance (public and private) and private sector engagement. The combination of FA and TA proved scalable, inclusive and transformational.
The programme is in its final year and is scheduled to end in March 2026. Its institutional legacy and financing mechanisms provide a strong platform for BEK wider portfolio. In this final year phase, there will be a focus on capturing lessons learned, with the objective of informing BEK’s new programmes. These includes Green Growth Nepal (GGN), Nepal in Business (NIB), and Resilient, Adaptive, Inclusive Nepal (RAIN), which aims to support enabling policies and implement adaptation actions and attract alternative and climate financing for climate change adaptation and mitigation and possibilities of engaging in the clean energy sector in Nepal with adaptation co-benefits.

## C. DETAILED OUTPUT SCORING

Output Title	Increased uptake of renewable energy technologies, resulting in increased economic output by Small and Medium Enterprises (SMEs) and improved energy access for poor people
Output number:		1	Output Score:	A+
Impact weighting (%):		100%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress (July 2024- June 2025)
Outcome Indicator 1: Annual volume of Public and Private investment in the Sustainable Energy Sector (excluding large hydropower).	GBP 10 million private finance mobilized for sustainable energy. (NREP Outcome indicator 2.1) / GBP 1 million public finance mobilized for sustainable energy. (NREP Outcome indicator 2.2)	Target exceeded / ~£10 million private finance and £1.41 million public finance was mobilized for sustainable energy projects with the technical assistance of NREP. / While not under NREP, the Green Hydrogen work is expected to mobilise roughly £1m in private co-investment.
Outcome Indicator 2: / The MOFE and MOEWRI have fully mainstreamed climate change/clean energy into all their work including sector budget tracking, monitoring, evaluation, and learning.	Contribute to CREF being acknowledged in Renewable Energy and Energy Efficiency (REEE) Bill (NREP Outcome Indicator 1.1)	Target has been achieved. / REEE Bill establishes a Sustainable Energy Fund, converting CREF into this Fund, recognizing CREF as AEPC’s nodal financing mechanism. The REEE Bill 2081 has been endorsed by Nepal’s National Assembly and is now under review in the House of representatives.
Outcome Indicator 3 Capacity of sustainable energy generated and number of people, institutions and MSMEs access to the clean energy. / (ICF KPI 7 and 2)	10 MW RE generated. 111,000 people, 100 MSMEs access to clean energy. (NREP outcome indicator 2.6 and 2.7, 2.8)	Target achieved – some targets exceeded and some moderately missed. / Around 17 MWp RE projects are installed and 121,373 people, around 72 MSMEs have access to clean energy solutions.
Output Indicator 2.1 Number of distributed sustainable energy projects implemented by provincial government, local government, and private sector.	30 distributed sustainable energy projects implemented with NREP support. (NREP output 2.1.1) / 3 investments made in DSE projects by subnational governments. (NREP output 1.2.3)	Target significantly exceeded. / 73 distributed sustainable energy projects have been implemented with NREP support. / 4 investments made in DSE projects by subnational governments.
Output Indicator 2.2 Clear/robust institutional roles and mandates in place for driving decentralized renewable energy (DRE) services and RE financing.	60 knowledge products – 50 social media posts on knowledge materials, 2 video documentaries, 8 success stories/articles/reports developed (NREP Output indicator 1.1.1)	Target significantly exceeded. / Around 110 knowledge products including 78+ social media posts, 8 video documentaries, 24 success stories/ case studies/ articles/ reports were developed with NREP support. These products have been shared via the AEPC and NREP websites, NREP social media and covered by national news.
Output Indicator 2.3 Domestic and international finance for climate and RE mobilized supported by MoFE/MoEWRI guidance.	One additional organisation provides funding support to a SECF-supported project. (NREP Output indicator 1.2.2) / 3 additional financial institutions that financed DSE projects supported by NREP. (NREP Outcome Indicator 2.5) / One concept note submitted to AEPC to help in attracting additional funding in the DSE sector. (NREP output 1.3.2)	Target achieved / KfW has approved the use of the Generation Based Window (GBW) of SECF to promote solar rooftop systems under the Promotion of Solar Energy in Rural and Semi-Rural Regions in Nepal (DKTI) programme. / 3 additional financial institutions financed DRE projects supported by NREP. / NREP supported AEPC in developing a $50 million concept note on the "Green Investment Facility Nepal" for the Green Climate Fund (GCF).
Output Indicator 2.4 Number of viable DSE businesses received TA.	30 new viable DSE businesses received detailed TA. (NREP Output indicator 2.1.2)	Target significantly exceeded. / NREP provided TA to 202 viable DSE businesses that require SECF funding. Out of these, 36 projects are owned or led by women.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score is A+. The programme has exceeded output milestones.
NREP has made a significant contribution to the market-based promotion of DSE projects, successfully mobilizing substantial private and public investment in Nepal’s DSE sector. AEPC/CREF has institutionalized the systems and processes of the SECF. Following the closure of NREP’s TA in March 2025, AEPC/CREF has continued to manage the fund effectively. To ensure a strong legal foundation, the Government of Nepal (GoN) has incorporated CREF into the REEE Bill, which has passed the National Assembly and is currently under review in the House of Representatives. Although the Government has not been able to allocate direct funding to CREF for SECF due to ongoing economic challenges, it remains firmly committed to the SECF’s success and is actively engaging with development partners like EU, Norwegian Embassy, KfW, GIZ, ADB, WB to secure additional financial support for SECF. As a result, KfW has approved the use of the Generation Based Window (GBW) of the SECF to promote solar rooftop systems under the DKTI programme.
The SECF has played a pivotal role in reducing investment risks for the private sector, thereby enhancing confidence in participating in the DSE sector. With technical assistance from NREP and VGF from the SECF, private companies are increasingly motivated to introduce innovative DSE technologies and business models that contribute to diversifying and expanding Nepal’s energy sector. For instance, Nebula Mobility Pvt. Ltd. has launched a battery-as-a-service model to promote electric two-wheelers. Similarly, Gadi Charge Pvt. Ltd. has introduced end-to-end EV charging solutions through its Charging as a Service (CaaS) model, operating its own stations and supporting franchisees to build a reliable and accessible EV infrastructure across the country.
Additionally, pellet companies have installed biomass pellet-based boilers in industries under the Energy Service Company (ESCO) model. This allows industries to transition from diesel or furnace oil boilers without upfront investment, instead paying based on pellet consumption.
NREP’s support to financial institutions through the LLG mechanism has effectively shared investment risks, encouraging banks to extend loans to DSE projects with reduced collateral requirements. As a result, three additional banks—Global IME Bank, Prabhu Bank, and Kumari Bank—began financing DSE initiatives last year, significantly improving access to finance.
NREP also introduced a reverse auction mechanism by blending financing from provincial and local governments to support last-mile household electrification. Through this approach, NREP facilitated electricity access for 369 households in Khatyad Rural Municipality, Mugu District. Under the initiative, the SECF successfully mobilized 42.3% of the total investment from the MoEWRI, Karnali Province, and 10.17% from Khatyad Rural Municipality. This blended financing model demonstrates an effective strategy for leveraging public resources to expand energy access in remote areas.
Despite its successes, the programme faced several challenges over the past year. Heavy rainfall at project sites and resistance from local leaders hindered the implementation of mini-hydro projects. Furthermore, delays by the NEA in executing net-metering for solar rooftop systems and in providing transformers for EV charging stations have hindered overall progress. The delay in the government's disbursement of funds to AEPC/CREF for the SECF has impeded the timely release of payments to private sector entities that have completed project implementation. This has consequently resulted in delays in fund reimbursement from FCDO to AEPC.
The Green Hydrogen project, while slower than expected at the start, picked up pace in the last quarter, and construction of the 200kW pilot project is expected to be completed by end-December 2025. The pilot project is done in partnership with Butwal Power Company (BPC) and will draw on excess electricity from one of BPCs hydropower projects to help generate hydrogen through electrolysis. Significant studies and trainings have been undertaken in parallel, to improve the viability of the demonstration project, and improve uptake of the lessons by government officials.
The NEA’s E&S Safeguards project successfully developed and submitted a comprehensive Environmental and Social Management System (ESMS), including key policies and plans. A total of 250 staff were trained through inclusive workshops, including a female-focused session. Essential safeguard documents were prepared for the Dudhkoshi hydropower project. The initiative significantly enhanced NEA’s capacity to manage E&S risks and align with international standards. Moving forward, ADB should support NEA in approving and institutionalizing the ESMS, allocating necessary resources, and integrating it into NEA operations to ensure long-term sustainability, compliance and improved environmental and social performance.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes to this output during the past year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The NREP team, in collaboration with AEPC and BEK, worked on all the recommendations provided in last year’s annual review. In alignment with the recommendation to coordinate with financial institutions for timely loan approvals, project financing, and improved access to credit for DSE projects, NREP and AEPC jointly conducted orientation programmes, facilitated the development of tailored loan products, and provided loan loss guarantees to mitigate banks' risk perceptions. As a result, banks have strengthened their capacity and demonstrated increased willingness to finance moderately mature technologies such as solar rooftop systems and electric cooking solutions. These institutions are now offering loans for such ventures with reduced collateral requirements. Nevertheless, banks remain reluctant to finance newer and less familiar technologies, such as pellet-based boilers, electric furnace, due to limited awareness and understanding of these innovations.
In response to the recommendation to enhance the capacity of local governments and private sector stakeholders in implementing Public-Private Partnership (PPP) models, NREP, in partnership with AEPC, collaborated closely with Khumbu Pasanglhamu Rural Municipality and private sector entities to design and initiate the Amadablam and Manjo Khola mini-hydropower projects. Both initiatives experienced delays due to heavy rainfall. Consequently, the NREP program was extended until March 2026 to ensure sufficient time for project completion. The Amadablam mini-hydropower project proceeded as planned. However, the Manjo Khola project was discontinued following opposition from certain local leaders, who expressed concerns that NEA might deprioritize grid extension to the area if the project were implemented. Accordingly, the funds initially allocated for the Manjo Khola project were reallocated to other initiatives within the SECF pipeline.
In accordance with the recommendation to ensure full disbursement of the allocated funds under the SECF, NREP focused on encouraging DSE project developers to complete installations within the stipulated timeframe and supported AEPC/CREF in the disbursement process. As a result, all funds scheduled for disbursement by March 2025 were successfully utilized.
Lesson Learned in the past year.
1. Institutional strengthening is most effective when it is co-created and directly connected to real-time delivery. AEPC and CREF demonstrated notable improvements in capacity when support shifted from designing abstract systems to engaging in practical activities such as joint application reviews and financial closures. This experience highlights the value of working together through hands-on processes. Future programmes should adopt a "learning by doing" approach from the beginning and avoid relying mainly on one-time trainings or plans.
2. Economies of scale play a key role in reducing the price of DRE technologies, which in turn lowers the need for VGF. In Nepal, for instance, NREP interventions contributed to increased market demand and sales of solar rooftop systems, resulting in lower prices and a gradual reduction in VGF requirements. However, new and emerging technologies and business models still require VGF to enter the market and remain financially viable until they benefit from economies of scale.
3. The private sector alone is unlikely to reach remote areas for last-mile electrification, making the involvement of federal, provincial, and local governments essential. With support from NREP, AEPC successfully piloted one PPP model and one reverse auction model, demonstrating how financing can be mobilised from sub-national governments. To accelerate progress toward 100% electrification, it is important to expand and strengthen such collaborative approaches.
4. The Renewable Energy Service Company (RESCO) model has demonstrated its effectiveness in promoting solar rooftop technology in industries by enabling a pay-as-you-use system, which removes the burden of upfront investment and ensures professional installation and management through DSE companies. This approach has encouraged industries to expand their solar systems after seeing real benefits, like in the case of Arihant Infrastructure Limited, where Gham Power Nepal Pvt Ltd., with support from the NREP, installed a 1.2 MW solar rooftop system. Encouraged by its performance, the industry is planning an additional 1 MW expansion on its own. The RESCO model also shows significant potential for promoting other clean technologies, such as pellet-based boilers and electric furnaces, helping industries move toward more sustainable energy solutions.
5. Industries that have adopted solar energy have experienced significant cost savings by reducing their reliance on diesel. As a result, many are now interested in further replacing their polluting fuels use and exploring other clean energy technologies. However, many industries are not fully aware of the available clean energy technologies and are hesitant to adopt them due to unfamiliarity. This highlights the need for targeted awareness-raising and capacity-building efforts to support informed decision-making and encourage wider adoption of clean energy solutions.
Recommendations for the year ahead
Recommendations	Responsibilities	Support	Timelines
Adopt a hands-on and co-created approach to institutional strengthening of government counterparts to enhance ownership and ensure effective implementation.	GGG programmes		To discuss with GGG to take this forward in FY 25/26
Continue targeted VGF support for emerging DRE technologies and business models until they reach economies of scale.	AEPC	Development partners	Discuss with development partners to take this forward in FY 25/26
Support AEPC in developing a full proposal based on the concept notes on a “Green Investment Facility” developed with NREP’s technical assistance, to mobilize climate finance to strengthen and sustain the SECF.	AEPC	GGN / RAIN programme	Discuss with GGN/RAIN to take this forward in FY 25/26
Encourage private sector companies working in the distributed sustainable energy sector to participate in the SME Catalytic Finance Facility to help expand their businesses.	AEPC	NIB programme	Discuss with NIB to take this forward in FY 25/26
Strengthen and expand public-private collaboration models, involving all levels of government, to accelerate clean energy adoption and mobilize sustainable financing.	AEPC	GGN urban component	Discuss with GGN urban component to take this forward in FY 25/26
Scale up the RESCO model to promote other clean energy technologies in industries by removing upfront investment barriers and ensure professional system management.	AEPC	Development partners	Discuss with development partners to take this forward
Raise awareness and build capacity to help industries confidently adopt a wider range of clean energy technologies.	AEPC	Development partners	Discuss with development partners to take this forward
Fully disburse allocated funds by focusing on completing installations of on-going sustainable energy projects and disbursing funds to project developers within March 2026	AEPC/CREF	Lead Adviser, Programme Manager	March 2026

## D. VALUE FOR MONEY

Key cost drivers and performance
Economy
NREP: NREP collaborated closely with AEPC and development partners such as GIZ to co-deliver workshops and awareness programmes, leveraging partner resources where possible. For example, NREP and GIZ jointly organized nationwide awareness events on DSE and the SECF, with NREP leading activities in Bagmati, Madhesh, Lumbini, and Karnali provinces, and GIZ in Koshi, Gandaki, and Sudurpashchim. To reduce costs, NREP utilized government venues such as AEPC and MoEWRI halls instead of hotel facilities wherever feasible. Furthermore, due to increased sales and market competition driven by the NREP, the price of solar PV systems in Nepal has declined by approximately 50%, compared to a global average of 30%. The additional 20% reduction is attributable to NREP interventions. As a result, VGF required for solar installations has decreased for the same power output. For instance, VGF - Interest Rate Buydown for a 500 kWp system has dropped from around NPR 28,000 to NPR 14,000.
Green Hydrogen: Delivered through the World Bank and so benefits from the robustness and scale of World Bank systems. The main costs are technical assistance and capacity building through a mixture of local and international consultants; the cost of hardware, such as the import of electrolysers; and World Bank’s management fee. Savings of £113,774 were found compared to the original proposal, thanks to a mixture of factors: favourable exchange rate fluctuations, a modest adjustment in the amount of technical assistance and capacity building, and some additional support from the World Bank itself. BPC was able to secure the tax exemption for import of the electrolysers as planned for.
NEA’s E&S Safeguards: The project strategically utilized NEA’s existing institutional frameworks and personnel, thereby minimizing the need for additional administrative resources. The training programs were thoughtfully designed and highly practical, equipping participants with skills directly applicable to hydropower project implementation. It is anticipated that the knowledge gained will contribute to the reduction of environmental and social risks, thereby enhancing the long-term sustainability of these projects.
Efficiency
NREP: NREP has effectively utilized VGF to attract private sector investment in distributed energy. Through different SECF windows, VGF has leveraged private investment at ratios ranging from 1.14 to 16.56 demonstrating a highly efficient market-based approach. This market-based approach has helped promote DSE using much less public money than traditional subsidy models. In addition to financial efficiency, these initiatives have yielded substantial economic benefits, including enhanced productivity, improved workplace environments, and reduced reliance on fossil fuels. For example, Laxmi Food Industry reported a 25% increase in productivity, a 40% reduction in energy costs, and notable improvements in working conditions due to decreased indoor air pollution and noise levels. These examples highlight strong private sector engagement and clear economic incentives for both energy users and providers.
Green Hydrogen: As mentioned, training and capacity building activities were very moderately reduced, without impacting delivery, and the World Bank plan to provide some additional training support. Additionally, NORAD provided £74,000 in grant support to BPC.
NEA’s E&S Safeguards: The project was implemented efficiently through strong coordination among NEA, ADB, and FCDO. Activities were completed on time, and resources were used effectively. The collaborative approach ensured smooth delivery of outputs. ADB plans to support NEA in finalizing and institutionalizing the ESMS and scaling up capacity-building efforts.
Effectiveness
NREP: The NREP through the provision of VGF, has successfully supported the introduction of innovative technologies and business models in Nepal. These include the RESCO model for biomass pellet burners in industries, digitally enabled fast EV charging infrastructure, and the battery-as-a-service model for two wheelers. These companies are now gradually expanding their operations. The programme has made a meaningful contribution to national and international climate and development goals. It supports the achievement of Sustainable Development Goal 7 (Affordable and Clean Energy), Nepal’s Second Nationally Determined Contribution (NDC) by promoting clean energy technologies such as e-cooking and e-charging, and the Long-Term Strategy for Net-Zero Emissions (LTS) by helping reduce greenhouse gas emissions.
Green Hydrogen: It’s still too early to say whether effectiveness has been achieved. Additionally, given its novel nature, it’s challenging to find compactors to benchmark against. Kathmandu University’s green hydrogen plant is only a few kW. Global estimates suggest $500,000-1.2m cost for a comparable sized pilot plant. Given Nepal’s project is small and frontier technology in Nepal, it is hard to compare, but the cost is likely to be high given current cost estimates.
NEA’s E&S Safeguards: The project was effective in strengthening NEA’s capacity to manage E&S safeguards. It developed the ESMS, delivered targeted training, and met participation goals. NEA staff gained practical knowledge, and senior management expressed satisfaction with the support provided by the project, noting improvements in compliance, performance, and readiness for future projects.
Equity
NREP: The NREP has actively promoted equity and inclusion by enabling women, marginalized groups, farmers, and SMEs to access renewable energy technologies such as electric cookstoves, solar water pumps, and irrigation pumps. These technologies were made accessible through partnerships with microfinance institutions and banks. In the past year, 121,373 individuals benefited, with women representing 51% of the total. Most beneficiaries accessed technologies on credit with discounted rates and affordable instalments. NREP also supported the electrification of 369 households in Khatyad Rural Municipality, Mugu District, in collaboration with sub-national governments, contributing to last-mile electrification. Additionally, repair and maintenance training was delivered, prioritizing women and marginalized communities, enhancing skills, creating jobs, and fostering empowerment. Field observations indicate increased participation, greater acceptance of technologies, and improved system performance. The transition to clean energy has reduced costs, improved working conditions, boosted employment, and strengthened energy security, contributing to inclusive and sustainable development.
Green Hydrogen: Follows high standards set by the World Bank GESI and Safeguarding principles.
NEA’s E&S Safeguards: The project promoted equity by integrating Gender Equality and Social Inclusion (GESI) principles, ensuring inclusive participation in training and decision-making. It prioritized women and marginalized groups, achieving 35% female participation overall training programme. It also organised a dedicated female-focused session. Capacity-building activities targeted staff across various levels, including marginalized groups and affected communities, ensuring equitable access to knowledge and skills in environmental and social safeguards. The ESMS and associated policies emphasized fair treatment of project-affected individuals, including indigenous peoples, and committed to improving their socioeconomic status.

E: RISK

Overview of risk management
The overall risk for CSD programme remains “Major”. The programme team and the partner regularly review, discuss and update the programme risks. The following picture provides a summary of the current CSD programme risk register which is limited to mostly NREP as NCCSP2 had already completed its implementation is the last fiscal year and the risk register was closed.

As shown above, the CSD risk register has two types of risks and there are nine active risks in total.
In addition to these risks, there were other minor risks which were noted but not included in the CSD risk register. The risks identified, and the mitigation plans are:
- Strategy and context related risks: High loan defaults among Microfinance Institutions (MFIs) have shifted their focus from SECF project implementation to loan recovery. To manage this, AEPC and NREP provided regular follow-up support and introduced a performance-based agreement to align payments with results. In the DSE project, heavy rainfall and landslides disrupted field activities. NREP responded by promptly informing BEK and postponing implementation to reduce potential losses. Political opposition also affected a mini-hydro project. AEPC and NREP identified this risk early through site visits and local consultations. As the issue could not be resolved within the project period, they recommended reallocating SECF funds to other EV charging projects to ensure effective resource utilization.
- Policy and programme delivery related risks: SECF began providing VGF to DSE companies from two years ago. While a few initiatives are approaching maturity, the majority remain in early development stages. Without sustained support, these businesses may face operational challenges and risk discontinuation. AEPC is addressing this risk through GIZ and KfW funding; however, the financial requirements remain significant. In NEA’s E&S safeguards project the key risk is the potential delay by NEA in approving and institutionalizing the ESMS, which could impede the integration of environmental and social safeguard practices across its operations. To mitigate this risk, ADB will actively engage with NEA’s Executive Director and leadership team to advocate for the timely approval and operationalization of the ESMS, ensuring alignment with national and international standards. There slow progress on Green Hydrogen, raises concerns the deadline of December 2025 may be missed. To mitigate this BEK is engaging with WB on a bi-weekly basis to manage any delays.
- Financial and fiduciary risk: The quarterly budget allocation by the GoN for the SECF may not always align with the quarterly disbursement schedule of the BEK. This misalignment could potentially result in delays in the disbursement of funds from BEK to the AEPC. To mitigate this issue, BEK is actively engaging with AEPC to facilitate the reallocation of budget in accordance with the planned disbursement schedule.
- Safeguarding: There is a risk that systems to prevent sexual exploitation, abuse, and harassment (SEAH) may not be fully effective. Staff involved in CSD programmes are responsible for ensuring that all participants and beneficiaries are aware of their right to protection and the process for reporting any concerns. Field staff are trained to identify safeguarding risks, and reporting mechanisms are in place to ensure complaints are addressed promptly and appropriately.
- Reputational Risk: NREP’s intervention has greatly increased private sector interest in distributed energy. Many businesses now see their projects as viable with VGF and have submitted concept notes and full proposals to AEPC for support from SECF. There is a growing pipeline of over 100 MW of solar projects and more than 200 EV charging stations. However, AEPC does not have enough funds to support all of them. To manage expectations, NREP and AEPC have clearly communicated the available funding and timelines. AEPC is also using GIZ and KfW funds to support some projects and is reaching out to other development partners for additional funding.
- People Risk: With the end of NREP Technical Assistance in March 2025, AEPC/CREF may face human resource constraints in managing SECF activities. To mitigate this, the NREP team has worked closely with AEPC and CREF to build institutional capacity and ensure a smooth handover of responsibilities and documentation. AEPC is deploying its own staff, along with personnel supported by GIZ and KfW, to implement and monitor DSE projects under SECF.
Annual Statement of Progress (ASP - financial aid programmes only)
Current level of fiduciary risk and direction of travel since last ASP	Major
Specific assessment of corruption risk and direction of travel since last ASP	Improving
Is a full FRA update required?	No

An ASP was conducted by PWC during June–July 2024 for AEPC/CREF. In last year's AR, the ASP was still underway, and it was noted that its findings would be reflected in this year’s report. Key observations include:
Budget reliability: This pillar remains as “major”. The OAG reports indicate low utilisation of the SECF budget in FY2022/23. Budget planning is based on ceilings rather than strategic plannings. These issues are linked to reduced budget availability from BEK following the reallocation of budget for Covid-19 recovery. SECF has implemented a rigorous due diligence process involving initial screening, due diligence of the applicants by independent assessors, evaluation by an independent panel, and final review by CREF’s Investment Committee.
Transparency of Public Finances: No change in trajectory; it remains “major”. Financial and non-financial reports such as performance reports are prepared separately and are not reconciled. SECF’s financial and audit reports are not publicly accessible, and financial reports lack details on fund disbursement timelines. Quarterly financial and technical reports are being prepared and submitted to BEK for review and approval.
Management of Assets and Liabilities: Improved from “severe” to “major”. A positive development is the formulation of an Investment Guideline, which will enhance value-for-money considerations. CREF/SECF with the support of NREP has been following a rigorous project selection process that includes initial screening, due diligence, evaluation by independent evaluation panel and final assessment by the Investment Committee. However, investment management does not account for future liquidity requirements, and no risk management framework or register currently exists.
Policy-based Fiscal Strategy and Budgeting: No change; remains “major”. SECF budgeting lacks long-term and medium-term perspectives and is not clearly linked to strategic plans. AEPC lacks a sustainability plan for post NREP operations. Nonetheless, government commitment is evident from the fact it has made significant investment to CREF as a fund and the Joint Secretary of MoEWRI leads the Investment Committee of CREF/SECF. AEPC, with GIZ support, is developing a sustainable energy credit policy and delivery mechanism. Once developed, the policy will recommend the necessary infrastructure within AEPC to effectively manage diverse financial matters associated with multiple funding agencies.
Predictability and Control in Budget Execution: Improved from “severe” to “major”. CREF is finalising Standard Operating Procedures (SOPs). This is expected to provide detailed guidelines for CREF operations and expected that the internal controls will be inbuilt with the implementation of the SOPs. A control process has been established whereby there is a maker and checker distinction – i.e. the handling bank does entries of accounting books and CREF does verification and approval. Compliance checklists have been prepared for each process such as Initial Screening Committee (ISC), Due Diligence Assessment (DDA), Independent Evaluation Panel (IEP), and IC approval. CREF with the support from NREP has instituted a rigorous process for project selection and approval.
Accounting and Reporting: Improved from “severe” to “major”. CREF is developing its own financial reporting system, which in the future can allow for reconciliation between CREF and the handling bank’s reports. CREF is using Microsoft Dynamics Nav as its accounting software. Report highlights that CREF has multiple funds under its umbrella, a consolidated financial report should be prepared, with separate GoN-compliant report for each funding source.
External Scrutiny and Audit: Improved from “severe” to “major”. Positive development since the 2022 FRA has taken place that financial statements are being prepared to be “audit-ready”. OAG, the audit institution of Nepal and an independent constitutional body, audits CREF as a part of AEPC’s audit. Audit observations pertaining to CREF is included in preliminary audit reports of AEPC. Any comments made by OAG in its annual report is subject to deliberation by the Public Accounts Committee of the Parliament, or similar authority at provincial and local governments. Therefore, any matters raised OAG relating to CREF will also be subject to legislative scrutiny.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.
The total budget of the programme is £58.5m, with an end date of 31 March 2026. As of the UK financial year 2024/25, the cumulative spend is £48.36 million (82.66% of total budget). The spend in FY 2023/24 was £7.11 million. The breakdown against the programme’s activities is outlined as follows:
Components	Spent (GBP) / Apr 2024 to Mar 2025
Nepal Renewable Energy Programme (NREP TA)	1,660,789
Nepal Renewable Energy Programme – Financial Aid to AEPC/GoN	2,150,000
World Bank Green Hydrogen - EFO	1,000,000
ADB Strengthening of NEA Capacity on Environment and Social Safeguards - MoU	500,000
Local Adaptation Plans of Action technical assistance	653,458
Support to GoN for the implementation of Local Adaptation Plans of Action (Reimbursement of FA (July 24- June 25) and costs of TA for closing NCCSP (July 25- Jan 25). Will be covered in the PCR.	1,153,794
Total	7,118,041

Nepal Climate Change Support Programme (NCCSP TA)
In this reporting period of the annual review, the NCCSP TA was engaged in evaluating the invoices and reimbursing the FA (financial aid) for the adaptation schemes as claimed by the Government of Nepal followed by closing the NCCSP programme. Details of these final closure activities will be covered in the CSD PCR. The details of the activities and results delivered through this FA were already covered in the last CSD Annual Review.

Nepal Renewable Energy Programme (NREP TA)
Implemented by DAI Europe, the NREP TA component began in February 2019 and concluded on 31 March 2025. Payments were made in arrears upon approval of quarterly progress reports (90% of total fees), with expenses reimbursed on an actual basis. The remaining 10% of fees were paid based on KPI’s review and approval.
DAI has submitted an independent audit report for the final year, which was jointly reviewed with BEK’s Head of Finance and raised no concerns. Programme-funded office assets were disposed off, following approval from the Development Director. All invoices, including the final one, have been processed and paid.
Total spend under NREP TA for the review period: £1.66 million.
Date of last narrative financial report	DAI – Quarterly Progress Report (Jan - Mar 2025)	Date of last audited annual statement	NREP TA audited report received on 19 August 2025 for final year (16 July 2024 to 31 March 2025)

Nepal Renewable Energy Programme (NREP FA)
In April 2023, a Financing Arrangement was signed between BEK and AEPC to mobilise Government-to-Government (G2G) funding, following the completion of a FRA conducted by Crown Agents. The payment modality is in reimbursable basis, AEPC/GoN spends its own funds, and FCDO reimburses the verified amount.
This marks the second year of NREP FA implementation. An Annual Statement of Progress (ASP) of AEPC/CREF was conducted by PwC through the framework contract which shows improvements in four pillars (from severe to major), with the remaining three pillars maintaining a “major” rating.
Total spend under NREP FA for the review period is: £2.15 million.
Date of last narrative financial report	N/A	Date of last audited annual statement	NREP FA audited report received on 12 June 2025 / (Office of the Auditor General, Nepal)

World Bank Green Hydrogen Project - EFO
An Externally Financed Output (EFO) agreement for the Green Hydrogen Project was signed between BEK and the World Bank in September 2025. In March 2025, a no-cost extension of nine months was granted, extending the project timeline to December 2025.
The first tranche of £1 million was paid during this review period. One additional payment is scheduled for next review year of roughly £348,000.
Date of last narrative financial report	N/A	Date of last audited annual statement	N/A

ADB Strengthening of NEA Capacity on Environment and Social Safeguards - MoU
A Memorandum of Understanding was signed between BEK and Asian Development Bank in June 2024. During the review period, two tranches totalling £500,000 were paid as per the MoU. The project was completed in March 2025, and ADB has submitted the final project report.
Date of last narrative financial report	N/A	Date of last audited annual statement	N/A

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
In case of NREP, monitoring and evaluation activities were carried out regularly through coordinated field visits by AEPC and the NREP team. These visits aimed to assess the quality of installations and verify project completion. They also enabled direct engagement with stakeholders and beneficiaries to identify implementation challenges. These challenges were discussed in fortnightly meetings between NREP and FCDO, as well as in Project Management Committee (PMC) meetings chaired by AEPC’s Executive Director, supporting evidence-based decision-making.
The FCDO team participated in field visits, stakeholder interactions, and capacity-building events, both independently and jointly with AEPC and NREP team to evaluate programme performance and delivery quality. Additionally, FCDO conducted a comprehensive review of NREP, focusing on SECF’s role in mobilizing private sector investment, scaling DSE initiatives, and promoting low-carbon development.
As part of the Annual Review, the FCDO programme team, including members of the corporate team, conducted field visits to DSE companies, industries, electric vehicle (EV) charging stations, and households supported by NREP. These visits involved direct observation of DSE projects and interactions with beneficiaries and were primarily undertaken for learning purposes. The insights and findings gathered through these activities were systematically documented in the Annual Review.
For Green Hydrogen, FCDO has monthly meetings with the World Bank team. The FCDO team are also planning a monitoring site visit, and potentially a senior site visit for the project inauguration.
In case of NEA’s E&S Safeguards, the FCDO team attended selected training sessions to assess the quality of the training delivered. Additionally, they engaged with NEA’s senior management to gain insights into the benefits and effectiveness of the support provided by ADB.
Evidence
NREP consistently applied field evidence and government data to support informed decision-making. A notable example includes a joint visit by AEPC and the NREP team to Khumbu Pasanglhamu Rural Municipality to assess the physical progress of the Amadablam and Manjo Khola mini-hydropower projects. They identified local leaders’ opposition to the Manjo Khola mini-hydropower project due to concerns over grid extension. The issue was promptly raised in meetings and recommended reallocating the funds designated for the Manjo Khola project to other viable projects within the SECF pipeline to ensure timely implementation.
Similarly, AEPC and NREP used government data and conducted field verification to identify unelectrified households in Khatyad Rural Municipality, Mugu District. Based on this evidence, they provided solar home systems to support last-mile electrification for these households.
Under the World Bank, the Green Hydrogen project draws on international and local expertise, as well as World Bank experience in this sector. Best practice on infrastructure delivery is followed.
In NEA’s E&S Safeguards project, ADB utilized internationally recognized E&S safeguard guidelines and best practices to inform the development of the ESMS and associated training modules.
Learning
AEPC, NREP, and FCDO teams used field observations and stakeholder interactions to identify successes and areas for improvement. Insights and findings were discussed in meetings and documented to inform decision-making. Selected learnings were shared through workshops and social media platforms as case studies to promote knowledge exchange. Lessons learned throughout the year were documented in the Annual Review Report, and the recommended actions are regularly reviewed and updated in the Quarterly Progress Reports to inform programme implementation and broader development efforts.