## Annual Review Template

Title: Increasing renewable energy and energy efficiency in the Eastern Caribbean
Programme Value £ (full life): £63,350,000.00		Review date: August 2025
Programme Code: [AMP ID#] 205061	AMP start date: 05 June 2015	AMP end date: 31 December 2025

Summary of Programme Performance
Year	2016	2017	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	B	A	A	B	B	A	B	A	B	B
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/4885414.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007435.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Caribbean countries have vast potential for renewable energy development. Within the CARICOM alone, the potential for solar photovoltaic (PV) energy is more than 500 terawatts, followed by around 60 gigawatts (GW) for biomass, 30 GW for wind, 10 GW for hydropower, and 6 GW for geothermal energy (particularly in the Eastern Caribbean and Montserrat). The peak electricity system demand varies but in 2023 most CARICOM countries demand was below 200MW while countries like Haiti, Bahamas and Jamaica had demand between 300 and 700MW – only Trinidad and Tobago had a peak demand of nearly 2GW. Some countries could meet their entire energy needs through renewables and potentially export surplus energy. However as of 2023[1] about 87% of the energy mix in CARICOM was still driven by fossil fuels leading to costly fuel imports and high energy prices (Caribbean electricity prices average around US$ 0.25 per kWh – some countries as high as US$ 0.40 per kWh). Reliance on costly imported fossil fuels contributes to higher levels of debt and impacts on funds available for use in other areas of national development, threatening energy security and progress towards sustainable development.
[1] 2023 CARICOM Energy Report Card

Through this programme, the UK has helped to reduce barriers to the adoption of renewable energy (RE) and energy efficiency (EE) measures across the Eastern Caribbean (EC). Governments received financing through grants and leveraged concessional loans for building technical capacity, strengthening the regulatory frameworks to support the renewable energy transition, and upstream de-risking of capital projects in renewable energy and energy efficiency. Our work is enabling EC countries diversify their energy portfolios with a focus on promoting locally sourced, cleaner, and more affordable RE and EE solutions which are key drivers of sustainable development in the region.

To date for ICF indicators being tracked UK climate finance has:
- prevented release of 3,580 tons of greenhouse gases (163.4tons CO2/year attributable to UK)
- installed 0.5MW of PV (6.5% or 0.03MW attributable to UK) and
- trained 142 persons in total across the Eastern Caribbean (28F; 116M) in energy auditing, solar PV installation and inspections, negotiating power purchase agreement and use of the RETScreen Clean Energy Management Software - a renewable energy project screening tool.

The original and new activities under the programme are as follows:
- £2.5m for the Sustainable Energy for the Eastern Caribbean (SEEC) in partnership with the European Union’s Caribbean Investment Facility and implemented by the Caribbean Development Bank (CDB) which provides technical assistance and support for investment in RE and EE in six countries[2].
  [2] Antigua & Barbuda (ANB); Dominica (DOM); Grenada; St. Kitts & Nevis; St. Lucia (SLU); St. Vincent and the Grenadines (SVG)
- £16.4m in support to geothermal development in the Eastern Caribbean to reduce the financial risk to governments in St. Vincent & the Grenadines (£4.3m), St. Lucia (£3.6m) and Dominica (£8.5m) of using constrained public funds for exploratory drilling.
- £445.5k for monitoring and evaluation of the programme.
- New £44m uplift in 2024 Business Casse Addendum
  - £34m development of the Caribbean Offshore Wind (OSW) project with the aim to develop an offshore wind market in the region and support a lighthouse project - a flagship renewable energy project designed to showcase the feasibility, benefits, and impacts of offshore wind energy development. It will serve as a model for future projects by providing insights into technical, environmental, and economic aspects of offshore wind development in the region.
  - £10m in support to geothermal development in Grenada with the aim of reducing the financial risk to the government for exploratory drilling.

This year the focus of the programme was on completing the EE retrofits to government buildings in St Vincent and the Grenadines (SVG) under the SEEC, progressing the geothermal exploration project in St Lucia and operationalising the £44m cost extension to the programme approved in 2024 for the geothermal development project in Grenada and support to implementing the regional offshore wind strategy and road map. We continued to work with our original implementing partners World Bank (WB) and Caribbean Development Bank (CDB) and started a new partnership with the Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE). The logframe was updated to add new output indicators, an impact indicator for new projects, and milestones for the ongoing and new projects. Due to delays in confirmation from implementing partners on key milestones to be delivered we completed the update less than six months prior to the Annual Review so it was submitted to and approved by the Development Director in April 2025.

Summary supporting narrative for the overall score in this review

The overall score for the programme is a B “outputs moderately did not meet expectations”. The score is driven by delays in all projects either due to more time taken to complete documentation for approval and procurement processes or challenges with substandard quality of work that required rework and lost time. The expected results this year were completion of the retrofits to government buildings in SVG, completing procurement and key documentation for the St Lucia Renewable Energy Sector Development Project (RESDP), initiating the new geothermal exploratory drilling project in Grenada with CDB Board approval and starting procurement, and progress on the offshore wind scoping study, capacity building and investment case prospectus.

Most of the outstanding milestones for 2025 will be met by the end of September. We will request a further no-cost extension, from 31 December 2025 to July 2028 to align the programme end date with the grant agreement of Grenada geothermal project and allow for the completion of a Battery Energy Storage System (BESS) project in Grenada which is due to be completed in March 2027.

Major lessons and recommendations for the year ahead

The programme continues to face delays due to lengthy processes and limited human capacity (inadequate staff numbers and available skill sets) in partner countries. We continue to address issues as they arise at the project level with additional support to partner countries through our implementing partners. There are systemic issues that would be better addressed across the project life cycle at a regional and local level in partner countries to improve their ability to deliver infrastructure projects in the planned time, cost and quality. The UK is considering systematic approaches to tackling constraints through its upcoming set of programmes. It also remains clear that regional approaches to procurement are essential in driving down some of the costs experienced on these projects. Regional agencies such as CCREEE, Organisation of Eastern Caribbean States (OECS) and CDB along with partners like WB and Inter-American Development Bank (IADB) are implementing initiatives seeking to address pooled procurement for renewable energy projects. The UK through our Global Clean Power Alliance (GCPA), Caribbean Development Team (CDT) broader programming including new programmes under design, UK Sustainable Infrastructure Programme and wider engagement in policy discussions are also supporting the drive for regional approaches to scale up renewable energy transition and strengthen climate resilience.
The recommendations for the year ahead are:
- Continue to engage in discussions on regional approaches to scaling up the renewable energy transition and identify opportunities for UK to support initiatives using various levers.
- Obtain approval to extend this programme to July 2028 primarily as a vehicle for monitoring and compliance of ongoing projects with no further spend planned past May 2026. The programme team will seek the necessary approval from the Development Director and has received approval from HMT Engagement team given that the extension will take the programme into the next spending review period.
- If the no-cost extension to the programme is approved the programme team will negotiate extensions to agreements with CDB and WB before 31 December 2025 to allow completion of respective projects.
- Team to continue to explore use of new programmes in conjunction with the Global Clean Power Alliance, the GCF Caribbean Climate Resilience Platform, the Caribbean Resilient Renewable Energy Infrastructure Investment Facility (RREIIF), OECS and other partners to tackle systemic issues preventing scale up of climate resilient infrastructure with an initial focus on renewable energy.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The expected impact “Improved energy security resulting from a more diversified and sustainable energy mix in the Eastern Caribbean” and the outcome “Barriers preventing countries in the Eastern Caribbean from achieving greater energy security are reduced” have not changed. However, an additional outcome indicator was added this year “Investment grade prospectus to establish a lighthouse project in 1 selected country completed”, to capture the planned outcome of the OSW project. The new projects added to the programme in 2024 through the Business Case Addendum as well as the original projects all align with the original programme theory of change.

Our theory of change is that through our support we can help address the major barriers preventing countries from achieving greater energy security. Based on the assumption that these barriers are a lack of finance and the lack of an enabling environment, we have:

1. Provided grant financing to help the implementation of economically feasible and financially viable projects. The upfront cost of sustainable energy technologies has proven to be high, and our grant financing has leveraged concessional financing to develop and implement them. This is particularly true for the development of geothermal resources; and
2. Funded technical assistance to address barriers such as limited technical capacity for project development and the unavailability of sufficient information to make informed decisions.
The theory of change still holds as affordable financing and the enabling environment - technical capacity and the needed regulatory environment - remain key barriers to significant scale up of renewable energy projects in the region. While there is still value in supporting individual projects there is a need for a comprehensive regional approach to address these issues to maximise on economies of scale where it is feasible to do so and boost regional project implementation capacity resources. This must be driven by political agreement through CARICOM and OECS for regional grid integration, pooled procurement and, aligned legislation and standards.

Support for this approach is gaining traction with Caribbean leaders for example with the approval of the Green Climate Fund - Resilience and Climate Action in the Caribbean Platform and the Caribbean Resilient Renewable Energy Infrastructure Investment Facility (RREIIF), two complementary initiatives. The Caribbean platform aims to deliver a programmatic, regionally led model for resilience building and climate action. Through upstream technical support it aims to mobilise greater public and private sector investment and strengthen coordination in key areas, such as sustainable energy transition, enhanced regional connectivity through resilient transport and related infrastructure, and the development of innovative financial instruments that do not increase debt burdens but absorb excess liquidity[3]. The RREIIF provides regional solutions for mobilizing private investments by leveraging scarce public resources through aggregated resilient renewable energy tenders, using financial innovation to reduce risks to resilient grid and storage investments[4]. RREIIF started implementation in three countries in 2025 with more countries to start implementation in 2026[5].
[3] Caribbean countries launch landmark platform to scale up climate investment | Green Climate Fund
[4] Caribbean Countries Strengthen Energy Resilience via New Facility | World Bank | Eastern Caribbean Central Bank
[5] Landmark Financing Agreement Marks New Phase of Resilient Energy Development in the Caribbean| Eastern Caribbean Central Bank | World Bank

In addition, the Basseterre Declaration of the OECS Decade of Action for Sustainable Energy Development was adopted on February 5, 2025, during the Third Meeting of the OECS Council of Ministers for Energy in Saint Kitts and Nevis. This declaration outlines a significant commitment to sustainable energy development in the Eastern Caribbean region for the period 2025-2035[6]. The CDT has initiated discussions with the GCPA team on how future programming to scale up renewable energy could support these initiatives.
[6] Decade of Action for Sustainable energy development (Basseterre Declaration) 2025-2035

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The pace of implementation has been significantly slower than originally planned. Despite the delays, UK support through grant financing and technical support has contributed to the outcome and impact indicators planned:
- Impact Indicator 1.1 – “Renewable energy generation capacity increases as a percentage share of total energy generation – slow but steady increases observed” – see Table 1 below.
- Outcome Indicator 1- “Increased lending by local financial institutions for small scale renewable energy and energy efficiency” – programme target reached in previous years leading to 0.4MW of solar PV installed by Small and Midsize Enterprise (SME) in Grenada.
- Outcome Indicator 2 – “Geothermal development programmes in target countries progress to next stage of development” - Following our support to drilling production and reinjection wells, Dominica is currently constructing their 10MW geothermal plant with commissioning expected in January 2026, while exploratory drilling is scheduled for St Lucia and Grenada between 2026 and 2028.
- Outcome Indicator 3 – “Investment grade prospectus to establish a lighthouse project in 1 selected country completed” – under development and scheduled to be completed by December 2025.
As with previous annual reviews, our concern is not if the projects can achieve their intended outcomes and impact, but when given the protracted timelines and increased funding often needed to deliver- with geothermal projects requiring additional financing from other sources to deliver the intended outputs.

This programme, as with other infrastructure programmes in the Caribbean, continues to experience a cycle of capacity and programme management challenges leading to slower than planned decision making and protracted procurement processes. These delays have contributed to increased costs, given changing market conditions and limited country level economies of scale. UK and other like-minded partners are exploring initiatives to break that cycle and support timely and cost-effective implementation of regional infrastructure projects.

We have also been working to address major barriers in the regulatory environment hampering the RE transition. In previous years we supported work done by the CDB to develop a Minimum Regulatory Function (MRF) for the Electricity Sector in Caribbean Countries – a threshold set of conditions deemed necessary for renewable energy investor confidence. The six priority areas of the MRF are: Integrated resource and resilience plans; Procurement and financing mechanisms for renewable energy; Mechanisms to access site and resource, and clear and non-onerous environmental permitting processes; Cost-reflective tariffs; Creditworthy utilities and Frameworks for distributed generation. This year CDB has done a gap assessment of the six priority areas in its borrowing member countries to identifying areas where development partners can provide support. The team will be using the information from this analysis to develop future UK interventions.

No further spend is planned under the current projects in this programme. The programme will be used as a vehicle to monitor progress on existing projects and track results. However, the remaining programme budget approved in the 2024 cost extension can be allocated, with Portfolio SRO approval, for further support on OSW. Since renewable energy remains a priority we are exploring mechanisms for future renewable energy programming to support new initiatives under the umbrella of the GCPA, including through the GCF Regional Platform, the Caribbean RREIIF, Basseterre declaration, supporting regulatory reform, further support to CCREEE on OSW or other regional/country specific initiatives or renewable energy financing facilities designed by other partners. The programme team is currently discussing where UK support would add best value to feed into its 2026/2027 to 2028/2029 Business Plan.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Despite significant delays on projects UK support is already delivering on the intended impact and outcomes for the region. Our support has led to a 500kW solar PV plant in SVG, installation of energy efficient street lighting in ANB and SVG, EE retrofits to government buildings in SVG and de-risked upstream geothermal development in DOM, SVG, SLU and Grenada. A key success is the Dominica geothermal project where our upstream support has contributed to construction of a 10MW geothermal power plant which is due to be commissioned early in 2026. The programme is also contributing to the knowledge base to drive development of a regional OSW market and is improving the enabling environment to support the renewable energy sector through capacity building in all six beneficiary countries.

The Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE) 2024 energy report cards are being validated. However, based on the published 2023 data on their CARICOM Energy Knowledge Hub (CEKH), CARICOM renewable energy total installed capacity in 2023 was 761.19 MW[7] up from 718.32 MW in 2022. UK support has contributed to this increase through the results achieved under this programme. The profile for 2023 in programme target countries is as indicated below with most countries showing incremental increases in renewable energy as a percentage of total installed capacity.
[7] 2023 CARICOM Energy Report Card

Country	Renewable energy generation capacity as a percentage share of total energy generation (%)[8]
	Baseline 2015	2021	2022	2023
St Lucia	<1	3	5	5.3[9]
Grenada	1.4	2	7.1	8.9[10]
Dominica	28.6	20 / (rebuilding after Hurricane Maria in 2018)	27.2	27.7[11]
St Vincent	17	15	17.4	19.0[12]
Antigua & Barbuda	0	6	12.5	12.5[13]
[8] CCREEE Knowledge Hub
[9] 2023 St. Lucia Energy Report Card
[10] 2023 Grenada Energy Report Card
[11] 2023 Dominica Energy Report Card
[12] 2023 St. Vincent and the Grenadines Energy Report Card
[13] 2023 Antigua and Barbuda Energy Report Card

Table 1: Renewable energy generation capacity as a percentage share of total energy generation
Climate and Nature is one of the FCDO’s six priority policy areas and this programme directly aligns with clean energy and associated mitigation goals, the GCPA, and to some extent supporting UK efforts to unlock greater volume and quality of finance from the global financial system. It is also a primary area of support prioritized for the Caribbean in our Development, Barbados and the Eastern Caribbean and ASIDS business plans.

## C. DETAILED OUTPUT SCORING

Output Title	SEEC is a well-managed programme with a healthy pipeline of projects - Mechanisms in place to identify, select, support and monitor projects to ensure they achieve improvements in RE/EE
Output number:		1	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Effective implementation of SEEC programme workplan (cumulative)	1 country project installation in progress (SVG- Govt): - Retrofits to government buildings (95 % completed) / 1 country project installation in progress / -The Grenada BESS Project approved by CDB Board in May 2025 / - Procurement process established, and first payment made from FCDO/SEEC funding.	Partly Achieved / 1 country project installation in progress (SVG- Govt): - Retrofits to government buildings (51 % completed) / Supply and installation of Solar 0.07 MW Photovoltaic Systems at; / a. The Coast Guard Base 0.025 MW / b. National Public Library 0.045 MW / The execution of Energy Efficiency measures at: / a. The Financial Complex; / b. Coast Guard Base and / c. National Public Library. / Partly achieved / 1 country project installation in progress / The Grenada BESS Project is expected to be approved by CDB Board by round robin by September 2025 / Procurement process established, but first payment has not been made FCDO/SEEC funding.
1.2 Number of project preparation / energy framework studies completed	Target achieved 2020
1.3 Number of projects implemented and directly supported by the Programme (Cumulative)	21 / (3 to be approved in year to August 2025)	Not achieved / Being included in broad technical assistance project with CCREEE. Aim is for approval at CDB’s September board meeting

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress on this output has been slow in the past year, mainly due to the contractor’s capacity constraints for the retrofits to public buildings in SVG and CDB’s inability to finalise a joint financing agreement with WB for the BESS project in Grenada. As a result, there were delays in the retrofits to public buildings project in SVG, approval of the BESS project in Grenada and the technical assistance projects under SEEC.

In addition, the Head of the Sustainable Energy Unit at CDB resigned at the end of April; this has increased the workload of the CDB team and caused a gap in leadership as recruitment for the new Head has been slow.

Overall, this output scored a C substantially did not meet expectations since Output Indicator 1.1 retrofits have not progressed as expected and approval of the Grenada BESS project is two months overdue with approval expected by September. CDB has selected consultants to prepare tender documents for the Grenada BESS project in parallel to Board approval. Contracts are to be signed by the end of August with documents completed by October 2025. While the milestone for Output Indicator 1.3 is now expected to be approved at CDB’s September Board meeting.

SVG – Solar PV and Retrofits to government buildings

The retrofits to the National Public Library, Coast Guard Base and Financial Complex in SVG were expected to be completed by October 2024. However, these sites are at varying levels of completion, with some works substantially advanced while others are further behind. In December 2024, the consultants engaged to certify the retrofits conducted their inspection and determined that the works could not be certified as complete as they did not meet requirements of the Terms of Reference. Their assessment highlighted significant concerns with both the adequacy of the design drawings and the quality of work produced by the contractor’s electrical engineer. The contractor strengthened its technical capacity by recruiting a new electrical engineer. The new engineer’s responsibilities include preparing accurate as-built drawings, correcting deficiencies in the electrical designs, and providing evidence, through updated calculations and verification, that the completed retrofits will deliver the anticipated energy savings. These additional steps, while necessary to safeguard the integrity and value for money of the investment, contributed to delays in meeting the original completion timeline.

The new engineer was contracted in January 2025 after the Government of SVG was satisfied that they could deliver the expected quality of work in a timely manner. The electrical design and assessment for The Financial Complex were completed and submitted to the consultant for review, and approval is pending. The design for the National Library is approximately 50% complete and is scheduled to be submitted to the consultant for approval in Week 1 of September. Meanwhile, work has commenced on the design assessments for the Coast Guard Base. It is expected that all designs for the three buildings will be completed and submitted for certification by September 2025.

A particular concern relates to the Financial Complex, where the presence of mould on one floor has prevented certification of the AC design. While mould remediation falls outside the current project scope, it must be resolved before AC retrofits on that floor can proceed. A decision is therefore required on whether this floor should be excluded from the project, or whether complementary resources can be mobilised to address the mould issue and enable the full scope of the AC retrofits.

While a total of 0.07 MW of roof-mounted PV panels were installed on the Coast Guard Base and National Library, they are not yet connected to the grid. At the Library, an issue with the permeability of the roofing material - outside the scope of this project - has prevented final certification and official commissioning of the panels. Discussions are ongoing with the Head of the Library Service to determine how this issue will be resolved. As of 8 August 2025, overall project implementation is assessed at 51% complete. With corrective actions underway and pending issues actively being addressed, the project is expected to reach full completion and closure by December 2025.

Grenada – BESS

The BESS project in Grenada is significantly behind schedule. As reported in our last annual review the appraisal mission was delayed due to the passage of Hurricane Beryl in July 2024. Since then, CDB held several months of negotiations with the WB to develop a joint financing agreement to deliver this project in coordination with the WB Caribbean Efficient and Green-Energy Buildings Project approved in February 2025. Unfortunately, the two organizations were unable to finalise a joint financing agreement and CDB had to commence restructuring of their project in May 2025. To expedite delivery CDB has approved and funded from its own resources a parallel consultancy to develop procurement documents for the BESS system so that once Board approval is obtained and the grant agreement signed, the tender can be issued to purchase the system. The consultants were identified and work on preparation of the documents is expected to commence by early September. The project is now expected to be approved by September 2025 but given the delays the planned FCDO funded activities cannot be completed by the current MoU end date of 31 December 2025.

FCDO funds were previously disbursed to CDB, and it is projected that they will be used by Q1 2026 however the target commissioning date for the battery storage system is March 2027. Given the critical need for the BESS, its importance in maintaining resilience of Grenada’s electricity system and the progress and commitment from the CDB despite challenges in the last few months, the SRO supports a time extension for this project. Once the programme extension is agreed, the SRO recommends extension be made down to March 2027 when commissioning of the BESS is projected to be completed.

SEEC Technical Assistance
The CDB is pursuing the development of a significant regional sustainable energy capacity strengthening initiative that was to be implemented over Q3 to Q4, 2025. Projects covered under the SEEC technical assistance (TA) programme are part of that imitative. The SEEC TA will focus on capacity support to Eastern Caribbean countries in (i) promotion of gender equality in the energy sector, (ii) development of a Green Strategy for the OECSC to expedite their energy transition, and (iii) strengthening of energy information systems and supporting knowledge management. There were significant delays in preparing these TA papers due in part to the reduced complement of staff at CDB since April. However, two of the three projects [(i) and (iii)] were incorporated into one TA paper that is expected to be approved at CDB’s September board meeting. The last project [(ii)] will be developed and sent to December board for approval.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output. The milestones in the logframe were updated and approved by the Development Director in April 2025 given the delays in confirmation from implementing partners on key milestones to be delivered.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This output continues to be delayed due to capacity constraints in contractors and failure to conclude a joint agreement between CDB and WB. In SVG the initially selected electrical engineer did not deliver to the required standard and there was a challenge finding a replacement with the required expertise to design the retrofits needed to meet the 25% energy saving. In addition, significant time was spent between the contractor and certifying consultant reviewing and revising designs for the work. A key lesson learned was the need to build capacity in SVG and the region to provide the type of service needed for designing the electrical retrofits. The Energy Unit in SVG is now building a database of electrical contractors with the required competency to expedite procurement in future projects. The CDB also proposed that in the future, for this type of project, it may be better to have contracts to design, supply and build to reduce the interplay between different parties which led to long delays. For the BESS project in Grenada, several months were lost in negotiation of a joint financing agreement which subsequently failed. Wherever feasible our multilateral partners should be encouraged to work together to maximise on efficiencies to deliver for partner countries in a timely manner.

The only recommendation from the previous year was for CDB to confirm the final project activities by December 2024 and complete all planned activities by 31 December 2025. As recommended FCDO raised the required urgency of action at the Project Steering Committee meeting in October 2024 and requested that clear milestones and actions to ensure delivery were put in place. However, given the issues in both the SVG and Grenada projects there were delays in finalising the agreed milestones. While the project in SVG will be completed before 31 December 2025, the Grenada BESS and TA projects cannot be completed in this timeframe.

If the UK chooses to approve a no-cost extension to the programme, the programme team recommends that we negotiate extension to the SEEC project to allow purchase and commissioning of the BESS in Grenada and completion of the remaining TA projects. Once approved the FCDO will facilitate the MoU amendment with CDB and revise the logframe accordingly.
Output Title	SEEC investments lead to increased uptake of energy efficiency and renewable energy measures by public sector
Output number:		2	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Potential units of energy saved by implementation of energy efficiency and renewable energy measures / (MWh, cumulative)	6998 MWh/year / (no additional savings expected until 2026) / (4,679 ANT streetlights, 1,380 SVG streetlights, 938 GDA PV, 0.72 SVG PV)
2.2 Increase in renewable energy generation implemented through SEEC / (MW, Cumulative)	0.97 / (0.9 plus capacity from three facilities in SVG retrofit – 0.07MW)	Achieved / 0.97 MW PV installed / (0.5 Argyle Airport, 0.4 Grenada small businesses, 0.025MW on Coast Guard Base and 0.045MW on National Library)
2.3 Amount of non-programme financing leveraged through guarantees ('000 USD)	Programme target met 2022
2.4 No. of individuals trained through capacity building interventions	Programme target met 2022

Briefly describe the output’s activities and provide supporting narrative for the score.

This output scored an A “met expectations” having met the expected milestone for Output 2.2 - Increase in renewable energy generation implemented through SEEC (MW, Cumulative).

The roof mounted PV panels were installed on the Coast Guard Base (0.045MW) and the National Library (0.045 MW) bringing the cumulative total installed to 0.97MW. The programme target has now been achieved. The PV panels are still in the testing phase and were not officially commissioned due to an issue outside of the scope of this project. The Energy Unit is working with the head of the library service to resolve an issue with the roofing material on the National Library which is delaying the contractor’s ability to have their works certified as completed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output. The milestones in the logframe were updated and approved by the Development Director in April 2025 given the delays in confirmation from implementing partners on key milestones to be delivered.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The output 2.2 target has been met and there are no further recommendations. Additional energy savings under output 2.1 will be realised once the solar PV is connected to the grid.

Output Title	Progress of geothermal development in Eastern Caribbean
Output number:		3	Output Score:	B
Impact weighting (%):		60%	Weighting revised since last AR?	Yes - reduced

Indicator(s)	Milestone(s) for this review	Progress
3.1 St Lucia geothermal development programme supported	Procurement documents completed for civil works / Procurement documents completed for Integrated drilling / ESIA/ESMP public disclosure completed by April 30, 2025. / Resettlement Action Plan (RAP) opened for public disclosure by April 30, 2025.	Achieved – Tender documents completed and published in May 2026. / Partly achieved – Tender documents drafted and addressing feedback from WB prior to resubmission for no objection. / Achieved - Public disclosure completed by April 30, 2025. / Not achieved – RAP prepared by consultant not satisfactory. PIU revised with support from WB safeguards specialist. WB provided no objection. RAP will be open for public disclosure in September 2025.
3.2 St Vincent & Grenadines geothermal development programme supported	Programme target met in 2023
3.3 Dominica geothermal development programme supported	Programme target met in 2023
3.4 Grenada geothermal development programme supported	UK FCDO/ CDB MoU signed / CDB Board approval of Grenada Grant Amendment / Civil works procurement process in progress	Achieved - UK FCDO/ CDB MoU signed on March 2025 / Not achieved - CDB Board approval of Grenada Grant Amendment scheduled for September 2025 / Achieved – Draft Request for Proposals for Integrated drilling and civil works contracts submitted to CDB for no objection

Briefly describe the output’s activities and provide supporting narrative for the score.

This output scored a B moderately did not meet expectations as four of the seven milestones were achieved, one was partially achieved and two were not achieved.

St Lucia Geothermal

The St Lucia RESDP is progressing although some deadlines were missed. The civil works tender was launched in May 2025, but the closure date was extended on two occasions to allow bidders more time to address requests for clarification and updated specifications. Bid closure is now scheduled for 3 September 2025. The drilling works tender documents were reviewed by WB and comments are being incorporated by the project implementation unit (PIU). The revised version will be submitted to WB for no objection in September. The tender is expected to be launched by September/October and be open for six to eight weeks. The ESIA/ESMP public disclosure was closed at the end of April 2025. Revisions were completed following public disclosure and the final documents were submitted to WB on 8 August 2025 and are awaiting no objection.

The Abbreviated Resettlement Action Plan (ARAP) was not open for public disclosure as planned due to the inadequate quality of the document submitted in April 2025. A full RAP was prepared with the support of WB’s safeguards specialist. The final document is now approved for public disclosure. The document is being redacted and will be open for public disclosure for two weeks from 10-25 September. Once approved it will be implemented to facilitate commencement of civil and drilling works once the contractors are selected

Although there has been significant progress and FCDO funds are being used to pay the Exploration Management Contractor (EMC) contractor, most of the funds will be disbursed once drilling commences. Current projections are that drilling will be completed by October 2027 and the grant agreement between WB and the GoSL ends in June 2028.

Grenada geothermal

When the programme was designed in 2015, support to Grenada geothermal was considered but the enabling environment was not in place at that time. Since then Grenada has demonstrated clear policy commitment and concrete steps in moving forward with geothermal development. In the intervening period the CDB approved support to the Government of Grenada (GoGR) for exploratory geothermal drilling to help the government make an evidence-based determination on whether to move to the next stage of geothermal resource development for electricity generation and help de-risk for private sector investment. There was a funding gap which did not permit an optimal drilling design and the GoGR requested UK support to finance a portion of the costs associated with the drilling of rotary wells which would improve the chances of successfully identifying a geothermal resource. In 2024, the UK was able to secure £10m to support geothermal development in Grenada.

The milestones for this year were focused on project initiation. FCDO signed an MoU with CDB in March 2025 to deliver the project. The remaining activities were related to CDB finalising their project appraisal document to incorporate amendments needed to utilise FCDO funds and expediting procurement for the required civil works and drilling.

While UK’s support is transformative for the project, greatly increasing the probability of success, it has led to some delays while the CDB team worked to incorporate new requirements given the change in drilling technique now possible with additional finance. This has required revision of the previously completed Environmental Impact Assessment to account for the larger well pads and higher water usage needed to drill rotary wells. It also required revision of the procurement documents for the drilling and civil works.

It was originally anticipated that the consultant would have been contracted to revise the ESIA by April 2025, but the planned mechanism was not possible, and a different approach had to be taken. The GoGR is now in negotiation with the consultant that prepared the original ESIA to conduct the revision. It is anticipated that the contract will be signed and work commenced in September 2025 with a five-month completion period.

The procurement documents were prepared with technical assistance from FRENZ Aotearoa New Zealand – Caribbean Facility for Renewable Energy. The draft request for proposals for both the drilling and civil works were submitted to CDB for no objection on 4 August 2025. The normal practice is for the ESIA to be completed prior to launching a tender. GoGR is seeking approval to use the existing ESIA to facilitate launch of at least the civil works tender process while the revisions to the ESIA are being completed to avoid a further five-month delay. This proposed measure is an attempt to expedite procurement activities so that drilling works can commence in 2026.

Approval of the CDB grant amendment with the GoGR has been delayed while the CDB project lead worked to address conditions precedent on the originally approved grant to Grenada for the project and the BESS project. The paper is in the final stages of internal review and is expected to be approved by the CDB Board in September 2025. The grant agreement with the GoGR is expected to end in July 2028.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This year the weighting for this output was reduced from 75% to 60% as the targets for two of the original three outputs indicators - support to St Vincent & Grenadines and Dominica geothermal development - were met in 2023. Support to St. Lucia geothermal development is ongoing and one new Output Indicator 3.4 - support to Grenada development, was added.

The logframe was updated and approved by the Development Director in April 2025 to add milestones for the Grenada geothermal project given that the MoU with CDB was signed in March 2025. We recommend a no cost extension to facilitate completion of this project. Once approved new milestones will be added to the logframe for future years following discussion with implementing partners.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The main recommendation for 2024 was that based on the delays in the St. Lucia RESDP and the added projects in the Business Case Addendum a decision should be made by early December 2025 on whether FCDO would support another no-cost extension to the programme.

Given the status of both projects at the time of this review, a no-cost extension to the entire programme is needed to provide time for their implementation. The programme team has discussed with our implementing partners CDB and WB to determine a new realistic end date. Current projections are that the St Lucia RESDP will be completed by June 2028 with all drilling and FCDO expenditure completed by October 2027. The Grenada grant agreement will end in July 2028 with drilling and final disbursement of FCDO funds completed. If UK agrees an extension the programme team will need to manage projects closely to ensure that new agreed milestones are met within the revised extension.

Output Title	Support provided to offshore wind energy development in CARICOM
Output number:		4	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	Yes new output added

Indicator(s)	Milestone(s) for this review	Progress
4.1 CCREEE Investment Grade Case and Prospectus for establishment of Offshore Lighthouse	Scoping studies at potential sites completed / External Consultant contracted / 5 validated country assessments completed / 3 stakeholder consultations completed / Inception report completed / 2 Capacity building reports completed	Scoping studies completed by CCREEE / Capacity building consultant selected contract to be signed by end of August. Technical consultant RFP issued with closure on 14 August with contract signing scheduled for the end of August. / Completed under scoping study / 1 completed in Trinidad – due to delays in finalisation of scoping study others planned by end of September / Inception report completed / 1 capacity building report completed

Briefly describe the output’s activities and provide supporting narrative for the score.

From September 2023 to March 2024, FCDO supported a baseline assessment of OSW potential in 21 countries in the Caribbean. The results of that assessment indicated that Antigua and Barbuda, Barbados, Jamaica, Suriname, and Trinidad and Tobago have “the greatest readiness to accommodate and facilitate offshore wind developments”. This project is the second phase of deeper investigation into the offshore wind potential within the eligible countries identified under the OSW phase 1 project. The expectation is that this activity will allow for high resolution quantification of the offshore wind resource potential within the selected areas, along with analysis of the technological and infrastructural requirements, evaluation of project development – including installation and maintenance – costs, and investigation of stakeholder interests and the possible environmental impacts for developing offshore wind farms in the areas. These actions aim to provide actionable insights into the specific requirements that will be necessary for the promotion and development of the lighthouse project.

The aim of this project is to narrow site selection from the five countries shortlisted in phase 1 to one site where the lighthouse OSW project will be implemented. The main outputs of this project will be an Investment Grade Prospectus for that site along with capacity building initiatives on OSW for stakeholders in the Caribbean. All activities are expected to be completed by December 2025.

This output scored a B moderately did not meet expectations due to delays in commencing capacity building and stakeholder consultations. While the capacity building plan was developed and one stakeholder consultation was held, the main engagements and training will occur from September onwards.

The scoping studies and validated country assessments were completed by CCREEE. The draft report was reviewed by FCDO and comments incorporated. There was a delay in receiving comments from some members of the project steering committee and additional data from the consultants from Phase 1. The data was received in June 2025 and CCREEE has analysed it for inclusion in the scoping study report. The studies and country assessments narrowed the site selection from the five countries shortlisted in phase 1 to three sites with final validation being conducted to select the final site. FCDO expects the draft final report to be submitted by week of 11 August for review prior to finalisation by the end of August.

Two external consultants are being engaged to complete 1) the investment case prospectus and 2) the capacity building plan. Selection of consultants was dependent on completing the scoping studies as the results of the studies informed both terms of reference and the overall capacity building plan. The capacity building plan was completed by CCREEE, and the capacity building consultant was selected and is addressing some comments in their proposal prior to signing the contract - expected by week of 11 August. The request for proposals from shortlisted consultants closes 14 August. Once evaluation of responses runs smoothly, CCREEE expects to be able to sign a contract by the end of August 2025.

Given that the capacity building consultant is currently being onboarded, only the main capacity building plan has been completed. Additional reports will be due following the planned training and the study tour. Only one stakeholder consultation was completed in Trinidad given the opportunity to conduct a round table on the sidelines of the Trinidad Energy Conference in February. No further engagements were conducted as it was determined that a more effective approach would be to await completion of the scoping study and selection of the site before engaging stakeholders to manage expectations. Now that the scoping study is almost completed the other stakeholder engagements are planned to start in September 2025.

The inception report was completed and accepted by FCDO.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new output which was added after approval of the Business Case Addendum in 2024. The MoU with CCREEE to deliver this work was signed in December 2024 and the milestones in the logframe were included and approved by the Development Director in April 2025 given the delays in confirmation from implementing partners on key milestones to be delivered. No changes are planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This is a new output so there are no recommendations from the previous AR. The project is scheduled to end 31 December 2025 with the expected targets; investment case prospectus and capacity building activities conducted.
## D: VALUE FOR MONEY

Key cost drivers and performance

As was the case in previous years, the main cost drivers for this programme were: long delays, increased cost of bids for infrastructure work due to market changes that occurred between design and implementation and supply chain issues due to lack of economies of scale on these projects. There were also challenges with the quality of work by some contractors and consultants leading to cost of time lost in revising work and the cost of hiring new persons to redo substandard work.

VfM performance compared to the original VfM proposition in the business case

A cost benefit analysis was completed in the Business Case for the SEEC programme which estimated a net present value of up to €45.5 (US$60.5) million over a 25-year period, assuming a six percent discount rate. It was estimated that the programme will result in 0.5MtCO2 saved over the 25-year period which is associated with a reduction of around 500GWh through energy efficiency measures, fuel switching and avoided fossil fuel new-build of around 200GWh to renewables.

When the retrofit project is completed an assessment of the projected savings for the 25-year period will be conducted to assess performance against the original VfM proposition. It is likely that given the time over run and changes in the market leading to fewer and smaller projects in target countries, the rate of return will be lower than projected.

The project is already providing benefits to SVG. For the streetlighting project over the period 2020 to date, 7,372 MWh of energy and XCD $4.95 Million were saved and approximately 5,529 Metric tons of CO2 emissions were avoided. The 500 kW Solar PV Plant at the Argyle International Airport went online in July 2023. To date the PV plant has saved the airport XCD $741,855.23 and avoided 660.01 tons emissions. Once completed the energy efficient retrofits will contribute additional savings with the consultant required to deliver energy savings of no less than 25% of the baseline determined in the energy audits. Once the EE and RE measures in the three government buildings are completed there will be additional cost savings and avoided CO2 emissions.

For the geothermal and OSW projects FCDO funds are being used for upstream de-risking to take projects to the stage where private investors can be attracted to take forward the projects to electricity generation. Success has already been noted in Dominica where the 10MW plant is under construction with commissioning projected for January 2026. Following completion of the investment case prospectus for OSW the next phase will be to collaborate with other partners and UK experts to develop the lighthouse project – expected to be proof of concept for Caribbean OSW market which can then be built out with private investment in the longer term. If successful our support to upstream derisking and strengthening the enabling environment could be an effective way to crowd in private investment and achieve greater value for money for the UK.

Assessment of whether the programme continues to represent value for money

Investing in the renewable energy transition in the Caribbean is one of the areas with the most significant transformational potential for sustainable development. It presents value for money not only in cost savings but also in greenhouse gas emissions and the social benefits that are derived with energy security from electricity that is not dependent on costly external fuel. Scaling up renewable energy transition globally is also one of the FCDO’s six priority policy areas and an area identified as priority for development intervention in the Caribbean.

E: RISK

Overview of risk management

The overall risk rating for the programme as at this review period is major, which has been maintained from project inception. The current active risks are categorized as follows: three (3) Strategy and Context; one (1) Public Service Delivery & Operations; three (3) Safeguarding; one (1) Reputational, and ten (10) Policy & Programme Delivery.

The programme has an eager appetite for strategy and context risks, a receptive appetite for policy and programme delivery and public service delivery and operational risks; and a cautious appetite for fiduciary, safeguarding and reputational risks. This is consistent with the overall risk appetite of the FCDO CDT.

 With the development of a new regional project – the Offshore Wind Phase II Project - a new partner – Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE) - was included under the programme which led to the inclusion of two (2) risks in the categories of Strategy and Context and Policy and Programme Delivery.

Under the Strategy and Context category there is a risk of a lack of political support at the level of the regional heads to push offshore wind as a regional initiative given that the project aims to provide a lighthouse project with a regional benefit, but the physical infrastructure will only be executed in one country at this stage. To mitigate against this the CCREEE has committed to ensuring early and consistent engagement with stakeholders via its communications, capacity building activities and also by way of ensuring the Project Steering Committee has representatives from the potential pilot countries. During the review period, activities completed toward mitigating this risk included the CCREEE presenting on their Offshore Energy work at the Trinidad Energy Conference and at the Caribbean Renewable Energy Forum (7 – 9 May 2025). In addition, the CCREEE has completed a capacity building plan for the stakeholders under the project, and plan to roll out more activities and communications around the same from September 2025.

Regarding the Policy and Programme Delivery category, given that the CCREEE is not fully staffed while engaging in multiple projects with various partners, the inadequate staff capacity was identified as a risk to effective and timely delivery of remaining activities given concurrent project demands. To mitigate this risk, in the project inception report, the CCREEE included plans to contract additional project support which the FCDO team has been tracking, along with overall project progress, during monthly meetings with the CCREEE team. Additionally, the SRO raises any concerns on delivery at Steering Committee Meetings.

Overall, the main risks categorized as major were centred on the partners’ ability to drive delivery to meet targets by the current programme end date. Implementing partners and partner countries reported delays of varying degrees, particularly due to internal bureaucratic processes, human capacity constraints and procurement processes across the projects.

Despite the capacity constraints the CCREEE is still projecting that the Offshore Wind project will meet its planned targets by the original end date (December 2025).

Challenges in the pace of delivery were experienced under the WB/St Lucia Geothermal project and the CDB/Grenada Geothermal project with both sharing updated implementation schedules during the review period which estimate project completion in mid-2028. To ensure the programme targets can be met and to provide some flexibility in case of slippage, the recommendation of this annual review is that the programme be extended to July 2028.

The focus going forward will be in ensuring the mitigation measures identified are executed or adjusted as needed to improve the pace of project delivery.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Programme Overview
During the period under review, delivery continued on two projects (the Support to Geothermal development in the Eastern Caribbean and the Sustainable Energy for the Eastern Caribbean project), which are being implemented by the World Bank and the Caribbean Development Bank respectively.
Two (2) new projects were added to the programme during the review period and Memoranda of Understanding were signed with the implementing partners – the Offshore Wind project with the Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE) signed in December 2024 (valued £500,000.00), and the Grenada Geothermal project signed with the Caribbean Development Bank in March 2025 (valued £10.0 million).
Reporting
Our partners continued to provide informal monthly updates on progress and issues as they arose. For the Grenada Geothermal Project, progress since MOU signature in March 2025 has been slow and mainly focused on advancing the project towards approval within the CDB governance structure. Consequently, all reporting has been by way of monthly meetings between the CDB and FCDO teams.
The World Bank issues semi-annual Implementation Status and Results Reports online. The latest report for the St. Lucia project was uploaded on 25 February 2025. This report shows that 22% of the USD 4.2m (£3.61m) provided by FCDO has been disbursed, which aligns with the current project status as the bulk of funds are earmarked for the Exploration Management Consultancy and to support the drilling programme.
For the SEEC programme, the CDB submitted the 18th Semi-Annual Report to 31 March 2025 on 23 April 2025 and held the SEEC Programme Steering Committee on 24 April 2025. The 19th Semi-Annual Report to 30 September 2025 is due to be submitted by 18 October 2025 with the Steering Committee meeting scheduled for 31 October 2025.
Regarding the Offshore Wind Phase II project, the CCREEE team provides updates by way of informal monthly meetings to discuss progress and also submits quarterly progress and financial reports. The 1st and 2nd quarterly progress and financial reports were submitted during the review period, covering 1 January to 31 March 2025 and 1 April to 30 June 2025 respectively. The reports are submitted in the month following the end of the quarter. In addition, the first Project Steering Committee, comprising representatives from the CCREEE, FCDO, Inter-American Development Bank and the Caribbean Development Banks, was held on 26 March 2025. This Committee provides strategic and technical guidance to the CCREEE in the execution of the Offshore Wind Project.
Visibility
All partners submitted signed Visibility statements in compliance with the FCDO programme requirements and executed various publicity activities ensuring the UK contribution is highlighted. CCREEE attended the Trinidad Energy Conference over the period 10 to 12 February 2025 where they shared a presentation on the progress made on accomplishing the Offshore Wind programme to date, and the next steps in the process. The presentation included UK branding.
For the Grenada Geothermal Project, which was signed with the CDB in March 2025, the Bank did press releases on the funding provided by the UK to support the expansion of the drilling programme for the project.
For the older projects – SEEC and St Lucia RESDP – the implementing partners provide communication products for respective projects, mostly around events or major milestones. There were no significant communication events for the SEEC in the reporting year however, the St Lucia project team hosts social media pages and a website, and also distributes quarterly newsletters on the project, all of which carry UK International Development branding.
Financial Management
All project funds were disbursed to the implementing partners for the SEEC (£2.5m), St. Lucia geothermal project (World Bank - £3.61m) and the Grenada Geothermal project (CDB - £10.0m) with the FCDO ensuring regular receipt of financial reports once available. For the Grenada project, there was no spend during the period under review, and therefore there were no financial reports to be reviewed and approved by the FCDO.
For Offshore Wind projects, programme funds are transferred to the implementing partners following receipt and approval of appropriate documentation which adheres to FCDO financial management policies. One final payment is planned to CCREEE for this project in Q4 of 2025.
Disbursements to implementing partners for the Grenada geothermal, SEEC and OSW projects were made prior to March 2025 with the intent of being recorded as spend in FY24/25. However, an internal accounting discrepancy resulted in the funds disbursed not being fully recorded against the FY24/25 budget. This was resolved in consultation with various Finance Specialists. Through managing this issue, the team can now ensure that future payments will be fully recorded during the intended financial year.
Partner Performance
All partners continue to provide strong technical and programme management support to beneficiary countries. While stakeholders in country reported their appreciation for the technical teams who engage frequently and provide required guidance to support project implementation, this year they expressed concern about some slow internal processes to review and provide comments or no objections.
Of note, the St. Lucia in-country project team gave high praise to the World Bank team whose Safeguards Specialist provided in-person support to assist them in finalizing the Resettlement Action Plan required under their Geothermal project.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring
Progress towards delivering outputs and outcomes was continuously monitored by the programme delivery team throughout the year. FCDO holds regular, monthly progress meetings with implementing partners as well as direct engagements with the beneficiary agencies on an ad hoc basis. The programme team also sits on the project steering committees – which includes representatives from the Inter-American Development Bank and the European Union and the Organisation for Eastern Caribbean States - for two of the projects, namely the CCREEE Offshore Wind project and the CDB SEEC programme.
For the CCREEE project, FCDO also reviews and comments on draft documents prepared to progress project implementation prior to their finalization.
In addition, partners are required to submit written reports, quarterly (CCREEE Offshore Wind project; CDB SEEC), and semi-annually (World Bank, St. Lucia Geothermal). All partners are required to submit financial reports at least annually once spend has commenced.
As it relates to physical monitoring, under the SEEC the CDB did not execute supervision missions to St Vincent and the Grenadines during the period under review, however the project supervision team has advised that given the physical progress of works to date and planned over the remainder of the project period, a mission is to be executed either late August or early September 2025.
Under the Grenada projects (SEEC Grenada, Grenada Geothermal) being implemented by the CDB, the CDB team executed a mission to review these projects during the week of 9 September 2024.
In relation to the St. Lucia geothermal project managed by the World Bank three (3) missions were executed in October 2024 (mid-term review mission), January 2025 (supervision mission), and June 2025 (Environmental Safeguards mission).
Site visits would not be required under the CCREEE Offshore Wind project given the objective of the project is to identify a site on which to construct a pilot lighthouse for the offshore wind in a subsequent phase of the project.
For physical monitoring, the SRO – the Climate and Renewable Energy Adviser executed a familiarisation visit to Grenada for the new geothermal project over the period 30 March to 4 April 2025 where she visited the two (2) geothermal sites in Mount St. Catherine. During the mission meetings were convened with stakeholders and frank and useful feedback obtained.

In photo: Geologist/Geoscience Manager, FRENZ (left); Climate and Renewable Energy Adviser UK FCDO (centre); and Delivery Manager/Director of Operations, FRENZ[14] (right) on the Grenada Geothermal site visits
[14] FRENZ - New Zealand Caribbean Facility for Renewable Energy. Further details available at: https://www.caribbeanfrenz.org.nz/

In photo: Climate and Renewable Energy Adviser UK FCDO (left), Geologist/Geoscience Manager, FRENZ (centre); and Delivery Manager/Director of Operations FRENZ (right) on the Grenada Geothermal site visits
The regular and ad hoc meetings, the written reports submitted, the draft documents reviewed for comments as well as the site visit helped to provide technical and strategic insights into delivery under each project and facilitated the development of appropriate recommendations aimed at ensuring the programme remains on track to achieve outcomes.

Learning
Learning has been a key part of the programme in the past year. In an effort to improve and avoid failures on the interventions, the FCDO facilitated strategic connections between project implementing teams to ensure they learn from each other, particularly where a previous similar project had been executed. This proved useful under the Grenada Geothermal Project where the connections to the World Bank team managing the St. Lucia Geothermal project resulted in sharing of key technical lessons learned that helped the Grenada team to revise project implementation approaches that would eliminate or significantly reduce risks to programme delivery.
Also, to minimize the delaying impact of their internal due diligence processes, the CDB team and the beneficiary country opted to fast track the preparation of procurement documents for the civil works and drilling required under the FCDO-funded portion of the Grenada geothermal project while awaiting internal approval of the project appraisal report which, once attained, will allow the appraisal to be submitted to the Board in September 2025 for final approval.

Date of last narrative financial report	CCREEE Offshore Wind - 23 July 2025 / World Bank St Lucia RESDP – 25 February 2025 / CDB SEEC – 31 March 2025	Date of last audited annual statement	CDB SEEC - 31 July 2024