## LogFrame Results
Impact | Impact Indicator 1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (March 2026) | Assumptions
Sustained economic growth and poverty reduction through strategic investments in resilient economic infrastructure. | Economic benefits (US$)/losses avoided (US$) for BMCs resulting from use of economic infrastructure | Planned | Not applicable | [6 empty] | Set baselines at project level for those currently without. (Rolling 5 year average) | Update rolling 5 year average | Measure benefits from completed projects. | Improvements from Baselines | Infrastructure and economic rates of return can be disaggregated by sector. Countries can derive sufficient economic benefit to derive sufficient income to support poverty reduction initiatives (job creation and income growth) More resilient infrastructure provision in targeted sectors and locations contributes to broader economic returns, income and employment generation and poverty reduction. Institutional and governance arrangements within countries are sufficient and appropriate to support sustainable development and economic growth. Cost benefit analyses are conducted as standalone inquiries, or as part of project outcome evaluations. HDI will be used for indicator, but country poverty assessments will still be used as supporting data.
Achieved
Source
EM-DAT database
| Impact Indicator 2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (March 2026)
| Human Development Index | Planned | baselines = 2015 | [7 empty] | Improvement in HDI score from baseline | Improvement in HDI score from baseline | Improvement in HDI score from baseline
Achieved
Source
HDI, CDB country poverty assessments and Jamaica Survey of Living Conditions (see detailed data sheet for references) as supporting documents
| Impact Indicator 3 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (March 2026)
| Unemployment rate (%) in UKCIF beneficiary countries (Disaggregated by sex and age) | Planned | Antigua & Barbuda – not available Belize – 6.6% (2017) Dominica – not available Grenada – 22.9% (2015) Guyana – 14.0% (2018) Jamaica – 7.7% (2019) Montserrat - 8.3% (2020) St. Lucia – 15.3% (2019) St. Vincent & the Grenadines – not available | [9 empty] | Overall reduction (% point reduction in the female and youth unemployment rates should at least be equal to the reduction in the overall unemployment rate)
Achieved
Source
Labour Force Survey data from beneficiary countries; employment data available from international sources (e.g. ILO and World Bank)
End of Programme Outcome | Outcome Indicator 1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (Dec 2026) | Assumptions
Transformative economic infrastructure supporting inclusive and sustainable growth and development in specific locations. | Re-estimated internal economic rate of return (EIRR) of >12% at completion | Planned | CDB average 12% | Estimated EIRR >12% | Estimated EIRR >12% | Estimated EIRR >12% | Estimated EIRR >12% on all projects except Montserrat at 11% | Estimated EIRR >12% on all projects except Montserrat at 11% | Estimated EIRR >12% on all projects except Montserrat at 11% | Measure baselines for projects through consultancy and EIRR estimates for completed projects - consultant engaged | Measure baselines for projects through consultancy and EIRR estimates for completed projects; Actual data for Belize show EIRR on track | ERR for complete projects meets or exceeds the threshold established at appraisal. | EIRR of >12% for completed projects and on track for incomplete projects | BMCs directly contributing own funds (investment) and indirectly trough policy enhancements to infrastructure developments. CDB continues to fund and support infrastructure enhancements in key priority infrastructure sectors. Where project EIRR is not recalculated, benefits estimated at project appraisal are assumed to remain valid at completion. Montserrat and Barbuda excluded Road safety is increased as a result of design standards being adhered to. Respective private business, private sector entrepreneurs undertaking investment to support new business growth and development. BMCs have the capacity to generate appropriate economic returns through the design and implementation of appropriate economic growth policies and strategies. Infrastructure provision facilitates trade which in turn contributes to sustainable levels of growth (social and economic) Respective governments commit to support infrastructure enhancements PPP's etc. UKCIF partners responsive to adapt, improve and strengthen key operational areas based on experience, technical support and advice. Joint planning and coordination with OIE to agree on potential priority areas for independent evaluation(s) and source(s) of funding. Perceptions surveys are designed, financed and undertaken. Projects generate positive employment.
|  | Achieved |  |  |  | On track: EIRR > 12 % for all projects except Montserrat | On track: EIRR > 12 % for all projects except Montserrat | On track: EIRR > 12 % for all projects except Monserrat (5%) and Dominica water (10%) | On track: EIRR > 12 % for all projects except Monserrat (5%) and Dominica water (10%) | EIRR not yet available for completed projects. Other projects on track: EIRR > 12 % for all projects except Monserrat (5%) and Dominica water (10%) | EIRR not yet available for completed projects. Other projects on track: EIRR > 12 % for all projects except Monserrat (5%) and Dominica water (10%) | No data available for 2025
Source
Economic appraisals and PCRs, appraisal documents; UKCIF tracking data
| Outcome Indicator 2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (Dec 2026)
| Number of people benefitting from access to improved climate resilient infrastructure (disaggregated by sex, and type of infrastructure) a) Total b) Male c) Female d) Infrastructure type: I. Roads II. Ports III. Water and sanitation IV. Irrigation v. Energy | Planned NB milestones are cumulative over time and from Dec 2020 are rounded to nearest 500 (except for the Irrigation projects because the numbers are too small to round) | 0 | 0 completed projects | 0 completed projects | a) 65,180 b) 32,551 c) 32,629 d) Roads - 65180 | a) 75000 b) 37500 c) 37500 d) Roads: 75000 Ports: 0 Water & Sanitation: 0 Irrigation: 0 Energy: 0 | a) 76000 b) 38000 c) 38000 d) Roads: 75000 Ports: 0 Water & Sanitation: 0 Irrigation: 0 Energy: 1000 | a) 76000 b) 38000 c) 38000 d) Roads: 75000 Ports: 0 Water & Sanitation: 0 Irrigation: 0 Energy: 1000 | Measure baseline number of beneficiaries for projects not yet in construction phase. Actual data for Belize Coastal against baseline. | Measure baselines number of beneficiaries for projects not yet in construction phase. Actual data for completed projects - on track per appraisal. | Beneficiary estimates for completed projects show on track to meet estimates | a) 413,771 b) 202,730 c) 211,041 d) Roads: 254,705 Ports: 115,036 Water & Sanitation: 41,730 Irrigation: 1,300 Energy: 1000
|  | Achieved |  |  |  | Not achieved due to delays in Antigua & Barbuda | Not fully achieved but close to meeting since the Antigua road is in use although it has not been finalised. | (a) total 75000 (Antigua and Barbuda RIRP); b) 37,500 male; c) 37,500 female | a) total 75000 (Antigua and Barbuda RIRP); b) 37,500 male; c) 37,500 female | (a) total 49,000 additional beneficiaries (Belize CHUP); (b) 24,500 male; (c) 24,500 female | Completed projects: (a) total 68,000 additional beneficiaries (Belize PGH); (b) 34,000 male (c) 34,000 female | Total 109,000 additioanl beneficaries for SVG (male: 56,419; female: 53,572. No update for Saint Lucia Lot 1.
Source
CDB appraisal documents and PCRs (see detailed data sheet for country breakdowns)
| Outcome Indicator 3 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (Dec 2026)
| % of beneficiaries of UKCIF-funded projects with positive perceptions of the project For road projects: positive perceptions of public transport (Satisfactory or above), disaggregated by Safety and Accessibility; For non-road projects: (tba based on project perception surveys). | Planned | Not applicable | Majority positive perceptions. | Majority positive perceptions. | Majority positive perceptions. | Majority positive perceptions. | Evaluation baseline data collected and reported for users of UKCIF-funded roads in Belize, Guyana and Saint Lucia (Baseline report due Dec 2021) | The perceptions of beneficiaries of UKCIF infrastructure projects are majority positive and improving over time | Evaluation baseline data collected and reported for users of UKCIF-funded roads in Belize, Guyana and Saint Lucia (Baseline report due Feb 2023) | Procurement and plans for endline evaluation on track. | Decision taken on when end-line evaluation will start. | 10 percentage point increase over baseline, with a majority (greater than 50%) having a positive perception of UKCIF-supported roads in Belize, Guyana and Saint Lucia.
|  | Achieved |  |  |  | No data available as no surveys conducted yet. | Hard data not yet available to assess. Preliminary feedback from community stakeholders in Antigua suggests some positive perceptions. | No data available | No data available | No data available | No data available | Decision was taken for endline evaluation to launch Q2 2026 but final decision made in March 2026 following ODA budget confirmation.
Source
UKCIF evaluation (road users surveys) for baseline (Dec 2021) and target (Mar 2024); supplemented by project perception surveys for 2022 and 2023.
| Outcome Indicator 4 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (Dec 2026)
| Cumulative employment data shows 7-10 FTE jobs per $1mn USD spend. *in construction and measured at end of project | Planned | Not applicable | Not applicable - # of person months of employment on 2 capital projects | Not applicable - # of person months of employment on 2 capital projects | Not applicable - # of person months of employment on 12 capital projects | Not applicable - # of person months of employment on 13 capital projects | Cumulative employment data for active capital projects shows at least 10.4 FTE jobs per US$1mn of cumulative spend to Dec 2021. | Cumulative employment data for active capital projects shows at least 10.4 FTE jobs per US$1mn of cumulative spend to Dec 2022. | Cumulative employment data for active capital projects shows at least 7- 10 FTE jobs per US$1mn of cumulative spend to Dec 2023. Disaggregated data for females and youth | Cumulative employment data for active capital projects shows at least 7- 10 FTE jobs per US$1mn of cumulative spend to Dec 2023. Disaggregated data for females and youth | Cumulative employment data for active capital projects shows at least 7- 10 FTE jobs per US$1mn of cumulative spend to Dec 2023. Disaggregated data for females and youth | At least 7-10 FTE jobs per US$1mn of investment (Calculated using total project costs and cumulative total of FTE jobs on the entire UKCIF portfolio from the construction phase) (Disaggregated data for females and youth better performance in jobs for identified groups in relation to relevant benchmarks where available)
|  | Achieved |  |  |  | Antigua & Barbuda roads project: 2,400 person hours of employment generated | No milestone to report against for Dec 2020. | No data available | No data available | No data available | No data available | No data available
Source
Project Supervision Reports, UKCIF monitoring data and Project Completion Reports. Based on contractors reporting the number of people working on site and ‘labour days’ attached to the work (see detailed data sheet for country breakdowns)
| Outcome Indicator 5 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (Dec 2026)
| Adequate funding available in following year's budget for operations and maintenance of UKCIF infrastructure (yes/no and amounts) | Planned | Not applicable | NA |  |  | 100% of completed projects | 100% of completed projects | 100% of completed projects have funding in place for next year and plans for future years. | 100% of completed projects have funding in place for next year and plans for future years. | 100% of completed projects have funding in place for next year and plans for future years. | 100% of completed projects have funding in place for next year and plans for future years. | All completed UKCIF infrastructure have adequate funding available in following year's budget for operation and maintenance and plans for future years' budgets.
|  | Achieved |  |  |  |  | No capital projects are completed. | No capital projects completed | No data available | No data available | O&M plans were available for the Belize projects. Ministry of Infrastructure Development and Housing allocated funding in for maintenance FY2024/2025 and FY2025/2026 for all roads in Belize. | No data available
Source
Budget statements of spending department, O&M plans
INPUTS (£) | FCDO (£) |  | Govt (£) | CDB loan | Total (£) | FCDO SHARE (%)
| 349800000 |  | 195.1m USD; 114.83 GBP (05/08/26 FX rate) | 381.5 USD; 283.19 GBP (05/08/26 FX rate) | 747.82m GBP | 42%
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9; December 2025 | Target (September 2026) | Assumptions
Water and sanitation infrastructure provided | Number of households with access to improved sanitation and water supply disaggregated by male / female headed household | Planned | Grenada: 2331 households (2020); 0km water mains laid or upgraded (2021). Dominica: 0 households (2021); 23.2km of pipeline rehabilitated (2021) | TA approved Grenada | TA approved Dominica Capital project approved: Grenada | Capital works underway: Grenada (X%) |  | Capital project approved: Dominica Grenada Capital works started: Dominica Grenada | Capital works commenced and on track for agreed completion: Dominica Grenada | Capital project for Grenada approved. Procurement for Dominica Water project commenced and on track for completion. | Procurements completed and Capital works for Dominica and Grenada commenced and on track for completion. | Dominica Water and Grenada Water on track to be completed by March 2026 | Grenada 4527 households with more reliable water supply; 14 kms water mains laid or upgraded. Dominica 6,751 households benefitting from improved access to safe water supply; 56.7km of expanded and rehabilitated pipelines | Water and sanitation infrastructure can be converted into an economic entity and linked with other forms of infrastructure. NOTES: Milestones and targets will be updated with actual infrastructure built or upgraded once capital projects have been approved and expected results are identified. Actual infrastructure built or upgraded will only materialise on completion of the project. Milestones until this point therefore show processes.
|  | Achieved |  | TA approved Grenada | TA approved Dominica | Not achieved Grenada capital project not yet approved (0%) | No milestones for this period. However, 2020 ended with momentum to resolve problems and move towards capital projects. | Capital project Dominica approved. Grenada not approved | Capital works not underway for Grenada or Dominica | Capital project for Grenada approved. Procurement for Dominica Water project had commenced, with first iteration unsuccessful. | Key contracts awarded, but works not commenced in Dominica. Grenada, procurement partially complete; works not started. | Dominica - In December 2025, capital works were in progress and expected to complete by end-March 2026, albeit with high risk. In Q1 2026, CDB confirmed that the project completion forecast would be extended in line with the project extension period offered by FCDO. Grenada - The civil works contracts have been awarded. Capital works were on track to be completed by end March but delays in late November/early December pushed the expected completion date to June or July 2026.
IMPACT WEIGHTING (%) |  | Source
6 |  | Appraisal documents (baselines) & Project Completion Reviews. CDB expenditure reports, CDB progress reports, interviews, FCDO reports For milestones: Project reports from contractor, supervising consultant and beneficiary country project teams
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 43.38m |  | 7.25m | 0 | 50.63m | 86%
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Port infrastructure implemented | Physical capacity for container throughput (TEU) in ports built | Planned | Montserrat: 1,839 (2018) St Vincent: 18,107 (2018) | TA approved St. Vincent Capital project approved Montserrat | Capital projects under way: Montserrat (3%) | Capital project approved: St. Vincent Capital works underway: Montserrat (30%) St. Vincent (X%) |  | Design-build procurement complete: Montserrat St. Vincent | Capital works underway and on track for agreed completion: Montserrat St. Vincent | Designs 100%completed for Montserrat St. Vincent | St. Vincent capital works on track for on time completion; Montserrat capital works completed | St Vincent capital works completed. Montserrat capital works on track to complete by September 2026 | Physical capacity for container throughput (TEUs) of both Ports increased from baseline and delivered as per design. | UKCIF beneficiary countries have the capacity to support and implement significant port infrastructure. Capacity of UKCIF beneficiary countries to attract additional economic return upon the completion of ports is in place. NOTES Milestones and targets will be updated with actual infrastructure built or upgraded once capital projects have been approved and expected results are identified. Actual infrastructure built or upgraded will only materialise on completion of the project. Milestones until this point therefore show processes. For the capital phase, percentage disbursed is used as a proxy for completion. The planned percentage completion is based on disbursement schedules in capital appraisal documents.
|  | Achieved |  | TA approved St. Vincent Capital project approved Montserrat | N/A | Capital project approved; St. Vincent Capital works underway: Only beginning in Montserrat (0%), not yet beginning in St. Vincent (0%) | There were no milestones for this period. However, the year ended with progress towards major procurement in the capital phase in St. Vincent, and continued delays to the main procurement in Montserrat. | Procurement for Montserrat not completed; Not completed for St Vincent | Procurement for Montserrat and St. Vincent completed; capital works underway for St. Vincent and Montserrat | Both port projects completed designs in 2023. Delay anticipated for the completion of the capital works in Montserrat. St. Vincent port project on schedule. | St. Vincent works progressing well and expected to be completed on time. Montserrat project facing delays. | St Vincent - Capital works complete. The port was opened on Saturday 25 October 2025. Montserrat - Remobilisation plan was launched in September 2025 but little progress was made by the end of 2025. Project not on track to complete by revised completion date of September 2026 but scale of delay unclear. | Keeping Montserrat In (revisit when we know next steps with project).
Source
IMPACT WEIGHTING (%)
8 |  | Baseline: https://www.cepal.org/en/notes/port-activity-report-latin-america-and-caribbean-2018#_ftn1. Appraisal documents & Project Completion Reviews. CDB expenditure reports. Feasibility study and appraisal documents. Interviews and field visits. For milestones: Project reports from contractor, supervising consultant and beneficiary country project teams
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 60.5m |  | 83.7m | 96m | 240.5m | 25%
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Roads rehabilitated | Length of roads built and/or upgraded (km) disaggregated by project - cumulative | Planned | 0 | TA approved Grenada Guyana St. Lucia Capital works underway: Antigua (63%) Jamaica EV (8%) | Capital project approved: Belize coastal Belize PSWG Dominica Capital works underway: Antigua (100%) Jamaica EV (25%) | Antigua - 8.8km Capital project approved: Grenada Guyana St. Lucia Capital works underway: Jamaica EV (55%) Jamaica SP (7%) Belize Coastal (26%) Belize PGHW (X%) Dominica (X%) Grenada (X%) St. Lucia (X%) | Capital project approved: Belize PGH Guyana LMH St Lucia Capital works under construction (%): Belize Coastal Capital works completed: Antigua: 8.8km | Capital project approved: Dominica Grenada WRC Procurement of contractor underway: Guyana LMH Capital works underway and on track for agreed completion: Belize Coastal Belize PGH St Lucia MH Capital works completed: Antigua 8.8km | Capital works underway and on track for agreed completion: Belize Coastal Belize PGH Dominica Grenada WRC Guyana LMH St Lucia MH | Capital works underway and on track for agreed completion dates (Belize): Capital works completed: Belize Coastal: 59km Belize PGH: 125km; Antigua on track for completion; Guyana - capital works on track for completion March 2026; St Lucia capital works underway and on track for completion. | Capital works underway for Dominica, Antigua completed; Guyana on track for completion March 2026; Belize completed , St Lucia completed | Dominica Road - On track to spend grant UKCIF grant allocation by March 2026. Guyana Road - On track for completion by March 2026. | Antigua - 8.7km Belize Coastal: 59km Belize PGH: 125km Dominica Road: 10.4km Guyana LMH: 121.1 km St Lucia MH: 40.2 km | BMC's able to commence road infrastructure in a timely and efficient manner. Sites and locations confirmed and prioritised. Road investments lead to socio-economic benefits that can be measured. NOTES: Milestones and targets will be updated with actual infrastructure built or upgraded once capital projects have been approved and expected results are identified. Actual infrastructure built or upgraded will only materialise on completion of the project. Milestones until this point therefore show processes. Road safety assessments and design in accordance with iRAP 3-star standard does not apply to farm roads (Jamaica).
|  | Achieved |  | TAs approved Grenada Guyana St. Lucia Belize PSWG | Capital project approved: Belize coastal Capital works underway: Antigua | Antigua did not meet 8.8 km target Capital projects approved: St. Lucia only Capital works underway: Antigua (57%) Jamaica EV (10%) Jamaica SP (0%) Belize Coastal (2%) | All 3 planned capital projects were approved in 2020. Belize Coastal road capital works underway; Capital works in Antigua had not yet been completed, but were in final stages | Capital project for Dominica not approved; Capital works underway for Belize costal, Belize PGH; Antigua not completed; Guyana procurement was underway; St Lucia, capital works underway | Capital project for Dominica approved, works not underway; Capital works underway for Belize costal and Belize PGH , Antigua not completed; Guyana capital works underway; St Lucia works underway but significantly delayed | Civil works completed for the Belize Coastal road and the Belize PGH was to be completed by March 2024. Antigua project still incomplete. Guyana capital works delayed but on track for completion in 2026. St. Lucia completion date pushed to 2025. | Belize CHP and PGHP capital works completed. Dominica contract awarded but work has not commenced. Guyana works ongoing but progress is slow. Expected completion date pushed to September 2025 for St. Lucia and December 2025 for Antigua. | Dominica Road - Overall progress approximately 32%. Expected to use UKCIF funding by September 2026. Guyana Road - Capital works were 58% complete by end-December. Project on track to fully spend the grant funds by March 2026. St Lucia Road - Overall 70% complete, Lot 1 (Milennium Highway) was completed in September 2025. On track to spend grant funds by March 2026 Antigua Road - Grant funds fully spent but some works remain incomplete (95% completion). Belize - Minor erosion affecting approximately 1% of CHUP road, linked to upstream deforestation, was address through remedial works by Nov 25. Project exit workshop held for both projects in Nov.
Source
Appraisal documents & Project Completion Reviews. CDB expenditure reports. CDB progress reports. FCDO reports. Interviews. Field visits.
| Output Indicator 3.2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026)
| % of roads Completed to iRAP 3 star standard (exclusive of farm roads) - * only measured after completion of the work | Planned | 0 | Road safety assessment complete: Antigua (Belize) Dominica Designs approved with adequate road safety provisions: Antigua | Designs approved with adequate road safety provisions: Belize Coastal | Road safety assessment complete: St Lucia Guyana Dominica Designs approved with adequate road safety provisions: Belize PGHW St Lucia Guyana | 100% | 100% of completed roads constructed to standard | 100% of completed roads constructed to standard | 100% of completed roads constructed to standard | 100% of completed roads constructed to standard | 100% of completed roads constructed to standard | 100% of UKCIF roads designed and constructed to iRAP 3 star standard
|  | Achieved |  |  |  | Road safety assessment complete: St Lucia, Dominica, Partially complete: Guyana; Designs approved: St Lucia | iRAP standard met for the projects in Antigua, Belize, and Saint Lucia. Other projects are still in process. | iRAP rating met for the approved project designs in Antigua, Belize Coastal, Belize Philip Goldson, Guyana, and Saint Lucia. Awaiting final designs for Dominica and Grenada road projects. | iRAP standard already been met for all projects except for the Grenada road project (designs not completed). IRAP rating for “as built” road in Antigua is still pending. | iRAP standard had already been met for all projects RAP rating for "as built' road in Antigua is still pending. | iRAP standard achieved for two completed roads: Belize CHP and Belize PGHP. | iRAP 3-star standard is being assessed for completed road projects (Belize).
Source
IMPACT WEIGHTING (%) |  | Appraisal documents & Project Reports & Completion Reviews. Interviews.
31
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 163m |  | 44.25m | 156m | 363m | 45%
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Agricultural land irrigated | Irrigated area by (ha) - cumulative | Planned | 0 | TA approved: Jamaica SP Capital works underway: Jamaica EV (8%) | TA approved: Jamaica SP Capital project approved: Jamaica SP Capital works underway: Jamaica EV (25%) | Capital works underway: Jamaica EV (55%) Jamaica SP (7%) | Capital works under construction: Jamaica EV Jamaica SP | Capital works underway and on track for agreed completion: Jamaica EV Jamaica SP | Capital works underway and on track for agreed completion: Jamaica EV Jamaica SP | Capital works underway and on track for agreed completion dates: Jamaica EV Jamaica SP | Capital works completed for Jamaica SP | Capital works completed for both Jamaica EV and SP projects. | Jamaica EV: 810ha Jamaica SP: 795ha | UKCIF beneficiary countries remain committed to supporting the programme Land remains available for implementation support in the project region. NOTES: Actual infrastructure built or upgraded will only materialise on completion of the project. Milestones until this point therefore show processes.
|  | Achieved |  | TA Jamaica SP still pending approval; Capital works did not begin as planned on Jamaica EV | TA approved: Jamaica SP Capital project approved: Jamaica SP | Capital works underway: Jamaica EV (10%) Jamaica SP (0%) | Capital works (well-drilling) are underway in the Essex Valley project and the Southern Plains project. Less progress has been made in Southern Plains. | Capital works are underway in Jamaica EV and Jamaica SP but the projects suffered additional delays and financing gaps in 2021 | Capital works underway Jamaica EV Jamaica SP | The Jamaica EV and SP projects advanced with installation of irrigation networks and farm roads. Projects are still on track to meet agreed completion dates. | Jamaica EV and SP projects both facing procurement delays. Capital works ongoing but incomplete. | Jamaica EV - Project 85% completed, renewable energy installations are 95% but awaiting installation of the pumps to be completed. Jamaica SP - Overall works are 95% completed. Parnassus Agro Park was commissioned in April 2025. Both projects delayed due to delays in procurement and delivery of pumps.
IMPACT WEIGHTING (%) |  | Source
9 |  | Appraisal documents & Project Completion Reviews. CDB expenditure reports. Interviews. For milestones: Project reports from contractor, supervising consultant and beneficiary country project teams
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 52.8m |  | 4.3m | 30m | 87.21 | 61%
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Renewable Energy Solutions Installed | Renewable power generation capacity installed (MW) | Planned | 0 | Capital works underway: Jamaica EV (8%) | Capital works underway: Jamaica EV (25%) | Capital project approved Barbuda Capital works underway: Barbuda Jamaica EV (55%) |  | Capital works commenced: Barbuda | Capital works on track to be completed in March 2025 | Capital works on track to be completed in March 2025 | Capital works on track to be completed in March 2025 | Capital works completed | Barbuda: 90kW Hours (powering 3 facilities) (targets confirmed from revised design) | UKCIF beneficiary countries remain committed to supporting the programme. Estimated power requirements hold true. Sites and locations confirmed and prioritised. Greater resilience achieved by burring all transmission and distribution lines NOTE: Actual infrastructure built or upgraded will only materialise on completion of the project. Milestones until this point therefore show processes.
|  | Achieved |  |  |  | Capital project approved Barbuda Capital works underway: Barbuda (0%) Jamaica EV (10%) | No milestone for this period. The project in Barbuda has made reasonable progress in the design phase in 2020. | Capital works had not commenced. Solar PV systems ere till in procurement stage. | Capital works not on track. Solar photovoltaic systems were still in procurement stage. | Installation of the solar PV was complete and battery storage component in progress. | Capital works 95% complete and on track to be completed in March 2025. | All capital works under original programme scope completed, although some defects being addressed under defects liability period.
Source
Appraisal documents & Project Completion Reviews. CDB progress reports.
| Output Indicator 5.2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026)
| Transmission or distribution lines installed or upgraded (km) | Planned | 0 | No milestone | No milestone | Capital project approved Barbuda Capital works underway: Barbuda (X%) |  | Capital works commenced: Barbuda | Capital works completed: Barbuda | Capital works on track to be completed in March 2025 | Capital works on track to be completed in March 2025 | Work completed on Barbuda Energy project. | 2.935KM
|  | Achieved |  |  |  | Capital project approved: Barbuda; Capital works Underway: Barbuda not yet started (0%) | No milestone for this period. The project in Barbuda has made reasonable progress in the design phase in 2020. | Capital works (underground cabling) had not commenced. | Capital works not complete. Underground cabling had not yet commenced. | Underground cabling completed and commissioned in July 2023. Capital works on track. | Installation of transmission lines is complete | All capital works under original programme scope completed. (Transmission lines completed in July 2023)
IMPACT WEIGHTING (%) |  | Source
1 |  | Appraisal documents & Project Completion Reviews. CDB expenditure reports. CDB progress reports.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | FCDO SHARE (%)
| 2.9m |  | 4.7m |  | 7.63 | 38%
INPUTS (HR) | FCDO (FTEs)
4.5
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Provisions for sustainability are in place | Operations and maintenance plans for UKCIF infrastructure formally agreed* (*Plans considered formally agreed when they are signed off by the implementing Ministry, and confirmed as such to CDB.). | Planned | Not applicable | O&M plan in appraisal: Antigua Rd Jamaica EV Montserrat | O&M plan in appraisal: Jamaica SP Belize Coastal | O&M plan in appraisal: Barbuda Belize PGHW Guyana St Lucia Belize PGHW Dominica Rd | O&M plan in appraisal: Belize PGH Guyana LMH Road O&M plan formalised: Antigua Rd | O&M plan in appraisal: Dominica Road Dominica Water Grenada WRC Grenada Water O&M plan formalised: Antigua Road | O&M plan formalised: Barbuda Energy | Operations and maintenance plans formally agreed 6 months after project completion (defined as end of final defects liability period expiry). | Operations and maintenance plans formally agreed 6 months after project completion (defined as end of final defects liability period expiry). | Operations and maintenance plans formally agreed 6 months after project completion (defined as end of final defects liability period expiry). | All UKCIF completed projects have formally agreed operations and maintenance plans | Good quality O&M plans are produced for all UKCIF projects.
|  | Achieved |  |  |  | O&M in appraisal: St. Lucia; Barbuda includes O&M in the contracts for the works | Appraisals for both the Belize Philip Goldson Highway and the Guyana Linden to Mabura Hill specify the requirement that O&M plans be submitted to CDB but do not provide any information on the Plan itself. In Antigua, there is a draft maintenance plan, but it still has to be finalised upon project completion. | The only capital project appraised in 2021 was the Dominica Water project. The appraisal specifies that the O&M plan is part of the project design and will be supplemented by institutional strengthening. The O&M plan for Antigua Road will only be formalised upon completion. | Milestone not achieved due to delays in implementation. The Barbuda Energy Project is a design-supply and install contract where the O&M plan will be an output of the design and installation processes. | O&M plan finalized and agreed for Antigua roads projects. Draft O&M plans available for Belize Coastal and Philip Goldson Highways. | O&M plans in place for Belize road and one component of the BERP project. Antigua committed to completing an O&M plan. | On completed projects: Belize Costal - O&M Plan in place Belize PGHW - O&M Plan in place SVG - O&M manuals are being integrated into the PMP work plan. For info on other projects: Dominica Road - Final stages of implementing the road asset management system (RAMS) to guide O&M for national road infrastructure. Jamaica - Engaging consultants to prepare O&M plans St Lucia - O&M being embedded into final construction stages and aligned with national road transport policy and strategy. Antigua finalising National Asphalt Maintenance Plan and progressing a comprehensive Roads O&M plan.
IMPACT WEIGHTING (%) |  | Source
10 |  | Appraisal Documents, Project Supervision Reports and Operations and Maintenance Plans produced. Interviews. CDB correspondence.
OUTPUT 7 | Output Indicator 7.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Key lessons and good practices are documented | Number of lessons learned workshops held during the course of the year | Planned | Not applicable | 1 | 1 | 1 | 1 | 1 | 1 | Learning plan proposals agreed and lesson learning conference held | Learning plan implemented in accordance with plan details | Learning plan implemented in accordance with plan details | 18 (cumulative). This indicator was not tracked quantatively in 2023, 2024 and 2025. | BMCs will share successes and challenges and the areas to be applied will be prioritised base don the programme's focus. Workshops are approved and take place.
|  | Achieved |  | 0 | 3 | 1 | 2 virtual “lessons learning” sessions were organized, in addition to an on-line training session on Environmental, Social, Health and Safety aspects of infrastructure projects. | Training on various topics (procurement, stakeholder engagement, and risk management) completed. One Lessons Learning session was held in December 2021. Plans for additional training (with certification), lessons learning, and the continuation of the Community of Practice are on track. | Training for project teams continued and provided opportunities for information exchange. Community of Practice cited as an important on-going forum. No specific lessons learning sessions were held in 2022 due to time constraints. | Lessons learned was the focus of the UK Caribbean Infrastructure Conference held in 2023. Lessons Learned Action Plan drafted and under discussion. | Draft Lessons Learning Plan to be implemented once agreed by FCDO and CDB. Knowledge products under preparation. | A revised Lessons Learned Plan was developed in June 2025, and activities have been implemented as planned.
Source
Workshop reports. Project Appraisal Documents. Progress Reports (Project Supervision Reports and/or Project Completion Reports. Interviews. CDB Progress reports. Meeting reports. Workshop reports.
| Output Indicator 7.2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026)
| UKCIF lessons produced and disseminated’ | Planned | Not applicable | 1 lesson learning report | 1 lesson learning report | 1 lesson learning report | 1 lesson learning report | 1 lesson learning report | 1 lesson learning report | Learning plan proposals agreed and lesson learning conference held | Learning plan implemented in accordance with plan details | Learning plan implemented in accordance with plan details | Lessons learned knowledge product produced, in line with the concept note agreed between FCDO and CDB
|  | Achieved |  | 0 | 1 | 1 | 1 report (on ESHS training) was produced and disseminated; 2 additional reports were produced in December and due to be released in 2021 | 1 report from Risk Management Training and Lessons Learning shared with all participants. | Although reports from 2021 were disseminated among project teams and within CDB, no new report was prepared. A survey was conducted to capture lessons learned by project teams during implementation. | UK Caribbean Infrastructure Conference held, with major focus on lessons learned. The Lesson Learned Action plan was under discussion. | An End-of-Year Knowledge Exchange on December 13, 2024, allowing UKCIF project teams to reflect on lessons learned over the past year | In 2025, three lesson learned sessions were held in May, June and August, in accordance with the draft plan. In addition to these sessions, two thematic knowledge sharing sessions were also held in 2025: - Economic, social and environmental costs of deferred maintenance and - Disability Inclusion web-based application In addition, the inaugural Caribbean Sustainable Infrastructure Conference was held by CDB in November 2025 and shared lessons learned from UKCIF.
IMPACT WEIGHTING (%) |  | Source
5 |  | Workshop reports. Project Appraisal Documents. Progress Reports (Project Supervision Reports and/or Project Completion Reports. Interviews. CDB Progress reports. Meeting reports. Workshop reports.
| Output Indicator 7.3 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025
| Key Stakeholders indicate that lessons learned inform policy and practice and there is evidence in policy papers and implementation practices | Planned | Not applicable | No milestone | No milestone | 35% | 50% | 60% | 70% | The majority of stakeholders indicate that lessons have fed into policy papers and implementation practice | The majority of stakeholders indicate that lessons have fed into policy papers and implementation practice | The majority of stakeholders indicate that lessons have fed into policy papers and implementation practice | Inidcator closed in June 2026.
|  | Achieved |  | NA | NA | No data available | Data collected attempted to establish usefulness of the training (> 50% stakeholder agreed); and whether there had been an improvement in a particular behaviour (response time by CDB) as an indicator of the lessons learning influencing policy and practice (>50% agreed) | Evidence collected from project teams established the usefulness of training and lessons learning sessions for their practice. At CDB, there is evidence of feedback being used to refine approach to training | Focus was on training. Survey results signal that all trainings were either somewhat helpful or very helpful to participants in the way they do their job. At CDB, there is evidence of feedback being used to refine approach to training.. | Post conference survey of participants confirmed that 100% of respondent found the trainings to be helpful; 82% found the trainings very helpful and influential in the way they carry out their jobs. | Project teams report willingness but not having time to implement tools and techniques. | No targeted surveys on lesson learning conducted, they will be conducted as part of final evaluation. | Inidcator closed in June 2026.
Source
Survey
OUTPUT 8 | Output Indicator 8.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Gender and social inclusion mainstreamed | % projects that have been designed incorporating key social, gender and inclusion considerations, including disability* *against standards in Social and Gender Framework for UKCIF and CDB's Environmental and Social Review Procedures (ESRP) | Planned | Not applicable | 100% 3 capital projects approved Antigua Jamaica EV Montserrat | 100% 5 capital projects approved - of which new: Belize Coastal Jamaica SP | 100% 11 capital projects approved - of which new: Barbuda Belize PS Dominica Rd Guyana St Lucia St Vincent | 100% | 100% | 100% | 100% | 100% | 100% | 100% of projects designed incorporating key social, gender and inclusion considerations, including disability* *against standards in Social and Gender Framework for UKCIF and CDB's Environmental and Social Review Procedures (ESRP) | Consideration to all gender and social inclusion will form part of the processes for the design and implementation of all projects under UKCIF Project ESMPs and GESI plans are of good quality, adequately reflecting and addressing the relevant social and gender considerations.
|  | Achieved |  | 100% 3 capital projects include social, gender, and inclusion considerations, including disability | 100% in the new capital projects approved (3); issues have mostly been addressed | Indicator met in the 2 new capital projects approved by December 2019: Barbuda and St. Vincent | For the 3 new capital projects in 2020, these have been incorporated even though they did not always have normal analytical inputs to do so. | 100% The Dominica water project approved in 2021 was informed by ESIA | 100% The Dominica road project approved in 2022 was informed by ESIA. | 100% ESIAs were completed for projects approved in 2023 | All capital projects designed with GESI considerations at time of approval (100 % with ESIAs). Training on the integration of disability inclusion in infrastructure projects was completed. The overall UKCIF Social and Gender Action Plan is being updated . | All UKCIF projects have been designed to incorporate social and gender considerations, and at the portfolio level, there is a UKCIF Social and Gender Development Framework. No new design was done during the reporting period.
Source
Reports on social impact assessments, gender analyses and gender guidance notes, specific gender & social inclusion strategies and/or Environmental and Social Management Plans for UKCIF projects. Desk assessment by the UKCIF Social Development Adviser. Appraisal reports. Interviews. CDB progress reports. Field visits.
| Output Indicator 8.2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026)
| % projects maintaining alignment with social, gender and inclusion strategies and ESMPs during the capital implementation phase. | Planned | Not applicable | 100% 3 capital projects under implementation* Antigua Jamaica EV Montserrat | 100% 5 capital projects under implementation Antigua Belize Coastal Jamaica EV Jamaica SP Montserrat | 100% 11 capital projects under implementation Antigua Barbuda Belize Coastal Belize PGHW Dominica Rd Guyana Jamaica EV Jamaica SP Montserrat St Lucia St Vincent | 100% of projects in capital implementation phase | 100% of projects in capital implementation phase | 100% of projects in capital implementation phase | 100% of projects in capital implementation phase | 100% of projects in capital implementation phase | 100% projects maintaining alignment with social, gender and inclusion strategies and ESMPs during the capital implementation phase. | 100% of UKCIF projects completed in alignment with social, gender and inclusion strategies and ESMPs.
|  | Achieved |  | Not possible to measure yet, only 1 capital project under implementation | Not possible to measure yet, only 1 capital under implementation; 3 others recently approved | Partial progress. There are challenges in 3 countries: Jamaica, Antigua and Barbuda, and Belize Costal | All capital projects continue to face challenges in maintaining alignment to ESMP, with the exception of Philip Goldson Highway and Guyana Linden to Mabura Hill projects, which were only approved in December 2020. Project reporting in this area has not been satisfactory in some cases. | Social and Gender Action Plan includes measures for monitoring alignment; stakeholders note slight improvement in reporting; in some cases, training already provided to contractors to help improve understanding, compliance and reporting in this area. | 100% of projects in capital implementation phase have ESMP. Social and Gender Action Plan includes measures for monitoring alignment. | 100% of projects in capital implementation phase have ESMP and GESI plans in place. | 100% of projects in capital implementation phase have ESMP and GESI plans in place. Progress is being made, but requires ongoing monitoring to ensure alignment with these plans. | Nine of the 13 UKCIF projects (69%) were deemed to be fully or largely in alignment. Four projects under implementation were deemed as only partially in alignment (Antigua Road, Dominica Road, Grenada Water, Guyana Road). The main issues related to outstanding or delayed resettlement/compensation actions, delayed implementation of social TA components and gaps or concerns on stakeholder engagement and grievance management.
IMPACT WEIGHTING (%) |  | Source
10 |  | Reports on social impact assessments, gender analyses and gender guidance notes, specific gender & social inclusion strategies and/or Environmental and Social Management Plans for UKCIF projects. Desk assessment by the UKCIF Social Development Adviser. Appraisal reports. Interviews. CDB progress reports. Field visits.
OUTPUT 9 | Output Indicator 9.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Assumptions
Resilience considerations mainstreamed | % of projects designed to deliver at least a ‘good’ increase in climate resilience.* *The increase in climate resilience to be rated as no increase, poor increase, good increase or excellent increase. (See further note on ratings in the Assumptions column) | Planned | Not applicable | 100% CVRA completed: Dominica | 100% CVRA completed: Antigua Belize Coastal Belize PGHW St Vincent Incorporation in designs: Antigua Belize Coastal | 100% CVRA completed: Barbuda Guyana Coast Guyana Road Grenada Water Jamaica EV Jamaica SP Montserrat St Lucia Incorporation in designs: Barbuda Belize PGHW Jamaica EV Jamaica SP Guyana Road Montserrat St Vincent St Lucia | 100% | At least good: 100% Excellent: 70% | At least good: 100% Excellent: 70% | At least good: 100% Excellent: 70% | At least good: 100% Excellent: 70% | At least good: 100% Excellent: 70% | All projects achieved at least a 'good' increase in climate resilience. 70% of projects achieved an excellent increase in climate resilience | Consideration of resilience will form part of the processes for the design and implementation of all projects under UKCIF. CVRA's capture all requirements to make designs climate resilient. Final designs incorporate correct climate resilience elements. NOTES: The increase in climate resilience to be rated as: • no increase- CVRA completed and considered in designs but less than increase - No CVRA completed or no CVRA recommendations are incorporated in the final designs • poor increase - CVRA completed and considered in designs but less than half the CVRA recommendations are on track to be incorporated in the final designs, • good increase - CVRA completed and considered in designs with the majority (>50%) of CVRA recommendations on track to be incorporated in the final designs, or • excellent increase - CVRA completed and considered in designs and nearly all (>80%) CVRA recommendations on track to be incorporated in the final designs.
|  | Achieved |  | 100% 1 TA completed | 100 % 6 CVAs, most TAs still in progress | CVRA completed: Barbuda, Jamaica EV, Jamaica SP, Montserrat, St. Lucia, St. Vincent, Antigua & Barbuda; Incorporation in designs: unable to verify | All projects require Climate Vulnerability Assessments at appraisal stage, as condition for approval. Projects reviewed provided evidence of CVRA engineering measures translating into the designs. | Data unavailable. All projects have approved CVRAs that informed appraisal and preliminary designs. But there has not been a formal assessment of all of the preliminary and final designs. | All projects have approved CVRAs that informed appraisal and preliminary designs. But there has not been a formal assessment of all of the preliminary and final designs | All project designs and required CVRA completed | All project designs and required CVRA were completed. | All projects include CVRA at appraisal. Implementation of climiate resilience aspects will be verified at completion. Supervision team (CDB/FCDO) interrrogate changes to project plans to determine whether resilience measures are affected, but no formal assessment undertaken. E.g. Budget reduction in Dominica Water project maintained the resilience measure of building more/larger water tanks to increase the ability to maintain clean water supplies through large storms.
Source
Project Appraisal Documents and consultants' reports. CDB Project Completion Reports. Interviews. CDB progress reports.
| Output Indicator 9.2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026)
| Proportion of projects including all climate resilience aspects from the final designs in the constructed infrastructure* *Measured by monitoring variations to final designs during construction. Detrimental changes or removal of climate resilience design elements from the “original” final designs would mean a project does not meet this indicator. | Planned | Not applicable | N/A - new indicator from 2021 | N/A - new indicator from 2021 | N/A - new indicator from 2021 | N/A - new indicator from 2021 | 100% of projects are on track to be built including the climate resilience aspects from the final designs | 100% of projects are on track to be built including the climate resilience aspects from the final designs | 100% of projects are on track to be built in accordance with the agreed design, including the climate resilience aspects from the final designs | 100% of projects are on track to be built in accordance with the agreed design, including the climate resilience aspects from the final designs | 100% of projects are on track to be built in accordance with the agreed design, including the climate resilience aspects from the final designs | Projects are on track to be built in accordance with the agreed design, including the climate resilience aspects from the final design. Output scoring range to align with CRA scoring: LF score CRA average A++ 5 A+ 4.5 - 4.99 A 4 – 4.49 B 3 – 3.99 C 2.99 and under CRA score of 4 = meeting expectations.
|  | Achieved |  | N/A - new indicator from 2021 | N/A - new indicator from 2021 | N/A - new indicator from 2021 | N/A - new indicator from 2021 | N/A- indicator requires assessment of built infrastructure | N/A - no built infrastructure | Projects completed were built according to design (based on Belize CHP) | Based on the Belize Coastal Highway and Philip S. W. Goldson Highway, completion with no report contrary to this indicator at this time. | Climate resilience as-built cannot yet be assessed, as this requires comparing as-built designs with CVRA recommendations at completion. CDB is procuring a consultant to carry out a Climate Resilience Audit in Q4 2026. But as an example of adaptive learning in projects: Jamaica EV - Contractor improved Solar PV fittings after some failed during Hurricane Beryl, to increase their resilience for future storms. There was no damage from Hurricane Melissa.
IMPACT WEIGHTING (%) |  | Source
10 |  | Project Appraisal Documents and consultants' reports. CDB Project Completion Reports. Interviews. CDB progress reports.
OUTPUT 10 | Output Indicator 10.1 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 |  | Assumptions
Projects achieving value for money considerations (economy and efficiency | Percentage of procurements above mandatory CDB financial threshold using competition to drive VFM Indicator Note: procurements that "use competition" refers to all procurement types except single source/direct contracting. The target of 100% refers to using competitive approaches in all cases except where justified; this is in accordance with CDB's Procurement Guidelines. The denominator is the total number of relevant procurements/ contracts in any given year. | Planned | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Inidcator closed in June 2026. | VfM considerations can be quantified and actually lead to systems improvements. Adequate comparison variables are in place for full VfM considerations to be assessed. Disbursements for indicator 10.2 calculated from date annual workplan agreed for following 12 months.
|  | Achieved |  | 99.32% of commercial contracts tendered using competition | Almost 100% contracts tendered using competition; sole source used in one case where justified | Almost 100 % of contracts tendered using competition | Currently 98% (of value) of contracts were let using a competitive bidding process. | 98% (of value) of contracts were let using a competitive bidding process | 100% All procurement processes used competitive bidding in 2022 in accordance with CDB’s Procurement Procedures for Projects and Procurement Policy for Projects financed by CDB | 100% - All procurement processes used competitive bidding in 2023 in accordance with CDB’s Procurement Procedures for Projects and Procurement Policy for Projects financed by the CDB. | In January 2024, CDB and FCDO agreed to change the procurement approach for the Dominica Water project to allow use of Force Account (although this is a non-competitive process). | 100% - required by CDBs procurement rules. | Inidcator closed in June 2026.
Source
Procurement documents, tender evaluations and project reports. CDB appraisal reports. Interviews. UKCIF tracking data.
| Output Indicator 10.2 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (March 2026)
| Percentage of annual workplan budgets actually disbursed in calendar year | Planned | Not applicable | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | £51,228,300 of annual allocated workplan budget disbursed
|  | Achieved |  | 39% of planned project disbursements achieved | 68% of planned disbursements achieved | 70% of planned disbursements achieved | The expected disbursement for 2020 was adjusted down by 52% in July due to implementation delays due to COVID-19. Only 55% of the adjusted figure was disbursed between January to December 2020. | Disbursements against the July 2021 revised projection were at 73%, below the 80% target. | The disbursement target of £56.7 million was surpassed due to large contracts commencing implementation. | The actual total disbursement for 2023 was £58.279 million, which is 90.3% of the amount projected in July 2023. | Disbursement was 61% of the forecast value for the calendar year | 57%. Total actual disbursements in 2025 were £59.2m against forecast disbursements of £104.2m.
Project contracts and reports. CDB progress reports. CDB financial data. UKCIF tracking data.
| Output Indicator 10.3 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026) | Indicator uses budget approved at appraisal as 'original budget'
| Proportion of projects completed within 12.5% of the original budget (disaggregated by TA/capital projects) Indicator note: Where overall projects have not yet been completed, individual contract completion to be reported instead. Reporting against milestones to differentiate between contracts and projects, and for TA/capital projects separately (target of 75% for each). | Planned |  | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% of projects
|  | Achieved |  | 100% - one completed contract in this period completed within the contract amount (Antigua TA) | 100% - one completed contract within contract amount | Data not available | No capital projects completed. Major Completed contracts to date are only for TAs (n=5). 80% of these contracts were completed within 12.5% of the contract amount. In 3 cases, there were in fact small savings on these. | No capital projects were completed. Except for Guyana LMH and Belize PGH, all other completed TAs were under budget. Overall TAs were completed 11.6% above the original approved budget (using total approved budget for all completed TAs as denominator). | No capital projects were completed in 2022. Except for the Guyana LMHP TA, all completed TAs have been completed within 12.5% of the contract amount. | 100% The completed capital project, Belize CHP was finalized within 12.5% of the original budget. | For capital works, Belize CHP and PGHP contracts were completed on time and within budget; Antigua RIRP final project cost is expected to be substantially above the original budget envelope. All completed TAs have been completed within 12.5% of the contract amount except for the Guyana LMHP TA (164% over original amount). | Belize CHUP, PGHP and Barbuda BERP works were completed within budget, while Antigua RIRP, SVG PMP and Montserrat exceed original costs. Most TA contracts were within 12.5% of budget, with expectation of Guyana LMHP TA. Based on the number of compliant projects across capital and TA, CDB reports the 75% target has been met.
Source
Memos to Director of Projects seeking approval for contract variations. CDB progress reports.
| Output Indicator 10.4 |  | Baseline | Milestone 1 March 2018 | Milestone 2 March 2019 | Milestone 3 March 2020 | Milestone 4 December 2020 | Milestone 5 December 2021 | Milestone 6 December 2022 | Milestone 7 December 2023 | Milestone 8 December 2024 | Milestone 9 December 2025 | Target (September 2026)
| Streamlined project implementation processes: *(b) time taken from approval to first disbursement (c) length of project extensions (in months) NOTE: The milestones and target for (c) are framed as the average project extension as a % of the original completion time. This is derived by calculating the additional time in months to complete each project beyond the original completion date as a % of the original estimate in months for completion at project approval, and then taking the average of these. * Sub-indicator (a) "% change in time taken from appraisal mission to approval" was removed from 2021 | Planned | a) 3.7 months (2015)* b) 12 months (CDB capital projects average 2016-18) c) Not available *a) "% change in time taken from appraisal mission to approval" removed from 2021 | Positive progress towards 2024 target | Positive progress towards 2024 target | Positive progress towards 2024 target | (b) Average time to first disbursement for TA = 13.7 months and for CAP = 13.2 months (for those projects that have reported a first disbursement), | b) time taken is < baseline c)average project extension relative to original completion time is < 50% *a) removed from 2021 onwards | b) time taken is < baseline AND < the previous year c)average project extension relative to original completion time is < 50% | b) time taken is < baseline c)average project extension relative to original completion time is < 50% | b) time taken is < baseline c)average project extension relative to original completion time is < 50% | b) time taken is < baseline c)average project extension relative to original completion time is < 50% | b) time taken is less than or equal to baseline c) < 50% (average project extension relative to original completion time)
|  | Achieved |  | no milestone | On track in streamlining appraisal to approval; first disbursements still taking a long time; no capital projects completed | Appraisal period longer than expected; Project transition from appraisal to first disbursement still a challenge; no projects completed | a) Data not available (b) Average time to first disbursement: Overall = 14.3 months; TA grants =12.5 months; Capital grants =16 months. (c) Antigua Road is the only capital grant extension to date = 24 months (but contract still not completed); On average, completed TAs (n= 5) have all been extended by at least 12 months. | (b) Average time to first disbursement for TA = 13.7 months and for CAP = 13.2 months (for those projects that have reported a first disbursement), | (b) Average time to first disbursement for TA = 13.7 months and for CAP = 15.6 months including Guyana LMHP and SVG KPMP Figures are higher than the baseline and higher than last year (for capital projects) (c) Antigua and Barbuda RIRP is the only capital grant extension to date that is more than 40 months (and contract still not completed). On average completed TAs (n= 6) have been extended by at least 12 months. . | (b) Average time to first disbursement in Months (TA) 15.1 Average Time to first disbursement in Months (CAP) 17.5 . (c) Antigua and Barbuda RIRP is the only capital grant extension to date that is more than 40 months (and contract still not completed). On average completed TAs (n= 6) have been extended by at least 12 months. | a) Average Time to first disbursement: TA = 13.7 months; CAP = 17.0 months. b) Antigua and Barbuda RIRP is more than 48 months delayed (with the project still not completed). In Belize infrastructure works are completed on two projects | b) average time to first disbursement: Overall = 15.3 TA grants = 13.7 Capital grants 17.0
IMPACT WEIGHTING (%) |  | Source
10 |  | Project reports (technical and financial) and Annual Reviews. Project tracker. CDB progress reports. UKCIF tracking data.
Note on M71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDB to confirm if the following will impact the result. - Guyana still has £39k TA to spend. - Saint Lucia has £13k TA to spend.
Note on M97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Response to CDB on query regarding commissioning. Capital works completed means they should be operational, so they should be commissioned.

## Change tracker
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indicator 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
#1-12 | See below | Milestone targets adjusted to reflect the programme for project approvals submitted to the CDB Board of Directors in May 2018. These changes respond to a recommendation in the programme's 2018 Annual Review: ‘Adjust output milestones and project implementation targets so that they still represent a challenge, but are also more realistic in relation to capacities for project implementation at country level.’ These are the best estimates that we currently have and experience has shown that these represent a significant challenge.
1 | Milestone targets for outcome indicator 1: # completed projects which have an assessed economic rate of return of: a)>12% or b) >15% by 2024 | Milestone targets adjusted to reflect the latest projections for completion of capital works: Antigua road: was March 2019 now March 2020 Grenada water: was March 2021 now March 2022 Montserrat port: was March 2021 now March 2022 Belize coastal: was March 2022 now March 2023 Belize PSWG: was March 2022 now March 2023 Dominica road: March 2022 unchanged Grenada road: March 2022 unchanged Guyana coastal: March 2022 unchanged Jamaica EV: was March 2022 now March 2023 St Lucia road: March 2022 unchanged SVG port: March 2022 unchanged Guyana road: was March 2023 now March 2024 Jamaica SCC: March 2023 unchanged Dominica water: March 2024 added | Katie Aaronson | 2018-05-02
2 | Milestone targets for outcome indicator 2: # people benefitting from access to improved climate resilient infrastructure (disaggregated by sex, and type of infrastructure) | Milestone targets adjusted to reflect the latest projections for completion of capital works - please see original and revised dates above for change #1 | Katie Aaronson | 2018-05-02
3 | Milestone targets for outcome indicator 4: # number of person months per year of direct employment on UKCIF infrastructure projects | Milestone targets adjusted to reflect the latest projections for capital works starting and finishing. March 2019: was 9 capital projects under implementation, now 2. The following capital projects were due to start by March 2019, now projected by March 2020: Belize coastal; Belize PSWG; Dominica road; Grenada water; Guyana coastal; Montserrat port; SVG port. March 2020: 12 capital projects under implementation - unchanged March 2021: was 12 capital projects under implementation, now 13 - Dominica water reconstruction project added March 2022: was 10 capital projects under implementation, now 13. Grenada water and Montserrat port capital projects were due for completion by March 2021, now projected by March 2022. March 2023: was 2 capital projects under implementation, now 6. Belize coastal, Belize PSWG and Jamaica EV capital projects were projected for completion by March 2022, now projected by March 2023. March 2024: was 0 capital projects uunder implementation, now 2. Guyana road capital project was due for completion by March 2023, now projected to finish by March 2024. Dominica water reconstruction project added. | Katie Aaronson | 2018-05-02
4 | Milestone targets for output indicator 1.1 - # households with access to improved sanitation and water supply. | Grenada capital works started: was March 2019, now March 2020 Grenada completion of capital works: was March 2021, now March 2022 Dominica water reconstruction project added: TA approved by March 2019; capital project approved by March 2020; capital works underway by March 2021; capital works finished by March 2024. | Katie Aaronson | 2018-05-02
5 | Milestone targets for output indicator 2.1 - # ports upgraded | SVG capital project approval: was March 2019, now March 2020 SVG capital works started: was March 2019, now March 2020 SVG completed project: March 2022 unchanged Montserrat capital works started: was March 2019, now March 2020 Montserrat completed project: was March 2021, now March 2022 | Katie Aaronson | 2018-05-02
6 | Milestone targets for output indicator 3.1 - km of roads built and/or upgraded | Milestone 1 corrected to reflect current projections for completion of Antigua project by March 2020 (Antigua 5km was previously erroneously included for March 2018) Antigua 8.8km March 2020 unchanged Belize coastal capital project approved: March 2019 unchanged Belize coastal capital works started: was March 2019, now March 2020 Belize coastal capital works completed: was March 2022, now March 2023 Belize Northern capital project approved: March 2019 unchanged Belize Northern capital works started: was March 2019, now March 2020 Belize Northern capital works completed: was March 2022, now March 2023 Dominica capital project approved: March 2019 unchanged Dominica capital works started: was March 2019, now March 2020 Dominica capital works completed: March 2022 unchanged Grenada capital project approved: was March 2019, now March 2020 Grenada capital works started: March 2020 unchanged Grenada capital works completed: March 2022 unchanged Guyana capital project approved: was March 2019, now March 2020 Guyana capital works started: was March 2020, now March 2021 Guyana capital works completed: was March 2023, now March 2024 St Lucia capital project approved: was March 2019, now March 2020 St Lucia capital works started: March 2020 unchanged St Lucia capital works completed: March 2022 unchanged | Katie Aaronson | 2018-05-02
7 | Milestone targets for output indicator 4.1 - Irrigated area by (ha) | Jamaica EV capital works completed - was March 2022, now March 2023 Milestones for Jamaica SCC unchanged | Katie Aaronson | 2018-05-02
8 | Milestone targets for output indicator 5.1 - #km coastal defenses provided in target areas | Guyana capital project approved: was March 2019, now March 2020 Guyana capital works started: was March 2019, now March 2020 Guyana capital works completed: March 2022 unchanged | Katie Aaronson | 2018-05-02
9 | Milestone targets for output indicator 7.1 - % projects that have been designed incorporating key social, gender and inclusion considerations, including disability | March 2019: was 13 capital projects approved, now 8. The 6 remaining capital projects are now due for approval by March 2020 (Grenada road; Guyana coastal; Guyana road; St. Lucia road; SVG port, Dominica water.) |  | 2018-05-02
10 | Milestone targets for output indicator 7.2 - % projects maintaining alignment with social, gender and inclusion strategies and ESMPs | Milestone targets clarified to ensure clear distinction between project completed and those still under construction, and avoid double counting of projects. Dominica water reconstruction project added to all targets. March 2019: was 1 capital project completed, 8 under implementation; now 8 under implementation. Antigua project completion now expected by March 2020. March 2020: 1 capital project completed unchangedl; was 8 under implementation, now 13. March 2021: 1 capital project completed unchanged; was 12 under implementation, now 13. March 2022: was 3 capital projects completed, now 8; was 10 under implementation, now 6. March 2023: was 11 capital projects completed, now 12; was 2 under implementation unchanged/ March 2024: was 13 capital projects completed, 1 under implementation; now 14 completed. |  | 2018-05-02
11 | Milestone targets for output indicator 8.1 - % projects with completed climate vulnerability assessments | March 2019: was 11 TAs completed, now 6 TAs completed. The following 5 TAs previously projected for completion by March 2019 are now expected by March 2020: Grenada road; Guyana coastal; Guyana road; St. Lucia road; SVG port. March 2020 now 12 TA s completed: Dominica water reconstruction project added. |  | 2018-05-02
12 | Milestone targets for output indicator 8.2 - # of assets produced, developed, improved or strengthened for climate resilience | March 2019: was 1 completed project, now 0 completed projects - completion of Antigua road now expected by March 2020 March 2020: 1 completed project unchanged March 2021: was 3 completed projects, now 1 completed project - completion of Grenada water and Montserrat port projects now expected by March 2022 March 2022: was 11 completed projects, now 8 completed projects - completion of Belize coastal, Belize Northern and Jamaica EV projects now expected by March 2023 March 2023: was 13 completed projects, now 12 completed projects - completion of Guyana road project now expected by March 2024 March 2024: was 13 completed projects, now 14; Dominica water reconstruction project added. | Katie Aaronson | 2018-05-02
13 | Milestone targets for outputs 1-5 | Removed 'TA completed and results clarified' milestones, as these unnecessarily duplicated the capital grant approval milestones. | Katie Aaronson | 2018-05-02
14 | Outputs 1-5 impact weightings | Impact weightings for outputs 1-5 have been adjusted to reflect the addition of reconstruction funding for Dominica and the resulting increase in spending on water and sanitation programming. The adjustments are as follows: Output 1: 2% to 6% Output 2: 7% unchanged Output 3: 27% to 24% Output 4: 10% to 9% Output 5: 4% unchanged This change responds to the 2018 Annual Review which recommended 'adjusting impact weights if it helps to focus risk management and resource prioritisation'. | Katie Aaronson | 2018-05-02
15 | Risk ratings for outputs | Risk ratings added for all outputs (previously omitted in error). Output 1 - Major Output 2 - Major Output 3 - Major Output 4 - Major Output 5 - Major Output 6 - Moderate Output 7 - Major Output 8 - Moderate Output 9 - Moderate This change responds to the 2018 Annual Review which highlighted 'the need for risk ratings on the outputs'. | Katie Aaronson | 2018-05-02
16 | Goal statement | The goal statement has been enhanced by qualify that we are dealing with investments in ‘resilient’ economic infrastructure, creating a linkage to resilience outputs and outcomes. | Lone Sorensen | 2019-09-26
17 | Outcome Indicator 1: # completed projects which have an assessed economic rate of return of >12% or b) >15% by 2024 | The wording of this indicator has been changed from counting completed projects to instead tracking whether the re-estimated economic internal return rate (EIRR) of UKCIF projects on completion is above 12%: ‘Re-estimated economic return >12%’. The original indicator had a stretch target of >15%. For simplicity, this has been removed to align with the UKCIF criterion of projects achieving an EIRR of >12%. New milestones track achievements against the 12% threshold and record the re-estimated EIRR on completion for each project. The target has been defined as the estimated EIRR at appraisal. We are using re-estimated EIRR as a proxy for projects delivering economic growth but are mindful that we cannot measure actual EIRR until long after the projects have been completed. CDB will typically re-run the economic appraisal as part of the Project Completion Report (PCR). This re-estimation exercise will take into account any increases in project cost and other factors considered in the sensitivity analysis. In instances where CDB does not re-run the economic appraisal, the estimated EIRR will prevail. | Lone Sorensen | 2019-09-26
18 | Outcome Indicator 2: # people benefitting from access to improved climate resilient infrastructure | The indicator wording now specifies the types of infrastructure that people will benefit from. The definition of ‘beneficiary’ for different types of project and in different contexts will be clarified in a methodology note (see detailed data tab) and figures will be added for projects that have completed capital appraisal. An assumption that UKCIF investments in road upgrades lead to increased road safety has been added to signal that beneficiaries of UKCIF roads benefit from greater road safety (ref also new output indictor on road safety in Output 3). This is a cumulative indicator. When a project reaches the capital phase and we know its number of beneficiaries, we record those beneficiaries against the milestone for the year when the project reaches ‘taking over certificate’ (i.e. before the defects liability period). This is when people start benefitting from the new or upgraded infrastructure. As other projects come on stream, their beneficiaries will be added at the relevant milestones and the figures will carry through to the end of the project. We currently have five capital projects in the portfolio (Antigua Road, Belize Coastal, Jamaica Essex and Southern Planes and Montserrat). | Lone Sorensen | 2019-09-26
| Indictor 4: # number of person months per year of direct employment | This indicator has been changed so it no longer measures person months per year but instead cumulative person months of employment at each milestone and at the end of the programme for each project and across the programme. It is not possible to set a quantitative target (as employment is the responsibility of the contractor and outside the programme’s control) so the target is more qualitative in nature, looking for ‘positive employment of women, youth and local/regional persons’ | Lone Sorensen | 2019-09-26
| Indicator 5: Funding available in next year's budget for operations and maintenance of UKCIF infrastructure | This is a new indicator which aims to measure sustainability of infrastructure investments. It does so by tracking whether there is budget available for operations and maintenance of UKCIF projects in the next year’s budget after their completion (i.e. at tacking over certificate point). | Lone Sorensen | 2019-09-26
| Outputs 1-5 (Infrastructure) | A measure of progress has been introduced after the approval of capital projects and before the infrastructure is completed. It tracks percentage actual expenditure against percentage planned expenditure at appraisal (i.e. using the disbursement schedules in the appraisal documents) and provides an expected percentage completion for all projects in the milestones. Assumptions have been updated to reflect this approach. | Lone Sorensen | 2019-09-26
| Outputs 1-5 (Infrastructure) | The impact weighting for outputs 1-5 has been increased from 50% to 60% to better reflect the importance of these outputs for the achievement of the programme objectives. They have all been recalculated based on recalculated budget allocations for different types of infrastructure. This takes into account the substitution of previous Output 5: Coastal Defences with a new Output 5: Renewable Energy (see below). It also factors in budgets allocated for farm roads in the Jamaica irrigation projects (which have been taken out of Output 4: Irrigation and added to Output 3: Roads) and budget allocated for renewable energy in Jamaica Essex Valley (which have been taken out of Output 4: Irrigation and added to Output 5: Renewable Energy). Calculating impact weightings based on what infrastructure is most transformational was dismissed given the lack of a firm definition of what is ‘transformational’. | Lone Sorensen | 2019-09-26
| Output 1: Water and sanitation infrastructure provided | This indicator has been updated so it asks for disaggregation of male / female headed households to capture gender and poverty dimensions. We have two projects which will contribute to this output. Neither has reached the capital phase, which is why this output currently only has process milestones. As soon as the projects enter the capital phase and the number of households is known, they will be reflected in the relevant milestones as well as the target, with disaggregation. | Lone Sorensen | 2019-09-26
| Output 2: Port infrastructure implemented | The original indicator for this output simply counted completed ports, which did not say much about the specifications of the new ports. It has been substituted by measuring the increase in physical capacity for container throughput (TEU) for the ports built. We have two projects which will contribute to this output. Both are in the design phase, although one (Montserrat) is a design build project and therefore technically a capital project. This is why the output currently only has process milestones. As soon as the projects enter the construction phase and the cargo capacity (TEU) we are building for is confirmed, this capacity will be reflected in relevant the milestones as well as the target. | Lone Sorensen | 2019-09-26
| Output 3: Roads Rehabilitated | A new indicator 3.2 has been added to track that roads are designed to iRAP’s 3-star standards. In the milestones it tracks the completion of road safety assessments and the approval of road designs that make adequate provisions for road safety. | Lone Sorensen | 2019-09-26
| Output 5: Renewable Energy Solutions Installed | UKCIF will no longer take any coastal defence work into the capital phase. The original Output 5 on 'coastal defences' has been replaced with a new output which captures outputs from investments in renewable energy (Barbuda and Jamaica Essex Valley). It has two indictors: One which measures renewable energy capacity installed (mirrors similar indicator in CDB’s Results Framework and speaks to DFID’s International Climate Finance KPIs). The other measures the km of transmission or distribution installed (another indicator from CDB’s Results Framework to ensure alignment). Two projects contribute to this output: Jamaica Essex Valley and the Barbuda Renewable Energy and Resilience Project. The second indicator is only relevant for the Barbuda project. This project has not yet been fully designed and approved. Once this has happened milestones and targets for both indicators will be updated to reflect what the project is expected to deliver. | Lone Sorensen | 2019-09-26
| Outputs 6 – 10 (cross-cutting deliverables) | Original Outputs 6-9 renumbered to Outputs 7-10 with the introduction of new Output 6 | Lone Sorensen | 2019-09-26
| Outputs 6 – 10 (cross-cutting deliverables) | Impact weighting for all cross-cutting outputs reduced from 50% to 40% to accommodate greater impact weighting for infrastructure built, with weightings for sustainability (Output 6), gender (output 8) and resilience (Output 9) set at set at 10% each, and lessons (Output 7) and value for money (Output 10) at 5% each | Lone Sorensen | 2019-09-26
| Output 6: Provisions for sustainability are in place | This is a new output which speaks to the new outcome indicator 5 which measures sustainability by tracking whether there is budget available for maintenance and operations in the following year. At output level this translates into tracking whether operations and maintenance plans have been formally agreed as part of the UKCIF projects. As the main concern here is tracking that sustainability measures have been identified and incorporated – and not whether projects are on track in relation to the rebased programme reflected in outputs 1-5 - it uses the project timelines set out in the most recent visual tracker of June 2019 for the milestones. | Lone Sorensen | 2019-09-26
| Output 7: Key lessons and good practices are documented | A new indicator ‘% of stakeholders who indicate that lessons learned inform UKCIF policy and practice’ has been added to track that lesson learning is not only documenting lessons but also being acted on. It will be measured using a survey, with expected positive responses increasing from 35% to 70% over time. | Lone Sorensen | 2019-09-26
| Output 8: Gender and social inclusion mainstreamed | Indicators remain unchanged but milestones now specify details on which projects are expected to be approved and when they will be in construction and/or have completed. As the main concern here is tracking that gender and social considerations have been included and implemented – and not whether projects are on track in relation to the rebased programme reflected in outputs 1-5 - it uses the project timelines set out in the most recent visual tracker of June 2019 for the milestones. | Lone Sorensen | 2019-09-26
| Output 9: Resilience considerations mainstreamed | The old indicator ‘% of projects with completed climate vulnerability assessment’ has been removed as it was somewhat meaningless because it measured a non-negotiable requirement. The other old indicator ‘# of assets produced, developed, improved or strengthened for climate resilience’ has also been removed as it was simply measuring completed projects. New indictor ‘% of projects designed incorporating climate resilience measures’ has been introduced in their place, with milestones of tracking completion of CVAs and incorporation of CVA recommendations into designs and a target of 100%. As the main concern here is tracking that resilience measures have been identified and incorporated – and not whether projects are on track in relation to the rebased programme reflected in outputs 1-5 - it uses the project timelines set out in the most recent visual tracker of June 2019 for the milestones. | Lone Sorensen | 2019-09-26
| Outcome 2 milestones | Beneficiaries tab added to better capture beneficiaries numbers. This superseedes the table in the 'Detailed Data' tab. Beneficiary numbers updated in the milestone for Outcome 2. | Harriette Stone | 2020-10-27
| Outcome 5 milestones | Milestones changed to 100% of completed projects instead of listing the projects due to be completed. | Harriette Stone | 2020-11-04
| Output Indicator 1.1 | Output indicator change to number of people from number of households. | Harriette Stone | 2020-11-04
| Output indicator 3.2 | Milestones changed to 100% from timeline of project approvals. | Harriette Stone | 2020-11-04
| Output 3.1 | Jamaica projects removed as misleading/double counting with irrigation outputs. | Harriette Stone | 2020-11-04
| Output 5.1 | Jamaica projects removed as misleading/double counting with irrigation outputs. | Harriette Stone | 2020-11-04
| Output 8.2 | Milestones changed to 100% of completed projects. Listings the projects due to be completed has been removed. | Harriette Stone | 2020-11-04
| Outcome 4 | Note added that this indicator is not being tested until Dec 21. | Harriette Stone | 2020-11-04
| All | Output and outcome indicators updated to reflect current projections for project implementation. | Harriette Stone | 2020-11-04
| Output indicators 1.1, 2.1, 3.1, 4.1, 5.1, 5.2 | %age spend has been removed from output indicator milestones. | Harriette Stone | 2020-11-04
| Outputs 1 - 10 | The impact weightings of outputs 1 - 10 have been altered to reflect the increased importance of Output 10. Output 10's weighting is increased to 10%. The additional 5 % has been removed proportionally from Outputs 1 - 5. | Harriette Stone | 2020-11-17
| Output indicators 1.1, 2.1, 3.1, 4.1, 5.1 and 5.2. | The milestones for output indicators 1.1, 2.1, 3.1, 4.1 an 5.1 and 5.2 were revised to reflect updated project timelines, to incorporate a COVID-19 adjustment (Updated project timelines reflect an adjustment of 5 months for TA projects and 4 months for capital projects added to the expected project timelines as at November 25, 2020, as reported in the UKCIF Visual Tracker presented to the UKCIF Steering Committee in December 2020. The wording of milestones for works underway was also revised to capture also capture whether works underway are on track for the agreed completion. | Cherianne Clarke | 2021-10-27
| Output indicator 6.1 | Some explanatory wording was included in indicator 6.1 outlining when/how an Operation & Maintenance plan would be considered formally agreed or formalised, as was recommended in the 2021 Annual Review. The milestones for the indicator were also updated to align with the adjusted project timings reflected in the updated milestones and targets for infrastructure output indicators 1.1, 2.1, 3.1, 4.1, 5.1 and 5.2 above. | Cherianne Clarke | 2021-10-27
| Output indicator 9.2 | Indicator 9.1 was changed from “% projects incorporating climate resilience measures” to “% of projects designed to deliver at least a ‘good’ increase in climate resilience”. Notes on an associated rating system (no increase or poor, good or excellent increase) were included, and the milestones and target were amended for the revised indicator 9.1. | Cherianne Clarke | 2021-10-27
| Output indicator 9.2 | A new indicator “Proportion of projects including all climate resilience aspects from the final designs in the constructed infrastructure” was added, with associated milestones and target. | Cherianne Clarke | 2021-10-27
| Output indicator 10.1 | The indicator wording was changed from “Value of procurements using competition to drive value for money (economy)” to “Percentage of procurements above mandatory CDB financial threshold using competition to drive VFM” and the related notes updated. | Cherianne Clarke | 2021-10-27
| Output indicator 10.2 | The indicator wording was changed from “Planned vs. actual disbursements (efficiency)” to “Percentage of annual workplan budgets actually disbursed in calendar year”. | Cherianne Clarke | 2021-10-27
| Output indicator 10.3 | The indicator wording was changed from “Contracts completed within 12.5% of the original contract amount” to “Proportion of projects completed within 12.5% of the original budget” and the related notes updated. | Cherianne Clarke | 2021-10-27
| Output indicator 10.4 | Indicator 10.4 (streamlined project implementation processes) was amended. Part a) of the indicator (% time taken from appraisal to approval) was removed, given limited utility at this stage. For part b) of the indicator, the wording was changed from “% change in time taken from approval to first disbursment” to simply “time taken time taken from approval to first disbursement” and a new baseline (12 months) and target (6 months) included, reflecting more appropriate and recent CDB information. Part c) of the indicator was changed from "Average (median) length of project extensions" to "length of project extensions (in months)", and new milestones and a new target were added (average project extension relative to original completion time is < 50%average), as well as related notes. No baseline was available for this updated indicator. | Cherianne Clarke | 2021-10-27
| Outcome indicator 3 | The indicator wording, milestones and targets were updated mainly to align with the evaluation data we are actually collecting, supplemented by the project-level perception data that should be collected. The data sources were also updated accordingly. | Cherianne Clarke | 2021-10-27
| Outcome indicator 4 | The milestones and target for this indicator were amended to reflect a target of 10.4 full-time equivalent jobs per $1mn of investment, drawing on recent IMF research and analysis (IMF Working Paper (2021): The Direct Employment Impact of Public Investment). The target wording was also amended to include the aspiration for some of the disaggregated figures. | Cherianne Clarke | 2021-10-27
| Impact indicator 3 (unemployment rates) | A new impact indicator on unemployment rates in beneficiary countries was added, disaggregated by age and sex, to capture the wider job creation/ economic impacts. | Cherianne Clarke | 2021-10-27
| Assumptions column (Impact, Outcome, Outputs 1-6 and Outputs 8-9) | Assumptions have been reviewed and updated as needed. Irrelevant information on old methodology has been removed, and explanatory notes on methodology etc. have been labelled, added or amended as needed, including to reflect the latest changes to indicators and measurement where relevant. | Cherianne Clarke | 2021-10-27
| Data sources | In general, data sources have been added for new indicators, and amended as needed for existing or updated indicators. | Cherianne Clarke | 2021-10-27
| Inputs | FCDO budget input increased to £349.8m as per approved business case costed addendum | Liz Trigg | 2023-10-24
| Timeline for all indicators across logframe | The timeline for the overall logframe was extended to reflect the new end date of the programme - Mar 2026 | Liz Trigg | 2023-10-24
| Impact indicator 1 | Milestones included for extended years, data source updated | Liz Trigg | 2023-10-24
| Impact indicator 2 | Indicator changed from Poverty rate to Human Developement Index (HDI) due to lack of available poverty data. HDI is a better proxy indicator in this context and the data is richer. Baseline set as 2015. Main data source set as HDI Index, with CDB country poverty assessments and Jamaica survey of living as supporting sources. Milestones included for extended years. | Liz Trigg | 2023-10-24
| Outcome Indicator 1 | Process milestones set for review and completion of ERRs for those projects which do not yet have one. Milestones included for extended years, Overall target maintained as portfolio ERR to equal or exceed 12% | Liz Trigg | 2023-10-24
| Outcome indicator 2 | Milestones included for extended years - final target numbers TBC once Grenada Water, Dominica Road and Dominica Water procurements complete. | Liz Trigg | 2023-10-24
| Outcome indicator 3 | Process milestones included for extended years, final target wording clarified - 10 percentage point increase over baseline with more than 50% having positive perception. | Liz Trigg | 2023-10-24
| Outcome indicator 4 | Indicator changed from person days to number of FTE jobs in construction per $1mn USD spend (disaggregated for females and youth where available) to align with CDB measurement criteria for investment - to be measured at end of projects. Milestones included for extended years. | Liz Trigg | 2023-10-24
| Outcome indicator 5 | Indicator wording changed to clarify 'following year'. Milestones included for extended years - requiring funding in place for next year and plans in place for future years. O&M plans included as data source. | Liz Trigg | 2023-10-24
| Output indicator 1.1 | Indicator changed to measure households not individuals due to availability of data and way project designs have been worded. Baseline figures included. Process milestones included and target figures set using data from appraisal documents.. Clarify use of Appraisal Documents as data source for baseline setting. | Liz Trigg | 2023-10-24
| Output indicator 2.1 | Process milestones set for extended years and target reworded to reflect increase over baseline. | Liz Trigg | 2023-10-24
| Output indicator 3.1 | Process milestones included for extended years, target data included from appraisal document data. | Liz Trigg | 2023-10-24
| Output indicator 3.2 | Milestones included for extended years and wording of target indicator clarified - 'designed and constructed to [ ] standard' | Liz Trigg | 2023-10-24
| Output indicator 4.1 | Milestones included for extended years and final target figures included from appraisal document data. | Liz Trigg | 2023-10-24
| Output indicator 5.1 | Interim milestones included for extended years and final target figures updated from revised design data | Liz Trigg | 2023-10-24
| Output indicator 5.2 | Interim milestones included for extended years and final target figures to be updated from revised design data when available. | Liz Trigg | 2023-10-24
| Output indicator 6.1 | Milestones included for extended years and reworded to clarify that O&M plans are only due on completed projects after end of defects liability period. Target reworded for clarity. | Liz Trigg | 2023-10-24
| Output indicator 7.1 | Process milestones included for extended years and target wording edited to reflect new lessons learning plan implementation | Liz Trigg | 2023-10-24
| Output indicator 7.2 | Process milestones included for extended years and target wording edited to reflect new lessons learning plan implementation | Liz Trigg | 2023-10-24
| Output indicator 7.3 | Interim milestones included and target reworded for clarity | Liz Trigg | 2023-10-24
| Output indicator 8.1 | Interim milestones included for extended years | Liz Trigg | 2023-10-24
| Output indicator 8,2 | Interim milestones included for extended years | Liz Trigg | 2023-10-24
| Output indicator 9.1 | Interim milestones included for extended years - following discussion on availability of other measures/indicators it was decided that further work will be carried out to assess other plausible measures in coming months, including on broader measures of resilience and also measurement of climate finance. Resource for this work to be identified. | Liz Trigg | 2023-10-24
| Output indicator 9.2 | Interim milestones included for extended years | Liz Trigg | 2023-10-24
| Output indicator 10.1 | Interim milestones included for extended years | Liz Trigg | 2023-10-24
| Output indicator 10.2 | Interim milestones included for extended years | Liz Trigg | 2023-10-24
| Output indicator 10.3 | Interim milestones included for extended years | Liz Trigg | 2023-10-24
| Output indicator 10.4 | Interim milestones included for extended years but removed measurement against previous year due to impact of external factors on this indicator. | Liz Trigg | 2023-10-24
| Guidance tab | Updated Smart Guide guidance with newer PrOF guide tab | Liz Trigg | 2023-10-24
Changes July 2026
| Outcome 1 | Changed from: ERR for complete projects meets or exceeds the threshold established at appraisal to: EIRR of >12% for completed projects and on track for incomplete projects | Jo Burton | 2026-07-01
| All outcomes | End of programme target moved from March 2026 to December 2026. | Jo Burton | 2026-07-01
| All outputs | End of programme target moved from March 2026 to September 2026. | Jo Burton | 2026-07-01
| Output 1.1 | End of programme target updated from 42.28km in Dominica to 56.7km. | Jo Burton | 2026-07-01
| Output 1.1 | End of programme target updated from 20,924 to 6,751 HHs in Dominica (following reallocation of $13m) | Jo Burton | 2026-07-01
| Output 3.1 | Change indicator disaggregation from site and location to project | Jo Burton | 2026-07-01
| Output 3.3 | Deleted as outout 3.2 already captures design and construction requirements. | Jo Burton | 2026-07-01
| Output 6.1 | Change target from: All UKCIF infrastructure has formally agreed operations and maintenance plans to: all UKCIF completed projects have formally agreed operations and maintenance plans | Jo Burton | 2026-07-01
| Output 7.1 | Change from: Learning plan implemented in accordance with plan details to: Number of workshops/learning sessions held (cumulative). Target = 18 | Jo Burton | 2026-07-01
| Output 7.2 | Change target from: Learning plan implemented in accordance with plan details to: lessons learned knowledge project produced, in line with the concept note agreed between FCDO and CDB | Jo Burton | 2026-07-01
| Ouput 7.3 | Indicator removed. It was more of an outcome than an ouput and the information for this indicator will not be available within the ouput timeline - it was looking at poklicy and practice change. | Jo Burton | 2026-07-01
| Output 8.2 | Change target from: 100% of UKCIF project maintained alignment during the capital phase with social, gender and inclusion strategies and ESMPs during the capital implementation phase to: 100% of UKCIF projects completed in alignment with social, gender and inclusion strategies and ESMPs | Jo Burton | 2026-07-01
| Output 9.2 | Change target from: 100% of projects are on track to be built in accordance with the agreed design, including the climate resilience aspects from the final designs to:Projects are on track to be built in accordance with the agreed design, including the climate resilience aspects from the final design. Output scoring range to align with CRA scoring: LF score CRA average A++ = 5 A+ = 4.5 - 4.99 A = 4 – 4.49 B = 3 – 3.99 C = 2.99 and under CRA score of 4 = meeting expectations. | Jo Burton | 2026-07-01
| Output 10.1 | Inidcator closed in June 2026 | Jo Burton | 2026-07-01
| Output 10.2 | Change target from: >80% (annual) to: £51,228,300 of annual allocated workplan budget disbursed | Jo Burton | 2026-07-01
| Outcome 2 | Beneficary target numbers amended to align with all appraisal documents. Amendments can be found in table to the right* | Jo Burton | 2026-07-01 | * | Original | Revised July 2026
| Outcome 5 | End of programme target changed from: All UKCIF infrastructure have adequate funding available in following year's budget for operation and maintenance and plans for future years' budgets. To: All completed UKCIF infrastructure have adequate funding available in following year's budget for operation and maintenance and plans for future years' budgets. | Jo Burton | 2026-07-01 | Total | 635,280 | 413771
| Outcome inputs HR | Changed from 4.5 FTE to 3.5 FTE | Jo Burton | 2026-07-01 | M | 317796 | 202730
| Outcome inputs £ | Updated based on revised poject profiles | Jo Burton | 2026-07-01 | F | 317484 | 211041
| Output inputs £ | Updated based on revised poject profiles | Jo Burton | 2026-07-01 | Roads | 336000 | 254705
[5 empty] | Ports | 115000 | 115036
[5 empty] | Water and sanitation | 182500 | 41730
[5 empty] | Irrigation | 780 | 1300
[5 empty] | Energy | 1000 | 1000

## PrOF guide
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case.
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.