BUSINESS CASE ADDENDUM

PROGRAMME TITLE	Humanitarian Emergency Response & Stabilisation Operations (HEROS)
Directorate/ Post	HFRD, MCD	Contact name	Ellie Gunningham, Charlie Dale, Joe Marshall
Original programme budget	£81.35m for core service delivery, increased by £18.6m (to £99.95m) with the first extension	Country or region targeted	Global
Cost extension value (if applicable)	£34.85m	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Minister
New increased or reduced programme budget (if applicable)	£134.8m	Original programme start and end dates	01 November 2017 – 31 October 2024, subsequently extended to 31 October 2025
Latest AR programme score	B	New programme end date (if applicable)	31 October 2028
		Programme ID	205176

Detailed information
Programme summary	(250 words maximum) / The HEROS programme is a core part of FCDO’s capability on humanitarian and conflict response. This extension is being sought to give time to ensure a successor programme can be procured, so we can maintain this capability and continue delivery of FCDO’s humanitarian crisis and conflict response. / The HEROS programme provides humanitarian emergency response operations and stabilisation support to FCDO to respond to global humanitarian and stabilisation challenges. It enables the FCDO to respond rapidly, at scale, to global humanitarian disasters and supports work on protracted crises, chronic emergencies and humanitarian reform. It also provides a flexible model to support HMG’s conflict, stabilisation and security work in fragile and conflict-affected states, both during steady state periods and in response to new crises. / The programme is jointly managed by the Humanitarian Crisis Response Department (HCRD) which sits within the Humanitarian, Food Security and Resilience Directorate (HFRD) and Migration & Conflict Directorate (MCD). It is delivered through an outsourced supplier, Palladium International Limited, along with a series of Accountable Grant Agreements with NGO’s and an MOU with OCHA for United Nations Disaster Assessment and Coordination (UNDAC) that are managed on FCDO’s behalf by Palladium. Palladium’s Humanitarian and Stabilisation Operations Team (HSOT) provide technical and operational expertise. HSOT have played a critical role in delivering FCDO objectives on crises such as Ukraine, COVID-19, Sudan, Syria and Israel-OPTs. Since the start of the programme, HEROS has supported over 100 humanitarian responses and worked in 150 countries, including through over 1,500 civilian expert deployments.
Changes	(300 words maximum) / The programme was previously extended to 31 October 2025. Work has since started on the re-procurement of a successor programme, but it has become clear that further time will be needed to design and procure this in a way that delivers against FCDO needs in a changing world and mitigates commercial and legal risks, by ensuring a level playing field and an attractive bidding opportunity for suppliers. Internal consultation with relevant leads, informed by government best practice, has determined that an extension of up to 3 years will be required, which includes 12 months to transition the services to any incoming supplier. / This extension will ensure there is no break in service, which would risk the FCDO losing its capability to respond to humanitarian and conflict-related crises worldwide. / The extension does not include any alterations to the services being delivered through HEROS. The extension will include flexibility to scale down or descope services from the contract or to exit altogether as we continuously assess the value for money of HEROS while we transition towards 0.3% ODA. There will be no changes to the theory of change. / If the programme is not extended, the funds could potentially be used to in-house some of the services provided through the HEROS contract. However, the HEROS programme provides specialist technical and operational expertise, including on humanitarian procurement and logistics, which does not exist in-house and would take longer than three years to build, at potentially greater cost. There would therefore be a high risk of major gaps in service.
Implementation	(100 words maximum) / This addendum does not change FCDO’s approach to implementation and both delivery and governance structures for the current iteration remain the same as in the original business case. / We intend that HEROS 2.0 will now run from 2028-2033, which will push the successor programme back in its entirety, rather than an extension eating into implementation time and budget for the successor programme.
Budget	(100 words maximum) / HEROS consists of core service delivery (funded by HFRD and MCD through the core programme budget) and a scalable component (funded by teams who use the services). This addendum is for the core programme budget. / The original budget was £81.35m, which was increased by £18.6m (to £99.95m) with the first extension. / The total value spent is £86.8m, leaving £13.15m headroom which will be utilised before the contract ends on 31 October 2025. / The 3-year extension will spend up to £34.85m with an annual breakdown as below. This will be paid for from within Directorate allocations, subject to the outcome of the Spending Review. / 1 November 2025 – 31 October 2026 £11.49 / 1 November 2026 – 31 October 2027 £11.52m / 1 November 2027 – 31 October 2028 £11.84m / Total £34.85m
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☐ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☒ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	(100 words maximum) / Irregular extensions to contracts carry legal risk. To mitigate this, we published a Voluntary Ex-Ante Transparency (VEAT) notice in February and held 1-2-1 meetings with suppliers. The VEAT started a 30-day period for suppliers to raise a challenge which has now expired, minimising the risk. / Residual risk remains if we do not do what we said we would in the VEAT and 1-2-1 meetings. We therefore need to continue taking all possible steps to reduce incumbent advantage and actively engage with suppliers. We will also need to ensure we stick to the new published timelines of October 2027/28 for the start of the successor programme.
Results/Monitoring and Evaluation	(100 words maximum) / The extension proposal includes approx. £400k for monitoring, evaluation and learning (MEL) activity which will build on work already being done to improve the quality of data and reporting of results. The HEROS team are already working with FCDO MEL leads to optimise programme MEL and will continue to do so. During the extension period, a full external evaluation of the programme will be conducted. / The theory of change in the original business case remains valid and does not require amendment. Impact and outcome-level results will remain the same.

REVISED APRIL 2025