Project Completion Review

Title: Increasing Access to Electricity in Sierra Leone
Final Project Spend £ (full life): £28,946,270	Review Date:	30 September 2025
Project Code: 205188	Start Date: 19/12/2016	End Date: 30/06/2025

Summary of Project Performance

Year	2017	2018	2019	2020	2021	2022	2024 / (2023 deferred)	2025
Project Score	B	B	A	A	B	B	B	B
Residual Risk Exposure Rating	Mo	Mo	Mo	Mo	Mo	Mo	Moderate	Mo

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/4552508.odt
DevTracker Links to all logframes used during project lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0004120.xlsx

A. Summary and Overview

Description of the project and what it has achieved

The Increasing Access to Electricity in Sierra Leone (Bo-Kenema) Business Case approved up to £31.5 million to improve electricity supply to Bo and Kenema cities and surrounding areas. Major components of the programme were construction of a 33 kV transmission line connecting Bo and Kenema, expansion and rehabilitation of 11 kV distribution networks in the two towns and surrounding areas and the purchase of pre-paid meters for installation largely within Bo and Kenema towns. There were also plans to rehabilitate a hydroelectric dam at Dodo and a fairly small allocation for capacity building. The funds were provided to the African Development Bank (AfDB) which implemented the project and itself allocated up to £11.5 million of funding.

The project was approved on 9 December 2016 and initially expected to run for four years. It was part of a two-year funding boost in UK development assistance to Sierra Leone aimed at kickstarting recovery from the Ebola epidemic and building greater resilience to any future health crises. The time limited nature of the funding uplift meant that investment ready projects were needed, and a project already assessed and designed by the AfDB that would improve energy supply to major urban centres appeared attractive.

The programme actually ran for eight-and-a-half years, more than twice as long as expected. During this time, it scored two As in Annual Reviews (ARs) and five Bs. Two Project Improvement Plans (PIPs) were initiated, the first of which was completed successfully, whilst significant elements of the second were not completed by AfDB. A number of significant scope changes were approved during the programme life including:

- The removal in 2018 of a temporary generation component that would have involved work on the Dodo hydro plant near Kenema and increased diesel generating capacity at Bo. This cut was made because procurement delays meant less implementation than planned occurred during two-year uplift in UK development support following the West African Ebola Epidemic. This scope reduction was accompanied by a reduction of £4.0 million in the ceiling of the Contribution Agreement (£27.5 million) with the AfDB, compared with the original intention (£31.5 million) (the decision was made before the Agreement was finally signed).
- The removal in May 2021 of the capacity building component. This happened when spending on the global COVID pandemic resulted in reductions to UK development assistance, with the capacity building being the only remaining component not already contractually committed. This scope reduction was accompanied by a Contribution Agreement reduction of £672,000 to £26,828,000.
- A design change in April 2022 to construct a 66 kV transmission line connecting Bo and Kenema to the Cote D’Ivoire, Liberia, Sierra Leone, Guinea regional interconnector rather than the 33 kV line in the original specification. The change to a 66 kV line was funded largely through offsetting scope reductions including the use of wooden rather than metal poles across most distribution lines. FCDO also increased its funding under the Contribution Agreement with the AfDB by £867,000 to £27,695,000.
- Two further design changes were approved by EDSA and the AfDB. The first, signed in September 2022, upgraded the design of some transmission line pylons. This resulted in additional cost, and a funding shortfall meant this amendment has not been registered by the AfDB. A final amendment was signed in June 2024 and descoped some 33 kV construction and reduced the specification of some pylons, while adding connections for 10 additional villages. No additional funding was requested from FCDO in relation to these two changes, and they did not result in any amendment to the FCDO Contribution Agreement with the AfDB.

Work was procured under three contracts:

1: Design, supply, installation, and commissioning of two new primary substations between Bo and Kenema and rehabilitation of two city centre substations;
2: Design, supply, installation, and commissioning of overhead transmission lines and rehabilitation of distribution networks; and
3. Supply and installation of prepaid meters within Bo and Kenema and surrounding villages.

The infrastructure constructed and settlements receiving power are shown on the map below:

  4 Substations 10 Villages along Bo-Kenema Highway

This improved the electricity distribution networks within Bo, Kenema and surrounding areas, and connected 48,757 additional customers. It is expected to directly benefit around 316,000 people in Bo and Kenema and surrounding villages in Sierra Leone over the next 25 years. High technical and commercial (T&C) losses, leading to overall utility operating losses, was recognised as a major challenge in the power sector alongside inadequate physical infrastructure. Installation of more pre-payment meters was seen as one way of reducing commercial losses and the installation of these in Bo and Kenema was expected to improve the financial sustainability of the Electricity Distribution and Supply Authority (EDSA) operations in these districts. Other development partners were working to improve EDSA’s operational efficiency including the World Bank through funding of a management contract and work done under the Millenium Challenge Corporation (MCC) Threshold Programme. These interventions did not, however, lead to major reductions in EDSA’s T&C losses and the Government is currently seeking to introduce a long-term operations concession for EDSA.

The project ultimately delivered the planned infrastructure (with scope and budget changes as outlined) and is likely to over-achieve the intended outcome of improved power supply for 316,000 people albeit significantly later than planned. Four outputs - concerning deliver, procurement and management, loss reduction and EDSA management capacity (comprising a 25% weighting) – scored Bs and one output regarding safeguarding, weighted 15%, scored a C. This resulted in an overall project score of B (moderately did not meet expectations).

Major lessons learned, evidence generated and recommendations

There are a number of important lessons from this project. It is unusual for the FCDO to invest in the procurement and delivery of electricity grid equipment. The post-Ebola context was important and projects such as this one would have been expected to provide a valuable and rapid economic stimulus. It is understandable that the FCDO brought in a large organisation like the AfDB, with a project already designed and experience of implementing grid projects. It is also noteworthy that the implementation period straddled some difficult external shocks, in particular the COVID-19 pandemic and reduction in UK Overseas Development Assistance (ODA) from 0.7% of Gross National Income (GNI) to 0.5%. Nevertheless, there are lessons for the FCDO in designing projects and working with multilateral organisations.

- FCDO should understand in more detail the steps needed to start activities. The long delay in the start of this project could have been at least partially anticipated with a better understanding of AfDB procedures. The business case did not discuss the next steps for the AfDB disbursing funds.
- Design issues should be reviewed by an independent sector expert, especially in areas where the FCDO has less experience. The business case argued that a single circuit 66kV line would be 60% more expensive and would not represent good value for money. A double-circuit 66kV line was then introduced later in the programme, funded by a modest increase in the FCDO contribution and savings elsewhere in the programme. The higher voltage and extra circuit will increase resilience and potential voltage stability. Had the line been included in the original specifications, it would have saved time and possible cost.
- The level of technical oversight of the project fell short of the Business Case expectation and should have been prioritised more. The Business Case said the SRO would be a Senior Infrastructure Adviser supported by an Infrastructure Adviser who would work full time on Bo-Kenema. Resource constraints meant a full-time adviser was not contracted and for much of the programme life the FCDO SRO was a non-specialist. This resulted in greater reliance on the AfDB for technical oversight, and the depth of technical engagement was affected by the AfDB decision to base their Task Team Leader outside Sierra Leone. The contract for independent technical review by the consulting engineer was ended and not replaced by local consultants, as had been expected. Design changes from EDSA or contractors were, therefore, largely assessed by AfDB teams outside Sierra Leone, which contributed to delays. In any similar project of this scale, a country based multilateral programme lead should be a requirement for UK funding and independent expertise should be introduced at least periodically in FCDO Annual Reviews.
- Assigning implementation to the EDSA Project Implementation Team (PIT) was also insufficient, as the PIT covers a number of projects and needed a dedicated sub-team to work on Bo-Kenema. Greater thought at Business Case stage should also have gone into the appropriate roles of EDSA and the Electrical Generation and Transmission Company (EGTC) in the project and engagement with EGTC should have been greater.
- Accompanying capacity building activities were essential to sustainability of the programme. The decision to cut funding for capacity building has contributed to knowledge gaps in management of the 66 kV line, lost opportunities to train staff in overall management of the system, and in the failure to make more progress in reducing technical and commercial losses. It will have knock-on effects to EDSA’s ability to maintain and extend the system.
- The Gender and Disability markers for the programme are ‘not targeted’. However, gender equality, disability and social inclusion (GEDSI) targets should be included as part of the log-frame for infrastructure projects of this sort. There are GEDSI issues around grids, their construction and access, and these should have been considered and monitored more. The AfDB also notes “detailed project gender analysis was not undertaken”, and “Gender analysis should be incorporated into the project appraisal and project implementation plan”.
- FCDO should consider the best approach to underperformance in a project implemented by a multilateral organisation, particularly where contractual commitments have been made by the multilateral and funds already disbursed to cover these. A Performance Improvement Plan (PIP) can set out expectations, but where funding agreements only provide for the return of uncommitted funds, FCDO is left with limited leverage. Multilaterals have little incentive to take on commitments based on UK funding if there is no disbursement risk, so other incentive structures should be considered if there is underperformance.
- Safeguarding and a sustainability and exit plan were the main actions remaining in the second PIP. The FCDO should take up with the AfDB centrally, at a senior level, the implementation of its safeguarding policies at a country level, to ensure that they meet agreed standards.
- Clear modalities for community engagement and safeguarding should be written into funding agreements. On this project FCDO often found itself needing to lead engagement that should have been led by the AfDB.

An ICAI report in 2018[1] (after this project was initiated), when reviewing DFID transport and urban infrastructure investments, recommended more realistic timetables for complex infrastructure projects and better assurance of the capacity of multilateral partners to implement safeguarding systems at country level. Both recommendations are pertinent to this PCR.
[1] ‘DFID’s transport and urban infrastructure investments: A Performance Review’, 12 October 2018.

How this report was conducted

The report was written through a combination of desk reviews and field visits. Teams travelled to Bo and Kenema twice for the review: once to interview political leaders and contractors; and a second time to engage with the local communities. The documents considered in the desk review included FCDO Annual Reviews, reports from monitoring visits by the FCDO and the AfDB, and the AfDB’s own Project Completion Report (June 2025). The review team comprised UK and Sierra Leonean staff based in the British High Commission (BHC), Freetown, with an outside view provided by a senior UK-based expert with no connections to the project.

Community Engagement

Actions following approval of this report

Following approval of the PCR:

- The AfDB can continue to receive and pay invoices until 30/10/2025 for work done prior to 30/6/2025. Once all valid invoices have been paid, they will assess whether all UK funds were disbursed. If any UK funds were not disbursed, the balance will be returned to the FCDO.
- If any funds are returned to FCDO, these will be returned to the central contingency fund.
- Audited accounts covering the final period of implementation should still be received from the AfDB.
- This PCR will be published.
- HERA and AMP housekeeping will be completed to ensure the programme budget is reduced to reflect the actual level of spend and any open Purchase Orders will be closed.
- The project will be archived.
There are no programme assets to be disposed of. All development assets, such as transmission lines and substations have been handed over to EDSA.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£32.4million (including £900,000 of design funds. Business Case was for £31.5 million)	£28,946,270
Timeframe	2016 – 2020	2016 – 2025
Outcomes	The expected outcome will be an improvement in the availability and reliability of electricity supply for 316,000 people through the rehabilitation, upgrade and expansion of the Bo - Kenema electricity distribution networks, including replacement and construction of new distribution lines, substations and connections for end users. This will increase electricity access in the project area from 20% to 56% over the next 48 months.	There have been no changes to the outcome or impact indicators from the original business case. The expected outcome is 316,000 people in Sierra Leone (specifically in Bo, Kenema and the surrounding villages) will have improved availability and reliability of power supply. EDSA estimate the number of programme beneficiaries is 334,000, though around 100,000 are not currently benefiting while a fault affecting the 66 kV line is rectified.

Overall assessment of project outcomes, sustainability and VfM

£900,000 of design funds were allocated prior to business case approval and these funded design work that contributed to the business case for this programme and also that underpinned a separate programme – Rural Electrification in Sierra Leone programme (RESL). Prior to design work being undertaken the tentative thinking was to have a single energy programme, but following design work it was decided to have separate on and off-grid programmes. A study looking at mini-grid tariffs was also undertaken using funds allocated under this programme. The outcome from design funds was the design and tariff studies.

Once the business case was approved, the project had the single outcome above.

EDSA have estimated the number of beneficiaries as 334,000, based on the calculation provided below. We have been unable to verify whether the 334,000 beneficiaries will mean the target of 56% access is also achieved. The population of Bo and Kenema is around 1.5m people, which would mean around 90,000 households needed to be connected (based on 6 people per household). The table below demonstrates the calculation is more complicated, including businesses, factories and offices. Nevertheless, the majority of new connections are with households.

The number of people estimated to benefit once all infrastructure is handed to EDSA and the 66 kV line is energised meets the outcome goal. A significant caveat is that insulation problems with current and voltage transformers (CTs & VTs) caused operation of the line to be suspended in June 2025. This infrastructure is part of substations handed over around 18 months before the 66 kV transmission line was energised. The contractor for these substations is in the process of replacing the CTs and VTs, but this is likely to delay reenergisation of the line by around three months. Sustained achievement of the beneficiary target depends on the success of this remedial work, as around 100,000 beneficiaries depend on this line for the improvement in their supply.

The higher voltage (66 kV double circuit, in addition to the 33kV lines) was added to the scope and additional connections without increasing the overall programme cost, though the change led to an increase of around $6 million to the cost of the transmission line contract in isolation.

Although (subject to successfully energising the 66 kV line, the outcome is positive, the expected project timescale was more than double the expectation in the original business case. The main causes were the following:
- Four years was over-optimistic for this sort of project in an environment like Sierra Leone;
- Delivery contracts took two years to put in place;
- The change in scope needed to upgrade the project with the 66kV line took a year to approve;
- Unanticipated right-of-way issues had to be settled along the route of new lines;
- Delay in the supply and delivery of materials and equipment for the lines, and inadequate technical teams on the ground, as identified in AfDB Supervision Reports; and
- The COVID pandemic in 2020 and 2021 made accessing supplies more difficult.

Our assessment broadly concurs with that of the AfDB, as detailed in their PCR. Had the AfDB Task Manager been located in Sierra Leone for the duration of the programme, it would almost certainly have helped mitigate some of the issues that arose with delivery. Funding constraints prevented the FCDO from meeting its original intent of employing an additional infrastructure specialist focused on this programme. Having a full-time adviser might have allowed FCDO to compensate more fully for the absence of a Sierra Leone based AfDB technical lead, though the programme structure gave the AfDB responsibility for agreeing design and monitoring progress and payments so no amount of FCDO resource would have fully mitigated delays resulting from AfDB human resource constraints.

Moreover, safeguarding and gender equality, disability and social inclusion (GEDSI) were not adequately built into the project at the beginning. Coverage of gender in the original business case was limited to possible savings for women collecting firewood for cooking. While access to the grid will enable use of electric cook stoves, it does not guarantee households will convert, given the monetary outlay required. The AfDB Supervision Reports go further, expecting the project to save time and labour on routine domestic tasks and create livelihood opportunities. A separate livelihood restoration activity was expected, and gender results to be collected as the project reached completion. The AfDB PCR reports that 81% of jobs created by the project were filled by men, which they attribute to the nature of the work. Outreach and awareness campaigns at the beginning of the project could have targeted women, but were not built into the project. The overall gender reporting in the AfDB PCR contains a number of assumptions about how women might benefit, but little hard data or analysis. The project was expected to target people who were developmentally furthest behind, and to target female employment during implementation. There were no gender indicators in the logframe, however.

On safeguarding, the FCDO did not have a policy at the time the business case was written, and dangers of exploitation were not raised[2]. There are significant risks in this type of project, where contractors are accessing remote areas and have power to connect people to a valuable utility. Safeguarding issues were first recorded in an Annual Review in 2021, by which time the project implementation had been underway for some time. A safeguarding output was added to the logframe in 2023 (Output 5 below) and some improvements were made in terms of information and communication. Interviews with communities suggested there may have been a safeguarding case that went unrecorded. It was not clear that communities knew how and where to report such cases. Failure to address the issue contributed to a B score in the 2024 Annual Review and safeguarding forming part of a second Performance Improvement Plan (PIP) in 2023. The issues were still not convincingly addressed, however.
[2] The UK hosted a summit on sexual exploitation and abuse in the aid sector in March 2018, and published its first Safeguarding Against Sexual Exploitation and Abuse and Sexual Harassment within the Aid Sector strategy in September 2020.

The AfDB was the implementing partner and responsible for ensuring safeguarding issues were addressed. The organisation has passed the FCDO’s Enhanced Due Diligence assessment. The AfDB argues that the programme was implemented in alignment with their sexual exploitation, abuse and harassment (SEAH) guidance and Integrated Safeguards System (ISS). This included adherence to the Bank’s requirements on risk prevention, awareness-raising, and grievance redress mechanisms. They also believe project execution followed the Bank’s safeguards on environmental and social standards, including provisions related to gender-based violence (GBV) and SEAH. However, they made no progress in delivering the logframe indicator of developing a safeguarding action plan and the PIP effectively remained open. The AfDB’s 27 June – 14 July 2025 supervision report noted that there was a lack of gender and social safeguards support across its energy projects. But it noted that a mechanism for reporting SEAH would be developed. The May 2023 Supervision Report noted that the FCDO had stepped in to boost training and sensitisation around SEAH. The AfDB’s Environmental and Social Safeguards Project Completion Mission Aide Memoire did not mention the PIP or the FCDO’s role in improving safeguards. (They did not meet with anybody from the FCDO.) The AfDB PCR notes that there was no adequate Stakeholder Engagement Plan, no operational Grievance Redress Mechanism, initially no Community Liaison Officer, and the Grievance Redress Committee met only once throughout the project duration. It seems the AfDB consistently failed to address the issue adequately. They appear to have taken a very structural approach: adherence to law, creation of instruments, delivery of reports, creation of and, appointment to certain positions. The absence of reported complaints is mentioned, presumably seen as evidence that there were no safeguarding incidents.

The sustainability of the project depends on the ability of the distribution network operator (EDSA) and to an extent transmission network and system operator (EGTC) to maintain and operate the equipment and lines. Some EDSA representatives have claimed that they are confident that staff have sufficient expertise, although there is recognition that in particular for some new equipment training would be helpful. Successive Annual Reviews raised concerns that staff were not trained to operate the new equipment. There is a piece of software on which they require training: SCADA (Supervisory Control and Data Acquisition). Other projects being planned also incorporate SCADA, and will probably involve some capacity building in its use, . How stable and reliable the network and therefore supply of electricity is, will have a significant effect on future outcomes. The review team visited a chocolate factory in Kenema, supplying chiefly a national market, that was not using the grid for its machinery due to voltage fluctuations. The Ministry of Energy complained to the AfDB Supervision Mission about the stability of the main Cote d-Ivoire-Liberia-Sierra Leone-Guinea (CLSG) high voltage line. Sustainability will also require replacement of faulty parts over time, from wear and tear, but also from theft and vandalism. There is keen awareness in the relevant District Councils that the community needs to play a role collectively in taking ownership of and protecting the investment. Nevertheless, normal maintenance will depend on EDSA and EGTC operating effectively and having budget for monitoring and spare parts. On the former, cuts to capacity building part of the budget in 2021 have increased the risk that the investment is not managed effectively or maintained. The original business case built in a 25% increase in the average electricity tariff, which might support maintenance costs: while there was a tariff increase, its effect was cancelled by inflation and currency depreciation. EDSA needs is to reduce its high technical and commercial losses, which has proven difficult, even with a World Bank supported management contract. The government is currently attempting to concession EDSA, again with support from the World Bank. The AfDB was expected to produce a sustainability and exit plan in January 2023, however it has not been delivered.

Overall, the project appears to have been cost effective. An investment of this scale delivering for approximately £45m, given all of the delays and difficulties during the COVID pandemic, is good value for money. For lines alone, the cost sits at the lower end of the expected cost range. Successive Annual Reviews and monitoring visits indicated that poverty in the region is widespread, the towns are developmentally behind Freetown and the connections are targeting beneficiaries irrespective of social status. A high number of female-owned businesses were reported to benefit. The AfDB reports 445 non-manufacturing SMEs and 100 manufacturing units have been established. Marginalised groups were found to be included in consultations.

Summarise the project’s theory of change and results framework, including any changes to outcome indicators

The theory of change (ToC) set out in the original business case briefly described how a mixture of (i) increased energy generation capacity; (ii) improvements to and expansion of the existing Bo-Kenema energy transmission and distribution lines; (iii) new connections and the provision of metering to raise revenue; an increase in the national electricity tariff; (iv) willingness of consumers to pay for electricity services; and (vi) an improvement in EDSA’s capacity to operate and maintain the network; would lead to an increase in access to and reliability of the electricity supply system which in turn will result in an increase in demand for services. More customers connected to the network were expected to improve EDSA’s revenue base and make it more financially viable. Customers would gain access to cheaper electricity, which would result in more livelihood opportunities along with other social benefits such as health care and education. Efficiency improvements in the network and EDSA’s management, along with a switch from predominantly carbon based to renewable energy sources, would have a beneficial impact on the environment.
The ToC was weakened in 2020, when a World Bank sector project ended without significant improvements in EDSA’s technical and commercial losses. It was further affected by FCDO ODA reductions that led to cutting of the capacity-building element of the project. From 2022 onwards, other issues were brought implicitly or explicitly into the ToC: the targeting of marginalised groups to ensure inclusion; socialising communities to avoid accidental or deliberate damage to equipment; and real terms tariff increase to improve EDSA’s finances. As stated in the previous section, there appears to have been an assumption in the business case and early years of the project that Bo and Kenema were developmentally behind as-a-whole, and that women-owned businesses would benefit, without backing that up with evidence of the population or business make up in the area.

Figure 3:The Bo-Kenema Project Theory of Change under the Original Business Case

## C: Detailed Output Assessment

Output Number and Title	1: Establishment of project management and procurement systems
Output Score	B
Impact weighting (%)	10%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
"i) AfDB grant and loan effective (qualitative) / ii) % of FCDO funds disbursed (from 2022) / "		Loan ratified and grant effective by April 2017 / ii) 70% of FCDO funds disbursed by 2022	i) AfDB grant/loan completed / ii) 100% of FCDO funds disbursed in 2023	Achieved / Achieved
Design and Supervision Consultants contract in place		Contract signed June 2017	Technical Consultant appointed within PIT in 2022. Design and supervision provision fully operational	Achieved, but with significant delay
Engineering Procurement and Construction contract in place		Contract signed Nov 2017	Contract amendments signed on 18/10/2020	Achieved, but with significant delay

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The output was ultimately achieved, however with significant delays. FCDO funds were available when the business case was approved in December 2016. The FCDO’s expectation was that the AfDB agreement with the GoSL would then be rapid, given the needs for post-Ebola recovery, and this expectation was set out in the logframe. However, it was a further two years before the funding agreement was signed, and two years after that before the engineering, procurement and construction (EPC) contract was put in place.

It was evident in the very first AR in 2017 that the timeframe that had been set out by the AfDB was too ambitious. While the loan and grant agreement were signed within two months, it then took time for it to become effective, and for tender documentation to be produced. The EDSA Project Implementation Unit (PIU) needed to be established and trained by the AfDB. The 2018 AR listed further delays but strengthened AfDB capacity and oversight from the GoSL, that led to fast progress in procurement.

It should be noted that the AfDB’s February 2025 PCR Takeaway report states that FCDO funds were disbursed two years after the AfDB’s, and this caused delays. Reporting from 2017-18, including the 2018 AR, shows that the FCDO view was that delays in agreeing a Contribution Agreement and subsequent procurement resulted from very slow staffing of the project by AfDB and a lack of focus and prioritisation within AfDB’s HQ in the early phases. The business case envisaged disbursement of £11.6m in 2017/18 and £21.2m in 2018/19. Yet an agreement was signed between the UK and the AfDB only on 29 August 2018 and the first £6m was disbursed in December 2018.

The Ministry of Energy were unhappy with the work of the design and consulting engineers, claiming that the contracted company fielded experts whose first language was French and spoke limited English. There was dissatisfaction with the resources deployed, though the consultant argued that resources needed to be available to provide effective supervision once work commenced. AfDB monitoring reports suggested technical errors with some of their work. We have not consulted the company that supplied the consulting engineers for their views. Their contract was cancelled in 2022 and an understandable decision made not to procure a replacement, given the expected short timescale to completion. Instead, EDSA intended to recruit experienced technical staff already in-country, who had worked on similar infrastructure projects, but this was not done. Reviews were instead done by government experts, which was reported to have sped up approvals but did so at the expense of an independent review function. That increased the onus on the AfDB TTL to provide a technical review function, but the TTL’s ability to do this was limited by being based in Monrovia and being responsible for multiple projects.

Lessons learned through this output, and recommendations for future programming

A number of lessons were collated under this output throughout project’s lifetime and through the fieldwork conducted for the review:

- The transfer of design responsibilities to an in-country PIU improved approval speed and value for money.
- Stronger governance mechanisms (e.g. monthly board meetings) proved essential for oversight and contractor accountability for timely and quality delivery.
- It is important that implementing partners provide better communication, monitoring, and risk management. The AfDB’s limited responsiveness and lack of in-country presence hindered timely decision-making and supervision.
- The inclusion of the 66kV line at the contracting stage would have saved considerable time. Nevertheless, it should not have taken the one year that interlocuters told us for the AfDB to agree the contract variation.
- It would have been better to appoint a single contractor for both lines and sub-stations. The decision to split into two contracts led to the substations being delivered two years before the lines were completed and energised. The FCDO has been clear from the beginning that the sub-stations should only be completed once they were ready to be energised. The time gap has led to some equipment in the sub-stations needing to be replaced.
- The output description was not changed and its significance reduced as only the funds disbursed remained unmet after 2017. Yet management of the contracts and of the overall project remained a significant issue throughout the project. The output might have been changed to incentivise improvement and might have combined with Output 5.

Output Number and Title	2: Rehabilitation of existing distribution and supply infrastructure
Output Score	B
Impact weighting (%)	50%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Length of transmission/ distribution lines constructed (km): 66kV double circuit 33kV double circuit / 33kV Single circuit / 11kV Single Circuit / 0.4kV	0 / 90.9 / 58.6 212.0 / 816.0	66kV DC - 70.6 KM / 33kV DC - 20.3 KM / 33kV SC - 58.6 KM 11kV - 212.0 KM / 0.4kV - 816.0 KM	Achieved: All transmission lines constructed as per design
# of 33/66/11kV Substations constructed / # of 33/11kV Substations constructed	4 substations	4 substations constructed	Partially Achieved: while the substations are constructed, the substation for the 66 kV line had not been successfully energised at the time of writing the PCR.
# of transformers installed: / 33/11kV / 33/0.4kV / 11/0.4kV	7 0 176	66/33/11kV: 4 installed and commissioned / 33/11kV: 3 installed and commissioned / 33/0.4kV: 25 installed and commissioned / 11/0.4kV: 176 installed and commissioned	Achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The logframe targets were mostly achieved. The transmission line changed from all 33kV to a mixture of 33kV and 66kV. The number of transformers installed also increased. When conducting the review, we viewed some of the sub-stations in rehabilitated buildings and in new structures. It was a transformation compared to the previous system. The 66/33/11kV sub-stations were not energised, however, due to a fault in one sub-station caused by the failure to coordinate completion of sub-stations and lines. We consider the installation to be substantially complete and therefore warrants a B score (moderately did not meet expectations). Significant investment has been delivered. Nevertheless, the continued problems with energising the 66kV line are concerning. Resolving these issues is essential for delivering the benefits intended.

It should be noted, however, that the work consistently underperformed. Annual Reviews show that, until 2021, progress was slow due to COVID-19-related supply chain disruptions and delays in design approvals. Only low-voltage lines (11kV and 0.4kV) saw partial completion, while high-voltage lines (33kV and 66kV) remained stalled. Substations were under construction but not yet commissioned.

By 2022, nearly four substations had been completed, and low-voltage line installation exceeded targets. The transmission line works, however, lagged due to route changes, compensation issues, and delayed AfDB approvals. Transformer installation was also behind schedule, with most units unconnected. Continued delays in transmission line construction over the next 18 months meant that substations could not be energised. The output consistently scored a B, reflecting underperformance despite infrastructure quality.

A new substation and new substation equipment

Interviews and documentation indicate problems with management, including underperformance of the design and supervision consultants, and absence of a resident AfDB Task Team Leader, that contributed to some of the delays. The contractors were not delivering on schedule, and performance improved only when management and oversight was strengthened. A long delay in the AfDB’s approval to a variation agreement, incorporating the 66kV line, was also frequently mentioned. Records of field monitoring by the FCDO began in 2019, and by the AfDB in February and July 2017 (records from the 2017 annual review). The AfDB’s field visits thereafter were roughly every nine months, which was not adequate to make up for the absence of a resident Task Team Lader

Lessons learned through this output, and recommendations for future programming

A number of lessons can be drawn from our interviews and the Annual Reviews:
- The project lacked robust contingency planning and risk funds to manage unforeseen delays and scope changes.
- Design delays and approval bottlenecks significantly impacted timelines and output delivery, for reasons that are unclear. The FCDO’s Appraisal Case appears to have been flawed, as it argued a single-circuit 66kV line would cost 60% more and therefore was not justified. Yet a double circuit 66kV line was then added and the cost ($6-8m) largely absorbed through savings in other areas. The variation agreement required to construct and energise the 66kV line then delayed completion by at least a year, again for reasons that are not clear. Had the 66kV line been part of the original design, the implementation would have been much quicker.
- Right-of-way and land compensation issues also caused delays and might have been anticipated and resolved earlier to avoid construction delays and cost increases.
- The appointment of multiple contractors, as already discussed above, caused unnecessary coordination problems and meant the project moving only at the pace of the slowest contractor/contract.
- The appointment of engineers (ideally including both EDSA and an external party), on the ground, as part of a dedicated project implementation unit (rather than using EDSA’s overstretched PIU) could have speeded up implementation and improved quality of delivery.

Overall, the initial design does not appear to have been robust enough, perhaps due to the post-Ebola context and the desire to stimulate new activity. The AfDB’s PCR also criticises the design: “the coherence between outputs, outcomes, and the higher-level development objectives was not optimally established at the design phase”. Partners were not as ready to start implementation as the FCDO had thought, and changes to design may have been inevitable, as the population of the area grew and local politics shifted. Faster and more adaptive systems for approving changes would have allowed quicker implementation and should be an explicit part of the assessment for long, complicated projects.

Output Number and Title		3: Reduced power losses and improved revenue collection of EDSA
Output Score		B
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Distributions losses (%), defined as Technical and Commercial losses from the distribution system	35% by December 2022		25% by December 2023	Approximately 35%
Number of meters procured and installed under the project (of which 37,000 for new customers).	50,000 individual and 500 business meters, with 37,000 being for new customers		All meters installed by December 2023	Achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The rationale for this output was that investment in the grid needed to be accompanied by measures to increase the revenue stream and reduce losses. The two activities that would contribute to achieving the output were capacity building focused on the operation of the Bo-Kenema system and the investment in new connections and prepaid meters. The first of these activities was cut in 2022, therefore the project was only contributing to the reduction in losses through the installation of prepayment meters from that time, not from improvements in EDSA capacity.

Procurement of meters took place in 2021, four-years after the start of the project. By 2022, installation exceeded expectations, and distribution losses were reported to have dropped from 40% to 35%, though full measurement awaited system commissioning. Beneficiary feedback indicated improved reliability and willingness to pay, though some users perceived faster meter consumption due to more accurate billing. The AfDB Supervision Mission in March 2024 confirmed that all meters had been supplied, installed and commissioned. The meters were designed to be tamper-resistant and mounted on poles to reduce theft and improve billing accuracy. In the field visit as part of this review, we were able to see the meters mounted outside dwellings in Bo and Kenema.

Distribution losses were reduced from 40% to 35% by 2022. Further reduction to 25% has proved more challenging. EDSA Management estimated losses remain around 35%. Lessons included the need to anticipate demand growth, ensure meter coverage for expanded scope, and support EDSA’s operational capacity. Despite delays, the intervention is expected to significantly enhance revenue collection and reduce losses once the full network is energised.

Lessons learned through this output, and recommendations for future programming

The main lesson from this output was that AfDB and FCDO should have worked with EDSA to review the target for installing new meters to align better with the change that introduced the 66kV line and included 12 nearby villages to the scope. The Council leaders in both towns told us that they wanted additional villages to be connected. It is something EDSA should be able to carry out without support; however, it will cost $14-67 per meter (estimated in the 2022 Annual Review) that will have to be covered by EDSA or its new customers. The Review Team heard that the Government of Sierra Leone (GoSL) has signed an agreement with one of the contractors to increase the number of connections, and that the AfDB had given its no-objection, but no money is available in the country allocation. The AfDB confirmed there is no funding.

Output Number and Title		4: Improvement in EDSA's capacity to manage projects and effectively carry out core business
Output Score		B
Impact weighting (%)		5%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Capacity Building and Training Plan	Capacity building plan finalised by Dec 2017		Descoped under budget realignment	Not Met:
# of progress, environmental and social & financial audit reports (quarterly, annual)	16 reports by December 2022		29 reports by December 2023	Achieved
Completion of studies relating to rural off and on-grid tariff methodology and energy needs of health facilities	Survey of sector participants to inform analysis complete by November 2020		RESL tariff analysis, comparative assessment of auction and payment by results models for mini-grids and energy for health work in collaboration with Saving Lives all completed to a high standard by March 2021.	Achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output was scaled back in 2021 in order to reduce the overall budget of the project, as part of the reduction in the FCDO’s Overseas Development Assistance (ODA) budget from 0.7% to 0.5% of Gross National Income (GNI). The weighting was also reduced, from 10% in the early years, down to 5% at the end. The early focus of this output was on establishing reporting systems and designing technical training activities, but a training plan was not delivered until 2019. The training activities were cut in 2021, without any training having been delivered, and the output focused thereafter on reporting. The ARs raise concerns about the impact on EDSA’s ability to operate and maintain the new infrastructure. EDSA told the review team that they were confident their staff have sufficient capability. We were not able to confirm their view independently and have heard anecdotally that training in particular on software like SCADA would be helpful.

In the 2024 AR, it was reported that one of the contractors delivered basic training to 10 EDSA engineers, but the quality and depth of content were limited. Written materials were still pending, and unfamiliarity with new substation technologies persisted.

Despite these challenges, the output consistently scored A, reflecting to an extent the degree of reporting performance. Looking across the period of the project, however, a B is a more appropriate score (objectives moderately not met). This is in part considering the fact that in some instances, issues that we would have expected to have been reported, were only mentioned once on-site visits in person.

Lessons learned through this output, and recommendations for future programming

Training was rightly built into the project at the beginning, as part of a sustainability plan. Therefore, the plan was undermined by the 2021 budget reduction. It would be easy to take a critical review of this decision, but it would be unhelpful without understanding the context. Many projects across the FCDO, including in Sierra Leone, were facing large budget cuts at this time. Trade-offs had to be made. Funding for much of the Bo-Kenema project was already firmly committed and the overall reduction in the budget was therefore relatively small, even if the impact on sustainability was significant. Training should not be seen as optional. There is no evidence, however, that the project team or BHC Freetown saw training in that way. It was one of many difficult decisions that were made across many projects. It should also be noted that there is a degree of responsibility on the counterpart. A removal of training should have been accompanied by a plan of how EDSA and others would ensure suitable upskilling and funding.

The change of scope to a 66kV line was not assessed for training implications. Staff in EDSA are unfamiliar with the required software, as responsibility for 66kV and above should sit with a different organisation (the Electricity Generation and Transmission Company, EGTC). To the extent that EDSA engineers will manage the 66kV line for the Bo-Kenema area, they will need to be able to use the software. The FCDO is exploring training options separate to this programme for EGTC and EDSA.

The issue of theft of equipment was raised frequently by EDSA and the authorities in the Bo-Kenema area. Managing the risk of theft was not built adequately into implementation. Some supervision visits found security around substations was lax. Authorities reported that somebody had been electrocuted when trying to steal equipment from an energised line. The question remains as to whether more of a co-ordinated approach could have been taken with police, security forces and local communities to prevent this.

The FCDO requested that the AfDB ensured proper handover and training are completed before project closure, and to include these elements in a sustainability and exit plan. The plan had not been received at the time of this PCR.

Output Number and Title	5: Improvement in partners' (AfDB, EDSA/PIT and contractors) safeguarding practice down the delivery chain (new from March 2023)
Output Score	C
Impact weighting (%)	10%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Level of implementation of Safeguarding action plan		No target	Safeguarding action plan developed by end April 2023 that is assessed by FCDO to be comprehensive and achievable, and activities implemented as planned	Not achieved: No safeguarding action plan developed by AfDB
i) # of mandatory trainings and awareness raising sessions on social safeguarding including against SEAH conducted by project partners (PIT, Contractors) in target communities / ii) # of mandatory trainings and awareness raising sessions on social safeguarding including against SEAH conducted by FCDO, AfDB and PIT for all staff on BoK		No target	i) 12 Target Communities trained on safeguarding against SEAH. / ii) 1 training session held for all staff on BoK by 30 April 2023 / ii) FCDO judge that all staff on BoK are trained at least once as a minimum requirement, followed by 3 follow up awareness sessions by the 15 December 2023	Partially Met: Awareness raising sessions held in 5 communities on safeguarding against SEAH. 1 training session held for staff on BoK / Met: 1 training session held for all staff on BoK. This was followed by awareness sessions during each field visit
Increased accessibility of reporting mechanisms/pathways for communities and beneficiaries to reporting instances of misconduct, including SEAH by end of April 2023.		No target	FCDO judge through beneficiary feedback that safeguarding reporting mechanism/pathways are sufficiently expanded by end April 2023 and made accessible to all target communities	Partially Met: beneficiary feedback indicates that reporting pathways were not sufficiently expanded and made accessible to all target communities.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output was introduced in 2023 to address safeguarding gaps identified in previous reviews, particularly around SEAH. The FCDO team felt that the gaps in addressing SEAH were sufficiently serious that specific milestones, including a safeguarding action plan, mandatory training for staff and communities, and better reporting mechanisms, needed to be set and monitored. The goal was to improve safeguarding practices among AfDB, EDSA/PIT, and contractors.

Despite FCDO’s efforts—including direct training and community engagement during field visits—progress was limited. AfDB failed to produce the required safeguarding action plan, and no formal training was conducted by EDSA or contractors in the 12 target communities. One training session (organised by FCDO) was held for 18 staff, but follow-up activities were not delivered. Posters and hotline information were inconsistently displayed, and reporting pathways remained unclear to many beneficiaries.

In 2023, the FCDO initiated a second PIP, due mainly to underperformance on this output. By the time the PIP started (April 2023), the FCDO had made its final disbursement. Progress was made in areas such as training of health and safety staff, distribution of flyers and development of hotlines and reporting mechanisms. A number of actions were not completed, however. Awareness raising was carried out in some, not all, communities. The FCDO received neither safeguarding training reports nor a responsible sustainability and exit plan. The PIP was not completed. Of most concern, community engagement during this review raised the possibility that at least one incident may have occurred and was not reported for fear that it might affect access by the community to electricity. The incident has not been investigated; therefore it is not possible to know if an incident actually occurred.

The FCDO’s intervention in this area appears to have improved attention to SEAH, but was probably too little, too late. Failings were brought to light in the December 2021 Annual Review, a year after the publication of the UK Safeguarding Strategy. Discussions between the review team and contractors confirmed that the AfDB focussed on technical issues. The PIT did appoint a community engagement officer. By the time of the PIP, FCDO did not have much leverage on the AfDB and PIT as it had disbursed all of its funding. The PIP may not have had any chance of succeeding, for this reason, and there are lessons for PIPs with projects, such as this one, implemented by multilateral institutions. The only opportunity could have been when agreement was sought to extend the timeline of the project, which was requested in December 2023, March 2024 and April 2025. The submissions for approval of these time extensions do not mention the PIP, therefore it is not possible to confirm whether or not withholding approval subject to more progress on the PIP was considered.

Given the significant failings on safeguarding, it is appropriate to score this output as a C (‘outputs substantially did not meet expectation’).

Lessons learned through this output, and recommendations for future programming

There are a number of clear lessons related to this output.

- Safeguarding should have been integrated into project design and the project management output. The aid industry as-a-whole was less focussed on the issue at that time, which to some extent provides an explanation. It could have been addressed more quickly and firmly after the UK Safeguarding Policy issued.
- The capability of and commitment from implementing partners – in this case, the AfDB – to meet safeguarding standards must be assessed at the country level. The AfDB has received an FCDO Enhanced Due Diligence assessment centrally. Its failure to ensure there was adequate community engagement or to produce a sustainability and exit plan suggests the standard was not met on-the-ground in this project.
- While FCDO-led training and sensitisation will have helped, sustainability requires stronger leadership on the issue from EDSA and the PIT.
- A PIP has not proved an effective instrument to pressure the AfDB on this issue. The earlier PIP, around poor technical delivery, appears to have been more effective, perhaps because it was earlier in the project, when cancellation was still a possibility. For the second PIP, cancellation of funding was no longer an option, and it is not clear what options were considered in the event that the actions were not carried out.

Output Number and Title	6: International Climate Finance (ICF): Key Performance Indicator 15
Output Score	A
Impact weighting (%)	5%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Extent to which ICF intervention is likely to lead to transformational change / i) KPI Box Marking / ii) Qualitative Assessment		i) Box Marking 1 – by December 2024 / ii) FCDO Assessment containing lessons learning and feedback from GoSL on project transformation against ICF methodology note	FCDO Assessment containing lessons learning and feedback from GoSL on project transformation against ICF methodology note	The GoSL had not provided feedback at the time of this review.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output 6 was only introduced in the final AR (March 2024). There were no activities associated with the output, other than assessments of what had already taken place. It evaluates the project against ICF KPI15, which measures innovation, scalability, and sustainability in climate-related interventions. In that regard, the AR concluded there was partial evidence that the project will lead to transformational change, specifically:
- Innovation through the introduction of new substation technologies and integration with the CLSG interconnector.
- Scalability by covering two of Sierra Leone’s largest cities and offering lessons for national energy reform.
- Sustainability via infrastructure designed to last over 25 years, contingent on effective operations and maintenance by EDSA.

The FCDO monitored other ICF KPIs, without incorporating them into the output:
- KPI 2.1, the number of people with improved access to clean energy;
- KPI 6, the net change in greenhouse gas emissions (GHG);
- KPI 7, clean energy capacity installed; and
- KPI 12,	volume of private finance mobilised for climate change purposes.

The 2024 AR awarded a KPI marking of 4 (‘partial evidence that suggests transformational change is likely’), the alternative being 3 (‘not enough evidence yet to assess, or the balance of evidence is inconclusive’). This review agrees with that assessment. A change from power 15% of the time to at least 90%, and a big expansion in access, provides an opportunity for attracting investment in basic processing that would be less competitive if using diesel generators to maintain supply. It should not only reduce GHG emissions (noting that the Bo-Kenema grid supply was also from diesel generators previously, whereas the CLSG line supplying the new grid is supplied by hydropower) and improve local air quality, but it should also create more jobs. Evidence remains partial because:
- At the time of the review, the 66kV line was not yet energised, and it is crucial for greater reliability and stability in the local grid.
- Voltage fluctuations remain a problem (and should be helped by the higher voltage transmission line). The review team visited a chocolate factory in Kenema that supplies Freetown, employing 61 full-time staff and many more on short contracts. It was using grid power for lighting only. The voltage was not sufficiently stable for their processing machinery. Factories such as this one will continue using diesel generators until they can rely on the continuity and stability of electricity supply.
- While reliable and affordable electricity is a critical enabler of transformation, it is not sufficient. There will be other factors, such as transport costs, affordable finance and availability of skilled workers, that will also be important.
- Operations and maintenance of the system will be needed to ensure reliability does not deteriorate over time.

Lessons learned through this output, and recommendations for future programming

There should be another way to incorporate an ICF assessment into projects other than creating a standalone output. ICF is a method of accounting, not a tangible deliverable. The overall project is unaffected by the creation of the output. It is not clear where ICF scoring fits in a PCR, however.

Climate considerations should have been included at the outcome level in the Theory of Change. The main pathway from the project to transformational change is through effective delivery of all of the outputs. There was no other pathway or outputs that would make transformational change more or less likely, without expanding to issues outside the scope of a grid electricity project.

A PCR is not the proper place to carry out a full assessment against KPI 15. A separate assessment should be carried out, using the ICF methodology and the following criteria: increased innovation; leverage/incentives for others to act; scalability; and sustainability.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the project.
The VfM assessment for this PCR is based mainly on the ARs. The final year of the project – which involved two no-cost extensions – was important to ensure that the final outputs were delivered.

The VfM analysis in the business case was based on more reliable and affordable electricity being delivered. Competitive tendering was expected to keep costs down. The project was expected to yield a 20.4% economic internal rate of return (EIRR) and a positive net present value, as well as a 9.3% financial internal rate of return (FIRR). These were considered conservative estimates, with some sensitivity to the timing of the CLSG interconnection and therefore the provision of cheaper generation supply. While the CLSG interconnection did not cause delay, the overall project has been delayed, losses have not fallen to the targeted 20% and the expected real terms electricity tariff increase has not been realised. The model has not been revisited, however, therefore it is not possible to say whether the FIRR and EIRR remained above their hurdle rates. The AfDB PCR assesses that the increased scope of the project and delivery beyond initial expectations will have outweighed any negative impacts on the return.

The project achieved economy through cost-effective procurement and delivery. Materials—such as substations, transformers, and transmission lines—were procured at competitive prices through rigorous tendering and contract variation processes. Infrastructure materials were the main cost driver, making up 80% of the budget. Local sourcing, such as timber poles from Sierra Leone, further enhanced cost-efficiency. Despite inflation and global supply chain disruptions, the project maintained strong cost control. The 2024 AR reported the AfDB’s late notification of a potential $150,000 deficit, which relates to the cost of extending connections to new communities along the 66kV line (see Output 3 above).

The project fared less well on efficiency. While procurement and construction were competitively priced, delays - especially in transmission line works - reduced overall delivery efficiency. Interdependencies between contractors meant that delays in the lines stalled progress in commissioning substations. FCDO had to step in to provide more oversight, increasing staff time and operational costs. Nonetheless, efficiency gains were made through adaptive work planning, such as prioritising low-voltage line installation and sourcing materials locally. The lack of contingency funding limited agility.

Performance on effectiveness was also mixed. While most outputs were eventually delivered or on track, delays impacted the timely realisation of benefits. Substations were built to a high standard and meter installation exceeded targets, contributing to improved energy access and reduced financial losses. However, the removal of capacity-building activities for EDSA weakened long-term sustainability. Despite these issues, the project is expected to lasting infrastructure with potential for transformational impact - if operations and maintenance are properly managed.

The project should have a positive impact on equity by targeting communities that had little or no prior access to reliable power. The intervention supported small-scale traders and households – council leaders spoke about ice traders, for example – with a high proportion of women benefiting from improved energy access for business and domestic use. The project did not explicitly target gender or disability inclusion, however, and could have performed better had it done so. Monitoring visits ensured that marginalised groups were represented in consultations, however engagement often relied on male-dominated community structures, limiting direct participation. Community engagement in general could have been done in a more inclusive manner such as through a mixed approach (not solely open plenary but more interview or focus group based) and using an independent organisation to bring community members together, instead of relying on contractors to do so. The project’s infrastructure-once energised - is expected to provide long-term benefits across social and economic dimensions, contributing to poverty reduction and improved livelihoods.

The project was extended a number of times, as set out in the table below.

Date	Type of Extension	Rationale
December 2020	Time, to December 2022	To accommodate delays caused by COVID-19 and supply chain disruptions.
March 2022	Cost	Contribution to cover the additional costs of right-of-way agreements for the 66kV line. Additional £857,000 cost was within the overall business case ceiling.
June 2022	Time, to December 2023	To allow completion of transmission and substation works following contract variation and COVID-related supply disruptions.
November 2023	Time, to March 2024	To finalise remaining transmission line construction.
February 2024	Time, to June 2024	To finalise remaining transmission line construction.
June 2024	Time, to March 2025	Works to construct the transmission lines had progressed more slowly than expected. A time extension was approved to allow completion of the remaining works
March 2025	Time, to June 2025	To allow project closure.

E: Risk

Overview of project risk during the past year and over the life of the project, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The risk management process for the project was significantly improved over the life of the project and for the past year. The PRO and SRO undertook detailed review of the project risk appetites in light of the changing context in Sierra Leone and continued to monitor this throughout the life of the project.

Risk exposure changed over the past year, with two key risks categories operating outside of risk appetite prior to project closure; these included Public Service Delivery & Operations and Reputational risks appetites. Thus, the ‘lack of detailed responsible handover and sustainability plan for the systems’ and the ‘limited works and technical obstacles identified through outstanding testing that impedes 100% completion’ means that part of the network is not operational at the time of the PCR which risks unsustainability of power supply to the intended beneficiaries, leading to unmet impact for the project. In addition, non-completion presents significant reputational risk to the UK as the majority financier, in terms of value for money of UK ODA spending, as well as delivering fully complete and functional electricity infrastructure, critical to Sierra Leone. In both instances, the FCDO project team was proactive to escalate to the FCDO Development Director and Senior Management levels for necessary actions. These did not however alter the overall project risk rating, which remained moderate overall across all years.

A key risk highlighted during due diligence on the delivery partners were the lack of oversight functions by AfDB given the absence of a dedicated Task Team Manager (TTM) based in Sierra Leone, Deployment of non-resident TTMs working on multiple projects resulted inconsistent engagement from the AfDB and required the FCDO to increase its own engagement to resolve issues where AfDB should have led. Throughout the life of the project FCDO Sierra Leone needed to proactively engage with the GoSL to monitor Bo-Kenema delivery in the absence of AfDB’s own project management presence in Sierra Leone.

The 2018 and 2022 annual reviews recommended the institution of PIPs, in compliance with PrOF Rules following two consecutive B scores in 2017 and 2018 as well as in 2021 and 2022. Both PIPs recommended robust Safeguarding Standards and Protocols, and a Sustainability Plan to be developed by AfDB for submission to FCDO for onward monitoring leading up to the project closure, A safeguarding audit, conducted in 2021, identified a series of SEAH areas in which the project and partners could improve on for quality assurance, compliance with the PrOF and FCDO best practice. In August 2021, a monitoring trip to site confirmed that there were insufficient mechanisms in place and limited understanding of safeguarding against SEAH at contractor-level, largely exacerbated by the demobilisation of the consulting engineers, who were contracted to supervise the risks. Although EDSA/PIU responded by appointing a dedicated Environmental Officer assigned to the project, the FCDO assessment identified gaps throughout the delivery chain which were tested again during the Annual Review field visit in November 2021. As part of that visit, FCDO held sensitisation session with EDSA/PIU, the two Engineering, Procurement, and Construction (EPC) contractors (Alpha T&D and Sinotec) including five communities on safeguarding protocols, accountabilities, and communication channels.

During the last four years of implementation, the FCDO project team prioritised engagement on Environmental and Social Safeguarding risks (including against SEAH) to ensure that partner policies and protocols protect individuals, communities and the environment affected by implementation, alongside ensuring these are adequately applied and monitored down the delivery chain. During quarterly monitoring visits, the PRO and SRO were proactive in engaging on site and first hand with mitigation and response, working with both EDSA PIT and contractors directly to have a keener eye on potential SEAH risks and necessary preventative mitigations. Thus, the 2022 annual review recommended the introduction of a result framework indicator on safeguarding practice against SEAH to support the monitoring and hold partners to account, and FCDO to continue encouraging enhanced leadership on safeguarding from senior AfDB leadership – including through central channels – and within the Sierra Leone Ministry of Energy.

As mentioned in previous reviews, where the project experienced turbulence and increased risk environment, the project overall continued to carry moderate risk. This is because, for the past two years, the project was better able to identify, assess, mitigate, and review risk. FCDO and its partners were able to implement more regular controls and integrated risk as part of day-to-day management of the intervention, promoting more accountability and openness around risks and issues, cemented through the monthly Board meetings.

It is important to note that there are unforeseen and inevitable risks associated to such infrastructure project as Bo-Kenema, including inherent health and safety (H&S) of staff and communities, theft and damage to electricity infrastructure, safeguarding risks among others that can undermine delivery, compliance, and FCDO’s reputation if materialised even after project closure. As a result, a proportionate risk management approach is expected to be in place in order to mitigate such threats going forwards. This will be taken forward by the Ministry of Energy, through EDSA/PIU as part of governance mechanisms.

Update on Partnership Principles

During the last annual review, it was recognised that at the time of approval in 2016, the business case emphasised that FCDO would monitor GoSL’s commitment to the UK Partnership Principles on an on-going basis. Previous updates had confirmed credible commitment by GoSL to three of the four principles: commitment to addressing the enablers and constraints to poverty reduction and progress against the SDGs; commitment to respecting human rights (including the economic, social and cultural rights as well as civil and political rights of poor people) and commitment to strengthening the management of public finances and fighting corruption. However, on the fourth principle – strengthening domestic accountability and enabling people to hold the government and public authorities to account – the BHC has perceived a gradual deterioration in domestic accountability safeguards and democratic governance mechanisms in Sierra Leone in recent years. No concerns were raised with the government following that review since all UK disbursement under this project was made in 2022/23 financial year.

F: Project Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The project’s theory of change relied on a mixture of (i) increased generation capacity coming online within four years of project inception; (ii) improvements to and expansion of the existing Bo-Kenema transmission and distribution infrastructure assets; (iii) new connections and the provision of metering for revenue protection; an increase in the national electricity tariff; (iv) willingness of consumers to pay for electricity services and (v) an improvement in EDSA’s capacity to operate and maintain the network. New evidence from the World Bank’s Energy Access project supports this project’s theory of change. It demonstrated considerable success in reducing technical losses and increasing customer connection in Bo and Kenema.

Delivery: Throughout the period of implementation, this project benefitted from a strong working relationship among the partners including AfDB, the MoE, and the EPC contractors (Alpha TND, Sinotec Co. Ltd, and Shenzhen CLOU Electronics Co. Ltd.). The Minister of Energy through EDSA/PIT continuously demonstrated a strong commitment to the project. Proactive and constructive dialogue on risk and managing the project was evident between EDSA PIT and BHC Freetown and also observed by BHC Freetown between EDSA PIT and the downstream contractors.

However, despite these healthy relationships, there were challenges and areas for improvement in some areas of AfDB project management. Proactive engagement from AfDB with BHC Freetown was well below expectations. The continued lack of in-country presence – especially in relation to the TTM - affected timely delivery of the project. The AfDB responded to FCDO feedback by providing additional oversight. However, the lack of in-country presence at the TTM level remained a crucial weakness. The FCDO project team in collaboration with the Project Implementing Team (PIT) within EDSA were proactive in ensuring monthly board meetings were held as planned, with the PIT Project Manager always ensuring that contractors reports are pulled together into the monthly Board papers for discussions. These meetings were critical to monitoring progress, highlighting risks and challenges for discussion and decision.

The FCDO’s supervision of delivery could have been improved, in two areas in particular. Firstly, the FCDO did not provide an energy specialist in BHC Freetown, despite a Senior Infrastructure Adviser as SRO being part of the business case. For much of the programme, the SRO was not a specialist in energy or infrastructure. Secondly, there does not appear to have been engagement on gender and inclusion early on in the programme, which led to design weaknesses. It is also noticeable that recorded submissions later in the programme for extensions mention neither the safeguarding issues nor the second PIP, which is surprising given the importance of these issues for this programme.

Financial Performance: AfDB Financial management, including disbursement rates to contractors at the early stage of the project was unexpectedly slow but greatly improved over the second half of the project lifetime with little payment delays as confirmed by contractors during monthly board meetings. This was driven by persistent tracking of project expenditure by FCDO project team on a monthly basis during project board meetings as well as during all monitoring visits.

AfDB financial and procurement rules and policies were robust in providing VfM, ensuring delivery of increased project scope within project budget amidst the reductions in FCDO funding due to delays at the initial stage of project implementation.

FCDO disbursed the final tranche payment over the 2022/23 financial year which the Bank committed in line with the project requirements. The programme was expected to complete in 2023, but ended up continuing for considerably longer than expected at the time of final payment. During this time the FCDO continued to monitor and track project expenditure through the quarterly interim financial statements (IFS) from EDSA Financial Management Specialist. Through the Project Board meetings, the team continued to monitor AfDB funds disbursements to contractors on a monthly basis.

Partner Reporting: EDSA/PIT provided prompt and high-quality narrative and financial reporting on project activities throughout the life time of this project through AfDB on quarterly basis. In all instances, these were provided using a robust risk-based approach to engagement between AfDB, FCDO and EDSA/PIT with proactive dialogue on risks and issues that could affect delivery. EPC Contractors performance during implementation of this project could be rated as satisfactory amidst sustained delays which resulted into multiple extensions post 2022.

In addition to quarterly reporting, FCDO received project updates from monthly meetings and narrative reports from PIU, rather than the AfDB. The timeliness of reports was good generally, although the quality required improvement from time to time.

Asset monitoring and control: The project has not had programme assets such as laptops or vehicles being used by the implementing partner. The development assets created, such as transmission lines and substations have all been handed over to EDSA, and there are therefore no assets remaining that require an asset disposal process. Programme assets are recorded in an asset register and checked annually but no such assets existed for this programme. Assets procured by second tier partners to use in contraction of infrastructure to be handed over were not owned by FCDO and were therefore not monitored through the asset register (Rule 27 in the Programme Operating Framework (PrOF) states that “Asset checks are not required for programmes where the funding agreements have made clear that these assets are not owned by FCDO” which was the case here), but FCDO field visits would often visit areas contractors were using for storage to verify that narratives on procurement and delivery were consistent with what was observable on the ground. For example, when distribution lines were being erected in Bo, the team visited the storage area for poles but did not attempt to count them.

Project-level approach to monitoring and evaluation

Monitoring and Evaluation – The AfDB team conducted at least one supervision mission to Sierra Leone every year throughout the project life, apart from a period during the COVID pandemic when travel was suspended by the AFDB (Sierra Leone had also closed external borders for part of the period). FCDO staff were always part of those supervision missions and were party to the aide memoires signed between the AfDB and the Ministry of Energy. These missions supported the training of staff of the EDSA Project Implementation Unit on procurement and financial management. The missions were also critical in identifying the causes of project delays, and proposing solutions. During one of those missions, the AfDB recommended recruitment of a Resident Engineer and procurement specialist to help fast track project implementation which helped to speed up installation works on the 66/33 kV lines. One major outcome of these missions was an improvement in EDSA project and financial management capability recognised by the AfDB Task Team Manager.

FCDO monitoring of the project was consistent over the life of the project, with quarterly monitoring instituted within the project management schedules and followed through each year (again with the exception of a period during the COVID pandemic). These monitoring visits significantly contributed to improved contractors’ activities thereby leading to improved project delivery.

As already outlined, the programme got off to a slow start. As a result, there was underperformance (project scoring consecutive Bs) in the 2017 and 2018 annual reviews, and the project was placed on a PIP. Under the PIP the FCDO ensured that monthly meetings involving EDSA/PIU, AfDB and FCDO took place, and a regular system of narrative and financial reports were provided to us. The FCDO team had constructive engagement with both EDSA and AfDB to understand barriers to progress and to take action accordingly. These engagements were effective in highlighting areas of critical concern, identifying bottlenecks requiring concerted efforts to address delays, and bringing aspects of the project back on track. We also ensured monthly project discussions on risk and mitigating actions were included in every monthly progress meeting. As a result of this, the 2019 and 2020 annual reviews ended up with A scores respectively. However, progress post 2020 annual review was mixed. Primary deliverables within the two remaining contracts were delayed and ran to slower timelines than expected during the first 6 months of 2020. This continued up until end of 2024 with the project scoring three consecutive Bs in the last three annual reviews (2023 annual review was deferred). Underperformance after 2020 resulted partly from slow AfDB approval processes for design changes, but also delays in procurement and shipping by EPC contractors, in part caused by COVID supply chain disruptions.

Over the reporting periods 2021 – 2022/23, there was notable improvements in project performance. For once, the team recognised an improvement in oversight, governance, and monitoring of implementation, which enabled FCDO, AfDB, Ministry of Energy (MoE) and the Project Implementation Team (PIT) to track progress, mitigate risk and manage issues more proactively. This resulted into some notable successes across each outputs. Under output 1, the project management and procurement systems continued to be fit-for-purpose and allowed the project activities to proceed, with 80% of contracted works completed. Under output 2, the substations at Bo, Kenema, Bandama and Bandajuma were constructed, with final electrical works remaining and expected to be commissioned by the Government of Sierra Leone (GoSL) in 2023. The transmission and distribution works progressed well with over 91% of the low voltage network (0.4kV) installed and steady progress on the 11kV, exceeding expectation and visible on the ground.

However, despite these positives, the project encountered additional challenges. The project had to respond to increased human settlement along the transmission route especially around Bo and Kenema (output 2). Subsequent contract variations were required for the 33kV and 66kV redesign which needed additional resources (within the overall financing framework) in order to maintain the scope and allow the project to continue. A time-extension was also initiated to take the project to end December 2023, with the agreed expectation that all works should be completed by June 2023. The above challenges were exacerbated by the African Development Bank taking longer than planned to approve the contract variation, again leading to multiple extensions to project end date, with the last extension ending on 30 June 2025.

Safeguarding issues entered the narrative off the AfDB’s Supervision Reports from 2021. One contractor commented that the AfDB was more focussed on technical details and on pushing them, while the FCDO’s approach was broader and more supportive. That is reflected in the Supervision Reports. The AfDB visit teams were staffed by technical experts and, although safeguarding and gender issues were mentioned, action points were almost entirely technical. Community feedback indicated that contractors did not always communicate clearly who they were and what they were doing.

It would be noted that throughout the life of the project, the FCDO had several cost and no cost extensions to the project leading up to 30 June 2025 (the last no cost extension). All submissions and approvals were duly approved by the Development Director. Additional FCDO funding was approved in March 2022 (within the business case envelope) to extend the agreement with African Development Bank to ensure there is sufficient finance for project activities to be finalised according to the scope agreed - taking into account a change in works required to appropriately respond to an updated environmental and social safeguarding issue. This was then followed by multiple no cost extensions in 2023 and 2024.

During the last extension, the FCDO project team was able to organise bi-monthly meetings between FCDO & AfDB Directors, to improve ways of working and promote senior management engagement to allow for timely completion of the project. This level of engagement was required to ensure that the project delivers on time and within cost.

The FCDO team conducted multiple quarterly monitoring visits to project sites, where they met with representatives of the EPC contractors (Alpha TND and Sinotec) and the EDSA project team to discuss progress, performance, risks and issues, alongside engagement with relevant stakeholders including community members to understand their concerns and also to reinforce FCDO’s zero-tolerance approach on safeguarding through sensitisation sessions in some of the beneficiary communities between Bo and Kenema.

Date of last narrative financial report	13/02/2025	Date of last audited annual statement	07/05/2025