Title: UK Aid Match II
Programme Value £ (full life): £166.22m		Review date: May 2025
Programme Code: 205210	AMP start date: / 19/12/2016	AMP end date: / 31/03/2027

Summary of Programme Performance

Year	2017/18	2018/19	2019/20	2020/21	2021/22	2022/23	2023/24	2024/25
Overall Output Score	A	A	A	A	A+	A+	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/32511147.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/51561965.xlsx

## A: SUMMARY AND OVERVIEW

Description of programme

The UK Aid Match II (UKAM) programme aims to give the UK public a direct influence on aid funding by matching public donations to charity appeals for projects that reduce poverty and contribute to achieving the Sustainable Development Goals (SDGs). The outcome of the programme is for individual projects, funded through UKAM, to support civil society organisations (CSOs) to contribute to the UK’s ‘leave no one behind’ commitments, ensuring the most marginalised benefit equally from the SDGs whilst increasing the UK public's engagement in international development causes.

UKAM is a competitive fund, where applications for funding are received and independently assessed in a two-stage process. The programme is open to any UK-registered CSO, and funds can be used for projects in FCDO priority countries or the 50 countries at the bottom of the Human Development Index. To be eligible for match funding, appeals must raise at least £100,000 and provide at least 400,000 opportunities for the public to view information about the appeal and the match funding offer. Matched funding is provided up to a limit of £2 million per appeal.

The second phase of the UKAM programme started in 2017 and in 2018 the MannionDaniels-led consortium was awarded the Fund Manager contract. To date, the UKAM programme has run five competitive funding rounds. This Annual Review refers to the reporting period March 2024 to February 2025 and during this time there have been no further competitive funding rounds.
[note] The latest round (Round 5) went live in April 2023

Challenges: As with previous years, grant holders and delivery partners have faced complex and evolving operating contexts through 2024. Global economic, security and environmental crises have caused delays and disruptions, making business continuity increasingly difficult. The lasting impacts of COVID-19, budget cuts and reduced funding opportunities have significantly affected organisations, while climate change - through shifting weather patterns and extreme conditions - continues to threaten development efforts. The war in Ukraine, insecurities in South Sudan and Palestine, Trump’s re-election and subsequent U.S. Agency for International Development (USAID) funding freeze, and various government plans to reduce ODA (Belgium, Finland, France, Germany, Italy, Netherlands, Switzerland, UK, etc.) have all added to ongoing uncertainty and risk. UKAM grant holders continue to initiate localisation and devolved power structures with varying effects.

In response, the fund manager has continued to prioritise adaptive performance management and learning to help grant holders navigate these challenges, whilst maintaining ambition on deliverables. This is done with rigorous change management processes (including change logs within logframes) and discussion with FCDO for complex cases. This support has enabled projects to continue delivering impact, with many achieving or surpassing intended goals. Tailored and individual support has been given to grant holders through the report period, enabling consistent performance.
[note] For example, IRC underwent significant adaptations to their "Strengthening Sustainable Nutrition Services and Resilience for Vulnerable Communities in Northeast Nigeria (SSNR)" project in Nigeria, driven by supply chain disruptions affecting the availability of nutritional supplements from World Food Programme and other partners. In response, the project pivoted to a more localised model, using locally available ingredients to produce a nutritional supplement. While this approach offers greater potential for sustainability, it also resulted in higher costs. Consequently, the project had to reduce the number of children and households it could support within the existing budget. These adaptations were made amid a series of major contextual challenges, including severe flooding following the collapse of a dam in Maiduguri, and the closure of several refugee camps.

Summary supporting narrative for the overall score in this review

UKAM has continued to perform well this year, which is consistent with previous reporting periods and is meeting or exceeding expectation at Output and Outcome levels. There has been significant achievement against Outcome 1 (related to total beneficiaries reached through UKAM projects). The details of both Outcome and Output level performance are discussed in more detail in the full Review.

Major lessons and recommendations for the year ahead

Lessons Learned

Enhancing public engagement through report backs
- Report backs continue to be crucial for sustaining public engagement in international development issues in the absence of new public appeals.
- Strategic use of storytelling, media partnerships, and ambassador involvement can significantly boost visibility and credibility for CSOs and projects.
- Ministerial support continues to provide impactful engagement for CSOs and their projects.
Effective Risk Management
- Regularly reviewing and adapting risk management strategies is essential in increasingly challenging and shifting operational contexts.
- Organisational changes in CSOs (e.g., decentralised governance) introduce both risks and opportunities which hold useful lessons for FCDO and wider sector.
- Continuing to support CSO capacity strengthening is key to managing delivery risks effectively.
Adaptive Learning and Communications
- Tailoring learning activities to grant holders’ time and capacity improves relevance and engagement and is increasingly important as the portfolio size reduces.
- New formats like peer carousels have improved learning exchanges and provide a more open way for more CSOs to share learning.
- As the fund scope reduces, reference group meetings have had to adapt to ensure they are engaging and creating useful spaces for feedback and learning.

Evidence reviews to capture evolving fund needs continue to be important:
Given the volatile operating context and changing funding landscapes for CSOs, fund-level evidence reviews remain critical to capture key learnings – both to support CSOs in project delivery and to inform FCDO and other stakeholders for shaping future funding models and development practice.

Recommendation	Owner/ main implementer	Deadline
Recommendation 1: Enhance public engagement of international development causes through quality report backs. Continue to prioritise CSO report backs and fund learning briefs as core mechanisms for driving public engagement and capturing learning. Support CSOs in developing compelling report backs by leveraging existing data and insights, and where appropriate, seek opportunities to enhance visibility. End of project communications messaging should seek to highlight impact, value for money and effective delivery, prioritising human stories that show real world impact. The most compelling messengers continue to be frontline workers and volunteers particularly healthcare professionals, who inspire confidence through warmth and credibility. Local voices are also highly persuasive and stories emphasising local leadership should be prioritised. Conduct evidence reviews to capture best practices and inform future public engagement strategies. This is especially important given ongoing critiques of Opportunities to View (OTVs) as a proxy for public engagement. Individual report backs and related donor engagement remain crucial for assessing the specific impacts of UK Aid Match. See sections B, TOC and output 3 for more detail.	MD	Ongoing
Recommendation 2: Continue to capture effective risk management practices: As the operating context continues to present challenges, the importance of supporting grant holders with effective risk management has become increasingly critical. The fund manager should continue to work with FCDO in this next stage of UKAM to capture these learnings, through a fund-level evidence review of risk management approaches and adaptive strategies – to capture insights and inform future programming. See Risk section E for more detail.	MD	Ongoing
Recommendation 3: Continue proportionate learning content and engagement with grant holders and FCDO. / As the portfolio’s scope reduces, learning events and communications should be proportionate to grant holders’ capacity, time constraints, and evolving needs. The learning plan should actively engage alumni grant holders and FCDO colleagues, exploring alternative models (such as Community of Practice) to foster targeted, peer-led learning. Additionally, opportunities to strengthen grant holder–FCDO engagement should be pursued during the transition period. This could include collaboration with the FCDO Inclusion team, involvement from country offices, and the design of final learning events that maximise value and participation. See MEL section G and output 4 section for more detail.	MD/ FCDO	Ongoing
Recommendation 4: Continue conducting evidence reviews and peer-learning events: The fund manager and FCDO should continue conducting evidence reviews on key issues and topics to strengthen evidence of what works – for example, on topics including: composite scoring; PIP effectiveness; adaptive grant management approaches; strengthening CSO MEL, and safeguarding and financial good practice. See MEL section G, and output 2 & 4 for more detail.	MD	Ongoing
Recommendation 5: Revisions to Fund Logframe: With no further funding rounds or appeals planned, several indicators in the fund logframe are now inactive or no longer relevant. It is recommended that these be reviewed and updated ahead of the 2025–26 annual report. In parallel, the weightings across all outputs (such as Output 3) should also be reassessed to ensure continued alignment with the fund’s current scope and priorities. See B (TOC) and Output 3 for more detail.	MD/FCDO	By end June 2025
[note] Report backs: All UK Aid Match grant holders are required to communicate the success of their projects at specific moments within the project’s lifecycle. This is called reporting back. These moments provide an opportunity for organisations to share stories and achievements from their project with the public, which in turn increases transparency in how the UK aid budget is being spent. Grant holders are expected to report back a minimum of three times throughout a project’s life cycle: three months after the initial fundraising appeal; at the midpoint of the project; at the end of the project.
[note] Opportunity to View: OTVs are a communications measurement used to estimate the number of times a piece of content can be seen by an audience. Common examples include social media followers / subscribers, average website users, media readerships, mailing list subscribers and event attendees.

Portfolio Analysis

Since the start of the UK Aid Match II programme, 101 projects have been funded, operating in 35 countries, across five separate rounds:

- Round One: 26 projects with FCDO matched funding commitments of £42.5 million
- Round Two: 27 projects with FCDO matched funding commitments of £24.8 million
  [note] One grant (Penny Appeal) was subsequently withdrawn following special conditions not being met.
- Round Three: 17 projects with FCDO matched funding commitments of £18.3 million
- Round Four: 17 projects with FCDO matched funding commitments of £22 million
  [note] Round four had 18 appeals, including two as part of the Randomised Control Trial component of the Ipsos Mori and Ecorys external evaluation of UK Aid Match II programme. One of these, Child.org, raised £22,575 in eligible match funding, which was added to their existing round two project (rather than a new project).
- Round Five: 13 projects with FCDO matched funding commitments of £13.5 million.
As of March 2025, 68 grants are now complete, 7 grants have ended, 26 are currently active. During the reporting period, 33 grants were active for all or some proportion of the year. Grant holders reached 800,048 new project participants and 43 submitted annual or project completion reports during the year.
[note] All end of project reports have been submitted and signed off, all end of project requirements have been met. The grant is closed.
[note] All project activities have ended, and the grant holder is working through final reporting activities.
[note] ‘Project participants’ refers to ‘beneficiaries’ – replacing with more inclusive language.

During this reporting year, most active grants had an average income of either +£20M (33%) or £1-5M (30%) - Figure 1.

Figure 1: Average annual income grants (2024-25 – 33 grants)

Appeals

No new funding rounds and appeals were planned for the year.

Live Grants
33 grants were live during the reporting period, and 7 of these ended during the year. These grants are operating in 15 countries across the globe (see Figure 2), with most projects delivering in Nepal (5) and Tanzania (3).

Figure 2: Geographical distribution of all live grants

The two largest sectors in the active portfolio are livelihoods and education, each representing 21% of all live projects (figure 3). Livelihoods received £13.2 million total funding, while education received total funding of £12 million (see Figure 3 below).

Figure 3: Active grants by value of grant and primary sector.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change has remained relevant during the reporting period, supporting a more diverse and engaged UK public in international development and strengthening civil society’s delivery of high-quality, impactful projects. However, with no further appeals planned and a reduced scope of grants, public engagement attributable to UKAM will decrease in the final phase of the fund. Engagement opportunities through the report-back process will be the key mechanism for the fund’s remaining influence on public perceptions of international development, and this will be a key focus for the final phase (recommendation 1). A review of the Theory of Change, logframe and weightings is recommended to ensure relevance to this final stage of the fund (recommendation 5).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact

The intended impact of the programme is to contribute to a decline in poverty in target countries through contribution to the SDGs, and a wider and more diverse constituency in the UK public engaging with international development.

There are two key impact indicators, and the programme is on track to meet them both.

Impact Indicator 1: Proportion of UK Aid Match grant holders who have contributed effectively to the SDGs.

Looking across the full UKAM II portfolio to date, 81% (56 out of 69) of completed projects achieved an A grade, reflecting a strong overall contribution to the Sustainable Development Goals. The remaining 19% of projects, predominantly from Rounds 1 and 2, delivered during the peak of the COVID-19 crisis and were most affected by restrictions and shifting community needs and scored a B. This year, 18 final completion reports were assessed, with 78% scoring A or above, meeting or exceeding expectations.
[note] Impact One methodology measures cumulative fund project scores. This includes all PCR scores and where this is not available, the latest AR score.

Total reach by SDG: A total of 601,934 new project participants were reached by SDG as follows:

- Goal 1: 45,707 people were supported with poverty reduction programming
- Goal 2: 97,701 people were provided with access to sufficient and nutritious food
- Goal 3: 154,775 people supported to live healthy lives
- Goal 4: 61,360 people equitably accessed free or affordable high-quality education
- Goal 5: 4,934 people reached with programming to empower women and girls
- Goal 6: 208,182 people supported with sustainable access to clean water and/or sanitation
- Goal 8: 5,307 people supported to achieve full and productive employment and decent work
- Goal 10: 1,837 people supported to reduce inequalities
- Goal 11: 22,131 people supported to foster and create sustainable cities and communities

Impact Indicator 2: Level of support amongst the UK public for UK aid
The UKAM programme aims to encourage a wider and more diverse constituency of the UK public engaging with international development. This is measured using Development Engagement Lab data on the UK public's attitude. The most recent evidence shows a slight decline in support for aid, with 45% thinking the UK Government should keep or increase its aid budget. This is against a target of 46% (and 51% actual last year).
[note] Data source: Oh, S. 2025. DEL Dashboard - Great Britain January 2025. London: Development Engagement Lab. (data period: January 2024-January 2025).
[note] Oh, S. 2025. DEL Dashboard - Great Britain January 2025. London: Development Engagement Lab. (data period: January 2024-January 2025).

The same survey highlights similar results in Germany and USA, suggesting a more global trend, while in France, there was a 1% increase. Aid reduction announcements have also been announced by various governments in the latter part of the report year, including Belgium, Finland, France, Germany, Italy, Netherlands, Sweden, Switzerland, UK, USA etc. which may further impact public perceptions more broadly, and future Development Lab results.
[note] Oh, S. 2025. DEL Dashboard - Great Britain January 2025. London: Development Engagement Lab. (data period: January 2024-January 2025).

Limitations with this data source have been noted in previous annual reports and remain relevant. UKAM is one of many influencing factors affecting UK public engagement with aid, and with no new and live public appeals, this influence is further reduced (and increases importance of report backs as an influencing mechanism). This will be reviewed as part of the fund learning and evidence reviews and logframe review in the period ahead (recommendations 4 and 5).

Outcomes
The outcome of the programme is for individual projects, funded through UKAM, to support CSOs to contribute to the UK’s ‘leave no one behind’ commitments, ensuring the most marginalised benefit equally from the Global Goals whilst increasing the UK public's engagement in international development causes.  Currently, outcomes are to be achieved through supporting a diverse set of CSOs with advice, guidance, tools, and opportunities to draw on learning from peers and programme experience to strengthen the reach, messaging and success of fundraising appeals, and the management and delivery of impactful projects.

There are three key outcome indicators, and the fund remains on track to meet them all.

Outcome Indicator 1: Total number of beneficiaries benefiting from UK Aid Match II projects (by sex and disability)
800,048 project participants have been reached this reporting year against a target of 700,000. This was achieved through 50 grants, either active or reporting final data. Figure 4 highlights project participants reached by sex, disability and cumulative totals.

Figure 4: Total reach disaggregated.
Characteristic	Total reported reach in report period
Female	466,450
Male	331,488
People living with disability	68,140
Total this year	800,048 (target 700,000)
Cumulative total (round 1-5)	8,349,316 (target 8,249,270)
[note] Disaggregated data does not equal total beneficiary data due to some projects not reporting disaggregated data.

The cumulative reach total is on track (by over by 1.2%) demonstrating that the programme is on track to meet its outcome. As in previous years, a small number of projects account for a large share of this reach, particularly those focused on eye health, public health, and WASH.
[note] For example, UNICEF 269 in Malawi (12% total reach); Sightsavers 265 in Malawi and Uganda (12%)

Disability inclusion: The number of reported participants with disabilities increased from 21,493 to 68,140 this year, which remains well below the 2022 peak of 227,826. This decline reflects fewer disability-focused projects reaching large numbers. However, the recent increase suggests improved data collection techniques can identify more participants living with a disability, even in non-disability-specific projects. A key factor influencing this is the introduction of composite scoring, which weighs gender, equality, and social inclusion (GESI) related performance at 15%. All round four and five grant holders now have GESI action plans with SMART milestones, regularly reviewed with detailed fund manager feedback.
[note] Specific, measurable, achievable, relevant, time-bound (SMART)

Challenges in collecting primary disability data persist, with many projects relying on national census estimates rather than direct data. This issue has been addressed through learning events, webinars, and a 2024 learning brief, and will be further explored through a disability Community of Practice in 2025.

Outcome Indicator 2: Proportion of the portfolio reaching at least 90% of target beneficiaries
While outcome indicator 1 tracks total target participant reach across the portfolio, outcome two assesses project-level performance, measuring whether grant holders reach at least 90% of their target participants. This is a key impact measure, particularly as a few large projects significantly influence overall numbers.

Progress this year remained strong, with 77% of grant holders meeting the 90% threshold, exceeding the 75% target. This aligns with last year’s trends and is a positive result given the challenging operating context.

Outcome Indicator 3: Average number of engagements with the UK public on UK Aid Match II project appeals:
No new funding rounds have been planned, therefore there is no milestone for this outcome during the reporting period.

OTVs present challenges as a metric of engagement success. They are based on average readership per publication, despite the low likelihood that all readers engage with every article. Previous annual reports and discussions with FCDO have highlighted the limitations of OTVs in measuring engagement with a more diverse UK audience. To provide a fuller picture, additional metrics such as social media engagements (likes and shares) and event attendance are also tracked to capture broader public engagement. As part of the fund’s evidence and learning plans, a review of engagements through public appeals and report backs and alternative and complimentary metrics is recommended (recommendation 1 and 4).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The UKAM programme has continued to make good progress during the reporting period, and despite many contextual challenges, has built on previous success and has scored A overall. As noted above, the fund is on track to succeed the milestone for Impact 1, demonstrating effective contribution to the SDGs. Although the public engagement element of the programme has become less significant as it moves through a mature stage of its delivery, overall public support for UK ODA spending hasn’t significantly changed.
Of the 14 output indicators, 8 were achieved or over-achieved, and the remainder were not measured during this reporting period. To build on the success of these scores, the FCDO will further refine the logframe for the next reporting period (recommendation 5). The programme continues to deliver strong value for money based on these results. Further, to date the programme’s highly performing projects have delivered key services to over 8.3 million people in some of the poorest, fragile and conflict-affected countries in Africa and Asia.
As such, the programme is contributing to the UK’s commitments to poverty reduction and leaving no one behind, and to build on the UK public’s generosity in our future partnerships with the UK international development sector, including through match-funding.
[note] International Development White Paper, 2023; International development in a contested world: ending extreme poverty and tackling climate change – A White Paper on International Development (publishing.service.gov.uk)

## C. DETAILED OUTPUT SCORING

Output Title	High quality project management of CSOs ensures that UK Aid Match II portfolio is implemented and delivered effectively
Output number:		1	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Proportion of grant holders on a Performance Improvement Plan (PIP)who demonstrate improved performance	55% of projects on a PIP demonstrate improved performance	71% (5/7) grant holders on a PIP made progress as expected.
1.2: Proportion of grant holders submitting quality reports (quarterly)	75% of grant holders submit good quality reports (quarterly)	85% (quarterly)
1.3: Proportion of grant holders expressing satisfaction with quality of fund management from an annual survey	85% expressing satisfaction with fund manager	100% (12/12 responses)
[note] Respondents reporting completely (75%) or somewhat (25%) satisfied.

There are three output level indicators that contribute towards the achievement of this output, and all have met or exceeded the target. The output score is A+.

Indicator 1.1: Proportion of grant holders on a Performance Improvement Plan (PIP) who demonstrate improved performance. (Moderately exceeded expectation)

During the reporting period, seven grant holders were placed on a PIP. The main reasons for this included challenges with stakeholder engagement, supply chain disruptions, access and communication difficulties, capacity gaps (staffing, resourcing, or project management), weaknesses in adaptive delivery or risk management, and delays caused by external factors such as insecurity, climate disasters, and political upheaval. 71% (5/7) grant holders meet their PIP milestones, and 29% (2/7) partially met milestones.

Project support plans (PSPs) also continue to be an effective, and a less intensive tool for addressing project management challenges. This process is designed to be supportive, collaborative, and non-punitive, recognising adaptive management is critical to successful project delivery. The fund manager, grant holder, and partners work together to identify barriers, agree corrective actions, and set milestones to realign progress, with monthly reviews to track improvements.
[note] Introduced in 2023–24, PSPs serve as a lighter-touch alternative to PIPs, helping grant holders strengthen key project documents (logframe, budget, GESI, sustainability plans) to improve reporting and grant management. While PIPs effectively address underperformance, they can affect team morale and are applied carefully. Some B/C scores at annual reporting reflect gaps in grant management or evidence rather than actual underperformance, requiring a different approach. PSPs provide targeted support without the full weight of a PIP.

Feedback from one grant holder from the fund manager survey about PIPs was: “The project has benefited a lot from the capacity building programmes and the performance improvement plan, the two have significantly helped to raise our performance towards the implementation of the project” Grant holder response from fund management survey 2024.

Indicator 1.2: Proportion of grant holders submitting good quality reports (moderately exceeded expectation)

All reports (quarterly, annual, and completion) are assessed against seven quality criteria: completeness, content, clarity, relevance, responsiveness, accuracy, and timeliness. While this indicator focuses on quarterly reports, the analysis covers the full grant cycle.

The fund manager provides feedback to improve reporting quality and project progress. While annual and completion report scores do not affect progress ratings, poor-quality reports, especially those with data credibility issues, often signal broader challenges, making quality a useful supporting assessment.
UK Aid Match works with a diverse group of UK grant holders and their in-country delivery partners often (and increasingly) through decentralised governance structures meaning the in-country partner is leading. Reports are written by country-based staff for whom English is not a first language, in contexts where digital access is variable. Grant holders also face competing priorities and frequent staffing changes which can impact internal handover processes - all of which can affect reporting quality. Additionally, reporting requirements are perceived as onerous by many grant holders/partners, a recurring piece of feedback. Quarterly report scores serve as a useful indicator for the fund manager to identify where additional support is needed. Scores often fluctuate from quarter to quarter, reflecting staff turnover with different individuals stepping in to complete reports (linked to broader funding uncertainties many CSOs face).
[note] For example, many grant holders rely on field staff feeding into reports using paper-based data collection methods which create a layer of complexity in write up.

85% of quarterly reports were rated good or excellent, matching last year’s 84% and exceeding this year’s 75% target. Of those projects on PIPs / PSPs, 89% (8/9) improved quality of reporting with time, reflective of tailored support and feedback. While annual and completion report quality declined slightly this year (61%) improvements in quality are seen in the upward trajectory of the final reports (86%).

Indicator 1.3: Proportion of successful grant holders expressing satisfaction with quality of fund management from an annual survey: (Substantially exceeded expectation)
The annual Fund Manager Survey is used as a tool to gather grant holder feedback on the Fund Manager’s performance. The survey is anonymous and is open to all grant holders who were active for any part of the reporting period. In February 2025, 100% of respondents gave an overall satisfaction rating of at least 4 out of 5, which is higher than last year’s 78% and surpasses the 85% target.

All respondents reported an open and trusting relationship with the fund manager, alignment on common goals (up from 88% in 2023) and that the fund manager added value to their project (previously 94%). Support for annual/completion reporting was rated good/excellent by 100% of respondents, an improvement from 86% last year, while 92% rated technical assistance in project design, adaptation, and MEL as good/excellent, up from 84% in 2023. These results highlight the integrity of the critical friend relationship between the fund manager and grant holders.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Annual targets were reviewed and extended with FCDO in 2024. Output 1.1 and 1.2 saw a small reduction in % targets to align with the smaller portfolio size and data volatility with percentage ranges.
[note] Data volatility: As the fund enters its final phase with no new funding rounds and a reducing portfolio, data has become increasingly volatile and less representative at fund level. With a smaller sample size, percentage-based indicators are more sensitive to change and can give a distorted view of performance. For instance, the same number of grants triggering a performance improvement plan (PIP) now represents a higher proportion of the portfolio than in previous years. In recognition of this, 2024–25 targets were adjusted to reflect the reduced portfolio size and the continued impact of complex external conditions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned
A key lesson from the report period has been the importance of in-person monitoring and support visits, which are critical for verifying progress, offering support, and building trust with grant holders and delivery partners. The fund manager visited six PIP projects during the period, with FCDO also joining for one visit.
[note] The fund manager visited grant holders in Ethiopia, Nepal, Kenya, Uganda, Cambodia this year. FCDO joined the Cambodia visit. FCDO country offices are also engaged through these visits.

Recommendations from previous AR
- Learning and support: A key recommendation for Output 1 from last year was for the Fund Manager to continue to provide grant support in key areas outlined in the 2023 FMS, including support with collaborative learning plans, safeguarding and accountability mechanisms. This has been done through webinars and infographics, and one-to-one support (online and in-country) with grant managers. With the programme in a late and mature stage, it remains important for learning and support to recognise and respond to this by keeping process changes to a minimum and by supporting grant holders with increased peer to peer learning and sharing experiences within the portfolio network and within the sector (recommendation 3).
- Effectiveness of Performance Improvement Plans and Project Support Plans: The previous Annual Review recommended the continued use of PIPs as a tool to support grant holders. In this reporting period, PIPs have continued to provide effective and proportionate support to grant holders and it is recommended that further learning on the effectiveness of these approaches is reviewed in 25-26 (recommendation 4).
- Maintaining existing processes and compliance requirements: Previous Annual Reviews and feedback from FMS have highlighted the reporting burden on smaller CSOs, and changes were made to reduce reporting as a result (reduced Q4 report alongside annual report). Feedback from grant holders has suggested this was a welcomed change. Additionally, given the mature point of the fund, it has been recommended that minimal changes (additions or otherwise) should be made to key processes and compliance requirements at this stage. This has been actioned and is a contributing factor in the positive results seen in the 2024 FMS.
Recommendations for the year ahead
The fund manager will produce learning briefs on the effectiveness of PIPs/PSPs and monitoring support visits as part of its ongoing evidence reviews in 2025-26 (recommendation 4).
The fund manager and FCDO will also continue to monitor key processes and compliance/ reporting requirements to ensure no major changes in processes are introduced in this final stage (continuing on a recommendation from previous year).

Output Title	High performing programmes delivering Global Goals
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Percentage of individual projects which achieve annual review/ PCR score of A or above	65% scoring A and above (average of two score sets)	Overall average: 63% scored A and above
2.2 Number of people benefitting from improved access to quality basic services	Cumulative total: 2,661,897 / Unique target this year: 500,000 individuals benefitting from improved access to quality basic services	Cumulative total: 2,683,128 (0.8% over target) / Unique this year: 521,231 (4% over target).
2.3 Timely response to humanitarian assistance to reach as many people in need as possible	N/A - No further funds from UKAM to be utilised for humanitarian purposes	N/A
[note] This indicator data covers reports scored within the reporting period Mar 24 to Feb 25, while Impact 1 data covers the cumulative total of the fund from R1-5 to date.
[note] A total of 29 GHs scored an A or higher in their most recent AR or PCR, whilst 17 GHs scored a B or lower. This equates to 63% of the portfolio achieving an A or higher for this indicator.

There are three Output Indicators that contribute towards the achievement of this output. The first two were met, while the third (2.3) is not applicable for this review because there are no further funds from UKAM to be utilised for humanitarian purposes. As such, the overall Output level score is A.

Indicator 2.1: Percentage of individual projects which achieve annual review/PCR score of A or above: (met expectation within MD’s score methodology)
In the report period, 46 reports - 28 Annual and 18 Completion reports were reviewed. Of these, 29 (63%) scored A or above, which is just below the target of 65% for the year.
[note] The data period for this Annual Report covers March 2024 to February 2025. However, two PCR scores and one AR score that were formally signed off in early March 2025 have been included in this year’s dataset. Given the timing of their submission, it was more practical to include them in the 2024–25 reporting rather than delay until the next full reporting cycle.

Challenging delivery context: Compounding crisis and global instability has continued to affect project delivery, with insecurity, political unrest, and climate emergencies impacting projects in Afghanistan, Ethiopia, Mozambique, Nigeria, South Sudan and Yemen. Projects in these locations account for 41% of all B scores. Individual scores are reported and discussed with FCDO throughout the year through the quarterly report process.

Year one annual report scores: Of 28 annual reports reviewed in the year, 12 were for projects reporting in their first year of delivery, with 33% scoring A and above. Early-stage projects are often over-ambitious with workplans / goals, as they also face challenges with recruitment, offices and supplies, partnership building, baseline assessments, and adapting to unpredictable contexts (including fluctuating costs). Data shows that longer-running projects tend to improve performance as they overcome initial hurdles, suggesting that as the fund matures, projects will gain momentum in meeting its Impact one targets. The fund manager will review the effectiveness of various adaptation approaches as part of various evidence reviews (recommendation 4).

Performance improves with time: As with data from the previous two years, there continues to be a trend of performance scores improving with time, both within this reporting period and cumulatively for the fund. Of the 46 reports reviewed in the year, 28 were annual reports and 18 were PCRs. For the annual reports, A and above scores averaged 54% whilst at PCR this was 78%. These trends are reflected across the lifecycle of the fund since 2021, with Impact Indicator 1 showing an average of 81% of all PCRs scoring an A and above, compared to an average of 48% of all annual reports scoring an A or above.

Compound indicator: The current indicator combines two distinct measures of progress - Annual Review (AR) and Project Completion Report (PCR) scores. While these can be distinguished and analysed separately, it is recommended (recommendation 5) that, for future reporting, they are split into two standalone indicators. This would allow for more accurate target setting that reflects typical performance trends over the project lifecycle, where earlier delivery challenges are often resolved by the time of project completion.

Composite scoring: This methodology was introduced for rounds four and five grants to enable a more holistic assessment of progress and creates frameworks for more tailored technical feedback around GESI and sustainability. Grant holder feedback on this approach has been positive to date. The fund manager shared initial insights with FCDO after the launch in 2023-2024, and a full review will be completed after the final cycles of annual and completion reviews in 2025-2026, assessing effectiveness of the methodology.

Indicator 2.2: Number of people benefitting from improved access to quality basic services: (moderately exceeded expectation)
During the reporting period, 24 projects supported 521,321 people with improved access to quality basic services. Of these, 70% (19 projects) exceeded their annual targets. For example, the British Asian Trust exceeded its target more than fourfold, enabling 1,000 women to access financial services against a planned 217. This success was driven by increased awareness-raising, particularly among their disability-focused partner, through promotion of digital wallets, and efforts to support rural women through offline mobile accounts. Similarly, WaterAid in Ethiopia, reached 23,137 people - 149% of their target, using a new gravity-fed system of water supply with a new community, providing climate resilient and inclusive water supply services to a higher number of people than planned. WASH and eye health projects account for a significant proportion of impact within this indicator, with project designs that have high reach, and proportionately high impact.

Overall, cumulative reach for this indicator is on track, with results currently 0.8% above target. Some additional data was excluded from this report due to timing and delayed submission of project completion reports. The outstanding figures will be captured in the next reporting cycle.

Challenging contexts: Some individual grants did not meet their reach and impact targets for this indicator due to contextual challenges (which occurred within 3-6 months of the annual report submission and therefore were not eligible to be rephased). For example, in Nigeria there were challenges with the supply chain for nutritional supplements, delays due to severe flooding which damaged offices and key infrastructure, and a broader growing humanitarian crisis. These contextual challenges reflect the difficult operating context for many CSOs which has been an ongoing discussion / risk for the fund in the year. These shortfalls are anticipated to be met in the following reporting period.
[note] UKAM applies FCDO’s change rules, whereby no changes to logframes or targets are permitted within 3 months of an annual report submission, and only with very strong technical rationale within 6 months of a report submission.

Indicator 2.3: Timely response to humanitarian assistance to reach as many people in need as possible: (Not measured in this review period)
This indicator has not been measured this year as there have been no UKAM programme funds used to support humanitarian responses.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

2.2 refinement: The fund manager reviewed the methodology for 2.2 as part of a data quality assurance exercise and made small refinements to clarify what counts as ‘people benefitting from improved quality basic services’. The methodology refers to each grant holder’s project logframe, measuring the total number of people impacted through relevant logframe indicators within the report period, provided the indicator(s) meet the following criteria. Multiple logframe indicators may be combined to count totals, with calculations made to ensure individuals are only counted once.

(1) Basic public services: Services delivered by a public or para-governmental institution to	meet basic individual or community needs and rights, such as justice, WASH, nutrition,	education, health, and access to formal banking.
(2) Improved access: Project participants must receive services they would not otherwise be	able to access, directly as a result of the project.
(3) Quality: The project must demonstrate that the provided services have a net positive effect	on the recipients and, where relevant, the wider community.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from Previous AR
- Composite score methodology implementation: Following implementation in 2023, the fund manager will continue to use this performance assessment with Round Four and Five grant holders, monitoring its effectiveness as a tool to assess performance – both to strengthen support to individual grant holders, and to inform wider learning for future funding mechanisms (recommendation 3).
- Reflection on support provided: The effectiveness of the support provided by the Fund Manager in MEL and quality of evidence will be further seen in the year ahead with the next round of annual reports. It will be important to monitor this and draw reflections as part of the ongoing evidence reviews, particularly looking at impacts from monitoring and support visits and PIPs (recommendation 4). As noted above, trends strongly suggest that project-level annual report scores will improve over time, particular with the Round 5 grant holders second year reviews due in May 2025).

Lessons learned this year
None specific to this indicator.

Recommendations for the year ahead

Disability inclusion: Learning from grant holders in recent years has highlighted the challenges with mainstreaming disability inclusion for CSOs that are not disability specialists and challenges with monitoring and evaluation of disability inclusion. This was explored in a previous evidence review shared with FCDO in 2023 and has remained relevant to the portfolio in 2024. To strengthen approaches, disability inclusion was a thematic learning topic, with a grant holder discussion series event and summary infographic shared. In 25-26, a disability focused Community of Practice will be explored to further engage grant holders and partners and strengthen projects inclusion approaches and quality of reporting (recommendations 3 and 4).

- Split out indicator 2.1: For the reasons set out above indicator 2.1 combines two distinct measures of progress - Annual Review (AR) and Project Completion Report (PCR) scores within the report year with an average taken for both combined. This compound indicator does not fully reflect the scores for each element, nor take into account the different trajectories for both target and actual. This indicator will be split out into two separate indicators / targets in the coming year’s logframe (recommendation 5).
- The fund manager will review the effectiveness of various adaptation approaches as part of the final learning for the fund (recommendation 4).

Impact data: Several grant holders PCR data was not included in the previous annual report due to timing of report submission and has been included this year. As the fund matures, the fund manager has and will continue to conduct quality assurance across key data sources to ensure all impact data is captured (as noted with refinement of 2.2 above). This will be included as part of a wider logframe review for 25-26 to ensure its relevance to this late stage of UKAM (recommendation 5).

Output Title	Greater diversity of UK public engaged in UK Aid Match II appeals
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of successful CSOs that have not received previous UK Aid Match II funding	N/A - No new funding rounds were planned	N/A
3.2 Opportunities to view UK Aid Match II appeals (average per CSO)	N/A - No new appeals were planned	N/A
3.3 Number of new donors reached through UK Aid Match II appeals (per CSO)	N/A - No new appeals were planned	N/A

There are three Output Indicators that contribute to the achievement of this output – however with no new funding rounds this year, all three had zero targets and actuals to report. The FCDO will refine the logframe, and the weighting for this Output further to reflect the programme’s remaining focus on project delivery and report backs in 25-26 (recommendation 5).
[note] Output 3 was left open with no fixed targets for 2024–25 to enable the fund to remain flexible and responsive to emerging needs, ministerial engagement, and shifting priorities. A similar approach was taken in 2023–24, where no targets were originally planned, but additional impact data was incorporated following the launch of the Street Child 301 appeal in December 2023, which continued into February 2024. With no new funding rounds planned, the Fund Manager recommends that Output 3 be formally closed ahead of the 2025–26 Annual Review, and that its 30% weighting be redistributed across the remaining outputs (recommendation 5).

Indicator 3.1: Percentage of successful CSOs that have not received UK Aid Match II funding (not scored in this reporting period):
Not applicable for this reporting period as there were no additional competitive funding rounds.

Indicator 3.2 Opportunities to view (OTVs) UK Aid Match II appeals (average per CSO): (met)
With no new appeals planned, report backs are the primary way for CSOs to share project successes with supporters. This year, two grant holders secured FCDO support: Scottish Catholic International Aid Fund (SCIAF) partnered with the former Minister for Development Anneliese Dodds on an op-ed in the Scotland Daily Record during the 16 Days of Activism campaign, highlighting their work with survivors of sexual and gender-based violence in the DRC. The Mines Advisory Group also obtained a quote from Mel Gibson, UK Ambassador to Laos, for their Unlocking the Land project, which featured on Relief Web and reached two million OTVs.
The fund manager and FCDO will continue to work closely with grant holders to ensure high quality, engaging and timely report backs. Regular support calls will continue, with a particular focus on round five grant holders, who must complete report backs by July 2026.

Indicator 3.3: Number of new donors per CSO: (not scored in this reporting period)
Not applicable for this reporting period as there were no additional competitive funding rounds.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes to this output during the last year. Output 3 will no longer be measured over the remaining period of the programme. The UK Aid Match team will consider redistributing the impact weighting from this output as part of the logframe review in 25-26 (recommendation 5).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on Previous AR recommendations

- Clear and consistent report backs: Continue efforts to engage grant holders to ensure report backs are thorough, considered and delivered. These remain a key channel for public engagement in this late stage of UKAM. Additional evidence reviews are also recommended to strengthen evidence of what works in CSO-led public engagement (recommendation 1 and 4).
- Explore the value of more flexible and responsive public appeals that can adapt to real-time, time-sensitive opportunities. While UKAM appeals have typically been pre-planned with predetermined partners and content, feedback from 2023–24 grant holders highlighted the benefits of adapting appeals in response to emerging opportunities. This learning will be further examined in upcoming evidence reviews and inform recommendations for future funding mechanisms with public appeal components (recommendation 1).
Lessons Learnt

As above, previous learning related to flexible approaches to public appeals (which came out in 2023-24) extended into 24-25 learning and will be further explored as part of ongoing evidence reviews in 25-26.

Recommendations for the Year Ahead
- The UK Aid Match team will consider redistributing the impact weighting from this output as part of a formal logframe review in 25-26 (recommendation 5).
- It will be important for the UKAM programme team in the FCDO to continue to work closely with the Fund Manager and the FCDO Communications Department to further amplify the report backs where possible, to increase their impact.
- To maximise future engagement, the fund manager will continue to identify opportunities and raise them with FCDO through fortnightly updates and monthly meetings (recommendation 1).

Output Title	Learning from UK Aid Match II contributes to an understanding of how to build and maintain public support for development issues whilst simultaneously building a more diverse, resilient, and effective civil society sector.
Output number:		4	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Proportion of participants reporting that the communications community of practise is useful and relevant	N/a communications community of practice complete	N/A
4.2 Proportion of participants that report making a change in their practice or approach as a result of engaging in the communications community of practice	N/a communications community of practice complete	N/A
4.3 Proportion of grant holders who report satisfaction with learning support from the fund manager	80% satisfaction rate	91% satisfaction rate
4.4 Proportion of the active portfolio of grants engaged with learning and capacity building activities	80% engagement	97% engagement
4.5 Proportion of grant holders who find UKAM learning activities relevant and useful	80% reporting relevance/use.	96% reporting relevance/use.

There are five indicators that contribute to the achievement of this output, two of which were not measured this reporting period. Progress against Output Indicators 4.3, 4.4 and 4.5 have met and surpassed their targets.

Indicator 4.1: Proportion of participants reporting that the communications community of practice is useful and relevant: (N/A - activity completed in 2023-24).
The communications community of practice ended in 2022 as did the consortium partnership with Social Change Agency, therefore this indicator is no longer measured in this/future reporting periods.

Indicator 4.2: Proportion of participants that report making a change in their practice or approach as a result of engaging in the communications community of practice: (N/A - activity completed in 2023-24).
As above, no new results to report, therefore this indicator is no longer measured in this/future reporting periods.

Indicator 4.3: Proportion of grant holders who report satisfaction with learning support from the Fund Manager: Moderately exceeded expectation.
91% of respondents rated learning support from the fund manager as good or excellent. This high satisfaction is corroborated throughout the 2024 fund management survey results: 100% of survey respondents completely or somewhat agreed that UKAM creates a supportive environment for learning, 100% completely or somewhat agreed that an appropriate amount of two-way learning and sharing among grant holders is facilitated by the fund manager, and 100% respondents completely or somewhat agreed that learning support was timely, high quality and relevant to their project.
[note] Fund management survey respondents who selected ‘neither agree nor disagree’ were excluded from the final total number of respondents.

FCDO engagement: FCDO has participated in Reference Group Meetings and events throughout the year. Satisfaction with this has improved, with 71% of respondents agreeing there was sufficient interaction and learning between grant holders and FCDO, up from 60% last year. However, survey data suggests a desire for more direct engagement, which could come through specialist webinars (for example, with the FCDO inclusion team linked to the disability Community of Practice), through in-person learning events and increased collaboration with country offices (recommendation 3).
[note] Although this scored 71% (5/7 responses), the questions had both the lowest response rate (after excluding neither agree nor disagree responses) and the lowest ‘agree’ responses overall - all other questions scored 100% within this subsection of agreement-based questions.

Figure 7 highlights that seven out of ten areas of support provided by the fund manager received 100% excellent or good ratings. While still exceeding the logframe target, capacity building is the area where grant holders felt least supported. Additional qualitative feedback received in the fund management survey and in post-event polls also suggests that cross cutting themes including capacity building, peer learning, and implementing technical guidance within specific contexts, would be useful and relevant to grant holders. This has been incorporated into learning plans for the year ahead, through a planned Community of Practice and more tailored discussion series events (recommendation 3).

Figure 7: Ratings of support

Feedback from one grant holder from the fund manager survey about PIPs was: “the project team have responded well to feedback from the fund manager and have been motivated to following up to meet new standards. This feeds through into the wider organisation as knowledge shared impacts the development of fundraising proposals that will incorporate past learning from FCDO / MD managed grants. Downstream partners have received a lot of capacity building which brings their internal processes, particularly around finances, up to an extremely high standard” Grant holder response from fund management survey 2024.

Indicator 4.4: Proportion of the active portfolio of grants engaged with learning and capacity building activities: (moderately exceeded expectation).

During the report period, 97% of grant holders attended at least one of seven events, with the January Reference Group and Safeguarding webinar most popular, with 74% and 61% attendance respectively. Attendance varied by size of CSO, with the smaller CSOs attending more frequently than larger International non-governmental organisations.

Given the increasingly smaller number of CSOs able to participate and contribute, overall engagement has been positive. The risk of reduced engagement has been discussed and noted in the fund risk register and is anticipated to become more pronounced in this final stage of UKAM. The 2025-26 learning plan has been designed accordingly, allowing flexibility to respond to needs and trends with this final small cohort, as well as alumni.

Indicator 4.5: Proportion of grant holders who find UKAM learning activities relevant and useful: (moderately exceeded expectation).
On average, 96% of poll respondents across seven events found them useful and relevant, increasing to 100% for the sessions on risk, safeguarding, fraud and financial reporting, and the January Reference Group Meeting. Additionally, 97% felt their expectations were met through the events, and 89% would apply the knowledge gained to adapt their project. This feedback has been used to design the 2025-2026 learning plan, with repeat sessions planned for compliance related topics (fraud, safeguarding, reporting).

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The fund manager and FCDO team will review the indicators, revising as necessary to ensure ongoing relevance to the fund late stage and plans for 25-26 (recommendation 5).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on Previous AR recommendations

- It is important for learning and support to recognise and respond to the programme’s mature stage by keeping process changes to a minimum and by supporting grant holders with increased peer to peer learning and sharing experiences within the portfolio network and within the sector. Progress: This has been adhered to through 23-24 with no major changes to processes or templates and is reflected in the positive feedback through the 2024 FMS.
- The Fund Manager should review the approach to grant holder learning plans and give further support as relevant following the next round of annual reports in 2024. Progress: Learning questions and how these connect with the CLPs were reviewed in 2024 to ensure the AR / PCR templates were aligned with the composite scoring methodology.
- It will be a priority for the FCDO team to continue to engage in-person and online with grant holders through similar events and visits. Progress: This has remained a priority for the FCDO team who joined most events / webinars, and reference groups in 2024, as well as the in-person support visit to Cambodia.
- The Fund Manager will develop a learning and communications plan as part of the follow up to this Annual Review, with input from the FCDO, taking account of the mature stage of the fund, the contract timelines, and key feedback from the annual Fund Manager survey. Events and support will have more of a focus on grant holder led peer learning as well as ongoing grant management support as relevant. Progress: Plan was developed and implemented.
- Ensure that relevant lessons learned from this, and previous, UK Aid Match II, are incorporated into the design and implementation of future FCDO match-funding programmes. Progress: lessons reviewed and incorporated where relevant as part of ongoing work.
Lessons learnt
Adaptive Learning and Communications
- Tailoring learning activities to grant holders’ time and capacity improves relevance and engagement and is increasingly important as the portfolio size reduces.
- New formats like peer carousels have improved learning exchanges and provide a more open way for more CSOs to share learning.
- As the fund scope reduces, reference group meetings have had to adapt to ensure they are engaging and creating useful spaces for feedback and learning.

Recommendations for the year ahead
Continue proportionate learning content and engagement with grant holders and FCDO. As the portfolio’s scope reduces, learning events and communications should be proportionate to grant holders’ capacity, time constraints, and evolving needs. The learning plan should actively engage alumni grant holders and FCDO colleagues, exploring alternative models (such as Community of Practice) to foster targeted, peer-led learning. Additionally, opportunities to strengthen grant holder–FCDO engagement should be pursued during the transition period. This could include collaboration with the FCDO Inclusion team, involvement from country offices, and the design of final learning events that maximise value and participation (recommendation 3).

## VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the Business Case

Economy: The fund’s main cost drivers are staff and operational expenses for effective management. A skilled team ensures value for money by balancing performance and costs. Key systems include due diligence, quarterly financial reporting, and annual audits, ensuring quality procurement, cost control, and competitive spending.
- Due diligence ensures that grant holders have appropriate policies and processes in place, with special conditions applied as needed to strengthen systems and support reporting and monitoring. All moderate and above conditions are included in grant agreements and tracked in the fund manager’s system. Round 1-5 had a total of 728 recorded special conditions, of which 97.7% have been completed, while 3 conditions (1.5%) remain active with ongoing monitoring of due dates
- Financial reports ensure thorough examination of transactions, with any excessive or ineligible costs addressed with grant holders. The annual financial review confirms that funds are being spent as planned, primarily on project activities and staff costs, with a small proportion allocated to NPAC/overheads—aligning with pre-agreed funding levels
- Audits ensure that strengthened policies and procedures from due diligence are being maintained
- Grant portfolio activity levels remain consistent with plans, and in some cases, have exceeded expectations within the fixed price of the fund manager contract. This has resulted in a greater volume of activity at no additional cost, delivering strong value for money.
Efficiency: UKAM integrates efficiency measures through quarterly key performance indicators (KPIs), ensuring timeliness, accuracy, and quality. All efficiency KPIs were met during the reporting period. Key efficiency drivers include:

- 90% of disbursements to grant holders completed within five working days of receiving funds from the FCDO; 100% of fraud and safeguarding cases formally reported to the FCDO within one working day of being notified.
  [note] A payment tracker is submitted to FCDO quarterly as evidence.
- Timeliness of core activities is closely monitored through quarterly KPIs, ensuring efficient management. Routine processes, such as financial claims, grant report reviews, and report back processing, follow pre-agreed timelines and are reported on each quarter. All KPIs have been met
- The fund manager uses Grantelope, a bespoke online grant management system that streamlines reporting by enabling grant holders to upload technical and financial reports in one place. This system enhances efficiency by enabling the fund manager to review claims/reports, provide feedback, and track submission timeliness effectively
- Routine monitoring systems and accessible web-based guidance ensure grant holders have the information they need and understand reporting and delivery expectations. Updates based on portfolio-wide lessons are shared through recorded webinars, while reporting format changes are minimised to prevent disruptions.
## Effectiveness: UKAM II remains on track to achieve its intended outcomes and impact within the agreed financial parameters, successfully meeting its effectiveness measures. The programme continues to reach beneficiary targets, enhance UK public engagement, and contribute to global development goals. Key effectiveness measures include:
- Quarterly and annual reporting - the key tools for ensuring that projects remain on-track - and active risk management with a risk tracking and escalation system, means that projects can adapt to changes in contextual risk and if necessary, as noted above, performance improvement plans put in place
- Consistently high output-level project scores and beneficiary reach demonstrates that the portfolio is effective in reaching its targets with 69% of all UKAM II grant holders that have completed their projects having met or exceeded their outcomes scoring an A or above and contributing effectively to the SDGs
- In this reporting period the programme has generated over 15.5 million OTVs engaging the UK public through a range of channels. This is despite no appeals or funding rounds being planned this year. The content of the messaging met the requirements of the Narrative Project, promoting positive messages of enabling development partners to succeed and thereby having a positive and effective impact on the sector
- The grant holders consistently rate the support from the fund manager highly and this is a direct result of the fund manager ensuring that the performance and learning support is relevant and appropriate. Hosting learning events online has meant that both grant holders and downstream partners can participate which has led a trend of improved performance of grant holders over the timeline of the projects.
## Equity: UKAM has been designed to align with FCDO development priorities which places an emphasis on supporting the most vulnerable, and to contributing to global equity goals. Equity measures such as disaggregation of project participant numbers and monitoring of targeted project participants have been built into the programme logframe indicators. Examples of how equity is being delivered are as follows:
- The fund manager assesses the targeting strategy of projects to ensure they are meeting the most vulnerable and marginalised populations. Assessments at annual review examine the extent to which equity aims are being met, alongside the review of disaggregated targets and milestones which have been reported in the progress against outcome section
- The objective driving the learning agenda is equality and ensuring that lessons are generated across the portfolio that are relevant to most grant holders and that high levels of participation is achieved. The fund manager has produced a series of learning pieces focusing on disability and lessons to improve data collection on disability within programmes.
To encourage diversity of funding and therefore more equitable results, the fund manager targets CSOs that are new to UKAM funding and smaller CSOs to encourage them to apply. Within round five, 69% of successful organisations have an average annual income of less than £20 million compared to round four (55%), and this round had the highest number of organisations (46%) who were new to UKAM compared to previous rounds.

Assessment of whether the programme continues to represent value for money
Overall, the programme continues to represent good value for money. Cumulatively, 8,349,316 project participants have been reached through the programme, against a cumulative target of 8,249,270. Furthermore, 77% of the portfolio have reached 90% of their target number of project participants, and 78% of projects have scored A or above at project completion. As such, the programme continues to contribute to achieving the SDGs and provide support to the most marginalised. The Fund Manager has continued to demonstrate strong performance as evidenced throughout the report. Ongoing engagement with grant holders and the capture and dissemination of lessons learned (both to grant holders and within the FCDO) will be increasingly important as the programme enters this final phase of delivery. It will be vital for relevant lessons learned from the UK Aid Match programme to be considered for any future programming.

## E: RISK

Overview of risk management
The overall programme risk level is moderate and has remained at moderate level over this reporting period.

Programme level risk management

The UKAM risk programme level framework, updated monthly with FCDO, tracks 14 portfolio risks - two new, three current, and nine ongoing, across people, finance, and policy/programme categories. The fund manager and FCDO have agreed mitigation measures for all risks, reviewed monthly in contract management meetings.
During the reporting period, four risks were retired following discussions with FCDO. Two new risks were added: the USAID 90-day funding freeze, and high programme staff turnover in CSOs - both posing potential challenges to programme success. Mitigation measures have been agreed upon and actions implemented in coordination with FCDO.
The programme continues to be impacted by fragile operating contexts, leading to setbacks, delays, and grant holders requesting no-cost extensions or budget revisions, affecting performance and financial forecasting. Inflation, cost of living, and exchange rate fluctuations further challenge budget management. To mitigate these risks, the fund manager has provided ongoing support, regularly reviewing workplans, budgets, and forecasts while enhancing performance management and adaptive strategies. Despite these challenges, the programme remains on track.

Project (portfolio) Risk Management
The fund manager takes a proactive approach to risk management, supporting grant holders in mitigating and adapting to escalating risks. All grant holders maintain quarterly updated risk registers, reporting on materialised risks and mitigation efforts, with performance and risk managers providing feedback and follow-up. The most significant issues are tracked and reported to FCDO monthly.
Throughout the year, UKAM has operated in fragile, conflict-affected contexts, with delivery (28%) and contextual risks (30%) being the most reported challenges. Political instability in Afghanistan, Ethiopia, Mozambique, Nigeria, Pakistan, South Sudan, Yemen, and Zimbabwe, along with elections in Mozambique, Tanzania, and Ghana, has required careful stakeholder management to prevent delays. Conflicts in Ethiopia, Mozambique and Sudan led to adaptive programming and operational adjustments, including project relocations (Leprosy Mission).
Economic volatility, including inflation and exchange rate fluctuations have added pressure to project budgets, exacerbated by the USAID 90-day funding freeze, which introduced risks around cost-sharing and staffing. Climate-related disruptions, including flooding, drought, and cyclones, further impacted implementation for some projects. Additionally, high staff turnover (linked to wider instability) has increased risk of institutional knowledge retention and programme continuity particularly as projects move towards completion.
To mitigate these challenges, the fund manager conducted a portfolio-wide risk review, strengthened adaptive management approaches, and prioritised business continuity planning, ensuring projects remain on track despite a complex risk landscape. Safeguarding and compliance efforts were also prioritised, with targeted action plans developed following October’s webinars. Despite these risks, proactive mitigation strategies have helped maintain programme performance.
As UKAM enters its final phase, business continuity amid global economic and geopolitical instability remains a top priority. Ongoing engagement with grant holders and FCDO will ensure emerging risks are addressed proactively, minimising disruptions to project delivery (recommendation 2).
## Fraud
UKAM has a zero-tolerance approach to fraud and the misappropriation of funds. All consortium partners and grant holders are supported to report fraud, bribery, theft or misuse of funds securely and confidentially through the external whistleblowing hotline service and/or through the FCDO reporting concerns mechanism.
[note] https://www.gov.uk/government/organisations/foreign-commonwealth-development-office/about/complaints-procedure#reporting-fraud-or-corrupt-practices
This year, six cases have been reported and investigated. Four cases have had relevant action taken against the perpetrators and lessons learned implemented to mitigate future occurrences. Two cases remain open.

The fund manager is responsible for case management of all instances of fraud, including the requirement to report fraud to FCDO within a 24-hour window. FCDO are kept informed of the progress of these cases through monthly meetings, and quarterly when the fund manager presents statistics showing the trends identified.

Overall, the most common reported fraud cases involve asset theft and bribery. Zambia and the Central African Republic account for the highest number of cases, and a large number were linked to one grant holder in Zambia, involving thefts from school storerooms, primarily food supplies. Although this project has ended, the issue was discussed with the grant holder, emphasising the need for stronger mitigation measures in future projects to minimise the risk of food supply theft.
## Audits
During the report period, 12 light-touch remote audits were conducted with a reclaim total of £2,277.35, from 10 grant holders. All were cleared with minor issues, related to:
- Missing receipts for small value expenditure in remote locations
- Inconsistences in supporting documentation
- Miscoded budget lines
- Transactions not recorded in the currency they were incurred
- Delayed payment processing
- Lack of cost share policy/ mechanism
## Safeguarding
During this reporting period, four new safeguarding cases were opened with FCDO, including one involving multiple historical cases.

In October 2024, a safeguarding and fraud webinar series covered FCDO reporting requirements, barriers to reporting, and contextual safeguarding, featuring grant holder speaker Restless Development. Key takeaways were shared via an infographic with grant holders, partners, and FCDO.

Safeguarding updates are integrated into quarterly reports and Safeguarding Action Plans for all round four and five grant holders. Safeguarding remains a priority in all in-person visits, ensuring continuous reflection on and improvement of project-level safeguarding measures.

## F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Forecasting

The fund manager has continued to work closely with grant holders on improving annual and quarterly forecasts. Grant holders’ forecasts are risk rated, according to the performance, between forecast and actual expenditure, consistency in forecasting performance, and the alignment of the forecast, with the budget and workplan. Red ratings require a discussion between the fund manager and the grant holder, and in some cases results in forecast revisions. The risk ratings are then used by the fund manager to further risk-reduce the quarterly and annual forecast submitted to FCDO.

As of 28 March 2025, the annual forecast for the 2024-2025 financial year stands at 109% of the original FCDO budget. The variance is due to underspent funds being reprofiled from 2023-2024 into early 2024 - 2025, due to project delays and no-cost extensions resulting from challenging operating contexts. This is a result of the fragile, conflict-affected environments in which many projects operate. The issue has been reported and discussed with FCDO monthly through the programme-level risk management procedures.

Annual Financial Review
The financial reporting and forecasting framework of UKAM is linked to the process for making claims for disbursement. On a quarterly basis all grant holders are required to submit a (quarterly) financial report and updated forecast to claim further disbursements. These quarterly claims are made in either of two windows – one in the first month of the quarter, and one in the second month.

During the reporting period, the fund manager processed and approved 159 financial reports. Total grant holder claims invoiced to FCDO between March 2024 and February 2025 (based on date of invoice to FCDO) is £15,281,183.
[note] This includes claims invoiced between March 2024 – February 2025 – noting February claims payments will be made to grant holders in March 2025.
The total fees and expenses invoiced for the year is £1,668,034 including VAT.
[note] This is the contractual amount payable for the contract year 1 Mar 24 to 28 Feb 25. Actual invoices raised and paid in the same period will vary to this, due to timing - Dec-Feb period invoices are raised in March. Actual value of invoices raised from 1 Mar 24 to 28 Feb 25 is £1,576,262 including VAT.
The full annual financial review for 2024-25 will be provided once all information has been processed following the close of FCDO financial year 31 March 2025.
## Assets
A revised approach to the management and disposal of assets was introduced March 2021, and continues to be implemented and improved. This has proved an effective means to manage assets and the asset disposal process. Since March 2024, 19 transfer requests have been approved by FCDO. The remaining 19 grant holder asset registers will be processed by the end of 2025.
## IATI
Support with IATI continues as standard: All grant holders are provided with guidance during the set-up phase and compliance with IATI reporting is monitored on a quarterly basis. The fund manager publishes IATI data on all transactions received by FCDO and disbursed to the grant holders under the UKAM II programme.

Contract Management and KPIs

Contract management is carried out through a regular programme of formal meetings with FCDO to monitor performance and risk throughout the year. The contract management approach is formed of the following meetings:
- Weekly informal updates: The fund manager meets with FCDO weekly to discuss any updates and issues arising
- Monthly meetings: The monthly meetings allow for detailed discussions to take place regarding the ongoing portfolio, programmatic issues arising and to monitor programme risks
- KPIs / quarterly reporting: KPIs are set quarterly, supported by a detailed quarterly report. A formal quarterly review meeting finalises KPI sign off, linking achievement to fund manager payment.

Throughout the reporting period all reports have been submitted on time, and 100% of KPIs have been achieved on time and to quality.

## G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The fund manager has implemented a comprehensive MEL strategy to strengthen CSO capabilities and generate robust evidence on UKAM’s impact. This includes project-level support (logframe refinement, MEL plans, independent evaluations, and reporting quality), portfolio-wide monitoring of indicators and KPIs, and a structured learning strategy to capture and apply lessons at both project and portfolio levels. Key outcomes from this monitoring and evaluation are summarised in the outcomes and outputs sections above.

As outlined in the 2025-26 Learning and Communications Plan, the fund manager has adopted a light-touch ‘Triple Loop Learning’ approach, which progresses from operational insights (loop one) to causal analysis (loop two) and strategic reflection (loop three). Grant holder and partner-led learning has primarily focused on the first two loops, while broader learning for FCDO and MannionDaniels will incorporate deeper strategic insights from loop three.

This ‘Triple Loop Learning’ approach has provided a simple framework to help structure grant holder and portfolio-level learning activities, providing greater cohesion and strategic direction in learning data generated. Within this approach, the UKAM learning strategy focuses on the following areas:
- Creating a supportive environment for individual grant holder and applicant learning
- Facilitating collaborative and collective learning between grant holders
- Identifying and sharing sectoral insights, trends, and lessons from across the portfolio
- Enhancing understanding on the role of CSOs in engaging the public and reducing poverty
- Understanding UKAM‘s effectiveness as a grant mechanism and manager.
## Creating a supportive environment for individual grant holder learning
The fund manager developed a strategic learning plan integrating routine learning and communication activities under three core themes: Safeguarding and Participation, Sustainability, and Disability Mainstreaming. These themes, shaped by grant holder and partner feedback, guide key activities such as events, webinars, podcasts, and infographics to enhance knowledge sharing and sector-wide impact.
Learning activities this year included the publication of three podcast episodes, eight newsletters, and 12 news items, alongside seven country and regional infographics. Key guidance documents on GESI, annual and completion reporting have been updated, and a safeguarding infographic was shared following related webinars. New initiatives include a peer learning carousel at the July reference group, an in-country learning event in Nepal. Grant holders receive one-on-one MEL support from performance and risk managers and fiduciary risk officers, assisting with logframe design, data collection, reporting, and troubleshooting – in a critical friend relationship. Additionally, grant holders had access to seven virtual events throughout the year, enhancing collaborative learning and MEL capacity. These included:
- Two webinars: Providing guidance on new approaches, templates, and advice based on portfolio-level trends
- Three Discussion Series: Peer learning sessions with presentations from grant holders on diverse and cross-cutting topics
- Two Reference Group Meetings: Held bi-annually to ensure accountability between the fund manager and grant holders, with networking opportunities.
Despite a smaller portfolio and concerns about event fatigue, engagement with learning activities remained high this year. In 2024-25, 97% of the active portfolio attended learning events, with 96% of poll respondents finding them relevant and useful.
As the number of active grant holders has decreased, the average number of attendees per event has dropped from 40 to 30. However, virtual events have increased access for international partners, including downstream and implementing country teams. As the portfolio continues to reduce, the fund manager will explore diverse event options, both in-person and virtual, to optimise frequency, relevance, and encourage meaningful grant holder participation (recommendation 3).
## Facilitating collaborative learning
This year’s learning plan focused on enhancing collaborative learning, starting with a one-day event in Kathmandu in April 2024, where five grant holders participated in interactive sessions on fraud, risk, and communications. Three discussion series events were held, with seven grant holders sharing good practice and learning from their projects. These had average attendance of 26 participants per session, representing 52% of active grant holders. Feedback has been positive, with 96% of attendees finding the events useful, up from 93% last year. The most popular session, “Safeguarding: Balancing protection and participation,” received 100% positive feedback from attendees. Downstream partners made up 7% of the average attendees across all events, consistent with their representation in compliance webinars.

In addition to these regular events, the fund manager will seek further engagement with grant holders and alumni as part of its ongoing evidence reviews - to further understand the impacts of organisational changes, including efforts to decentralise governance structures, deliver programmes through local partners and engage community actors in more participatory processes (localisation) (recommendation 4).
[note] ‘Localisation’ is a broad term, with many interpretations and meanings, and subject to a growing body of research, discussion and debate. Bond has a growing bank of resources on the topic here.
## Communications resources
In addition to the collaborative learning events, the fund manager has produced various supplementary resources, including podcasts and infographics. These resources have been shared through quarterly grant holder newsletters and on the fund manager’s social media platforms.

UK Aid Match has a podcast channel called ‘The Learning Post’, which aims to share news from grant holders, projects and wider stakeholders with both grant holder and partner networks and the UK public. Three podcast episodes were released this year:
1. Organisational approaches to disability inclusion: Insights from MannionDaniels, fund manager for UKAM focuses on how to strengthen organisational disability inclusion, including recruitment and reasonable adjustment.
2. Towards gender justice in the DRC: How SCIAF is supporting survivors of sexual and gender-based violence, discusses SCIAF’s six-pillar approach to supporting survivors of sexual and gender-based violence, with the inclusion of two powerful case studies by Centre Olame, SCIAF’s and their downstream partner.
3. Sustainability in action: Ripple Effect and mdsustain share their journey discusses sustainable agriculture and green futures through Ripple Effect’s partnership with mdsustain.

Table 11: Podcasts download and completion rate.
Podcast episode	Downloads	Completion rate
Organisational approaches to disability inclusion	28	92.37%
Towards gender justice in the DRC	52	83.78%
Sustainability in action	30	61.11%
[note] Completion rate refers to rates of listeners who listen to the entire episode, rather than stop before it ends

This year, podcasts averaged 36 downloads per episode, up from 30 last year, reflecting stronger audience engagement. The strategy of releasing one podcast per quarter, focusing on grant holder and project-led content, likely contributed to this growth. The average completion rate for episodes has increased to 79%, up from 65% last year and 59% the year before. UK listeners still lead in downloads, accounting for 61%, compared to 45% last year. To diversify the audience, two out of three podcasts featured speakers from outside the UK, and a March 2025 episode was led by downstream partners in Uganda.
## Monitoring and support visits
The fund manager conducted four in-person monitoring visits this year, with FCDO joining one of these (Cambodia). These visits covered five grant holders in Nepal, one in Uganda, one in Kenya, and two in Cambodia. These key countries host multiple projects facing challenging delivery contexts. Support visits were rated extremely or significantly useful in the Fund management survey. The field visits provide an opportunity to understand in depth the project context and stakeholder relationships as well as to hear from project staff and participants about key successes and challenges. These visits also include discussing and providing support with fiduciary management, safeguarding, GESI approaches, participant feedback mechanisms, evidence quality and reporting issues.

No in-person fiduciary audits were required this reporting period.
## Identifying sectoral insights and trends
As the grant holder pool naturally decreases, a decline in engagement with learning products and events was expected; however, continued engagement and positive feedback have remained strong. The fund size will be monitored, with a focus on tailoring learning activities to the remaining cohort’s needs. Mixed engagement patterns indicate a growing interest in thematic topics like safeguarding and compliance, with a preference for collaborative learning, such as discussion series and breakout room reflections. This will be explored further in the upcoming disability theme, with plans to include a 'community of practice' based on recent feedback.
## Enhancing understanding of the role of CSOs in public engagement
The fund manager closely collaborates with grant holders on their report backs to their UK supporters to ensure they provide meaningful updates on the impact of their donations, including holding individual calls with grant holders to discuss expectations. Grant holders are continuously encouraged to share project achievements and impact with their supporters, with the overarching objective of improving public perceptions of international development with the UK public. Ministerial engagement remains a high impact mechanism for public engagement which the fund manager will continue to encourage (recommendation 3).
## Fund communications
### Report backs
This year, grant holders completed 28 report backs, sharing news through impact videos, supporter magazines, and social media posts. Most grant holders met the agreed timelines, with flexibility granted to accommodate specific needs, such as aligning with International Awareness Days or focusing on other priorities like global conflicts outside of UKAM.

This year, grant holders accumulated 15,551,118 Opportunities to View (OTVs), with more to be added as engagement trackers for three of the 28 report backs are still pending. On average, OTVs were 622,044 per report back, down from 1 million last year and 630,887 in 2023. Notable contributions include 2,893,455 OTVs from UNICEF, amplified through Soccer Aid’s channels, 2,013,074 from Mines Advisory Group, who secured a quote from actor Mel Gibson, UK Ambassador to Laos, and 1,833,959 from the British Red Cross. Data shows that the first report back typically garners higher OTVs than mid-way and final report backs.

However, figures remain strong throughout the project cycle, highlighting that grant holders can achieve solid engagement when supported to deliver impactful communications. Considering the challenging funding landscape for CSOs amid the global economic crisis, report backs remain a key mechanism for grant holders to engage with supporters and the wider community.
### Outreach
The quarterly grant holder newsletter has seen a slight decrease in open rates this year, from 67% last year to 57%, though this remains strong compared to the industry average of 20%. Engagement metrics have increased, from 14% last year to 28% this year, thanks to continuous monitoring of link use, content, and design. Popular content includes impact stories, new podcast episodes, and grant holder guidance.

The alumni newsletter, targeting both UKAM and UK Aid Direct grant holders, achieved an average open rate of 45%, down from 57% last year. However, engagement metrics per newsletter have increased, from 4% last year to 13% this year.

FCDO engagement: To enhance FCDO in-country engagement with UKAM projects, the fund manager produced four country and three regional infographics for FCDO priority countries. These infographics offer a comprehensive overview of projects, including key impact statistics, project reach data, and sector focus. They have proved valuable during monitoring visits, fostering stronger relationships between grant holders, the fund manager, and FCDO country offices.
## Feedback mechanisms and accountability
The six-monthly reference group meeting, the annual reporting process and the annual fund manager holder survey are the three main mechanisms by which the fund manager seeks feedback from grant holders. The reference group is an interactive forum whereas the survey and annual report questions solicit structured feedback. An average of 28 grant holders have attended the two sessions held this year, with sessions covering the themes ranging from the 2023 Fund management survey results, reduced quarterly reporting, and the first grant holder learning carousel format, with a wider range of short grant holder presentations and Q&A.
12 active grant holders shared feedback in this year’s fund management survey. This is a decrease from the previous two years but expected due to the shrinking nature of the portfolio. Initial findings have been highlighted throughout this report, and a full analysis will be shared with the FCDO as part of the follow-up to this annual report.

Date of last narrative financial report	April 2025	Date of last audited annual statement	December 2023