## IGC 2024 Annual Review

Title: International Growth Centre (IGC) - Phase 3
Programme Value £ (full life): £57.4 million		Review date:
Programme code: 205219	AMP start date: October 2019	AMP end date: September 2026

Summary of Programme Performance
Year	2020 (Feb)	2020 (Sept)	2021	2022	2023	2024
Overall Output Score	A	A	A+	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Project GB-1-205219 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-205219/documents

## A: SUMMARY AND OVERVIEW

Description of programme
The International Growth Centre was established by DFID in 2008 in response to the findings of the Growth Commission, an independent body that examined economic growth and development, and which identified the need for more independent research into the elements of economic growth necessary for countries to develop. It is delivered by the London School of Economics (LSE) in partnership with the University of Oxford (Oxford). Phase 1 of the programme ran from 2008 – 2013. Phase 2 began in 2013 and ended on 30th September 2019. The current phase, Phase 3, began operations on 1st October 2019 and runs to September 2026.
The programme aims to promote sustainable and inclusive economic growth in developing countries through four key functions:
1. the provision of high-quality independent, practical and demand-responsive policy support and research to developing countries, drawing on a network of researchers and experienced practitioners;
2. the delivery and dissemination of world-class research and policy analysis on selected cross-cutting aspects of growth;
3. the building of local research capacity in developing countries; and
4. the stimulation of the growth policy debate among a broad range of policy, donor community, private sector, civil society and media stakeholders to influence growth policy design, implementation and outcomes in developing countries.
The IGC model is based on sustained engagement with policy makers in-country, primarily through a network of staff in the countries where it has offices. It also occasionally engages with countries where it has no permanent presence, via staff based regionally and in its London hub. Through this close engagement, the IGC identifies key issues that affect growth and uses this to shape research that is produced by the IGC and its network of researchers. The outcome of research is fed back to policy makers through policy briefs, synthesis, and advice from experts.
The policy advice and research produced by the IGC aims to respond to the most important academic and policy questions on how to foster sustainable and inclusive growth in developing countries. The IGC is designed to adapt to FCDO Ministerial priorities. Over the past several years there has been an increase in the amount of IGC research outputs on the topics of climate change and green, sustainable growth. The launch of the initiatives has been one of the mechanisms IGC uses to implement the Responsive Policy Function, and strengthen thought leadership from the central team into the various regions and countries.
The programme is structured across three key areas: the country programme; the research programme; and four thematic “initiatives” (Tax for Growth, State Fragility, Firms, and Cities that Work), which undertake research in non-resident countries. The interconnectivity between the elements of the programme is key to the success of the operating model. For example, working papers that are published within the research function directly contribute to the policy discussions and processes in resident countries, non-resident countries, and, supported by IGC’s reputation and credibility, across a broad range of international fora including among multilateral development banks.
From specific policy priorities such as improving public transport (Ethiopia), to influencing entire country growth strategies and national prioritisation processes (Uganda), the programme’s activities are wide-ranging and vast in terms of geographical coverage, policy questions, and thematic focus. The programme’s convening power is impressive, including multi-stakeholder events with Ministers, Heads of State, multilateral development banks, municipal authorities and world-class universities.
Summary supporting narrative for the overall score in this review

We have awarded the IGC programme an A+ for the reporting year, as programme outputs moderately exceeded expectations.

In terms of influencing policy discussion in resident countries, non-resident countries and with regional and global stakeholders (Output 1), IGC met or exceeded all output indicators but one, receiving an A overall. This is an improvement compared to the B achieved in the previous reporting year. The programme’s influence on economic policy was high, and the programme team was impressed by the IGC country offices’ strong relationships with partner governments. For example, the team observed that in Ethiopia and Uganda, the IGC team had developed trusting relationships with government officials over a number of years and are able to directly inform policy decisions as a knowledge partner as a result of these relationships.

In the area of ‘pushing knowledge frontiers’, which sees the IGC delivering frontier research on inclusive growth with a view to affecting global academic debates (Output 2), the programme received an A+ for this reporting period. The programme exceeded each of its output indicators to such an extent that the programme team may wish to reconsider whether the targets are calibrated appropriately to reflect the capacity of the programme. IGC’s ability to identify promising research proposals and to generate high-quality publications is a key strength and was well demonstrated within the reporting year. IGC’s long-term aim is to build sustainable local ecosystems of researchers and policymakers to promote the use of evidence in decision-making and support the development of high-quality, policy-relevant research.

Furthermore, the programme has been successful in widely sharing its ideas and impact in an accessible way in support of its policy and academic outcomes, and to increase general global engagement with issues of inclusive growth in developing countries (Output 3). During this reporting period, the programme built on its impressive catalogue of events and campaigns and continued to deliver tailored communications, meeting or exceeding 9 out of 10 targets for this output and scoring an A+. For example, the programme launched its Tax for Growth Initiative, a new thematic initiative which supports tax administrators and policymakers to develop effective approaches to make taxation work for development, through research and data-driven solutions.

Finally, the programme also performed well in organisational learning (Output 4), again achieving an A+, though more work is needed to explore the relevance of the cited activities as best practice examples of organisational learning.

Major lessons and recommendations for the year ahead

Over the course of this reporting year the IGC undertook a large amount of activity across a broad range of thematic areas. The programme’s complexity — particularly the volume of research being undertaken and the number of separate initiatives underway — has given rise to overlap, complementarity, and synergies. There are also synergies with other FCDO-funded programmes such as the Tax and Public Finance Centre of Expertise, and the Green Cities, Infrastructure and Energy Centre of Expertise. Additional complexity arises from IGC’s need to respond to changing FCDO priorities, while at the same time meeting the needs of other donors (IGC has been majority funded by the FCDO since its founding, but has benefited from support from other donors, such as the Rockefeller Foundation, the Bezos Earth Fund, etc.).

In light of this, now is an appropriate time for IGC and FCDO to further strengthen aspects of communications and relationships at the country level. This presents an opportunity to refresh the governance of the programme and revisit its approach to questions of gender and partnerships with local researchers. This is to ensure that the results and expertise of IGC are properly understood across FCDO, and that IGC is best supported to deliver maximum policy impact over the remainder of the programme. The recommendations in this review are also intended to ensure coherence between UK interventions beyond IGC, with a view to delivering good value for money.

Please see below a summary of the recommendations from this Annual Review:

RECOMMENDATIONS
Output 1
1a	FCDO and LSE to review their shared approach to measuring impact of the Responsive Policy Function. Both to agree on a revised process to deliver on the new RPF pilot, following the governance structure set out in the contract ToRs, with Programme Board approval. IGC will also deliver statistics on projects that are tagged as responsive in the 2025-26 AR.
1b	Output Indicator 1.1 (contribution to policy discussions and processes in resident countries) covers a vast range of programme activity. Moving forward, a stronger emphasis on policy impacts should be prioritised, and FCDO should ensure that there is a strong requirement for these policies to be directly growth-inducing, or at least strongly contributing to growth. IGC to propose possible light-touch deliverables that could more effectively highlight our contributions to growth in the geographies where we operate.
2	IGC should build synergies with FCDO Centres of Expertise into the strategy documents it produces for each of the four initiatives. Green Cities, Infrastructure and Energy CoE has built some links with the Cities that Work Initiative, and the Public Finance and Tax CoE has built strong links with the Tax for Growth Initiative. A stronger and more explicit strategic approach to align to FCDO CoEs, not least the Green and Inclusive Growth CoE, will likely produce stronger results for all programmes. FCDO and IGC to work together to deliver progress on this before close of contract.
Output 2
3	IGC should continue to maximise linkages and synergies with other growth research programmes funded by FCDO, in particular with Private Enterprise Development in Low-Income Countries (PEDL), Structural Transformation and Economic Growth (STEG) and the Gender, Growth and Labour Markets in LICs (G2LM) programmes. This could include liaising with policymakers, collaborating on projects, disseminating evidence or producing synthesis pieces. The IGC team should ensure IGC country office staff are sighted on other FCDO programmes and aim to hold more workshops with these programmes, with FCDO playing a facilitating role and tracking change stories.
4	IGC should continue to look at ways to track academic impact beyond top 5 journal publications. For example, this could include trying to capture the number of researchers involved in publications who previously did not work with the IGC. IGC to update on developments in their approach in 2025, and to address this recommendation through an end-of-programme review, which will include detailed information on the new approach and how it responds to FCDO’s feedback.
Output 3
5	IGC should continue to improve communications on its achievements to increase visibility of the programme within FCDO and beyond. In particular, colleagues working on communications should aim to produce brief impact examples that can be more easily inputted into briefings, speeches, etc. Where IGC’s successful interventions are potentially scalable or replicable in other contexts, more communications outputs will be a powerful tool to increase the visibility of the IGC’s achievements among FCDO leadership and external stakeholders. IGC (with FCDO support) to continue to work on delivering an external campaign focused on its highest-impact achievements and explore publishing in platforms with strong FCDO readership. This could be complemented by regular communication between FCDO PRO for IGC and the IGC comms lead, to ensure products are well-tailored to FCDO and widely disseminated and understood.
6	IGC to incorporate plans for how the learnings of the programme could be preserved and taken forward as part of their end of programme exit plans. IGC to include a wrap-up document on the lessons learnt from implementing Phase 3, for delivery by Q2 of FY 2026-27.
7	The IGC has implemented a series of actions to increase engagement in their online platform – lessons of what has worked will be useful in planning IGC’s next phase and ensuring continued engagement with past outputs after the current phase ends. (Output 3.3, D). IGC to share an updated digital engagement strategy with FCDO by September 2025, and to report on engagement metrics in the next logframe submission. This reporting could include potential explanation of (and mitigation for) lower engagement with the IGC blog reported in this review period, and exploration of opportunities to use AI in communications.
Output 4
8	IGC will develop a wrap up report that distils key lessons from the implementation of Phase 3 to inform and support growth-promoting policies. The report will include insights into what worked and what didn’t, an analysis of drivers and pathways to impact based on available data, and reflections from local posts—particularly from a political economy perspective. The final outline of the report will be agreed between FCDO and IGC by October 2025.
Programme Management
9	FCDO should implement a quarterly ‘Programme Board’ at working-level below the Governance Board, to make programme-level, strategic decisions. This will also improve coordination between FCDO and IGC, as well as with other interventions, and will enable the prioritisation of IGC bids. FCDO to implement the Programme Board by August 2025. / .

10	Monthly statements have been updated to align expenditure categories with FCDO proforma categories, making it easier to track spend against budgets. As the end of the programme approaches, IGC and FCDO should implement and quality assure these new processes, with a view to improving visibility over internal financial systems, particularly the expenditure reporting, through improved quarterly reporting
Monitoring, Evidence and Learning
11	FCDO to facilitate closer working between IGC and other FCDO economic development programmes in-country. IGC to ensure country staff are meeting regularly with Posts in-country to maximise IGC’s profile and capitalise on synergies between FCDO-funded initiatives, while recognising the importance of IGC’s reputation as an independent learning partner.
12	I IGC to present their findings to FCDO more regularly, with the FCDO IGC programme team identifying opportunities and facilitating dialogue This would ensure transparency, accountability, and informed decision-making, while also fostering partnerships and synergies with other FCDO programmes. IGC to track and collate the number of presentations/findings shared with FCDO, both in London and by IGC representatives in-country, to share by May 2026.
Responsive Policy Function
13	FCDO and LSE to work together on a mechanism to respond to very short-term requests (six months or less) from partner governments, via FCDO posts, under the Responsive Policy Function (RPF) / The FCDO-organised Programme Board should look at all the activities in the RPF on a quarterly basis. FCDO and LSE will agree on a revised process to deliver on the RPF, following the governance structure set out in the ToRs.
Gender & Inclusion
14	As part of the wrap-up report delivered at the close of this phase of the programme IGC should produce a portfolio gender analysis. The approach to this analysis should be agreed by September 2025. IGC to foreground gender where possible for the remainder of the programme and report on progress in the Annual Report. It would be beneficial if IGC could include mention of race and ethnicity in the wrap-up report, to broaden the scope beyond gender – if there is a lack of data, IGC could provide an assessment of what data ought to be collected to facilitate such analysis. / FCDO to organise discussion with IGC with relevant policy team on women’s economic leadership and empowerment.
Localisation and Capacity Building
15	IGC and FCDO to review the suitability of how we measure academic impact to value the work done by local researchers, to give greater depth to this measurement beyond whether it appears in ‘top 5 journals’ (see recommendation 4 above about tracking academic impact). IGC to address this recommendation through updates on state-of play and inclusion in the end-of-programme review of detailed information on the new approach and how it responds to FCDO’s feedback.
16	By October 2025, IGC and FCDO to review the current payment policies to ensure that local researchers are not disincentivised from participating in commissioning processes.
Ongoing/partly implemented/yet to be implemented recommendations from 2022-23 Annual Review
ToC	A new transformational change approach was finalised by March 2024 and reported to FCDO. IGC to present approach to FCDO programme staff by October 2025.
Output 1	IGC retain and protect flexible policy function, particularly to be able to respond to short term requests for technical assistance where appetite for political reforms suddenly increases. / IGC and FCDO will take this work forward by committing to implement the RPF pilot by end 2025.
Output 1	Considering growing recognition and demand for IGC work among staff at post, IGC should continue to improve its relationships with the local FCDO offices in the countries where it operates. FCDO to continue to facilitate introductions and disseminate IGC outputs. IGC to track engagement with FCDO representatives across geographies (as captured in Recommendation 11, above)
Output 3	FCDO to work with IGC on a more comprehensive dissemination strategy to ensure that their research is understood within FCDO in 2024. Progress and next steps are captured in the recommendations above.
Output 3	FCDO to work with IGC on increasing visibility of IGC in FCDO, amongst diplomats, etc., as a key tool of global influencing. Progress and next steps are captured in the recommendations above.
Gender	IGC continues to produce high quality research on gender and climate nexus and raise profile of this work through dissemination. Following progress by IGC in commissioning work on gender and climate, IGC and FCDO will continue to disseminate this work.
Gender	Undertake data collection and disaggregation of gender and inclusion research products and report this to FCDO. / Progress and next steps: IGC has enhanced its tracking and monitoring systems in response to this recommendation, including by tagging all active projects for gender and climate-compatibility (specifically, whether they are ICF eligible). To further cement progress, IGC’s end-of-programme review to include detailed analysis of gender and climate tagging across the portfolio. IGC will ensure that the 2025–26 Annual Report includes tagging information for all project types, going beyond CB projects.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

As captured by the programme’s Theory of Change (ToC), the target impact of the IGC programme is improved policy environment for inclusive, sustainable growth in the countries and policy areas in which the IGC has been active.

This planned impact is measured through three indicators: real GDP growth rates, GDP per capita growth rates, and poverty headcount ratios.

IMPACT	Impact Indicator 1 (resident country growth rates)	Real GDP Growth Rate (%) in IGC Resident Countries
		2019	2020	2021	2022	2023
Improved policy environment for inclusive, sustainable growth in the countries and policy areas in which the IGC has been active.	Real GDP growth rates of IGC resident countries	5	-0.5	3.2	4.72	3.95
	Impact Indicator 2 (resident country per capita growth rates)	GDP per capita Growth Rate (%) in IGC Resident Countries
		2019	2020	2021	2022	2023
	GDP per capita growth rates of IGC resident countries	2.7	-1.2	3.2	2.6	1.9
	Impact Indicator 3 (resident country poverty headcount ratios)	Average poverty headcount ratio (% of population) in IGC Resident Countries
	Poverty headcount ratios at $1.90 a day (2011 PPP) (% of population) of IGC resident countries	32.1%

Contributing to this impact is the target outcome that IGC produces evidence-based pivotal contributions to a relevant shift in processes, structures or ideas that affect a large part of the population or a substantial part of the economy.

OUTCOMES	Outcome Indicator 1 (Transformational Change Cases)	Milestone(s) for this review	Progress
Evidence-based pivotal contributions to a relevant shift in processes, structures or ideas that affect a large part of the population or a substantial part of the economy.	Number of 'transformational' policy and academic changes resulting from IGC research and advice.	3 (4)* / *Figures in brackets () refer to cumulative targets.	3 (4)

There are also two intermediate outcomes:

INTERMEDIATE OUTCOMES	Intermediate Outcome Indicator 1 (policy changes)	Milestone(s) for this review	Progress
IGC research and engagement results in policy stakeholders changing policies and processes.	Number of policy decisions made as a result of IGC research and advice. Indicated by number of 'Level 4s'* assigned to IGC projects. / *The IGC’s methodology impact and definition of levels can be found at Annex 1.	13 (63) / Previously / 30 (80)	13 (77)
IGC research affects frontier academic debates on inclusive growth issues.	Intermediate Outcome Indicator 2 (academic influence - citations)
	Number of papers (including working papers) published by IGC-funded projects in Phase 3 with over 10 citations in academic journals.	2 (4)	5 (7)

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

In terms of programme impact, real GDP growth rates, GDP per capita growth rates and poverty headcount ratios in IGC resident countries (at the time of writing, Bangladesh, Ethiopia, Ghana, Jordan, Mozambique, Pakistan, Rwanda, Sierra Leone, Tanzania, Uganda, Yemen & Zambia) have all seen a dip from 2022 to 2023. This reflects global trends, influenced by spillover effects from Russia’s invasion of Ukraine, tight global financial conditions and macroeconomic challenges. It may also be a result of the impacts of climate change in some areas, for example in Zambia, where agriculture and energy sectors contracted in the reporting year. This makes it difficult to argue that inclusive, sustainable growth has taken place in the countries and policy areas in which the IGC has been active. We note that it is possible, given that IGC support incrementally builds resilience, that these impacts could have been worse if we consider the counterfactual of a situation in which IGC was not involved.

Nonetheless, the programme is on track in terms of delivering its outcomes and intermediate outcomes. For the number of 'transformational' policy and academic changes resulting from IGC research and advice, the cases selected for this reporting period were the Ugandan Economic Growth Forum, the Ghana Commodities Exchange project and the Conflict Resolution and Social Cohesion in Northern Mozambique project. Each example demonstrates the strength of the IGC operating model, the key to which is the long-term nature of changes, where key results are achieved through a combination of data gathering, research, relationship building, workshops and other events that together lead to major policy changes in a resident country. Summaries of the three cases can be found in Annex 2.

It is important to note that for Intermediate Outcome Indicator 1 – Policy Changes, both the annual and cumulative targets were reduced for the reporting period with agreement from the SRO, in order to reflect budget reductions over the lifecycle of the programme, as well as adjusting for the COVID-19 pandemic. This means that the programme is exceeding against both indicators.

Progress on previous recommendations
2023 Recommendation(s)	2024 Progress	Implemented?
IGC finalise their approach to transformational policy and academic changes by March 2024.	The new Transformational Change methodology was delivered in November 2023, and the first three cases were delivered in September 2024. The analysis of the second set of cases will begin in November, with the three cases expected to be concluded by June 2025.	Implemented

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The IGC programme represents a unique offer within FCDO’s research programme portfolio since it bridges the gap between academic research and policymakers in-country. It continues to perform well. However, as the end of the programme’s lifecycle approaches, this is an appropriate time for IGC and FCDO to refresh the thematic focus and priorities of IGC and develop a sustainable transition strategy.

## C. DETAILED OUTPUT SCORING

OUTPUT 1: Policy Influencing

Output Title	IGC influences policy discussion in resident countries, non-resident countries and with regional and global stakeholders.
Output number:		1	Output Score:	A
Impact weighting (%):		45	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 - National policy influencing (resident) / A) Number of instances of IGC projects contributing to national or sub-national policy discussions and/or processes in resident countries. Indicated by: A) combined number of 'Level 3s' and 'Level 4s' in resident countries; and B) Annual proportion of 'Level 3s' ranked as 'High' or 'Medium'.	A) 70 (231)* / B) 85% / *All figures in brackets () refer to cumulative targets.	A) 74 (295) / = EXCEEDED B) 84% / = MARGINALLY NOT MET
1.2 - Production of new final outputs / Resident country programmes with a minimum number of projects producing new final outputs, responding to country strategy, dependent on their budget size.	All country programmes produce a minimum number of outputs based on country programme size	Verified 10 of 10 countries achieved / = MET
1.3 - Country-specific strategies / Resident country programmes achieving at least 2 of their annual strategic objectives, as agreed prior with the IGC Hub and shared with FCDO.	All countries achieve at least two targets	Verified 9 of 9 countries achieved / = MET
1.4 - National policy influencing (non-resident) / Number of instances of IGC projects contributing to national or sub-national policy discussions in non-resident countries. Indicated by combined number of Level 3s and Level 4s in non-resident countries.	9 (40)	9 (47) / = MET
1.5 – Responsive Policy Function strategies / RPF teams that achieve at least 2 of their annual strategic objectives, as agreed prior across the IGC Hub and shared with FCDO.	Each team achieves at least two targets	Verified 4 of 4 teams achieved this target / = MET
1.6 - Regional and global policy influencing / Number of instances of the IGC directly affecting policy discussions and/or processes on a regional and global scale. Indicated by combined number of Level 3s and Level 4s with regional and global stakeholders.	2 (6)	10 (28) / = EXCEEDED
1.7 - Regional and global policy engagement / Number of engagements by IGC staff and IGC affiliates talking on behalf of the IGC at regional and global policy forums with significant audience feedback.	4 (21)	7 (28) / = EXCEEDED

Briefly describe the output’s activities and provide supporting narrative for the score.
We have awarded this output with an A. Two output indicators have been exceeded, four met and one partly exceeded and partly not met
Output 1 captures the IGC’s policy influencing work across all its functions: the resident country programme; the responsive policy function in non-resident countries; and thematic work aimed at a regional and global audience, including via policy initiatives. IGC undoubtably has strong and influential relationships with partner Governments and international institutions across a wide range of growth-related issues and is effective at using these to influence policy. There could be a product that documents policy-influencing work, similar to the IGC Teams dashboard, which outlines ongoing research and small fund facility projects.
While several of the FCDO Missions are well-sighted on and engaged with their counterpart IGC country office and therefore have confidence and visibility over IGC’s value and impact, others have much less insight. This is sub-optimal, since there are significant benefits to all FCDO posts where IGC has a country office having a clear view and a strong relationship with FCDO’s flagship programme. Without this in place, significant potential value and impact from the programme is lost. Some FCDO Posts are not clear on the rationale for priority workstreams chosen by IGC and we recommend that the current good practice the reviewers have seen in some IGC resident countries, where FCDO posts are routinely kept abreast of IGC priorities and workstreams be extended across the geographical footprint of the programme, particularly on initiatives, thematic priorities and evidence funds.
The current operating model of the programme is such that FCDO Posts intentionally do not drive the activities of the IGC country offices. Instead, the central IGC hub works with the IGC country teams to produce strategies from year to year. This enables the programme to retain independence, which is valuable in maintaining its credibility as a trusted partner to host governments. FCDO Heads of Mission have expressed strong views that this independence and impartiality is valuable and important to retain and protect. Several FCDO missions noted examples of where the IGC has been a highly valued partner. However, in some countries this arms-length relationship with Post risks opportunities, particularly short-term opportunities, being lost. FCDO teams at Posts could potentially benefit more from IGC’s expertise, and conversely FCDO officials may be able to alert IGC to potential priority areas for advice or research.
In Zambia, the President and Office of the President hold IGC in high regard, and have communicated this to FCDO Ministers, with particular reference to the IGC’s work on decentralisation.
In Pakistan, the British High Commission has a close and effective working relationship and highly values the IGC’s role in helping to build national capacity for policy-relevant research and to stimulate and help grow the public discourse on inclusive growth. IGC looks not only at prospects for reform through Government, but also at approaches that do not require government, such as private sector, civil society and Section 42 companies[1]. The High Commission also values the excellent relationships IGC has with government, universities and business. Climate change is a central theme of IGC Pakistan’s policy work, providing evidence on how the rural poor cope with devastating floods, as well as highlighting the barriers to access to climate finance for Pakistan. IGC’s work with the World Bank on maternal and child health, to collect data in order to measure the impact of flood disaster is also highly regarded by the government and the FCDO mission.
[1] Section 42 Companies under Pakistan law are associations with not-for-profit or charitable objectives and can be registered as companies without ’limited’ status.
In Rwanda, IGC’s work on export growth has been recognised by the Mission as a highly effective long-term effort, leading to actionable policy recommendations that are making a difference to the Government of Rwanda’s work on trade strategy and policy.
Outputs 1.1 and 1.4 are the two outputs relating to policy influencing at national or sub-national level. These are separated into those for IGC resident countries (output 1.1) and non-resident countries (output 1.4). 31% of the budget is allocated to country programmes. As would be expected, a high proportion of policy influencing examples arise from the IGC resident countries.
Over the reporting period, IGC reported 74 cases of projects contributing to the national or sub-national level discussions in accordance with the IGC’s policy impact methodology. The cases are spread across the 9 countries in the country programme as follows; 13 are in Ethiopia, 7 in Ghana, 12 in Mozambique, 10 in Pakistan, 8 in Rwanda, 5 in Sierra Leone, 7 in Uganda, 8 in Zambia, 2 in Sierra Leone, and 9 in Bangladesh. This spread meets the threshold of minimum new outputs per country office according to its size (captured by output 1.2: “10 out of 10 country offices produced their minimum new outputs”). The five largest country programmes are Ethiopia, Pakistan, Rwanda, Zambia and Uganda. The new outputs produced comprise a mix of largely blog posts, policy briefs and working papers.
These 74 project cases have successfully influenced policy discussions and processes across a remarkably broad range of policy areas, including: migration, climate and weather services that enhance farmer productivity, inflation, gender gaps in job markets, electricity tariff structures, digitalisation and job matching, improving the experience of civil service recruits and improving people management, risk mitigation in urban flooding, integrating rural migrants in cities, predicting the effects of climate change on vulnerability to food insecurity, advancing health-care access, identifying and solving constraints in the agriculture supply chain, value addition exports and export growth, The full list of these policy impact cases under output 1.1 are included as an Annex to this review. It is notable that the range of activities across these 74 impact cases is very broad. It is worth FCDO considering whether it is preferable to refocus the workstreams towards a narrower range of activities. This could be an effective way to strengthen the focus on growth inducing activity, and create more ambitious levels of policy change moving forward.
Output 1.5 measures how many of the four initiatives, set up during this contract—Cities that Work, State Fragility, Tax for Growth, and Firms—have achieved two of their strategic objectives. The Firms initiative is divided into two evidence funds: Small and Growing Businesses, and the Agri-SME fund. Each of these initiatives are staffed by a small, dedicated team, and sets a total of 4 or 5 strategic objectives annually. These objectives include producing synthesis papers, sharing knowledge products with country offices, fundraising for the evidence funds, strengthening cross-country collaboration, and creating policy and research assets. In non-resident countries there are 9 cases of levels 3 and 4 policy impact, all of which were carried out under three of the four initiatives; Cities that Work, Tax for Growth, and State Fragility.
IGC’s achievements in successfully influencing policy discussions on a regional and global scale are captured in output 1.6, with 10 cases achieving levels 3 and 4 in IGC’s impact methodology. 8 of these cases arise from work done within the IGC’s policy ‘initiatives’, while one is country specific (Rwanda). Of these 10 cases, most notable is the Development Finance Institutions Forum, which has been held annually since 2019 at the Blavatnik School of Government. The event is co-organized by IGC, British Investment International, African Development Bank and the International Finance Corporation. The forum brought together 26 Development Finance Institutions, including the Inter-American Development Bank and the Association of European Development Finance Institutions. IGC presented work on ‘local currency finance solutions’, incorporating analysis of and solutions to the problem of delivering development finance in local currency for conflict affected states. IGC’s expertise directly influenced the Dutch Development Bank’s own financial fragility strategy. FCDO notes this example of IGC’s ability to credibly influence policy across the multilateral architecture and its success in accelerating this work on international agendas over the longer term.
Output indicators 1.1, 1.4 and 1.6 and 2.1 are based on the IGC’s impact methodology, which measures the degree to which projects have successfully influenced policy discussions or processes. IGC’s policy impact methodology is explained in Annex 1.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Some annual milestones for Output Indicator 1.1 were changed, so that impact was more evenly distributed among reporting years. The overall programme period target was not changed.
	Milestone 5 (23/24)	Milestone 6 (24/25)	Milestone 7 (25/26)	Milestone 8 (26/27)	Target (full programme period)
Planned	A) 81 (242)	A) 61 (303)	A) 41 (344)	A) 40 (384)	384
Changes as of May 2024	70 (231) Annual target Reduced	68 (299) Annual target increased	65 (364) Annual target increased	20 (384) Annual target Reduced	384 No change

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on previous recommendations
2023 Recommendations	2024 Response from Supplier	Implemented?
FCDO & IGC to review the suitability of the milestones for output indicators 1.2 and 1.3 and their measurement, to ensure that they are not unrealistically stretching at the next programme board.	As above, SRO agreed milestone changes for these outputs in early summer 2023.	Yes
IGC retain and protect flexible policy function, particularly to be able to respond to short term requests for technical assistance where appetite for political reforms suddenly increases.	The way that the ‘flexible policy function’ has been implemented contrasts with its intention as set out within the Phase 3 business case. The programme’s country economists perform ad hoc responsive policy requests as part of their ongoing relationships with Ministries. Country Teams use a variety of mechanisms to respond to policy demands in their respective countries, including in-house projects, the Small Project Facility, off-cycle projects, and Commissioning Board projects. In IGC’s resident countries, responses to short-term requests are most impactful, as they build on established relationships and the existing research portfolio. However, FCDO is keen to see this facility implemented via a responsive policy function with engagement from the FCDO country post as initially intended in the Phase 3 BC.	Partly / NB the original intention of the RPF was for IGC to begin short-term work in response to changes in partner-government priorities. In implementation the Governance Board did not review the request and approve them to proceed, nor did it act as a gateway for the short-term work to proceed to longer term work. The work described in LSE’s response is not explicitly captured in the logframe. We will adjust the logframe in order to ensure that all work is captured effectively and that the Governance Board approves the short-term work.
FCDO & IGC to review the logframe indicators to ensure that the milestones remain suitable for the current climate, by the next Governance Board.	Review expected to be finalised in FY 2025-26.	In train
Considering growing recognition and demand for IGC work among staff at post, IGC should continue to improve its relationships with the local FCDO offices in the countries where it operates. FCDO will agree with IGC an appropriate level of frequency for their contact with FCDO posts, both in countries where IGC has a country office and in countries where work is being undertaken, but IGC do not have a permanent presence.	There has been no material change to the IGC’s relationship with FCDO posts since this recommendation. However, this relationship can be difficult to measure and depends on the individuals both at post and in the IGC Country Office. During the research for this Annual Review, one IGC Country Director noted that though the IGC office’s relationship with FCDO post is good, it would benefit from both more informal and formal exchange. On the other hand, a Country Economist in Uganda shared that though FCDO and IGC tend to work independently, IGC recently went to a meeting with the FCDO staff about how to create synergies and avoid duplication. Overall, it seems more work could be done in this area.	Not yet implemented

As above, the IGC have made mixed progress in addressing the Output 1 recommendations from the previous reporting year and should continue to pursue them. Additional recommendations for the year 24/25 are:

Recommendation 1a: FCDO and LSE to review their shared approach to measuring impact of the Responsive Policy Function. Both to agree on a revised process to deliver on the RPF, following the governance structure set out in the ToRs. IGC will also deliver statistics on projects that are tagged as responsive in the 2025-26 AR.
Recommendation 1b: Output Indicator 1.1 (contribution to policy discussions and processes in resident countries) covers a vast range of programme activity. Moving forward, a stronger emphasis on policy impacts should be prioritised, and FCDO should ensure that there is a strong requirement for these policies to be directly growth-inducing, or at least strongly contributing to growth. IGC to propose possible light-touch deliverables that could more effectively highlight our contributions to growth in the geographies where we operate.

Recommendation 2: IGC should build synergies with FCDO Centres of Expertise into the strategy documents it produces for each of the four initiatives. Green Cities, Infrastructure and Energy CoE has built some links with the Cities that Work Initiative, and the Public Finance and Tax CoE has built strong links with the Tax for Growth Initiative. A stronger and more explicit strategic approach to align to FCDO CoEs, not least the Green and Inclusive Growth CoE, will likely produce stronger results for all programmes. FCDO and IGC to work together to deliver progress on this before close of contract.

OUTPUT 2: Pushing Knowledge Frontiers

Output Title	IGC delivers frontier research on inclusive growth that affects global academic debates.
Output number:		2	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 - Working papers / Number of academic working papers produced by IGC-funded research.	40 (97)	53 (117) / = EXCEEDED
2.2 - Academic conferences and seminars / Number of presentations of IGC-funded projects at high-quality economics research conferences.	4 (27)	10 (66) / = EXCEEDED
2.3 - Academic publications / Number of papers produced by IGC Phase 3-funded research accepted for publication (including revise and resubmit) in an academic journal.	8 (12)	12 (22) / = EXCEEDED
2.4 - High-quality peer-reviewed publications in economics and closely related disciplines / A) Proportion of papers produced by IGC Phase 3-funded research accepted for publication (including revise and resubmit) in a high-quality peer-reviewed economics journal, or a high-quality peer-reviewed journal in a discipline closely related to economics (e.g. political science). B) Proportion of papers produced by IGC Phase 3-funded research accepted for publication (including revise and resubmit) in a 'top-5' economics peer-reviewed journal.	A) 40% / B) 10%	A) 83% / = EXCEEDED / B) 17% / = EXCEEDED

Briefly describe the output’s activities and provide supporting narrative for the score.

Overall, the IGC exceeded all 5 targets in indicators 2.1 to 2.4- thus, this output score is graded A+/A++. IGC’s ability to identify promising research proposals and to generate high quality publications is a key strength of the programme.
Output 2.1. Working papers – during the reporting period, 53 academic working papers were produced, exceeding the target of 40, and bringing the cumulative total of working papers produced in Phase 3 to 117. Project countries ranged from South Asia (Bangladesh, India, Pakistan), Sub-Saharan Africa (Ethiopia, Sierra Leone, South Africa, Zambia, Kenya, Mozambique, Ghana), South-East Asia (Myanmar, Thailand) and the Middle East (Jordan). The IGC’s working papers focus on understanding determinants of sustainable and inclusive economic development, with this year’s papers including:
- Labour markets, jobs and firms: e.g. Gender gaps and job advertisements in urban labour markets in Ethiopia, Digital Skills for Women Entrepreneurship in Pakistan, The Origins of Distorted Beliefs: Implications for Unemployment and Labor Market Interventions in Ghana.
- Firms and Structural Transformation including Managers, Motivation, and Worker Productivity: Evidence from Survey Enumerators in Uganda, Vulnerabilities and solutions for Mozambican enterprises in the face of the COVID-19 crisis, Training with Technology- Lessons from a field experiment with Kenyan MSMEs.
- Domestic revenue mobilisation: Zambia Fiscal Decentralisation, Public Reporting and Property Tax Compliance: A Field Experiment in Kampala Uganda, Tax compliance and local government autonomy: experimental evidence from Mozambique.
- Climate, Energy, and Environment: Engineering Energy-Efficient Behaviours and Conservation in Household Electricity Market in Urban Dhaka, Environmental and Economic Impacts of Agrivoltaics in Bangladesh, Impact of Vehicle Taxation on Transport Sector Emissions: Evidence from Ghana, The Economic Impact of Sustainability Standards on Smallholder Coffee Producers: Evidence from Sidama Region, Ethiopia
- Cities: Neighbourhoods of opportunity? Moving to public housing in Addis Ababa, Land Governance and Urban Development in India, Public vs Private Provision of Transportation Services and its Implications for Women Employment in Lahore Pakistan, New City Building: White Elephants or Effective Development Strategy? (Evidence from Zambia)
Output 2.2. Academic conferences & seminars – the target was exceeded with 10 instead of 4 IGC-funded projects being presented at high-quality economics research conferences.
Output 2.3. Academic publications – This year, 12 papers from Phase 3 were accepted for publication in academic journals (including revise and resubmit), exceeding the target of 8. Notably, two papers (on ‘Optimal Public Transportation Networks: Evidence from the World’s Largest Bus Rapid Transit System in Jakarta’ and ‘Union Leaders: Experimental Evidence from Myanmar’) were provided a ‘revise and resubmit’ to the prestigious American Economic Review, a top 5 economics journal.
Output 2.4. High-quality peer-reviewed publications in economics and closely related disciplines- this year, 83% of the papers which were accepted for publication were accepted in a high-quality peer-reviewed economics journal or in a journal of a closely related discipline (e.g. political science), exceeding the target of 40%. Notably, the proportion of accepted (including revised and resubmitted) papers produced by IGC Phase 3-funded research accepted for publication in a ‘top-5’ economics peer-reviewed journal was 17%, exceeding the target of 10%.
Examples of IGC pushing knowledge frontiers	Output Indicator
“Gendered Differences in Mobility and the Demand for Transport: Evidence from a Field Experiment in Urban Ethiopia”, working paper produced by IGC-funded research exploring gender disparities in mobility in Ethiopia. The paper finds that introducing improved transport for women meets latent demand, enhances access, and underscores the need for gender-sensitive transport policies in planning and implementation.	2.1
“Environmental and economic impacts of agrivoltaics in Bangladesh”, policy brief produced by IGC-funded research exploring how agrivoltaics are a more sustainable and land-efficient energy source than fossil fuels.	2.1
“Overcoming the exclusion of Karachi’s migrant communities”, a policy brief produced by IGC-funded research exploring the political behaviour and policy concerns of Karachi’s largest internal migrant community, the Pashtuns.	2.1
“Fiscal Exchange and Tax Compliance: Strengthening the Social Contract Under Low State Capacity”, a presentation of an IGC-funded project at the University of Oxford Centre for the Study of African Economies (CSAE).	2.2
“Integration of African countries in regional and global value chains: Static and dynamic patterns”, IGC-funded research paper accepted for publication in the World Economy Journal.	2.3
“To what extent do we learn from past epidemics: a mobile phone survey of selected villages in Liberia”, IGC-funded research paper accepted for publication in the Journal of Global Health Reports.	2.3

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The target for output indicator 2.1. on working papers was initially set at 33. As IGC met this target in the previous reporting year, the 2024 target was increased to 40. This was exceeded this year. Output indicator 2.3, academic publications, was also increased from four to eight, reflecting five publications in 2022/3.

The way that the IGC’s Research Commissioning Board (CB) is delivered has been evolving over this phase, the results of which were demonstrated in the reporting year. By continuing to promote the importance of stakeholder engagement early in the research process, for CB9, 58% of the proposals had an established relationship with a stakeholder or a counterpart and 22% of the proposals were developed in close collaboration with the stakeholders. Adopting a ‘co-creation’ approach to research generation enhances policy impact and demonstrates the relevance of IGC research.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations in 2022-23.

IGC has continued to demonstrate its ability to fund high quality publications and to present these at high-quality academic conferences. Recommendations for the year ahead include:
Recommendation 3: IGC should continue to maximise linkages and synergies with other growth research programmes funded by FCDO, in particular with Private Enterprise Development in Low-Income Countries (PEDL), Structural Transformation and Economic Growth (STEG) and the Gender, Growth and Labour Markets in LICs (G2LM) programmes. This could include liaising with policymakers, collaborating on projects, disseminating evidence or producing synthesis pieces. The IGC team should ensure IGC country office staff are sighted on other FCDO programmes and aim to hold more workshops with these programmes, with FCDO playing a facilitating role and tracking change stories
Recommendation 4: IGC should continue to look at ways to track academic impact beyond top 5 journal publications. For example, this could include trying to capture the number of researchers involved in publications who previously didn’t work with the IGC. IGC to update on developments in their approach in 2025, and to address this recommendation through an end-of-programme review, which will include detailed information on the new approach and how it responds to FCDO’s feedback.

OUTPUT 3: Global Profile and Influencing

Output Title	IGC widely shares its ideas and impact in an accessible way in order to support the achievement of its policy and academic outcomes, and to increase general global engagement with issues of inclusive growth in developing countries.
Output number:		3	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 - Content campaigns / Number of successful content campaigns undertaken by the IGC Communications Team.	4 (18)	10 (29) / = EXCEEDED
3.2 - Synthesis pieces / Number of synthesis products produced by the IGC.	8 (36)	9 (56) / = EXCEEDED
3.3 - Blogs / A) Number of blogs published on the IGC website. / B) Of which there is a minimum proportion of blogs on national or global debates (non-project) / C) Number of blogs published on the I4I platform / D) % yearly increase in engagement	A) 50 (290) / B) 20% / C) 140 (420) / D) 20% increase each year in engagement	A) 66 (388) / = EXCEEDED / B) 57% / = EXCEEDED / C) 175 (624) / = EXCEEDED / D) -40.86% / = NOT MET
3.4 - Media mentions / A) Number of mentions in formal media outlets of IGC or IGC activities. Including, but not limited to: IGC projects, content, events, analysis, and opinions of associated personnel (e.g. affiliated researchers) talking on behalf of the IGC. / B) Number of distinct topics where IGC or IGC activities have been mentioned in formal media outlets.	A) 140 (910) / B) 10	A) 438 (1635) / = EXCEEDED / B) 15 + / = EXCEEDED
3.5 - Engagement with IGC and IGC-affiliated platforms / A) % increase in number of users visiting the IGC website / B) % increase in followers on Twitter / C) % increase in number of users visiting the VoxDev website	A) 10% / B) 15% / C) 15%	A) 23.5% / = EXCEEDED / B) 17.7% / = EXCEEDED / C) 33.6% / = EXCEEDED

Briefly describe the output’s activities and provide supporting narrative for the score.
This output monitors the IGC’s communication and engagement activities as a way of capturing its international reputation and influence. This is a key part of the theory of change that warrants measurement. The impact on policy uptake is captured elsewhere (output 1).
In 2023/24 IGC built on its impressive catalogue of events and campaigns and continued to deliver tailored communications, meeting or exceeding 9 out of 10 targets of this output.
Over the review period, IGC delivered 10 content campaigns, exceeding its target of 4 (indicator 3.1). This period marked the launch of the Tax for Growth Initiative, a new thematic initiative that supports tax administrators and policymakers to develop effective approaches to make taxation work for development, through research and data-driven solutions. The related campaign included a half-day event featuring a keynote from the FCDO Chief Economist; high-level panel discussions; and presentation of four papers, all supported by event webpages on the IGC website, audio/visual content on YouTube and Soundcloud on ‘Why do tax research and evidence matter for economic growth’, plus related explainer videos, a blog series, synthesis papers, and social media campaigns on Facebook and LinkedIn. This series introduced the initiative to the development community with wide outreach including academia, policymakers, donors (FCDO), NGOs, and policy influencers including 275 attendees at the main event.
Other major campaigns included those in support of the ‘Resilient and Resurgent Bangladesh: Sustaining economic growth in a changing climate’, comprising a two-day hybrid conference and related social media campaign, synthesis paper, event webpage and audio/visual content aiming to disseminate TEPP-funded projects and to showcase ongoing work as well as promoting the IGC’s image in country, the LSE Environment Week 2023, a one-week event focused on environmental economics at LSE with associated social media and digital content, a campaign in support of the IGC-EGC Conference on Firms, Trade and Development, a two-day conference about “Firms, Trade, and Development” co-organised between the IGC and the Yale Economic Growth Centre, and campaigns supporting the 8th Urbanisation and Poverty Reduction Conference, and Zambia Economic Growth Forum 2024.
The number of synthesis pieces, blogs published by IGC, and IGC media mentions (indicators 3.2, 3.3. and 3.4.) exceeded their targets. The IGC’s work received 438 mentions in formal media outlets including the Financial Times, SAPO (Portugal), The Business Standard (Bangladesh), the Economic Times (India), Ghana Web, Dawn (Pakistan), Sohu News (China). The number of distinct topics where IGC or IGC activities have been mentioned in formal media outlets exceeded its target of 10 (sub-indicator 3.4B), with 15+ topics covered including work on State Capabilities, State Fragility, Markets, Public Sector Organisation, Infrastructure and public services, Access to Energy, Tax and State Revenue, Social Protection and inclusive labour markets. Output 3.5 exceeded its target, with a higher percentage increase (23.5%) of users visiting the IGC website, a higher percentage increase in followers on Twitter, and a higher percentage increase in number of users visiting the IGC-supported VoxDev website versus targets.
The only sub-indicator not met is 3.3D. The percentage yearly increase in engagement on the IGC blog. Instead of a target 20% increase in annual engagement, this indicator saw a 40.86% decrease in engagement across both IGC and I4I blog. This is partially explained by changes to tracking methodologies in Google Analytics and an erratic social media landscape. The I4I website experienced a major hack in late 2022, and the IGC team has been working on a variety of approaches to fix security issues on the site which also affected data received from Google Analytics.
An overall output score of A+ was given to this output as all indicators were met or exceeded, except for sub-indicator 3.3D due to the reasons outlined above.

Examples of IGC global profile and influencing	Output Indicator
Launch of the Tax for Growth Initiative, a new thematic initiative which supports tax administrators and policymakers to develop effective approaches to make taxation work for development, through research and data-driven solutions.	3.1
“Why do SMEs matter?”, a synthesis brief covering the impact of small and medium-sized enterprises (SMEs) in developing countries and implications for development finance institutions (DFIs) and impact investors.	3.2
“Market-based solutions for sustainable development: Lessons from the Delta Blue Carbon project in Pakistan”, a blog published on the IGC website.	3.3

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following the previous Annual Review the following changes were made:

1. The target for output indicator 3.4 on media mentions was initially set at 170 mentions with 12 distinct topics. Although IGC met this target in the previous reporting year, the 2024 target was revised down to 140 with 10 distinct topics. This was exceeded this year.
2. Output indicator 3.5B, engagement with IGC and IGC-affiliated platforms (as measured by % increase in followers on Twitter/X) was also revised down from 15% to 10% given changes to the social media landscape - this was also exceeded this year.

Progress on previous recommendations
2023 Recommendations	2024 Progress	Implemented?
FCDO to work with IGC on a more comprehensive dissemination strategy to ensure that their research is understood within FCDO in 2024.	Whilst some progress has been made, such as the three impact cases that have been written up and shared with FCDO, we have yet to agree a comprehensive dissemination strategy. IGC organised a research-to-policy seminar in 2023, showcasing impact cases with the participation of Country Economists from Sierra Leone, Ghana, Ethiopia, and a Policy Economist from our State Fragility Initiative to highlight our work in Yemen.	Partly
FCDO to work with IGC on increasing visibility of IGC in FCDO, amongst diplomats, etc., as a key tool of global influencing.	IGC has also invited FCDO colleagues to participate in IGC-organised events. Highlights include the participation of the Research Directorate in the EGF (Economic Growth Forum) Uganda held in 2024, as well as the participation of FCDO representatives in the SGB conference in early 2024. IGC Executive Director, Jonathan Leape, also participated in the FCDO Economics Conference 2024. The IGC State Fragility Initiative organised a two-day workshop on 'Strengthening Institutions in Conflict-Affected and Post-Conflict States' in September 2024. The keynote address was delivered by the FCDO Chief Economist, A presentation on IGC’s commissioning board to FCDO’s Growth Research Team is scheduled in late October/early November 2024. However, this will continue to be a recommendation for the coming reporting year.	Yes / ongoing

Recommendations for the year ahead:
Recommendation 5: IGC should continue to improve communications on its achievements in order to increase visibility of the programme within FCDO and beyond. In particular, colleagues working on communications should aim to produce impact examples which are brief, so that they can be more easily input into briefings, speeches, etc. Where IGC’s successful interventions are potentially scalable or replicable in other contexts, more communications outputs will be a powerful tool to increase the visibility of the IGC’s achievements among FCDO leadership and external stakeholders. As a next step, IGC (with FCDO support) to continue to work on delivering an external campaign focused on its highest-impact achievements and explore publishing in platforms with strong FCDO readership. This could be complemented by regular communication between FCDO PRO for IGC and the IGC comms lead, to ensure products are well-tailored to FCDO and widely disseminated and understood.

Recommendation 6: IGC to incorporate plans for how the learnings of the programme could be preserved and taken forward as part of their end of programme exit plans. IGC to include a wrap-up document on the lessons learnt from implementing Phase 3, for delivery by Q2 of FY 2026-27.

 Recommendation 7: The IGC has implemented a series of actions to increase engagement in their online platform – lessons of what has worked will be useful in planning IGC’s next phase and ensuring continued engagement with past outputs after the current phase ends. (Output 3.3, D). IGC to share an updated digital engagement strategy with FCDO by September 2025, and to report on engagement metrics in the next logframe submission. This reporting could include potential explanation of (and mitigation for) lower engagement with the IGC blog reported in this review period, and exploration of opportunities to use AI in communications.

OUTPUT 4: Organisational Learning

Output Title	IGC actively reflects on its own practice and performance and implements key learnings from these insights to improve its delivery of outcomes.
Output number:		4	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 - Learning framework / Progress made against the IGC Learning Framework	75%	97% / = EXCEEDED
4.2 - Improving commissioning processes and outcomes / % of targets or recommendations agreed in previous year's Commissioning Report achieved by the IGC.	75%	100% / = EXCEEDED
4.3 - Improving communications and events / % of targets or recommendations agreed in the previous year's Global Events and Communications report achieved by the IGC.	75%	100% / = EXCEEDED
4.4 - Better understanding policy impact / Number of complete internal reviews which consider the IGC's contribution to significant policy impact.	2 (6)	5 (10) / = EXCEEDED

Briefly describe the output’s activities and provide supporting narrative for the score.

This output was designed to capture the IGC’s capacity as an adaptive, learning organisation. Overall, this output was awarded an A+, recognising the continued progress IGC have made in improving its organisational learning.

IGC has made strong progress on this output during this year. All indicators exceed the target. Beyond the numbers, efforts on monitoring & improving performance have been qualitatively strong this year.

Examples of IGC organisational learning:	Output Indicator
Local Researcher Engagement / Objective: / Maintain and improve our local researcher outreach and engagement through capacity building, providing proposal feedback and Bureau for Research and Economic Analysis of Development (BREAD) lecture series. / Evidence of delivery: / 43% of approved projects include at least one local researcher, defined as a researcher of local origin. / 18% of the local research proposals were of high quality in CB9 as compared to 15% in CB8. / 2023 BREAD lecture series on Energy and Environment was very successful in attracting local researchers. The series had a total of 1,854 unique registrants, 77.1% of attendees from developing countries, and an average attendance of 497 participants per session across 10 lectures. After CB9, RP also shared detailed feedback with 44 local researcher teams with proposals just below the bar. / Research Programme team is conducting a detailed analysis on local researcher engagement and project generation by holding sessions with country teams. The final analysis will be shared as part of the CB9 report.	4.2
Transformational Change Methodology / Objective: / Identify the conditions under which Transformational Change can happen and draw actionable conclusions on the factors that enable change, with the aim of informing IGC's strategy and Theory of Change going forward, focusing resources where they can generate the greatest impact, and improve our communication strategies. / Evidence of delivery: / This review has now been completed. The review (1) provides a framework which conceptualises four dimensions that underlay Transformational Change: innovative contribution, institutionalisation, scalability, and impact, and (2) proposes a methodology based on exploratory case studies to systematically study these cases.	4.4

Describe any changes to this output during the past year, and any planned changes as a result of this review.
N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year
N/A

Recommendations for the year ahead

Recommendation 8: IGC will develop a wrap up report that distils key lessons from the implementation of Phase 3 to inform and support growth-promoting policies. The report will include insights into what worked and what didn’t, an analysis of drivers and pathways to impact based on available data, and reflections from local posts—particularly from a political economy perspective. The final outline of the report will be agreed between FCDO and IGC by October 2025.
## D: VALUE FOR MONEY

Key cost drivers and performance
VFM: Economy and Efficiency
VfM performance compared to the original VfM proposition in the business case

IGC remains an efficient and effective programme, achieving high value for money.

Economy: the main cost drivers are fee rates of downstream partners/suppliers, travel costs, and expenses. The staff costs are fixed within the contract. The IGC keeps a VfM register which records where savings have been made in areas, including overall fees, projects, and office/space services. These demonstrate an overall saving of £4,111,281.73, highlighting where the IGC has achieved economy. Of note, is that the expertise IGC is able to convene as an integral part of its operation represents a significant reduction in the typical costs normally charged by these individuals as consultants. For example, some of the expert technical academics advising on climate change and foreign exchange policy are made available to IGC at as low as 20% of their market rate. Staff costs account for a large proportion of the overall cost and are fixed within the contract terms and conditions.

The IGC has played an active role in LSE’s tendering process for a new travel supplier. The IGC has taken great care to ensure this supplier could provide more competitive flight and hotel rates. The new supplier contract went live in October 2023, and the IGC has seen a 33.6% decrease in average flight cost in comparison to LSE’s previous provider.

Whilst the internal IGC programme management systems are strong and sophisticated, more could be done to improve the visibility that FCDO has over those systems. FCDO is working with IGC to improve the FCDO’s visibility over the internal financial systems, particularly the expenditure reporting, through improved quarterly reporting.

Efficiency: The IGC has achieved efficiency via a variety of means. Automated output reminders have enhanced efficiency by maximising delivery of crucial outputs, minimising missed deadlines and therefore project delivery and impact delays. A mid-year financial review was carried out to identify areas of underspend and reallocate activity across financial programmes. This ensured that each pound of the budget was used in a way that added value to the programme and prevented inefficiencies. Quarterly output management has helped to foster accountability and transparency across the network of IGC’s downstream suppliers to ensure timely delivery of research services and academic outputs. Cost-benefit automation via SPEAR, an internal project and financial management system, has also resulted in a more efficient and streamlined process. In this process, the reviewers were able to view the full budget and the comments made by other reviewers, which improved efficiency. An internal audit conducted in June 2023 resulted in a £12,000 credit to FCDO, and the IGC intends to resume periodic internal audits across country programmes in the coming year.

Effectiveness: The IGC conducted a VfM action plan to understand how best to balance economy, efficiency, and effectiveness needs across the organisation. All internal staff members were invited to participate in a survey, resulting in an action plan being created in October 2023 – future reports should include the progress of the next stages of the action plan. Further SPEAR developments, including a new and improved budget management form and automated system for managing withholding tax obligations, have been implemented. The IGC also continues to work towards ensuring the budget is used to maximum effect. For this, the team has aligned outputs with thematic areas, resulting in 85.05% of the budget being directly spent on thematic areas within IGC’s portfolio. This is a slight increase from last year’s proportion of 83.06%, demonstrating the IGC’s commitment spend each pound as effectively as possible.

Equity: Equity entails promoting a fairer investment and impact, ensuring that each pound spent contributes to building an inclusive and diverse organisation. The IGC has continued to prioritise equality, diversity and inclusion (EDI) within operations and with staff. EDI is an integral part of IGC’s annual Team Strategy Meetings (TSM) to ensure these values are internalised. IGC have also recently started disaggregating their data by gender and other inclusion markers. As mentioned elsewhere in the review, there is room for improvement in terms of ensuring equity in the area of gender and incentivising local researchers’ participation in projects.

VfM performance compared to the original VfM proposition in the business case

Based on the findings from this annual review, and the expectations set in the business case, the IGC is providing good value for money.

E: RISK

Overview of risk management

The overall risk rating assigned to IGC is moderate.

Strategy and Context risk is assessed as major. Uncertainties with IGC's contract extension pose financial risk. The IGC will hit the contract limit before the end of the programme, approximately April 2025. If operations end abruptly, this would lead to curtailment of research projects and potentially the loss of expert staff and capability. This disruption could result in reputational damage among host governments who would otherwise benefit from IGC advice and reduced impact, leading to diminished value-for-money. This could be mitigated by an increase in the value of the contract.

Safeguarding and Fraud

IGC’s policies and channels to report, escalate and investigate concerns are clear. Cases reported and escalated demonstrate the system is working. Overall, FCDO has high confidence in both LSE’s fraud detection, reporting and prevention, and their safeguarding procedures

Safeguarding risk is assessed as moderate. Following allegations of institutional weaknesses within the LSE when it comes to safeguarding, to further strengthen LSE mitigations, FCDO has refreshed our safeguarding approach by issuing Chief Scientist's letter on Fraud and Safeguarding to IGC, raised, discussed the matter with LSE/IGC management, and requested assurances that allegations are escalated and taken seriously and staff are made aware of policy. One case was reported in a country office, and this was investigated to a satisfactory conclusion.

The risk of fraud, bribery and corruption is assessed as moderate. We continue to review IGC's fraud compliance systems and communicate frequently with the delivery team about expectations on fraud and bribery. There have been two cases where a downstream supplier has identified fraud, in two countries. The downstream supplier’s approach was robust, and we are satisfied that IGC management had a clear line of sight to monitor effectively.

Operational risk is assessed as minor. IGC has the appropriate internal capacity to deliver the project and deliver expected results.

Fiduciary risk is assessed as moderate. Financial management of IGC is robust with transparent and clear financial reporting on regular basis.

External and Reputational risk are assessed as moderate. FCDO and IGC continue to have dedicated risk management meetings. A joined-up approach to risk assessment to foster a more joined up and proactive approach to risk management, aligning country risk assessments, the risk register and a watchlist have been maintained to manage any external factors could impact the success of the programme.

Risk reporting from the LSE is up to date and detailed. The ‘Country Watchlist’ is a helpful addition to the core risk register, and urgent issues are usually escalated to the SRO on an ad hoc basis when they arise, rather than waiting for the quarterly risk meeting. However, FCDO also raises issues with IGC, for example on the recent political uncertainty in Bangladesh.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Governance
The IGC programme has various governance levers, including:

Governance Lever	Frequency	Cast List
Governance Board	Bi-annually	IGC: Executive Director (SMT), Finance Director (SMT), International Programmes and Impact Director (SMT), / FCDO: EDD Deputy Director (SCS), JIGT Team Leader, GRT Team Leader, SRO, PRO, Economic Advisor, Programme Manager
Risk Meeting	Quarterly	IGC: Finance Director (SMT), Head of International Compliance / FCDO: SRO, PRO, Programme Manager
Finance Meeting	Monthly	IGC: Finance Director (SMT), Head of Financial Management, Finance Systems Supervisor / FCDO: SRO, PRO, Programme Manager
Programme Management Calls	Fortnightly	IGC: Finance Director (SMT), International Programmes and Impact Director (SMT) / FCDO: SRO, PRO, Economic Advisor

Overall, the above framework allows high levels of accountability in some areas, and less in others.
Though the Governance Board is a somewhat helpful forum, because of its relative infrequency and the presence of multiple senior officials, it is rarely an appropriate time to discuss and agree on programme-level actions. However, the programme management calls are not an effective solution to this, since they are not a sufficiently formal platform to achieve the desired accountability and transparency.

Governance structures for the IGC should evolve as the financial, institutional and thematic set-up of the programme changes over time. To support this, the IGC and FCDO should establish a Quarterly Programme Board to deliver on three key functions: i) supporting FCDO’s Centre of Expertise model, which enables country missions to buy into the centrally managed programme; ii) overseeing short-term RPF activities; and iii) addressing any emerging issues. This board will serve as the central governance mechanism for coordinating these workstreams, approving new activities under, and extending existing ones as needed.

Recommendation 9: FCDO should implement a quarterly ‘Programme Board’ at working-level below the Governance Board, to make programme-level, strategic decisions. This will also improve coordination between FCDO and IGC, as well as with other interventions, and will enable the prioritisation of IGC bids. FCDO to implement the Programme Board by August 2025.

Commercial

There is currently a contract amendment being put to the Procurement Steering Board to extend the financial limit of the IGC Phase 3 contract.

Financial Performance

The LSE demonstrates strong budget management of the IGC programme through its internal reporting system. The monthly finance meetings are a helpful forum to discuss the latest monthly statements with FCDO, as well as progress to date on forecasting and accruals. For this reporting year, the full allocated budget was spent by the IGC. The IGC provides the FCDO with monthly financial statements, as well as quarterly forecast estimates and invoices. There is an annual audit process to ensure that statements are accurate.

The budget for the review period was £10 million and IGC successfully spent 100% of this budget. The IGC’s financial management has been continually improving. For example, the accrual balances have significantly improved but remain relatively high which is in part due to the nature of the programme and its downstream partners.

Recommendation 10: As agreed in May 2025, monthly statements were updated from June 2025 onwards to align expenditure categories with FCDO proforma categories, making it easier to track spend against budgets. As the end of the programme approaches, IGC and FCDO should implement and quality assure these new processes, with a view to improving visibility over internal financial systems, particularly the expenditure reporting, through improved quarterly reporting.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evaluation

Monitoring activities throughout the review period have been both desk- and field-based. The FCDO programme team travelled to Ethiopia and Uganda as part of this Annual Review and met with a range of stakeholders including IGC programme staff (UK-based and country-office based), FCDO staff at Post, and policymakers and Ministers in-country. Research predominantly took the form of interviews.

Evidence

The FCDO team found that the programme was operating well in-country and that the IGC country teams were well-embedded in the relevant ministries and able to make impact in various policy areas. The team found some disconnect between the central hub and the country offices which could be improved.

Learning
There is scope for the IGC to engage more with FCDO, both in country, and in HQ, in order to share learning, add value and avoid duplication. This can also include cross-learning between IGC countries as well as with FCDO.

Recommendation 11: FCDO to facilitate closer working between IGC and other FCDO economic development programmes in-country. IGC to ensure country staff are meeting regularly with Posts in-country to maximise IGC’s profile and capitalise on synergies between FCDO-funded initiatives, while recognising the importance of IGC’s reputation as an independent learning partner.

Recommendation 12: IGC to present their findings to FCDO more regularly, with the FCDO IGC programme team identifying opportunities and facilitating. This would be to ensure transparency, accountability, and informed decision-making, while also fostering partnerships and creating synergies with other FCDO programmes. IGC to track and collate the number of presentations/findings shared with FCDO, both in London and by IGC representatives in-country, to share by May 2026.

H: RESPONSIVE POLICY FUNCTION

During this reporting year the Responsive Policy Function milestones have been delivered through the initiatives; namely Cities that Work, State Fragility and Tax for Growth, and the Country Programmes. The two evidence funds, Small and Growing Businesses fund and Agri-SME Evidence fund, are captured together under ‘firms’ for the purposes of this year’s activity reporting. Many of the objectives and corresponding outputs are long-term. For example, they include launching the new Agri-SME Evidence fund, fundraising for the SGB Evidence fund, and synthesising and facilitating policy impacts of work conducted so far. The Agri-SME fund aims to expand the knowledge base on finance and agriculture markets across Sub-Saharan Africa. The SGB fund supports collaboration between researchers and practitioners on how to support small businesses to create jobs. These two research funds open calls for papers and commission robust academic research. A further Responsive Policy Function proposal has been developed by LSE, to be further developed in Q3 2025.

Recommendation 13: FCDO and LSE to work together on a mechanism to respond to very short-term requests (six months or less) from partner governments, via FCDO posts, under this Responsive Policy Function. The FCDO-organised Programme Board should look at all the activities in the responsive policy function on a quarterly basis. FCDO and LSE will agree on a revised process to deliver on the RPF, following the governance structure set out in the ToRs.

I: GENDER & INCLUSION

There were two recommendations in the 2023 Annual Review relating to gender & inclusion:

Progress on previous recommendations
2023 Recommendation(s)	2024 Progress	Implemented?
IGC continues to produce high quality research on gender and climate nexus and raise profile of this work through dissemination.	IGC have made progress on this recommendation. LSE and FCDO to work together to continue progress and improve dissemination.	Ongoing
Undertake data collection and disaggregation of gender and inclusion research products, and report this to FCDO.	IGC included inclusivity markers in the AR 2023-24 for the last two Commissioning Boards, including gender, climate change and marginalised groups. In addition, IGC has also reported on the following gender markers information: / Proportion of gender focused impact cases (primary + secondary) and gender data availability for FY 23-24 (Output 1.1 and 1.4). / Proportion of working papers in all P3 (Output 2.1) · Proportion of conference presentations in P3 (Output 2.2). / Proportion of published papers in P3 (output 2.3) / Proportion of ongoing SPFs. Note: We mention that this indicator is in progress because it represents a continuous effort where more data can be analysed, and it remains an ongoing priority for IGC.	Yes / ongoing

There are two core metrics to analyse the IGC Phase 3 programme’s work on gender & inclusion. The first is the quality and volume of their outputs which feature a gender and inclusion angle in either a primary or secondary capacity. The second is the diversity of the programme’s staff, particularly within its senior leadership and from a steering committee perspective.

Quality and volume of IGC’s gender and inclusion outputs

As of May 2025, out of IGC’s 644 active projects, 63 have a primary gender focus. This demonstrates a strong focus on gender, but gender could still be mainstreamed further into both research and country office/policy work.

Through a mix of desk and field research, FCDO highlighted some points of resistance:
- A perception that gender is not relevant to areas of economics, particularly macro.
- A fear that partner governments may consider gender 'ideological', and focusing on it may therefore bringing up gender will alienate them.

FCDO team found the idea the gender is not relevant to macroeconomics to be fairly common during the field research for this review. However, as the IMF has advised[2], gender is a “macro-critical” issue and fiscal and monetary policy choices affect women and men differently because of their different positions in the economy, both market (paid) and non-market (unpaid). In light of this, it will be important to maintain focus on gender.
[2] Interim Guidance Note on Mainstreaming Gender at The IMF

Diversity within the programme's staff
The IGC has various leadership levers. On the senior Management Team, women are well-represented with three women and two men comprising the SMT. Of the seven-person steering group, two are women. Only one of the seven Country Directors is a woman and only two of the twelve senior country economists are women. This reflects a disparity between the gender representation in the programme’s London hub versus in-country. The drivers of this have been assessed by the reviewers through a mix of desk and field research, and identified the following points of resistance:
- Belief that there is a lack of high-quality female economists and researchers.
- Concern of "inclusion for inclusion's sake".

Recommendation 14: As part of the wrap-up report delivered at the close of this phase of the programme, IGC should produce a portfolio gender analysis. The approach to this analysis should be agreed by September 2025. IGC to foreground gender where possible for the remainder of the programme and report on progress in the Annual Report. It would be beneficial if IGC could include mention of race and ethnicity in the wrap-up report, to broaden the scope beyond gender – if there is a lack of data, IGC could provide an assessment of what data ought to be collected to facilitate such analysis.
FCDO to organise discussion with IGC with relevant policy team on women’s economic leadership and empowerment to review how to improve gender and inclusion outputs.

J: LOCALISATION & CAPACITY BUILDING

In this period, the IGC performed less well on localisation and capacity building of local researchers, although this is improving thanks to various measures put in place over the life of the programme. The IGC focuses on research excellence, and its approach to localisation and capacity building is primarily via matching and collaboration between local researchers and experienced Principal Investigators, as well as providing advice from IGC local staff provided to local researchers on proposals.

In IGC Uganda, a strong community of evidence of international and local research groups exists including presence of UNU-WIDER, the IMF and World Bank, and leading local research institutions and thinktanks like Makerere University and EPRC. The IGC could do more to strengthen collaboration with local researchers to improve local context and thus improve research quality.

In Ethiopia, IGC has a big focus on building capacity. A major challenge is getting local researchers commissioned. Last year, the majority of proposals were submitted by Ethiopians but fell below the IGC quality threshold. In Ethiopia, like Uganda, local researchers are often more expensive than international researchers because they lack financial resources from their home institutions. Collaboration between local and international researchers has helped to raise the quality of the projects, including helping international PIs learn more about local context and local PIs to learn about the international standard.

Another issue reported to the FCDO programme team was limits placed on claimable PI hours, which act as a disincentive to local researchers who depend on this as an income stream. This funding approach should be reviewed by IGC and FCDO as part of the localisation work.

The IGC Central team have expressed openness to thinking about research differently with a greater focus on policy impact in local contexts, whilst still maintaining research quality.

Recommendation 15: IGC and FCDO to review the suitability of how we measure academic impact to value the work done by local researchers, to give greater depth to this measurement beyond whether it appears in ‘top 5 journals’ (see recommendation 4 above about tracking academic impact). IGC to address this recommendation through updates on state-of –play and inclusion in the end-of-programme review of detailed information on the new approach and how it responds to FCDO’s feedback.

Recommendation 16: By October 2025, IGC and FCDO to review the current payment policies to ensure that local researchers are not disincentivised from participating in commissioning processes.

Annex 1: How does IGC measure policy impact?

How does IGC measure policy impact?
Measuring policy impact is notoriously difficult. The IGC’s impact methodology attempts to present a simplified and aggregated measure of its contribution to policy across all countries by assigning ‘impact levels’ to each project. There are two levels of impact reported in the logframe.
Level 3: hearing with senior/influential policymakers, with evidence that recommendations were internalised and/or that exchanged ideas have influenced policy discussions.
Level 4: policy decision demonstrably and substantially informed, caused or influenced by the IGC based on evidence.

Annex 2: Outcome 1. Three Cases of Transformational Change
The case study, "Transformational Change: Conflict Management and Social Integration in Mozambique," highlights the significant impact of the International Growth Centre's (IGC) initiatives in Cabo Delgado. Since 2015, the IGC has funded seven research projects with a total investment of nearly GBP 180,000, focusing on conflict management and the social reintegration of Internally Displaced People (IDPs). Key results include the implementation of information campaigns that effectively countered the political resource curse and reduced violence by promoting local accountability. These campaigns led to a significant shift in government and community practices, with religious leaders in Cabo Delgado institutionalizing conflict prevention through an interfaith statement and radio campaigns.
The IGC's research demonstrated the effectiveness of non-military, low-cost strategies for conflict prevention, influencing the government's approach and contributing to the establishment of the Agency for Integrated Development of the North (ADIN). The research also highlighted the importance of social cohesion and community-led responses to integrate IDPs, leading to improved relations between IDPs and host communities in Pemba.
The interventions reduced the appeal of insurgent groups by clarifying the roots of Islam and promoting peace, resulting in a decrease in youth radicalization. The IGC's work has been instrumental in fostering collaboration between Christian and Muslim leaders, leading to the creation of the "Council of Peace" and ongoing efforts to address conflict through evidence-informed approaches. The case study underscores the importance of long-term research collaborations, effective communication, and responsive, context-specific research in achieving transformational change in conflict-affected regions.

The case study, "Transformational Change: Ghana Commodity Exchange (GCX)," highlights the significant results and impact of the GCX on Ghana's agricultural sector. Launched in November 2018, the GCX addresses market inefficiencies affecting nearly 40% of the workforce. The International Growth Centre (IGC) played a pivotal role, investing nearly GBP 0.5 million since 2014 in research, policy engagement, and capacity-building activities. This support facilitated the development of baseline measures, the use of technology for real-time market data collection, and the promotion of evidence-based policy changes. Key results include the expansion of the GCX from one to eight warehouses, integrating over 350,000 farmers into its network. By 2022, the GCX facilitated trade worth over GHS 31.3 million, significantly improving market access, price transparency, and economic outcomes for farmers. The IGC's research also introduced the 'nano commodities exchange' model, which aims to enhance inclusivity for smallholder farmers by creating local agricultural markets. The GCX's success has attracted international interest, influencing similar initiatives in other African countries and contributing to the formation of the African Commodities Exchanges Association (ACX). This association aims to harmonize trade regulations and expedite cross-border transactions, further amplifying the GCX's impact. Overall, the case study underscores the importance of long-term research collaborations, strong policy champion support, and responsive, context-specific research in driving transformational change and achieving significant economic and social benefits for Ghana's agricultural sector.

The case study, "Transformational Change: Ghana Commodity Exchange (GCX)," highlights the significant results and impact of the GCX on Ghana's agricultural sector. Launched in November 2018, the GCX addresses market inefficiencies affecting nearly 40% of the workforce. The International Growth Centre (IGC) played a pivotal role, investing nearly GBP 0.5 million since 2014 in research, policy engagement, and capacity-building activities. This support facilitated the development of baseline measures, the use of technology for real-time market data collection, and the promotion of evidence-based policy changes. Key results include the expansion of the GCX from one to eight warehouses, integrating over 350,000 farmers into its network. By 2022, the GCX facilitated trade worth over GHS 31.3 million, significantly improving market access, price transparency, and economic outcomes for farmers. The IGC's research also introduced the 'nano commodities exchange' model, which aims to enhance inclusivity for smallholder farmers by creating local agricultural markets. The GCX's success has attracted international interest, influencing similar initiatives in other African countries and contributing to the formation of the African Commodities Exchanges Association (ACX). This association aims to harmonize trade regulations and expedite cross-border transactions, further amplifying the GCX's impact. Overall, the case study underscores the importance of long-term research collaborations, strong policy champion support, and responsive, context-specific research in driving transformational change and achieving significant economic and social benefits for Ghana's agricultural sector.

The case study, "Transformational Change: Uganda Economic Growth Forum (EGF)," highlights the significant impact of the EGF on Uganda's economic policy landscape. Launched in 2017 as a joint initiative between the Ministry of Finance, Planning, and Economic Development (MoFPED) and the International Growth Centre (IGC), the EGF has become a pivotal platform for inclusive and evidence-informed policy dialogue. The IGC has supported the EGF through funding seven events, two research projects, and a book, with a total investment of approximately GBP 250,000.
Key results include the institutionalisation of the EGF as part of Uganda’s annual budget cycle, ensuring that high-quality research informs economic strategy. The EGF has facilitated discussions on crucial topics such as agriculture, tax policy, tourism, and climate change, leading to tangible policy changes. For instance, insights from tax policy presentations prompted MoFPED to reconsider its approach to tax incentives, and discussions on tourism contributed to a substantial increase in government funding for the sector.
The EGF has also fostered collaboration between Ugandan and international researchers, enhancing the local research ecosystem. The forum's emphasis on sustainability has influenced the integration of climate change and carbon pricing into national policies. The EGF's success has led to its replication in Zambia, demonstrating its scalability.

Overall, the EGF has reshaped economic policy debates in Uganda, promoting evidence-based decision-making and fostering long-term research collaborations. Its integration into the national budget cycle and broad participation from diverse stakeholders underscore its role in driving transformational change in Uganda's economic planning and policy implementation.

Annex 3: Output 1.1 Summary list of the 74 reported instances of IGC projects contributing to national or sub-national policy discussions and/or processes in resident countries

Project Location	Project focus	Policy Impact	Changes		Substantive Activities	Key Stakeholders Engaged
Bangladesh	Energy-Efficient Technologies in Manufacturing	Promotes the adoption of energy-efficient technologies in the leather goods and footwear sector.		Influences managers' beliefs about cost savings and willingness to pay for new technologies.	Conducting a Randomised Controlled Trial (RCT) to track managers' evolving beliefs and willingness to adopt new technologies.	SMEF, Government of Bangladesh
Zambia	Informal Settlements Mapping	Addresses the lack of spatial data for informal settlements in Lusaka.	Improved understanding and mapping of informal settlements to inform policy decisions.		Collaboration with UN-Habitat, Ordnance Survey, and Commonwealth Association of Architects to create an automated base map.	Ministry of Local Government, Ministry of Lands and Natural Resources
Ethiopia	Inclusive Transportation Strategies	Develops inclusive transportation strategies in Addis Ababa.	High-quality, free transport reduces travel burdens and improves social and economic well-being, particularly for women.		Research collaboration with Boston University, AidData, and Econinsight Center for Development Research, supported by IGC Ethiopia and Policy Studies Institute.	Ministry of Transport, Addis Ababa City Roads Authority
Ethiopia	ICT Access and Use	Addresses the need for robust information on ICT access and use by firms and households.	Enhanced survey methodology to gather detailed ICT data for policymaking.		Collaboration with the Ministry of Innovation and Technology to develop ICT modules for existing surveys.	Ministry of Innovation and Technology, Ministry of Planning and Development
Ethiopia	Rural-to-Urban Migration	Quantifies the impact of rural-to-urban migration on city growth.	Provides insights to help policymakers manage population growth in cities.		Ongoing collaboration with multiple stakeholders to identify the causal impact of migration on urban development.	State Ministry of Trade and Regional Integration
Ethiopia	Climate and Weather Services	Evaluates the impact of climate services on agricultural productivity.	Identifies the low access to climate information services and their potential benefits.		Large-scale survey of farming households and analysis of climate service dissemination methods.	Ministry of Planning and Development, Ethiopian Institute of Agricultural Research
Ethiopia	Waste Management	Evaluates the feasibility of the current waste billing system.	Identifies challenges and potential improvements for waste segregation and management.		Scoping exercise to assess the effectiveness of the waste billing system.	Ministry of Agriculture, Policy Studies Institute
Ethiopia	Climate Information Usability	Examines the usability of climate information for agricultural activities.	Demonstrates significant improvements in technical efficiency with climate information use.		Workshop to share research findings with policymakers and researchers.	Ministry of Agriculture, Policy Studies Institute
Ethiopia	Artisanal and Small-Scale Mining	Aims to increase productivity in the ASM sector.	Provides a comprehensive baseline survey to inform policy decisions.		Follow-up study to identify factors affecting productivity in the ASM sector.	Ministry of Mines and Petroleum
Ethiopia	Labour Market Efficiency	Evaluates the impact of job postings on matching efficiency.	Provides insights into improving job search and matching processes.		Field experiment with varying job advert information content.	Policy Studies Institute, Ministry of Labour and Skills
Ethiopia	Social Protection for Garment Workers	Examines job-displacement insurance for laid-off workers.	Highlights the need for strengthened social protection policies.		Randomisation experiment in Hawassa Industrial Park.	Ministry of Finance, Ministry of Planning and Development
Ethiopia	Inclusive Growth Conference	Guides the research agenda on sustainable growth.	Identifies critical research gaps and informs policy decisions.		Full-day conference with policymakers, researchers, and industry leaders.	Ministry of Planning and Development, Ethiopian Coffee & Tea Authority
Ethiopia	Migration and Labour Mobility	Studies the constraints and opportunities for migration.	Provides a basis for broader research on migration and labour mobility.		Background research and stakeholder engagement.	Ministry of Labour and Skills, Policy Studies Institute
Ethiopia	Skills Gap Analysis	Quantifies the skills gap to inform educational reforms.	Aims to improve job-matching and productivity.		Collaboration with the Ministry of Labour and Skills.	Ministry of Labour and Skills
Ghana	Business Establishment Survey	Assists in preparations for the next IBES.	Ensures the survey responds to policy needs.		Workshop event with stakeholders to share findings and insights.	Ghana Statistical Services, Ministry of Trade and Industry
Ghana	Electricity Tariff Changes	Observes responses to changes in electricity tariffs.	Informs policy on incentivising electricity use.		Partnership with Northern Electricity Distribution Company to analyse data.	Northern Electricity Distribution Company, Public Utility Regulatory Committee
Ghana	Labour Market Efficiency	Evaluates the impact of an online job portal.	Identifies accessibility issues and designs a mobile solution.		Pilot of Text4Jobs Ghana using USSD mobile technology.	Youth Employment Agency, Ministry of Employment and Labour Relations
Ghana	Commodity Markets	Supports smallholder farmers in decision-making.	Pilots innovative mini-markets for commodity exchanges.		Continuation of work on commodities markets.	World Food Programme, Ministry of Food and Agriculture
Ghana	Civil Service Reforms	Strengthens the partnership with the Office of the Head of Civil Service.	Shares research findings to inform civil service reforms.		Workshop with civil service leaders and department heads.	Office of the Head of Civil Service
Ghana	Dissemination Event	Presents findings from ongoing studies.	Informs policymakers and stakeholders on various research topics.		Workshop with policymakers, academics, and industry stakeholders.	Fair Wages and Salaries Commission, Ministry of Employment and Labour Relations
Ghana	Organisational Socialisation	Explores socialisation methods in the civil service.	Provides insights into improving individual and organisational performance.		Qualitative interviews and surveys with civil service recruits.	Office of the Head of Civil Service
Jordan	Water Conservation	Fosters water-saving behaviours through religious messaging.	Encourages responsible water use and reduces wastage.		Partnership with GIZ and the Ministry of Islamic Affairs to evaluate the intervention.	Ministry of Planning, Ministry of Water
Mozambique	Flood Preparedness	Enhances household resilience to flooding.	Increases protective actions and collective behaviour.		Information campaigns and digital tools to raise risk awareness.	Municipality of Quelimane, Ministry of Land and Environment
Mozambique	Tax Revenues in Quelimane	Enhances local fiscal autonomy and reduces dependence on central government.	Preliminary findings suggest low tax compliance and awareness.		Meetings with municipal officials, focus groups, baseline survey, dissemination event.	Municipality of Quelimane, Commission on Tax Revenues
Mozambique	Municipal Tax Compliance	Shapes urban development through improved tax compliance.	Implementation of a digital taxation system in Maputo and Matola.		Meetings with municipal officials, pilot sample, follow-up project.	Municipality of Maputo, Municipality of Matola
Mozambique	National Development Strategy	Contributes to Mozambique's medium-term development strategy.	Recommendations included in the final strategy document.		Meetings with MEF, engagement with Prime Minister, formal document submission.	Ministry of Economics and Finance, Prime Minister
Mozambique	Rural-Urban Migration in Quelimane	Integrates rural migrants into urban labour markets.	Maps used for disaster preparedness and social programs.		Meetings with city government, survey data collection, dissemination event.	Municipality of Quelimane, City Mayor
Mozambique	Maize Value Chain Ecosystem	Revitalises the maize value chain ecosystem.	Recommendations for contract farming models.		Seminar with ICM, follow-up meetings, final study presentation.	Mozambique Cereals Institute, Ministry of Industry and Trade
Mozambique	National Development Strategy (Duplicate)	Contributes to Mozambique's medium-term development strategy.	Recommendations included in the final strategy document.		Meetings with MEF, engagement with Prime Minister, formal document submission.	Ministry of Economics and Finance, Prime Minister
Mozambique	Climate Risk and Food Security	Enhances food security policies in response to climate change.	Incorporation of resilience questions in food security surveys.		Meetings with MADER, dissemination of preliminary results, feedback incorporation.	Ministry of Agriculture and Rural Development
Mozambique	Market Access Improvements	Evaluates the impact of rural road upgrades on economic development.	Interim findings shared with MADER and other stakeholders.		Collaboration with Stockholm University and World Bank, dissemination workshops.	Ministry of Agriculture and Rural Development
Mozambique	Healthcare Access	Improves healthcare access and outcomes in Mozambique.	Positive influence on primary healthcare provision and malaria treatment.		Collaborative event with INS, dissemination to policymakers and NGOs.	National Health Institute, Ministry of Health
Mozambique	Integration of IDPs	Promotes bottom-up integration of internally displaced persons.	Increased religious tolerance and community cohesion.		Community meetings, collaboration with IOM and ADIN, dissemination events.	ADIN, Islamic Organisation of Mozambique
Mozambique	Tax Evasion and Fraud	Improves revenue collection and broadens the tax base.	Preliminary results shared with ATM, feedback incorporated.		Meetings with ATM, development of terms of reference, follow-up project.	Mozambique Revenue Authority
Pakistan	Flood Impact on Rural Households	Assesses the effects of flooding on migration and welfare outcomes.	Collaboration with RSPN and PPAF, data used for impact evaluations.		Meetings with stakeholders, dissemination events, follow-up project.	Rural Support Network, Pakistan Poverty Alleviation Fund
Pakistan	Air Quality Information	Improves access to reliable air quality data.	High willingness to pay for air quality information, weak priors for information sources.		RCT with residents, dissemination workshop, collaboration with stakeholders.	Environmental Protection Department Punjab, Pakistan Air Quality Initiative
Pakistan	Energy Sector Reforms	Evaluates the impact of subsidies and enforcement on electricity bill payment.	Preliminary findings shared with government, ongoing collaboration.		RCTs in KP and Punjab, dissemination to government and stakeholders.	Federal Ministry of Energy, Power Division
Pakistan	Air Quality Monitoring	Develops a representative database of air quality in Punjab.	Engagement with EPA, development of online dashboard.		Installation of air quality sensors, meetings with EPA, follow-up project.	Pakistan Environment Protection Agency, Ministry of Climate Change
Pakistan	Climate Change Policy	Informs policy around climate change and co-generates research ideas.	Continuous engagement with stakeholders, development of knowledge briefs.		Meetings with AEDB, workshops, MOUs with various departments.	Ministry of Energy, Planning and Development Board
Pakistan	Flood Impact on Rural Households (Duplicate)	Assesses the effects of flooding on migration and welfare outcomes.	Collaboration with RSPN and PPAF, data used for impact evaluations.		Meetings with stakeholders, dissemination events, follow-up project.	Rural Support Network, Pakistan Poverty Alleviation Fund
Pakistan	Workshops on Energy, Food Security, Agri-Food System, and Sustainable Cities	Identifies policy and research gaps, builds consensus, and establishes working groups.	Collaboration with key stakeholders, support for ADP and air quality management.		Workshops, roundtable discussions, MOUs with P&D and EPCCD.	Planning and Development Board, Environment Protection Climate Change Department
Pakistan	Pathways to Development Conference	Increases visibility and engagement with senior academics and policymakers.	Follow-up events and collaborations, video podcast series.		Conference, presentations, video podcasts, follow-up events.	Planning Commission, Punjab Planning and Development Department
Pakistan	Mother and Child Support Programme	Supports inclusive growth and social protection delivery system.	Scaling up of CCT programs, midline data collection.		Baseline and midline surveys, collaboration with UNICEF and World Bank.	Government of Sindh, World Bank
Pakistan	Tax Compliance and Organisational Effectiveness	Improves tax compliance and organisational effectiveness in Punjab.	Identification of non-compliant taxpayers, development of automated dashboard.		MOU with PRA, survey, development of dashboard, follow-up project.	Punjab Revenue Authority, Finance Minister of Punjab
Rwanda	Rules of Origin for AfCFTA	Enhances Rwanda's competitive edge in regional trade.	Development of recommendations for RoO negotiations.		Discussions with MINICOM, development of policy paper.	Ministry of Trade and Industry, Director General of Trade and Investment
Rwanda	Peer Review of Trade Policy	Improves the content and credibility of Rwanda's trade policy.	Identification of plagiarism, integration of recommendations into policy.		Peer review, discussions with MINICOM, integration into World Bank report.	Ministry of Trade and Industry, Director General of Trade and Investment
Rwanda	Collaboration through Research Event	Integrates empirical evidence into policy formulation.	Positive impacts on firm revenue, employment, and tax revenue.		Event with Yale, presentations, ministerial panel discussions.	Ministry of Trade and Industry, Ministers of Infrastructure, Trade and Industry, Education
Rwanda	Future Drivers of Economic Growth Report	Informs Rwanda's National Strategy for Transformation.	Update of FDG report, integration of recommendations into policy.		Collaboration with World Bank, discussions with government officials.	Ministry of Finance and Economic Planning, Central Bank, Ministry of Trade and Industry
Rwanda	Supplier Development Unit	Facilitates matchmaking between SMEs and MNCs.	Identification of barriers to buyer-supplier linkages.		Firm survey, discussions with RDB and World Bank.	Rwanda Development Board, Minister of Trade and Industry
Rwanda	Trade and Climate Change Workshop	Integrates economic development with environmental sustainability.	Rwanda's participation in ACT initiative.		Workshop, discussions with MINICOM and World Bank, follow-up project.	Ministry of Trade and Industry, Ministry of Environment
Rwanda	Export Growth Fund Evaluation	Enhances Rwanda's export capabilities and industrial policies.	Allocation of additional funds to EGF.		Evaluation report, discussions with BRD and government officials.	Development Bank of Rwanda, Ministry of Finance
Rwanda	National School Feeding Programme	Enhances efficiency and sustainability of school feeding strategy.	Comparative analysis of global practices.		Report, discussions with Minister of State in Charge of National Treasury.	Ministry of State in Charge of National Treasury
Sierra Leone	Property Tax Reform in Kenama	Expands revenue base to fund development programmes.	Scale-up of property tax reform system.		Diagnostic results, pilot programme, weekly technical committee meetings.	Kenama City Council, FCDO Sierra Leone
Sierra Leone	Income Opportunities for Maize and Poultry Producers	Creates income opportunities and improves nutritional outcomes.	Implementation of recommendations in solar mini-grid project.		Workshop, presentations, follow-up meetings.	UNOPS, Government of Japan
Sierra Leone	Agricultural Value Chains	Increases farmer adoption and production of maize.	Support for farmers with affordable processing services.		RCT with poultry farm, collaboration with MAF and PPFA.	Ministry of Agriculture and Forestry, Pig and Poultry Farmers Association
Sierra Leone	Political Party Debates	Supports political parties in candidate selection.	Recommendations for candidate selection process.		Collaboration with political parties, dissemination of findings.	Political Party Registration Commission, National Electoral Commission
Sierra Leone	Fragility and Resilience in Mano River Union	Consolidates peace dividends amid persistent challenges.	Request for support from ICPNC on peace and conflict studies.		Event, bilateral meetings, participation in technical working group.	Independent Commission for Peace and National Cohesion, Ministry of Planning and Economic Development
Zambia	Electronic Fiscal Devices	Improves VAT collections and tax compliance.	Implementation of EFDs, analysis of trade data.		RCT, collaboration with ZRA, dissemination of findings.	Zambia Revenue Authority, Commissioner of ZRA
Uganda	Frontline Supervision	Improves worker performance through effective supervision.	Persistent changes in worker performance.		Field experiment, presentations, media dissemination.	nnovations for Poverty Action (IPA), World Bank’s Development Impact Unit (DIME)/Senior DIME economists
Uganda	Government Procurement and Firm Performance	Enhances firm performance through government contracts.	Positive correlation between government sales and firm performance.		Analysis of VAT data, presentations to PPDA and PSDU.	Public Procurement and Disposal of Public Assets Authority, Private Sector Development Unit
Uganda	Climate Change Workshop	Raises profile of IGC in climate change research.	Collaboration with NEMA on environmental issues.		Workshop, presentations, follow-up meetings.	National Environmental Management Authority, Ministry of Finance
Uganda	Potential Growth Rates Analysis	Provides insights into Uganda's economic landscape.	Identification of factors affecting productivity.		Analysis, presentation to Bank of Uganda, discussions with government officials.	Bank of Uganda, Ministry of Finance
Uganda	Economic Growth Forum	Influences economic policy and fosters collaborations.	Policy recommendations and follow-up projects.		Forum, presentations, discussions with government agencies.	Ministry of Finance, Planning, and Economic Development, Uganda Revenue Authority
Uganda	Public Investment Efficiency	Enhances efficiency of public investment in Uganda.	Analysis of financial and implementation records.		Collaboration with PAP, presentation of findings, discussions with officials.	Project Analysis and Public-Investment Department, Ministry of Finance
Zambia	Rural Electrification	Evaluates impact of rural electrification on economic development.	Insights for updating the Rural Electrification Master Plan.		Collaboration with REA, ZamStats, and Zesco, dissemination of findings.	Rural Electrification Authority, Ministry of Energy
Zambia	Agricultural Market Efficiency	Informs institutional reforms and macroeconomic policies.	Identification of market constraints and policy recommendations.		Analysis of market data, presentations to stakeholders and policymakers.	Presidential Delivery Unit, Ministry of Agriculture
Zambia	Agricultural Productivity Constraints	Identifies constraints and provides policy options.	Evaluation of government programmes and market outcomes.		Interviews with policymakers, presentations, follow-up projects.	Ministry of Agriculture, Ministry of Livestock
Zambia	Economic Growth Forum	Influences policy and practice for sustainable growth.	Summary of policy recommendations for government.		Forum, presentations, discussions with stakeholders.	Ministry of Finance and National Planning, International Monetary Fund
Zambia	Administrative Data Infrastructure	Promotes evidence-based policymaking.	Establishment of Evidence Lab.		Mapping of data landscape, collaboration with MoFNP, creation of Evidence Lab.	Ministry of Finance and National Planning, Zambia Statistics Agency
Zambia	Food Reserve Agency Reform	Informs potential reforms of FRA.	Policy recommendations for FRA operations.		Analysis of RALS data, presentations to stakeholders, discussions with policymakers.	Presidential Delivery Unit, Ministry of Agriculture
Zambia	Constituency Development Fund Reform	Enhances management and disbursement of CDF.	Decentralization of CDF approvals and budget controls.		Analysis, recommendations, legislative advancements.	Ministry of Local Government, Cabinet Office
Zambia	Mining Sector Development	Fosters sustainable growth and diversification in mining sector.	Inclusion of recommendations in government strategies.		Consultative meetings, review of policy documents, announcement of geological survey.	Ministry of Mines, Presidential Delivery Unit

IGC Team	Project Name	Summary
Bangladesh	BGD-20179/How Do Managers’ Beliefs about New Technologies Evolve? Informational	This project involves an RCT with Bangladeshi leather goods and footwear producers to study how managers' beliefs about an energy-efficient technology evolve.
Cities That Work	ZMB-21011/Mapping informal settlements in Lusaka	This project pilots the creation of an automated base map of Lusaka to identify informal settlements.
Ethiopia	ETH-22092/Gendered Differences in Mobility and the Demand for Transport: Evidenc	This study in Addis Ababa examines the impact of providing high-quality, free transport on mobility and social well-being, especially for women.
Ethiopia	ETH-22181/Enhancing ICT Sector Survey Data in Ethiopia	This project develops ICT dedicated modules for existing surveys in Ethiopia to provide detailed information on access and use of ICTs by firms and households.
Ethiopia	ETH-22091/Migrants and City Growth: Evidence from Ethiopia	This study aims to quantify the impact of rural-to-urban migration on city growth in Ethiopia to help manage large population inflows.
Ethiopia	ETH-21095/Can climate and weather services enhance Ethiopian farmers’ resilience	This study estimates the impact of weather and climate services on farm productivity in Ethiopia using household survey data.
Ethiopia	ETH-23110/Exploratory study on Solid Waste Management (SWM) in Ethiopia	This scoping exercise evaluates the feasibility and effectiveness of the current waste billing system in Ethiopia to support sustainable waste management.
Ethiopia	ETH-23026/Climate information, production decision making, and technical efficie	This study finds that using climate information significantly improves technical efficiency in Ethiopian agriculture.
Ethiopia	ETH-21156/Ethiopia: Formalizing and Enhancing performance of artisanal and small	This study aims to identify factors that could increase productivity in the artisanal and small-scale mining sector in Ethiopia.
Ethiopia	ETH-20174/Gender gaps and job advertisements in urban labour markets	This field experiment in Addis Ababa examines if providing wage information in job postings improves matching efficiency.
Ethiopia	ETH-22138/The welfare and incentive effects of job-displacement insurance	This randomization experiment studies the impact of job-displacement insurance payments on workers laid off from the garment industry in Ethiopia.
Ethiopia	ETH-23128/Resilient Ethiopia: Sustainable Growth in a Changing Climate	This event in Ethiopia discusses sustainable growth and identifies critical research gaps related to climate change and inclusive growth.
Ethiopia	ETH-22145/Migration, Displacement, and Labor Markets in Ethiopia: Project Prepar	This research helps understand the constraints to internal and international migration in Ethiopia and forms the basis for a broader research agenda.
Ethiopia	ETH-21166/Assessing Skill Gaps in Ethiopia’s Urban Labour Market	This project quantifies the skills gap in Ethiopia to improve job-matching processes and enhance worker productivity.
Ghana	GHA-23084/IBES Users’ Engagement Workshop	This workshop in Ghana prepares for the next round of the Integrated Business Establishment Survey (IBES) by sharing findings and insights.
Ghana	GHA-22188/Electricity Tariff Structure and Firm-Household Usage Behaviour: Evide	This study observes changes in electricity consumption and tariffs in Ghana to incentivize households toward using electricity as their primary energy source.
Ghana	GHA-21168/ Making digitization more inclusive for job matching	This project pilots a USSD mobile technology solution to improve access to an online job portal in Ghana.
Ghana	GHA-22241/Betting Against the Future – Smallholder Farmers in Africa, Forward Co	This project pilots innovative mini-markets for commodities in Ghana to help smallholder farmers make better sales decisions.
Ghana	GHA-23046/Workshop on the Socialization of New Recruits in the Ghanaian Civil S	This event in Ghana shares research findings on civil service reforms and socialization of new recruits.
Ghana	GHA-23047/IGC Ghana Research Evidence Workshop/Day 2023	This dissemination event in Ghana presents findings from various ongoing studies to policymakers and stakeholders.
Ghana	GHA-22141/The Socialization of New Recruits by Their Line Managers in the Civil	This study explores how new recruits in Ghana's civil service are socialized by their supervisors.
Jordan	JOR-23028/Religious Leaders, Water Scarcity and Collective Adaptation: Evidence	This project in Jordan fosters water-saving behaviors by tapping into religious value systems and beliefs.
Mozambique	MOZ-21180/Preparing for urban flooding: The impact of risk mitigation informatio	This project in Mozambique uses low-cost information interventions to educate households on flood preparedness and resilience.
Mozambique	MOZ-22067/Tax compliance and local government autonomy: experimental evidence fr	This project investigates the property tax revenue collection system in Quelimane, Mozambique, focusing on tax compliance and building a coalition of stakeholders.
Mozambique	MOZ-23049/Taxation and Urban Development: Evidence from Maputo	This project studies the impact of reducing tax compliance costs on urban development in Mozambique, with a pilot sample of 40,000 households and 20,000 firms.
Mozambique	MOZ-22200/Contributing to the Review of Mozambique's National Development Agenda	This project provides inputs on sustainable development and digitisation for Mozambique's National Development Strategy, which were included in the policy document released in January 2024.
Mozambique	MOZ-21101/A Field Experiment on Integrating Rural Migrants in Cities	This project maps rural migrants in Quelimane, Mozambique, and designs interventions to help the city government with their integration.
Mozambique	MOZ-22097/Socialization and Harmonization Seminar of the Maize Value Chain Ecosy	This seminar in Mozambique discussed the findings of the Maize Value Chain Ecosystem Study and gathered contributions from various stakeholders.
Mozambique	MOZ-22200/Contributing to the Review of Mozambique's National Development Agenda	This project provides inputs on sustainable development and digitisation for Mozambique's National Development Strategy, which were included in the policy document released in January 2024.
Mozambique	MOZ-22195/Predicting the effect of climate change on vulnerability to food insec	This project quantifies the relation between environmental factors and food availability at the household level in Mozambique.
Mozambique	MOZ-22258/The last mile: the impacts of market access improvements in remote rur	This study evaluates the impact of market access improvements on economic development in rural Mozambique by upgrading 1200 km of rural roads.
Mozambique	MOZ-23137/Advancing Healthcare Access in Mozambique	This event in Mozambique disseminates findings from research on improving healthcare access and outcomes.
Mozambique	MOZ-22190/Do social interactions help to integrate internally displaced people?	This project studies the integration of IDPs in Pemba, Mozambique, through community meetings to promote bottom-up implementation.
Mozambique	MOZ-24162/Application of AI to prevent tax evasion and fraud	This study in Mozambique addresses tax evasion and fraud, proposing measures to improve revenue collection.
Pakistan	PAK-23007/Curse of the Cow: Barriers to Climate Adaptation in Pakistans Biblic	This project studies the effects of the 2022 flooding in Pakistan on migration, assets, employment, and welfare outcomes of rural households.
Pakistan	PAK-22039/Belief formation, signal quality, and information sources: Experimenta	This project in Lahore, Pakistan, studies beliefs about and demand for air quality information from different sources.
Pakistan	PAK-22224/Pushing on a String? Price and Enforcement Interventions to Reduce The	This project in Pakistan evaluates energy sector reforms and proposes interventions to combat electricity theft.
Pakistan	PAK-22025/Monitoring and Information Provision on Air Quality in Punjab	This project in Punjab, Pakistan, installs air quality sensors to develop a representative database of air quality.
Pakistan	PAK-23059/Making Pakistan Resilient: Synthesising knowledge on Climate Change	This project in Pakistan informs policy on climate change by identifying knowledge gaps and generating research ideas.
Pakistan	PAK-22179/The Impact of Flooding on Migration and Occupational Change Amongst th	This project studies the effects of flooding in Pakistan on migration, assets, employment, and welfare outcomes of rural households.
Pakistan	PAK-23060/Agenda Setting around Climate Change: Engaging with Stakeholders	This project in Pakistan hosts workshops on energy, food security, and sustainable cities to identify policy and research gaps.
Pakistan	PAK-23148/Pathways to Development – Conference on Equitable and Sustainable Grow	This conference in Pakistan discusses inequalities and social justice, presenting research on growth and development.
Pakistan	PAK-23051/A Maternal and Child Health Intervention in the Context of Unprecedent	This project in Sindh, Pakistan, evaluates the impact of a CCT programme on healthcare access and outcomes.
Pakistan	PAK-22180/Organizational Effectiveness and Tax Compliance in Punjab, Pakistan (2	This project in Punjab, Pakistan, aims to improve tax compliance and organizational effectiveness of the Punjab Revenue Authority.
Rwanda	RWA-22249/Maximizing domestic value-added in exports	This project in Rwanda establishes optimal rules of origin for key industries to enhance Rwanda's competitive edge in regional trade.
Rwanda	RWA-23050/Reviewing Rwanda’s National Trade Policy II draft	This project in Rwanda provides a peer review of the new trade policy, offering substantial contributions to policy development.
Rwanda	RWA-24167/YALE-IGC Policy Dialogue. Theme: Collaborationg through Research: Path	This event in Rwanda discusses the integration of empirical evidence into policy formulation, focusing on export growth.
Rwanda	RWA-24166/"Future Drivers of Economic Growth 2" - Trade and Private-Sector Devel	This report in Rwanda informs the National Strategy for Transformation, focusing on trade and private sector development.
Rwanda	RWA-21188/Creating comparative advantage: identifying information and technology	This project in Rwanda explores barriers to forming local buyer-supplier linkages to develop the domestic supply chain.
Rwanda	RWA-24164/Workshop on "Climate Change and Trade"	This workshop in Rwanda discusses the nexus of trade and climate change, highlighting Rwanda's engagement in global climate policy.
Rwanda	RWA-22257/Evaluating Rwanda's Export Growth Fund	This project in Rwanda evaluates the Export Growth Fund's impact on export capabilities and informs policy recommendations.
Rwanda	RWA-23158/School Feeding: Case Studies and Lessons for Rwanda	This project in Rwanda enhances the National School Feeding Programme by drawing lessons from global practices.
Sierra Leone	SLE-22031/Property Tax Reform and Improving Tax Compliance in Kenema: Scoping an	This project in Sierra Leone upgrades property value assessment procedures to expand the revenue base for development programmes.
Sierra Leone	SLE-21167/Identifying constrains in energy complementary value chains	This project in Sierra Leone creates income opportunities for maize and poultry producers and improves nutritional outcomes.
Sierra Leone	SLE-22256/Solving constraints along the agricultural value chain in Sierra Leone	This project in Sierra Leone investigates strategies for increasing farmer adoption and production of maize.
Sierra Leone	SLE-22102/Candidate Entry into Local Government	This project in Sierra Leone supports political parties in selecting candidates for local councils.
Sierra Leone	SLE-23138/Consolidating Peace and Building Resilient in Sierra Leone: Challenges	This study in Sierra Leone discusses fragility and resilience in the Mano River Union subregion.
Tax for Growth Initiative	ZMB-23011/Firm Responses to Tax Policy Innovations: Experimental Evidence from Z	This study in Zambia focuses on the effectiveness of policies intended to increase fiscal capacity and improve tax compliance.
Uganda	UGA-22057/Managers, Motivation, and Worker Productivity: Evidence from Survey En	This field experiment in Uganda explores the role of supervisors as coaches and their impact on worker performance.
Uganda	UGA-21123/Public Procurement as an Industrial Policy	This study in Uganda assesses the performance of local firms selling to government entities and its impact on firm performance.
Uganda	UGA-23079/Climate Change Workshop	This workshop in Uganda discusses the impacts of climate change on household wellbeing, agricultural productivity, and urbanisation.
Uganda	UGA-23163/Re-estimating potential growth in Uganda	This paper in Uganda analyzes potential growth rates and their implications for economic policy.
Uganda	UGA-23080/Economic Growth Forum (EGF) VII	This forum in Uganda discusses strengthening competitiveness to foster economic growth.
Uganda	UGA-21018/Identifying bottlenecks in public investment in Uganda	This project in Uganda enhances the efficacy of public investment by analyzing financial and implementation records.
Zambia	ZMB-22089/The Heterogenous Effects of Rural Electrification: Evidence from Zambi	This project in Zambia evaluates the impact of rural electrification on economic development.
Zambia	ZMB-23054/Unlocking Zambia’s potential for regional agri-food exports in resilie	This study in Zambia analyzes the efficiency of regional agricultural markets and the impact of restrictive export policies.
Zambia	ZMB-23055/Understanding the constraints to agricultural productivity in Zambia	This study in Zambia identifies constraints to agricultural productivity and provides policy options.
Zambia	ZMB-23132/2024 Zambia Economic Growth Forum: Pathways to Growth	This forum in Zambia discusses sustainable and inclusive economic growth, focusing on key areas for the country's future.
Zambia	ZMB-23096/Mapping the Data Landscape within the Government of Zambia	This project in Zambia maps the current data landscape to promote evidence-based policymaking.
Zambia	ZMB-23141/Evaluation of Zambia’s Food Reserve Agency	This project in Zambia informs potential reforms of the Food Reserve Agency to improve farm level outcomes.
Zambia	ZMB-22118/Constituency Development Fund Capacity Survey	This project in Zambia reforms the management of the Constituency Development Fund to address operational challenges.
Zambia	ZMB-22189/Mineral Resource Governance in Zambia	This project in Zambia develops a resource-led development strategy for the mining sector to maximize its contribution to economic growth.