## Annual Review 2025

Title: Centre for Disaster Protection
Programme Value £ (full life): £95.5m		Review date: 24 September 2025
Programme Code: 205231	AMP start date: 22 September 2017	AMP end date: 30 September 2029

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/18080341.odt
DevTracker Link to Latest Business Case Addendum:	https://iati.fcdo.gov.uk/iati_documents/D0006784.odt
DevTracker Link to results framework:	Logframe still in process of being published

A. SUMMARY AND OVERVIEW

Description of programme

The Centre for Disaster Protection programme is the UK’s flagship Disaster Risk Finance (DRF) technical assistance programme. The programme has two components, Centre for Disaster Protection (known as the Centre) and the World Bank Disaster Protection Programme (DPP or London hub). This annual review assesses progress against both components.

The programme supports developing countries and the humanitarian and development community to strengthen their pre-disaster planning and financial arrangements so they can better manage crisis and disaster risks, reducing the impact on people and helping to safeguard economic development. It draws upon UK and global expertise in risk, finance and insurance to provide:

- Advice and Analytics: impartial advice and analytics for developing countries, development and humanitarian agencies, civil society and other key actors, supporting them to design and implement risk financing arrangements and to embed them within effective systems for disaster preparedness, response and recovery.
- Research and Evidence: investment in global public goods that develop best practice, methodologies and tools, and produce evaluations and evidence on what works leading to a greater used of pre-arranged financial instruments.
- Capacity Building: knowledge and training for developing country Ministries of Finance, national disaster management agencies and other line ministries, as well as humanitarian agencies, civil society and other relevant stakeholders.
- Innovation: work to generate and incubate new and innovative solutions to development and humanitarian problems.
Policy and Outreach: influencing the multilateral system and external partners to align policy and programming with emerging best DRF practice to optimise impact.

The Centre for Disaster Protection programme was approved in Sept 2017. Three addendums and extensions to the Business Case have been made since its inception. In March 2018, an agreed an additional grant of £3m from the Commonwealth Summit 2018-20 Fund to provide technical assistance to eight Caribbean Commonwealth states and one UK Overseas Territory after the devastating hurricanes of 2017. A further addendum in November 2019 approved an additional budget of £62.1m to scale up and extend the project for a further three years (2021/22 to 2024/25). In December 2023 a further addendum was approved to extend the life of the programme to September 2029, within the existing agreed budget of £95.5m.

Centre for Disaster Protection (The Centre)

The Centre has a co-leadership structure. It is jointly led by an Executive Director, Chief Finance and Operations Officer, and two Associate Directors. It is supported by a Managing Agent, DAI Global UK who signed a contract amendment in September 2024 to extend their contract until June 2029. The Centre is accountable to a Board. The Board is the governing body of the Centre and is responsible for setting the Centre’s strategic direction and ensuring the effective operations of the Centre in fulfilment of its purpose and development impact, on which it reports to FCDO. The Centre is based in London and has a core full-time team of 27 staff. It has a wider roster of experts and flexible staff it can draw on as needed.

World Bank Disaster Protection Programme (DPP)

The DPP, based in London and financed through the Risk Finance Umbrella Trust Fund (UTF), aims to strengthen the financial resilience of low- and middle-income countries against disasters and climate shocks. The team of 4 staff delivers technical assistance and develops innovative national and regional disaster risk financing (DRF) solutions, which are typically implemented through World Bank operations.

The UTF, supported by the UK, Switzerland, and Japan, enables collaboration with a broad range of donors and partners. The DPP plays a distinct but important role in the development of DRF solutions and complements other financing resources, such as the Global Shield Financing Facility (GSFF)[1]. The DPP focusses on upstream technical, analytical, and advisory work to inform policy and design risk finance instruments, while GSFF supports the implementation of mature DRF solutions. The DPP’s expertise is frequently leveraged by GSFF-funded activities, providing just-in-time niche support for project implementation.
[1] The Global Shield Financing Facility sits in the World Bank and supports vulnerable countries and communities with increased access to climate shocks, disasters, and crises through technical advisory services, partnerships and financial packages.

Through private sector collaboration with London market financial organisations, the DPP contributes to technical knowledge products, facilitates exchanges, and ensures alignment with the FCDO’s disaster risk financing priorities, including strengthening risk pools.

Summary supporting narrative for the overall score in this review

The programme has continued to perform well this year. Programme outputs have either met or exceeded expectations meaning in this annual review overall, it has scored an A+ – outputs moderately exceeded expectations.

The Centre built on 2024’s significant achievements when the High-Level Panel published their report findings and recommendations on closing the crisis protection gap in January, supported by the FCDO’s Minister for Development. The Centre used their influence to position the paper as global thought leadership and have been making opportunities to use it as an influencing tool at the highest level. Building momentum from the Panel’s main recommendation to scale up pre-arranged finance, the Centre played a critical role in launching a global coalition who committed to this at the 4th Financing for Development Conference in Sevilla in July 2025.

The strength of the Centre’s advisory and training services positions them well for their increased focus on in-country, demand led work with the new five-year strategy. The strength of their service provision has been reflected through robust performances against their programme outputs this year. There is further work to do to strengthen the evidence base for success against outcome targets, which the Centre are prioritising through their ambitious Evidence function. Critical to the strategy is growing the demand-led, in-country focus and making a sustained, ambitious pivot to this approach.

In line with the vision from the original business case the Board, co-leads, FCDO and the Centre are exploring options to transition from the current largely FCDO funded model, into an independent entity with multiple funding sources.

During FY25, the DPP delivered strong results in a challenging resource environment. Engagements focussed primarily in the East and Southern Africa and South Asia regions, totalling 10 countries. With 4 members of staff and £900,000 in funding, the DPP facilitated private capital of US$ 375m across six African countries from the international insurance market and contributed to financial protection of 2.5 million vulnerable people from micro solutions alone. The FCDO should continue to support the DPP to focus on opportunities in countries where they can leverage the influence of major Bank lending operations.

The DPP has established itself as a leading force in thought leadership, driving the development of innovative products and providing strategic guidance to client countries. DPP’s technical expertise has informed the development of key products and methodologies for disaster risk financing, such as the IDA21 Crisis Response Toolkit and value-for-money assessments of different DRF instruments. The programme provides support to key FCDO impact areas, including technical inputs into new papers or analysis (for partners like CDP), and technical assistance to regional risk pools like ARC.

In response to last year’s agreement to review, this year the DPP logframe was reviewed and revised. It is now more aligned with the Risk Finance Umbrella Trust Fund reporting, has more ambitious targets, and better reflects the unique added value of the DPP.

Notable programme activities and results this year have included:

The Centre

1. Kenya National Treasury: Through a partnership between the British High Commission and the National Treasury of Kenya, the Centre has been advising on the development of the second iteration of Kenya’s National Disaster Risk Financing Strategy. The Centre is supporting an inter-ministerial group to provide technical input into the strategy process and deliver bespoke training through a series of in-country workshops. The revised strategy is expected to address a broader range of risks and instruments and to establish clearer links to national development goals. This work will continue next year.
2. Ministry of Finance, Gambia: The Gambia is a Pathfinder Country for the Global Shield, and, at the request of the World Bank and the Gambian Ministry of Finance, the Centre is supporting the development of a comprehensive national disaster risk financing strategy, including strengthening its contingency fund and designing risk transfer solutions for floods and windstorms.

Global Shield: In its’ role as coordinator, the Centre successfully operationalised the Technical Advisory Group (TAG) to the Global Shield Against Climate Risk, delivering country-specific technical reviews for Pakistan, Costa Rica and Senegal. A regional review for the Pacific is expected by September 2025, which will mark the completion of the Centre’s contractual obligations under this engagement.

Scaling up pre-arranged finance: The Centre played a critical convening role when the UK and Bridgetown Initiative jointly launched a Global Coalition to Scale up Pre-Arranged Financing under the Sevilla Platform for Action. This new initiative emerges directly from the High-Level Panel process and looks to take forward its recommendations, including explicitly increasing the volume and scale of pre-arranged financing tenfold – a process that the Centre will play a critical role in implementing. This will include contributions through their thought leadership as well as governance management and a secretariat function.

High Level Panel report on closing the crisis protection gap: The High-Level Panel published a landmark report in January which was the catalyst and guiding light for the Pre-Arranged Financing coalition launched under the Sevilla Platform for Action, at the Financing for Development Conference.

DPP

Pakistan: The DPP led the design of a Crisis Response Facility (CRF) for implementation under the Pakistan Resilient and Accessible Microfinance (RAM) Program, a US$125m operation approved by the World Bank Board. This operation is also leveraging US$25m in GSFF funding. The CRF will support the microfinance sector and its borrowers after severe floods and is expected to benefit over 1 million people in the next five years.

Nepal: In Nepal, the DPP developed a flood model which will be used by the government in the design of a sovereign risk transfer product, as well as by the Nepal Insurance Authority (NIA) to implement risk-based pricing for property insurance in Nepal’s insurance market.

REPAIR: The Regional Emergency Preparedness & Access to Inclusive Recovery (REPAIR) Project provides affordable, pre-arranged finance to governments and country systems in Eastern and Southern Africa. It benefitted from significant just-in-time support from the DPP in FY25 and features prominently in the DPP FY26 work program. The DPP supported the onboarding of Malawi and Zambia to the REPAIR program with technical notes and training prepared to support government design decisions, and helping countries share experience. This onboarding (alongside Angola, Burundi and Seychelles) was approved by the World Bank Board in early July 2025. In FY25 the REPAIR contingent financing layer provided a payout of US$16.9 million to the government of Mozambique following Cyclone Jude to deliver urgent relief—including food assistance, medical supplies, and shelter—to nearly 318,000 people affected by the cyclone.

DRIVE: In the Horn of Africa (Djibouti, Kenya, Ethiopia and Somalia), the DPP provided technical inputs required for the implementation of the insurance product offered under DRIVE. In FY25, over 180,000 pastoral households were covered by packages of financial services, with co-financing from the GSFF. The enabling environment for the initiative was strengthened through the enactment of new laws, new regulations and guidelines, and extensive training of the regulator. This will support millions to access appropriate products to enhance resilience to climate risks.
Major lessons and recommendations for the year ahead

All programme components

Lesson: The funding landscape is changing rapidly. With an increasingly crowded DRF landscape and growing demand for DRF technical assistance, coordination between different DRF programmes and funding vehicles is becoming ever more important.
Centre

Recommendation for country-level work: As the Centre looks to scale up its’ country-level, demand-led work, to drive lasting systems change, the work needs to be appropriately resourced and aligned with client demand and political economy context. In addition, the Centre should be investing in local anchoring and partnerships – i.e. regional partners, national think tanks, and local institutions – this will enhance legitimacy and effectiveness, particularly where in-country presence is limited.

Lessons from the Sahel programme: The main lesson from the recently concluded Sahel work is that there is a need to balance a regional perspective, with a more targeted focus on country specific issues.
Recommendation: Deeper, more targeted country engagement is likely to be a better model for future support.

Lesson on the Centre’s convening role: The High-Level Panel and the launch of the Crisis Protection 2.0 agenda successfully convened a wide range of stakeholders and generated strong visibility. These platforms demonstrated the Centre’s convening power and its ability to shape the global DRF narrative.
Recommendation: Given the increasing number of actors and activity in the DRF space the need for coordination is rapidly increasing. The Centre has already demonstrated its ability to play this convenor / role and should aim to develop this role further through the Sevilla Platform for Action on Pre-Arranged Finance.

DPP

Lesson on differing incentives: While private sector involvement improves the availability of risk information and contributes to sustainability, it is important to recognise differing incentives between technical assistance providers, governments and the private sector.
Recommendation: Finding a way through the differing incentives of all partners, the DPP should continue to ensure that clients get informed and independent advice that enables them to make the best possible decisions.

Lesson on holistic design of DRF approaches: DRF instruments should be designed as part of an integrated package, rather than as standalone products such as insurance. They must be linked to operational preparedness to ensure funds reach beneficiaries quickly and effectively. Transparent post-disaster fund execution, inter-agency coordination, and integration with national budget systems are critical for translating payouts into meaningful support. These lessons have been central to the design of the REPAIR program in Southern Africa.
Recommendation: To achieve this, the DPP should focus on multi-stakeholder partnerships—including public and private actors—to enable timely responses and to mobilise private capital.

Lesson on evidence-based policy making: Robust analytics and global evidence are foundational to informing government DRF policies. Sustained policy dialogue over the long term is necessary to embed these insights. Equally important are training and tool development efforts that support knowledge transfer and help clients internalise DRF concepts.
Recommendation: Strengthen efforts to build the global evidence base for DRF and continue to exchange knowledge of the evidence between all stakeholders— including governments, development actors, academia, and the private sector. This enhances understanding of the evidence, builds trust, fosters innovation, and can lead to high-impact partnerships.

Lesson on complementarity with other funding programs: Funding sources such as IDA and/or GSFF are crucial to finance the implementation of DRF financial instruments. However, their success depends critically on highly specialised upstream technical expertise in Disaster Risk Financing. This expertise plays a critical role in advancing complex DRF solutions through World Bank Operations and securing Board approval. Given the complexity of implementation, this specialized expertise must be available throughout the project lifecycle.
Recommendation: Leverage other funding sources as much as possible to ensure that DPP expertise is applied to solutions that have a tangible impact on shock proofing governance finances and households.

Progress against recommendations in last year’s annual review

	Recommendation	Progress
1	Agree and develop a roadmap to the Centre’s future organisational state (CDP) The Centre’s Board and FCDO agree that the Centre has reached a level of maturity and international influence where it is the right moment to identify the most appropriate future organisational structure where the Centre can deliver maximum impact. The Centre should continue to work with the FCDO and Board to develop a clear and agreed roadmap to achieve this transition.	Ongoing – continuing efforts that have built in momentum and pace this year. Good progress made to diversify funding and exploring different operating models by engaging with philanthropies and not-for-profit hosting entities.
2	Develop a clear and defined offer on its country-level work (CDP) The Centre has provided exceptional technical support to various country Governments over its lifetime. As part of its 5-year workplan, the Centre should refine and define its offer to countries. This will require a clear articulation of the best organisational model for the Centre to deliver, associated resource requirements and targeted impact.	Achieved – the Centre’s Board agreed its new 5-year workplan in June. This positions ambitious, country-level and demand-led work at the core of the Centre’s strategy. This is designed with sustainable growth in mind as the Centre moves into its future state.
3	Consider how the Centre’s support to the Global Shield impacts its broader work (CDP) The Global Shield has the potential to be a critical part of the DRF architecture and through its role as GS Technical Advisory Group (TAG) coordinator, the Centre has the opportunity to directly influence the effectiveness of the Shield initiative. The Centre should however continue to balance this work and ensure it does not adversely impact its impact across its other work pillars.	Partially achieved – In September 2025, the Centre will have completed its contractual obligation as TAG coordinator. The demands of this role stretched the Centre internally and created trade-offs with other work pillars. It created challenges for the Centre because of the unpredictable nature of the TAG role making it difficult to forecast resourcing and plan across functions. / The Centre will continue to work with the Global Shield in ways that strategically contributes to its 5-year workplan to upscale demand-led country work.
4	Continue efforts to diversify funding (CDP). The Centre have agreed a funding diversification strategy and guidelines with their Board and are actively pursuing funding opportunities. The Centre should continue to pursue a variety of funding where appropriate, including considering opportunities for core funding alongside earmarked funding.	Partially achieved - The Centre continues to actively pursue funding opportunities and has targeted philanthropies strategically, thinking about core funding alongside earmarked funding.
5	Ensure resourcing constraints do not undermine the Centre’s ability to deliver against both its workplan and emerging opportunities (CDP). The Centre’s growing influence and reputation on DRF has led to increasing demands and calls on Centre staff time and focus. The Centre is a lean organisation, and these demands can be both stretching and could potentially have an impact on the quality of the Centre’s support. It is important that the Centre is staffed to respond to growing demand for its services, including at senior levels.	Partially achieved – the Centre has shifted its senior staffing recruitment approach in response to the current external funding environment, so recruiting for one less senior leadership team member than initially planned / Through the Sahel programming the Centre has learnt lessons about the limits of drawing on internal expertise to meet demand sustainably – in future, risks will be flagged earlier about potential pressure on wider CDP work / The Global Shield TAG coordinator role impacted resourcing for the Centre and created trade-offs in its other work pillars, demonstrating a lesson about forecasting potential resourcing constraints and mitigating when the workload is difficult to predict, as it was with the coordinator role.
6	Update programme logframe to reflect new programme end date (all) The programme has been extended to 2029 through a business case addendum. The logframe will need to be updated to reflect this change. This should align with the Centre’s five-year workplan and with the Umbrella Trust Fund’s workplan.	Partially achieved - CDP output targets were finalised in September-October 2024 and will be updated again shortly to align with the five-year workplan which was only approved in June 2025. / DPP outputs and indicators were finalised in June 2025, later than planned as the overall MEL plan for the RF UTF wasn’t finalised until then. The DPP outputs and indicators align with the Umbrella Trust Fund’s workplan.
7	Demonstrate the benefits of the DPP being part of the Risk Finance Umbrella Trust Fund (UTF). The FCDO should consider how best to capitalise on the benefits of UTF membership, focusing on stronger coordination with our UTF partners (Switzerland and US)	Partially achieved – a workshop with DPP in December 2024 offered clarity on the differences between the Umbrella Trust Fund and the Global Shield Financing Facility. The FCDO have sought to use the Partnership Council Meetings to influence the direction and approach to the UTF. / While the US withdrew from the UTF, Japan has joined. The UTF programmes benefit from mutual support through being together in the trust fund, though are quite different in their objectives.
8	Clarify the role and future ambition of the DPP (DPP). FCDO and World Bank should agree a strategy, underpinned by a refreshed logframe and indicators, for the DPP over the remainder of the programme. This should include a focus on the DPP’s comparative advantage, how the DPP interacts with other World Bank programmes and the Bank’s wider role in the DRF agenda, and the benefits/costs of the DPP’s London location.	Ongoing - The DPP’s logframe and indicators have been refreshed this year. Future ambition for scaling existing, well-established programmes has been agreed between the FCDO and World Bank. The Centre and DPP have been considering opportunities to work together and the mutual benefits of being in London.

Recommendations for the year ahead

	Recommendation	Target date
1	Future state for the Centre: CDP to continue to build the momentum for the future state work, by aligning their five-year strategy and ambition with what they want from a host organisation and their organisational growth. This process will be conducted collaboratively where possible with leadership from the Board, co-leads and FCDO. The transition will occur during the next strategy cycle, and 2026 will be a critical year.	Ongoing
2	Growing work in country: Under the Advisory and Training workstream, the Centre should prioritise generating demand-driven work in low, lower and lower-middle income countries where the potential for impact is highest. Recognising that significant DRF work already happens in upper middle-income countries, the Centre should pursue opportunities in low, income countries where political economy analysis demonstrates that high impact will be possible and continue to support lower middle-income countries. This should include work with FCDO Posts to assess potential for impact.	June 2026
3	High Level Panel report: The Centre to more actively promote the report and make opportunities to push for ambitious progress on the recommendations across the DRF space. FCDO to find opportunities for the DPP to contribute to the recommendations too. / To maintain a tracker through the Sevilla Platform for Action, with one-year workplan commencing September 2025.	Ongoing
4	Resourcing: Ensure that the Centre is staffed to respond to growing demand for its services, including at senior levels. The CDP should report on this at the People Committee and flag any risks to strategy delivery that are related to resourcing constraints.	Ongoing
5	Strengthening evidence: The Centre should produce a high quality, well-presented evidence pack setting out their role, ambition, achievements and impact to date.	February 2026
6	Gender disaggregation of data: The Centre did not receive enough data on gender to be able to disaggregate their training statistics this year. When running joint training with other organisations the Centre should emphasise gender data collection as priority, encourage data disclosure from participants, and share best practice with other organisations running training in the development space.	June 2026
7	Owing to excellent performance on indicator 4.2, increase the target for the number of people receiving DRF training by the DPP. For this annual review the target was 100 and the DPP trained 648 people. For the next review period, the DPP should make the target more ambitious, though in line with the funding they are receiving – (suggested target of 300).	October 2025
8	Continue to consider linkages between different programmes under the Risk Finance Umbrella Trust Fund (DPP). The RTF mid-term evaluation due to conclude in mid-2026 should be used to consider this and any key findings should be highlighted by the DPP.	Ongoing
9	Leveraging wider World Bank funding (DPP): Create opportunities through the UTF to leverage wider World Bank funding in the countries the DPP is working in, leading to catalytic effects. Identifying opportunities by FCDO speaking to other donor countries about their priorities, and DPP to assess wider Bank priorities for potential links.	Ongoing

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme theories of change (TOCs) operate at the component level, which reflects the different approaches the DPP and the Centre take.
The Centre’s original theory of change was developed in 2019 and informed by a linked five-year strategy and was significantly revised in 2022.
The TOC was revised and approved again by the Board in June 2025, to reflect the growing ambition of the Centre and increased focus on demand-led advisory services. It is aligned with the Centre’s 2025-2030 strategy and the accompanying five-year workplan. The Centre’s revised TOC focuses on tailored, demand-led country-level advisory and capacity-building support, whilst growing its systems-level thought leadership and global influence. Next year’s annual review will be against the new theory of change.
The DPP theory of change combines some of the elements set out above (high quality DRF expertise aimed at key stakeholders and increased quality and demand for DRF instruments) as well as leveraging World Bank lending operations, support for regulatory reform, strengthened enabling environment for markets, and more efficient and inclusive disbursement mechanisms for channelling disaster finance directly to government agencies, businesses and households. The DPP’s work has also been captured in and aligns with the Risk Finance Umbrella Trust Fund Theory of Change.

Intermediate Outcome Indicator 1	Milestone(s) for this review	Progress
1.1 Percentage of clients (countries/ organisations) that provide positive feedback on the Centre’s advisory and QA services (disaggregated by client/user type)	75%	100%
1.2 Percentage of people trained reporting intended use of the new knowledge and skills (disaggregated by gender, client)	90%	Total average: 90%
1.3 Percentage of people trained reporting satisfaction with training, (disaggregated by gender, client)	80%	Total average: 92%

Intermediate outcome 1 relates to the Centre’s Advisory and Training (A&T) pillar. It assesses how the Centre’s clients report against the quality of the A&T offer and whether the skills and knowledge being transferred are being used. There was excellent performance against this indicator in the past year with 100% providing positive feedback on the Centre’s advisory and QA services, and 92% reporting satisfaction with training. The percentage reporting intended use of new knowledge and skills was 90% against a 90% target, meaning a ‘good’ rating. Most of the respondents were from the humanitarian sector (WFP, UN OCHA) and the Pacific Catastrophe Risk Insurance Company (PCRIC) risk pool. The PCRIC pool reported increased visibility and credibility from member states as a result. This offers good evidence that the Centre’s A&T offer is strengthening country and partner organisations’ DRF capacity.

Intermediate Outcome Indicator 2	Milestone(s) for this review	Progress
2.1 Number of advisory-linked evidence requests addressed resulting in new evidence, guidance and tools	10	8
2.2 Number of instances of research and evidence uptake	10	26

Intermediate outcome 2 relates to the Centre’s evidence pillar. Throughout the reporting year, the Centre successfully addressed eight evidence requests linked to advisory that led to the development of new evidence, guidance and tools (mentioned below) that have informed and shaped the DRF landscape. This includes a presentation on ‘The Art and Science of Trigger Design’ for the Climate Resilience Debt Clause (CRDCs) technical working group, and targeted sessions for government officials as part of a joint workshop with the REAP programme. This was slightly below this year’s target of 10. However, the Centre’s research and evidence has gained strong global traction and widely cited in publications across the DRF and wider development finance landscape. This includes the V20/CVF citing the Centre’s analysis on CRDCs, a London School of Economics paper ‘Implementation Update: Launch of US$9.25M Climate Risk Insurance to Protect Vulnerable Communities from the Impacts of Drought in Syria - Insurance Development Forum’, that cited two Centre publications.

Intermediate Outcome Indicator 3	Milestone(s) for this review	Progress
3.1 Number of media and digital instances amplifying the Centre’s policy thought leadership, evidence and expert content on priority issues	25	46
3.2 Number of targeted priority partners and champions across sectors and stakeholder organisations who echo the Centre’s policy and technical recommendations	10	20

Intermediate outcome 3 relates to the Centre’s engagement pillar. Indicator 3.1 captures the Centre’s role in shaping the DRF discourse. There were 20 instances of prominent stakeholders taking up the Centre’s figures, including the WFP’s DRF annual report that signalled its support for the High-Level Panel and backed the goal of scaling up pre-arranged finance to 20% by 2035.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This was the first year of the programme’s five-year extension to 2029. Reporting on the new five-year strategy will start from the next annual review, but so far early progress shows it is on track to contribute to the expected outcomes and impact by 2029.

Centre for Disaster Protection

There has been strong performance by the Centre against its expected outcomes over the reporting period.

Outcome	Milestone(s) for this review	Progress
1.1 Number of evidence-based Centre policy recommendations incorporated into priority government/multilateral stakeholders’ policy	8	9

The Centre's influence in shaping policy through evidence-based recommendations continues to be noteworthy. These have been actively integrated into the strategies and policies of key stakeholders, including the 4th Financial for Development Conference, the G20 Disaster Risk Reduction Working Group, and the Global Shield.

Outcome	Milestone(s) for this review	Progress
1.2 Number of new, developing country-facing DRF instruments/approaches/innovations under development supported by Centre including the priorities of the agreed Big Wins	6	7

The Centre made significant progress in supporting the development of new, developing country-facing DRF instruments and approaches. These were:

1. In Chad- a disaster risk finance diagnostic and detailed flood impact analysis informing a pilot shock-responsive programme, collaborating with the World Bank and other partners
2. A peer review of the Mahila Housing Trust’s extreme heat parametric insurance product, focusing on reducing basis risk and improving payout timeliness with clear recommendations to inform the product’s renewal early this year, and focuses on protecting female workers from the economic impacts of extreme heat events
3. A WFP CAT Bond for Mozambique, Somalia and Mali, (iv) in its role as Coordinator of the Global Shield TAG, leading the technical review of Requests for Proposals from four Global Shield pathfinder countries and regions (Costa Rica, Senegal, Pakistan and Fiji)
DPP

The DPP performed strongly against their expected outcomes over the reporting period.

Outcome	Milestone(s) for this review	Progress
2.1 Number of new or improved budgetary mechanisms for managing climate shocks, disasters, and crises in place / (Previously: Number of instruments/funding mechanisms adopted under risk financing strategies to provide finance following a disaster, climate shock or crisis).	2	3 (Mozambique (2), Philippines)
2.2 People covered/protected by the market-based risk finance and insurance solutions (disaggregated by gender)	1 million	2.17m - (900k Horn of Africa (58% female), 700k Malawi (50% female), 570k Kyrgyz Republic (51% female)
2.3 Number of people who have received payouts from pre-arranged risk financing instruments/funding mechanisms	100k	1,188,000 - (Horn of Africa 80,000 (58% female) Malawi 290k (50% female), Mozambique 818k (50% female)
2.4 Number of countries with new or improved budgetary mechanisms for managing climate shocks, disasters, and crises in place	2	3 (Mozambique, x 2; and the Philippines)
2.5 Number of countries with new or improved market-based financial mechanisms for managing climate shocks, disasters, and crises in place	2	6 (Somalia, Kenya, Ethiopia, Kyrgyz Republic, Mozambique, the Philippines)
2.6 Number of new or existing institutions with capacity strengthened that support financial markets for risk finance	1	4 (Malawi, Nepal, Pakistan, Kyrgyz Republic)

Outcomes 2.3-2.6 were new for this year. Outcomes 2.5 and 2.6 performed particularly strongly against their targets. Outcome 2.5 saw the DPP support the iterative improvement of micro-insurance to work for pastoralists through the DRIVE programme in Somalia, Kenya, and Ethiopia. This work demonstrates how the insurance product trigger level creates positive incentives for savings and other products. This outcome also provided demand-led advisory work and technical support to the governments of the Philippines, Mozambique, and Kyrgyz Republic.

Outcome 2.6 included work to strengthen the capacity of the Reserve Bank of Malawi, the state bank of Pakistan, and the capacity of the Nepal Insurance Authority. In Kyrgyz Republic, an event on affordable DRF through public private partnerships knowledge strengthened government capacity to design and scale effective insurance programmes.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Based on strong programme performance and the increasing relevance of the DRF agenda to Ministerial priorities, the programme is in demand from country governments and FCDO Posts. The programme has consistently proved its value for money, achieving significant impact in protecting large numbers of vulnerable people through innovative solutions. The programme should therefore continue.

How the programme supports the wider FCDO portfolio and HMG targets
The Centre and DPP directly supports and enables delivery towards two of the Foreign Secretary’s priorities - climate and humanitarian, as well as the focus on growth. The Minister for Development’s speech at the 4th Financing for Development Conference in Sevilla and The Foreign Secretary’s Kew Speech on the climate crisis also highlight the importance of developing new and effective financing models for responding to disasters.
The programme is also directly helping to deliver against the international targets, including:

- The High-Level Panel recommendations on scaling pre-arranged finance. The Centre will be proactively progressing work linked to the two commitments to disaster risk financing and pre-arranged finance which are in the final negotiated text from the 4th Financing for Development conference. This was finalised in early July 2025. This was a once in a decade event that took place in Sevilla, Spain.
- Starting from the next Annual Review period, the Centre agreed to take up a critical role in the Sevilla Platform for Action on Pre-Arranged Finance. They will be working with FCDO as part of this UK and Bridgetown Initiative co-launched coalition to scale up pre-arranged finance for disasters.
- The REAP (Risk-Informed Early Action Partnership) goal of making one billion people safer from disasters by 2025.
- SDG Target 13.1: Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries.
- SDG target 1.5: By 2030, build the resilience of the poor and those in vulnerable situations and reduce their exposure and vulnerability to climate-related extreme events and other economic, social and environmental shocks and disasters.

Output Title	Centre for Disaster Protection / Quality risk finance product development and capacity development in partner countries
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

## C. DETAILED OUTPUT SCORING

Indicator(s)	Milestone(s) for this review	Progress
Number of organisations using the Centre’s advisory and QA services (disaggregated by client type)	12	12
Number of people trained in DRF, disaggregated by / - Gender, / - Location, / - Economic status of country (LIC, LMIC, MIC, HIC)	150	186 / Please see narrative below about disaggregation.
Global Shield institutional arrangements and products developed (or improved) as a result of the Centre’s support	4	4

Briefly describe the output’s activities and provide supporting narrative for the score.

During the reporting period, the Centre delivered high-quality services focused on client engagements with humanitarian agencies and multilateral/regional development banks (MDBs/RDBs), consolidating the Centre’s reputation as a trusted technical partner in DRF. The humanitarian clients using the Centre’s advisory support include the World Food Programme (WFP), International Federation of Red Cross and Red Crescent Societies (IFRC), International Rescue Committee (IRC) and United Nations Office for the Coordination of Humanitarian Affairs (UN OCHA). Among the development partners actively using Centre’s advisory support are the World Bank (through the Social Protection teams in West Africa), KfW (German Development Bank) and the Global Shield. Finally, the Centre has had active advisory projects in regional and national settings, either though risk pools (Pacific Catastrophe Risk Insurance Company (PCRIC)) or with the national governments in Kenya, Gambia and Chad.

Output indicator 1.2 is the number of people trained in DRF, disaggregated by gender, location and economic status of the country. Performance has exceeded the milestone (150), with 186 trained, but gender disaggregation was limited, due to challenges in data collection when running workshops jointly with other organisations. CDP has agreed to mitigate these issues by emphasising upfront (when planning joint training) why gender inclusion and data disaggregation are a priority, and what is needed. CDP will actively encourage data disclosure from participants and reassure about confidentiality.

Output indicator 1.3 met the target with 4 Global Shield institutional arrangements and products developed or improved because of the Centre’s support – Pakistan, Costa Rica, Senegal and Fiji. The Centre will publish the outcomes on its website to promote transparency and knowledge sharing in the DRF community.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the output this year, but CDP logframe outputs will be updated again shortly to align with the five-year workplan which was approved in June 2025. The weighting was revised up by 5% to reflect the budget as a proportion of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See section A above.

Output Title	Centre for Disaster Protection / Stakeholders use DRF evidence generated, consolidated and shared through the Centre
Output number:		2	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – revised up by 5%

Indicator(s)	Milestone(s) for this review	Progress
Number of knowledge products delivered/produced	12	12
Number of evidence-related learning events held	12	18
Number of publication downloads / page impressions of Centre evidence pieces/publications	20,000	38,698

Briefly describe the output’s activities and provide supporting narrative for the score.

The Centre produced a total of 12 high-quality, impactful knowledge products that have significantly advanced the global dialogue on DRF. Among these were three flagship reports, which played a key role in shaping policy, informing stakeholders, and elevating public discourse on DRF and pre-arranged financing. These flagship publications also helped raise the Centre’s profile in prominent policy discussions, including at the 4th International Conference on Financing for Development, with Centre staff participating in side events, as well as the G20DRR working group.

The CDP successfully designed and launched a new multi-year programme of work, ‘Understanding country preferences’, focused on understanding the preferences and perspectives of government officials with respect to pre-arranged financing and addressing demand-side challenges. This workstream will help the Centre as well as the main providers of DRF to understand the views of government officials regarding the relevance and performance of PAF instruments and architecture more broadly, what they value about the current system, and what are the main weaknesses/issues that impede demand for PAF.

The remaining nine knowledge outputs – comprising insight papers, policy briefs, guidance notes and country case studies – addressed critical themes such as premium support, adaptive social protection, value for money and innovative DRF instruments. Collectively, these products not only advanced global thinking on DRF but also informed policy and operational decisions across a wide range of stakeholders, including donors, multilateral development banks, national governments and DRF practitioners.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output weighting was revised up by 5% this year. CDP logframe outputs will be updated again shortly to align with the five-year workplan which was approved in June 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See section A above.

Output Title	Centre for Disaster Protection / Disaster risk evidence, advocacy and influence/ Target stakeholders view the Centre as a credible, authoritative actor and associate the Centre with its values
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of high-level engagements between CDP team and key target stakeholders	12	34
Number of new thought leadership or media pieces produced by the Centre	40	29

Briefly describe the output’s activities and provide supporting narrative for the score.

Over the course of the reporting year, the Centre delivered 34 high-level engagements – nearly three times the target – demonstrating continuing influence and the ability to take the DRF and crisis management agenda forward at decision-making levels. The increase in engagements was driven by several high-profile events. Most notably, these included the (once-a-decade) International Conference on Financing for Development, and the Centre’s publication and launch of Crisis Protection 2.0: Future- Proofing Our World: A Roadmap to Close the Crisis Protection Gap Through Pre-Arranged Finance (the report of the High-Level Panel on Closing the Crisis Protection Gap (HLP)), State of Pre-Arranged Financing for Disasters 2024, and Demystifying Pre-Arranged Financing for Governments: Stocktake of Financial Instruments from IFIs, with a number of follow-up activities and outreach to profile the reports’ recommendations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the output this year, but CDP logframe outputs will be updated again shortly to align with the five-year workplan which was approved in June 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See section A above.

Output Title	Disaster Protection Programme / Technical assistance for knowledge products delivered in-country and disseminated
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of DRF trainings and workshops delivered by the DPP	5	18
4.2 Number of people receiving DRF training by the DPP	100	648
4.3 Number of corporate World Bank analytics and tools benefitted with DPP inputs	3	3
4.4 Number of global DRF dialogues (E.g., G7, IDF, APEC) influenced by the DPP’s inputs	2	5
4.5 Number of World Bank projects (both lending and ASA) informed	2	2

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 made strong progress against its targets this year. Indicator 4.1 delivered training in Ethiopia, Pakistan, Malawi, The Philippines, Kenya and Nepal, including funding two delegates from Kenya to attend the Insurance Development Forum Summit in Venice in June 2025 alongside the DRF and Insurance Learning Week.

Indicator 4.2 performed exceptionally well against target, with the same countries as Indicator 4.1. This included a joint workshop with the Government of Zambia on developing a DRF strategy, and the Reserve Bank of Malawi on Climate Risks for Banks and insurers. Workshops on Physical Risk assessments for the financial sector in the Philippines and Malaysia reached over 200 people.

Indicator 4.3 included three highly specialised outputs, one being a regional analytical piece for Malawi and other countries providing an economic analysis for REPAIR. This is now being used as a blueprint for other country and project assessments. The DPP used connections with the Insurance Development Forum in London to conduct interviews with key stakeholders in the global reinsurance market to inform a specialised insurance chapter within the annual World Bank Finance and Prosperity report, to be published in Autumn 2025.

Indicator 4.4 led to outputs including engagements with the Insurance Development Forum, and with wider World Bank staff. DPP training for World Bank staff helped them to understand DRF approaches, so they are better equipped to identify opportunities to incorporate DRF in the Bank’s wider operations. Indicator 4.4 also included collaboration with the Italian Ministry of Economy and Finance, the Network for Greening the Financial Sector, and the World Bank Academy Impact Program.

Indicator 4.5 supported 2 new projects, alongside four existing ones. The DPP led the design of a Crisis Response Facility in Pakistan, which is a $125m USD operation approved by the World Bank Board. This facility is also leveraging an additional $25m USD of Global Shield Financing Facility (GSFF) funding. It will support the microfinance sector and is anticipated to benefit over 1 million people in the next five years. The second project was the Eastern and Southern Africa REPAIR Phase 2, with Angola, Burundi, Malawi, Seychelles and Zambia joining the $926m USD regional programme. This aims to provide these countries with scaled up pre-arranged finance to respond to disasters. Malawi is leveraging USD $70m World Bank IDA under this programme and around USD $9m will be used for insurance premiums.

There are no underperformance issues to highlight this year though the good performance lends itself to testing that future targets are not set too low.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no major changes made in the past year. We have agreed changes to the output indicators for 2025/2026 to scale up ambition because of strong performance this year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See section A above.

Output Title	Disaster Protection Programme / Technical inputs to deliver high-quality risk analytics and forecasting tools & technologies, and support CDRFI strategies and policies and innovative financial solutions
Output number:		5	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of new (or improved) DRF analytic products and technologies delivered by the DPP	5	14
5.2 Number of prototypes of risk finance instruments/funding mechanisms supported by the DPP	2	3
5.3 Number of laws, regulations, amendments, policies and strategies supported by the DPP for strengthened financial market development for risk finance	1	1

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 5 performed strongly against target. Indicator 5.1 included the development of three analytical reports in Malawi including a roadmap for assessing and managing climate risks for banks and insurers, and a technical assessment of the Government of Malawi’s Disaster Risk Finance strategy including an actuarial assessment for Malawi to join REPAIR in Phase 2.

In Nepal, the DPP supported the development of the Nepal Flood Risk model completed in October 2024 and used model output to revise tariff rates as part of the Nepal Insurance Authority’s risk-based pricing strategy. DPP also contributed to the completion of the Valuation Guidelines for Public Assets for Nepal, a framework for the collection of information about physical assets and methodology for determining their value for insurance purposes. They also supported work in the Philippines, Kyrgyz Republic and are continuing work on DRIVE.

On indicator 5.2, this is in addition to products in addition to those captured under 5.1. This year, the three prototypes included work in Mozambique to improve the Tropical Cyclone models available to the government, as part of REPAIR. It also includes flood risk modelling in Nepal to inform the design of sovereign risk transfer mechanisms, and flood risk modelling and analytics options for use in parametric flood triggers for the CRF in Pakistan.

For indicator 5.3, the DPP assisted the government of Somalia in adopting the Somalia National Takaful Law and the Somalia Takaful Market Conduct Regulations to enable conditions for the private sector to scale up business in Somalia. Three regulations have been adopted, effective June 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Changes were made in May 2025 to ensure the output language is in line with that used in the Risk Financing UTF MEL Plan. This more closely reflects the DPP’s technical inputs (analytical products, finance instruments and tools). The changes have been recorded, including date of and rationale for change, in the ‘change frame’ tab on the logframe template.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

See section A above.
D: VALUE FOR MONEY
Key cost drivers and performance

Centre

For the Centre for Disaster Protection the key cost drivers are staff and consultancy costs – including daily rates for the core team and advisers (long-term and short-term). 67% of Centre expenditure in 24/25 was staff costs. Please refer to the 5 Es section below for more detail on value for money.

The Centre have made efforts to manage the impact of inflationary pressures. For the costs of the daily rates of technical expertise, the Centre negotiates rates within Global Economic Development Framework (GEDF) bands and additional reviews are conducted before extension or repeat engagement. The Centre works closely with the Finance and Risk Committee on all high importance procurements, including those below threshold, to ensure transparency and oversight. For example, in the past year the Centre adhered fully to fee rate caps, with 69 % of the total number of assignments applying rates lower than the cap. They closely monitor inflation rates and economic trends to accurately forecast potential increases in daily rates.

DPP
The main cost drivers are consulting services and staff. All consultants (firms and individual experts) are hired in line with World Bank procurement rules which ensure that service providers with the best overall financial and technical offering are chosen. There has thus far been minimal disruption to DPP activities with the move from being a single donor trust fund to sitting under an umbrella trust fund.

For contractual services, this is affected by inflation as well as the location of the firm whose service are contracted. For contractual services, the DPP only outsources work which cannot be done (cost) efficiently in-house.

To maximise VfM in the project, the DPP follows competitive procurement for contracts in line with WB guidelines; covering DPP work as well as other project work in one mission, to allow co-financing of missions and hence minimisation of travel costs (where possible); and leveraging partnerships where possible.

The World Bank’s crisis and disaster risk finance team has developed a VFM framework that will strengthen ex-ante analysis of the benefits of DRF solutions from a financial perspective. The DPP has contributed to this and will ensure it is integrated into future DPP activities.

VfM performance compared to the original VfM proposition in the business case

As set out in the original Centre for Disaster Protection Business Case: ‘Value for money will be continually monitored through evaluating delivery in the following areas based on the theory of change’. These areas are technical assistance; innovation, analytics and learning (all outputs), and financial (admin and programme costs etc.) and value-add (leveraged funding, co-investment, partnerships and in-kind contributions) (both inputs). These are captured below using the 5 Es of FCDO’s value for money framework: economy, efficiency, equity, effectiveness, with the 5th being the thread that ties them together - ultimate cost-effectiveness in achieving our foreign policy objectives:

Economy (Buying inputs of the required quality at the lowest cost)

No major VfM problems or unexpected concerns have emerged. FCDO continues to monitor the impact of inflation on programme activities.

As above, staff costs (core staff and consultants) remain the major programme cost driver. For the World Bank, salaries are approved by the World Bank Board. For the Centre, these continue to be set by competitive salary benchmarking against market rates. The Centre’s recruitment process and reputation ensures that high quality staff are secured at lower-cost rates compared to many opportunities available to candidates in finance and related sectors, fitting within the Centre’s permitted fee structure under the Managing Agent contract. Investing in long-term employees has been a strategic focus to enhance the Centre's effectiveness and efficiency.

This approach is driven by the complex and multidisciplinary nature of the Centre’s work, requiring consistent DRF expertise and deep institutional knowledge. To ensure they remain competitive, they have focused on partnerships and thought leadership and consequently attracted experienced staff and consultants who are well-respected in the disaster risk finance field.

Within programme operations and implementation, the Centre has proactively maximised VfM through targeted use of specialist expertise, expansion of internal capacity, and regular financial scrutiny by senior management, proactively reprogramming underutilised funds.

Efficiency (Producing outputs of the required quality at the lowest cost)

The Centre undertook several changes this year to enhance internal efficiency and improve how their organisational functions support delivery. For example, by rolling out an improved project management process and system and supporting staff to confidently use it, they are ensuring that their internal systems can more efficiently enable them to reach desired project outcomes. This was a lesson from the Global Shield and Sahel projects.

The Centre’s Board governance was strengthened by establishing a dedicated Governance Committee. This committee undertook its first discussion on Board composition, skillsets and decision-making processes, supporting stronger oversight. In parallel, financial planning processes were refined. Forecasting improved significantly with actual expenditure kept within a 10% variance over the year, reflecting enhanced monitoring and budget discipline.

Equity (Ensuring outputs/outcomes are targeted at the poorest and most marginalised)

The Centre’s approach to VfM is closely aligned with its commitment to equity. Targeted interventions, including capacity building aim to ensure that all segments of society, particularly the most vulnerable, benefit equitably from the Centre’s work. As a critical partner of the G20 Disaster Risk Reduction Working Group, they have been aligning their work with South Africa’s G20 presidential priority on equity.

The Centre continues to incorporate mainstream gender, equity and social inclusion (GESI) principles through all its activities. The Centre’s project ‘proposal and approval’ template incorporates a GESI rating to ensure that gender and other socioeconomic factors are considered across project design, implementation, financing and MEL systems.

Effectiveness (How well Outputs produce Outcomes)

Effectiveness remains a cornerstone of the Centre’s VfM framework, underpinning efforts to achieve intended outcomes in an efficient and sustainable manner. This year, the Centre reviewed their strategy and theory of change. This led to a refreshed strategic framework and accompanying organisational development plan which aims to maximise impact and effectiveness.

Delivery effectiveness continued to be underpinned by cross-organisational collaboration. Major initiatives such as the Global Shield programme and Sahel workstream required contributions from all functions, including advisory, evidence, engagement and operations. These integrated delivery efforts were also a feature of the Centre’s support to the High-Level Panel, reinforcing the Centre’s capacity to rapidly respond to requests.

Quality assurance was further strengthened through routine use of peer review mechanisms across multiple activities. This included internal reviews of analysis, outputs and engagement materials, including after-action reviews for the High-Level Panel, STAAR, and Sahel projects, providing an opportunity for learning and continuous improvement. Overall, the Centre maintained a strong delivery record while investing in a more robust and future-oriented strategic foundation.

The DPP looks to strengthen its effectiveness by ensuring it is using the latest practices and emerging innovations in disaster risk finance. For example, services procured under the DPP are at the forefront of latest research, including catastrophe modelling and product structuring. And as far as possible, the DPP look to ensure their clients adopt the standards that international insurance markets are currently using.

Assessment of whether the programme continues to represent value for money

The programme continues to represent good value for money. FCDO and programme partners regularly discuss value for money, explaining FCDO’s approach to VFM and discussing areas where VFM savings can be achieved in the programme. Partners have acknowledged the need to secure VFM and have provided feedback on how they are driving VFM as part of this annual review.

E: RISK

Overview of risk management

The overall risk rating of the programme remains moderate and within Public Finance and Tax Department’s wider risk appetite. The programme team adopts a zero tolerance to fraud and safeguarding and specifically require implementing partners and their delivery partners to do likewise. The programme risk register is reviewed and updated quarterly.

The possible risks that would have most major impact are that the Centre’s activities do not lead to higher use of risk finance tools, and that those in place do not lead to benefits for the most vulnerable people. The programme team monitor and mitigate these risks by ensuring that the Centre only engages where there is clear demand, taking a portfolio approach in countries with a high chance of success. They ensure they work alongside the World Bank and GSFF and engaging through FCDO for political access and supporting Post’s priorities.

The Centre’s risk register focuses on delivery risks to the Managing Agent’s contractual obligations and to the Centre itself. The risk register is submitted to the Finance and Risk Committee on a quarterly basis for quality assurance together with a summary of key risks and mitigation actions. These are also included in the Quarterly Progress Reports. Any changes to the risk register are flagged through this process.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Overall, the delivery partnerships under the CDP programme work well and provide strong technical inputs. Reporting and financial management is also good, and working relationships are open, flexible and responsive. FCDO has an Administrative Agreement with the World Bank for the DPP through the Risk Financing Umbrella Trust Fund as co-donors with Japan and SECO (Switzerland).

Centre for Disaster Protection

FCDO and DAI have KPIs to measure the performance of the Managing Agent and the Board, assess staff and stakeholder engagement and monitor the accuracy and timeliness of financial reporting and progress against the Centre’s workplan. These include three ‘silver’ KPIs for publication by the FCDO. DAI provides quarterly progress reports which include narrative against all outputs and VFM analysis with updated financial forecasting.

World Bank

The reporting requirements on the DPP are set out by the administration agreement between FCDO and the World Bank. They are common for Bank arrangements. They do not give the same level of detail as we receive for the Centre’s Managing Agent contract. FCDO has access to financial reporting through the World Bank’s Development Partner platform.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

This year, as the TAG co-ordinator, the Centre provided Monitoring, Evaluation and Learning (MEL) support to the Global Shield In-Country Process (ICP). This included building and delivering a MEL approach embedded into the Shield’s processes to support robust evidence and learning. The MEL component is expected to conclude by December 2025. Looking ahead, the Centre will explore ways to contribute to the Global Shield’s ambitions by leveraging its advisory, training, evidence and policy capabilities in line with the workplan, focusing on where it can deliver the greatest value to countries.

The Centre’s MEL framework collects and analyses data disaggregated by gender and economic status to understand how interventions including capacity-building efforts for DRF practitioners, affect specific populations and low-income/fragile countries, e.g. the Sahel and Pacific regions.

The DPP adopts an outcome-based approach to implementation and delivery. The program implementation teams conduct regular field missions to i) design programs in the preparatory phase; ii) and to supervise and monitor program activities under implementation. In addition, all program activities are discussed with clients and other stakeholders in regular Video Conferences between missions. Thus, interaction with clients and monitoring of progress is continuous and program decisions are taken based on the continuous feedback obtained; and implementation activities can be adjusted on a real-time basis. DPP evaluation will be strengthened as part of the RFU MEL framework. A mid-term evaluation of the RF UTF is about to begin and will conclude in mid-2026.

This annual review was completed as a desk exercise by the FCDO SRO and Senior Programme Manager, with timely cooperation from programme partners.

Evidence

Disaster Risk Finance remains a relatively new and niche area. The Centre’s evidence pillar is contributing directly to building the broader evidence base for DRF. The launch of the inaugural ‘State of Pre-Arranged Financing for Disasters’ report was a key milestone in 2023. This comprehensive report is a groundbreaking effort to analyse the best available data on pre-arranged financing for disasters. Building on this over the last year, the High-Level Panel Report on Closing the Crisis Protection Gap was published in January.

The Centre played a critical convening role when the UK and Bridgetown Initiative jointly launched a Global Coalition to Scale up Pre-Arranged Financing under the Sevilla Platform for Action. This new initiative emerges directly from the High-Level Panel process and looks to build out from its recommendations, including explicitly increasing the volume and scale of pre-arranged financing tenfold – a process that the Centre will play a critical role in.

For DPP, there are no major changes in evidence that affect the programme. The DPP continues to contribute to deepening the DRF evidence base. However, reductions in funding for development have also impacted the DRF agenda, including DPP supported program and including evidence generation. For example, the DRIVE project procured specialist service providers to conduct a rigorous impact evaluation which is now at risk of not being finished.

Learning

During the year, the Centre continued its commitment to producing high-quality knowledge products that contribute to advancing DRF globally by delivering a total of 12 impactful knowledge products, including three flagship reports, insight papers, guidance notes and country case studies. These flagship publications helped raise the Centre’s profile in prominent policy discussions including at the 4th International Conference on Financing for Development with Centre staff participating in side events, and the G20DRR working group.

The DPP supports workshops in all client countries where counterparts are trained, including on lessons learned in other countries. Where possible the DPP brings clients together to exchange experience and lessons. Three examples from this year are:

1. The DPP facilitated a knowledge exchange between the Ministry of Finance of Malawi and Zambia in December 2024 to share experience of DRF, as they both looked to update their DRF strategies. These exchanges were supported by DPP produced evidence, technical analysis and diagnostic assessments.
2. Several DPP countries benefitted from a regional workshop conducted as part of the REPAIR program in South Africa in March 2025.
3. Lessons from DPP supported programmes are shared widely beyond DPP countries. In April 2025, the first WB DRF Academy was held in Istanbul. While the target audience were MENA and ECA countries (where DPP has a minimal footprint), several programs supported by the DPP, including the Pakistan RAM program, featured heavily in the Academy.
Date of last narrative financial report	CDP: July 2025 / World Bank: July 2025	Date of last audited annual statement	CDP: (DAI) September 2024 / World Bank: September 2025