## Annual Review Template

Title: FSDA - Financial Sector Deepening Africa Platform
Programme Value £ (full life): £670m		Review date: 17/10/2025
Programme Code: [AMP ID#] 205238	AMP start date: 17/03/2017	AMP end date: 31/12/2030

Summary of Programme Performance
Year	18/19	19/20	20/21	21/22	22/23	23/24	24/25
Overall Output Score	A+	A+	A	A	A	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/5723842.odt / https://iati.fcdo.gov.uk/iati_documents/53760423.odt / https://iati.fcdo.gov.uk/iati_documents/62211076.odt / https://iati.fcdo.gov.uk/iati_documents/D0003055.odt
DevTracker Link to results framework:

## A. SUMMARY AND OVERVIEW
Description of programme

FSD Africa is a specialist development agency established by FCDO in 2012, working across more than 30 countries “to bring about a long-lasting shift in the way capital is allocated
to benefit people and planet. to make finance work for Africa's future.” The programme uniquely focuses on developing domestic financial markets, recognising these as key enablers of economic and social transformation across the continent. With a team of more than 100 professionals, almost all from Africa, FSD Africa works in partnership with governments, regulators, financial institutions, asset managers, and other development agencies to build a fit-for-purpose financial system that meets Africa's specific development needs through policy and regulatory reform, thought leadership, and capacity support.

Central to this mission is FSDAi (FSD Africa Investments), the programme's development capital fund, that deploys patient capital to early-stage companies and funds that are building Africa's financial infrastructure including intermediaries. At the end of the review period FSDAi had a portfolio of 17 investments, with a robust pipeline of future activity.

The programme aims to mobilise capital, especially domestic private capital, to provide long-term financing for Africa's development needs and create systemic change in the financial markets. FSD Africa addresses the most intractable financial market challenges across sub-Saharan Africa, including the lack of long-term finance in local currency, inadequate risk management capacity, and the need for green financing solutions. Through its comprehensive approach spanning early-stage finance, financial markets development, and adaptation and resilience initiatives, complemented by FSDAi's investment capital, the programme works to tackle systemic challenges such as sovereign debt distress, energy transition financing needs, climate adaptation costs, and jobless growth. The ultimate objective is creating a well-functioning financial system that allocates capital to sustainable outcomes and reduces poverty while establishing a more sustainable future for Africa's people and natural environment.

FSD Africa agreed a new five-year strategy, with input from FCDO, reflecting changed African and global context. This took place in the context of a planned reduction in UK ODA. This has resulted in key changes to this programme, which will be reflected from March 2025 onwards.

Summary supporting narrative for the overall score in this review

FSD Africa has continually performed well in Annual Reviews, this year achieving an “A+” score (i.e. moderately exceeding the expectations for outputs), with risk assessed as Moderate. Milestones for outputs were moderately exceeded, with some exceptions.

Notable highlights from this review period include:
- the Ethiopia Securities Exchange (ESX) launch - Ethiopia opens first stock market since Emperor Haile Selassie. This will establish modern capital markets in Ethiopia for the first time, creating new, deeper and more transparent financing options for both the private sector and Government, while providing an accessible and inclusive investment option for Ethiopians and international investors.
- Approval of a £10m investment into ARM-Harith’s Climate and Transition Infrastructure Fund (ACT Fund) to unlock local institutional capital for climate infrastructure.
- The first investment in Nature-Based Solutions with US$2.5m commitment to West Africa Blue
- Committed capital (deployed to investees) rose from £64m to £82m, with another £47m of deals approved by the Board. Commitments to climate-focused opportunities constitute 49.5% (£40.7m) of committed capital.

Case study: West Africa Blue

Nature-based solutions aim to reduce emissions and address biodiversity decline, through the protection, sustainable management and restoration of ecosystems. FSDAi invested £2m in its first nature-based solution in 2024.

FSDAi is funding and de-risking a new mangrove restoration and conservation project with West Africa Blue, a blue carbon project developer whose innovative approach ensures transparent benefit sharing with local communities. Based in Sierra Leone, this project has an impact target of sequestering 0.7 million metric tonnes CO2 and covers two of the country's four major mangrove estuaries, protecting 92,000 ha, supporting a vital carbon sink and building coastal resilience.

Major lessons and recommendations for the year ahead

FCDO, FSD Africa Board and management should review governance arrangements to ensure they are appropriate for attracting and engaging with long-term funders. Currently, there is no formal mechanism for non-FCDO funders to engage with the FSD Africa and FSDAi strategies. Some partners may wish to have a more active, formally set out role.
FCDO should review roles and responsibilities with African posts and headquarters, particularly for priority countries. Consideration should be given to reporting arrangements, programme management models, and local engagement, with the merits of standardised processes being considered.
FSD Africa should develop a multi-year evaluation plan in light of the new FSD Africa strategy, focusing on learning.
FSD Africa should continue to diversify funding sources, drawing on senior FCDO support as is appropriate.
FCDO should work with FSD Africa and FSDAi to consider the long-term future of FSDAi. FCDO investment and funding is forecast to run until 2030, but now is the time to consider options for shareholders post 2030.
FSD Africa should develop an indirect costs options paper, to ensure that indirect/overhead costs are recovered from all funders to the extend possibly. This will promote sustainability of FSD Africa by ensuring that essential indirect costs are covered even as funders’ budgets rise and fall.

Progress against recommendations in last year’s annual review is summarised in Annex A.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

FSD Africa's Theory of Change
The ToC is set out in FSD Africa’s strategy. The year under review saw the introduction of a refreshed five-year strategy, encompassing the remainder of the programme’s life (2025-30). Its new strategy statement is to: “Design, implement and invest in catalytic interventions in African financial markets to bring about a long-lasting shift in the way capital is allocated to benefit people and planet.”

The revised strategy retains a strong focus on climate action, recognising both that the climate crisis is exacerbating Africa’s challenges, and that climate investment could be a powerful lever for economic transformation. The strategy aims to channel capital into high impact parts of the green economy, with a focus on energy transition, adaptation finance, SME finance, debt management, carbon markets, and gender.

Both existing and revised theories of change highlight the fundamental societal vulnerabilities posed by challenges such as poverty, climate change and biodiversity loss. The programme collaborates with partners and uses a variety of tools and techniques to drive the efficient flow of finance into mechanisms for addressing these vulnerabilities. These include grants and returnable grants, investment capital, technical assistance, knowledge management and data, partnerships, and networks. The ToC tracks these activities through to outputs - innovative financial products and services, transactions, and new intermediaries; outcomes - deeper and more sophisticated domestic capital markets, and increased employment or income generating opportunities; and programme impacts - a more sustainable future for the financial sector, people, and the environment in Africa. The diagrammatic ToC for the existing ToC (which informed the year’s activities) is shown below.

Real and Social Sector: There are fundamental shortfalls in opportunities for people in Africa to lead lives where their basic needs are met, as outlined in the SDGs. Challenges include poverty, inequality, hunger, inadequate healthcare, poor education provision, lack of access to housing, clean water and sanitation, clean and affordable energy, shortage of job opportunities, poor infrastructure, climate change, biodiversity loss and a polluted environment. Global issues have negatively affected African countries, including the reduction in ODA budgets from main important donors. FSD Africa stepped up during this period to mitigate adverse impacts of these outcomes, including provision of technical assistance to governments, central banks, and regulators, while FSDAi continued to invest.

Recommendation: The Board (on which FCDO is represented) should agree a refreshed strategy for FSD Africa, integrating FSDAi’s new strategy, which was approved in 2023.

Progress Update: A new strategy has been developed and was agreed with the Board in March 2025. The strategy seeks to “Design, implement and invest in catalytic interventions in African financial markets to bring about a long-lasting shift in the way capital is allocated to benefit people and planet”. This is an ambitious strategy, and efforts to mobilise finance for its implementation is underway from other funders as well.

Recommendation: FSD Africa should review the transmission mechanism between outputs, outcomes, and impacts. FSD Africa should build an evidence base about how activities give rise to outcomes, and the time needed for outcomes to be achieved. This should feed into the revised Logframe.

Progress Update: As part of its revised strategy, FSD Africa has revised outputs, outcomes, and intended impacts, along assumptions and targets. For the logframe, we will provide annual disaggregated targets, detailing timelines and explaining any anticipated lags. This will help clarify the linkages between outputs, outcomes, and the overall impact.

We have deployed various mechanisms, including process reviews or rapid assessments, outcome evaluations, voices from the field (impact stories), and annual impact reports to build an evidence base for how FSD Africa's activities translate into outcomes. Last year, FY24/25, we developed an impact strategy that assesses how to mobilise capital for impact and how to allocate capital to ensure impact objectives are achieved. This year, FY25/26, we are developing a 5-year evaluation plan that aligns with the organizational strategy (2025 - 2030), identifying the key strategic questions FSD Africa seeks to answer and having these inform the thematic evaluations to be carried out in the next 5 years.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is broadly on track to achieve its outcomes and impacts, despite uneven progress in achievement of outcome milestones. Progress towards outputs has been strong, but evidence about outcomes and impacts is mixed. Regarding outcomes, people are accessing basic services in keeping with expectations, but milestones regarding people’s climate adaptation and finance mobilised/catalysed was less than expected, while resilience to financial shocks remained unmeasured.

The impacts picture is more positive. Greenhouse gas emission reductions, and job creation figures exceeded the milestone. The resilience of people and small businesses was not measured in the year under review, with last year’s measurement suggesting missed performance.

Missed milestones may indicate that the causal links between outputs and outcomes take more time than originally understood, as noted last year. The new strategy is accompanied by a refreshed logframe that revisited the previous casual links.

Impact and Outcomes

Impact 1.1 - Environmental benefits delivered

Indicator(s)	Milestone(s) for this review	Progress
Net change in greenhouse gas emissions (tCO2e) – tonnes of GHG emissions reduced or avoided as a result of FSD Africa initiatives (million metric tCO2e) - ICF indicator.	1.73	2.406

FSD Africa employs a comprehensive methodology for tracking and reporting greenhouse gas (GHG) emissions, focusing on both emission reductions and avoidance. The primary aim is to measure the net change in GHG emissions as achieved by comparing emissions against a business-as-usual trajectory. For instance, interventions such as installing renewable energy sources in place of fossil fuels or investing in electric scooters are carefully monitored for their emission reduction impacts.

The net change in GHG emissions is primarily driven by FSDAi investments, with ALCBF contributing the largest reduction at 1.22 million tCO₂e, followed by Persistent Energy at 0.74 million tonnes, and Nithio at 0.44 million tonnes.

Annex B provides details of the progress in the review period.

FSD Africa Theory of Change

Impact 2.1 - Economic opportunities created

Indicator(s)	Milestone(s) for this review	Progress
Number of jobs created, protected and supported through FSD Africa initiatives.	17,950	22,092

The financial sector plays an important role in creating, protecting and supporting jobs.

FSD Africa employs a comprehensive method to assess and calculate jobs supported by its interventions. This process begins with a theory-based assessment to determine whether a given project is likely to have a significant effect on employment. The jobs numbers are then estimated using primary data from project partners or financial service providers, and any supply chain effects are modelled. When possible a 'decent jobs assessment' is conducted to evaluate the quality of the jobs, considering factors such as gender equality, inclusion of vulnerable groups, earnings, job security, and career development prospects. This framework generates a range of conservative to optimistic estimates, providing an average that can be used for reporting purposes.

The method also includes quantifying the total jobs created and supported by estimating how many jobs are likely to be created and supported by the innovation and determining FSD Africa's contribution share. This involves measuring jobs at different levels, such as new jobs added in real economy firms, jobs supported in the wider supply chain, and jobs supported through increased expenditure. The framework uses multipliers based on the volume of capital deployed and adjusts the total jobs supported by a 'contribution share' to account for FSD Africa's role. The process concludes with a clear understanding of the effect on target beneficiary firms and the wider value chain, as well as the quality of the jobs created and supported.

During this reporting period, an additional 11,659 jobs were created, protected, or supported through FSD Africa’s portfolio. Blue Orchard led with 4,752 jobs supported in the past year, followed by the Nyala Facility with 2,499 jobs. Of the total additional jobs created, 4,142 were filled by women, and 4,472 were classified as green jobs.

Annex C shows the breakdown of the jobs created:

Case Study: BimaLab – gender and insurtechs
BimaLab Africa is gender-focused capacity building initiative that accelerated 25 insurtech startups across 16 African countries while implementing comprehensive gender integration strategies. The programme achieved gender-positive outcomes by ensuring 49% of selected startups were women-led, despite traditionally male domination insurtech sector. The programme's gender-responsive approach included minimum slots for women founders, specialised coaching sessions focused on leadership, and gender-balanced mentorship that provided women founders with experienced role models.
The programme's impact extended beyond startup acceleration to create systemic change in Africa's insurtech ecosystem through its focus on products serving women customers. Participating ventures developed 86 innovative products, with 78% specifically targeting low-income populations where women face the greatest exclusion from traditional insurance services. Examples include products that address maternal health coverage and flexible payment structures that accommodate women's income patterns.
BimaLab's advocacy efforts through conferences and social media platforms amplified women's voices in the Insurtech space. The programme's regulatory track delivered critical gender inclusion capacity building to 15 regulatory bodies across Africa, equipping them with tools to create more inclusive policy frameworks that support women's participation in the insurance sector.
Key learnings emphasised the importance of gender-sensitive policies that include gender impact analysis in product development, targeted financial literacy campaigns for women, and advocacy for increased gender diversity within regulatory agencies.

Impact 3.1 - Fragility and vulnerability

Indicator(s)	Milestone(s) for this review	Progress
Proportion (%) of individuals and small businesses (MSMEs) who feel protected against a) illness, b) environmental shocks, and c) financial shocks; and equipped with the human, social and environmental capital they need for the future.	MSMEs - 80% / Individuals – 80%	Not re-measured during reporting period. / Results from 2023-24: / MSMEs – 87% / Individuals – 59%

In 2024, FSD Africa commissioned surveys of individuals and MSMEs. No survey was conducted in the review period, so these results have not been refreshed.

For individuals, clients of four portfolio companies in Kenya, Tanzania and Nigeria were surveyed. For MSMEs, eight portfolio companies of one of FSDAi’s fund managers were surveyed. With a positive assessment provided by, on average, 73% of individuals and MSMEs, FSD Africa is slightly off track against this milestone.

Outcome 1.1 – Increased resilience to financial shocks and support for macroeconomic stability

Indicator(s)	Milestone(s) for this review	Progress
Percentage of partner financial intermediaries in each focus country that have effective public reporting on risks and on strategy for mitigation.	50%	No figures reported.

High quality risk disclosures contribute to financial stability by providing investors and other market participants with a better understanding of firms' risk exposures and risk management practices. FSD Africa supported improved financial reporting through a variety of interventions. The target (at strategies’ end in 2026) is for half of all financial intermediaries to have effective public reporting. The milestone has not yet been met. Progress is tracked through the Task Force for Nature-Related Financial Disclosures (TNFD), which measures the proportion of Sub-Saharan African countries mandating TNFD-aligned disclosure. To date, no country in the region has introduced mandatory requirements. However, progress is evident, with voluntary disclosure guidance notes issued in South Africa, Nigeria, Kenya, Morocco, Mauritius, Egypt, Ghana, and Zambia. Results against this indicator are therefore expected to materialise at the overall programme level.

Outcome 2.1 – Number of people supported to better adapt to the effects of climate change

Indicator(s)	Milestone(s) for this review	Progress
Number of people supported to better adapt to the effects of climate change as a result of FSD Africa support (ICF Indicator).	800,145	181,111

During this reporting period, FSD Africa supported an additional 63,175 people to better adapt to the effects of climate change, bringing the cumulative to 181,111 people reached. The main contributing intervention are Catalyst Fund reaching 56,167 new users and TECA reaching an additional 7,008 users.

While the progress has been gradual, several ongoing interventions including Geothermal, Nithio, Climate Action Platform - Africa and Universal Climate Resilience are expected to significantly contribute to this indicator within the overall programme. This outcome require time to materialise, as the interventions are still in early delivery stages, with measurable impact anticipated later in the programme cycle. Under the new logframe, target computation for this indicator will count only individuals, with business support translated into employee impact.

Case study: Tolbi

Catalyst Fund provided $200,000 (£161,324) in pre-seed funding and venture-building support to Tolbi, a Senegalese agri-tech startup using AI and satellite technology to close Africa’s agricultural data gap. This early support enabled Tolbi to build a trusted platform delivering real-time insights to farmers, cooperatives, banks, and governments.

Tolbi tripled its revenue in one year, grew its team from 7 to 21, and expanded its farmer network from fewer than 1,000 to over 1,500 active users. 87% of farmers improved their practices and over 90% adopted climate-smart agriculture, leading to higher yields, reduced input waste, and greater resilience to climate shocks.

Catalyst Fund capital also unlocked an additional $1 million (£772,576) from Orange, Digital Africa, and local investors. Tolbi is now preparing a $2.5 million (£1.9m) seed round to expand into Côte d’Ivoire, Mali, the DRC, and Ghana by 2026.

As Tolbi’s co-founder Mouhamadou Lamine Kebe explains, "In Africa, the biggest bottleneck is data. Without accurate data, there’s no visibility, and without visibility, there’s no investment."
“Tolbi helps us avoid wasting inputs and protect the environment,” says Saliou Ndiaye, a rice farmer. “And when a crisis hits, we’re not caught off guard.”

Outcome 3.1 - Improved access to high quality and affordable basic services (i.e. healthcare, clean energy, housing) for low-income and marginalized groups and women.

Indicator(s)	Milestone(s) for this review	Progress
Number of people with improved access to basic services (Energy, Healthcare, Housing).	1,191,034	1,034,210 / Renewable Energy – 97% / Healthcare – 3%

As the financial sector deepens and broadens, enterprises are better able to source investment and consequently expand and deliver at scale, thus reducing the unit cost while increasing the supply of services. During this reporting period, FSD Africa reached an additional 629,705 people with improved access to basic services. To date, over 1 million people have gained improved access to basic services, with most of this impact driven by the energy sector (97%). This progress was mainly contributed by FSDAi investments, including:

- Persistent Energy which has newly enabled energy access to about 260,000 people by providing early-stage capital and operational support to energy companies (https://tinyurl.com/3ted63ka)
- Nithio, which uses data-driven blended finance models to support last-mile solar distribution, reaching additional 140,221 people. (https://tinyurl.com/2udpmctu )
- Africa Climate Venture (ACV) reached additional 16,587 people with access to clean energy, through its climate venture-building model that supports innovative energy startups across Africa.
- DDFinance reached 25,959 people with improved access to healthcare.

Case study: Nithio

Nithio, with support from FSDAi has expanded energy access for nearly 563,465 people across Kenya, Nigeria, and Uganda by financing off-grid solar solutions. Through its AI-driven credit risk platform, Nithio provides capital to Pay-As-You-Go solar companies and microfinance institutions, enabling households and small businesses to adopt affordable, clean energy. This has resulted in the deployment of nearly 24,147 solar systems sold, improving livelihoods and reducing reliance on polluting energy sources.

FSDAi’s £3.251 million investment helped Nithio lower financing costs, particularly for smaller, local solar providers operating in underserved regions like Northern Nigeria and the Kenya-Somalia border. By focusing on these markets, Nithio ensures that off-grid communities gain access to reliable electricity, powering homes, supporting small enterprises, and avoiding 665,654 metric tons of CO₂ emissions. The initiative highlights how targeted financing can bridge Africa’s energy gap while promoting inclusive and sustainable development.

“A well-known player in innovative early-stage vehicles, and one of the earliest investors into Nithio FI's open-ended vehicle, FSDAi continues to inspire confidence in other investors to come in, helping Nithio build a reliable track record,” says Grace Fenton, Partnerships Director at Nithio.

“Nithio recognises the outsized impact energy access can have on women and seek to scale access equitably,” says Benita Murray-Bruce, Head of Legal at Nithio.

Outcome 4.1 – Amount (£m) of finance mobilised/catalysed by FSD Africa

Indicator(s)	Milestone(s) for this review	Progress
Amount (£m) of finance mobilised/catalysed by FSD Africa from the public and private sector for projects designed to address the needs of low income and marginalized groups and women, and climate change purposes (ICF indicator).	1,603	1,283

Capital mobilisation/catalysation in Africa offers the opportunity for economic growth and development. A lack of capital holds countries back from achieving the SDGs. FSDAi’s investment in these markets and FSD Africa’s system-focused interventions facilitate the scaling of new and existing flows of capital. FSDAi’s investment has a target of 80% green finance. Some projects such as the Ethiopia Stock Exchange (ESX) will deliver essential market systems change, which is essential to a sustainable and prosperous future even though some of them may not be classified as “green”.

Annex D has details of progress against this indicator.
Case Study: Burn Manufacturing

Burn Manufacturing, a clean cookstove manufacturing and distribution company incorporated in Kenya, launched a US$5m short-term bond in 2023 to finance manufacturing expansion and research and development. The bond was 100% oversubscribed, raising US$10m, enabling BURN to increase monthly capacity in Kenya from 150,000 units to nearly half a million, and to develop four assembly sites in Tanzania, Malawi, the DRC and Nigeria.

FSD Africa provided technical assistance to align the bond with the International Capital Market Association’s Green Bond Principles, and supported the second-party opinion through Agusto & Co. FSD Africa’s support was vital for BURN’s inaugural green bond offering, helping the company demonstrate that its energy-efficient cookstoves deliver health, environmental and livelihood benefits, and persuading regulators to adopt a more holistic understanding of green investment.

Following the raise, BURN expanded its presence from 8 to 14 countries, created nearly 1,000 new jobs bringing its workforce to over 3,000, and reached two million families with safer and cleaner cooking alternatives, saving each about US$1,000 over the product’s life. The bond also enabled the development of Africa’s first electric induction cooker for low-income households and contributed to eight Sustainable Development Goals.

“FSD Africa got wind of our fundraising efforts and just jumped in to support us through programme activities and green certification as part of their objective to develop capital markets here in Africa,” explains Ted Miller, Head of Corporate Finance at BURN Manufacturing Kenya. “Two million new families can now breathe less emissions every day and save about £750 over the life of their (respective) products.”

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue based on its own merits and in light of the context. With official development assistance (ODA) to Africa declining, mobilising private capital is more critical than ever to bridge the growing financing gap for climate resilience and inclusive growth. Performance remains strong, both in terms of consistent delivery of outputs and also in early indications that these are feeding through to the outcomes and impacts covered in this section. FSD Africa continues to fill an unmet need in providing early stage, high risk-high finance in Africa, complementing other international, British and FCDO activities.

## C. DETAILED OUTPUT SCORING
Summary scores:

Output	Weighting	Score
Reduced currency and refinancing risk improving stability and creditworthiness: Proportion of FSD Africa supported portfolio, and completed transactions that are financed in local currency	12.5%	B
Deeper and more sophisticated domestic capital markets, new asset classes and improved investment opportunities: Number of FSD Africa supported transactions that have been closed.	12.5%	A+
Development of new policies, regulations, investment guidelines and masterplans to create an enabling environment for (green) capital markets development, equitable digitization of the economy, health, finance and insurance industry: Number of regulations, policies and investment guidelines and masterplans developed/refined for financial markets to create an enabling environment for (green) capital markets development, equitable digitisation of the economy, health, finance and insurance industry.	25%	A+
Market infrastructure development e.g. new data and analytics, digital infrastructure, digital data protection strategies, green finance standards, metrics, Credit Enhancement Facilities, OTC Exchange: Number of market infrastructure designed/improved/adapted.	25%	A+
Innovative financial products and services, transactions and new intermediaries focused on green, housing and health finance, insurance and digital economy, tailored to the needs of low income and marginalized groups and women: Number of ‘innovative' intermediaries supported.	12.5%	A+
Increased capacity of and collaboration between governments, private sector and civil society on green finance, risk prevention and management, consumer and data protection and the livelihood needs of low-income and marginalized groups and women: Number of institutions reached by FSD Africa-sponsored capacity building and TA initiatives.	6.25%	A++
Increased capacity of and collaboration between governments, private sector and civil society on green finance, risk prevention and management, consumer and data protection and the livelihood needs of low-income and marginalized groups and women: Number of active strategic partnerships/collaborations.	6.25%	A+

Output Title	Reduced currency and refinancing risk improving stability and creditworthiness:
Output number:		1	Output Score:	B
Impact weighting (%):		12.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Proportion of FSD Africa supported portfolio, and completed transactions that are financed in local currency.	60%	55.6%

Briefly describe the output’s activities and provide supporting narrative for the score.

55.6% of FSD Africa’s supported transactions were financed in local currency, against the 2024/2025 milestone of 60%. Additional details can be found on the issuance table below under output 2.

One new local currency transaction was closed during the reporting period. Prado Power Limited, a Nigerian renewable energy company, successfully raised NGN 1.95 billion (£916,508) through a 7-year green sukuk (ie. Islamic compliant bond), backed by InfraCredit facility. This financing will enable the deployment of four solar-hybrid mini-grids with a combined capacity of 850 kWh pa across communities in Benue and Akwa Ibom States. The mini-grids will provide grid-quality power to approximately 15,800 households and small businesses, catalysing local economic activity through productive-use appliances like threshers and mills.

InfraCredit played a pivotal role in the issuance by providing its AAA-rated partial credit guarantee, which significantly enhanced the sukuk’s credit profile and attracted local institutional investors. This guarantees de-risked the transaction, enabled Prado Power to access long-term capital on more favourable terms, and ensured that the green Sukuk met high standards of financial credibility and sustainability.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes planned for this output. A new logframe has been agreed for FSD Africa for the 2025 - 2030 strategy, and this output will be retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

Output Title	Deeper and more sophisticated domestic capital markets, new asset classes and improved investment opportunities.
Output number:		2	Output Score:	A+
Impact weighting (%):		12.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of FSD Africa supported transactions that have been closed	20	27

Briefly describe the output’s activities and provide supporting narrative for the score.

Three new FSD Africa transactions were closed during the review period. Two of these, the Risk Sharing Backstop Facility and Acre Export Fund I, are from FSDAi, while one (Prado Power) is from FSD Africa:
The Risk Sharing Backstop Facility (RSBF) is a financial mechanism designed to support InfraCredit in issuing construction funding guarantees for climate-aligned early-stage infrastructure projects in Nigeria (see also output 5)
The Acre Export Finance Fund I aims to bridge the financing gap in climate-aligned infrastructure projects across Africa, by funding otherwise missing commercial debt tranches required by export credit agencies.
Prado Power (see output 1)

Annex E shows all completed transactions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes planned for this output. A new logframe has been agreed for FSD Africa for the 2025 - 2030 strategy, and this output will be retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

Output Title	Development of new policies, regulations, investment guidelines and masterplans to create an enabling environment for (green) capital markets development, equitable digitization of the economy, health, finance and insurance industry
Output number:		3	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of regulations, policies and investment guidelines and masterplans developed/refined for financial markets to create an enabling environment for (green) capital markets development, equitable digitisation of the economy, health, finance and insurance industry	45	69

Briefly describe the output’s activities and provide supporting narrative for the score.

In addition to the 52 previously developed regulations, policies and investment guidelines, 17 new were developed during the period under review.

The 17 policies, regulations and guidelines are covered below under various interventions:
- Under the Risk, Resilience and Regulatory Lab (R3LAB) programme, two key regulatory/policies were developed. In March 2024, the National Insurance Commission of Nigeria (NAICOM) drafted their Insurtech guidelines and proactively engaged stakeholders in the insurance industry to review the document and proposed regulations before final publication. In the second phase of the programme scheduled for December 2024, R3Lab supported the development and adoption of insurance regulatory sandbox policies in Zambia and Zimbabwe, marking a significant step toward fostering innovation and regulatory alignment in the region’s insurance sector.
- Under Africa Pensions Supervisors Network (APSN), three new pension investment policies were initiated to enhance sustainable and inclusive investment practices across Africa. In 2023, APSN completed the review and development of cross-border (diaspora) pension guidelines in Nigeria. In 2024, the network finalised reporting guidelines for ESG and climate-related disclosures for the pensions industry in Kenya, Nigeria, and Ghana. Additionally, the development of an ESG Disclosure Guidance Note for Kenya is currently ongoing.
- In December 2024, the Climate Action Platform - Africa (CAP-A) strengthened Africa’s position for COP29 by supporting the Climate Envoy in developing technical inputs for negotiations on the New Collective Quantified Goal (NCQG) and Article 6 of the Paris Agreement to ensure Africa’s priorities on equitable climate finance and transparent carbon markets were represented in the negotiations.
- In December 2024, BimaLab supported insurance regulators in Ghana and Nigeria to develop and launch insurtech sandboxes in both countries, with five insurtechs admitted and operating in Ghana and two in Nigeria. By March 2025, BimaLab had also collaborated with regulators in Zambia and Zimbabwe to develop insurance sandbox regulatory frameworks, laying the groundwork for future sandbox implementation in those markets.
- Between April and September 2024, under the Risk Transfer for Geothermal Energy Exploration Programme, the Geothermal Resource Risk Product underwent four rounds of revisions led by ICEA Lion (lead insurer), Kenbright, and Parhelion (Kenya). Final documents were submitted in April, and by June, the policy wording, claims, and proposal forms were finalised. The product was officially approved by the regulator in September 2024.
- Four new policies and guidelines were refined for Ethiopia Securities Exchange (ESX), including the finalised Corporate Governance Policy in September 2024, the Risk and Compliance Policy Framework and the Conflict of Interest Policy in December 2024, and the finalised 5-Year Strategy Plan in March 2025.
- Under the SADC (Southern African Development Community) Green Bond Programme, two guidelines were developed. In September 2024, the Botswana Stock Exchange (BSE) finalised its Sustainability Disclosure Guidelines, and in December 2024, BODIVA’s (Bolsa de Dívida e Valores de Angola) stock market rules in Angola were reviewed internally to support the issuance of sustainability and green bonds.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes planned for this output. A new logframe has been agreed for FSD Africa for the 2025 - 2030 strategy, and this output will be retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

Output Title	Market infrastructure development e.g. new data and analytics, digital infrastructure, digital data protection strategies, green finance standards, metrics, Credit Enhancement Facilities, OTC Exchange
Output number:		4	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of market infrastructure designed/improved/adapted	11	12

Briefly describe the output’s activities and provide supporting narrative for the score.

Three new market infrastructure were designed/improved/adapted during this reporting period:
The Ethiopia Central Securities Depository (CSD) is a flagship initiative led by the National Bank of Ethiopia (NBE), with technical and financial support from FSD Africa, to establish a secure, efficient, and modern post-trade infrastructure for the country's emerging capital markets. The CSD facilitates the electronic custody, settlement, and transfer of securities, beginning with government securities and scalable to include corporate bonds, equities, and funds.
FSD Africa committed £700,000, supporting vendor selection, system design, training, and deployment, while also embedding technical advisors and leveraging global expertise. Since its approval in 2021, the intervention has achieved key milestones including vendor contracting, system design finalisation, stakeholder engagement, user training, and the CSD successfully went live in November 2024. Integration with Ethiopia’s forthcoming securities exchange (ESX) and full operationalisation of the platform are underway, positioning the CSD as a foundational building block for Ethiopia’s capital market development and long-term financial resilience.
Risk, Resilience and Regulatory Lab (R3Lab) is a platform focused on addressing challenges faced by regulatory agencies through collaboration and cooperation. R3Lab platform was developed to create an enabling regulatory environment by encouraging and facilitating regulatory and supervisory interactions between insurance regulators in Africa. In June 2024, R3Lab Toolkit for regulating responsible innovation was launched. This launch was a significant milestone in enhancing the capabilities of financial supervisors across Africa, providing them with innovative tools to address the evolving challenges in financial regulation and supervision.
In September 2024, Kenya’s Insurance Regulatory Authority (IRA), in partnership with the Ministry of Energy, State Department of Industrialisation, and East African insurers launched Africa’s first Geothermal Risk Underwriting Facility, offering up to US $2 million in insurance for early-stage geothermal drilling to attract private investment. This was developed with support from FSD Africa working alongside Parhelion Underwriting and Kenbright. The facility aims to attract private investment by de-risking exploration phases, which are typically too risky for commercial lenders. The initiative also supports policy reform, insurer capacity building, and aligns with Kenya’s energy transition goals to expand clean, affordable energy.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes planned for this output. A new logframe has been agreed for FSD Africa for the 2025 - 2030 strategy, and this output will be retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

Output Title	Innovative financial products and services, transactions and new intermediaries focused on green, housing and health finance, insurance and digital economy, tailored to the needs of low income and marginalized groups and women
Output number:		5	Output Score:	A+
Impact weighting (%):		12.5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of ‘innovative' intermediaries supported	19	26

Briefly describe the output’s activities and provide supporting narrative for the score.

Seven innovative intermediaries were supported during this reporting period: FSD Africa supported two innovative intermediaries by finalising the scoping study for the SME fund in Rwanda and finalised the selection process for a fund manager to manage the Kenya SME fund. These efforts are part of a broader strategy to enhance private equity and debt markets across Africa, by increasing local institutional investor participation and enhancing capacity building among stakeholders.

Under FSDAi there are five new investments, one of which was not announced as of time of publication of this annual review. The remaining four are comprised of:
The Risk Sharing Backstop Facility (RSBF) is a Nigerian financial intermediary set up to help InfraCredit provide guarantees for early-stage, climate-friendly infrastructure projects. It supports local banks and financiers by covering up to 80% of credit risk, encouraging them to fund projects that face construction-phase risks. InfraCredit only draws on the RSBF if a project defaults. Successful projects are later refinanced through corporate bonds backed by InfraCredit, helping to grow Nigeria’s capital markets.
FSDAi committed £10 million to RSBF through a loan. This support aims to unlock local institutional capital, especially from pension funds, and boost green infrastructure financing. While no deals were closed as of March 2025, RSBF has a strong pipeline of renewable energy and green housing projects.
West Africa Blue is a blue carbon project developer focused on conserving and restoring mangroves in Sierra Leone’s Sherbro River Estuary and Yawri Bay. The project aims to generate carbon credits by protecting 74,000 hectares of threatened mangroves, while supporting local communities through job creation and benefit sharing.
FSDAi is supporting the intervention with a US$2.5 million loan, while FSD Africa supported it with a £89,500 grant. The funding will help cover early-stage costs and develop a community-focused benefit sharing agreement. This is FSDAi’s first direct investment in a nature-based solution and aims to demonstrate the bankability of high-quality blue carbon projects in Africa.
The ARM-Harith Climate and Transition Fund (ACT) is an infrastructure equity fund focused on climate-aligned projects in Nigeria and West Africa. It is managed by ARM-Harith, a joint venture between Nigeria’s ARM and South Africa’s Harith. The fund is structured into three vehicles, two in Nigeria (USD and naira-denominated) and one in Mauritius for international investors. ACT targets sectors such as renewable energy, waste management, and clean transport, aiming to unlock local pension capital and address key barriers such as currency risk and limited appetite for infrastructure equity.
FSDAi committed £10 million (US$13 million) into ACT, this support is designed to de-risk participation for Nigerian pension funds and catalyse about US$40 million in local capital.
The Climate Resilient Africa Fund (CRAF) is a venture capital fund that invests in early-stage startups addressing climate adaptation and nature loss within Africa’s agri-food systems. Targeting countries such as Egypt, Kenya, Ghana, Nigeria, Morocco, and South Africa, the fund supports pre-seed to Series A ventures developing innovative solutions including precision agriculture, bio-food technology, and digital tools for smallholder farmers.
FSD Africa Investments (FSDAi) is providing catalytic support to CRAF by anchoring the first close with a proposed $3 million investment, with follow-on commitments of up to $10 million. This aims to de-risk the fund for other investors, promote climate-gender frameworks, and help unlock local currency capital, particularly in Egypt where investment constraints are high.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes planned for this output. A new logframe has been agreed for FSD Africa for the 2025 - 2030 strategy, and this output will be retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

Output Title	Increased capacity of and collaboration between governments, private sector and civil society on green finance, risk prevention and management, consumer and data protection and the livelihood needs of low-income and marginalized groups and women
Output number:		6.1	Output Score:	A++
Impact weighting (%):		6.25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of institutions reached by FSD Africa-sponsored capacity building and TA initiatives.	441	852

Briefly describe the output’s activities and provide supporting narrative for the score.

342 new institutions were reached by FSD Africa’s sponsored capacity building and TA initiatives as shown in the chart below:

Case Study: African Natural Capital Alliance - ANCA

ANCA was developed in 2022 to secure an effective African voice in shaping global nature-related finance frameworks. It has now grown to 83 member organisations, representing a broad coalition including financial institutions (Access Bank, Ecobank, Equity Bank, KCB, Old Mutual, FirstRand, Investec, Sanlam, Zanaco), civil society groups (African Wildlife Foundation and CrossBoundary) and public bodies such as Ghana's Ministry for the Environment. FSD Africa have played a central role as founding convenor and coordinator, alongside providing tailored support to member organisations, e.g. providing EarthAcre - an innovative start-up developing biodiversity assets that directly and transparently pay communities - with tailored support for their launch in April 2024.

FSD Africa have also supported the ANCA Nature Executive Fellowship; the first year of the fellowship supported upskilled 23 financial executives, NGO directors, and indigenous people and local community organisation representatives to develop plans for financeable nature projects (including ecosystem restoration projects, carbon credit mechanisms, and nature capital funds) within their organisations.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes planned for this output. A new logframe has been agreed for FSD Africa for the 2025 - 2030 strategy, and this output will be retained.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

Output Title	Increased capacity of and collaboration between governments, private sector and civil society on green finance, risk prevention and management, consumer and data protection and the livelihood needs of low-income and marginalized groups and women.
Output number:		6.2	Output Score:	A+
Impact weighting (%):		12.5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of active strategic partnerships/collaborations.	108 (cumulative)	114

During this review period, 19 new partnerships were formed, bringing the cumulative total to 114. These include 7 under Adaptation and Resilience, 1 under Early-Stage Finance (Carbon CoE), 10 under Financial Markets and 1 under FSDAi, as shown in the chart below:
Strategic Partnerships

Some notable examples include:
- Adaptation and Resilience pillar partnered with Impact Actuarial to advance Environmental, Social, and Governance (ESG) integration in the insurance sector by training insurers including AAR insurance, Britam and ICEA Lion. The collaboration aimed to provide technical assistance (TA) to AAR Insurance in developing and implementing a robust ESG strategy and creating sustainable insurance products, particularly in areas like disaster risk, agriculture, and renewable energy.
- Early-stage finance (through the Carbon Markets centre of expertise) partnered with Verst Carbon to collaborate on the Africa Biochar Carbon Dioxide Removal Aggregation Programme, a continent-wide initiative aimed at scaling biochar carbon removal projects. Verst Carbon will lead the design, business planning, and development of a pipeline of investable projects, while FSD Africa will provide technical assistance, funding support, and help structure appropriate financial instruments.
- Financial Markets pillar partnered with the Bank of Industry (BOI) Nigeria, to support the successful issuance of BOI’s Green/Sustainability Bond Programme scheduled for 2025. The partnership aims to strengthen BOI’s capacity in sustainable finance through technical assistance, the development of a sustainability strategy and framework, and alignment with international Green Bond Principles.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Collaboration will continue to be a focus of FSD Africa work, but this indicator will not be carried forward into the new logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against recommendations from the previous AR are in Annex A, while recommendations are in Section A.

## D. VALUE FOR MONEY
Key cost drivers and performance

The VFM framework was updated in 2022. Rubrics were agreed for each of the “five E”s provide frameworks that set out criteria and standards for different levels of performance. This Annual Review is based on FSD Africa’s and FSDAi’s performance data and VFM analysis of the programme for period ending March 2025, complemented by FCDO analysis up to and including Sept 2025.

VfM performance compared to the original VfM proposition in the business case

Some notable highlights of the year which drive value for money include:
- The procurement unit redefined its procurement strategy with the core areas identified to anchor the unit's operations for the next 3 - 4 years.
- FSD Africa obtained CIPS Procurement Excellence Award, for its continuing work to improve procurement.

Economy - Good
Economy describes the extent to which FSD Africa manages its purchase of programme resources, buying inputs of the appropriate quality at the right price. FSD Africa achieved a “good” economy score.

Central overheads continue to be maintained within the 20% limit set out in FSD Africa’s MOU with FCDO, though this year’s Programme Management Costs were 19%, up from 17% in the previous year. This uptick was driven by costs associated with the development of the new strategy (which entailed use of overheads to procure consulting support).

Travel costs overall remained at 2% of total spend, though unit costs for accommodation fell substantially, reflecting improved planning for travel.

Competitive procurements accounted for 60% of all procurement at £5.2m, while single sourced procurements accounted for 40% at £1.9m. Localisation continues to be a procurement objective. Of the competitively sourced engagements, African firms were awarded a total of £1.6m while non-African firms were awarded £3.5m. Through single sourcing, around £0.5k was issued to non- African firms, while regional firms were issued with £1.5m.

Recommendation: FSD Africa should review the method of calculating programme management costs, with an eye to ensuring that indirect costs (“overheads” or “programme management costs”) are fully recovered from all funders. This will ensure sustainability of operations, prevent underfunding of support functions, help in accurate budgeting and costing, and promote transparency in financial management.

Efficiency - Adequate
Efficiency measures the extent to which FSD Africa does the right things in the right ways, producing the intended quality and quantity of outputs within the available resources and time frame. FSD Africa achieved “adequate” efficiency.

The performance of 36 interventions was assessed against expected output achievements and budgets. Only about one third of the interventions producing the intended quality and quantity of outputs within the available resources and timeframe. However, the percentage of projects significantly under or over budget, or achieving less than half of agreed targets fell for the third year running, from 32% to 17%. As some variation in pace and budget of activities is to be expected, this is considered “adequate”.

Effectiveness – Adequate
Effectiveness measures FSD Africa’s contributions to intended outcomes. Of three outcomes with relevant milestones, one (people with access to basic services) was on track, albeit not achieving 100% of the milestone. Progress is being achieved in the other two outcomes at a slower pace than initially hoped. Nevertheless, results are well-linked to the theory of change and underpinned by strong activity and outputs. Thus, an “adequate” rating is appropriate.

Cost-Effectiveness - Good
Cost-Effectiveness measures FSD Africa’s contribution to intended impacts, commensurate with expectations for the funding allocated. FSD Africa achieved “good” cost-effectiveness.

Outcomes have been met for two of three impact areas, where spending and activity has generated expected results in climate action and job creation.

In the new 2025 – 2030 strategy, FSD Africa will move away from survey-based indicators and instead count the number of people and MSMEs reached with the intent to improve their adaptability and resilience to climate and financial shocks.

Equity - Good
Equity measures the extent to which FSD Africa contributes to meeting the needs of low income and marginalised groups and women. FSD Africa achieved a “good” score against its rubric.

A strong focus on promoting equity has yielded good results across the portfolio. Some examples include:
- The Gender Impacts Tracing Study demonstrates the positive effect of the 2X challenge framework on women in leadership roles in companies supported by the Nyala Facility and Persistent Energy;
- 60% of BimaLab participants were women-led, and 150 gender responsive insurance products were developed;
- The Gender Bond Toolkit, developed by FSD Africa in partnership with others, and shared though a series of workshops throughout the year, put a spotlight on the role of gender bonds in Africa
- FSD Africa has adopted sustainable procurement guidelines to help incorporate sustainability in procurement practices. This is aimed to promote contracts with African firms, and to driver better gender equity outcomes through procurement.

Assessment of whether the programme continues to represent value for money

The programme continues to represent good VFM. Output attainment remains strong. The Theory of change has been revised as part of the new strategy. FSD Africa demonstrates adequate or good performance against the 5 E’s of FCDO’s value for money framework. With the global reduction in ODA, mobilising private finance, and especially African finance, to invest in people and climate action in Africa is all the more imperative.

E: RISK

Overview of risk management

The overall risk level for the Programme remains Moderate. As highlighted in the previous annual review, increasing organisational complexity and the expansion of delivery chains may elevate the significance of other risk categories, particularly Financial and Fiduciary risks, including the potential for fraud. The FCDO maintains close oversight of these risks through regular engagement with FSD Africa’s pillar and risk leads, site visits to FSD Africa’s offices, and ongoing collaboration with FCDO posts as well as FSD Africa’s downstream partners and investees.

Progress has been made on last year’s recommendation; “FSD Africa (non-profit) and especially FSDAi will need to review where it puts its efforts to counter fraud and promote safeguarding”. Through extensive internal discussion with FCDO internal advisers and FSD Africa, a fuller understanding was developed of where FSD Africa and FSDAi could put its efforts to counter fraud and promote safeguarding, as noted in Annex A.

Due to budget uncertainty the recommendation that “FSD Africa should follow through on its decision to in-house its internal audit function – currently contracted out.” was not implemented. This was driven by FCDO budget uncertainty and the impending Spending Review; subsequently the UK Government confirmed the ODA budget will remain at 0.3 GNI, whilst retaining their commitment to return to 0.7 GNI when fiscal conditions allow. FCDO was fully consulted in the decision to not implement this recommendation.

At the FCDO level, the following key risks were highlighted (excerpt from FCDO risk register as at March 2025):

Description and Category	Gross Risk Rating	Residual Impact	Residual Rating and trajectory
C4: Africa Context / Strategy and Context	Severe	FSD Africa operates as an adaptive programme, capable of engaging in areas where risks are considered manageable. It leverages its networks to identify promising opportunities for progress and remains prepared to withdraw when plans encounter insurmountable barriers.	Major (Stable)
F38: Misuse of funds / Financial and Fiduciary	Almost Certain (in the absence of mitigation)	FSD Africa recognises and proactively addresses the risks associated with fraud. This includes conducting thorough due diligence on investees and maintaining continuous oversight, including through participation on the boards of investee organisations. During the reporting year, FSDAi commissioned external support on fraud prevention and management.	Moderate (Stable)
D2/D3: Strategic misalignment – FSD Africa/FSDAi project selection and organisational focus / Policy and Programme Delivery	Major	Ongoing engagement with management, along with FCDO’s participation on Boards—including the Development Impact Committee—supports continued strategic alignment. FSD Africa also has a dedicated development impact team and collaborates closely with partners to evaluate both impact and attribution.	Moderate (Stable)

Category Trends (Decrease/Stable/Increase)
- Strategy and Context: Incidents of significant conflict continued to rise across Africa during the reporting period. Persistent macroeconomic challenges, such as debt distress, currency depreciation, and restricted access to global capital markets, further highlight the critical importance of FSD Africa’s work. Fundraising by FSD Africa’s investees continues to be a challenge, and FSDAi has had to extend timelines for fund closes in some cases. [Major - Stable]
- Policy and Programme Delivery: FSD Africa’s governance structures continue to reflect best practices and are consistently evolving. Organisational and structural changes are being effectively managed, supported by a culture of ongoing enhancement. This culture is expected to adapt and refine risk mitigations over time. High budget uncertainty pushed aspects to Severe, however with confirmation of FY26 budget this aspect reduced to Moderate. [Moderate - Stable]
- Safeguarding: Overall, the residual likelihood and impact of risks remain steady for both the programme and its stakeholders. There is evidence of effective management in handling reports and incidents through to resolution. The decision to bring the risk function in-house has proven to be a valuable step, enhancing oversight and responsiveness. Furthermore, the discontinuation of proposals in Sudan and the DRC reflects FSD Africa’s strong commitment to its duty of care, prioritising the safety and well-being of staff and partners. [Moderate - Stable]
- Public Service Delivery and Operations (i.e. capacity of FCDO internal operations which support programme delivery): Uncertainty about FSD Africa’s budget over the spending review period (2025–26 to 2029–30) remain in place and constrain the ability of FSD Africa to hire staff and scale up new areas of work set out in their strategy. Final decisions are expected by year end. [Minor - Stable]
- Financial and Fiduciary: Oversight of fiduciary risk management is ensured through the Senior Responsible Owner’s (SRO) participation on FSD Africa’s Board and its committees. Additionally, the Programme Responsible Owner (PRO) contributes to governance by serving on the Financial Audit and Risk Committee. FSD Africa takes a proactive approach to managing fraud risks, having taken advice from a specialist financial crime consultancy. An independent valuation was again procured by FCDO, confirming the value of FCDO’s equity. [Moderate - Stable]
- Reputational: FSD Africa continues to demonstrate its strategic relevance and is widely recognised as a reliable and valued delivery partner. [Minor - Stable]
- People: Internal staffing constraints have been alleviated, with a new team members recruited to join FCDO’s FSD Africa team. [Major - Stable]

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Commercial and financial issues continue to be well managed by both FSD Africa and FCDO.

Finance
Financial performance is satisfactory. Narrative reports and audited Annual Reports and Financial Statements are clear and concise, and delivered in a timely fashion allowing the FCDO programme team to meet reporting deadlines.

FSDAi’s portfolio internal rate of return was -3.05% net (against an expectation of zero return) and 0.16% gross (against an expectation of 2%). This reduction against last year (when net return was 0.37% and gross 1.7%) is largely a function of the depreciation of the USD. IRR targets are set for GBP, whereas FSD Africa holds its assets in USD, and the USD depreciated by 20% over the year in review.

As of 31 March 2025, FSDAi had £82.2m in signed commitments across 17 FT investments spanning 25+ African countries.

Delays to confirmation of programme budgets by FCDO at the start of financial year continued to cause uncertainty and impact on delivery as FSD Africa requires reasonable notification of budgets to maximise opportunities from its intervention pipeline. Looking beyond the reporting period (2024-25), the changes to ODA announced by the UK Government introduced uncertainty, however the programme has remained consistently aligned with the Government’s priorities and, importantly, is strongly aligned with UK Government and Foreign Secretary priorities.
With increasingly diverse funders, there is a need for FSD Africa to provide additional financial reports to funders. This adds to complexity of financial management. As FSD Africa continues to find new funders, attention will need to be paid to the burden of reporting and cost sharing.

Programme Management
FCDO and FSD Africa continue to hold monthly programme management meetings covering operational processes, people management, financial management, risk management, compliance and audit. These meetings are useful forums to discuss and resolve issues relating to the internal management of the organisation. They also provide FCDO with an opportunity to give steers and policy updates on issues that might impact on FSD Africa’s operations. Matters regarding fraud and safeguarding concerns were also discussed routinely.

The implementation of a reporting project plan; MS Projects specifically, following last year’s recommendation has delivered notable efficiencies and improved ways of working between FSD Africa and FCDO. Timely and concise weekly updates, with key figures, disaggregation e.g. ICF, and persons, from FSD Africa ensured a readily available source of responses for FCDO commissions – that FCDO could also access directly. (See also appendix A)

FSD Africa and FCDO should review regular reporting requirements, and develop standard timetables, formats and definitions, to avoid last minute work. Many processes are routinely completed (such as quarterly narrative reporting), but some, such as the International Climate Finance return, the annual review process, and reporting of capital mobilisation numbers to OECD, could be optimised.

Commercial
The contract to independently value FCDO’s shareholding in FSDAi was successfully relet in the year in review. Other commercial considerations are noted in the “economy” section of value for money.

Investment in FSDAi
FCDO funds FSDAi with share purchases, which cover both its investments and operating costs. Quarterly share purchases were made in the year under review, though the timing of purchases has now been changed to twice yearly, following completion of the analysis recommended in last year’s annual review.

Corporate Governance of FSD Africa and FSDAi
FSD Africa and FSDAi are both companies incorporated in Kenya. As such, they are governed by a Board of Directors (with the same Board being appointed to both companies). In addition to the Chief Executive and Chief Investment Officer, the Board is comprised of paid non-executive directors with extensive corporate governance and financial sector experience. The Board is supported by independent advisers.

Both Boards are supported by four committees:
- Finance Audit and Risk Committee (FARC): responsibility for assessing the company’s accounts and budget, monitoring risk, internal controls and audit. The committee meets at least quarterly, usually just before the quarterly board meeting.
- Investment Committee: oversight of all FSD Africa and FSDAi proposals. The investment committee meets frequently, as needed to review proposed activities and investments. As the investment portfolio has increased, there is a need to review the composition of this committee, and ensure that the workload is manageable by Directors.
- Development Committee: reviews the development impact of the companies activities and portfolios.
- Nomination and Remuneration Committee: responsible for agreeing the remuneration envelope, director level recruitment and salaries.
There are clear Terms of Reference for all Board Committees. The Board is supported by a contracted Company Secretary.

G: MONITORING, EVIDENCE AND LEARNING

FSD Africa has a well-resourced development impact team. The team supports those involved in investment or project delivery to monitor and evaluate their activities and supports learning and evaluation by programme teams. It also leads on the annual development impact report and supports learning and evaluation studies.

Monitoring and Evaluation

FCDO is closely engaged in monitoring and evaluation. Focused discussions at the Board level take place within the quarterly Development Impact committee. Pillar leads meet regularly (at least quarterly) with PRO and SRO to discuss progress.

The SRO attended an early-stage finance conference in September 2024, and engaged with a variety of FSDAi fund manager. A subsequent visit to Ethiopia in February 2025 allowed an opportunity to meet many Ethiopian partners, including the Ethiopia Stock Exchange and Capital Markets Authority.
PRO and SRO work closely with posts, who feed in their views on local implementation.

In FY 25/26 FSD Africa has planned a thematic evaluation on the impacts of the nature programme delivered through the Taskforce on Nature-related Financial Disclosures (TNFD), the African Natural Capital Alliance (ANCA), and the regulatory component.

FSD Africa conducted “Voices from the Field” which provide a people-centred review of the impact of FSD Africa’s work. All impact stories from these visits are published on the FSD Africa website.

Evidence

In 2024-25, FSD Africa carried out several studies to generate evidence in key thematic areas that has been critical in informing delivery of programmes, including:
- A research study generating evidence on green jobs in Africa forecasting that the green economy will generate over 3 million direct jobs by 2030.
- A study on carbon markets, noting their relevant to capital mobilisation in Africa
- A gender impacts tracing study assessing the impact of gender diverse leadership on development outcomes for women gender related investments under FSDAi, as well as identify pathways through which these investments influence positive outcomes for women.

Learning

As part of the Strategic Learning Agenda that sought to determine whether a green growth trajectory in Africa delivers better and more inclusive development outcomes when compared to business-as-usual, FSD Africa carried out two research studies on:
- Assessing the impacts of green bonds in Africa across capital markets, the environment, and social inclusion.
- The social and economic impacts of Carbon markets in Lower- and Middle-Income Countries Africa, Asia and Latin America.

Case Study (Learning): The social and economic impacts of carbon markets on LMICs.

Carbon trading, particularly voluntary carbon markets, is gaining prominence in global climate mitigation efforts, raising concerns about its impact on local communities. This literature review examines carbon market participation on social and economic effects in local communities in low- and middle-income countries (LMICs).

The report, based on 52 empirical studies in Africa, Asia, and Latin America, highlights systemic challenges and potential risks. These include delayed payments, lack of inclusion in governance, land tenure inequalities, and increased workload for women, often without commensurate compensation.
The findings reveal a stark reality: while carbon markets hold potential to generate co-benefits alongside emissions reduction, this promise is highly contingent on project design, governance structures, and enabling policy environments. For example, agricultural and clean energy projects demonstrate more substantial positive community impacts than many forest conservation efforts, which may restrict access to vital natural resources and exacerbate social tensions.

The study explores factors enabling carbon markets to foster inclusive development, including transparent benefit-sharing models, high-integrity standards, premium pricing, and community engagement. It also highlights critical knowledge gaps, such as equity outcomes and the scalability of community benefits.

The review informs FSD Africa’s work in supporting the development of benefit sharing frameworks, and FSDAi’s work in originating and investing in carbon market projects.

The Social and Economic Impacts of Carbon Markets - FSD Africa

Date of last narrative financial report	18/11/2025	Date of last audited annual statement	18/11/2025

## ANNEXES
Annex A: Progress made from FY23/24 annual review recommendations:

Recommendation	Progress Update
1. The Board (on which FCDO is represented) should agree a refreshed strategy for FSD Africa, integrating FSDAi’s new strategy, which was approved in 2023.	A new strategy has been developed and was agreed with the Board in March 2025. The strategy seeks to “Design, implement and invest in catalytic interventions in African financial markets to bring about a long-lasting shift in the way capital is allocated to benefit people and planet”. This is an ambitious strategy, and efforts to mobilise finance for its implementation is underway from other funders.
2. FSD Africa and FCDO should agree a revised logframe to accompany the new strategy.	The FSD Africa board approved the Development Impact narrative and the KPI's framework in March 2025. This provides guidance to the development of a new logframe to accompany the new strategy which will be logged within FCDO six months before the next annual review.
3. Recommendation: FSD Africa should review the transmission mechanism between outputs, outcomes, and impacts. FSD Africa should build an evidence base about how activities give rise to outcomes, and the time needed for outcomes to be achieved. This should feed into the revised Logframe.	Progress Update: As part of its revised strategy, FSD Africa has revised outputs, outcomes, and intended impacts, along with assumptions and targets. For the logframe, FSD Africa will provide annual disaggregated targets, detailing timelines and explaining any anticipated lags. This will help clarify the linkages between outputs, outcomes, and the overall impact. / FSD Africa has deployed various mechanisms, including process reviews or rapid assessments, outcome evaluations, voices from the field (impact stories), and annual impact reports to build an evidence base for how FSD Africa's activities translate into outcomes. FSD Africa developed an impact strategy that assesses how to mobilise capital for impact and how to allocate capital to ensure impact objectives are achieved. In keeping with an AR recommendation, FSD Africa is developing a five-year evaluation plan that aligns with the organizational strategy (2025 - 2030), identifying the key strategic questions FSD Africa seeks to answer and having these inform the thematic evaluations to be carried out in the next five years.
4. FSD Africa should review its approach to oversight of its projects outside of East Africa, as part of its strategy revision. As FSD Africa is increasingly engaged across Africa, it will become more challenging to assess relevant political and business interests, to build networks with likeminded partners, and to monitor programmes. FSD Africa cannot deploy full-time staff in every Africa country, so will have to form a view about how to most effectively use its teams.	FSD Africa does not intend to set up offices outside Nairobi, Kenya, where it is currently headquartered. Programme administration will continue from the Nairobi office for the foreseeable future. / Consideration was given to boosting staff numbers in West Africa. Budget uncertainties mitigated against this, but it will be kept under review. / FSD Africa leverages FCDO country posts and works closely with them when planning country visits, consultations with country stakeholders, etc. This has proved helpful. Through regular progress monitoring calls with its partners, FSD Africa is also able to understand country contexts further, which shapes its thinking and planning for the countries. / In addition to the FCDO country posts, FSD Africa also has a number of its staff based outside Kenya these include: South Africa, Zambia, Egypt, Ghana, Nigeria and Uganda.
5. Recommendation: FSD Africa should set out how its gender approach will be implemented across the pillars of its work.	FSD Africa has initiated a strategic refresh of its gender approach, aligning it with the new strategy and the creation of the Gender Centre of Expertise (GCoE). This refreshed approach focuses on embedding gender-intentional finance across FSD Africa's investment and programme work, with the goal of reducing systemic barriers that limit women's economic empowerment opportunities in Africa. Key progress made includes: A new gender strategic framing has been developed and is under internal consultation. It outlines a shift from ad hoc gender mainstreaming to targeted gender intentional interventions, aligned to FSD Africa's market systems mandate. The strategy proposes a spotlight model, where a select number of projects will be supported end to end as demonstration projects for deeper gender integration. A practical screening and assessment tool has been introduced (currently under refinement with the DI team) to assess all new projects with no gender scope, some gender opportunity and high potential for gender impact (spotlights).
6. FSD Africa should further improve its risk management. Working with FCDO, it should review the boundaries of fraud and safeguarding action. With long investment chains (extending sometimes through two intermediaries to ultimate clients), FSD Africa and especially FSDAi will need to review where it puts its efforts to counter fraud and promote safeguarding. Similarly, FSD Africa should follow through on its decision to in-house its internal audit function – currently contracted out.	Fraud and Safeguarding action – FSD Africa’s on-boarding process for grantees and investees includes a rigorous due diligence process that assesses adequacy of policies, processes and controls in place for partners to handle fraud and safeguarding incidences. Where gaps are noted, action plans are agreed with the partners and embedded in the contractual agreement. Partners are further required to report any incidences and how they have been addressed. The FSD Africa and FSDAi risk teams respectively assess how reported incidents have been addressed by the partners and internally report to FARC and FCDO as per the escalation matrix. Discussions are ongoing with FCDO on modalities of regular updates on reported incidents. / Internal Audit - In FY2024/25 FSD Africa embarked on in-housing the function, a decision that was approved by the Board. With uncertainty about the UK aid budget, management decided to freeze recruitment plans until there is more clarity on the budget. KPMG continues to provide Internal Audit services in the meantime.
7. FSD Africa and FCDO should review regular reporting requirements, and develop standard timetables, formats and definitions, to avoid last minute work. Many processes are routinely completed (such as quarterly narrative reporting), but some, such as the annual review process, and reporting on capital mobilisation numbers and international climate finance figures, could be optimised.	A project tracker has now been put in place that aligns the different reporting requirements between FCDO and FSD Africa. This project tracker captures all expected reports, their submission timelines and the relevant templates, helping to streamline the reporting process to FCDO.
8. FCDO should review the timing of its share purchases in FSDAi, considering the implications of different timing on both efficiency and risk.	A new process has been put in place. It introduces a more structured and forward-looking funding approach that enhances governance, investor confidence, and operational efficiency. / FSDAi will adopt a biannual cycle for capital calls. The Board will review and approve the investment pipeline twice a year, enabling timely and predictable funding decisions. This reduces administrative burden and avoids end-of-year funding pressures. / This approach provides assurance to private investors that FSDAi has the financial backing to close deals, which is especially important in the context of ODA budget uncertainty. / The process also strengthens alignment between FSDAi, the Board, and FCDO, ensuring that capital deployment is strategic, transparent, and well-governed.

## Annex B: Impact 1.1 - Environmental benefits delivered
The table below represents the achievements for the 2024-25 only.

Investment	Parameter	Value	Unit	Source of data
ALCBF	Total emission reductions		tCO2e	ALCBF Impact data reporting
	Apportioned to fund	6,954,000	tCO2e	Assumed
	Carbon credits sold	0	tCO2e	Assumed
	FSD Africa investment (deployed)	16.15	mGBP	FSDAi Portfolio dashboard
	Co-investment	75.6	mGBP	FSDA intervention tracker
	FSD Africa share of investment	18%		Calculated
	FSD Africa attributed emission reductions	1,224,056	tCO2e	Calculated

Nithio	Total emission reductions	444,783	tCO2e	Nithio Impact data reporting (based on Gogla tool)
	Apportioned to fund	444,783	tCO2e	Assumed
	Carbon credits sold	0		Assumed
	FSD Africa investment (deployed)	3.4	mGBP	FSDAi Portfolio dashboard
	Co-investment		mGBP	FSDA intervention tracker
	FSD Africa share of investment	100%		Calculated
	FSD Africa attributed emission reductions	444,783	tCO2e	Calculated

Persistent	Total emission reductions	1,937,562	tCO2e	Persistent Impact data reporting (based on Gogla tool)
	Apportioned to fund	1,937,562	tCO2e	Assumed
	Carbon credits sold	0		Assumed
	FSD Africa investment (deployed)	2.6	mGBP	FSDAi Portfolio dashboard
	Co-investment	12.8	mGBP	FSDA intervention tracker
	FSD Africa share of investment	38%		Calculated
	FSD Africa attributed emission reductions	736,274	tCO2e	Calculated

Spark Energy	Total emission reductions	1,635	tCO2e	Spark Impact data reporting (based on Gogla tool)
	Apportioned to fund	1,635	tCO2e	Assumed
	Carbon credits sold	0		Assumed
	FSD Africa investment (deployed)	2.25	mGBP	FSDAi Portfolio dashboard
	Co-investment	5.5	mGBP	FSDA intervention tracker
	FSD Africa share of investment	41%		Calculated
	FSD Africa attributed emission reductions	668	tCO2e	Calculated
FSD Africa total attributed emission reductions		2,405,780	tCO2e
FSD Africa total attributed emission reductions (million tCO2e)		2.406	mtCO2e

## Annex C: Impact 2.1 - Economic opportunities created
Indicator(s)	Milestone(s) for this review	Progress
Number of jobs created, protected and supported through FSD Africa initiatives.	17,950	22,092

The table below represents the achievements for the 2024-25 only.
Intervention	Total estimated jobs for FY 2024/25 only Attributed to FSD Africa	Disaggregated by gender (women) -FY 2024/25 only	Type (Green/ / Non- green)	Number of green jobs- FY 2024/25 only
Nithio	1,338	281	Green	1,338
Persistent Energy	841	177	Green	841
BlueOrchard	4,752	2,286	Non-green	-
Nyala Facility	2,499	1,042	Non-green	-
Spark Energy	895	188	Green	895
Catalyst Fund	709	149	Green	709
IHS	689	21	Green	689
THF	- 63	-	Non-green	-

Total Jobs estimated	11,659	4,142	Green jobs	4,472

## Annex D: Finance mobilised / catalysed
Indicator(s)	Milestone(s) for this review	Progress
Amount (£m) of finance mobilised/catalysed by FSD Africa from the public and private sector for projects designed to address the needs of low income and marginalized groups and women, and climate change purposes (ICF indicator).	1,603	1,283

“Mobilisation” is capital leveraged by FSD Africa from the private sector, including investment by funds in which FSD Africa investees and companies in which those funds invest. “Catalysation” refers to private investment which follow technical assistance or grant support, for which a credible link is made.

During this reporting period, FSD Africa mobilised and catalysed an additional £213 million to bring the total to £1.283 billion.
	Cumulative (2017-Mar 2025) (£ million)
	Non-ICF	ICF	Total
Mobilised	£681	£178	£859
Catalysed	£153	£271	£425
Total	£834	£449	£1,283

The largest contribution during this reporting period was from Transform Health Fund (£98m), Persistent Energy (£45m) and ESX (£30m). Several interventions contributed to this indicator for the first time, including Spark Energy (£20m), Nithio (£8.8m), LCARP III (£3m) and Prado power (£0.917m) under InfraCredit.
While the progress is gradual, several interventions are in the early stages of implementation and are expected to majorly contribute to the indicator towards the end of the programme. These include Universal Climate Resilience (UCR), Carbon Accelerator Programme for the Environment (CAPE), Buyers Pre-Finance Platform for Nature-Based Solution and West Africa Blue.

36% of the capital mobilised and catalysed to date are from green interventions, including Persistent Energy, Spark Energy, Catalyst Fund, Nithio, ACV and the green bonds. While non-green interventions have contributed a higher percentage (64%) of capital mobilised/catalysed, there is a strong pipeline expected to contribute to green capital mobilisation/catalysation including the green bonds, as shown in the table below:

Intervention/Transaction	Green/non-Green
Universal Climate Resilience	Green
Carbon Accelerator Programme for the Environment (CAPE)	Green
Buyers Pre-Finance Platform for Nature-Based Solution	Green
Pan-African Fund Managers’ Initiative (PAFMI)	Non-Green
West Africa Blue	Green
EABX Market Development Fund	Non-Green
ARM Harith	Non-Green
Kenya SME Listed Fund	Non-Green
The African Climate Acceleration Fund (ACAF)	Green
Technical Assistance for a green securitisation transaction in Kenya - Kaleidofin	Green
Mobilising Insurance Capital for Africa's Green Investments (MICA)	Green
SME Listed Fund - Kenya, Rwanda, Tanzania	Non-Green
Lagos State Bond Issuance	Green Bond
3rd issuance of Sovereign Nigeria	Green Bond
Morocco GPC	Green Bond
Kenya Sovereign Issuance	Debt sustainability (SLL)
Tanzania Sovereign Issuance	Sustainable Bond
EPZA Tz - Bagamoyo	Green REITs
Sosai Gender Bond	Gender Bond
Decima	Green Sukuk
People's Bank of Zanzibar (PBZ) blue bond	Blue Bond
Kaleidofin Securitisation	Green Bond

Cumulative capital mobilised and catalysed to date:
Capital Mobilised vs Catalysed (£m)
Capital Mobilised
Capital Catalysed
Cumulative Capial Mobilised vs Catalysed by Non-ICF vs ICF
## Annex E: Closed Transactions
The table below shows the breakdown of the 27 closed transactions, 15 of the total transactions were issued in local currency:

No	Transaction	Country	Currency issued	Amount raised (currency issued)	Amount in GBP (£m)
1	EnVolt Green Bond in Mauritius	Mauritius	Local Currency	MUR 510 million	9.10
2	CRDB Green Bond (Tanzania)	Tanzania	Local Currency	TZS 172 billion	56.55
3	NMB Sustainable Bond (Tanzania)	Tanzania	Local Currency	TZS 212.9 billion	69.26
4	North South Power Green Bond	Nigeria	Local Currency	₦6.33 billion	11.04
5	OneWattSolar Green Bond	Nigeria	Local Currency	₦3 billion	5.23
6	NMB Gender Bond	Tanzania	Local Currency	TZS 74.27 billion	26.00
7	Morocco ONCF Green Bond	Morocco	Local Currency	MAD 1billion	80.00
8	Morocco Gender Bond	Morocco	Local Currency	MAD 200 million	16.00
9	International Housing Solutions (IHS)	Kenya	Local Currency	KES 13.87 billion	80.00
10	Darway Coast Nigeria LTD	Nigeria	Local Currency	₦1.6 billion	3.02
11	Hotspot Limited	Nigeria	Local Currency	₦1.9 billion	2.03
12	ACOB Lighting Technology	Nigeria	Local Currency	₦1.5 billion	1.31
13	Tanga Uwasa	Tanzania	Local Currency	TZS 53.12 billion	16.69
14	Ethiopia Securities Exchange (ESX)	Ethiopia	Local Currency	ETB9 billion	51.00
15	Prado Power	Nigeria	Local Currency	₦1.95 billion	0.92
16	ImFact	Kenya	USD	$6.53 million	5.06
17	Nithio	Kenya,Nigeria, Uganda, Tanzania,DRC	USD	$11.2 million	8.8
18	Persistent Energy	Tanzania, Ghana, Nigeria, Kenya, South Africa, Angola, Burkina Faso,	USD	$68 million	53.4
19	Nyala Facility	Nigeria, Senegal, South Africa	GBP/USD/EUR	$15.99 million	12.39
20	ACV Fiscal C-DEL	Kenya, Rwanda, South Africa	USD	$1.77 million	1.37
21	Catalyst Fund	Nigeria, Ethiopia, Ghana, Kenya, South Africa, Egypt, Senegal	USD	$18.45 million	14.30
22	Transform Health Fund	Kenya, Rwanda, Tanzania Côte d’Ivoire, Togo, Burkina Faso, Mali, Uganda	USD	$126.42 million	98
23	Spark Energy	Uganda, Kenya, South Africa	USD	$25.80 million	20
24	Cavex	Kenya, Senegal	USD	$0.00225 million	0.00174
25	Burn Manufacturing	Kenya	USD	$10.45 million	8.10
26	Acre Export Finance Fund 1	Angola	USD	N/A	N/A
27	RSBF – InfraCredit	Nigeria	USD	N/A	N/A
Total					649.57