## Annual Review Template

Title: Girls and Out of School Children: Action for Learning (GOAL)
Programme Value £ (full life): £130 million		Review date: 09 February 2026
Programme Code: 205246	AMP start date: / 09 February 2023	AMP end date: / 31 August 2028

Summary of Programme Performance
Year	23/24	24/25	25/26
Overall Output Score	B	A	B
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	DevTracker Programme GB-1-205246 Documents (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-1-205246 Documents (fcdo.gov.uk)

Acronyms
AGA	Accountable Grant Arrangement	MOU / MTs	Memorandum of Understanding / Master Trainers
B-TAG / BERs	Bridging Technical Assistance for Governments / Budget Execution Reports	NGOs	Non-governmental organisations
CPD / CLP / DPD	Continuous Professional Development / Catch-up Learning Programme / Directorate of Professional Development	NRSP / NOC / ODA	National Rural Support Programme / No Objection Certificate / Official Development Assistance
DARE	Data and Research in Education Programme	PRO	Programme Responsible Owner
EBex / PECTAA	Education Budget Excellence Unit / Punjab Education, Curriculum, Training and Assessment Authority	PPP / PMIU / PEA	Public Private Partnership / Programme Monitoring and Implementation Unit / Political Economy Analysis
FCDO	Foreign, Commonwealth and Development Office	QAED	Quaid-e-Azam Academy for Educational Development
GOAL	Girls and Out-of-School Children: Action for Learning Programme	RSPN	Rural Support Programme Network
GPE	Global Partnership for Education	SEDU / SRSP	School Education Delivery Unit / Sarhad Rural Support Programme
ICF	International Climate Finance	SBA	School-Based Assessment
I-SAPS	Institute of Social and Policy Sciences	SRO	Senior Responsible Owner
KP	Khyber Pakhtunkhwa	SED / SDPI	School Education Department / Sustainable Development Policy
KPIs	Key Performance Indicators	TA / TaRL	Technical Assistance / Teaching at the Right Level
MG -COT	Multigrade Classroom Observation Tool	ToC	Theory of Change
MEL	Monitoring, Evaluation and Learning	VfM	Value for Money

A. SUMMARY AND OVERVIEW

Description of the programme
The Girls and Out-of-School Children: Action for Learning (GOAL) programme supports the provincial governments of Punjab and Khyber Pakhtunkhwa to build inclusive education systems, especially for girls and the most marginalised children. The context for GOAL continues to be challenging. Learning Poverty stands at 77 percent which means that there is not only huge deprivation from access to schooling, but those in school are not learning enough either. Public spending on education remains low at an historical average around 2 percent or less. compared to the global norm of 4-6%. Pakistan will struggle to achieve high levels of productivity and sustainable growth unless its young population completes at least a basic education that enables them to progress through higher grades and gain employable skills in the economy.

The GOAL Business Case was ambitious in scope with a focus across the full spectrum of school education systems, with a lifetime budget of £130m until August 2028. Currently, the active components in GOAL include: (1) a safe return of children to learning in floods-affected areas until March 2026; (2) a bridging technical assistance to governments (B-TAG) until June 2026, and (3) ILMpact, an innovative model for catch up and remedial learning in government schools in 15 districts of Punjab and Khyber Pakhtunkhwa until August 2027. More details are provided in Annex A. Procurements of the long-term Technical Assistance (TA), and monitoring and evaluation (M&E) components have yet to be completed; this aspect is discussed in detail in the Commercial section.

Since February 2025, GOAL has been streamlined and adapted in light of the Ministerial decisions related to the Official Development Assistance (ODA), the new Modern Development principles, and the UK-Pakistan cooperation portfolio strategy. The programme will see a reduction in the lifetime budget;[1] an enhanced focus on foundational learning, quality of teachers and teaching methods, and education finance. The five outputs have been streamlined into three to reflect this shift, further details are provided in Section B, paragraph 10. GOAL is already transitioning out of service delivery, with Technical Assistance being the major vehicle for systems strengthening and helping the governments to mobilise and use their own resources more effectively. Most of these changes are reflected in this annual review and have affected the pace of delivery and procurements during the review period.
[1] The lifetime budget is expected to be reduced from £130m to £56m, but this is subject to confirmation through the Spending Review decisions.

About changes to UK ODA:
1. At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
2. The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
3. ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
4. We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
5. The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

Summary supporting narrative for the overall score in this review

Overall, the GOAL programme moderately did not meet expectations and scored a B. Although most of the milestones met expectations, the first two outputs scored an overall B because GOAL’s progress on commercial aspects and ILMpact did not meet expectations. Procurement of the long-term TA component had to be cancelled as it was no longer viable in light of the ODA changes described above. This was an unexpected outcome, with knock-on effects on the pace and stability of the TA component’s direction. In addition, the reduction of the ILMpact budget led to a delayed start. Programme management and quality of work challenges have also emerged due to a complex delivery structure with a large number of partners with overlapping roles. Progress on two milestones related to professional development of teachers (output 1) and teacher licensing (output 2) remained slow, and hence, the milestones were not fully achieved.

Despite these challenges, progress was satisfactory on a majority of milestones. Six out of 18 milestones scored an A+ (exceeded expectations), eight scored an A (met expectation), and four scored a B (moderately did not meet expectation). GOAL continued to support some of the most marginalised children in Punjab and Khyber Pakhtunkhwa. This also included humanitarian work in schools in Sindh. Key highlights of achievements are outlined below:
  1. GOAL continued to work collaboratively with the governments of Khyber Pakhtunkhwa and Punjab in the review period. Through ILMpact, this included reflecting government priorities in district selection. Through humanitarian assistance, following 2025 monsoon flooding, this included responsive programme design and district section – five from KP given the scale of flood damage to schools there and two from Punjab. Through BTAG, this partnership worked across the system in both provinces and included inter-provincial exchanges, particularly on teacher licensing regime designs. This was evident in the learning exchange GOAL facilitated in Sindh, joint-planning on Matric-Tech programming in both education departments, and parallel reviews and follow-up actions on Education Budget Excellence (EBex) units in both provinces.
  2. GOAL also measurably improved learning across intervention schools, influenced policy design and uptake in both provinces, and continued to support government priorities in education.
  3. Learning support, including teacher training, learning materials provision, and reading corners in schools, for 74,537 marginalised students (59% girls) and rehabilitation of 364 schools in flood-affected areas at a cost of £66 per child, compared to the previous estimate of £98 per child. 43,373 girls were re-enrolled in these schools. The percentage of students scoring in the ‘good’ range increased from 36% to 69% in KP and from 48% to 90% in Punjab.
  4. TA-led reforms in Punjab’s School Councils Policy increased the spending limits for civil works from Rs.0.4 million to Rs.2.5 million. This is enabling school councils to lead civil works under appropriate supervision and standards, but with lower costs – for example cost per classroom went from PKR 4.2 million to PKR 1.35 million. This is a good example of how policy TA can create conditions for efficiency in public spending.
  5. TA-led reforms also supported the revision of Parent Teacher Council Guides 2025 in Khyber Pakhtunkhwa. The updated guidelines include an enhanced mandate of PTCs inclusive of creating gender-responsive learning environments, child protection, monitoring teacher performance and disseminating information on government incentives/resources for education in communities. The guidelines also include a higher spending limit of 7 million PKR per year, subject to approvals and checks.
  6. 24,000 students in over 900 government schools received remediation learning. This low-resource pilot utilised the government’s own teachers and delivered targeted instruction support. During the current review period, instruction time was doubled. Endline assessments showed between 13-18.5% improvements on average for students across three subjects – Urdu, English, and Maths.
  7. The TA team has set up a Delivery Unit within the School Education Department. The Unit will use government’s own data to track progress on the Chief Minister’s key reforms and enable the Minister and senior leadership to remove bottlenecks. The aim is to build the structure and capacity for ownership by the Department. Progress through the School Education Delivery Unit (SEDU) is expected in the first two quarters of 2026.
  8. Good progress has been made to enhance TA’s focus on education finance. This includes a research study on innovative education financing and setting up of Budget Excellence Units (EBex) in the two provinces. These units will act as the hub for analytical leadership for public financial management reforms for school education budgets. Two Budget Execution Reports (BERs) have already been produced. These BERs have already resulted in identification of utilisation bottlenecks and government action to resolve them.
  9. ILMpact brought innovation to tracking of learning in Khyber Pakhtunkhwa and Punjab. This was done using digitised data collection feeding into a publicly accessible dashboard showing student learning levels and journeys at the individual level while still ensuring data protection of students. The use of digitised data collection also improved reporting and reduced transaction costs. Progress to embed this into the system is expected in the following review period.
Major lessons and recommendations for the year ahead
The previous Annual Review made seven recommendations. Four of these are on track, one is delayed (theory of change refresh), one is completed, and two are not completed due to changes in ODA and procurement directions. The ToC refresh was delayed due to the time required for pivoting GOAL in line with ODA cuts and evolution of a modern UK-Pakistan partnership. However, it was completed as part of the review process (Annex B). The recommendations on TA procurement and onboarding of third-party MEL partner are not completed, but plans are underway. Detailed recommendations tracker inclusive of output specific recommendations from the previous review period are added in Annex C.

Key lessons learned from this period include:
  1. Working with the political context secures government buy-in. Collectively, more frequent and direct engagement with senior government counterparts helped identify potential blockers early and kept the FCDO GOAL team more informed of government priorities.
    1. Progress on empowering school councils and introducing teacher licensing in Punjab are not new as part of FCDO support. However, the government’s response has been much more positive. The difference was the political context – the government of Punjab wanted to build additional classrooms and repair infrastructure across the province. The policy reforms proposal delivered what the government exactly wanted, and hence, it was easier to secure political support and approvals. Similarly, on teacher licensing, the Education Minister of Punjab was disappointed with board examination results and engaged with the public on this. This provided an opportunity to bring this reform back onto the table.
    2. In Khyber Pakhtunkhwa, frequent engagement with the Education Minister, Advisor to the Minister, and Secretary enabled inter-provincial knowledge-transfer, updated Parent-Teacher Council guidelines, and better information-exchange among development partners. Travelling to Peshawar remained a challenge, however, the team continued to meet KP counterparts in Islamabad and travelled to green districts such as Mansehra and Abbottabad to visit schools and engage teachers, PTCs, and district officials.
  1. Regular consultation with other development partners is vital. This will enable FCDO and trusted development partners to be consistent in messaging, aligning and distributing work on key priorities, and sharing key evidence/lessons learned frequently. This will further strengthen FCDO’s own education portfolio, avoid duplication of resources, and identify opportunities to fill gaps and build complementarities in future programme design. An example of avoiding duplication during this review period includes finalising work on innovative financing. DARE and GOAL team members collaborated closely to identify potential overlap and repetition in a key stream of work. Through more external consultations, it became clear that both bilateral assistance programmes had to pivot planning considerably, and that there are opportunities for collaboration and better impact across partners.
  2. Long delivery chains and overlapping roles between downstream partners creates cumbersome interdependencies. This is the case particularly where technical and delivery responsibilities intersect. These complexities often lead to implementation delays, disproportionate allocation of programme management and technical time, and weak accountability along the delivery chain.
  3. Locally led partners demonstrate strong agility by responding quickly to emerging and shifting priorities. Their ability to scale up immediately, combined with a deep understanding of local context, culture, and political dynamics, enables them to deliver effectively and ensure strong value for money. Leveraging local expertise during programme design and implementation can significantly enhance responsiveness, efficiency, and impact.

1. Key recommendations from this review are as follows:
    1. Prioritise procurement of new TA supplier: The FCDO team should work closely with the commercial team to streamline procurement of the TA before the interim arrangement comes to an end in June 2026. The team should also put in place options to avoid a gap in TA and manage the risks of any delays in the procurement (GOAL SRO and PRO, June 2026).
    2. Transition out of Service Delivery: This process needs to be undertaken as soon as possible in like with the UK ministerial steers. Instead, interventions should take a system-strengthening approach, building government institutional capacity to design and sustain reform for the long term (GOAL SRO, ILMpact team, April 2026).
    3. Pivot the ILMpact’s thematic focus and delivery structure to align with the UK’s Modern Development Partnership principles. ILMpact should focus on its niche thematic areas with a clear TA strategy for the government to adopt and take the learning innovation to scale. The simplification process should focus on teaching and learning in affordable ways, gathering essential cost and building evidence for success. The number of delivery partners should also be reduced to minimise complexity (FCDO and British Council GOAL SROs, April 2026).
    4. Strengthen the ILMpact component’s performance: ILMpact has faced challenges in partner-management, human resource planning, and quality of materials produced. Clear plans for quality assurance and performance management must be made and tracked for the following review period. Section 2 provides more specific observations regarding this. (GOAL SRO, Education Adviser, ILMpact team, June 2026).
    5. Mainstream climate and resilience in GOAL’s systems strengthening TA. This focus is essential to ensure inclusion and continuity of education for marginalised children in climate-vulnerable districts. The programme’s support so far has achieved good results in terms of increases in enrolment, inclusion, and learning gains at £66.30 per child. Continued coordination with the Education Cannot Wait (centrally managed programme), experience from floods-response work and TA related to the climate resilience should inform the scope of work of future TA (Lead Advisor and SRO GOAL, May 2026).
    6. Provide targeted training to partners on resource accounting and forecasting and maintain monthly financial and delivery reviews with all implementing partners. (PRO GOAL, March 2026).
    7. Work in partnership with the FCDO governance team in Pakistan and utilise central FCDO offers to strengthen Public Financial Management TA to government (GOAL SRO, PRO, April 2026).
    8. Work with the Operational Excellence team to strengthen the GOAL Logframe and set more rigorous milestones (PRO GOAL, June 2026).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme’s impact statement is as follows: More inclusive provincial education systems delivering better quality education. Two outcomes will contribute to this impact, namely (a) improved teaching and learning, and (b) increased access to education for girls and marginalised children. The GOAL theory of change stipulates that if challenges and barriers to access for girls and marginalised children are addressed and learning quality is improved through teaching and learning interventions, then the impact statement can be actualised. The original theory of change described five pathways and outputs to do this:

  1. Reduced barriers and schooling costs for girls and marginalised children
  2. Increased awareness and prioritisation of education
  3. Improved teacher knowledge, skills, and classroom practice
  4. Learning facilitated through quality resources and guided by assessments
  5. Improved planning and management at the school, district and provincial level.

Following a review preceding the Annual Review process and strategic shifts following ODA decisions, these were consolidated into three outputs as follows:

  1. Improved planning and management at the school, district and provincial level
  2. Improved teacher knowledge, skills, and classroom practice
  3. Reduced barriers and schooling costs for girls and marginalised children

Key assumptions underpinning the Theory of Change are still relevant such as reduced financing governance challenges, and the link between learning quality and access. However, the scope of activities was aligned with principles of Modern Development Partnerships and UK government’s latest priorities and approved ways of working. Pathways to impact also need to be streamlined given tighter budgets and timelines.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to deliver system reforms (see paragraph 6 for examples). However, the pace has remained slower than anticipated in this year. The bridging TA was not originally designed for an extended duration; integration of reforms into government systems was envisaged through the long-term TA, which has been significantly delayed due to procurement challenges. Moreover, ILMpact had a protracted inception phase and a slow start to implementation due to the complexity of its delivery structure, delays in government approvals, and ODA uncertainty. Uncertainty and conflict in KP’s merged areas was a contributing factor which led to a delay in district selection as well.

The GOAL Business Case also includes outreach targets. Progress against them is as follows:

  1. 250,000 marginalised children supported to enrol and stay in school: GOAL will exceed this target and reach approximately 431,000 children by August 2028. Out of this, humanitarian assistance has already benefitted 165,000 children in flood-affected areas. Bridging TA has delivered learning pilots which have reached an additional 200,000 students. ILMpact will benefit 66,000 children. A caveat for these numbers is that the duration of learning support varies and is not for full academic year in all cases.
  1. 150,000 girls supported to read by age 10. This target is off-track and at risk due to ODA cuts and the shift away from service delivery. The current plan is to support 88,000 girls with remedial learning support. The team is working with the implementing partners to fast-track progress.

The key outcome for GOAL is enabling better quality of teaching and learning in government school classrooms of Khyber Pakhtunkhwa and Punjab. While the programme is making progress against this outcome, sustaining reforms undertaken will require more time and more frequent engagement across the high and middle tiers of education governance. Getting long-term TA arrangements in place will be critical to achieving this.

The secondary outcome for GOAL is enabling access to school for the most marginalised. Progress against this outcome is on-track, with BTAG (until March 2025) and ILMpact providing remediation learning support and working to institutionalise inclusive pedagogical practices with both provincial governments. The Data and Research in Education (DARE) programme has also contributed to this outcome with better data protection, inclusion of four Washington Group functional disability questions in the Annual School Census, and the approval of the Data Standardisation framework in 2023.

On-going work is focused on sharpening the technical focus on key reform areas where government’s appetite to adopt and scale is evident. This includes two key steams of work. First, strengthening delivery of quality learning through the existing teaching workforce, capacity building of the Directorate of Professional Development (DPD) in Khyber Pakhtunkhwa and the Punjab Education Curriculum Training and Assessment Authority (PECTAA). Second, expanding the pool of domestically available resources available to the government for education and improving the management of existing resources. It is critical that the implications of the revised focus and new approach feed through to the delivery partners as well as government and inform the way they operate during the remainder of GOAL and for the longer term.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Despite challenges, GOAL is achieving good results and is positively influencing policy discourse in KP and Punjab in areas of teaching methods, school councils, multi-grade teaching, professional development of teachers, and public financial management. The programme is also responding quickly to political opportunities and interests. Work on school councils and teacher licensing is a good example. The ongoing efforts to sharpen the technical focus and rationalise the delivery model provide sufficient evidence that the programme continues to represent good value for money.

## C. DETAILED OUTPUT SCORING

Output Title	Improved planning and management at the school, district and provincial level
Output number:		1	Output Score:	B
Impact weighting (%):		50	Weighting revised since last AR.	Yes -up from 15% to 50%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Institutional capacity of KP and Punjab education departments to undertake budget review and analysis.	i. Education Budget Excellence Unit (EBex) KP notified and meeting quarterly to conduct reviews of budget and utilisation.	Achieved. (A). (EBex) established, notified, and two meetings convened.
	ii. EBex Punjab functions outlined and shared with SED for feedback.	Achieved. (A) The Unit has been set up, produced budget analysis, and is leading to decisions.
1.2 Number of schools/districts introducing innovative models for school governance	i. Establishing a School Education Delivery Unit (SEDU) – Enabling Reform Tracking and Strategic Coordination within SED Punjab.	Achieved. (A) SEDU has been launched.
	ii. Policy drafted and accepted by government for increased financial allocations for School Management Councils[2] (SMCs) in Punjab and Parent-Teacher Councils (PTCs) in Khyber Pakhtunkhwa (KP)	Achieved. (A) Policy approved by education department and received cabinet approval in Punjab. Policy for KP has been approved by education department.
	iii. One Budget Execution Review cycle per province completed and findings shared with provincial education departments.	Achieved. (A) BER completed and accepted by government in Punjab and KP.
	iv. Selection for implementation of ILMpact in 350 schools in 13 districts completed. Punjab: 200 / KP:150	Achieved, (A)353 schools selected with government approval (203 Punjab, 150 KP) across 13 districts
1.3 Teachers professional development departments at provincial and districts level strengthened to deliver better quality teacher support.	i. Recommendations for revising Multigrade Teacher Support Programme digital content, based on teacher feedback, developed and submitted to department	Achieved. (A) / Recommendations shared with government in addition to Technical Assistance (TA) support to implement.
	ii. Classroom Observation Tool (COT) for teachers in Multigrade classrooms updated and approved by government.	Partially achieved. (B) COT updated following FCDO feedback and shared with government. Not yet approved.
	iii. 150 Master Trainers (MTs) of 15 Provincial and District Education Departments trained on remedial and catch-up learning	Partially achieved. (B) 123 (89 MTs in Punjab and 34 in KP) trained across 15 districts.
[2] School management councils are called School Councils in Punjab and Parent Teacher Councils in KP. Their functions are the same across Pakistan with minor differences in governing policies.

Briefly describe the output’s activities and provide supporting narrative for the score.

19.	This output is designed to improve governance and institutional capacity within the provincial education systems of Khyber Pakhtunkhwa and Punjab. The milestones for this year focused on public financial management, empowerment of parent-teacher councils, and continuous professional development (CPD). Substantive progress was achieved across this output, notably on setting up Budget Excellence Units for the first time in both provinces and influencing the financial powers of School Councils in Punjab. The TA team also made progress on multi-grade teaching reforms; however, an oversight related to collection of learning data was observed towards the end of the review period and government approval was delayed. The milestone related to teacher training was only partially achieved. This was due to a delay in approvals from the provincial governments – in Punjab this was due to a concern around misalignment with the academic calendar and in KP this was due to delays in Non-Objection Certificates (NOCs). Although most of the milestones scored an A, the overall score for this output is a B because two important milestones about professional development of teachers were missed. Another main reason for this score is the slippage of the TA procurement timelines. Although there is no indicator on this in the log-frame, completion of this procurement was expected during this review period.

20.	Output indicator 1.1 focused on improved public financial management. As explained above, GOAL is being pivoted to support the provincial governments use their own resources better to achieve more efficiency and impact. A key intervention was to set up new Budget Excellence Units to review budgets so that the leadership could review the efficacy of allocations, timely budget releases and spending on development schemes. The objective is to institutionalise these functions within each department within the project life cycle. Both units have been set up and have produced the first batch of budget analyses. In Punjab, the analysis identified that only 15% of Rs 100 billion Development Budget was utilised in five months. In KP, the utilisation rate was 17%. This has enabled the respective education secretaries to issue instructions to address bottlenecks to accelerate budget releases. This is an indication of early wins as a result of setting up these units.

21.	Output indicator 1.2 tracks TA interventions that promote innovative models for school governance. In this year, the milestones included the establishment of a Delivery Unit within the School Education Department of Punjab, more empowered school management committees, Budget Execution Reviews (BERs), and scaling-up of an innovation in remedial learning in public schools. A brief description of progress against each milestone is provided below.

  1. School Education Delivery Unit (SEDU): SEDU has been established as a lean structure within the School Education Department in Punjab to institutionalise promising reform undertaken by GOAL’s bridging TA, support common priorities of the Punjab government and FCDO in education, and to add rigour through use of evidence and monitoring for key Chief Minister’s initiatives in education. During this review period, SEDU was collaboratively designed with government ownership and buy-in and notified despite a challenging context and timelines.
  2. School Management Councils: GOAL’s bridging TA was integral in drafting, influencing, and gaining approval of the update School Councils Policy in Punjab, resulting in increased spending powers, including an annual budget of 2.5 million PKR from the earlier 400,000 PKR. In KP, the TA improved the Parent Teacher Council guidelines by strengthening the gender and inclusion functions with a financial power being up to 7 million PKR per year. These are important gains, given lessons learned from earlier programming, such as through GOAL’s humanitarian support, which proved that work completed through school management councils is more cost-effective, quicker, and better quality.
  3. Budget Execution Reviews: This set of milestones focuses on reviewing recurrent and development spending and funding flows. The analysis is used by the Education Department’s leadership to enable efficient spending of the government’s existing resources and remove bottlenecks in release of funds or implementation.
  4. Remedial Learning Innovation through ILMpact: This milestone was about finalisation of schools for the ILMpact intervention, at least 353, within the review period. British Council navigated complex challenges using provincial steering committees, flexible preferences (within FCDO’s criteria), transparent and rapid data sharing, and responsiveness to emerging government needs. This milestone directly supports FCDO’s commitments on foundational learning and aligns with provincial Foundational Learning policies, enabling government to prioritise marginalised children.

22.	Output Indicator 1.3 measured GOAL’s support for multi-grade teaching and their ability to deliver instruction according to children’s learning needs. This output needs improvement—both in meeting milestones and ensuring coherence—so that GOAL’s support aligns better with government learning priorities. Currently, learning improvement is a part of all three GOAL components. However, coordination and learning across components needs to improve so the overall ‘GOAL offer on learning’ is more coherent.
Multi-grade teaching is central to Teacher Professional Development in KP and Punjab where over 80% of primary schools operate in this mode. While mono-grade classrooms are ideal, financial constraints make them unrealistic even in the long-term. Below is a brief update on progress against each milestone.

a.	Multigrade Teacher Support Programme: This piece of work is preceded by policy work under the UK-funded KP and Punjab Education Support Programmes, provincial situation analyses under GOAL during 2023-24, and teacher training modules and academic tools development and implementation for over 29,000 primary school teachers. The teaching resources were peer reviewed by six Focus Groups of 275 teachers before finalisation to ensure they were fit for purpose. The recommendations finalisation was informed by all preceding work, the focus groups, as well as a two-tiered classroom observation strategy – first, the government’s own mentors (AEOs and School Leaders in KP, Head Teachers in Punjab) and second, independent BTAG supported observers.
b.	Classroom Observation Tool (COT) for teachers in multigrade classrooms updated and approved by government: Prior to GOAL support, government system observers were using mono-grade classroom observation tools to observe, score, and debrief teachers in multigrade settings. GOAL technical assistance support enabled this tool to be adapted, tested, and finalised in partnership with the government. The tool is awaiting formal government approval – finalisation took longer due to learning indicators not being adequately incorporated in initial versions. A MEL framework to ensure rigour was also developed for this tool.
c.	Catch-up/remedial learning training: 123 Master Trainers against a target of 150 were trained during the review period. These Master Trainers went on to train over 1,350 teachers. The shortfall of 27 Master Trainers was due to the delay in finalisation of districts in KP. Training support included remedial learning through teaching at the right level (TaRL), targeted instruction, and inclusive teaching practices. These enabled teachers to start implementation of Catch-Up learning with newly enrolled students of grades 1-2 as well as Remedial Learning for grades 3-6.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

We have consolidated GOAL outputs, including Output 1, due to re-prioritisation in line with ODA cuts. The five outputs have been reduced to three. Previously, Output 1 was ‘reduced barriers and schooling costs for girls and marginalised children’. This has been de-prioritised in favour of an enhanced focus on learning and system-strengthening support for the education departments in Khyber Pakhtunkhwa and Punjab. The weightage for this output has increased from 15% to 50%.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The last Annual Review made four recommendations for Output 1. The recommendation around locally hired staff through downstream partners for more efficient delivery was completed impacting the Safe Return to Learning component as well as ILMpact. The recommendation around accelerating innovation in PPPs and enabling government to explore innovations such as impact bonds is being explored as part of the scope for the long-term TA. The recommendation on informing Education Cannot Wait (ECW) work through GOAL’s humanitarian assistance was completed with representation from FCDO and respective implementing partners on all steering committee meetings. The final recommendation was also completed – GOAL results are included in the overall humanitarian results at the mission level.

The key lesson learned is that being adaptive and available in terms of support to government is crucial to a positive relationship with important stakeholders. FCDO’s education team increased the frequency of visits and in-person meetings with government during this review period. Additionally, having embedded TA in both provincial education departments enabled FCDO to respond positively to additional support the government needed, and this has strengthened relationships with government beyond just GOAL-specific work. For example, the Punjab Education Minister asked for support to align teacher training materials to student learning outcomes defined in the curriculum. The bridging TA was able to provide this support. This also enabled FCDO to push through approvals within its core remit.

1. Key recommendations for Output 1 include:
  1. Manage the risk of remit diversion: The SEDU and EBex units have excellent potential to contribute to GOAL’s impact statement long-term. However, if their staff is overtasked, then it will reduce their potential impact. Both risks need to be managed early through close collaboration with the government (GOAL Lead Advisor and SRO, on-going)
  2. Bring more coherence in similar workstreams: All the three GOAL component implementing partners are providing teacher training support in their respective areas. There needs to be a more integrated approach for cohesive messaging to government on institutionalising teacher professional development support across partners (GOAL Lead Advisor and SRO GOAL, ILMpact and B-TAG partners, May 2026).
  3. Focus on implementation of Foundational Learning Policies in the Delivery Unit and Education Budget Excellence Units. This will ensure that progress is being tracked and presented to the senior leadership for adequate resource allocation and implementation (GOAL SRO, March 2026).
  4. Track the decisions from Budget Execution Reviews. EBex functions have started to provide early wins – findings and decisions following reviews need to be tracked and documented to ensure progress (B-TAG, on-going).

Output Title	Improved teacher knowledge, skills, and classroom practice
Output number:		2	Output Score:	B
Impact weighting (%):		40	Weighting revised since last AR.	Yes – up from 10% to 40%.

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of policies and strategies co-developed with provincial governments, strengthening Teachers Professional Development.	i. Political Economy Analysis (PEA) for teachers' licencing and certification conducted and approved by FCDO for both KP and Punjab.	Partially achieved. (B) First drafts received, not approved yet.
	ii. Public Private Partnership policy developed for Punjab and approved by the government.	Achieved. (A) Policy developed and approved by government.
2.2 Number of teachers trained to deliver project supported innovative learning models.	i. 6,209 teachers participated in the Continuous Professional Development - Elementary programme in Punjab and KP. / Punjab: 3194 (M: 1194, F: 2000) / KP: 3015 (M: 1599, F: 1416)	Achieved. (A) 6,209 teachers participated in CPD Elementary. Gender and provincial targets met.
	ii. 90 teachers across 90 schools (30 Punjab, 60 KP) complete training on LittleLab (AI supported tool to improve Foundational Learning)	Achieved. (A) 90 teachers from 90 schools trained on the AI intervention. Provincial target also met.
	iii. 1200 (516 male, 684 female) teachers trained in improved pedagogical practices.	Achieved. (A) 1,922 teachers (812 male and 1,110 female) trained
	iv. 800 teachers to receive training for ILMpact	Achieved. (A) / 1,352 teachers (852 Punjab and 500 KP) trained

Briefly describe the output’s activities and provide supporting narrative for the score.

1. This output focuses on improved teaching and learning in government school classrooms. During the review period, some progress was made against this output including technical assistance for developing new policies and capacity building focussed on knowledge, skills and professionalisation of teachers in Punjab and Khyber Pakhtunkhwa. Although the majority of milestones against Output 2 were achieved, the focus has remained on teacher trainings during the review period. Five out of six milestones were achieved, but the overall score is a B. Progress on teacher licensing, a crucial reform, has remained slower than expected. This output also includes interventions which were part of ILMpact. This component has not met expectations due to delays, high forecast variances, and management challenges as is trailed in the summary section.
2. Notably, both governments of Khyber Pakhtunkhwa and Punjab expression apprehensions on the value add of development partner teacher support. KP counterparts also referred to data indicating low teacher content knowledge[3]. In contrast, both counterparts, especially in the relevant departments expressed satisfaction with GOAL interventions. Overall, coherence on this output and communication of the overall GOAL teaching and learning offer needs to improve.
  [3] Teacher Content Knowledge - Pakistan - Khyber Pakhtunkhwa Province | Global Education Policy Dashboard

1. Output indicator 2.1 tracks progress on reforms related to teachers and professional development in both KP and Punjab Progress is being made on teacher licensing, a vital reform to make professional teachers available in the system. GOAL enabled two policy exchanges – an exposure visit to Sindh to learn from their experience as well as a consultation on best practice in Punjab. A brief description of progress against each milestone is provided below.
  1. Political Economy Analysis (PEA) for teacher licensing in KP and Punjab: These use the Thinking and Working Politically (TWP) lens considering structures, agency and rules based on past reform and roll-out, incentive structures, and global examples where teacher licensing regimes impacted quality of learning and where they did not. Given collaboration with the governance helpdesk, a higher level of rigour was applied. The analysis is being used to assess trade-offs for different designs of teacher licensing.
  2. PPP policy approval in Punjab: The policy includes leveraging private sector resources and expertise across a range of delivery options, including through innovative financing.

1. Output Indicator 2.2 measures progress on TA interventions that enhance teachers’ capacity to deliver innovative learning practices, including Artificial Intelligence-powered foundational learning, activity-based learning, and targeted instruction. Progress against milestones is described below.
  1. Continuous Professional Development (Elementary): In Khyber Pakhtunkhwa, there were high quality teacher induction and CPD resources through earlier FCDO support. Following KP government’s steer, GOAL was able to step in during the 2023-24 financial year to bridge gaps at the Elementary level. This review period saw additional progress in seven districts, including synchronous and asynchronous learning management systems and teacher feedback, subject-specific training, training of government trainers, and classroom observations. In Punjab, there was a similar gap at the Elementary school level. The approach differed slightly with additional support provided to Head Teachers, enabling them to provide better coaching and feedback to teachers on an ongoing basis.
  2. AI-empowered innovation: Governments of KP and Punjab have been keen to introduce Artificial Intelligence-enabled solutions in classrooms. B-TAG delivered AI-solutions in crowded urban classrooms. Compared to control schools, treatment schools have seen statistically significant progress against 20 development goals that include numeracy, literacy, and soft skills. This also enabled schools to track learning at the individual student level.
  3. Improved pedagogical practices: Teacher training on improved pedagogical practices was a part of the package of humanitarian support to 343 schools. Additional teachers from each school participated in these training sessions, leading the milestone target to be exceeded. Learning gains from this support have been promising, with students in the ‘good’ category increasing from 36% to 69% in KP and 48% to 90% in Punjab.
  4. ILMpact trainings: Following finalisation of teaching and learning resources, and upskilling of government Master Trainers, teacher training sessions were conducted. The initial target for this milestone was conservative at 800 across 400 schools. Training sessions included remedial learning for grades 3-6 in Punjab and 3-5 in KP, catch-up learning for newly enrolled students, and early childhood learning support. Inclusive teaching practices were ensured across all three streams through expert assistance from Sight Savers International and Think Equal.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

We have consolidated all GOAL outputs, including Output 2, due to re-prioritisation in line with ODA cuts. Previously, output 2 was ‘increased awareness and prioritisation of education’. This has been merged into the teaching and learning workstream. This output is now ‘improved teacher knowledge, skills, and classroom practice’. The new combined output has a revised weightage of 40%.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The previous annual review made five recommendations; four of these were completed. The recommendation on empowering women and girls through the Global Partnerships for Education’s (GPE) gender-hardwiring approach is not fully achieved. FCDO’s role as Coordinating Agency for GPE in KP will help accelerate progress.

A key lesson learned is that interventions underway need to be affordable and scalable for the government to be able to implement on their own. Classroom observations in an ILMpact supported school as part of the annual review showed 2-3 teachers per classroom with only 20-25 students. The model will need to evolve considerably to ensure student-teacher ratios are similar to mainstream government school classrooms, and that interventions are scalable within domestic resources. This also means that TA support should continue to prioritise the existing teaching workforce to improve learning levels through existing inputs in the system, most importantly for the Continuous Professional Development and teacher licencing workstreams.

1. There are three recommendations for Output 2.
  1. ILMpact’s model needs to be streamlined to be more affordable and coherent. This means streams of work that are not adoptable by government should be deprioritised. Delivery structure also needs to be simplified, and performance needs to be strengthened as laid out in Section A recommendations (SRO GOAL, ILMpact - British Council, April 2026)
  2. GOAL should work collaboratively with KP and Punjab education departments to rationalise and improve coherence of teacher professional development support. This should include a clear steer on GOAL’s own components and contributions to teachers’ professional development as well as the contribution of Multilateral organisations that the UK contributes to (GPE, UNICEF, and World Bank). This rationalisation should be informed by DARE evidence as it becomes available. (Policy and Partnerships Coordinator GOAL, June 2026).
  3. Public Private Partnership interventions and milestones should move to Output 1 because they fit in the governance and management stream of work. (PRO GOAL, January 2026).

Output Title	Reduced barriers and schooling costs for girls and marginalised children
Output number:		3	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	Yes – reduced from 30% to 10%.

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of girls/marginalised children enrolled/supported through remedial learning and catch-up programmes	i. 15,000 students, with at least 50% girls, across 900 schools in KP and Punjab have received instruction through the remedial learning programme with an increase in learning.	Achieved. (A) 24,000 students supported with measurable learning gains against a target of 15,000. Gender and schools target met as well.
3.2 Number of teachers and parents trained on safeguarding/inclusion and learning activities in KP and Punjab	i. 1,250 (605 male, 645 female) SMC/PTC members capacitated on school governance, community mobilisation	Partially achieved. (B) / 1,050 members trained against a target of 1,250.
	ii. 440 (187 male, 253 female) SMC/PTC members capacitated in provision of psychosocial support for students.	Achieved. (A)760 members trained against a target of 440.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is designed to support the government to reduce access barriers for marginalised children such as due to gender, geography, disability, and socioeconomic background. This output scored an A, with two milestones scoring an A, one scoring a B. The programme made good progress on remedial learning support in low-resource schools, and support to school management committees.

Output indicator 3.1 measures the number of students supported with remedial learning. This support resulted in measurable learning gains across three subjects in both provinces. In Punjab, students’ English scores improved by 14.6%, 16.4% in Urdu, and 18.5% in Maths. In KP, the improvements were 13.2% in English, 11.56% in Urdu, and 13% in Maths. During this review period, the primary contributor to this was B-TAG. Following the onboarding of British Council for ILMpact, the BTAG component was wrapped up in March, and ILMpact will be the primary contributor to this in the next review period.

Output indicator 3.2 tracks progress on management and psychosocial support training sessions with Parent-Teacher and School Management Councils. Progress against each milestone is described below:

  1. School management training: Given the frequency of natural disasters in some of the targeted geographies and the observed impact from 2022 floods, upskilling PTCs/SMCs in schools has been a continued priority. This has enabled council members to enrol previously dropped out and at-risk children to schools. During the review period, additional flooding in some areas especially Sindh led to delays in training and milestone for school management training being under-achieved.
  2. Psychosocial support: This training support has been designed to include psychosocial support for students as well as management support for parents and teachers to enable them to better support students in schools, including newly enrolled and at-risk children.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

All GOAL outputs have been consolidated, including Output 3, due to re-prioritisation in line with ODA cuts. The weightage for this output has been reduced. The programme will not fund direct delivery interventions, and instead, will provide TA for better targeting of government’s own resources to tackle access barriers.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

There was one recommendation that learning levels should be included in school selection criteria. This was completed with ILMpact prioritising schools with low learning levels.

A key lesson learned is about the importance of Social Emotional Learning (SEL). Teachers shared that they observed more engagement from students when this was part of daily lessons. Over time, it led to students being more enthusiastic and ready for learning. Parents also shared that capacity building support helped them feel more empowered and engaged as members of school councils, making longer term membership and engagement more likely.

1. There are three key recommendations from the review period for Output 3.
  1. Role of communities: FCDO should convene a workshop with other development partners and government departments to share results and lessons learned from working with PTCs/SMCs. The design for the upcoming longer-term technical assistance should include alignment and institutionalisation of capacity building resources for school management committees across KP and Punjab (Lead Advisor GOAL, May 2026)
  2. Cost data: ILMpact should collect data on unit costs for providing remedial support and enabling learning gains for students with the highest learning gaps. This data will be vital to build evidence about the cost-effectiveness of the model (ILMpact team, May 2026).
  3. Dissemination of learning: RSPN’ and ILMpact’s work on school safety and safe learning environments should be consolidated in the form of lessons learned and shared with government as well as development partners. (Policy and partnerships coordinator, GOAL, May 2026).

## D: VALUE FOR MONEY

The original VfM proposition in the 2022 GOAL Business Case was based on four dimensions: economy, efficiency, effectiveness, and equity. Under economy, the focus was on reducing unit costs for teacher training, technical assistance, and learning materials without compromising the quality outcomes. Efficiency was defined by lowering the cost of attending school for supported pupils, increasing awareness among families, and training teachers in improved methods. Effectiveness was to be measured through additional enrolment of marginalised children, improvements in literacy and numeracy scores, and enhanced teacher capability. Equity was to be assessed through geographic targeting of disadvantaged districts, gender balance, inclusion of children with disabilities and minorities, and improvements in teacher-pupil ratios and quality measures.

Cost Drivers and Allocative Efficiency
During the reporting period (November 2024 – October 2025), the key cost drivers were post-floods rehabilitation of schools and provision of learning kits under the humanitarian component, consultancy fees for short- and long-term experts engaged through bridging technical assistance and service delivery streams, and management costs including the office setup, rental costs, and project overheads. The humanitarian response activities remained the dominant cost driver, accounting for approximately 46% of the total programme expenditure (£4.94 million). This reflects that the humanitarian response component had reached a mature stage and was operating in full implementation mode during the reporting period

This was followed by bridging technical assistance (B-TAG) at 28% and the ILMpact component at 21%, reflecting the programme’s prioritisation of post-crisis recovery. This allocation indicates the need for balancing urgent restoration of schooling for 74,537 children with investments in long-term system strengthening through a big focus on education finance, institutional strengthening, Continuous Professional Development (CPD), School based assessments (SBA), and AI pilots. This cost structure will change substantially with the closure of the humanitarian component in March 2026, exit of service delivery and an enhanced focus on systems strengthening TA.

Economy: Significant cost savings were achieved across all components. The humanitarian component led by RSPN rehabilitated 364 schools and supported 74,537 marginalised students (59% girls) at a cost of £66.30 per child, compared to the previous estimate of £98 per child, through competitive bidding, bulk procurement, and community-led civil works (20–25% savings against market rates). ILMpact reduced costs through bulk printing and centralised procurement of learning materials, in-house content development, and cascading training models, while digitised MEL systems further lowered the monitoring costs. Additionally, B-TAG successfully embedded delivery within provincial systems such as SEDU. This was complemented by hiring more experienced staff to ensure smooth relationship management.

Efficiency gains were evident through streamlined delivery and adaptive planning. ILMpact trained 123 Master Trainers and 1,352 teachers within two months using a cascading model, digitised data collection improved reporting, and reduced transaction costs. Tools co-developed with governments under B-TAG such as multi-grade classroom observation tool (MG-COT), schools-based assessment (SBA) item banks, and continuous professional development (CPD) modules, facilitated accelerated approval processes, and efficient decision making within government system.

RSPN adopted cluster-based training to maximise the coverage and reduce per capita costs, while modifying its programme design to include Reading Corners and reusable hygiene kits for quicker and more cost-effective delivery. Dynamic efficiency was demonstrated through adaptive measures that reduced costs and accelerated delivery: ILMpact shifted to government training venues, saving 50% on the planned training costs, and digitised MEL tools to cut monitoring expenses; RSPN leveraged ILMpact’s catch-up learning programme (CLP) materials for flood-affected schools, avoiding duplication and reducing per-child cost from £98 to £66.

Effectiveness has been demonstrated through measurable outcomes at scale. RSPN’s humanitarian support enabled thousands of children to return to safe learning environments, complemented by psychosocial support and menstrual hygiene kits that improved girls’ attendance and retention. ILMpact supported the government’s enrolment campaigns and helped enroll 10,365 out-of-school children (64% girls, 7% children with disabilities, and 6% minorities) in Punjab, initiated remedial learning for 20,000 girls, and established 130 STEAM clubs engaging 3,624 girls. Baseline assessments for 9,000 students were completed, with endline planned for March 2026. B-TAG trained over 46,000 educators and reached more than two million learners at low marginal cost, while CPD scale-up improved instructional quality (COT scores rising from 3.46 to 3.95 in Punjab). Innovative pilots under B-TAG, such as AI-enabled learning, improved foundational outcomes by 20 percentage points for 1,268 children, and remedial learning pilots achieved 5–11 percentage point gains in literacy and numeracy for 8,000 students within four weeks. These achievements mainly align with GOAL outcome indicators 1.0 and 2.0.

Equity remains central to GOAL’s design and delivery. ILMpact prioritised out-of-school girls, children with disabilities, and minorities, completing accessibility audits in 100 schools and integrating inclusive pedagogy across interventions. B-TAG reached over 1.05 million girls and 23,000 female teachers and heads, prioritising girls’ schools for remedial learning, CPD, AI-literacy pilots, and climate resilience initiatives. RSPN targeted flood-affected rural districts, ensuring interventions reached the most vulnerable groups, including girls in conservative communities and children with disabilities.
Overall VfM Assessment
Based on this analysis, the GOAL programme continues to represent strong VfM compared to the original business case proposition. Cost savings have been achieved through shared resources, in-house development, and leveraging government systems. Efficiency gains have come from streamlined delivery and adaptive planning. Effectiveness is evidenced by early learning improvements, systemic reforms, and humanitarian reach, while equity targets have been exceeded across all components

On the strength of this evidence, the programme demonstrates good VfM and should proceed as planned. However, while one of GOAL component ILMpact and its partners successfully delivered programme outputs, the office setup and associated overhead costs represent a significant share of management expenditure. These costs could be optimised further to improve VfM through simplifying the delivery chain. In addition, VfM metrics will need to be revisited in light of the enhanced emphasis on systems strengthening TA and exit from service delivery interventions.
E: RISK

Overview of Risk Management
The overall risk rating for the GOAL programme is ‘Major’. The GOAL team maintains a quarterly-updated risk register covering all seven risk categories, with mitigation plans and assigned owners. Programme risks align with BHC Pakistan’s risk appetite. The GOAL programme team tracks delivery through regular review of delivery chain maps, proactive risk discussions with partners and follow-up on due diligence recommendations in monthly and quarterly meetings. Partners report on risks and management effectiveness, while high-impact risks are escalated immediately. All current Due Diligence Assessments remain valid; however, the team has already initiated the work on updating the Due Diligence Assessment of RSPN.
Risk Category	Residual Risk Rating	BHC in Pakistan Appetite	FCDO Appetite	Programme Risk Appetite
Strategy and Context	Major	Eager	Receptive	Receptive
Policy and Programme Delivery	Major	Eager	Receptive	Cautious
Public Service Delivery and Operations	Major	Receptive	Cautious	Cautious
People	Minor	Cautious	Cautious	Cautious
Safeguarding	Moderate	Cautious	Cautious	Cautious
Financial and Fiduciary	Moderate	Receptive	Cautious	Cautious
Reputational	Moderate	Cautious	Cautious	Cautious

Strategy and Context (Major): During the review period, Pakistan’s political, economic operating context remained volatile. Key factors included a deteriorating security situation in May due to India-Pakistan war, conflict and terrorism, significant political reshuffling in Khyber Pakhtunkhwa (KP), frequent changes in the education department leadership in both provinces, and another catastrophic flash flood impacting both Punjab and KP. Additionally, reductions in Official Development Assistance (ODA) and shifts in the UK government’s development priorities necessitated adjustments in the scope of TA and ILMpact’s transition away from direct service delivery toward strengthening government capacity. The humanitarian component experienced minor delays in certain districts, while new flooding created additional humanitarian needs, which were responded through signing a new grant arrangement with RSPN following advice from the commercial team

The adaptive TA design proved effective in aligning with evolving priorities. Embedded technical staff and mid-level planning sessions enabled local troubleshooting and secured senior leadership buy-in. Regular district-level follow-ups ensured progress without disrupting provincial timelines.

Policy and Programme Delivery (Major): This risk rating was increased from Moderate to Major during the reporting year mainly due to the withdrawal of the long-term TA tender and delivery challenges on the ILMpact component. These risks were mitigated through amending the scope of the bridging TA and agreeing a time and cost extension. Minor delivery risks on the humanitarian and BTAG components were effectively mitigated through established networks and embedded team’s proactive engagement at provincial, district, and school levels. However, under the ILMpact component, the delays in securing NOCs for KP districts, onboarding of downstream partners delayed implementation activities. Later, considering the weakening security situation in merged districts, the provincial government approved two alternative districts, which were subsequently put on hold following changes in the political leadership. Similarly, delays in approval of learning materials left limited time for interventions in winter-zone districts in KP.

Proactive engagement of FCDO and British Council’s teams with the senior leadership team has helped finalise the revised list of districts in KP. The BC is now planning to recruit additional teaching resources for winter camps in order to compensate for the lost time. Similarly, to ensure continuity of the TA support to the education departments in both provinces, the existing grant arrangement with ISAPS was extended for a period of 12 months to allow the new procurement process to be completed and handover of TA workstreams.

Fiduciary Risk (Moderate): All lead implementing partners maintain robust systems and processes to mitigate fiduciary risks. The GOAL programme team ensures strong oversight through routine spot checks to verify expenditures against approved budgets and actual activities, conducts field visits to confirm funds are used as intended, and reviews quarterly financial reports detailing expenditures, variances, and forecasts. FCDO’s policies on fraud, corruption, and anti-bribery have been shared with all partners, who also receive regular refresher training from the GOAL team and BHC finance team. Systems established by the partners to track fiduciary risks are robust.

Safeguarding Risks (Moderate): Comprehensive due diligence assessments were completed for all partners prior to grant agreements, with progress against recommendations monitored regularly. The GOAL team ensures that implementing partners maintain robust safeguarding policies and SEAH reporting mechanisms to protect staff and beneficiaries, complemented by mandatory participation in FCDO trainings. Safeguarding registers are reviewed periodically, and sexual exploitation, abuse and harassment (SEAH) training is integrated into inception and implementation phases for partners, downstream entities, and beneficiaries. Knowledge of safeguarding policies and procedures is verified during field visits to reinforce accountability and protection standards and any concerns shared with the FCDO team are immediately escalated to the relevant teams in the headquarter.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Performance and Delivery Against Planned Timeframe
The GOAL programme has now completed its third year of implementation which has proven to be challenging due to reduction in Overseas Development Assistance (ODA) allocation. The commercial tender for the Long-Term Technical Assistance (LTTA) was withdrawn and both the ILMpact component and Bridging Technical Assistance to Government (B-TAG) component were pivoted to align with changes in the UK’s development approach. A new humanitarian grant was signed with RSPN to respond to the devastating impacts of 2025 floods, building on the success of the predecessor humanitarian grant.

Both B-TAG and the humanitarian grant components have delivered well against the agreed costed workplan and timelines. The BC-ILMpact component continued to face delivery challenges such as delayed conclusion of the inception phase, delays in securing approvals from the provincial governments, time-intensive finalisation of downstream partners, high forecast vs spend variance, management of ineligible expenditure cases, and reporting on cash basis for some budget lines. These issues will need immediate attention to ensure smooth operations of the ILMpact as a learning initiative.

All implementing partners (IPs) have submitted financial and programme management reports to the GOAL Programme Management Team (PMT) in a timely and structured manner, as per agreed reporting schedules. Financial management on the technical assistance (B-TAG) and humanitarian component (RSPN) has been satisfactory demonstrating sound practices and effective oversight.

Commercial Performance
All the three components of the GOAL programme were amended during the reporting period in response to the shift in FCDO’s strategic priorities and changing context. The Accountable Grant Arrangement (AGA) with I-SAPS was extended by 12 months ending in June 2026 due to delays and cancellation of the long-term TA procurement. The extension ensures continuity of TA to provincial governments while a successor TA supplier is being procured. This extension also enabled the TA to pivot towards two priority workstreams: Education financing and professionalisation of teachers. Similarly, the humanitarian grant with RSPN was amended to reduce the overall budget, realising the savings and allowing two more months for successful closure of the grant. However, within the same timeframe, the country was once again struck by another humanitarian disaster and new grant signed with the same partner. While this extension had a transaction cost linked to it, it did demonstrate the ability of the partners to adjust their workplans and budget forecasts while aligning to governments priorities and risks within the context. These extensions to the AGAs were agreed after satisfactory performance was reported against the agreed milestones.

The ILMpact grant was also amended with a significantly reduced budget and scope in order to align with the shift in priorities. However, the component continued to face implementation challenges due to very complex delivery chain (more than 13 consortium and delivery partners) and blending of technical and delivery roles within the same partner. This caused significant coordination and dependency challenges amongst the partners, all downstream partners incurred set-up costs and decentralised procurements which resulted in loss of time undermining the value for money.

A standardised approach of Payment by Results (PBR) has been applied to I-SAPS and BC-ILMpact with payments paid in arrears and 30% of payment linked to satisfactory completion of milestones and deliverables. This mechanism and staggering of deliverables allowed more discussions with our partners to finalise high quality technical deliverables and ensured compliance with agreed standards. During the review period, I-SAPS met all Quarterly KPIs whereas BC only missed their Inception phase milestone and 50% of the second tranche of the inception phase payment was released in the next quarter.

Financial Performance
Overall, the programme has spent £16.96 million. This amounts to 40 % of the reduced lifetime budget of 40 million. In the current AR period (1 November 2024 to 31 October 2025), the total expenditure was £10.68m against a budget of £16m. The overall budget of the GOAL programme has been cut by more than 50% in response to the Spending Review process, reduced ODA allocations, transitioning out from service delivery, removal of the financial aid component, and pivoting towards systems strengthening TA support.

Overall, the financial management and financial controls have been assessed as fair. The forecast vs spend variance remained within 10% for ISAPS and RSPN. However, BC-ILMpact demonstrated significantly high negative variances mainly attributed to an elongated delivery chain, delays in obtaining necessary approvals from the relevant government departments etc and weaknesses in the planning and coordination between the lead and downstream partners. The GOAL programme team responded to these challenges through monthly tracking of spending trends against planned projections and pushing the lead partner to bring more accuracy in their work planning and forecasting with the downstream partners and relevant government departments.

The routine spot check of expenditures in the quarterly invoices was conducted for all the three partners. Minor observations were made on both I-SAPS and RSPN which were then clarified and settled. However, the process proved to be very time-intensive and challenging for the ILMpact grant. The processes revealed several issues ranging from the lack of understanding of reporting on resource accounting bases, and varied capacity of partners. These observations were discussed at length with the partner involving FCDO’s Finance Team as well. As a result, BC strengthened their own compliance check on the invoices and disallowed approx. £70k in expenses incurred by their downstream partners. They have also now introduced a new system where expenses pending further expenditures are separately reported to FCDO. BC-ILMpact have strong mechanisms for identifying and reporting any concerns.
Recommendations
1. Reduce the number of consortium partners and clarify roles to address coordination delays and dependency risks (BC & GOAL team, January 2026).
2. Consider centralised procurement to improve efficiency and value for money. (Programme Manager-BC-ILMpact, March 2026)
3. Provide targeted training to partners (especially BC and their downstream partners) on resource accounting and forecasting (GOAL PRO).
4. Maintain monthly financial and delivery reviews with all implementing partners. (PRO GOAL programme, March 2026 onwards)
5. Review the escalation protocols and strengthen downstream compliance checks. (PRO, and Programme Managers of ILMPact and BTAG)
6. Monitor Forecast vs Spend variance through a performance related indictor. (BC & Goal Team April onwards)

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
1. The GOAL Monitoring, Evaluation and Learning (MEL) framework consists of the Theory of Change and an integrated log frame which establishes partners’ accountability and attribution to its high-level results. The GOAL log frame was revised in September 2025 and finalised in October 2025, which resulted in revised milestones for this review. To note, the Log frame changes continued into October, meaning that milestones were finalised less than the best practice of six months prior to Annual Review system date. This was necessary to apply changes that improved the focus and efficiency of outputs. Given outputs were consolidated from five to three, it took additional time for key Health and Education Group leadership to align and agree to all changes.
2. GOAL maintained a robust MEL framework during Year 3, enabling adaptive management and evidence-based decision-making. Monitoring was supported through monthly progress tracking, Back-to-Office reports, and quarterly reviews, complemented by regular stakeholder engagement at provincial and district levels. FCDO and partner teams dedicated significant time to MEL, including weekly check-ins and financial reporting.
GOAL partners continue to have robust M&E arrangements in place.
During the review period, MEL teams from delivery partners continued monitoring and reporting progress against agreed log-frame milestones, alongside broader targets and indicators such as teacher perceptions and focus group feedback, to inform future training adaptations. Implementing partners utilised data from community engagements, focus group discussions, monitoring visits, spot checks, and mid-course reviews with beneficiaries and stakeholders to assess school rehabilitation, enrolment trends, and improvements in educational quality. The FCDO team held quarterly meetings with partners and maintained regular engagement with the Khyber Pakhtunkhwa and Punjab governments to track progress across all three active GOAL components.

Partner MEL Systems and Resources
- ILMpact (British Council): Partnered with Sustainable Development Policy Institute (SDPI) as MEL lead, responsible for baseline and endline learning assessments, diagnostic studies, and independent verification of early childhood care and education (ECCE) and remedial learning outcomes. SDPI also supported gender and inclusion analysis.
- Humanitarian component (RSPN): Deployed its Management Information System (MIS) dashboard for real-time tracking of school rehabilitation, enrolment, and learning kit distribution. Community-led verification and third-party validation ensured transparency and accountability.
- B-TAG (I-SAPS): Integrated MEL within provincial systems through tools such as the Multi-grade Classroom Observation Tool (MG-COT), CPD dashboards, and School-Based Assessment analytics. MEL specialists worked with PMIU, PECTAA, and DPD to embed data collection and reporting into government workflows, reinforcing sustainability.

The GOAL team continued to track progress against the agreed workplans through review of quarterly reports and technical deliverables. Quarterly progress review meetings were held resulting in learning-based adaptation in delivery approaches. Additionally, the team thoroughly reviewed the means of verifications submitted along with quarterly reports to establish confidence in both the process and the outputs. Monitoring data allowed the team to proactively identify potential delays and respond quickly to emerging challenges to measure results accurately and adjust strategies accordingly. The humanitarian component also convened two provincial lessons learned workshops bringing together stakeholders from provincial government, FCDO Team, public schools, UNICEF, National Rural Support Progamme (NRSP)/Sarhad Rural Support Programme (SRSP) and other educational partners and agreeing on best practices for supporting education in climate-vulnerable communities, particularly post flooding. These lessons were compiled and shared with all three provincial governments.

The GOAL team conducted three visits to Lahore, two visits to Khyber Pakhtunkhwa (Haripur and Mansehra), and at least six project sites. Project sites included all three implementing partners. We observed activities in schools and collected feedback from school departments in both Punjab and KP, which also provided insights into the responses of key annual review questions. Review discussions also took stock of emerging needs that align with the GOAL Business Case and shared updates on the UK’s own evolving approach as well. GOAL team members also participated in the Khyber Pakhtunkhwa government’s Global Partnership for Education programme’s Joint Sector Review and Technical Working Group on Data.

During the review period, classroom observations were prioritised by the FCDO GOAL team. Following these, implementing partners were debriefed on observations and where needed, course corrected. The observations for ILMpact called for improvements in the quality of delivery. FCDO and British Council are working together to gather more data on the reasons and correct these as soon as possible.

FCDO MEL Partner (Planned for Year 4)
FCDO will procure a dedicated MEL partner to harmonies systems across all components, conduct independent verification of log-frame indicators and VfM metrics, and build capacity within provincial departments for data-driven decision-making. The Terms of Reference (TOR) are in the finalisation stage. Once reviewed by the Procurement and OPEX MEL teams, a formal Request for Proposal (RFP) will be initiated through the Procurement Hub. It is expected that the MEL partner’s procurement to be completed by Q1 of the next financial year, ensuring that before the next Annual Review, the partner can deliver consistent data quality, independent verification of results, and systematic learning.

Assets Management and Monitoring
Overall, amongst the three active component of the GOAL programme, BC-ILMpact and its consortium/downstream partners reported 719 assets valued at GBP 148,055, while B-TAG listed 54 assets worth GBP 13,000. No assets were procured by RSPN using GOAL grant funds. Updated asset registers are submitted to FCDO as part of the quarterly progress and financial report. The value of assets register is then reconciled with the financial reports to verify the expenditures against the allocations made in the agreed budget.

As part of the annual review, the GOAL Programme Officer conducted a sample-based verification exercise of assets. Due to resource constraints, the assets in Punjab were physically verified and photographic evidence and details for assets located in KP were obtained from the lead implementing partner. The programme officer noted that the assets in I-SAPS BTAG Lahore office and those at the School Education Delivery Unit recently been established were properly tagged, maintained and software licenses on the IT equipment were all valid. Similarly, assets managed by the ITA (a consortium partner of BC-ILMpact) were also maintained and properly documented. However, several concerns including non-availability of assets at the location, improper maintenance, poor handling and other health and safety issues were noted at a downstream partner’s office. Feedback has already been provided to BC for investigation.
Recommendation
1.	The British Council should conduct a detailed Assets spot-check of its downstream and consortium partners and report to FCDO to strengthen transparency and accountability. (PRO GOAL and Programme Manager BC ILMpact, March 2026)
2.	Complete procurement of a dedicated MEL partner by quarter 1 of the next financial year to strengthen monitoring, evaluation, and learning across all programme components. (PRO GOAL, June 26)

Date of last narrative financial report	10th November 2025 (all partners)	Date of last audited annual statement	RSPN – November 2025 / ISAPS – December 2025 / ILMpact – N/A

Annex A: Current status of GOAL programme components
Component 1: Humanitarian support “Bringing Children Back to School” (BCBS): The humanitarian support component was implemented in eight districts across South Punjab, Khyber Pakhtunkhwa (KP), and Sindh that were severely affected by flooding in 2022 and 2024. The BCBS grant focused on rehabilitating schools and creating safe learning environments for children. Key interventions included provision of furniture and reading corners, psychosocial support, teacher training, and school governance training for Parent Teacher Committees. In addition, teaching and learning material kits were distributed to facilitate the return to education, along with ‘School-in-a-Box’ and teacher kits. The BCBS grant concluded in August 2025 following a time and cost extension signed earlier in the year with RSPN. Partner: Rural Support Programmes Network (RSPN). Start date: 01 January 2025. Status: Closed. Value: £10 million.
Component 2: Bridging Technical Assistance (TA) - (B-TAG): This component provides targeted technical assistance (TA) to support the Departments of Education in KP and Punjab on key priority areas carried over from the closure of the Punjab Education Sector Programme and KP Education Sector Programme, as well as priorities outlined in the GOAL business case and shared government–FCDO objectives. It was designed to provide ‘bridging’ TA while the procurement for the long-term TA under Component 5 was cancelled as it was no longer viable due to ODA budget cuts. The B-TAG grant is implemented by I-SAPS. Until the last extension, which ended in June 2025, the component was valued at £3.7 million. A further time and cost extension was approved in June/July 2025, adding £1.9 million and extending the implementation period until June 2026. The procurement process for future long-term TA is now underway. Partner: Institute of Social and Policy Sciences (I-SAPS). Start date: June 2023. Status: Active. Value: £5.6 million.
Component 3: Learning demonstration for government ILMpact: This component is delivering teaching and learning interventions for girls and the most marginalised children such as those from religious minorities; mostly in rural communities including KP Merged Districts and South Punjab. Partner: British Council-led consortium. Start Date: Memorandum of Understanding (MOU) signed, and inception period started on 1 September 2024;end date August 2027. Status: Active. Value: Up to £11.6 million (reduced from £20m).
Component 4: Financial Aid: This component was originally designed in the Business Case to enable the Governments of Punjab and KP to scale up effective demonstration models that will be developed through other components of the GOAL programme. However, when Financial Aid was paused for Pakistan, this component was deprioritised. . Partner: KP and Punjab departments of Education. Value: up to £30m. Status: Closed.
Component 5: Long-term Technical Assistance (TA): This component will provide long-term TA for priority areas to improve learning outcomes, teacher professional development and education financing. The previous TA procurement was cancelled due to the ODA budget reductions. Procurement is current underway with reduced budget. Partner: TBC. Value: up to £8-11. Status:
Component 6: Monitoring and Evaluation: Through this component, GOAL will have third-party monitoring and an evaluation process to generate evidence and inform future education sector programming.. Partner: To be procured. Value: to be determined Status: Planning stage
Component 7: Education Endowment Fund: This component was set up as an option to use unallocated Financial Aid funds in component 4 of the GOAL programme. It was to enable an innovative and sustainable mechanism funded through CDEL to deliver funding for an additional set of learners who are under resourced to attend school: those children with disabilities and from religious minorities. Status: Closed (12 August 2024) as there was insufficient time to set up this mechanism within FY 2024/25 deadlines.
Component 8: Programme-funded posts: Within the original GOAL Business Case, there was a provision for project-funded staff essential for programme delivery, whose roles could be sourced externally if not available in-house. This component covers additional positions, including an SEO for Policy and Partnerships to strengthen alignment between GOAL activities, Centrally Managed Programmes, and other development partners. It also funds the GOAL Education Advisor. Both positions are supported for the full duration of the GOAL programme. Partner: FCDO inhouse. Value: up to £0.25m. Status: Active. Start Date: since October 2024.
Component 9: Humanitarian Support – Safe Return to Learning. In September 2025, a new grant titled “Safe Return to Learning” (SRL) was signed with RSPN in response to the floods that primarily impacted KP and Punjab. SRL runs until March 2026 and covers seven districts across Punjab and KP. This grant builds on the lessons learned from BCBS and continues to support school rehabilitation and safe learning environments for affected children. Partner: Rural Support Programmes Network (RSPN). Start date: 08 September 2025. Status: Active. Value: £3.0 million.

Annex B: GOAL’s updated Theory of Change
Annex C: Recommendations from 2024 Annual Review
	Recommendation	Responsibilities	Status
1	FCDO, in collaboration with all GOAL partners, should lead a review of the theory of change and pivoting of the programme strategy in line with the emerging direction of the UK-Pakistan development cooperation. A sharper focus on supporting girls in foundational learning and to get them through secondary education, a simpler component structure, building a modern UK-Pakistan education partnership, and linking with DARE and other cross-mission interventions (e.g. inclusion work under Aawaz, British Council’s education programmes) should be key considerations. It is important to wait for all components to be active so that all partners co-create a shared vision and programme strategy.	Lead: SRO/ PRO with implementing partners, by end May 2025	Completed as part of current AR
2	FCDO team should circle back to findings and lessons learned from the Punjab Education Sector Programme (PESP) and Khyber Pakhtunkhwa Education Sector Programme (KESP). This includes drawing on what worked to improve inclusion and outcomes for girls and marginalised children. For example, the end-of-project third party evaluation includes evidence on successful delivery mechanisms but also indicates potential opportunities lost with regards to the discontinuation of Financial Aid. The education team should consider what alternatives are available to draw on effective delivery mechanisms in absence of Financial Aid. This could include, for example, leveraging Asian Development Bank and World Bank’s new Country Partnership Framework	Lead: SRO/ PRO with implementing partners, ongoing	Completed.
3	FCDO should ensure an effective and timely transition from the bridging TA to long-term TA, with a clear handover process. This will be a priority and will start once the long-term TA inception process begins so that there could be a seamless handover between suppliers. FCDO should also ensure that the new supplier is looped in early on FCDO’s education strategy and portfolio shifts so that their approach is fully aligned. The team should ensure a strong effort on implementation, scale-up and inclusion of women and girls in line with the emerging UK-Pakistan development strategy	Lead: SRO, February to end June 2025	Jan/Feb 2026 / Not completed.
4	All GOAL partners should contribute to monitoring and evaluation of the programme to deliver results and share evidence and learning with Government partners. This will include aligning third-party monitoring as well as a formal evaluation of the overall GOAL programme. It will also entail a revision of the GOAL logframe and incorporating achievable and new stretching indicators, milestones and targets that avoid a proliferation of lower impact TA-only activities and that are in line with the FCDO’s new Pakistan partnership/development strategy and spending priorities.	Lead: SRO/PM with implementing partners, by July 2025	End October 2025 / GEMFA Delayed / Reporting on MEL within components ongoing
5	Once all the long-term TA and MEL components are onboarded and the service delivery component enters the implementation phase, more ambitious milestones that respond to the outputs explicitly should be set for the next two review periods. Process-level milestones should be minimised.	Lead: PRO and implementing partners, October 2025	End August 2025 / Completed.
6	All GOAL partners to document, publish and disseminate their research findings and learnings from the programme. Sharing this evidence with Governments in both provinces, as well as with Development Partners and the public is important for transformative change and will be a priority as part of the communications strategy for GOAL and a synergies framework for learning from research produced under the Data and Research in Education (DARE) programme. This will need to be reviewed once all components become active in the coming year.	Lead: SROs of both implementing partners	Jan - July 2025. Completed
7	A GOAL Steering Committee should be set up, separately in Punjab and Khyber Pakhtunkhwa, as soon as the long-term TA supplier is onboarded. The committees should include representatives from all GOAL components regardless of end-date and work together to build in lessons learned into future planning. The committees should also include designing complementarities, building synergies and addressing BHC Pakistan-leaderships key questions and concerns in partnership with the MEL component into its mandate. The committees will enable the GOAL programme to have a unified identity among all suppliers, especially in terms of eternal communication and engagement. The teams should ensure more focussed plans by province are in place, well-coordinated with the respective governments and other Development Partners	Lead: SRO/Education Advisor with implementing partners and relevant provincial government departments by end June 2025	End October 2025 / On hold

8	RSPN was to document key lessons learnt during their implementation to feed into GOAL’s and ECW’s approach for work around resilience of the education system by July 2024. With extensions of the humanitarian component, this recommendation will continue into the next reporting period.	GOAL Education Adviser	Completed.
9	1.a. A key lesson learned during this review period was how the inclusion of locally hired project staff through downstream partners, especially in difficult context such as the merged districts in KP, was effective in terms of reducing costs, increasing pace, and adapting support. This is an approach to consider during inception of both the Service Delivery and long-term TA components.	GOAL SRO and PRO, February to June 2025	Completed.
10	1.b. As the PPP reforms are underway in Punjab, there is opportunity to work with the School Education Department’s approach by speeding up the bridging TA on innovations related to public-private partnerships (PPPs). This should be prioritised as soon as possible and shared with both provincial governments to foster linkages, healthy competition, and progress in this space. I-SAPS has compiled a comprehensive education PPPs report which outlines global best practices including CSR Partnerships, impact bonds and investments, and private sector expansion in marginalised areas. Given the radically different nature of the interventions described, an introductory session should be convened. Following the introductory session, the long-term TA should convene a series of consultations around this and investigate feasibility in the Pakistan context.	I-SAPS, February 2025 for introductory session	Completed.
11	1.c. As a member of the Education Cannot Wait (ECW) steering committee, FCDO should continue to share evidence from GOAL’s humanitarian assistance delivered by RSPN, and I-SAPs on school climate resilience school plans.	GOAL Education Adviser, June 2025	Completed.
12	1.d. Results from the humanitarian assistance component should be reflected in the central FCDO commission on Humanitarian Results	GOAL Education Adviser, annually	Completed.
13	2.a. Community engagement with a clear set of intended outcomes is helpful in solving problems at the district level. Conversations with parents, influential community members, and teachers enabled better support to mothers and other female family members to be involved in school governance. This should continue in the humanitarian component and all remaining schools to be supported (by end June 2025) and this learning considered in the inception periods of both the Service Delivery and long-term TA components.		Completed.
14	2.b. Efforts to empower women and girls need to be pursued using the Global Partnership for Education (GPE) ‘gender hardwiring’ approach as well. The new policy and partnership coordinator in FCDO should lead on this in GPE and development partners’ dialogue processes.	FCDO, March 2025 onwards	Completed.
15	2.c. Once the implementing partner for long-term Technical Assistance is onboarded, a more targeted approach empowering mothers on home-based learning, participation in school governance, and other factors that can impact continued access and quality of learning should be prioritised.	FCDO, from March 2025	Completed.
16	3.a. It is important for I-SAPS and British Council to include baseline learning levels in all phases of interventions, as part of the school selection criteria. This includes, but is not limited to, the remediation pilot.	SRO, British Council and I-SAPS, February 2025	Completed.
17	3.b. I-SAPS should prioritise the approval of DPD service rules in consultation with officials, addressing any unmet concerns. Follow-up meetings should remain a priority in terms of TA to the government at all stages.	I-SAPS, January 2025)	Completed
18	4.a. Ensure I-SAPS, BC and when the long-term TA is onboarded, provide learning and assessment focused interventions designed to be longer than most interventions under this output which have had a duration of 4-5 weeks. For delivery pilots and interventions going forward, classroom interventions should be a minimum of 10 weeks.	From February 2025)	Completed
19	5.a. Interprovincial interactions should be prioritised even in politically challenging times at both Ministerial and secretary level as well as lower management tiers and creative solutions around this should be pursued with the British Council and I-SAPS, including the continuation of inter-ministerial and inter-provincial dialogues early in 2025.	SRO, March 2025	Completed
20	5.b. I-SAPS should continue to explore ways to target leadership and governance training to be adapted to include more women. If women are limited in the middle and high tiers for leadership for future professional development support, lower-tiers and even recruitment practices can be reviewed to build a solid pipeline of women leaders in education governance.	SRO, I-SAPS, June 2025	Ongoing