Programme Completion Review

Title: Comic Relief Red Nose Day 2019 – Mental Health and Wellbeing in Kenya Programme: Strengthening civil society to support those with mental health problems to enjoy their rights
Final Programme Spend £ (full life): £2,084,716 / Programme Value £ (full life): £4,730,607 / FCDO: £2,100,000 / Comic Relief: £2,630,607	Review Date:	March 2024
Programme Code: 205285	Start Date: / 1 April 2019	End Date: / 31 March 2024

Summary of Programme Performance
Year	2020	2021	2022	2023	2024
Overall Output Score	A	A	A+	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-205285/summary
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-205285/summary

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved

The Mental Health and Wellbeing in Kenya programme aimed to ensure people with mental health conditions and psychosocial disabilities can access the support they need, are empowered to speak out and live free from stigma and discrimination. The programme addressed the poor availability of quality mental health services, inadequate support in the community, human rights violations, and exclusion because of stigma and discrimination which contribute to the social, economic, and political marginalisation of people with mental health conditions and psychosocial disabilities in Kenya.

The programme’s strategy of investing in Kenyan organisations to increase access to quality mental health services and to reduce stigma and discrimination related to mental health was relevant and timely, and coincided with policy developments to improve mental health and the provision of mental health services in Kenya. In June 2019, President Kenyatta indicated in his official Madaraka Day (Kenyan Independence day) speech that the country was facing a mental health crisis and ordered the Ministry of Health to implement programmes and policies to address the problem. A Cabinet meeting in November 2019 directed the formation of a Mental Health Taskforce to address the mental health concerns of Kenyans and help guide the government on resource allocation for mental health. The Taskforce had completed its work (but had not yet published its report) just before the start of the COVID-19 pandemic in early 2020. Building on the momentum of the report and its recommendations, and with a heightened recognition of mental health related concerns intensified by the global COVID-19 pandemic, the Mental Health Amendment Bill was passed by the Senate on 21 June 2022 and signed into law on 1 July 2022; funded partners in this programme took part in advocacy contributing to the Bill’s successful passage. The Bill’s overarching interest is to ensure that all people with mental health needs receive the highest attainable standard of care and obliges both national and county governments to provide the necessary resources for the provision of mental health care and treatment.

The overall score of A is informed by the successful achievement of the targets of the programme’s two outputs, which remained the same throughout the programme. Firstly, grant making resulted in investments of £2,904,155 made directly to a total of 10 Kenyan civil society organisations (CSOs) and representative groups that implement activities to tackle mental health related stigma and discrimination, and to improve access to quality mental health care. Ongoing management and support to the funded partners helped them effectively deliver their planned activities and outcomes. Secondly, the programme supported funded partners to strengthen their resilience to sustain their work. The programme invested in organisational strengthening (OS) made up of (a) consultancy support for each funded partner to undertake self-assessments in 2021 to identify organisational priorities and an OS plan, and (b) OS grants in 2022 to funded partners to implement their OS plans. In total, £577,346 (12% of the total programme value) was granted directly to Kenyan CSOs’ work in mental health and their organisations. As a result of the investments, each funded partner delivered activities to tackle mental health related stigma and discrimination and/or improve access to quality mental health care and undertook activities to improve their organisational capacity to effectively and sustainably deliver benefits to people with mental health conditions and to communities.
[note] The term ‘representative group’ refers to organisations which represent and are led by people with lived experience of mental health conditions and psychosocial disabilities.

Major lessons learned, evidence generated and recommendations

Context: The external and policy environments had both negative and positive effects on the delivery of the programme: In Kenya (and globally), the COVID-19 pandemic had a negative impact on mental health. At the same time, the pandemic helped bring mental health issues into the spotlight, both in relation to the public’s awareness of mental health issues, and the Kenyan government’s response to mental health. There was an increased demand for funded partners’ mental health services as a result of their campaigns and outreach and the more positive policy and social environment related to mental health. However, this placed a greater pressure on partners delivering community-based frontline mental health services.

Support to CSO partners including Organisational Strengthening (OS): The rationale for the programme’s focus on supporting and strengthening CSOs recognised the roles they play in: contributing to reductions in poverty; highlighting the needs of those who have been excluded and left behind; reaching and empowering marginalised communities (particularly those that the government has not reached) through their relationships, trust and legitimacy in their communities; and holding decision makers to account. The programme’s holistic approach to strengthen CSO partners individually and collectively (including supportive grant management over the programme period, facilitated self-assessments, funding for both project work and OS, and a learning network) was effective, as evidenced in the end of programme evaluation. Specific lessons related to all these types of support are reported in Section C of this report.
Grant making: Two key lessons emerged in relation to making grants to CSO partners. Firstly, for more established CSO partners such as those funded through this programme, future programmes should consider providing flexible, core funds to allow partners to prioritise their funding to meet their programme objectives as well as their organisational needs. Flexible, core funding grants promote quality programme implementation and organisational sustainability. This approach is in line with Comic Relief’s move toward trust-based philanthropy and the principles underlying the Shifting the Power movement. Secondly, more flexibility may be needed if the programme is targeting a nascent sector in the programme country, both in relation to the size of the grants on offer, and the type/size of organisation eligible to apply. If seeking to fund smaller CSOs, possible strategies are to provide funding through in-country intermediaries or lead partners, to provide seed money or catalyst grants, or to provide flexible core funding grants appropriate in size to the organisation’s capacity.
Programmatic learning: The programme generated significant information that strengthens the evidence on ‘what works’ in (1) improving access to quality and sustainable mental health services in line with human rights approaches and (2) tackling stigma and discrimination:
- Rights-based and user-centred approaches enhance the quality and sustainability of mental health services at the community level. These approaches also promote the inclusion of groups that would otherwise be marginalised.
- Community initiatives led by people with lived mental health experience are effective in reducing stigma and discrimination and promoting health-seeking behaviour amongst community members who need mental health services. Initiatives involving people with lived experience foster agency among mental health champions and build ownership of interventions at the community-level.
- Deploying or establishing structures at local level that focus on resource mobilization and allocation, co-ordination and oversight are crucial for improving access to mental health services. These structures provide an important space for different actors and stakeholders to share, collaborate and hold each other accountable in promoting access to quality and sustainable mental health services and in delivering in practice what is provided for by policy and in law.
- Data and evidence on the prevalence of mental health challenges, and the availability of and access to mental health services and drugs, fed into critical components of success. These included raising awareness, building an alliance of actors to advance the delivery of quality and sustainable mental health services at community level, and working with duty bearers and holding them to account.

How this report was conducted

This Project Completion Review (PCR) is based on evidence from three sets of documents from the Mental Health and Wellbeing in Kenya programme, including: (1) the main programme documentation written by Comic Relief and approved by FCDO: Comic Relief’s four annual reports (annotated by FCDO), the 2019 Business case for Comic Relief’s Aid Match II programme, the 2019 theory of change and a revised theory of change (2023), the programme logframe, the Monitoring Evaluation and Learning (MEL) Strategy, Comic Relief’s organisational strengthening model, and the programme’s risk register. (2) Individual project documentation: funded partner reports (six monthly and annual), with feedback from Comic Relief, visit reports by Comic Relief staff, funded partners’ OS plans and OS progress reports, and independent end of project evaluations. (3) Independent consultant reports: the 2023 final programme evaluation, the 2023 Learning Study of the OS pilot (involving this and two other FCDO-Comic Relief joint funded programmes), and a report summarising partner learning on transforming access to mental health services at community level in Kenya.

Actions following approval of this report

1. Comic Relief to submit final payment for activities undertaken up to 31 March 2024.
2. Comic Relief to submit a certified statement of financial expenditure by 30 April 2024 and return any unspent funds by 31 May 2024.
3. Comic Relief to submit, within 6 months of the end of Comic Relief’s financial year, their 2022/2023 Annual Audited Accounts showing FCDO’s contribution to the Mental Health and Wellbeing in Kenya (RND19) programme.
4. Comic Relief and FCDO to hold closing meeting with FCDO following response to final evaluation to discuss learning and agree application of it to other FCDO- Comic Relief grant programmes.
5. Comic Relief to post a summary of programme and main learning on Comic Relief web site and disseminate link to FCDO, grant holders and other external parties as appropriate.
6. FCDO to share evaluation report with FCDO Private Sector Development Advisory cadre.
7. FCDO to close down financial information upon receipt and checking of Comic Relief’s 2022/2023 Annual Audited Accounts and archive programme information.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£4,730,606	£2,084,716
Timeframe	April 2019 to March 2024 (5 years)	April 2019 to March 2024 (5 years)
Outcomes	Through the action of Kenyan CSOs and representative groups, stigma and discrimination associated with mental health conditions and psychosocial disabilities expressed by community members and government stakeholders is effectively tackled. / People living with mental health conditions and psychosocial disabilities have improved access to quality mental health services in line with human rights approaches. / Civil society organisations and representative groups working in the mental health sector have improved organisational capacity	The logframe outcomes did not change over the course of the programme. / The outcomes and their targets were achieved, evidenced by: / Numerous examples of notable changes in individuals with lived experience of mental illness; community members; health care facilities, NGOs and other organisations; funded partners; and government stakeholders/duty bearers, as documented in stories of change and case studies submitted with Annual Reviews and in independent evaluations of funded partners’ projects. These changes related to stigma and discrimination; access to quality mental health services; and organisational capacity and were corroborated in the programme’s final external evaluation and OS study. / 28,215 people with mental health conditions and/or psychosocial disabilities received quality, person centred, accessible community-based mental health interventions. (154% of target achieved).

Overall assessment of programme outcomes, sustainability and VfM

Impact and outcomes assessment
The programme’s logframe outcomes were achieved within the timeframe and budget originally allocated. Quantitatively, 28,215 people with mental health conditions and/or psychosocial disabilities received quality, person-centred, accessible community-based mental health interventions over the programme period, exceeding the target of 18,345. Qualitatively, 20 stories of change and 10 case studies were documented in Annual Reports to demonstrate the three programme outcomes (1) evidence of community members demonstrating reduced stigma toward people with mental health conditions and psychosocial disabilities through positive changes in knowledge, attitudes, behaviours and norms, (2) evidence of improved approaches to mental health care that address mental health conditions as part of a holistic model of care and support, integrated into health systems where appropriate, and (3) evidence of civil society organisations' and representative groups' progress against jointly-agreed organisational strengthening priorities. The final programme evaluation corroborated these and other notable positive changes at different levels, summarised below:

Individuals with lived experience of mental illness
- Mental health service delivery led to better quality of life.
- Individuals had improved confidence and skills in self-advocacy.
- Demand among individuals for mental health services increased.
### Community members
- Representation of mental health conditions in the media improved.
- Community care networks grew and were strengthened.
- Overall community awareness increased, and stigma around mental health issues and services decreased.
Funded partners
### Organisations were strengthened in a variety of areas, for example strategic planning, monitoring and evaluation systems, safeguarding policies and protocols, governance, staff skill development, amongst other areas.
### Healthcare facilities and NGOs
- Developing partnerships and training drove positive change among healthcare and NGO actors, including increased quality of and access to mental healthcare.
- Providers increased demand for training and resources to provide improved care.
- Funded partners and other NGOs improved their mental healthcare practices.
### National and county governments
- Funded partners engaged key government actors, using stories and data to increase awareness to influence action.
- Technical Working Groups effectively brought together community and government actors to spread rights-based approaches to mental health policy and implementation.
- Funded partners were largely effective in advocating for key policies to be passed and repealed, including the passing and signing of the Mental Health Amendment Bill and the launch of a national suicide prevention strategy.
- National policy advances were made with other bodies in addition to government, such as the Media Council of Kenya.

The changes in national and county governments noted above contributed to progress toward the impact level goal of ensuring that people with mental health conditions and psychosocial disabilities are engaged, empowered and able to enjoy their rights on an equal basis with others in Kenya. At the impact level, the programme directly reached 67,519 people, exceeding the impact target of 46,400.

Sustainability
The programme can be considered sustainable when locally led, ongoing, positive social change becomes embedded in the culture of communities, CSOs and governments and they ways in which they operate. As reported in the end-of-programme evaluation, many of the programme’s outcomes are highly likely to be sustained including: changes in attitude and awareness on mental health issues; changes in knowledge (e.g. for people who benefited from various training activities supported by the programme); changes in mental health policies/standards; changes in planning/budgeting at local government level in counties where partners operated; changes in the quality of mental health services; increased capacity of funded partners; positive reputation of funded partners for having been funded by Comic Relief.

One of the key aspects of the programme was to support funded partners to strengthen their resilience and future sustainability. Though funded partners’ ongoing activities and human resources will be affected and potentially put at risk at the close of the Mental Health and Wellbeing in Kenya programme, funded partners cited multiple ways in which involvement in the programme strengthened their organisations beyond funding: new relationships and stronger networks with other funded partners and county level stakeholders; space for reflection as part of the learning activities; and identifying needs and receiving funding for OS which enabled them to invest in priority areas to strengthen their organisations. The intention of the OS work in particular was that funded partners would have improved organisational capacity to effectively and sustainably continue to deliver benefits to people with mental health conditions and to communities at the completion of the programme. Comic Relief invested in real-time reflection, learning and iteration related to the OS work, through a year-long OS Learning Study. By the end of the programme, all funded partners were able to identify one or more areas of improvement that made their organisation more resilient and/or sustainable as a result of the OS support received.

Positive changes in the mental health policy environment helped accelerate change. The COVID-19 pandemic helped bring mental health issues even higher up the Kenyan government’s agenda. Funded partners engaged in public awareness campaigns from the start of the programme, which coincided with the start of the pandemic, resulting in a greater understanding of mental health. The Government of Kenya’s Mental Health Amendment Bill, passed and signed into law in July 2022, has the potential to transform how people in Kenya access comprehensive mental health services, if well implemented. As part of the end-of-programme evaluation, funded partners identified some of the barriers, challenges and opportunities within the mental health environment in Kenya to ensure that all people with mental health needs receive the highest attainable standard of care. Revisiting the programme’s theory of change, partners identified three change pathways to create a thriving mental health ecosystem in Kenya: (1) systems (collaboration of key actors, policies, resource prioritisation and allocation, standards and accountability); (2) provision of care (adequate numbers of a diversity of practitioners with the skills to deliver quality care); and (3) cultural and social norms (knowledge, awareness, attitudes, language, and visibility). This revised theory of change provides a vision and a catalyst for future efforts of all mental health actors in Kenya to work toward positive and sustainable change.

Value for Money
The original Concept Note adopted FCDO’s 4 Es approach to Value for Money (VfM). Overall VfM is elaborated in Section F. This section discusses the VfM indicators Effectiveness and Equity, while Economy and Efficiency are addressed in Section D.
[note] Economy (cost of delivering the programme), Efficiency (delivery against targets), Effectiveness (achievement of outcomes), and Equity (inclusion of all social groups)
[note] Over the course of the programme, Comic Relief refined its VfM Framework so that the 4Es better capture ‘the extent of social change catalysed through Comic Relief’s investment.’ This refinement incorporates Local Ownership (Economy), Mobilising the System (Efficiency), Impact and Learning (Effectiveness) and Targeting the Gaps (Equity) and includes Sustainability.

Effectiveness

The decision to fund local CSOs was central to the programme’s VfM strategy. Local CSOs can engage, empower and amplify the voices of people with lived mental health conditions, seen as important methods to effectively tackle mental health related stigma and discrimination and ensure that people-centred mental health services are accessible, appropriate and of good quality. These were key aims of the programme, identified through the development of the programme design and theory of change. In line with best practice in the sector, the approach effectively shifts power to those with lived and learned experience in the country of delivery.

A key success factor in achieving effectiveness was the rigorous partner selection and start-up process, with attention to developing a clear causal relationship between outputs and outcomes in the logframe, supporting funded partners to select appropriate quantitative and qualitative indicators, and then investing in the capacity of the funded partners to deliver their programmes and to measure and report the selected indicators. Investments in strengthening funded partners’ organisational functioning contributed to strengthening their impact and, in some cases, their reach. The overall effectiveness of the Mental Health and Wellbeing in Kenya programme is demonstrated by the positive outcomes and contribution to impact as described in the ‘Impact and outcomes assessment’ section above.

Equity
One of the strengths of the programme’s portfolio was the diversity of target groups reached by funded partners’ projects and the resulting contribution to the principle of ‘leaving no one behind.’ All funded partners worked directly and/or indirectly with people who are living with mental health conditions and who are marginalised and excluded because of these conditions. Some partners supported particular groups that were further excluded and/or disadvantaged by their experience, disability, or living environment. Examples included: survivors of sexual violence; people with both intellectual disabilities and mental health conditions; children and young people living in a refugee camp; pregnant and recently-delivered women living in informal settlements.
[note] ‘Mental health conditions include a range of disorders that arise from genetic, biological, psychological and social factors. People may experience these conditions with varying levels of severity with some mental health conditions having limited effects on a person’s normal day-to-day activity (including personal relationships and ability to work) while others may involve substantial disability and support needs. A mental health condition is considered a disability if it has a long-term effect on normal day-to-day activity. (Sources: Ryan, G. et al (2019). Mental Health for Sustainable Development: A Topic Guide for Development Professionals. K4D Emerging Issues Report. London and Brighton, UK: Mental Health Innovation Network and IDS; DfID (2020): An Approach and Theory of Change to Mental Health and Psychosocial Support for Global Development Actors, mind.org.uk). Comic Relief’s funded partners used various terms to describe the people they support: people with mental health conditions, psychosocial disabilities, psychiatric disabilities, mental health problems, mental illnesses, or mental health issues, for example.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The programme’s Theory of Change was drafted in consultation with Kenyan CSOs and stakeholders from the mental health sector, including the Kenyan Ministry of Health, in August 2019, and subsequently used to inform the design of the grant funding call launched in October 2019. It was finalised with FCDO in 2020. The overall expected impact, outcomes, and outputs in the Theory of Change, summarised in the diagram below, remained the same throughout the programme. Following agreement with funded partners regarding their project level outcomes, indicators and targets, Comic Relief finalised the implementation logframe in December 2020, which was approved by FCDO in February 2021. There were minor, non-substantive changes to the logframe indicators during the programme..
[note] Specifically: (1) reference to the mid-term evaluation was removed in Novmber 2022 as it was decided to combine it with the final external evaluation which commenced in January 2023; (2) targets for Outcome 2 indicator 1 were reduced from 20,357 to 18,345 to reflect the removal of one partner’s final year target, due to cancellation of the project for breach of contact; and (3) the final target and source for Output 1 Indicator 1 was amended to align with the deliverables from the OS Study and with the new OS indicator in the logframes of the two programmes also taking part in the OS Study (RND13 and RND15).

Figure 1. Mental Health and Wellbeing in Kenya programme Theory of Change

The expected impact of the programme was that people with mental health conditions and psychosocial disabilities would be engaged, empowered and able to enjoy their rights on an equal basis with others in Kenya. The outcomes and outputs leading to this intended result related to supporting CSOs and representative groups, firstly, to develop and implement mental health related programmes with a focus on (a) tackling mental health related stigma and discrimination, and (b) improving access to quality mental health services, and, secondly, to strengthen their organisational capacity so that they are able to further develop and sustain their work in the longer term.

The key assumptions underpinning the model were (1) that a sufficient number of CSOs and representative groups working in the areas of the programme’s objectives able to absorb and manage the grants would be identified, (2) that the selected partners would be effective in developing and implementing programmes which were well aligned with the programme objectives, (3) that the policy environment continued to support the objectives of the programme, and (4) that there would be a desire for collaboration amongst CSOs, representative groups, government and other stakeholders working in the mental health sector in Kenya.

Overall, the logic of the model held up as evidenced by the achievement of the outcomes and impact (summarised in the section above). Two calls for proposals ultimately resulted in the development of a portfolio of projects managed by funded partners to tackle mental health related stigma and discrimination and improve access to quality mental health services. Funded partners were supported to deliver their projects as well as to strengthen their organisational capacity and organisational functioning in various areas. Support included specific grants for organisational strengthening and a facilitated learning network in which funded partners took part in coordinated learning events to share experiences, reflect on their work, and the needed actions of all stakeholders to better support people with mental health conditions in Kenya. The policy environment was positive, though there is still work to be done to strengthen systems to support improved provision of mental health care and support in Kenya. As part of the end of programme evaluation in 2023, funded partners reviewed the programme’s Theory of Change and articulated their vision for a thriving mental health ecosystem in Kenya. The emerging Theory of Change included two outcomes found in the programme’s original theory of change (provision of care; cultural and social norms, incorporating stigma and discrimination), and a third outcome, systems (policies, procedures, data, standards, budgets and plans), partially included as assumptions in the programme’s original theory of change. This revised Theory of Change helped funded partners situate their current work, will help them plan future work strategically, and will encourage momentum and collaboration amongst funded partners and other stakeholders beyond the end of the programme.

## C: Detailed Output Assessment

Output Number and Title		Output 1. Comic Relief supports Kenyan CSOs and representative groups (funded partners) to define their priorities for OS, to be working towards them and reviewing their progress over the course of their grant
Output Score		A
Impact weighting (%)		40%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
1.1 Comic Relief's model for organisational strengthening (OS) jointly designed, reviewed and developed with funded partners	OS model evaluated to assess effectiveness and sustainability (February 2021)		Comic Relief's model for OS has been reviewed, refined and updated, and developed into a practical guide on funding OS work	Comic Relief's model for OS was reviewed, refined and updated. A reference document entitled ‘Practical Guidance for Comic Relief Teams on Organisational Strengthening Approaches’ was produced.
1.2 Number of funded partners who have completed joint assessment of OS priorities	All funded partners have assessed progress against OS priorities and have been supported by Comic Relief to consider next steps once the grant ends (February 2021).		All funded partners who were implementing their projects at the time of the OS assessments have assessed progress against OS priorities and have been supported by Comic Relief to consider next steps once the grant ends	All funded partners (9 of 9) who were implementing their projects at the time of the OS assessments assessed their progress against OS priorities. One grant was terminated before the end of this process so 8/9 were supported by Comic Relief to consider next steps once the grant ends.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

One of the principles of Comic Relief’s grant-making is ‘investing in local organisations’ for funded partners to effectively and sustainably deliver benefits to their target communities after their programme funding period ends. The Kenya Mental Health and Wellbeing programme has been designed to provide targeted organisational strengthening support to all funded partners. The support takes different forms and includes direct technical support from Comic Relief staff, advisory services from specialist consultants/consultancies and capital investment. Output one focused on supporting funded partners to strengthen the resilience and future sustainability of their organisations, in line with a commitment by Comic Relief and FCDO to invest more intentionally in strengthening CSOs. All of the end-of-programme targets under this output have been achieved.

Output Indicator 1.1: Two categories of organisational strengthening support were provided to support achievement of this output: (1) immediate support to further enhance organisations’ ability to deliver their projects successfully and meet all compliance, safeguarding, MEL and reporting requirements (related to Outcome 3 above), and (2) support for longer term priorities to enable partners to access sustainable funding, develop new organisational structures and systems, innovate and grow in line with their organisational strategies.

To address the former, applicants identified their immediate organisational development priorities within their grant applications and project budgets, which were explored as part of the grant making process and which provided an insight into organisations’ organisational needs. To address the latter, during the first year of the programme, a model for organisational strengthening was designed by Comic Relief with support from two expert, independent consultants. The model identified six guiding principles for Comic Relief’s future work to strengthen CSOs, and recommended approaches based on good practice. The six guiding principles are: (1) cultivate partner ownership, (2) enable access to quality local organisational strengthening providers, (3) ensure quality organisational strengthening methods, (4) adequately resource organisational strengthening change processes, (5) ensure participatory MEL systems to reinforce ownership, learning and adaptation, and (6) influence other stakeholders. Guidelines to inform the implementation of the bespoke OS model were first developed in consultation with Comic Relief staff. Funded partners were then invited to critique and help refine the model and ensure its relevance to the Kenyan context and to partner needs.
[note] The development of the OS model was part of the deliverables of the joint Comic Relief - FCDO-funded Shifting the Power Programme. The report, Investing in Organisational Strengthening for Social Change (June 2020), provides a backing for Comic Relief’s policy on OS.
[note] The Mental Health and Wellbeing in Kenya partners (RND19) were part of a larger cohort (which included partners from two other Comic Relief-FCDO programmes, All In, All Learning (RND15) and Maanda (RND13)) to pilot the implementation of the OS model.

As part of piloting the new organisational strengthening model, Comic Relief delivered the following key steps:
- Facilitated self-assessment: Comic Relief invited all funded partners within the Kenya Mental Health and Wellbeing programme, along with funded partners from the All in All Learning and Maanda programmes, to participate in a self-assessment process, which had the aim of enabling funded partners to develop an organisational strengthening plan. Tamarind Tree Associates, a specialist consultancy, was contracted by Comic Relief to facilitate this process for funded partners.
- Top-up funding: Comic Relief launched a closed top-up funding call for the funded partners who had been part of the facilitated self-assessment process. This enabled funded partners to apply for additional resources to deliver parts of their new organisational strengthening plans. Each application was assessed and funding was approved by Comic Relief’s Social Impact Committee in March 2022.
- Implementation: Funded partners implemented their organisational strengthening plans over a period of 12-18 months. Funded partners delivered a range of activities, for example (1) trained staff in areas such as leadership, governance, financial management, (2) developed and refined strategic plans; (3) delivered activities to support resource mobilisation, and (4) updated and improved MEL systems.
- Accompaniment: The funded partners had the option to continue to work with Tamarind Tree Associates whilst implementing the organisational strengthening plans. This took the form of accompaniment support whereby Tamarind Tree Associates acted as a critical friend and sounding board as the funded partners developed their organisations.
- Learning: Comic Relief recruited a consultant, the Kenya-based Galvanizing Africa Consult, to conduct a learning study of the pilot. The aim of the study was to (1) assess the effectiveness of Comic Relief’s approach to organisational strengthening and adherence to the framework, (2) understand and explore the experience of the funded partners taking part in the pilot, (3) identify lessons that will increase the effectiveness of Comic Relief organisational strengthening work, and (4) showcase the impact of the support.

Given the diversity of partners, their previous experience of OS activities, and their varying capacities to absorb OS support, an individualised approach through facilitated self-assessment was confirmed as an appropriate starting point to help further identify each partner’s OS priorities and support needs. Following the facilitated self-assessment, where funded partners were supported by an organisational strengthening specialist consultant to identify priorities and develop their organisational strengthening plans, Comic Relief invited funded partners to submit applications for OS-specific funding according to the priorities they had identified. All nine funded partners received a grant. Partners used OS funding for a variety of areas: strategic planning, restructuring and revising job descriptions to better serve organisational needs, developing feedback mechanisms and performance review processes and targets, training on programme management and finance, enhancing MEL capacities, resource mobilisation, refreshed and strengthened strategic oversight role and relevance of Boards and other governance bodies, support for staff care and wellbeing, and reviewing and updating policies including around safeguarding, amongst other areas.

A Learning Study of the OS pilot was undertaken over a 12 month period, to document feedback from partners on the organisational development processes; their experience of the quality of the support provided, and whether it was inclusive and empowering; and their overall engagement with Comic Relief on organisational strengthening. This process enabled adaptations and learning to be incorporated and documented to refine the six principles of the model. The end-of-programme evaluation noted partners’ appreciation for and the immediate utility of the programme’s OS component. A reference document entitled ‘Practical Guidance for Comic Relief Teams on Organisational Strengthening Approaches’ incorporating suggested refinements was produced as one of the outputs of the OS Learning Study. Comic Relief plans to disseminate its learning to other donors and stakeholders to demonstrate and communicate the potential impact of organisational strengthening support.

Output Indicator 1.2: All partners included activities on improving organisational capacity (related to Outcome 3) in their applications, the results of which were captured in partners’ monitoring and evaluation systems and reported annually to Comic Relief. The types of organisational strengthening activities generally supported either compliance with the conditions of their grant (such as strengthening safeguarding policies and practices; financial systems; governance structures; programme management etc.) or technical aspects of their programme (such as improved MEL systems).

As noted above, an organisational strengthening specialist worked with each of the nine active funded partners from the Mental Health and Wellbeing in Kenya portfolio (as well as four funded partners from RND13 and eight funded partners from RND15) to facilitate the process of organisational strengthening self-assessments. Partners were encouraged to consider areas to help their organisation sustainably continue to deliver benefits to people with mental health conditions and to communities when the programme’s funding ends. Each funded partner in the Mental Health and Wellbeing in Kenya programme completed an organisational strengthening self-assessment, received an OS grant, and evaluated their progress through self-reporting on a six-monthly basis. The OS Learning Study provided additional insights into partners progress and achievements and is summarised in the section on learning below.

Lessons learned through this output, and recommendations for future programming

OS model
The foundational grounding provided in Comic Relief’s OS policy document developed during the programme outlines the importance of OS work for Comic Relief and was a valuable part of the delivery of this output. Validation of the model by partners helped build ownership of the OS process.

Implementation of the OS model
Funded partner ownership of the OS process is critical to successfully embedding organisational change. Funded partners were initially introduced to the OS model as a group when most partners had been implementing their work for nearly a year. The OS study found that funded partners interpreted Comic Relief’s support for OS differently, with some seeing OS simply as an additional area of Comic Relief funding rather than a process that was for the benefit of the partner organisation. Finding more ways to help partners fully appreciate the why, the how, and the what of the OS process at the start of the funding relationship may further cement partners’ ownership of OS. Done collectively, this could help create a foundation for the concepts of cooperation and collaboration between funded partners that were found to be so valuable from the learning network activities reported elsewhere in this report. In future, Comic Relief will build support for OS into the first 12 months of all grants where budget allows, to integrate it more effectively in grant start up processes and programme delivery from the outset. This would also enable funded partners a longer period for their OS activities, running in tandem with their project-focused work, so that changes within their organisations are more likely to be embedded by the time their grant closes.

The quality of OS support is critical, particularly for the OS self-assessment. The OS provider supporting the self-assessment must be able to (1) develop trusting relationships with the funded partner, (2) use inclusive methods for the self-assessment, (3) engage partners in open questions and hold no preconceived frameworks of what the partner organisation should be. In the spirit of a partner-owned process, in future, it may be beneficial for partners to select an OS specialist from a list of providers, local if possible. In this programme, facilitated self-assessments were undertaken virtually due to COVID-19 restrictions, but ideally would take place in person.

Some funded partners who sought tailored, technical OS support to implement their OS plans experienced challenges in identifying and contracting local providers. Practical guidance on how to identify local service providers and how to procure services competitively could support partners in the future, and this has been added into the practical guide for funding OS work to ensure Comic Relief factors this into future OS funding opportunities.

OS alongside programme implementation for quality programming, resilience and sustainability
In addition to investment in funded partners’ mental health focused work, partners highly valued Comic Relief’s investment in OS, seen as key in promoting organisational sustainability. The OS model was not finalised when the programme started, so funded partners’ funding for OS was granted later in the programme, after their projects were already underway. This led to some partners perceiving a dichotomy between project versus OS funds instead of a sense of holistic support for funded partners and their work. Flexible core funding, in which partners can prioritise funding according to the programme objectives as well as their organisational needs, are seen as most beneficial for quality programme implementation and organisational sustainability and could be considered in future programmes.

Trust and power dynamics
From the outset, Comic Relief was aware that it would need to find the right balance of being a funder of the OS work without exerting undue control over the process, and without expecting particular outcomes. Partners taking part in the OS pilot noted the qualities of Comic Relief that made it stand out amongst its funding partners: open-minded, flexible, understanding, supportive. Comic Relief was prepared to fund any OS activities that were prioritised during the self-assessment process, though the funding pot was limited so each partner had to prioritise their plan. However, the OS Learning Study noted that some partners were still guided by what they perceived to be Comic Relief's priorities and that this is a key area for Comic Relief to continue to develop in future work on organisational strengthening. This is something that has been incorporated into the OS Funding Guidance, to ensure Comic Relief is intentional around this in future OS funding. The strategies noted above, coupled with even clearer communication from Comic Relief on why it supports OS, will help address this in future programmes. The provision of unrestricted funding also helps shift power from funders to partners.

Output Number and Title		Output 2: Comic Relief grant-making and management supports funded partners to deliver their planned activities and outcomes
Output Score		A
Impact weighting (%)		60%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
2.1 Number of grants made and percentage of programme funds allocated	100% of grants budget allocated / (February 2021).		Total grants budget allocated	Total grants budget allocated
2.2 Percentage of projects in the overall portfolio that have received a high quality monitoring visit by Comic Relief (to date)	100% (all projects receive a high quality monitoring visit) / (February 2021)		100% - 9/9 grants visited	100% / 9/9 active projects were visited by December 2022.
2.3 Programme score on the 'Funder-Grantee Relationship' Summary Measure in the Centre for Effective Philanthropy survey	Average programme score of at least 5/7 / (February 2021)		Average programme score of at least 5/7	Funder-Grantee Relationship Score: 6.8

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

All of the end-of-programme targets under this output have been achieved.

Output Indicator 2.1: The programme originally allocated £3,850,000 for CSOs: up to £3,450,000 for grants to CSOs to implement work toward the programme’s outcomes and £400,000 for grants to support partners’ organisational strengthening priorities. Ultimately £3,986,970 (104% of the target) was granted to partners: £3,285,531 was granted to funded partners for their projects, £585,532 for OS activities, and an additional £120,000 for cost of living top-up grants to support inflation and the rising costs of funded partners’ activities and operations. Slightly less than this (a total of £3,134,235, 81% of the target) was actually spent, due to cancellation of two grants part-way through implementation, and a small overall underspend by two funded partners.

Achieving the target required two rounds of grant making and flexibility in the allocations between grants for funded partners’ projects and their organisational strengthening activities. Following an open call for proposals in November 2019, the first set of eight awards was made in March 2020 in which 85% of the grants budget was allocated. Investing in representative groups and enhancing representation of people with lived experience were priorities for both FCDO and Comic Relief from programme inception, however no fundable applications from representative groups were received through the programme’s open call in late 2019. A more proactive approach to reach representative groups supporting people with mental health conditions and psychosocial disabilities was used for a second call for proposals in 2020. This involved a desk-based scoping exercise in which eighteen delivery organisations led by people living with mental health conditions and four intermediary funding partners were identified, of which four delivery organisations were deemed a good fit to the programme (none of the intermediary funders were found to be a good fit to the programme), three passed the eligibility checks and were invited to apply, two organisations submitted applications and both were awarded grants. The additional two awards in February 2021 brought the allocation of funds for partner projects to 94.1% of the amount ringfenced for projects. The remaining budget of £200,570 was added to the £400,000 budget ringfenced for OS grants (as described in Output 1 above), and of this, £585,532 was awarded. To accommodate challenges that funded partners were facing related to inflation and rising costs of basic goods and services, partners with live projects were awarded cost of living top-up grants in September 2023. A total of £120,000 was awarded in top-up grants, funded by Comic Relief only.

Output Indicator 2.2: Comic Relief commits to visiting each funded project once during its lifetime and conducts additional visits should concerns over performance or compliance arise, or if additional opportunities for learning are identified. Comic Relief met its monitoring visit target, visiting nine projects over the course of the programme, representing 100% of the live projects. Seven of the monitoring visits were virtual, due to travel restrictions during the COVID-19 pandemic, and two were in-person visits. During these visits, Comic Relief engaged with funded partners on the performance of their projects, reflected on key lessons learned and assessed and discussed compliance issues. Summaries of all monitoring visit reports were provided to FCDO.
[note] One of the ten grants was cancelled for breach of conditions within the first six months of the award in 2020 and therefore was not visited. A second grant was cancelled in its final six months of the award in 2023 for breach of conditions; this grant was visited prior to its suspension and subsequent cancellation.

In addition to monitoring visits, Comic Relief’s grant management included (1) support to funded partners to develop Funding Overview Forms at the start of their grant; (2) desk review of funded partner annual progress reports, six-month updates, and organisational strengthening updates, (3) calls and written communications with funded partners as needed. The latter enabled Comic Relief to actively understand all partners’ risks and adapt the programme in response to the needs of partners, for example by enabling them to change delivery plans, budgets, or targets where justified and necessary.
[note] Funding Overview Forms outlined funded partners’ intended outcomes, indicators and learning plans and were used as a basis for partners’ annual reports. At the programme level, data from funded partners’ reports were aggregated and reported in the programme’s annual reports.

Other support to funded partners included the establishment of a learning network facilitated by a Kenya-based consultant serving as the Learning Coordinator. They provided monthly one-to-one learning support to each funded partner, and facilitated a series of coordinated learning events leading to the development of two learning resources: (1) a policy brief on accessing mental health services used as a tool to advocate for greater attention and funding allocations for mental services at the county level, and (2) a document outlining learning from funded partners’ experiences on transforming access to mental health and wellbeing services. The end of programme evaluation noted that the programme’s learning events were well received by funded partners and useful in shaping collective advocacy efforts, sharpening the quality of partners’ service delivery, and providing a forum for collective learning among funded partners. Finally, funded partners participated in a learning study to document the OS process including its effects. The convenings held to gather information about the OS process proved to be valued and supportive in terms of peer networking and learning, an unintended positive outcome.

Output Indicator 2.3: The final indicator under Output Two relates to the biennial survey in which Comic Relief participates with the Centre for Effective Philanthropy (CEP). The CEP survey independently assesses the quality of Comic Relief’s engagement with funded partners and benchmarks this with peer organisations, using a consistent set of questions. This survey is sent to all funded partners that have received funding from Comic Relief in the previous 12 months. The most recent survey was circulated to Funded Partners in September 2023. The ‘Funder-Grantee Relationship’ score is an average of the scores (from 0, most negative, to 7, most positive) of funded partner perception of the funder in six areas: approachability, responsiveness, trust, candour, respectfulness, and funder compassion for those affected by partners’ work. The Mental Health and Wellbeing in Kenya programme was scored highly by funded partners in the last two surveys: 6.6 on the 7-point scale in 2021/22 and 6.8 in 2023/24, exceeding the target of 5 on the 7-point scale.

To triangulate the findings from the CEP survey, the end-of-programme evaluation explored funded partners’ experience with Comic Relief and its grant management approach. Funded partners reported a positive experience with Comic Relief’s grant management overall. Funded partners valued Comic Relief’s investment in their direct work as well as their organisation, the promotion of delivery of quality interventions (and not just reach of interventions), flexibility of funding to respond to implementation and organisational challenges, support beyond funding through the learning network, Comic Relief’s accessibility and responsiveness, and Comic Relief’s affirmation of funded partners’ expertise and contextual knowledge.

Lessons learned through this output, and recommendations for future programming

Grant making
One of the assumptions of the theory of change was that there would be a sufficient number of CSOs and representative groups able to absorb and manage the grants through work that is relevant to the programme’s objectives (see Section B). The number of CSOs working in the mental health sector in Kenya who were able to meet Comic Relief’s eligibility criteria, including a minimum annual income level, was quite small. It was difficult for small grassroots organisations to receive funding from the programme. To address this, after the first round of grant making, Comic Relief launched a second invitation-only call for proposals, targeting representative groups and applied a lower organisational income threshold, with eligibility investigated by Comic Relief in advance of the invitation. The balance between grants for projects and for OS was also changed, so that more funding was available for OS for funded partners. Unrestricted funding in which partners can prioritise expenditure according to the programme objectives as well as their organisational needs, should be considered in future programmes. Unrestricted grants promote quality programme implementation and organisational sustainability. Comic Relief is considering providing more of its investment in flexible core funding, in line with a move towards trust-based philanthropy and the principles underlying the Shifting the Power movement.
[note] In the first call for proposals, this minimum was set at £75,000 per annum, and in the second call for proposal, this was reduced to £50,000 per annum. The minimum threshold figures were based on Comic Relief experience that organisations who have previously not managed funding at this minimum level are less likely to have adequate systems in place for good management and governance of a Comic Relief grant.

Furthermore, more flexibility may be needed if the programme is targeting a nascent sector in the programme country – both in relation to the size of the grants on offer, and the type/size of organisation eligible to apply. Other options are to fund smaller CSOs through in-country intermediaries, consider providing seed money or catalyst grants for small organisations to develop their applications, or provide flexible core funding appropriate in size to the organisation’s capacity.

Grant management
Start-up processes
Robust MEL frameworks and support to partners to establish their Funding Overview Forms helped ensure realistic expectations were set, and robust data was collected throughout the lifetime of grants. Comic Relief’s MEL team provided bespoke support for most partners, while an in-country consultant was contracted to support smaller partners and those with weaker MEL systems to build their capacity and accompany them in the finalisation of their Funding Overview Forms. Start-up webinars for new partners were also delivered remotely using small groups and a number of shorter sessions.

Grant management approach
A flexible approach to grant management was important to mitigate programme delivery risks, particularly in relation to the COVID-19 pandemic. Regular points of engagement and an ‘open door’ approach meant that partners felt they could ask Comic Relief for support. Partners were allowed (and supported) to adjust their project plans and budgets where necessary. Despite this, partners were challenged to cover rising costs amidst the global cost of living crisis. To address this, unrestricted cost of living top-up grants (£15,000 per partner) were awarded in September 2023. As noted above, Comic Relief is considering providing more of its funding via unrestricted grants.

Monitoring and support visits
A structured and consistent approach ensured that all partners received a high quality monitoring visit (undertaken remotely or in-person). New monitoring visit protocols and tools were put in place to ensure a consistent approach to planning, undertaking and documenting project visits. This resulted in the collection and reporting of consistent information on the quality of in-country discussions, grant performance, grant compliance, monitoring, evaluation and learning and recommendations for further actions. Some adjustments were needed for working remotely with partners (whether for monitoring visits or other points of contact), for example tighter agendas and shorter sessions to avoid ‘zoom fatigue’. Comic Relief concluded that a high standard of due diligence can be achieved both in-person and remotely, though remote visits are more transactional and less relational than face-to-face visits. Comic Relief recently changed its terminology from ‘monitoring visits’ to ‘learning and support visits,’ to better reflect its emphasis and approach to its visits with funded partners. Comic Relief will develop internal guidance to determine when in-person visits and/or remote visits should take place. This will take into consideration aspects such as (1) value for money, (2) environmental impact of travel, (3) progress on grant, (4) relationship with funded partner, and (5) risks to grant implementation.

Learning, coordination and peer support
Funded partners perceived the programme’s learning component positively, as an additional non-monetary contribution from Comic Relief. The learning network provided time for funded partners to pause, reflect, generate new knowledge, share practical ideas, and build capacity and was a forum for collective learning, collective advocacy, and a space for partners to validate one another’s experiences, broaden their knowledge of mental health initiatives in Kenya, and grow their networks. The skills of the Kenya-based Learning Coordinator were key to building a strong learning cohort for the programme. Other factors contributing to the successful outcomes for partners included: the diversity of funded partners, highly participatory sessions designed by the Learning Coordinator, and the opportune timing for progressing mental health in Kenya. In future, Comic Relief will establish the learning component at the outset of the programme. The learning component could further build opportunities for members to extend their networks and visibility for the long term, among the cohort itself, and with other organisations such as donors or conference convenors. These opportunities were seen as particularly useful as the programme came to a close.

Funder partner relationship
Comic Relief’s most recent score on the funder-grantee relationship measure was 6.8 of 7.0, a very positive result. In the end-of-programme evaluation, funded partners cited the following strengths of Comic Relief’s approach as a funder: (1) the investment in a coordinated learning network with resources to bring partners together on a regular basis; (2) support for organisational strengthening alongside project implementation; (3) encouragement to focus on quality work that matched partners’ internal capacities; (4) promotion of local ownership; and (5) accessibility, responsiveness, and adaptation following feedback from partners. Funded partners noted the following elements that would further strengthen the funder-partner relationship, for consideration in future programmes: (1) the provision of unrestricted funds for a longer period of time; (2) using Comic Relief’s social capital to bring greater visibility to funded partners’ work; and (3) having a Comic Relief presence in-country to further build relationships and trust, or alternatively, having more opportunities for communication with Comic Relief staff outside of reporting times, more frequent visits from Comic Relief, and/or more provision of support by local firms where required.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The main cost driver of the Mental Health and Wellbeing in Kenya programme – which did not change over the course of the programme – was the grants made to CSO partners (accounting for 84% of the programme’s costs) supporting funded partners to (1) deliver activities to meet the outcomes of the programme and (2) strengthen their organisations to sustainably continue to deliver benefits to communities at the end of the funding period. The independent end of programme evaluation concluded positive changes were catalysed by the investment, demonstrating VfM. Funded partners’ interventions targeted gaps in the Kenya mental healthcare system while maintaining an equitable approach, which extended these changes. Further evidence of VfM includes the funding structure, the overall design and management of the programme by Comic Relief (programme level VfM); and the ways in which funded partners implemented their projects (partner level VfM), elaborated below:

- The programme’s funding structure represented an economic way for FCDO to invest in an experienced and knowledgeable grant-making and management organisation to implement a focused programme investing directly in a group of Kenyan CSOs. Comic Relief matched or exceeded FCDO’s more than £2 million investment for grant funding, organisational development and programme monitoring, learning and evaluation, and additionally invested £630,607 of its own funds to supplement FCDO’s £100,000 contribution for programme management (programme level – economy, efficiency).
- The programme was situated within Comic Relief’s Impact and Investment Directorate, alongside other FCDO-Comic Relief co-funded programmes, benefitting from Comic Relief’s established grant management systems as well as good practice in grant making and management generated across the Directorate, providing efficiencies and economies of scale (programme level – economy, efficiency).
- The programme directly benefitted from the FCDO-Comic Relief joint funded Shifting the Power Business Case design and the development of Comic Relief’s organisational strengthening model. The experiences of funded partners in this programme have fed into the iterative process of delivering the Shifting the Power programme. This represents value for money for both programmes (programme level – economy, efficiency, effectiveness).
- The strategy of funding local CSOs to lead the work and employ local staff contributed to projects that were a) locally designed to respond to the expressed culture and the needs of people the organisations targeted and b) locally owned (programme level – effectiveness, economy).
- The programme’s output delivery scores over the course of the programme ranged from A to A+ in all programme reviews. All of the output targets were achieved on time and within budget (programme level - efficiency).
- The programme outcomes were achieved (as documented in the programme’s annual reviews and end-of-programme evaluation, and summarised in Section B) on time and within budget (programme level – effectiveness).
- Comic Relief scrutinised partners’ alignment with the VfM principle of economy during application, assessment and grant management (including monitoring visits), including practices on procurement, planning and budgeting processes, and financial management (programme and funded partner level – economy).
- Comic Relief supported funded partners to adapt activities and budgets where necessary to respond to changes in context (for example, the COVID-19 pandemic), staying within project budgets. All variances of spend over 20% for any budget line were negotiated with Comic Relief’s portfolio manager, and changes to budgets were assessed on VfM criteria (programme and funded partner level – effectiveness, economy).
- Collaboration across the cohort of funded partners and with other stakeholders including government created efficiencies (funded partner level – efficiency).
- Through Comic Relief’s communications work, the issues addressed by funded partners through their projects are also given a platform to raise awareness. This includes gathering case studies and stories using project participants’ own voices and sharing them via social media and through films broadcast on the BBC on Red Nose Day. Work is currently underway to gather further stories using Kenyan filmmakers working with funded partners to celebrate the results of the programme and raise further awareness. Funded partners will also be able to use these stories for their own fundraising and communications (funded partner level – efficiency).
- Funding organisational strengthening resulted in improved capacity of funded partners in a variety of areas, enhancing the likelihood that funding will lead to benefits which remain after funding ends. All of the funded partners identified changes at the organisational level related to improved quality, impact and/or reach of their work and/or organisational functioning, which they believe will be sustained over the long term, as documented in the OS Learning Study (programme and funded partner level – effectiveness, sustainability).
- The programme incorporated a coordinated learning agenda, supporting funded partners to generate, share, and disseminate learning. This resulted in a network of mental health CSO actors with a strong vision of collective action to strengthen work in the sector and engage all stakeholders in this vision (funded partner level – effectiveness, sustainability).
- The programme selected funded partners who worked directly and/or indirectly with people who are marginalised and excluded due to mental health conditions, and thus responded to the principle of ‘leaving no one behind’ (programme level – equity).
- Some funded partners’ projects targeted specific groups who are further excluded and/or disadvantaged by their experience, disability, or living environment (partner level – equity).

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

Over the final year, and for the duration of the programme, Comic Relief continued to identify and manage risks for the Mental Health and Wellbeing in Kenya programme at the individual grant (project) and programme level.

A programme level risk register, summarising each risk and mitigating actions, was in place, which was updated and reviewed with FCDO on a quarterly basis throughout the programme period. In addition, Comic Relief’s Funding Team, which oversees all investments, updates its risk register each quarter. This is reported to the Executive Leadership Team and Audit and Risk Committee on a quarterly basis. Comic Relief also has an Assurance function which oversees the management of risks across all of Comic Relief’s work.

Comic Relief completed FCDO’s standard Due Diligence Assessment in 2020. The Assessment found adequate arrangements were in place regarding internal control and risk management. It recommended updates to several organisational policies, which were completed. As this is updated every 3 years, another Due Diligence Assessment began in 2023 and review of all documents is currently underway.

At project level, grant management procedures include risk as one of the considerations at assessment stage. The structured approach to reporting by grant holders to Comic Relief and follow-up meetings to review progress and issues enables identification of risks and mitigating actions. Portfolio managers conduct an analysis of risk against key risk categories for each grant in Comic Relief’s grant management system (Salesforce), which is reviewed every six months.

The main factors affecting the risk exposure of the Mental Health and Wellbeing in Kenya programme over the last year were the cost of living crisis; a safeguarding incident concerning one funded partner that required a significant response; and the ongoing and imminent planned closure of each of the projects.

However, the main factor affecting the risk exposure of the Mental Health and Wellbeing in Kenya programme over the duration of the programme was the global COVID-19 pandemic. Most risk levels heightened during the initial months of the outbreak (from March 2020) but the situation continuously shifted across the sub-Saharan African countries, including Kenya, where FCDO and Comic Relief joint-funded programmes were operational. In this programme, the COVID-19 pandemic impacted all projects that were live when governments began to introduce restrictions on movement at the end of March 2020. The situation affected the delivery of activities, because many communities could not be visited by partners, and, even if travel was possible, the need for social distancing meant that group meetings could not be held. Grant holders’ offices were closed and some staff had limited capacity to work from home. Grant managers discussed and agreed mitigation measures with all grant holders individually. They included revision of work plans, re-scheduling and revising itineraries of final evaluations, and re-assigning some funds for the purchase and distribution of personal protective equipment (PPE) to communities. Organisations providing frontline mental health services sourced PPE and continued to deliver. The prevalence of mental health conditions increased as a result of the COVID-19 pandemic, leading to increased demand for partners’ services.

Further information on risks that have faced the delivery of the Mental Health and Wellbeing in Kenya programme, against each of FCDO’s specific risk categories, is outlined in the table below. It should be noted that the risk levels are post mitigation and capture the status at the end of the Mental Health and Wellbeing in Kenya programme. The overall residual risk level of the Mental Health and Wellbeing in Kenya programme remained as moderate.

Overall, Comic Relief has delivered within risk appetite over the life of the programme.

Category	Residual risk rating	Update for Final Year of Programme and Reflections on Grant as a Whole
Strategy and External context	Moderate/Minor	The three risks linked to strategy and external context include (1) shifts in political contexts such as civil unrest, increasing restrictions on civil society or reduction in government backing of projects (reduced in the final year from Moderate to Minor), (2) pandemics and other infectious disease outbreaks impact projects (remained at Moderate), and (3) changes to the climate (remained at Minor). / The overall residual risk slightly reduced to Moderate/Minor, compared to the previous reporting period. Political will remained high, evidenced by the earlier passage of the Mental Health Amendment Bill and its signing into law, and the development of a national suicide prevention strategy; and with peaceful national elections in 2022 and no other political violence in 2023. In the final year there was evidence of further high political will by the government of Kenya, with more budget being allocated for mental health expenditure at county level, and attendance of government representatives at the Mental Health Summit organised by Basic Needs Basic Rights Kenya in October 2023. / The risk associated with pandemics and other infectious diseases appeared to reduce in severity linked to the development of COVID-19 vaccines but remained Moderate. There were no further lockdowns in 2023 so partners could implement activities as planned. / The risk linked to climate change remained as Minor, as although severe drought affected areas such as Kenya’s Arid and Semi-Arid Lands region, drought did not affect the areas where the projects were being implemented. / Robust programme mitigations for external context risks were in place throughout the programme, including monitoring of the political environment, and advocating for improved prioritisation for mental health services in Kenya. Funded partners monitored contextual risks which were reported every six months. In the event of significant difficulties, the Portfolio Manager would have worked with the partner to agree a revised plan and budget, but this was not necessary.
Financial and Fiduciary	Moderate	The primary financial and fiduciary risk during the entire programme reporting period was that (1) funds were not used for the intended purposes or were not properly accounted for (remained at Moderate). In addition, there is a risk around (2) the sustainability of partners if they experience falls in funding levels or cuts to donor funding (remained at Moderate). / There have been no incidents of fraud during this annual review period; there was one grant cancelled due to fraud in 2020. / Mitigating actions include routine financial due diligence checks by Comic Relief as part of the grant management process, which includes a review of recent annual accounts along with detailed reviews of expenditure reports and requests for changes to budgets. Funding agreements with grant holders set out requirements for financial management and reporting of expenditure. Grant holders are expected to sign a similar agreement with their local partners that use programme funds. Furthermore, Comic Relief staff review financial procedures as part of the learning and support visits (previously known as monitoring visits). The financial health of grant-holders is also being closely monitored.
Policy and Programme Delivery	Moderate	The two key risks linked to policy and programme delivery include (1) global events leading to increased costs for partners to deliver projects (remained at Moderate) and (2) non-achievement of value for money (remained at Moderate). / The overall residual Delivery risk level remained as Moderate, as per the previous reporting period. In the previous reporting year, a new Risk linked to the sharp rise in the cost of living in Kenya, a failed subsidy for the staple food (maize), rising fuel costs, and a weakened local currency, was added. Comic Relief mitigated this risk by providing a £15,000 cost of living top up grant to each funded partner in the final year of the project, using Comic Relief’s own funds, which funded partners could use flexibly. / In the previous reporting year, the risk to project implementation due to COVID-19 was closed, as restrictions ended and partners resumed activities as normal. / Mitigating strategies included: Comic Relief allowed funded partners to adjust their project plans, targets and budgets, in line with Comic Relief policy, if they experienced challenges related to global events and contextual challenges such as the increase in the cost of living. Comic Relief also continued to monitor value for money through monitoring visits, scrutinising narrative and financial reports, and re-assessing value for money if partners requested changes to their plans and budgets.
Operational	Moderate	This risk most recently concerned Comic Relief having insufficient internal capacity to effectively oversee implementation of the programme and ensure its objectives are met. This risk remained as Moderate, with no particular issues in the final year of the programme, following an earlier more turbulent period at Comic Relief due to a new strategy and internal organisational change. Management of these challenges was adequately covered throughout the life of the programme, thanks to the following mitigating strategies: consistent oversight from the Funding Leadership Team; regular supervision of all Comic Relief staff, including check-ins on capacity and objectives; and opportunities for support from other team members if required. In the final year of the programme, a new Director of Funding was appointed. / Earlier in the programme there were concerns that there might be cuts to the UK Aid budget, but these did not materialise and the programme remained unaffected, and the risk was closed.
Safeguarding	Major	The primary risk under this category is that grant holders and their delivery partners have insufficient safeguards and reporting measures in place to protect the people they are working with from harm. / The Safeguarding risk remained at Major during this reporting period. The risk description changed throughout the life of the programme, from a focus on heightened safeguarding risks (particularly violence against women, girls and other vulnerable people) during the COVID-19 pandemic to responding to a major safeguarding incident centred around one funded partner during the final year of the programme. To respond to the latter, Comic Relief used its own funds to recruit independent investigators to find out what had happened and make a plan to respond to the incident and help to support survivors and witnesses. FCDO agreed that Comic Relief could use part of this programme’s underspend to make grants to two organisations who specialise in mental health delivery to survivors of sexual violence, and this funding was awarded in late 2023. / Comic Relief has a comprehensive Safeguarding Framework in place which meets all FCDO safeguarding requirements. Safeguarding is included in the assessment of all grants, including a review of child protection/safeguarding policies. Comic Relief monitors grant holder capacity and provides support where required, including allowing project funding to be allocated to strengthening safeguarding policies and practice where needed. Safeguarding is monitored through on-going grant management and included in monitoring visits. Furthermore, all partners are required to report safeguarding incidents within their organisation to Comic Relief and Comic Relief completes an investigation where issues arise. All staff at Comic Relief have received refresher training on their responsibilities and on reporting concerns on safeguarding or any other wrongdoing; Comic Relief has introduced a new facility to allow people outside of Comic Relief to report anything that may cause them concern.
Reputational	Moderate	The key risk is that the credibility of Comic Relief, FCDO and/or its funded partners is damaged as a result of the behaviour/actions of Comic Relief or its funded partners, including poor project management, the misuse of funds, a failure to safeguard people intended to benefit from the programme or other issues compromising the successful delivery of the Programme. / There have been no changes in the residual risk rating since the last annual review period. / To mitigate against this risk, reputational risk was assessed as part of the assessment phase for all projects to be funded. Mitigating actions were recommended by the assessor. Through ongoing grant management (including monitoring visits), grant managers were able to identify any potential for reputational risk to the grant holder, their implementing partners, Comic Relief or FCDO and support them to mitigate this risk. Comic Relief's Conditions of Grant sets out the expectation for grant holders to notify Comic Relief of any major changes to the project or the delivery organisations. This includes whether any allegations have been made against them or if any negative publicity has been received. Portfolio managers are supported in their response and follow-up actions by Comic Relief's dedicated Assurance Team who also report relevant concerns to FCDO. / A potential area of reputational risk arose as a result of the safeguarding incident involving a funded partner; this was mitigated by working closely with survivors and witnesses to provide support; and working with relevant actors in Kenya who support survivors with their legal cases and provide other forms of support. Comic Relief has made grants to two organisations providing specialist mental health support to survivors of sexual survivors in the area where the violence took place in order to provide ongoing support.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Quality and timeliness of narrative reporting and audited financial statements
Comic Relief reported to FCDO on the Mental Health and Wellbeing in Kenya programme twice annually through the Annual Review and a six-month update, as well as this Project Completion Report at the end of the project. All narrative reports and annual audited accounts were submitted in a timely manner. Comic Relief has a full and comprehensive audit annually. This includes a review of all individual fund balances and checks all grant agreements to ensure that Comic Relief is spending in line with conditions of grant from funders, including all FCDO funds. In evidence in the audited accounts, Comic Relief has a separate line for FCDO funds, under Restricted Funds. This line includes all income from FCDO in the year and all expenditure against those funds is signed off by the auditors.
[note] In Comic Relief’s most recent audited financial report (2022-2023), this is found in note 20. This line includes all income from FCDO in the year and all expenditure against those funds.

The programme’s funded partners reported to Comic Relief every six months. Audited financial statements were submitted to Comic Relief by each funded partner with their annual report (narrative and financial) each year. Portfolio Managers, and Accountants (if an individual grant is over £500,000), reviewed the statements to ensure the funded partner continued to be financially sound, that Comic Relief funding was correctly recorded in the accounts and that the funded partner organisation continued to be governed well.

Proactive dialogue on risks and updating delivery chain maps
Comic Relief has a reporting protocol in place for reporting serious incidents and concerns to FCDO and an agreed approach to investigation and reporting thereafter. Comic Relief and FCDO are committed to ensuring that their funded partners are protecting the people whose lives they intend to benefit. As set out in Section E, a comprehensive risk register for the Mental Health and Wellbeing in Kenya programme was put in place and reviewed on a quarterly basis with FCDO. An up-to-date delivery chain map was submitted with each Annual Review and with this Project Completion Report.

Quality of financial management

Comic Relief provided timely forecasting and financial reporting in each reporting period, showing quarterly forecasts and expenditures.

Final Year (April 2023-March 2024)
The forecast of spend of FCDO’s contribution (which includes all costs: partner grants, MEL and management costs) was £208,004 as set out in the table below, against the final period’s actual expenditure of £2,084,716.

	Forecast	Actual
April to June 2023 (Q1)	£124,803	£124,803
July to September 2023 (Q2)	£31,691	£64,781
October to December 2023 (Q3)	£30,178	£110,149
January to March 2024 (Q4)	£21,332	£25,625
Total	£208,004	£376,552.05

Overall Programme Period
The table below reports a summary of spend of FCDO’s contribution (forecast and actual) over the programme period. As the key cost driver of the programme was payments for partners’ grants, the accuracy of forecasts was affected by implementation challenges faced by funded partners resulting from the COVID-19 pandemic, particularly in Years 2 and 3 of the programme. Annual underspend was primarily related to necessary adjustments to partners’ activities with subsequent changes to budgets over the year (primarily due to project delays and changes as a result of COVID-19 affecting partners’ work) and across years. Underspend was carried forward and, £2,084,716 of the FCDO grant was used by the end of the programme period.

	Forecast	Actual
Year 1 (April 2019-March 2020)	£30,500	£28,001
Year 2 (April 2020-March 2021)	£513,376	£503,503
Year 3 (April 2021-March 2022)	£458,123	£441,346
Year 4 (April 2022-March 2023)	£787,697	£763,658
Year 5 (April 2023-March 2024)	£208,004	£376,552.05
Total	£1,997,700	£2,084,716

Monitoring and disposal of assets.
There were few assets procured under the programme, and these were typically for office equipment, hardware and software for funded partners’ work. Procurement of assets by funded partners came from Comic Relief’s contribution to the programme. The purchase and management of all assets, therefore, followed Comic Relief’s procurement and asset management policies, which state that where capital expenditure is approved, it must be clearly demonstrated that any assets acquired will be used during and at the end of the programme on activities in the spirit of the original grant agreement. Grant recipients had to show that no conflicts of interest existed between the parties acquiring or providing the assets and that they complied with relevant national laws and guidelines on the disposal of assets. As part of project monitoring visits, funded partners were asked about assets purchased as part of the grant, and were asked to see evidence of how assets were being used and logged. Comic Relief’s Monitoring Visit guidance includes information around assessing policies and practices related to procurement and management of assets, ensuring that project staff were confident in using these policies and procedures and looking for evidence of these being followed as part of grant management. When projects ended, Comic Relief asked grant holders to explain the process for handover/use of assets, and was satisfied that all assets will continue to be used in the spirit of the original grant agreement until the end of the asset’s useful life.

VfM measures of Economy and Efficiency
VfM is further elaborated in Section B (Effectiveness and Equity in relation to programme outcomes) and Section D (Value for Money Performance). This section summarises the key programme-level measures of Economy and Efficiency.

Economy
- The programme’s funding structure provided an economic way for FCDO to invest in an experienced and knowledgeable grant-making and management organisation to implement a focused programme investing directly in a group of Kenyan CSOs. Comic Relief matched FCDO’s £2 million investment for grant funding, organisational development and programme monitoring, learning and evaluation, and additionally invested £630,607 of its own funds to supplement FCDO’s £100,000 contribution for programme management.
- At the application and assessment stage, applicants were scrutinised on economy – for example exploring procurement policies, financial management systems and skills, programme scoping and project planning to ensure that robust checks and balances were in place. Assessment meetings for new funding included detailed interviews on these areas.
- All monitoring visits to existing funded partners also routinely scrutinised VfM economy, including collecting updated data on procurement, financial management and planning.
- All variances of spend over 20% for any budget line had to be negotiated in advance by funded partners with their Comic Relief Portfolio Manager.
- Similarly, any annual underspend was renegotiated at year end and re-budgeted for the following financial year.

Efficiency
- The programme was situated within Comic Relief’s Funding team, alongside other FCDO-Comic Relief co-funded programmes, benefitting from Comic Relief’s established grant management systems as well as good practice in grant making and management as well as learning from other work on mental health and programmes being delivered in similar contexts, generated across the Directorate, providing efficiencies and economies of scale.
- Comic Relief’s commitment to learning meant that budgetary resources were committed for dissemination of learning with the aim of influencing decision makers and promoting replication by others. Funded partners were also required to report annually on dissemination of project learning. Opportunities for funded partners to be supported to generate and share learning from the work they delivered were built into programme support.
- The Learning Networks have been led by a Learning Coordinator, and were an opportunity for organisations to share learning, collaborate and advocate for collectively identified mental health issues or policy gaps at a national level.
- Through Comic Relief’s communications work, the issues being addressed by funded partners through their projects were also given a platform to raise awareness.
- Lastly, individual project VfM is verified by independent evaluations undertaken at the end of funded projects. For example:
  - BNBR demonstrated value for money by working with mental health champions to facilitate social contact events and other training, while BNBR played a facilitative role. Also, mentorship of champions has enabled them to reach other youth with mental health problems without the project having to recruit personnel for that. The project aimed to reach 1 million people through a public mass media campaign but was able to reach almost 3 million people at very low cost which is a testament of how effective and efficient social media is as a tool for information dissemination.
  - HERAF used strong advocacy strategies to seek for increased investments in mental health programmes in Kenya by demonstrating value for investment in the sector, especially at County government levels.
  - HRK established and trained Interpersonal Therapy Groups (IPTGs) and community health volunteers through orientations and on-the-job training to strengthen their capacity. This has resulted in quick uptake of mental health interventions at the community level and demonstrated value for money.

Programme-level approach to monitoring and evaluation

The programme embedded a strong learning component throughout, with an emphasis on partner-led bottom-up learning and reflection, and not just quantitative data extraction.

Funded Partners submitted Funding Overview Forms at the start of the programme setting out their goals for the funding, their learning ambitions, their project aims and their quantitative and qualitative targets. Comic Relief reviewed these forms and gave feedback particularly where targets could have been more meaningful (e.g., Proposing qualitative indicators over quantitative ones) and/or realistic (e.g., Proposing the reduction of overly high targets). Funded partners continually reflected on their work and referred back to their Funding Overview Forms, revising them when necessary. This approach ensured funded partner targets remained realistic despite changes to context and operating environment.

Output, outcome and impact indicators were selected at the programme inception phase, and the data from all projects, sourced from funded partner annual reports, was collected and aggregated once a year. This included quantitative data, e.g., on the number of total beneficiaries, and qualitative data, e.g., on case studies/stories of change demonstrating impact. The annual outcomes data gave a sense on how the programme was progressing in terms of impact year-on-year.

An independent external evaluation, led by Picture Impact and Green String Network, took place from January to December 2023. The evaluation team was deliberately selected because of their participatory approach to research, their use of creative and inclusive research methods, their background in mental health, and their geographic proximity to the partners. The evaluation involved in-person visits to funded partners and numerous online workshops, alongside secondary data analysis where the evaluators reviewed and analysed funded partner reports and other programme documents. During the final reporting stage of the evaluation, the partners were invited to feed back on the report and case studies/stories of change, and to edit/challenge any findings relating to their work. The final evaluation report was written to a high standard, it contained rich data and insights, and the recommendations will be taken on board both by Comic Relief and hopefully by funded partners as well. A management response has also been produced and shared with FCDO.

There was a strong collective learning element on the programme, whereby the funded partners came together frequently as a learning network, guided by the Learning Coordinator to reflect on their work, learn from peer organisations, discuss shared challenges, support others, and collaborate on joint advocacy. The learning network developed two learning outputs to help advance their work going forwards, described in Section C (Output 2). While some partners felt they would have benefitted from even more structure, coordination and opportunities for collaboration and networking, the feedback from the partners taking part in the collective learning was overwhelmingly positive.

Date of last narrative financial report	20 February 2024	Date of last audited annual statement	22 February 2024