## Annual Review
Title: The EdTech Hub (Educational Technology Hub)
Programme Value £ (full life): £36,297,928		Review date: 15 June 2025
Programme Code: 205288	AMP start date: 15th March 2019	AMP end date: 16 June 2027

Summary of Programme Performance
Year	2018	2019	2020		2021	2022	2023	2024	2025
Overall Output Score	A	A	B		A	A	A+	A	B
Risk Rating	Major	Major	Major		Major	Moderate	Moderate	Moderate	Moderate
DevTracker Link to Business Case:				54104789.odt
DevTracker Link to results framework:				https://iati.fcdo.gov.uk/iati_documents/90000555.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
The Education Technology (EdTech) Hub programme is a global applied research initiative designed to provide rigorous evidence and policy advice to decision-makers. The programme is funded centrally by the Foreign, Commonwealth & Development Office (FCDO) Research and Evidence Directorate (£20.3 million for research components) and the Girls' Education Department (£16 million for innovation and technical assistance).
The programme is established as a recognised brand within the EdTech sector. The EdTech Hub programme aims to address evidence gaps regarding the effective use of technology in education within low- and middle-income countries. Its primary goal is to facilitate decision-makers in planning and funding impactful technology-enabled interventions that enhance foundational learning for all children. This is achieved by providing access to research, innovation, and technical assistance to ascertain 'what works' in educational technology and how such interventions can be scaled effectively.

This annual review covers the reporting period April 2024 -March 2025. This year, FCDO aligned closely with the Gates Foundation (co-funder of the EdTech Hub) in our respective reviews of the overall performance of the programme (further details in Section G).

The EdTech Hub programme comprises four interrelated components, collectively working towards a unified theory of change (the entire programme will be referred to as the ‘EdTech Hub programme’ throughout this document):
1. Main Component (£28 million): An 8-year contract led by Results for Development (R4D), which forms the core of the EdTech Hub (2019-2027). We will refer to this component as the ‘EdTech Hub’.
  [note] R4D lead a consortium that includes BRINK, Open Development and Education (ODE), Jigsaw Consult, and the University of Cambridge Faculty of Education (UoC).
2. World Bank Trust Fund (£2 million): Focused on global leadership in EdTech and the establishment of an EdTech Policy Academy (2019-2027).
3. AI Observatory and Action Lab (£3.5 million): A two-year Accountable Grant led by the EdTech Hub on Artificial Intelligence (AI) - launched this reporting period (2024-2026).
4. Programme Funded Posts (£2.8 million): Three posts aimed at enhancing FCDO's global profile and leadership in the EdTech sector, with two of these roles currently filled (one in research and one in policy) (2019-2027).
In addition to the main FCDO EdTech Hub contract, R4D secured funding from a range of partners, including the Gates Foundation, UNICEF, and several FCDO country offices (Tanzania, Malawi, ASEAN, Ghana), as well as UNESCO, the Jacobs Foundation, and others. Total funding amounted to over £18.7 million. A full list of partners is provided in Annex A.

The main component of the EdTech Hub adopts an integrated approach that combines research, innovation and technical assistance to enhance educational outcomes through technology in Low Income Countries (LICs) and Lower Middle-Income countries (LMICs), with a primary focus on seven countries. The integrated approach is detailed below.
[note] Tanzania; Sierra Leone; Malawi; Kenya; Ghana; Bangladesh and Pakistan

Research: The EdTech Hub allocates around 70% of its budget to research, currently comprising 24 studies, including Hub-Led Research (HLR) and sub-contracted studies. 17 have been completed, with six ongoing studies and 22 new shorter-term outputs designed this year. The research covers eight themes.

Innovation: The EdTech Hub promotes innovation through 'sandboxes'. These are pilot projects that allow for collaboration with local EdTech implementers. These controlled environments facilitate the testing and development of new ideas through iterative experiments, with three sandboxes initiated in the current reporting period.

Technical Assistance: The EdTech Hub provides technical assistance (TA) to government partners via its Helpdesk service, supporting over 70 countries, in addition to more bespoke TA in in our focus countries. Additionally, the EdTech Hub supports the World Bank’s EdTech Policy Academy, a two-week hands-on clinic designed for education staff, partners, and representatives from client countries to tackle specific policy challenges.

In November 2024, the EdTech Hub launched the AI Observatory and Action Lab, an initiative funded by the Accountable Grant component of the EdTech Hub programme. In partnership with Fab Inc, this initiative encompasses a range of activities aimed at understanding and anticipating challenges, conducting real-world testing, and delivering clear, timely, and actionable guidance to help education system decision-makers ensure that the integration of AI in education across LICs and LMICs is both equitable and effective.

Summary supporting narrative for the overall score in this review
The EdTech Hub programme has scored a B during this reporting period, reflecting both successes and areas for improvement.
Notably, the finance and programme management aspects have shown good performance, with variances from forecast financial values exceeding targets. Additionally, the EdTech Hub has made commendable progress in engaging with research leadership from LICs and LMICs and promoting female authorship, demonstrating its commitment to inclusivity.
The recent introduction of the AI Observatory and Action Lab has generated interest within the global education sector and begun to produce valuable knowledge products. As this component is only one-month post-inception, however, its overall effectiveness is yet to be fully assessed.
Output 1 faced challenges, however, with several milestones unmet, including the target for publishing research articles. This shortfall underscores the need for enhanced strategies in research dissemination and communication. The Gates Foundation's review further highlighted the necessity of improving cohesion and strategic integration within the EdTech Hub's initiatives at the country level to effectively address these issues.
As the programme enters its final stages, the EdTech Hub must sharpen its strategic focus, align more closely with country partner priorities, and ensure that its research and technical assistance efforts are effectively integrated to support measurable outcomes in the education sector.

Major lessons and recommendations for the year ahead
Overall programme recommendations are presented in this section. Output and programme-management specific recommendations are presented in sections C and F of this review.
Recommendation 1: Improve timeliness of research publications by March 2026
To enhance the effectiveness of research outputs, the EdTech Hub should refine its publication process to ensure the timely acceptance and dissemination of articles in peer-reviewed journals.
Recommendation 2: Develop a communications and engagement strategy by March 2026
The EdTech Hub should establish a robust communications and engagement strategy designed to effectively leverage key stakeholders and policymakers. This strategy should incorporate targeted initiatives to actively promote research findings and stimulate discussions on critical topics, thereby enhancing the visibility and reach of its knowledge products. Additionally, it should focus on strengthening engagement with the intended audience through improved communication efforts, including website enhancements, to ensure that insights effectively inform decision-makers and drive impactful educational practices.
Recommendation 3: Strengthen implementation planning and evidence integration in focus countries. The EdTech Hub should develop comprehensive implementation plans for its strategies at the country level by November 2025, including clear legacy plans for FCDO funded products and tools where possible and appropriate. To ensure sustainability and effective follow-up on catalytic initiatives already invested in, such as the accountability dashboard in Ghana, it is essential that the EdTech Hub retains an in-country presence aligned with its integrated approach.
Recommendation 4: Prioritise smooth and effective close-out of ASR and HLR research studies by March 2026. This process should prioritise successful submissions to academic journals and the dissemination of findings through multiple channels, including policy briefs and presentations at regional and global conferences where feasible. Furthermore, the EdTech Hub should actively integrate research evidence into actionable policy recommendations and implementation strategies. This involves utilising insights from ongoing research to inform the development of national education strategies, ensuring that these strategies are firmly based on evidence of effective practices.
Recommendation 5: AI Observatory and Action Lab should refine workstreams to prioritise tangible, context-specific impacts. In collaboration with the Steering Group, the EdTech Hub should ensure that future lab initiatives effectively drive behavioural change and support the integration of evidence into EdTech and AI decision-making. Additionally, FCDO recommends that communications and engagement activities be tailored to the immediate needs of policymakers, with their effectiveness evaluated through targeted stakeholder feedback.
Recommendation 6: Revise the Value for Money (VfM) framework by September 2025. The EdTech Hub should revise the VfM framework to incorporate indicators for evaluating cost-effectiveness. This includes developing and implementing at least three new cost-effectiveness indicators.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The Theory of Change (ToC) for the EdTech Hub programme (Annex B) has been updated to reflect the programme’s evolution and more clearly outline how the EdTech Hub achieves its purpose and vision, detailing the pathways from interventions to desired outcomes within broader education systems. This updated ToC aligns more closely with the goals and impact of the FCDO Business Case and logframe. This ensures that decision-makers can access and effectively use evidence to spread and scale more effective, inclusive, equitable and cost-effective EdTech programmes, ultimately improving learning for all children. The review of the logframe and ToC, identified as a recommendation in the 2023-24 Annual Review, has been successfully completed.
The revised ToC now more clearly outlines how the EdTech Hub aims to fulfil its purpose and vision, detailing the various pathways from interventions to desired outcomes within the broader education systems in which it operates. Additionally, a new Output 4 has been added to the logframe to track progress against the new AI Accountable Grant.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme's progress towards its expected outcomes and impact reflects a mixed picture, showcasing both successes and areas needing improvement, as outlined in Table 2. The review conducted by the Gates Foundation provides additional insights, with several examples included in this assessment to illustrate the main findings.
Table 2: EdTech Hub logframe outcomes
No	Outcome	Outcome indicator	Milestone target(s) for this review	Progress this reporting period
1	Longer-term outcome: Evidence generated by EdTech Hub influences decision-makers and the education technology ecosystem	1.1 Examples of EdTech Hub influencing the global research agenda on technology for education	3	3
		1.2 Examples of decision makers drawing on learning generated and / or catalysed by the Hub, disaggregated by those based in low- and middle-income countries (LMICs), also disaggregated by AI Observatory & Action Lab	Main: 16 / AI: N/A	Main: 17 / AI: N/A / Based in LMICs — 17
2	Robust and relevant research is accessed and used	2.1 Percentage of the Hub’s knowledge products that have intellectual leadership from a) researchers and organisations in LMICs and b) female researchers	53%	54% (LMIC) / 79.23% (Female authors)
		2.2 Examples of interactive discussions on EdTech research evidence and learning, also disaggregated by AI Observatory & Action Lab	Main: 18 / AI: 1	Main: 20 / AI: 1
		2.3 Average views of EdTech Hub knowledge products, disaggregated by geography	264	228.26
		2.4 Altmetrics composite index of engagement with knowledge products produced by the Hub	25% from rolling baseline	6.66%
3	EdTech Hub engages in partnerships which catalyse further interest, research, and investment in technology for education	3.1 Examples where the Hub brokered a relationship on specific research, in a specific country or, on a particular course of action	10	11
		3.2 Percentage of partners reporting positive feedback on the Hub’s role in facilitating collaboration and catalysing further interest in technology for education, also disaggregated by AI Observatory & Action Lab	Main: 80% / AI: N/A	75%
[note] 75% of the respondent rated the Hub with a score of 4 or more (on a scale of 1 to 5, with 5 being the highest)

The EdTech Hub has made notable progress in influencing the global research agenda on educational technology. Key examples include its impact through Design-Based Implementation Research in Malawi (Box 1). The EdTech Hub has also met expectations in enabling decision makers to utilise insights generated or catalysed by its initiatives. This is illustrated by the Gates Foundation's review of the Teacher Continuous Professional Development (TCPD) work in Tanzania (Box 2) and the at-scale research that informed blended learning policies for teacher development in Bangladesh (Box 3). These examples reflect the EdTech Hub's contributions to the EdTech ecosystem. Additionally, the programme has engaged with research leaders from low-income countries (LICs) and low- and middle-income countries (LMICs) and promoted female authorship, highlighting its commitment to inclusivity and representation in research.

Box 1: Embedding Evidence for Impact: Strengthening Malawi’s National Numeracy Programme through Design-Based Research
Through design-based implementation research, EdTech Hub provided evidence-informed technical assistance to Malawi’s National Numeracy Programme (NNP), directly shaping teacher professional development. The Hub’s rapid research and user testing led to the development and refinement of Teacher Learning Circles (TLCs) and guides, aligned with the new White Rose curriculum. These contributions were integrated into the extended pilot phase, resulting in improved TLC training for master trainers and positive learning outcomes.

Box 2: Gates Foundation Case Study - Tanzania
In Tanzania, the EdTech Hub has established a strong connection between its research and country teams, particularly in the area of Teacher Continuous Professional Development (TCPD). The EdTech Hub's study evaluates the effectiveness and sustainability of the government’s technology-supported, decentralised, and school-based TCPD programme aimed at enhancing teaching and learning in rural primary schools. During the first phase, the EdTech Hub shared emerging insights with the government, facilitating the refinement of the national programme and ensuring that research directly informs policy and practice.

Box 3: Leveraging EdTech Hub Insights to Transform Teacher Professional Development in Bangladesh. In Bangladesh, the at-scale research led by The Open University and University of Dhaka engaged policymakers to influence future blended learning programmes for teacher professional development (TPD). Through interactions with stakeholders from the Directorate of Primary Education and Aspire2innovate, research findings from the 3MPower project highlighted the need for an interconnected approach to blended learning, combining online and face-to-face training. This understanding resulted in co-developed policy briefs, a pedagogical framework for TPD, and strategies for headteachers to support continuous professional development, assisting the design of the next national Primary Education Development Programme to enhance teaching quality.

While the programme has achieved significant successes, there remain important areas for improvement. Insights from the Gates Foundation’s highlights that, although the EdTech Hub is responsive to government demand and engages a range of stakeholders, its activities could be more strategically aligned. The EdTech Hub’s impact would be further enhanced by integrating research and evidence more systematically into its country-level engagement, ensuring that activities contribute to a clear, overarching strategic direction and national priorities.

Box 4: Gates Foundation Case Study - Sierra Leone
In Sierra Leone, the EdTech Hub collaborated with the government, World Bank, and UNICEF to develop the national edtech strategy through a two-day workshop. This workshop aimed to capture the government’s initial priorities while involving diverse stakeholders to validate and shape these priorities. There is potential for the EdTech Hub to enhance its role by actively influencing the strategy with evidence and best practices. Moving forward, positioning itself as a constructive partner, as requested by the Minister of Basic and Secondary Education, could help ensure that the strategy effectively addresses learning outcomes.
In addition, while the average views of EdTech Hub knowledge products did not meet the overall target, it is notable that products accessed via the evidence library achieved a higher average viewership (317 views) compared to those accessed through the main website (248 views). The Altmetrics composite index of engagement stands at 6.66%, significantly below the 25% target. Looking deeper, website engagement has declined, with an 11% drop in average monthly visitors and a 10% decrease in sessions. In response, The EdTech Hub is adopting the Gutenberg framework, a content management system, to make navigation easier for users, and enhance search engine optimisation (SEO) for better visibility in search results. Although newsletter subscribers have increased, engagement rates have varied, leading to the need to redesign content strategies. Overall, these statistics highlight the need for improved approaches to enhance the visibility and impact of the EdTech Hub's outputs.
[note] The Altmetrics composite index measures engagement across the Hub's library, social media, newsletters, and citations.
While the EdTech Hub has effectively brokered partnerships, partner feedback reveals opportunities for improvement. Although 75% of partners provided positive feedback regarding the EdTech Hub's role in facilitating collaboration, this is slightly below the 80% target. The EdTech Hub achieved ratings of 80% or more across seven outcome areas, except for the investment of additional resources. Significantly, 100% of partners reported acquiring valuable knowledge and evidence about EdTech, and 92% have actively utilised the insights shared by the EdTech Hub. This feedback underscores the importance of the EdTech Hub strengthening its collaborative efforts to ensure that partners feel fully supported and engaged.
[note] Feedback was solicited from 43 partners, resulting in 28 responses, which reflects a 65% response rate. From July to November 2024, partners participated in a survey consisting of 15 questions, of which 6 were quantitative and contributed to the overall scoring.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The EdTech Hub's goals continue to aim to align with existing and emerging FCDO priorities, focusing on enhancing educational outcomes through digital development, promoting systemic change for marginalised groups, and advancing education equity. The recent introduction of three new focus topics of Special Educational Needs and Disabilities (SEND); climate; and education in emergencies and protracted crises, underscores the EdTech Hub's commitment to tackling pressing challenges, contributing to sustainable development and reaching the most marginalised learners. Furthermore, the launch of a new AI initiative is designed to empower decision makers, ensuring that the integration of AI in education across LICs and LMICs is both equitable and effective.
To date, the EdTech Hub has produced 531 knowledge products, with 506 (95%) classified as global public goods. The demand for technical support from the EdTech Hub is evident with 403 technical support requests over the lifetime of the programme and 24 new partnerships, resulting in over £18.69m in additional investment to the main contract.
The EdTech Hub's comparative advantage is based on its expertise and established relationships with ministries of education and the donor community, which facilitate its efforts to address high-priority evidence gaps. Its focus on providing evidence-based, cost-effective edtech solutions supports its role within the sector.

## C. DETAILED OUTPUT SCORING
Output Title	Robust research, advice, and hands-on support is implemented to plan
Output number:		1	Output Score:	B
Impact weighting (%):		80	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of articles published in agreed peer-reviewed journals, disaggregated by a) open access and b) gender of author	3 (17 cumulative)	Milestone not met: / Published: 2 (16) / 2 open access / 2 female authorship
1.2 Number of studies from Hub’s core research portfolio completed.	3	Milestone moderately not met: 2
1.3 Number of studies as part of the three new focus topics — climate; emergencies and protracted conflict; and SEND — disaggregated by (i) initiated (ii) completed, and (iii) study type	11	Milestone exceeded: 18 / (i) Initiated – 18 / (ii) Completed – 4 / (iii) Primary research – 8 / Secondary research – 10
1.4 Number of collaborative engagements to provide hands-on support and advice initiated, disaggregated by a) Helpdesk requests; b) innovation (sandbox); c) in-country technical assistance	70	Moderately not met: 67 / (37 FCDO main contract) / Helpdesk – 24 (8) / In-country TA – 41 (27) / Sandbox – 2 (2)
1.5 Percentage of partners of collaborative engagements who report receiving quality advice from EdTech Hub	90%	Milestone moderately not met: 87%
1.6 Percentage of knowledge products which are reviewed by a technical expert (internal or external)	External: 55% / Internal: 97% / (Cumulative percentage)	Milestone met: / External: 56% / Internal: 97% / (Cumulative percentage)
1.7 Percentage of knowledge products produced jointly with partners	46%	Milestone not met: / 43.6%
[note] 100% open access for all studies counting towards FCDO logframe target
[note] 100% female authorship all studies counting towards FCDO logframe target

Briefly describe the output’s activities and provide supporting narrative for the score.
This output, which aims to track generation of robust research, technical advice and support to enhance effectiveness of edtech initiatives, scores a B due to several milestones not being met.
1.1. The EdTech Hub published two articles this year so missed its target of three. The two research studies focus on SMS practices for education within the Kenya portfolio (Annex C).
The first study examines the use of SMS for education during the Covid-19 pandemic, specifically the Keep Kenya Learning programme. It showcases the rapid development of SMS content for literacy, numeracy, and social-emotional learning, demonstrating effective adaptation of educational materials and providing practical insights for future SMS educational initiatives. The second article, published in the British Journal of Educational Technology, explores the effectiveness of SMS messaging for education in Kenya through the M-Shule platform, which enhances literacy for primary-aged learners without requiring internet access. The study highlights positive learning outcomes, cost-effectiveness, and the importance of addressing gender disparities in mobile access.
1.2. The two core research studies completed this year are:
1. HLR 5: Raising Readers This study focuses on enhancing parent and caregiver engagement in literacy learning in Kenya using technology.
2. ASR 3: Low-Tech Remote Education Trials This study evaluates low-tech mobile learning solutions that utilise simple SMS messages and phone calls to deliver mathematics instruction to families in Kenya and Sierra Leone.
The EdTech Hub did not meet their target of three studies this year, as political unrest in Bangladesh led to the postponement of one study scheduled for completion. Given these extenuating circumstances and the application of appropriate risk management procedures, the delay was justified. FCDO considers this milestone to be only moderately not met.
1.3. EdTech Hub has initiated 18 studies across three new focus areas: climate, emergencies and protracted crises, and SEND, with four studies completed (Annex D). These include Rapid Evidence Scans examining both EdTech's role in enhancing learning outcomes for neurodivergent learners in LMICs, outlining effective strategies for support and personalised engagement, and EdTech interventions and promising practices in refugee education.
1.4. EdTech Hub has moderately fallen short of its target for collaborative engagements, achieving a total of 67. It is important to clarify that this figure includes only those collaborations funded by the core programme and does not account for engagements under partnerships secured outside core programme funding, including additional FCDO Accountable Grants from Post. Of the 67 collaborative engagements, 37 were directly funded through the FCDO main contract, comprising 8 helpdesk requests, 27 instances of technical assistance, and 2 sandboxes.
[note] The remaining engagements came from UNICEF, World Bank, and Gates Foundation.
A key example of the EdTech Hub's impact is its collaboration with the World Bank to assist the Sierra Leone Ministry of Basic and Senior Secondary Education (MBSSE) and the Teaching Service Commission (TSC) in developing a National Digital Learning Strategy (NDLS) through a helpdesk request. Feedback from the Gates Foundation has underscored the need for follow-up activities beyond the initial drafting of strategy documents, highlighting the importance of comprehensive implementation planning and long-term support.
Discussions with the EdTech Hub country team revealed that resource limitations hinder the delivery of these follow-up activities. It is essential for the strategy to include detailed implementation plans and a framework for ongoing improvement to ensure its effectiveness and sustainability. EdTech Hub must prioritise the allocation of sufficient resources for in-country initiatives, particularly in its core focus countries, to maximise the impact of its technical assistance.
1.5. In terms of partner satisfaction with EdTech Hub's advice, 87% of partners reported receiving quality guidance. While this figure is slightly below the 90% target, it is noteworthy that the target was revised from 80% at the mid-year point and represents an increase from 78.26% last year. The average satisfaction score for 2024/25 is 4.77 (out of a maximum of 5), which is 10.2% higher than the score of 4.43 in 2023/24.
[note] 49 partners were sent the survey, 31 responded (63% response rate).
1.6. The percentage of knowledge products produced jointly with partners stands at 41.7%, which does not meet the 46% target. This suggests a need for the EdTech Hub to strengthen its collaborative efforts to ensure that partners are more actively involved in the production of knowledge outputs.
1.7. The quality assurance of knowledge products has met its target, with 56% reviewed by external technical experts and 97% internally, ensuring that outputs meet rigorous standards.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
In 2024/25, significant changes were made to this output, including the addition of new indicators (1.2 and 1.3) to better reflect the status of the research portfolio. Additionally, existing indicators were disaggregated to provide a clearer understanding of what is being delivered and through which mechanisms:
- Output 1.1: Number of articles published in peer-reviewed journals, now disaggregated by Open Access and author gender.
- Output 1.4: Number of collaborative engagements for hands-on support, disaggregated by Helpdesk requests, innovation (sandbox), and in-country technical assistance.
Targets were also increased for specific indicators to reflect higher ambition:
- Output 1.2: Target for collaborative engagements increased from 45 to 70.
- Output 1.5: Target for partner satisfaction with EdTech Hub's advice raised from 80% to 90%.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.

The EdTech Hub has identified several key learnings from its research and implementation efforts. Engaging with research participants, such as teachers and government officials, is essential for creating ongoing feedback loops and ensuring that research informs shared prioritisation of recommendations. Evidence dissemination should extend beyond technical EdTech content, with the EdTech Hub successfully sharing functional learnings, such as an open-source guide for building an evidence library and the EdTech for Entrepreneurship Course. The EdTech Hub is continuously refining its approach to evidence synthesis, finding that tailored policy briefs, like the at-scale research policy briefs for 2024/25, engage specific audiences more effectively than general learning briefs.

Recommendation 1 (2023-24): Prioritise effective communication around the research studies, findings and impact of the research.
Progress: The EdTech Hub has made some progress in enhancing its communication around research. Key activities have included expanding the Learning Brief series to share operational learnings, producing guidance on establishing evidence libraries, and developing policy briefs. Improvements have been implemented on the EdTech Hub's website, including actions taken based on results of an Accessibility Audit; however, further work is required to enhance user experience and update content. The EdTech Hub's participation at CIES in 2025 including nine panel sessions and a keynote address, contributing to ongoing discussions in the sector.
Recommendation 4 (2023-24): Create research workplan for new focus themes.
Progress: Following consultations with FCDO, workplans have now been finalised for research topics of SEND, climate, and education in emergencies and protracted crises. These plans clearly outline the primary and secondary research studies, partnership-building efforts, and thought leadership activities to be undertaken, along with the allocated budgets for each area. Additionally, dedicated website pages have been created for these topics. The pages will be regularly updated as the work progresses.
Recommendation 6 (2023-24): What Works Hub for Global Education (WWHGE) and EdTech Hub strategic link-up.
Progress: The EdTech Hub has enhanced its collaboration with the WWHGE in Tanzania and Kenya through joint initiatives, including user research for the Teacher Continuous Professional Development Learning Management System. In Kenya, the EdTech Hub is a key technical partner for the Education Evidence Hub. Additionally, the EdTech Hub has presented at WWHGE conferences, and its Research Director has joined the WWHGE Research Coordination Group to advance implementation research in education.
Output recommendation:
The EdTech Hub and FCDO should review and update the logframe indicators for Output 1, with particular attention to: (i) study publications, and (ii) knowledge products, by October 2025. Revised indicators for study publications should capture both the number of submissions and the conversion rate to published outputs, to enable more accurate identification of bottlenecks and more effective progress tracking. Additionally, the definition of knowledge products should be reviewed to ensure clarity and consistency.
Output Title	Investments in EdTech Hub management and governance strengthen structures and processes that facilitate strategy implementation and accountability mechanisms
Output number:		2	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Reduced from 10% to 5%

Indicator(s)	Milestone Target(s) for this review	Results as of March 2024
2.1 Percentage of milestones completed to standard on time	99%	Milestone moderately not met: 91%
2.2 Percentage of variance from the forecast financial values	2%	Milestone met: / -0.43% (0.43% variance)
2.3 Average score of responses from the Pulse Survey	4.18	Milestone moderately exceeded: / 4.21

Briefly describe the output’s activities and provide supporting narrative for the score.
The EdTech Hub programme output 2 has scored an A during this reporting period with the majority of outputs met.
2.1. During this reporting period two outputs required multiple revisions to improve quality before receiving final approval. This was particularly evident for outputs published directly on the website, which did not undergo the standard copy-editing checks typically applied to publications.
2.2. Financial management, along with the accuracy of forecasting and reporting, continues to be strong, thanks to regular communication with the Delivery Leadership Team.
2.3. The Pulse Survey (run by R4D, providing annual anonymised feedback from the EdTech Hub members on people issues and how well the programme and consortium is operating) milestone was exceeded. Findings highlighted improvements made in relation to individuals work being recognised, team level decision-making and relationships, and collaboration within and across EdTech Hub teams. Further improvements can be made in relation to engagement with finance and contracting central service functions. Actions such as development of a Finance Data Dashboard and finance Delivery Leadership Team meetings have been taken.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The weighting of this output was changed from 10% to 5% to incorporate a new output ie Output 4 (as outlined in section B).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

There were no recommendations from last year's Annual Review. Programme management learning is detailed in Section F.
Output recommendation:
The EdTech Hub and FCDO should review and update the relevant logframe indicator to ensure that the terms “to standard” and “on time” are clearly and accurately defined by October 2025. This review should establish objective criteria and benchmarks for assessing quality and timeliness, enabling consistent measurement and effective monitoring of progress against these standards

Output Title	EdTech Hub – World Bank technical exchange, collaboration, and capacity building on EdTech knowledge products are implemented to plan
Output number:		3	Output Score:	A+
Impact weighting (%):		5%	Weighting revised since last AR?	Reduced from 10% to 5%

Indicator(s)	Milestone Target(s) for this review	Progress to March 2025
3.1 Number of EdTech Hub Exec Committee & Strategic Advisory Board meetings attended	80%	Milestone exceeded: / 83%
3.2 Number of [joint] knowledge products (KPs) produced each year (research papers, evidence reviews, knowledge packs, think pieces, Helpdesk briefs, sandbox findings, podcasts, etc.)	4	Milestone exceeded: / 6
3.3 Number of participants completing the EdTech Policy Academy course each year	200	Milestone exceeded: / 281
[note] The Hub has no direct involvement in the EdTech Policy Academy implementation, and so this data is provided directly by the WB EduTech Team.

Briefly describe the output’s activities and provide supporting narrative for the score.
The World Bank and EdTech Hub have implemented a range of activities aimed at enhancing technical exchange, collaboration, and capacity building in EdTech knowledge products.
3.1. The World Bank has offered valuable strategic guidance to the EdTech Hub by actively participating in decision-making during the EdTech Executive Committee and Strategic Advisory Board meetings. Additionally, the partnership has been strengthened through the World Bank's involvement in the newly launched AI Observatory and Action Lab which enabled the EdTech Hub to present at the inaugural AI Community of Interest for Global Education Policymakers.
3.2. In 2024/25, the partnership between the EdTech Hub and the World Bank resulted in the development of six knowledge products available as global public goods. These include a podcast on selecting EdTech solutions, insights on AI implementation in Nigeria, and a study on digital personalized learning platforms in the Dominican Republic. Additionally, a curated list of EdTech policies for Sub-Saharan Africa was created to guide the World Bank's Policy Academy.
The EdTech Hub produced a resource list to support the World Bank's Digital Skills Toolkit for Sub-Saharan Africa, addressing key questions such as how to prepare youth for future employment. A landscape analysis for Sierra Leone informed the co-creation of the National Digital Learning Strategy (as part of a Helpdesk request).
3.3. During this reporting period, 281 participants from 23 countries were trained through the Policy Academy, focusing on strategies for teacher capacity building and implementing EdTech strategies. Key takeaways included the importance of formal EdTech policies, adequate digital infrastructure, and collaboration among stakeholders.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

There were no recommendations from last year's Annual Review. Lessons learned are detailed and one recommendation is detailed in Section F.
Output recommendation:
The EdTech Hub and FCDO should revise the logframe indicator for Output 3.1 by October 2025. This is to ensure it accurately reflects the World Bank’s buy-in and strategic leadership role.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The weighting of this output was changed from 10% to 5% to incorporate new output 4 (as outlined in section B).
Output Title	AI Observatory & Action Lab supports decision-makers with guidance to shape a more effective and equitable future for AI in education in LMICs.
Output number:		4	Output Score:
Impact weighting (%):		10%	Weighting revised since last AR?	This output was added in 2024/25

Indicator(s)	Milestone(s) for this review	Progress
Number of AI Observatory & Action Lab knowledge products published.	2	Milestone exceeded: / 4
4.2 Number of stakeholders reached through participation in events, fora, and global discussions as well as country engagement.	25	Milestone exceeded: / 42
4.3 Number of key stakeholders engaged in Action Lab Initiatives, including through scoping engagements on the on-demand services, outreach to users of the tools, benchmarks, and forthcoming initiatives.	2	Milestone exceeded: / 8
4.4 Percentage of variance from the forecasted financial values for AI Observatory & Action Lab	10%	Milestone exceeded: 5.7%

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4, tracking delivery under the AI Observatory and Action Lab, was newly introduced this year. The inception report was submitted on 21 February 2025. This new two-year component is one month into its delivery phase and has received an A+ score based on completion of milestones agreed at the end of the inception phase.
4.1. Four knowledge products have been published on AI during this time, surpassing the initial target of two. These include:
1. EdTech Hub’s AI Observatory: Greater equity in learning outcomes in the age of AI.
2. What we’re reading and hearing about AI in education.
3. Humanity’s last exam and education in AI.
4. What do AI futures mean for human connection?
4.2. During the inception period and one month of implementation, the AI Observatory made progress in stakeholder engagement and driving shared understanding of AI's role in education. As part of the horizon scanning work, four curated discussions titled Let’s Talk about AI engaged 42 participants from 37 organisations across 22 countries. The discussions were designed to understand from education practitioners the current realities, future possibilities, and what is needed to shape equitable education in the age of AI.
4.3. During the reporting period, the EdTech Hub successfully engaged four key stakeholders in Action Lab initiatives, building on eight scoping calls primarily related to FCDO programmes. Two on-demand engagements have progressed to the development phase of their Terms of Reference, focusing on implementing a chatbot for school quality assurance and testing generative AI for education content accessibility.
Additionally, the Observatory is advancing a benchmarking initiative to evaluate the performance of AI models, with three benchmarks already established. This benchmarking work is designed to assess and score the efficacy of AI models in terms of their performance on standardised tasks, providing valuable guidance for informed decision-making for AI use in education. Notably, the Visual Maths Benchmark and SEND Pedagogy Benchmark specifically address challenges related to early-grade learning and pedagogy for students with SEND.
4.4. The percentage of variance from the forecast financial values was targeted at less than 10%, and the actual variance was 5.7%. This indicates effective financial management and adherence to budgetary expectations for this accountable grant.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output was incorporated into the EdTech Hub Logframe in December 2024 following the introduction of the new Accountable Grant, with a weighting of 10%.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

There were no recommendations from last year's Annual Review as this is a new output.

Recommendation (2023-24): Expanding the portfolio into artificial intelligence in education
Progress: The EdTech Hub signed an Accountable Grant for the AI Observatory and Action Lab. In addition, the EdTech Hub has actively engaged decision-makers and generated evidence on AI, receiving six Helpdesk requests related to this area. Notably, in December 2024, the Government of Tanzania requested a review of its EdTech strategy guidelines for teacher colleges and schools, which includes considerations for AI integration.
Lessons learned:
1. There is a clear demand for AI-related technical support from FCDO education advisers and the education ministries with whom they are partnering; however, requests vary significantly in maturity and clarity. The existing eligibility principles and a primary access point should be utilised to process requests, balance responsiveness with prioritisation to maximise learning and impact.
2. Stakeholders involved in our research have expressed uncertainty and hesitation around the adoption of AI in education systems. The EdTech Hub should support informed action by developing context-specific initiatives, frameworks and tools that empower policymakers and implementers.
3. With substantial activity from donors and NGOs in this area, effective alignment and communication are crucial to prevent duplication and fragmentation of support for education practitioners.

Output recommendation:
1. The EdTech Hub and FCDO should revise the logframe indicators for Output 4 by October 2025. This is to ensure they are fit for purpose, with clearly defined and ambitious targets, particularly in light of the significant achievements in Output 4.2.
2. The AI Accountable Grant should leverage the EdTech Hub’s Helpdesk as the primary access point for FCDO on-demand requests by August 2025. Since FCDO staff are already well-acquainted with the Helpdesk, it is advisable to avoid establishing a separate support mechanism. Instead, the FCDO on-demand service should be integrated as an extension of the existing Edtech Hub Helpdesk. R4D should confirm the implementation of this Helpdesk integration.
3. The AI Accountable Grant should collaborate closely with other donors and NGOs to align workstreams, particularly within the World Bank's AI Community of Interest, by July 2025. By actively participating and co-convening, the EdTech Hub can identify emerging themes, address evidence gaps, and share our insights. This collaboration will inform Helpdesk support, shape Action Lab priorities, and ensure our work remains aligned with global conversations.
## D: VALUE FOR MONEY
Key cost drivers and performance, Value for Money (VfM) performance compared to the original VfM proposition in the business case.
The EdTech Hub programme is evaluated against the FCDO four E’s measurement approach, which includes Economy, Efficiency, Effectiveness, and Equity. For the upcoming reporting period, we recommend updating the VfM framework and developing indicators to evaluate cost-effectiveness, as this aspect is not currently included in the existing framework. The assessment below highlights key areas for enhancing the VfM offering.
Economy: finance, contracts, and Monitoring Evaluation for Learning Adaptation (MELA)
The primary cost driver for the EdTech Hub is project team resources, managed through fee rate caps specified in the main contract. To ensure value for money, the EdTech Hub regularly evaluates the balance between long-term expertise, such as country leads, and short-term expertise for specific Helpdesk requests. For contract renewals, proposed rate changes are benchmarked against other applicants to ensure alignment with market norms.
During this reporting period, the EdTech Hub expanded its team by adding 29 new members, including 15 specialists, to support the outputs detailed in this report. This expansion includes staff replacements, an increase in the Helpdesk team, and new hires for the growing areas of education in emergencies and protracted crises, climate, and Special Educational Needs and Disabilities (SEND). Consequently, medium-rate band members now account for 52% of total costs, up from 41% last year, while both high and low-rate bands represent smaller proportions of overall staff costs. This shift indicates growth, but it is essential to assess its impact to ensure that increased costs are justified by improved outcomes. As the programme nears its conclusion, staff cost rates should align with contract spending and outcomes, with necessary adjustments made for the next year if contract spending decreases.
Programme management costs for the EdTech Hub have risen to 8.8% of overall expenditure, up from 4.15% in March 2024. This increase is primarily due to the programme's lifecycle, where contract spending is declining while management costs remain stable, resulting in a higher proportion of expenditure in this category. The departure of key team members and the onboarding of a new finance manager have also contributed to this change. Continuous evaluation of these dynamics will be essential for maintaining value for money and overall programme efficiency.
Efficiency: finance and integrated approach
The EdTech Hub assesses efficiency by examining the proportion of overall expenditure allocated to its integrated approach in relation to management and governance costs, as well as the effectiveness of converting inputs into outputs. Currently, 84% of total expenditure is dedicated to research, technical assistance, and innovative solutions, which marks a slight decrease from 88% in the previous year. This change on last year also includes a 2-percentage point increase in research spending, reflecting the EdTech Hub's focus on their new research themes. However, there has also been a 6-percentage point reduction in technical assistance, largely due to this component being funded by accountable grants secured by the EdTech Hub, alongside a 3.6 percentage point increase in management and governance costs.
While enhancing management and governance is vital for effective oversight, it is imperative that the EdTech Hub maintains a strong focus on programme delivery and the achievement of impactful outcomes, particularly those outlined in the FCDO main contract. The EdTech Hub's completion rate for milestones stands at 91%, which is lower than the previous year, indicating a potential area for concern. This decline underscores the necessity for continuous evaluation of resource allocation to ensure that management expenses do not impede the EdTech Hub's core objectives.

Effectiveness: investments influenced and leveraged by the EdTech Hub
In this reporting period, the EdTech Hub secured £6.09m in new investments, including GBP 3.5 million for the AI Observatory & Action Lab, £0.6m from FCDO Ghana, £0.309m from Enabel, and £1.25m from International Development Research Centre (IDRC). The establishment of ten new contracts with nine donors—six being new partners—highlights the growing demand for the Hub's expertise and its effectiveness in attracting funding. The EdTech Hub's in-country support has influenced EdTech investments, such as a £75,000 pilot funding for an eContinuous Professional Development (eCPD) initiative in Malawi, developed in partnership with onebillion and FCDO. In Sierra Leone, insights from the EdTech Hub's HLR 3 study informed a GPE proposal, securing over $4m in funding. Additionally, the EdTech Hub's research on Tanzania's MEWAKA model has led to government directives for national teacher certification, enhancing training access and improving educational outcomes at scale.
However, a recent VfM assessment of the research portfolio revealed limited effectiveness in documenting connections with decision-makers and evidence use, resulting in an Amber/Green rating. Key lessons emphasised the need for realistic resource allocation, proactive stakeholder engagement, and better documentation of decision-maker interactions. By addressing these areas, the EdTech Hub can further enhance its effectiveness and ensure its investments yield meaningful educational improvements across its portfolio of work.
Equity: The EdTech Hub demonstrates a strong commitment to equity through its focus on gender, partnerships with LMICs, and disability inclusion. In the reporting period, it has produced 17 global public goods on gender, coinciding with the introduction SEND as a new research theme. To address disability, the EdTech Hub has developed 12 knowledge products specifically related to SEND.
The EdTech Hub has engaged 24 LMIC-based partners, with 66.7% classified as primary collaborators, enhancing their capacity through targeted coaching and training. Furthermore, 54% of the EdTech Hub's 520 knowledge products feature LMIC authors, with 72.94% of recent publications including them. In addition, the EdTech Hub has made significant improvements to its website accessibility following an audit conducted in the previous reporting period, improving equitable access to resources.

E: RISK
Overview of Risk Management
During this reporting period, the risk rating for the EdTech Hub programme is classified as moderate, with all residual risks falling within the programme’s risk appetite across various categories.
The EdTech Hub has successfully integrated risk management into its governance framework, facilitating regular discussions and the identification of risks at both output and portfolio levels. Significant risks are escalated to EdTech leadership as needed, and quarterly meetings with the FCDO ensure ongoing communication and oversight. The programme employs a risk register, which is reviewed quarterly by both the FCDO and the EdTech Hub. Currently, approximately 59% of risks are classified as moderate, 35% as minor, and 6% as major. The agreements with the World Bank are also included in the EdTech Hub’s risk matrix.
With the onboarding of the AI Observatory and Action Lab Accountable Grant this year, a more streamlined approach to risk management has been adopted. The EdTech Hub has incorporated AI-related risks into the main risk register, providing a quarterly risk narrative that encompasses both components of the programme. AI risks are also included in the quarterly risk meetings with the FCDO. This approach is cost-effective and fosters a robust forum for discussing risk management across the entire portfolio.

Notable risks and mitigation strategies from this year:
Financial and fiduciary risks: The reduction of the UK’s ODA budget has introduced uncertainty regarding programme spending and deliverables. In response, the EdTech Hub has adjusted its Q1 forecast to deprioritise non-urgent work until budget allocations are clarified. A detailed costed workplan has been developed to provide a breakdown by output, aiding the FCDO in making more strategic decisions. The EdTech Hub and FCDO maintain open communication regarding budgets. To enhance this approach, the EdTech Hub could proactively consider how to position the EdTech portfolio within a constrained funding environment.
People risks: The departure of two key staff members—the Engagement Director and the MELA Lead—posed a risk of losing institutional knowledge, particularly in effective research management and understanding FCDO compliance requirements for programme management. To mitigate this risk, personnel changes were strategically planned, with the EdTech Hub expanding existing roles and onboarding new team members. Detailed handovers and training were implemented, along with ongoing monitoring to assess the impact of these changes on programme continuity and effectiveness.
Policy and delivery risks: The ambitious two-year timeline for the AI Accountable Grant presents a risk of not being met, which could lead to programme underspend and hinder the overall achievement of project objectives. To mitigate this risk, the FCDO Project Manager and Policy Manager are proactively implementing the agreed workplan to ensure accountability from the EdTech Hub. A robust governance system is in place to closely monitor progress and promptly address any emerging issues.
Strategy and context risks: Changes in Tanzania regarding the Ministers' data initiative present a reputational risk to the programme. Concerns about the lack of technical expertise, political motivations prioritising optics over results, and the potential for overly positive updates have strained the relationship between FCDO Tanzania and the Government, leading to considerations of withdrawing funding for the primary data dashboard. To mitigate this risk, the EdTech Hub is engaging various development partners to analyse and present government-published data for decision-making, ensuring scrutiny of its robustness. Additionally, to maintain a strong relationship with the Government, the EdTech Hub is providing responsive technical assistance and supporting sub-national initiatives. It is recommended that the EdTech Hub arranges a meeting between FCDO Tanzania, FCDO HQ, and the EdTech Hub to discuss next steps.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Programme management:  Over this review period, there have been a few changes to key staff within the EdTech Hub. This includes the departure of the EdTech Hub’s engagement director and Monitoring and Evaluation for Learning and Adaptation (MELA) lead, and the onboarding of the new Finance Manager. All changes were managed smoothly between all relevant partner staff and the FCDO programme team, with minimal impact on delivery.
Reporting: R4D provides quarterly reports to FCDO, who conduct formal quarterly meetings with the World Bank team to assess the results framework. FCDO also holds monthly meetings with the EdTech Hub to discuss programme management, focusing on deliverable progress, risks, safeguarding, finances, and contractual matters. The Programme Responsible Owner (PRO) and Senior Responsible Owner (SRO) are members of the Edtech Hub Strategic Advisory Board, which convenes bi-annually. The PRO also participates in the quarterly Executive Committee meetings, serving as the chair for both the Executive Committee and the Strategic Advisory Board.
Contractual compliance, changes and performance
EdTech Hub: Four payments have been made to the EdTech Hub contract since the last Annual Review, based on quarterly invoices in arrears. Milestones are agreed at the start of each quarter and payment issued at the end of the quarter, based on milestones having been met and completed to a satisfactory standard (70% milestone, 30% actuals payment mechanism).

Quarter	Quarter Budget Forecast (GBP)	Quarter Actual Spend (GBP)
1	£694,864.76	£594,330.96
2	£930,984.48	£914,378.07
3	£761,610.23	£614,357.88
4	£1,001,139.98	£987,819.17
Total	£3,124,206.90	£3,110,886.09
Variance between year budget forecast and actual spend			0.43%

Financial management and accuracy of forecasting and reporting are monitored via quarterly finance reports from the EdTech Hub, with excellent forecasting accuracy delivered this year. For FY25/26, R4D have provided a detailed costed workplan for their £2m forecast, to demonstrate how these funds will be spent.
World Bank Trust Fund: No payments were made to the Trust Fund during this reporting period. The FCDO aims to hold quarterly update meetings with the World Bank to align on priorities for the upcoming period, as well as receiving the annual report on the Foundational Learning Compact (FLC) and the FLC quarterly newsletter. However, the limited size of the World Bank team looking after this specific component often leads to delays in more detailed updates and reporting on the Trust Fund.
[note] The FLC is the umbrella multi-donor Trust Fund this component sits under.
Recommendation: The FCDO Programme team will work with the WB team over this next reporting period to develop a more efficient communication and reporting mechanism that facilitates more comprehensive and timely updates.
Accountable Grant component
In FY24/25, £523,100.24 was paid under the AI Observatory and Lab Accountable Grant. This is paid in arrears to R4D, as the prime implementing partner, upon submission of a quarterly report and invoice.
Financial forecasts, broken down by quarter, are submitted and scrutinised at the beginning of the financial year. The EdTech Hub then provide monthly verbal progress updates to discuss any risk of over or underspend. Percentage variance between forecast and actual spend is captured quarterly as part of the overarching log frame, with a tolerance range set at 0-10%. For this reporting period there was a 5.71% variance between expenditure and the agreed budget for the AI AG.
For FY25/26, R4D have forecast a budget of £2,151,891.48 and have provided a high level workplan for how this will be spent. FCDO will continue working with R4D to scrutinise plans, secure a high level of confidence in the forecasts, and secure value for money.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and evaluation
FCDO: The Annual Review is the primary mechanism for assessing progress against log frame indicators. This year, with this review occurring two years before the programme's conclusion, support from the Gates Foundation has facilitated a thorough evaluation of the EdTech Hub's delivery and impact at the country level, leading to actionable recommendations for the final two years. Their insights, gathered through stakeholder interviews on the effectiveness of research initiatives and alignment with government educational goals, have been incorporated into FCDO’s main review. The EdTech Hub provides quarterly progress updates, while FCDO staff engage with the EdTech Hub team bi-monthly and hold quarterly meetings with World Bank partners. The log frame and Theory of Change remain vital tools for measuring progress, and the EdTech Hub has updated its quarterly commercial and finance reporting to improve alignment and enhance overall reporting effectiveness.
EdTech Hub: The EdTech Hub’s Monitoring, Evaluation, Learning, and Adaptation (MELA) team tracks results and performance through regular reporting against the Results Framework indicators. They employ monitoring tools and rigorous data collection and analysis methods, integrating both quantitative and qualitative approaches. Whenever possible, data collection is linked to existing processes from the EdTech Hub’s research, technical assistance, and innovation teams to ensure VfM.
The primary goal of the monitoring systems is to provide EdTech Hub teams with clear insights into their progress. The Data Dashboard and quarterly MELA readouts offer a concise overview of key performance indicators, facilitating informed decision-making for user teams.
World Bank: The World Bank reports against Results Framework on a quarterly basis through meetings and the FLC Trust Fund reporting cycle, ensuring to specify lessons learned through their monitoring of work.

Date of last narrative financial report	30 April 2025	Date of last audited annual statement	20 September 2024

Annex A: List of funding partners in addition to FCDO main contract:
Donor	Amount in GBP
Aga Khan Foundation	121,881.91
AI Observatory	3,500,000.00
BMGF	5,918,066.66
EIDU	479,566.73
Enabel	309,368.51
ASEAN	1,245,165.00
FCDO Ghana	641,743.00
FCDO Malawi	30,000.00
FCDO Tanzania	2,210,599.99
GSMA	20,541.46
IDRC	1,260,613.00
Jacob's	623,984.62
MoE Madagascar	1,26,901.03
SEAMEO	16,108.00
Mott Macdonald	88,698.14
IDRC - Summa	103,986.91
UNESCO	75,840.00
UNICEF	1,513,408.62
Zizi Foundation	243,107.49
VSO	126,058.00
Save the children	19,750.00
Total	18,675,389.07

Annex B: EdTech Hub’s new ToC, 2024.
Annex A: Theory of Change, 2024
Annex C: Research portfolio (Bold indicates completion this reporting period).

Sr No	Study	Status	Completion year	Research partner	Implementing Partner	Country	Focus area
1	Designing for Scale: Understanding Design Affordances and Social Interaction on a Personalised Learning Programme	Complete	2023/24	Nairobits	Oppia	Kenya	Digital Personalised Learning
2	Digital personalised learning to improve numeracy outcomes in Kenyan primary school classrooms	Phase 3 Active / FCDO Phase 1 and EIDU Phase 2 complete		Women Educational Researchers of Kenya (WERK)	EIDU	Kenya	Digital Personalised Learning
3	The impact of GIS-supported teacher allocation in Sierra Leone	Active		Education Commission and Fab Inc	Teaching Service Commission, Ministry of Basic and Senior Secondary Education, World Bank	Sierra Leone	Teacher Continuous Professional Development / Data for Decisions
4	The impact of a tech-supported, school-based TCPD model on learning outcomes in Tanzania	Active		Aga Khan University / Aga Khan Foundation – Schools 2030 / University of Dar es Salaam	Tanzania Institute of Education, President’s Office, Regional Administration and Local Government and Ministry of Education, Science and Technology	Tanzania	Teacher Continuous Professional Development
5	Raising readers—using technology to improve parent and caregiver engagement in literacy learning in Kenya	Complete	2024/25	Kenyan Government / Keep Kenya Learning / Global Book Alliance	WorldReader	Kenya	Digital Personalised Learning / Participation & Messaging
6	Optimising messaging to promote returns to school in Ghana for marginalised learners	Complete	2023/24		Eneza Ghana implementation partner Craft Education	Ghana	Participation & Messaging / Girls’ Education & Technology
7	Low-tech personalised learning to improve Girls’ Education & Technology in Kenya	Complete	2023/24	M-Shule	M-Shule	Kenya	Girls’ Education & Technology / Digital Personalised Learning
8	Girls’ Education and technology – evidence from the GEC	Complete	2023/24		Girls’ Education Challenge	Global	Girls’ Education & Technology
9	How do EdTech solutions spread? Understanding system level factors impacting the implementation and scale of EdTech innovations in Bangladesh	Complete	2023/24		HundrED	Pakistan / Sierra Leone / Tanzania	Participation & Messaging
10	Building Foundational Learning Through Technology	Active			Voluntary Services Organisation	Sierra Leone	Digital Personalised Learning
11	Technology to Empower Actors Across the Learning Ecosystem	Active		Harvard University	Harvard University	Pakistan	Digital Personalised Learning
12	3Mpower (Mobile Learning for Empowerment of Marginalised Mathematics Educators)	Active		Open University	Open University	Bangladesh	Teacher Continuous Professional Development
13	Low-tech remote education trials	Complete	2024/25	Youth Impact / NewGlobe / Rising Academies	Youth Impact / NewGlobe / Rising Academies	Kenya, / Sierra Leone	Data for Decisions / Digital Personalised Learning
14	Understanding the impact of edutainment on gender norms, socio-emotional and learning outcomes for girls	Active		Busara Centre for Behavioral Economics – Implementing and Research Partner / Ubongo	Busara Centre for Behavioral Economics – Implementing and Research Partner / Ubongo	Kenya	Girls’ Education & Technology
15	Investigating EdTech and learning outcomes at secondary level during Covid-19 pandemic: evidence from a randomised control treatment experiment in South Punjab	Complete	2021/22	SDPI	SDPI	Pakistan	Teacher Continuous Professional Development
16	Impact of IRI-based mobile lessons on educational outcomes of primary graders: a randomised controlled trial in rural Bangladesh	Complete	2021/22	Monash University	Global Development and / Research Institute	Bangladesh	Participation & Messaging
17	Exploring the impact of radio lessons, peer learning and targeted paper-based resources on girls remote learning in Kenya	Complete	2021/22	Education Development Trust	Wasichana Wetu Wafaulu programme, GEC	Kenya	Girls’ Education & Technology
18	T-TEL COVID-19 impact assessment study	Complete	2021/22	Transforming Teaching, Education & Learning	Learners, teachers, tutors, Colleges of Education, university leads, and Ghana Tertiary / Education Commission staff	Ghana	Teacher Continuous Professional Development
19	Learning from experience: a post-Covid-19 pandemic data architecture for a resilient education data ecosystem	Complete	2021/22	Fab Inc	Ministry of Basic and Senior Secondary Education	Sierra Leone	Data for Decisions
20	Integration of technology in education for marginalised children in the urban slums of Dhaka City during the Covid-19 pandemic	Complete	2021/22	Beyond Peace	Beyond Peace	Bangladesh	Participation & Messaging
21	Nudges to improve learning and gender parity: supporting parent engagement and Ghana’s educational response to Covid-19 pandemic using mobile phones	Complete	2021/22	Innovations for Poverty Action (IPA)	Innovations for Poverty Action (IPA)	Ghana	Girls’ Education & Technology
22	Understanding barriers to girls’ access and use of EdTech in Kenya during Covid-19 pandemic	Complete	2021/22	Busara Centre for Behavioral Economics	Busara Centre for Behavioral Economics	Kenya	Girls’ Education & Technology
23	Dialling up Learning: Testing the Impact of Delivering Educational Content via Interactive Voice Response to Students and Teachers in Ghana	Complete	2021/22	Rising On Air	Rising Academies	Ghana	Teacher Continuous Professional Development
24	Making EdTech interventions inclusive and effective for all in Ghana: the role of policies and programmes	Complete	2021/22	Participatory Development Associates (PDA)	Ministry of Education Service, Plan International, Mastercard Foundation, and Lively Minds	Ghana	Participation & Messaging

Annex D: New research topic studies (bold indicates study completed this reporting period)
Sr No	Topic	Study	Study Type	Status	Initiation year	Completion year
1	Climate	Building on the Hub’s (2023) primary research in response to the 2022 Pakistan floods that explored the feasible and scalable use of EdTech in response to future floods, EdTech Hub will produce a public-facing practical brief for Government (federal and provincial) consultation and donor consultation. This brief will explore opportunities to use existing interventions to bolster learning continuity (including student-facing and teacher-facing interventions) in response to future climate emergencies in Pakistan. §	Secondary Research	In progress	Nov 2024
2	Climate	TZ Case study — implementation research on a school-centred flood early warning system, which will be implemented as part of the Shule Bora program.	Primary	In progress	Jan 2025
3	Climate	The RER will be on the theme: The impact of climate change on education and the role of technology within this (World Bank 2024). This will identify the most effective ways in which technology can be used for Climate Resilience, according to the four key themes identified by the World Bank (see p.19): 1) Education management for climate resilience, 2) School infrastructure for climate resilience, 3) Ensuring learning continuity in the face of climate shocks, and 4) Leveraging students and teachers as change agents.	Secondary Research	In progress	Jan 2025
4	EiE	7231_Min standards Desk Review Report. The main objectives are to understand the key commonalities between existing guidance documents (from adjacent disciplines beyond EdTech in emergencies itself) as an indicator of good practice whilst identifying gaps in current guidance documents for EdTech within EiE. This may include gaps in content, accessibility and equity. The study will establish whether a new set of guidelines for EdTech in EiE is required, and if it is, to develop a set of recommendations for inclusion within this guidance to further support for existing good practice and address the gaps identified	Secondary Research	Completed	Sep 2024	Dec 24
5	EiE	A study on the role of the Ministry of Education and Science and its Digital Transformation strategy during war, particularly looking at how national strategies can be integrated with the national EiE responses.	Primary Research	In progress	Feb 2025
6	EiE	EdTech Hub will undertake the development of global guidance for a desk study to develop guidance materials for education in emergencies — this will be in collaboration with INEE. This desk study will review existing guidance, identify gaps in guidance provisions, and provide guidance document design recommendations. In consultation and collaboration with key guidance users, we will develop an EdTech in EiE settings guidance document with an emphasis on accessibility and appropriate user design. Topics may include connectivity and infrastructure; capacity and culture; content and solutions, cost and sustainability, coordination and leadership, and data and evidence. We are currently discussing the most needed topics with our EiE partners and collaborators.	Secondary Research	In progress	Oct 2024
7	EiE	7223_Remote Learning ReR — The study will understand how EdTech has been used to support education in emergencies since 2019, whilst exploring how effective recent EdTech-related efforts have been in supporting learning in emergency contexts. The study includes evidence that aligns with the definition of remote learning and emergency remote teaching	Secondary Research	In progress	Jan 2025
8	EiE	7221_EiE and Refugees ReR — Review on Education in Emergencies. The study will understand how EdTech has been used to support education in emergencies since 2019, whilst exploring how effective recent EdTech-related efforts have been in supporting learning in emergency contexts.	Secondary Research	Completed	Nov 2024	Feb 2025
9	EiE	7221_EiE and Refugees ReR — the study focuses on Refugees and will understand which EdTech interventions within refugee education have been effective whilst identifying promising practices relating to the use of EdTech within refugee education	Secondary Research	Completed	Jan 2025	March 25
10	EiE	7246_Can’t wait to learn Implementation Research — This research proposal seeks to explore two main dimensions of how PLCs can support middle-tier professionals in emergencies and what role the use of DPLs can play in supporting such work: / What are the most effective approaches to establishing professional learning communities amongst education practitioners supporting the use of digital personalised learning in non-formal education in an emergency education context? / What are the impacts for the participants of these professional learning communities beyond the effective utilisation of digital personalised learning in nonformal education provision?	Primary Research	In progress	Jan 2025
11	Climate	Study the design and implementation of socio-emotional learning (SEL) programme for caregivers and parents in Bangladesh.	Primary Research	In progress	October 2024
12	EiE	7244_MoE Ukraine Digital Transformation — this study will assess the available evidence on using technology to support psychosocial support (PSS) and social and emotional learning (SEL) in education in emergency settings. This work will document up to three specific case studies of psychosocial support and / or SEL interventions that have made a meaningful contribution to our understanding of important intervention design, implementation, and support criteria.	Primary Research	In progress	Feb 2025
13	Climate	Study the use of technology to support caregivers’ and parents’ role in education programming in climate-affected regions of Kenya (adaptations of learning continuity efforts spearheaded during COVID-19 pandemic)	Primary Research	In progress	January 2025
14	EiE	7242_ Ahlan Simsim — case study to assess the available evidence on using technology to support psychosocial support (PSS) and social and emotional learning (SEL) in education in emergency settings. This work will document up to three specific case studies of psychosocial support and / or SEL interventions that have made a meaningful contribution to our understanding of important intervention design, implementation, and support criteria.	Secondary Research	In progress	Feb 2025
15	EiE	Write a working paper on cost-effectiveness of EdTech interventions in EiE contexts (to complement EdTech Hub’s work on cost-effectiveness of EdTech interventions more broadly in LMICs	Secondary research	Not started
16	EiE	Work with FCDO’s ERICC initiative on an article for a Special Issue focused on the use of EdTech in emergencies. This will include reviewing and, if necessary, supplementing the EdTech evidence within ERICC’s research database	Secondary research	Not started
17	EiE	726_EiE Implementation research (To be confirmed)	Primary Research	Not started
18	SEND	Ghana’s Parliamentary Cabinet is currently approving the Inclusive Education policy; we will write a brief on how it addresses neurodivergent learners and recommend how technology can better support the needs of those learners, their educators, their caregivers, and special education coordinating teams	Secondary research	In progress	Jan 2025
19	SEND	Implementation research for tech-enabled screening and support to teachers in Ghana	Primary Research	In progress	Jan 2025
20	SEND	eCPD pilot with SEND content — In partnership with personalised learning provider onebillion and FCDO’s Malawi education advisor, EdTech Hub has developed a concept to use the teacher-facing tablets from Malawi’s BEFIT program to address SEND topics. The model will test content and a personalised digital approach to continuous professional development (CPD) related to a number of important topics for teachers	Primary Research	In progress	Nov 2024
21	SEND	Implementation research to support Malawi’s learning agenda	Primary Research	In progress	Jan 2025
22	SEND	A Rapid Evidence Scan which articulates what we currently know about the use of EdTech to support and improve the learning outcomes of neurodivergent learners, especially those in LMICs. The goal of this scan will be to define a pathway for supporting neurodivergent learners (ranging from providing support to teachers to identify these learners, customise instruction, track their progress, all the way to direct personalised learning engagement) and articulate the ways in which EdTech has been used effectively across this pathway.	Secondary research	Completed	Oct 2024	Mar 2025