## Annual Review

Title: Strengthening Disaster Resilience and Responding to Humanitarian Emergencies in Nepal
Programme Value £ (full life): 56,000,000		Review date: 25 June 2025
Programme Code: AMP ID#300003	AMP start date: 06/09/2016	AMP end date: 31/03/2025

Summary of Programme Performance
Year	2017	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	B	B	A	A+	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300003/documents
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300003/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Strengthening Disaster Resilience and Responding to Humanitarian Emergencies in Nepal (SDR) programme’s aim is to reduce risk and build resilience to natural hazards in Nepal at the federal, provincial, and local levels.

This review covers the period of April 2024 to March 2025 (Total Spend: GBP £13,842,319.63 million). The review will focus on the 2 key activities within the programme for the reporting period:

Joint Recovery Action Plan (JRAP)[1] and Humanitarian Response: Western Nepal Earthquake and the Onset Emergencies Joint Programme (£12,725,000). The Joint Recovery Action Plan (JRAP) was implemented in response to the 6.4 magnitude earthquake that struck western Nepal in November 2023 and caused widespread destruction and severely impacted vulnerable communities in Jajarkot and Rukum West districts[2]. During the reporting period, the JRAP advanced critical recovery interventions to support displaced and marginalised populations, including female-headed households, children, persons with disabilities, and ethnic minorities. As a multi-cluster programme, the project was coordinated by the UN Resident Coordinator’s Office (RCO) and implemented by: IOM; UNFPA; UNICEF and WFP[3]. The scope of JRAP was expanded in September 2024 to enable partners to swiftly mobilise resources and effectively respond to urgent needs with life-saving interventions, complementing the response and recovery efforts of the government in the areas affected by the floods that hit eastern Nepal. A strengthened RCO (a core principle of UN80 reform) was critical in providing an effective co-ordination function for the participating agencies.
[1] Joint Recovery Action Plan (JRAP)- Western Nepal Earthquake | MPTF Office
[2] A magnitude 5.7 earthquake struck Jajarkot, Karnali Province, Nepal, on 3 November 2023, killing 153 people and injuring at least 375. The earthquake was widely felt in western Nepal and northern India,and was the deadliest to strike the country since 2015.
[3] IOM: International Organisation for Migration, UNFPA: United Nations Population Fund; UNICEF: The United Nations Children’s Fund; WFP: World Food Programme

1. Responding To Humanitarian Emergencies (START Fund Nepal)[4]: (£597,713). Torrential rainfall during the annual monsoon season in early July, mid-August, and late September 2024 caused massive flooding across Nepal as well as several mudslides. The September floods, which caused the most damage and deaths, were caused by the heaviest rainfall recorded in the region since at least 1970, the result of a low-pressure system. The impact of the floods was further increased by poor infrastructure and settlement planning, including unplanned construction on floodplains. Severe floods began on 26 September and heavily impacted several of eastern Nepal's districts. Floods and landslides resulted in the deaths of 224 individuals, with 158 injured and 24 reported missing. Over 700 private houses were completely damaged, while 500 were partially damaged[5]. In light of the situation, NDRRMA invited SFN to provide support in the most affected areas. Based on NDRRMA's request and the situational needs reported by partners, an alert was raised for flood response. Following a decision by the allocation committee, interested partners were asked to submit their proposals. The project selection committee selected four promising proposals from a total of ten to respond to the crisis. Overall, BEK provided funding to START Fund Nepal (SFN) through the following tranches:
  [4] ﷟N-24 Nepal (Response- Flooding All Nepal) | Start Network
  [5] As outlined in the Situation Report published by NDRRMA
  1. £198,713 in August 2024 to respond to small and medium-scale emergencies.
  2. £399,000 in October 2024 as an addition to respond to the Jajarkot earthquake.
The agencies involved through SFN were: Catholic Relief Services (CRS) Nepal; ActionAid International Nepal (AAIN); World Vision International Nepal; Action Contre la Faim (ACF)/Action Against Hunger; Qatar Charity and Plan International.

Summary supporting narrative for the overall score in this review

This reporting review period covers one output for SDR: Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance and focuses on 14 key indicators: 10 indicators for JRAP, and 4 for START Fund Nepal.

Overall, the programme has scored well against previous years. The overall progress over the past year by UN agencies (JRAP) demonstrates a clear improvement on timeliness and coordination against previous years, and points to lessons-learned across the delivery-span of the programme.

The START Fund Nepal component (referred to as: Responding to Humanitarian Emergencies) also demonstrated strong performance, and was able to coordinate NGO partners effectively and deliver the objectives of the programme in a coherent and timely manner.

The areas of greatest strength in the programme were the scale and pace at which UN agencies were able to respond to emerging crises, and to coordinate effectively. The areas for improvement include the continued capacity development of the GoN, and strengthening of localisation commitments.

Major lessons and recommendations for the year ahead

This annual review marks the final review of the programme. A successor programme, RAIN, was established in November 2024, and further recommendations for the overall programme will be captured in the Programme Completion Review (PCR) for SDR. All of the recommendations are to be taken forward by BEK’s Climate and Resilience team and Start Fund Nepal as applicable under the RAIN programming on an ongoing basis.
Recommendations:
(JRAP): To continue to empower the RCO as a convener for any future UN coordinated projects, and for BEK to advocate this approach among key and emerging donors in Nepal.

(JRAP & START): To improve localisation commitments and local voices from the outset of future programmes, including, where possible, in the design phase[6].
[6] Given the volume of NGOs, it is recommended to have 1 key NGO representative, with the capacity to attend regular engagements with the RCO/UN agencies, and ensure sufficient feedback to and from the broader NGO community within the relevant cluster/affected geography.

(JRAP): To improve cluster coordination among the local, district & provincial levels, and national-level, in order to interlink coordination across the WASH, Shelter, Nutrition, Food Security and Protection clusters[7].
[7] At the local level, where clusters do not exist, the Local Disaster Management Committee, Executive Committee, and Ward Committee should be fully engaged.

1. (START): To increase Anticipatory Action capacity through the utilisation of a wider range of existing tools:
  1. Broader utilisation of weather forecasting data;
  2. Consultation with humanitarian actors & local communities;
  3. To draw further evidence and lessons from existing anticipatory action projects (both in Nepal and in similar contexts globally).

(START): To ensure coordination and continued relationship management with both the National Disaster Risk Reduction and Management Authority (NDRRMA) and the provincial, local government.

(JRAP & START): To consider a qualitive approach to Safeguarding and AAP (on top of existing efforts), in order to ensure a comprehensive approach to any reporting concerns and feedback, in an effort to ensure all concerns are reported and where necessary acted upon.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The SDR Theory of Change (ToC) incorporates strategic interventions on risk reduction, emergency preparedness, humanitarian response and policy support, informed by comprehensive monitoring, evaluation and learning across the portfolio, contributing to reducing disaster risk and resilience building in Nepal.

The assumptions of the SDR Theory of Change have been significantly tested over recent years, during which unforeseen events (notably COVID-19) meant the programme rapidly reprioritised humanitarian assistance at the expense of building longer-term resilience.

The original theory of change focused on: 1. Risk reduction; 2. Preparedness; 3. Response; 4. Mainstreaming; 5. Evidence. This Annual Review focuses on a scaled-down ToC as initially envisaged in the Business Case, due to the closure of prior projects, and as part of the final year of delivery.

Outcome and impact indicators have remained consistent in the SDR ToC framework, aligned with the results framework under Output 1: ‘Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance’.

In light of the need for the programme to pivot to emerging humanitarian responses, the indicators measured in this review focus solely on Output 1 (Humanitarian Response) under the final year of the programme (whereas the previous review in 2024 focused on Output 2: preparedness, which has since concluded).

Multi-Partner Trust Fund
During the 2022 Annual Review of SDR, UN agencies raised concerns around the timeliness of financial disbursements from UNDP (as the UN signatory) in relation to the Multi-Partner Trust Fund (MPTF)[8]. This had impacted the timeliness of responses to the pandemic, and decreased effectiveness when compared to other NGO and UK-UN bilateral funding mechanisms.
[8] BEK established a Multi-Partner Trust Fund (MPTF) in 2019 for preparedness. Funding was channelled in response to the COVID-19 pandemic in 2020, which supported both the Government of Nepal (GoN) and the UN, through: WFP, UNICEF, UNFPA, UN Women, IOM and WHO, with coordination through the UN Resident Coordinators Office (UNRCO).

BEK independently reviewed the joint UN preparedness and response funding modalities in Nepal (MPTF and Making Preparedness Pay, plus UNRCO coordination and information management) in 2023, in order to identify the impact UK funding, through joint UN programmes, has had on long-term disaster preparedness and system strengthening to medium and large-scale disasters in Nepal, and to assess whether current MPTF modalities for joint UN approaches remained suitable for preparedness, response, and coordination/information management. It raised concerns regarding the design process (and whether it was sufficiently collective), accountability and ownership of aligned activities and joint outcomes and the effectiveness of the MPTF modality. It also included recommendations on addressing these concerns in future.

As part of the delivery of JRAP, the findings and recommendations from the FCDO review of MPTF were shared with the RCO and the UN agencies engaged with the programme, as a condition of delivery and improvement[9]. IAD recommendations on mitigating risk from cash transfers and beneficiary selection were also shared as a condition of funding.
[9] This was to ensure timely delivery without delay in disbursement of funds from MPTFO to UN HQ, followed by disbursement in Nepal.

The recommendations proved effective: the agencies achieved the agreed recommendations outlined in the MPTF review, notably in terms of ensuring the RC role being central to the coordination process, and improvements in the design and initial delivery phases: which was demonstrated through regular and close engagement (every 2 weeks, followed by monthly) with all agencies convened by the RCO and with FCDO participation.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The impact statement for the SDR programme: 'Nepal reduces risk and builds resilience to earthquakes and other hazards' with the impact indicator on the 'number of people who have built resilience against natural hazards' has exceeded expectations in some areas (immediate response), but required greater traction in others (longer-term resilience) owing in part to the overall length of the programme and the pivot towards emerging responses.

The outcome statement for the SDR programme is 'increased preparedness and improved capacity of disaster risk management systems enable to build resilience to natural hazards in Nepal' and progress against the outcome indicators for this review period are set out below in Section C.

The formation of the National Disaster Risk Reduction and Management Authority[10] (NDRRMA) in 2019 with an appointed Chief Executive was a positive step in ensuring an institutional set-up to coordinate disaster resilience at the federal, provincial, and local levels. BEK has continued to support NDRRMA, and over the past year alone the NDRRMA has worked successfully with the Ministry of Finance (MoF) and local and provincial governments to disburse NPR 50k in two tranches to houses affected by the earthquake as grant for temporary housing[11].
[10] NDRRMA: https://bipad.gov.np/np
[11] There had been delays in the delivery of Detailed Damage Assessments (DDA), however GoN allocated NPR 3 billion for reconstruction in Jajarkot and West Rukum from May 2025 onwards.

The Standard Operating Procedures (SoP) for the Humanitarian Staging Areas (HSAs) have, over the past year been successfully approved. However, they have not yet been implemented. This poses challenges for the GoN to manage the operational and dormant logistics hubs across the country sustainably. Overall, it has also impacted the SDR programme's ability to achieve its outcome of sustainable management of logistics hubs across Nepal by the GoN.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The SDR programme has aligned with BEK campaign goals on climate and resilience, the FCDO’s Humanitarian Framework[12] and the International Development Strategy[13]. Furthermore, the SDR has responded to both ICAI and IAD recommendations in from 2022 & 2023. All recommendations were completed in previous reporting years.
[12] Humanitarian Framework: UK humanitarian framework - GOV.UK
[13] International Development Strategy: UK government's strategy for international development - GOV.UK

Flexibility has been built into the programme, providing BEK with the agility needed to rapidly respond to humanitarian emergencies, even in its final year of delivery. Lessons from previous years have been applied – particularly to JRAP, to ensure a rapid, more coordinated and effective response to humanitarian emergencies.

The SDR programme enabled BEK to close active programme components responsibly by March 2025, and apply lessons to provide evidence for the next phase of BEK support on climate and resilience. SDR’s successor, RAIN, will apply lessons and recommendations from this review, as well as any relevant future programmes established by BEK.
## C. DETAILED OUTPUT SCORING

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A
Impact weighting (%):		45%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.1 (Food Security, JRAP) / Provide conditional and unconditional food assistance (cash transfers) to most vulnerable households affected by the earthquake through reconstruction and rehabilitation of community assets (green public works)	# of households/people (disaggregated by gender and disability and geography) receiving conditional and unconditional cash transfers Target: 53,825 individuals (10,765 Households (HHs) - conditional and 30,360 individuals (6072 HHs) - unconditional / # amount of cash (conditional and unconditional) in GBP delivered to most vulnerable households / # of community assets (green public works) reconstructed and rehabilitated with # bio-engineering solutions (trees planted) Target: 30	9838 households (50253 people with 25326 male and 24927 female which includes 371 male and 290 female people with disability) receiving conditional (food assistance for assets) cash transfers. / 954 households (4532 male and 1980 female which includes 603 male and 37 female people with disability) receiving conditional (food assistance for training) cash transfers. 6072 households (29363 male and 14351 female which includes 353 male and 358 female people with disability) receiving unconditional cash transfers. / £2.343 million conditional (food assistance for assets), 0.23 million conditional (food assistance for training), £1.3 million unconditional. Approximately £4 million cash disbursed to the most vulnerable households. / 25 community assets (green public works, road rehabilitation) reconstructed and rehabilitated with 40,480 trees planted as bio-engineering solutions. / (Refer to infographics below for geographies) / Milestones Met: A
Output Indicator 1.2 (Food Security, JRAP) Provide unconditional cash top-ups to pregnant and lactating women in earthquake affected areas targeting the most vulnerable households	# of women and children (disaggregated by gender and disability and geography) receiving unconditional cash transfers as part of nutrition top-up Target: 4465 individuals (number of pregnant and lactating women and children of 6-23 months of age) / # amount of cash (unconditional) in GBP delivered to most vulnerable households as part of nutrition top-ups to pregnant and lactating women and children	905 lactating and 842 pregnant women, and 1399 female and 1402 male (children between 6-23 months) receiving unconditional cash transfers as part of nutrition top-up / £0.272 million nutrition top up unconditional cash delivered to most vulnerable households as part of nutrition top-ups to pregnant and lactating women and children. / (Refer to infographics for geographies in Annexes) / Milestones Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

To respond to nutrition needs and to expand food security support in the affected areas, the Food Security Cluster through WFP-supported programme activities provided food security and nutrition support to households struggling to restore their livelihoods in Jajarkot district and Rukum West district after the November 2023 earthquake.

Support has been provided in the form of conditional and unconditional cash transfers, and nutrition cash top-ups.

Through conditional cash transfers, the Food Assistance For Assets (FFA) and Food Assistance For Training (FFT) modalities have mobilised and engaged beneficiaries in the reconstruction and rehabilitation of public infrastructure damaged by the earthquake using a build back better approach for long-term community resilience.

Unconditional cash transfers were provided to vulnerable households unable to participate in FFA or FFT modalities, while nutrition cash top-ups were provided to family members of FFA and FFT beneficiaries, as well as unconditional cash recipients for pregnant and breastfeeding women and girls and children under the age of two.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output, given the clear tasking of deliverables to UN partners based on their mandate and role in the cluster system, as well as the relatively short timeframe in which to deliver. However key indicators differ from last year, given the need for funding to respond to emerging crises.

In light of the majority of funding for the programme being allocated to WFP (given the type of response focuses on raw materials and cash allocations), significantly greater weighting has been given to this indicator (45%) with the remainder of indicators being weighted evenly (10% and 5%) based upon expenditure.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Figure 1 WFP Infographic outlining Strategic Achievemets for the Food Security Cluster funded by JRAP.

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1.3 (WASH, JRAP) / Community WASH infrastructure are repaired or reconstructed and rehabilitated that includes community water supply schemes, community/HH toilets and school toilets and handwashing stations supporting the most vulnerable households in earthquake affected areas.	# of community WASH supply schemes and toilets that are repaired or reconstructed and rehabilitated helping # people (disaggregated by gender, disability and geography) Target: 70 assets (50 repaid and 20 reconstructed), 5000 HHs toilets and 25000 people / # of schools with functional WASH facilities toilets and handwashing stations helping # students (disaggregated by geography, gender and disability) Target: 50 schools and 15000 children	49 water supply schemes repaired benefitting 17656 people and 22 water supply schemes re-constructed benefitting 9406 people; Total of 2,564 toilets were reconstructed benefitting 12,192 people and further 2,748 toilets repaired benefitting 13,610 people. Out this a total of 16 disable friendly toilets were also reconstructed. / 51 schools supported with water, sanitation and hygiene facilities benefiting 14,814 student and additional 12 schools were provided with water supply through community water supply system support benefitting additional 1,387 students / (Refer to infographics for geographies) / Milestones Met: A
Output indicator 1.4 (WASH, JRAP) / Hygiene Education is promoted and essential WASH supplies is provided as part of preparedness to promote hygiene behaviour and help to prevent disease outbreak in earthquake affected areas	# of people participated in hygiene promotion sessions (disaggregated by gender, disability and geography Target: 65000 / # number of LGs provided with critical WASH supplies (preparedness support provided by geographically by LGs) Target: 10	82,070 people participated in Hygiene promotion sessions in over 100 communities. / 10 LG were provided with technical support and training on development DPRP and also provided support to update their WASH data on NWASH Management Information System (MIS) and initiation of WASH planning process. A further 10 LGs were provided with training on Water Quality testing and water testing kits. WASH supplies for preposition were also provided to 10 LG targeting 1000 HHs that included Hygiene kits, buckets, mugs, portable toilets, IEC[14] materials, water purifiers for immediate support needs to 1000HHs in case of future disasters. / (Refer to infographics for geographies in Annexes) / Milestones Exceeded: A+
[14] Information, Education and Communication materials

Briefly describe the output’s activities and provide supporting narrative for the score.

To support the recovery of water, sanitation, and hygiene (WASH) infrastructure and promote hygiene practices, the WASH Cluster, through UNICEF-supported programme activities, prioritised improving WASH services in earthquake-affected areas.

UNICEF provided technical support and capacity building to enhance the capacities of provincial and local governments and cluster coordination mechanisms, in order to ensure there are coordinated preparedness, response and recovery processes on the ground.

71 communities were supported through water schemes, 51 schools were assisted with the repair and reconstruction of WASH facilities, and over 5,000 households were assisted with the repair and reconstruction of damaged toilets and handwashing facilities and provided hygiene education and supplies to promote dignified living and behaviours and thus reduce the risk of waterborne disease outbreaks in 100 vulnerable communities, reaching over 82,000 people.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output, given the clear tasking of deliverables to UN partners based on their mandate and role in the cluster system, as well as the relatively short timeframe in which to deliver. However key indicators differ from last year, given the need for funding to respond to emerging crises.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1.5 (Shelter, JRAP) / Communities are provided with access to shelter assistance packages and socio-technical support to households rebuilding their homes using earthquake resistant and climate friendly technologies.	# of masons trained (disaggregated by gender and geography) Target: 500 / # of engineers trained (disaggregated by gender and geography) Target: 100 / # of houses constructed using CSEB blocks and people reached (disaggregated by gender, geography and disability) Target: 23+ / # of stone cutting and CSEB blocks enterprises established (disaggregated by gender and geography) Target: 26	157 local masons (28 female and 129 male) trained on earthquake-resistant technologies in facilitation of DUDBC[15] (based on DUDBC's 7 days masons training curriculum); 533 local masons (117 female and 436 male) received 2-day orientations on using CSEB[16] interlocking technology. / Six different training sessions have been conducted for the municipal engineers and sub-engineers on various topics. Since the participants of the training sessions were from the same pool, the maximum # of participants i.e. 64 (5 female and 59 male). / 26 houses constructed (24 CSEB and 2 SMM). 34% of the total model houses are under female ownership; 38% of the total model house owners (1 female and 9 male) are persons with disabilities (either with visual impairments, hearing impairments, physical impairment and one with both physical and hearing impairments). / 28 stone cutting and CSEB blocks enterprises established. All owners are male. / Refer to infographic for geography. / Milestones Exceeded: A+
Output Indicator 1.6 (Shelter, JRAP) / Affected communities have increased capacity and awareness on building back better techniques through an accountable and transparent two way grievance handling mechanisms and strengthening local government's legal framework	# of affected households that are provided with earthquake safer shelter construction techniques messages, information of BBB through IECs and other materials (disaggregated by gender and geography). Target: 5480 / # of affected community people benefitting from existing grievance handling mechanism established at the local level (disaggregated by gender and geography) Target: 3100HH[17]s / # of plans, policies and guidelines endorsed by the local government (building bye laws, reconstruction and recovery action plans and resilience plans). Target: 20	18322 households were provided with earthquake safer shelter construction techniques messages, information of BBB through IECs and other materials (includes socio-technical facilitation, intensive door-to-door technical support, theatre events, mobile van campaigns, consultation meetings, model houses, enterprises, and help desks). / 3462 affected community people benefitting from existing grievance handling mechanism established at the local level (includes direct beneficiaries reached through socio-technical facilitation, mobile van campaigns and theatre events) / 33 plans, policies and guidelines endorsed by the local government (building bye laws, reconstruction and recovery action plans and resilience plans). 13 Recovery and Reconstruction Action Plan for all 13 municipalities; 1 Local Disaster and Climate Resilience Framework (LDCRF) for Barekot Rural Municipality; 5 Building Bylaws for Junichande, Kushe, Shivalaya, Banfikot, and Chhedagad Municipalities; 1 Disaster Preparedness and Recovery Plan (DPRP) for Banfikot Rural Municipality; 13 Green Technology-Based Enterprise Operational Guideline for all 13 municipalities / Refer to infographic for geographies. / Milestones Exceeded: A+
[15] Department of Urban Development and Building Construction
[16] Compressed Interlocking Bricks
[17] Households

Briefly describe the output’s activities and provide supporting narrative for the score.

The Shelter Cluster interventions reached the affected population through IOM-supported programme activities including the construction of model houses using compressed stabilised earth bricks (CSEB), some of which are designed with accessibility features.

In addition to providing immediate shelter solutions, support was provided to establish CSEB and stone-cutting enterprises, and equipping them with machinery, tools, and training to strengthen local rebuilding capacity.

Through targeted community awareness campaigns, training programmes for masons and engineers, and theatre performances, community members were provided with knowledge on safe construction practices, ethical rebuilding standards and the prevention of sexual exploitation and abuse (PSEA).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output, given the clear tasking of deliverables to UN partners based on their mandate and role in the cluster system, as well as the relatively short timeframe in which to deliver.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A+
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.7 (Protection, JRAP) / Vulnerable populations, including children, women, and adolescent girls, have enhanced protection from violence, exploitation, abuse, and neglect through strengthened systems, accessible services, and coordinated psychosocial support.	# of women and adolescent girls increase access to GBV services (disaggregated by geography) Target: 245 / # of women (pregnant and postnatal) and newborns in need of access to safe ANC and delivery services and # of SRH camps organised (disaggregated by geography) Target: 28 camps and 5600 women / # of women and girls utilising and accessing the established # women friendly services as per the set standards (disaggregated by geography) Target: 1500 women and girls / # of pregnant women getting cash assistance with possible complication for referral (disaggregated by geography). Target: 700 women	392 women and adolescent girls with increased access to GBV[18] services provided with different GBV response services including referral to other services (health, legal, psychosocial). / 33572 women (pregnant and postnatal) and newborns in need of access to safe ANC and delivery services and 28 SRH camps organised / 4004 women and girls utilising and accessing the established number of women friendly services as per the set standards. / 1129 pregnant women with possible complications for referral getting cash assistance. / Milestones Met: A
Output Indicator 1.8 (Protection, JRAP) / Child protection systems are functional and strengthened to prevent and respond to violence, exploitation, abuse, neglect, and harmful practices and psychosocial needs of the affected and vulnerable populations identified, and a response provided through coordinated community-based psychosocial services including referral for specialised services.	# of vulnerable children affected by earthquake situation supported with emergency assistance (legal aid, livelihood support, temporary shelters, medical support, care arrangements, cash support, material support) Target: 2250 / # of children reached with # child friendly spaces (disaggregated by gender, disability and geography). Target: 219 / # of people supported through individual/group psychosocial counselling (disaggregated by gender, disability and geography). Target: 1100 / # of people (male, female, children, PwDs) reached through community sensitization (disaggregated by gender, disability and geography) Target: 15,000	2518 vulnerable children affected by earthquake situation supported with emergency assistance (legal aid, livelihood support, temporary shelters, medical support, care arrangements, cash support, material support / 279 children reached with 4 child friendly spaces / 2136 people supported through individual/group psychosocial counselling / 16087 of people (male, female, children, PwDs) reached through community sensitization. Disaggregation by geography in infographics. / Milestones Exceeded: A+
[18] Gender-Based Violence

Briefly describe the output’s activities and provide supporting narrative for the score.

In light of the pre-existing vulnerability of the affected population to protection risks exacerbated by the earthquake, the Protection Cluster, through UNICEF and UNFPA-supported programme activities, expanded the reach of protection initiatives in the earthquake-affected areas of Jajarkot and Rukum West in the recovery phase.

Implementation of the recovery phase included:
a) Establishing four additional child-friendly spaces (CFSs);
b) Identifying vulnerable children and providing emergency services;
c) Continuing awareness interventions through radio, print media, and other platforms;
d) Deploying counsellors and community-based psychosocial workers to address
psychosocial needs;
e) Ensuring access to age-appropriate quality multi-sectoral gender-based violence
services to women and girls;
f) Providing essential and life-saving sexual
and reproductive health services through the provision of inter-agency reproductive
health (IARH) kits, mobile reproductive health services and emergency assistance to
pregnant women and postpartum complications.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output, given the clear tasking of deliverables to UN partners based on their mandate and role in the cluster system, as well as the relatively short timeframe in which to deliver.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.9 (PSEA and AAP, JRAP) / Ensure Accountability to affected population (AAP) that all the resources are wisely used with maximum benefit to the earthquake affected people and ensure Protection Against Sexual Exploitation and Abuse (PSEA) are embedded within the project, aiming at fostering a culture of respect, safety, and accountability across all levels of engagement.	# of community level awareness events on PSEA organised / # of Community Perception Surveys conducted and shared with UN and communities for feedback / # of capacity building sessions organised Target: 3100 HHs	A total of 171 community-level awareness events on PSEA were organised, reaching a wide audience through various channels. These included PSEA awareness sessions delivered via door-to-door services, reaching 821 households; mobile van community awareness sessions, engaging 619 households; theatre events, which reached 2,127 household; bulk SMS messages reaching 11,411 individuals; PSEA orientation training events under “Food for Training” and “Food for Asset” programs reaching 10,786 individuals; FM radio announcements, reaching 92,493 individuals; PESA community outreach events reaching 1,574 individuals; PSEA sensitization for mothers group, reaching 8,566 mothers. Total Reached: 3,567 households and an additional 124,830 individuals through 171 PSEA community awareness events. / The RCO conducted four rounds of community perception surveys across all wards of 13 municipalities in the Jajarkot and Rukum West districts. A total of 6,000 household interviews were carried out, with 1,500 unique households surveyed in each round, ensuring no household was interviewed more than once. / A total of 32 focus group discussions were conducted across four rounds of surveys. These included 4 discussions targeted at female participants, 8 discussions focused on people with disabilities, and 10 discussions with male participants. In total, 324 individuals took part in the group discussions. / A total of 24 Key informant Interviews were conducted in 4 rounds of surveys with local authorities, community leaders, health workers, community-based organisations, organisation of people with disabilities and teachers. In total, 24 individuals were reached. / 4 rounds of community consultative meetings were organised, and the findings of the survey were presented to the Mayor, Deputy mayors, Ward chairperson and community people through consultation program organised in Jajarkot and Rukkum (West). / Total Reached: 6,000 households and an additional 348 individuals through AAP activities. / A total of 8 interagency initiative capacity-building sessions and workshops were organised for local government officials, UN frontline staff, and implementing partners on PSEA as part of JRAP implementation. These included 2 workshops for local government officials, 4 orientation sessions for UN field staff, and 2 capacity-building sessions for implementing partners, with 230 participants in total. / A total of 43 capacity-building sessions were organised for suppliers, vendors, implementing partners, stakeholders, and health workers. These included 15 PSEA capacity-building events reaching 179 individuals, and 28 training sessions for health workers and female community health volunteers, reaching 622 individuals. Total Reached: 51 capacity building sessions were organised reaching 1,031 individuals / Milestones Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

Given the project’s focus on the most vulnerable earthquake-affected populations and the acknowledged heightened risk of sexual exploitation and abuse (SEA), PSEA was a top priority, led by the RCO and worked in tandem with other agencies, notably IOM, UNICEF, WFP and UNFPA.

Demonstrating a firm commitment and accountability to the affected population and community, the Resident Coordinator’s Office led and supported all clusters in implementing robust PSEA measures through various interventions, utilising a multi-layered strategy.

This strategy emphasised the systemic strengthening of implementing partners, capacity building, collaboration with local government, and comprehensive community engagement across all municipalities. The commitments and measures put in place for this component were strong, however there were no reported cases of SEA reported – given the scale and context of the funding, lessons may need to be applied for future programming in order to identify further improvements for reporting mechanisms.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output, given the clear tasking of deliverables to UN partners based on their mandate and role in the cluster system, as well as the relatively short timeframe in which to deliver.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.10 (Nutrition, JRAP) / Strengthen the quality and scale of preventative nutrition services for most vulnerable groups through supplementary feeding, appropriate infant and young child feeding practices, micronutrient supplementation and optimal maternal nutrition. including breastfeeding and complementary feeding through building capacity of community health workers and Female Community Health Volunteers to provide IYCF counselling.	# of mother/caregivers receive IYCF counselling and nutrition education (disaggregated by gender, disability and geography). Target: 5560 / # of Community Health workers and Female Community Health Volunteers trained. Target: 90% of 680	8566 mother/caregivers received IYCF counselling and nutrition education (8142 female and 424 male which includes 14 disabled caregivers/mothers) / 624 Community Health workers and Female Community Health Volunteers trained (468 female and 156 male) which is 92% / Milestones Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

The Nutrition Cluster, through UNICEF and WFP-supported programme activities expanded the reach of nutrition programming in the earthquake-affected areas of Jajarkot and Rukum West in the recovery phase.

Implementation of the recovery phase included:

Strengthening infant and young child feeding (IYCF) knowledge and practices of
mothers and caregivers;
Capacity building of health workers and female community health volunteers (FCHVs). The capacity of health workers and FCHVs through the enhancement of their competencies in IYCF counselling: they were trained and equipped with in-depth knowledge of effective counselling techniques, critical aspects of infant and young child nutrition, and the practical application of this knowledge to support mothers and caregivers.
In addition, nutrition mobilisers were deployed across eight local levels of Jajarkot and Rukum West to ensure high-quality counselling support. These counsellors collaborated closely with community health workers and FCHVs to deliver one-to-one household-level counselling to mothers and caregivers, addressing their specific needs and concerns. Overall, this capacity-building and counselling programme has made significant progress toward empowering health workers and volunteers to champion better nutritional practices, contributing to improved nutrition for infants and young children.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output, given the clear tasking of deliverables to UN partners based on their mandate and role in the cluster system, as well as the relatively short timeframe in which to deliver.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.11 (BEK) / Timely approval and disbursement of humanitarian funding to I/NGOs and UN agencies leading to adequate, well-coordinated multi-sector humanitarian response to people impacted by the monsoon and other disasters.	Funding decisions being made between 1-3 weeks after submission of humanitarian proposals.	BEK made funding decisions within 3 weeks after three iterations for the Joint Recovery Action Plan (JRAP) proposal submitted jointly by the UN Agencies: UNFPA, IOM, WFP and UNICEF coordinated by UNRCO / Milestone Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

BEK acted swiftly to ensure funding decisions were made in an evidence-based and timely manner, working closely with the RCO in order to ensure rapid delivery.

BEK discussed the JRAP proposal with the UNRCO (and partner UN Agencies: WFP, UNFPA, UNICEF and IOM) in mid-April 2024 and after three iterations, an agreement of £12.5 million was signed in early May 2024 within three weeks.

Similarly, BEK provided additional funding of £399,000 to START Fund Nepal (SFN) within two weeks of the September 2024 floods in order to respond to unmet needs of the affected population.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.12 (BEK UK NFI Kits) / # of people (disaggregated by gender and disability) who have received in-kind humanitarian sectoral goods and services (shelter, dignity, WASH, winterisation and other kits).	To be reported against actual response	19593 people (9802 female and 9791 male) who have received in-kind humanitarian sectoral goods and services (shelter, dignity, WASH, winterisation and other kits). UK Prepositioned NFI kits / Milestone Met: A

Briefly describe the output’s activities and provide supporting narrative for the score.

Prepositioned Non-Food Items (NFI) Stocks: International NGOs (CARE consortia and Save the Children) have prepositioned stocks (shelter, dignity and hygiene kits, winter clothes, water filters and mobility kits) across Nepal to enable rapid emergency responses. During this review period, UK-funded prepositioned relief items have reached 19,593 beneficiaries (9802 female and 9791 male) responding to floods, landslides, fires and earthquakes. 5920 kits were distributed which included 1217 shelter kits, 2564 dignity kits, 359 hygiene kits, 108 winterisation kits and 1672 household water filters. Remaining stocks (in limited quantity) were stored in Save and CARE warehouses across the country. See infographics the Annexes below on people reached and the geographies of stocks distributed.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

Output Title	Humanitarian Response. Lives saved and increased resilience of vulnerable individuals to shocks due to the monsoon and other disasters through the provision of timely humanitarian assistance.
Output number:		A	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, in light of new indicators

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 1.13 (Start Fund Nepal and JRAP Flood Response) / # of people able to meet their immediate needs for food and non-food items through targeted vouchers/cash-based support (data to be disaggregated by gender and disability) / # of days taken by Start Fund Nepal members to start response activities.	To be reported against actual response / # of people/HHs provided with unconditional cash transfers for floods (disaggregated by gender, disability and geography) Target (JRAP): 13,170 people (2634 HHs)	21486 households (55,418 people, 27,591 female and 27,827 males reached) via Start Fund Nepal with 1753 HHs receiving food baskets, 1386 HHs cash for work, 989 HHs with multipurpose cash and 635 households receiving nutritional top-ups / 1210 households (6487 people with 3267 female and 3220 males, including 21 male and 9 female people with disabilities) received unconditional cash transfers and 75 GBV survivors received unconditional cash (JRAP Flood Response). / Milestones Met
Output Indicator 1.14 (Start Fund Nepal and JRAP Flood Response) / # of disaster-affected people (disaggregated by gender and disability) who received support through Start Fund responses (especially NFIs, shelter, access to WASH and GBV prevention services)	To be reported against actual response / # of pregnant women and new mother receiving winter kit to cope with harsh winter condition (disaggregated by geography) Target (JRAP): 400 women / # of women and adolescent girls increase access to GBV services (disaggregated by Geography) Target (JRAP): 2500	Through Start Fund Nepal 1200 HH received hygiene kits, 1500 dignity kits, 6000 water bottles, 807 HHs received WASH and 1072 HHs received shelter kits and 6939 people receiving protection messaging and 896 people with counselling. / 400 pregnant women and new mother receiving winter kit to cope with harsh winter condition (JRAP flood response) / 2670 of women and adolescent girls increase access to GBV services (JRAP Flood) / Milestones Met

Briefly describe the output’s activities and provide supporting narrative for the score.

This is implemented by Save the Children UK with Care Nepal as a host agency that retains the UK’s capabilities to respond to small and medium-scale disasters (floods, landslides, forest fires, cold waves and heatwaves) and promote localisation. After the September 2024 floods, the MoU was amended in October 2024 with an additional contribution of £399k. The MoU was also extended until March 2025 to ensure a responsible closure and transition to the new phase of support under RAIN.

On average, Start Fund members activate an emergency response within 72 hours of receiving an alert and have 45-60 days to complete activities. For this review period, SFN activated 4 alerts (3 anticipatory: heatwave, landslides and floods and 1 emergency flood response) within 53 hrs (on average) and reached 21,486 households (55418 people, 27591 females and 27,827 males reached) disaster-affected and at-risk people (21,486 households) through responses across 6 provinces, 13 districts and 33 local governments.

Overall, responses were timely and appropriate, with adequate real-time and post-distribution monitoring. Interventions were timely, identifying gaps and prioritising the most affected and vulnerable. For example, the flood response specifically targeted affected households, particularly vulnerable affected populations, including the elderly, pregnant women and children under the age of 5. Interviews with key agencies as part of this review note the challenges in the distribution of aid in communities – notably from those households not receiving support. However this was mitigated by a clearly defined criteria, which was outlined to affected communities.

This phase has delivered the following training for new partners:
- Sessions on writing an alert note and proposal;
- Project selection and allocation principles;
- Safeguarding and risk management;
- Core humanitarian principles.

This training directly responded to and incorporated content and recommendations from the IAD review of the SDR programme on minimising risk of fraud, corruption, beneficiary selection and safeguarding. The delivery of this component demonstrates a clear follow-up by BEK to the recommendations made by IAD.

Overall, Indirect Cost Recovery (ICR) sharing increased to 85.71% (up from 35.71% the previous year). Furthermore, L/NNGOs participated in 56.25% of allocation meetings and 53.85% of project selection committees through SFN – further enhancing FCDO’s localisation commitments.

Through the MPTF, the UK contributed an additional £225k to provide support to flood affected areas under Food Security and Protection cluster which was delivered by WFP in the form of unconditional cash support and UNFPA who delivered support to pregnant women and new mother via winter kits and to cope with harsh winter condition and increased access to GBV services for women and adolescent girls.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no major changes in the past year to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Key overarching recommendations from last year’s annual review have been met. However, these do not relate to this specific indicator (further recommendations are captured in section G).

## D: VALUE FOR MONEY

Key cost drivers and performance

The VFM assessment for this review period covers interventions from the Joint Recovery Action Plan (JRAP) and Start Fund Nepal (SFN). The value for money assessment using economy, efficiency and effectiveness and equity considering overall cost effectiveness is described below.

Start Fund Nepal (SFN): This project has demonstrated good VFM regarding timeliness, quality and appropriateness of localised humanitarian interventions. The average time to reach disaster-affected communities with lifesaving assistance is 3.29 days (standard is within 5 days), and on average, funding decisions are made within 53 hrs (standard is maximum 72 hrs). Start Fund Nepal reached over 55, 418 (target was 61092) beneficiaries (including 296 with disability) across the four alerts raised during this review period. Around half of the beneficiaries are women, and approximately 80.33% of funds were allocated indirectly to local NGOs. Increased delivery through local NGOs will be more cost effective in the longer term. Overall, SFN represented good VFM.

Joint Recovery Action Plan (JRAP): Through the Multi Partner Trust Fund (MPTF), efficient project delivery was achieved with lesser UN partners such that programming was not thinly spread. Through a series of meetings with agencies as part of this review, UN partners commended the cohesive approach set out by the RCO and referred to many instances where agencies co-shared or represented on the behalf of each agency (a ‘One-UN’ approach) in order to achieve the objectives of the programme. For instance, agencies coordinated clearly in advance to ensure access in hard-to-reach areas through vehicle sharing, improving value for money overall. Coordination from RCO helped to effectively achieve the objectives within the stipulated timeline. VFM assessment for individual partners has been assessed below.

WFP – Food Security Component
WFP demonstrated strong VfM through the timely delivery of both unconditional and conditional cash transfers. Unconditional transfers were completed within one week, while conditional transfers (cash-for-work) were delivered in two tranches over three months. The quality of interventions was ensured through regular monitoring, resulting in the completion of 25 community assets. Equity was a key consideration, with 2,012 individuals reached—over 50% of whom were women. In terms of cost-effectiveness, approximately £4 million (60%) of allocated resources were directly used for cash transfers, effectively reaching the affected population. This sub-component clearly demonstrated good value for money.

UNICEF – WASH Interventions
UNICEF delivered WASH interventions efficiently, completing the repair of 49 schemes and reconstruction of 22 within six months—half the time typically required. These interventions benefited over 17,000 people, reflecting both timeliness and quality. Approximately £1 million (50%) of resources were allocated to direct delivery. Hygiene promotion activities were also efficiently implemented, reaching over 82,070 people within eight months. Equity was well addressed, with 2,518 children receiving emergency assistance and the construction of four child-friendly spaces.

IOM – Shelter
IOM delivered 24 disaster-resilient houses within three months, supported by strong engineering oversight and community engagement. Notably, 40% of housing beneficiaries were persons with disabilities, highlighting a strong equity focus.In addition, IOM established 28 stone block cutting and brick-making enterprises, which were appropriate for stimulating local employment and economic recovery in earthquake-affected areas. The intervention also promoted gender equity, with over 20% female participation in a traditionally male-dominated construction sector.

UNFPA – Protection Services
Although UNFPA experienced initial delays, implementation accelerated significantly post-monsoon. The component demonstrated strong equity considerations, reaching 4,000 women with protection services and 392 women with GBV-specific support. The interventions were appropriate and targeted, focusing on at-risk pregnant and lactating women as well as GBV survivors in the aftermath of the earthquake.

Over the past year, the programme has utilised a pooled funding approach to both JRAP (UN) and START Fund (NGO), demonstrating value for money through a collective approach to funding and pooling resources among agencies. A pooled funding approach also reduces the overall programme management resources required from the donor (FCDO), as opposed to standalone due diligence assessments and agreements with each partner and generally results in less duplication among agencies.

VfM performance compared to the original VfM proposition in the business case

The original Business Case aimed to achieve greater value for money via a Monitoring, Evaluation & Learning (MEL) unit, which would be used to generate management information and results data to inform decision making. As part of its terms of reference, the MEL unit designed a series of Value for Money metrics for the components under the Disaster Resilience and Climate Smart programmes. However, the MEL unit was ultimately terminated due to funding constraints and VFM assessments were accessed at a programmatic level than at a portfolio level. All SDR activities and components will be closed by March 2025 and the overall VFM performance compared to the original VFM proposition in the business case will be appraised in the Project Completion Report (PCR) in 2024/25 given the COVID-19 flex and adaptation to respond to early recovery efforts in 24/25 for Jajarkot earthquake.

Assessment of whether the programme continues to represent value for money

The programme has completed its final year of delivery (and therefore no recommendation will be made to continue). Recommendations from this review should be applied to future programmes, including RAIN, to ensure lessons on VfM continue to be applied. The SDR programme continued to represent strong VFM and has responsibly closed its major components. It remained the vehicle to respond to large to medium scale emergencies in Nepal.

E: RISK

Overview of risk management

The overall risk for the SDR Programme is Major. This remains within BEK's corporate risk appetite.

All implementing partners updated their risk registers regularly and executed appropriate mitigation actions as part of the formal reporting requirements. Over the reporting year, agencies demonstrated the escalation of risk clearly. Furthermore, the strong working relationship with the RCO has enabled risk to be mitigated early through the JRAP component, via regular, ad-hoc meetings.

Strategy and Context (Appetite: Receptive)

Strategy and context remained a major risk for the SDR programme. Frequent changes at the (GoN) ministerial level impacted influencing opportunities to endorse key policy reforms on transitioning the logistics hubs and delineation of roles and responsibilities in disaster risk management.

Furthermore, a lack of clarity on the jurisdiction between the federal, provincial, and local governments on disaster resilience, continues to lead to uncoordinated efforts to prepare and respond to the humanitarian crisis.

The strategy within the START fund project to use 7 NGOs which were non-SFN members[19] posed risks. This was mitigated by BEK meeting lead INGOs and NGOs in Kathmandu as to how they would manage the risks of delivery, and to ensure compliance with UK funding criteria.
[19] IAD recommended that that while this is not against the rules, BEK need to ensure close monitoring of the risks.

Policy and Programme Delivery (Appetite: Receptive)

The major risk to delivery was accepted (as with previous years). There remain unclear guidelines on using unconditional multipurpose humanitarian cash by national and international NGOs in Nepal. UN agencies can deliver unconditional cash, however this is not the case with I/NGOs. Start Fund Nepal members rely on engagement and agreement with local governments on using conditional and unconditional humanitarian cash and vouchers without clear directives on the use of humanitarian cash.

A humanitarian response plan with clear roles and responsibilities is in place, and is reviewed by BEK on an annual basis.

BEK also regularly undertakes training on crisis and post-preparedness, and has undertaken 2 crisis exercises in the last year in addition to the annual review of preparedness plan including using the FCDO risk profile tool and training on humanitarian information management.

The UK supports UN humanitarian coordination and strongly collaborates with donors on preparedness and emergency response. The UK has also invested in preparedness (Humanitarian Staging Areas and some pre-positioned stocks) across Nepal. BEK can also request the deployment of a Humanitarian Response Group (HRG) field team, search and rescue capability and Emergency Medical Team.

Furthermore, the UK maintains strong links with the Nepali military (who act as first responders) through BEK's Defence Attaché. Despite a major risk, appropriate mitigation action warrants the overall risk to be moderate with an appetite to be receptive.

Engagements with key partners as part of this review included references to the risks around delivery in hard to reach and landslide affected areas during the monsoon season – which significantly heightens the chances of landslides. As part of the delivery of this programme, WFP noted injuries to staff contracted to build roads, mitigated by clear health and safety procedures, as well as insurance covering healthcare bills for those affected.

As part of this review, IOM also noted the challenges to their female staff accessing safe and acceptable accommodation[20] in remote areas for prolonged periods (up to 8 months). This was mitigated by ensuring female staff were only posted to regions with adequately safe accommodation.
[20] Notably, ensuring accommodation in guesthouses had a lockable door/separate washrooms.

Financial and Fiduciary (Appetite: Cautious)

The risk for financial and fiduciary programming was accepted as major. Notably, this programme contains a significant cash component, delivered by WFP and START Fund, who engaged with local government, beneficiaries and financial service providers to agree on cash transfers.

There was a risk that UK funds are diverted and not used for intended purposes, however this was mitigated by real-time monitoring and checking receipts, as well as due diligence assessments to ensure adequate controls are in place. In light of recommendations made by IAD in 2023, BEK conducted fraud risk assessments across the delivery chain for all humanitarian implementing partners (WFP, START Fund). The appetite for this risk remained cautious with a net risk of moderate, provided mitigation measures were in place.

Reputational (Appetite: Cautious)

Reputational risks remains major, with the net risk as moderate after appropriate mitigation measures (with a cautious appetite).

For JRAP, there was a risk that the UN agencies would be unable to deliver a high volume of funding within such a short timeframe, leading to improper financial settlements or misuse of UK taxpayer resources, thereby increasing the reputational risk for the UK in Nepal. However, UN partners as well as (at a smaller scale) Start Fund Nepal demonstrated the ability to deliver effectively whilst maintaining pace.

Furthermore, Start Fund Nepal demonstrated steps taken over the reporting period to build the capacity of NGOs through a tailored capacity-building programme, informed by extensive due diligence assessments. SFN provided adequate controls (due diligence assessments before signing agreements and evidence from past performance and partnerships) to minimise reputational risks.

Safeguarding (Appetite: Cautious)

Safeguarding remained a major risk for the programme. SDR partners had adequate safeguarding policies and controls in place as per corporate requirements, but consultants and downstream partners may not understand them, and there was a risk these might not be implemented in the field during implementation.

UN partners (through the JRAP) utilised a standalone PSEA expert as part of the programme, who worked across all agencies, and was also able to ensure delivery partners also ensured a response tailored to disability.

Inefficient controls for implementing safeguarding policies, including reporting, may impact effective delivery, may harm beneficiaries and pose a reputational risk for BEK. The programme team engaged with implementing partners and shared FCDO's reporting process via Reporting Concerns (an integral part of FCDO’s MoUs, Accountable Grant Agreements, and Contracts) and reminds them to share this in equal token with downstream implementing partners and consultants such that they are comfortable in reporting any concerns to FCDO anonymously apart from the organisational reporting and control mechanism in place.

Partners revised their safeguarding risk and mitigation measures, which are discussed as a recurring agenda during quarterly discussions. Controls are in place for monitoring, prevention, detection, and reporting. Likewise, due diligence has been carried out for lead partners, and they are responsible for carrying out further checks on downstream implementing partners, sharing these reports with FCDO and providing assurance on reporting and controls (for example, Start Fund Nepal and WFP).

The programme team continued to work across BEK with the Safeguarding Champion and adopted a consistent approach to mitigating safeguarding risks, share lessons and best practices to better understand these risks, report acts as necessitated, and adopt a zero-tolerance tolerance for safeguarding.

The programme had no safeguarding cases over the course of the year (for both JRAP and START). This may indicate strong safeguarding mitigation procedures, however given the size of the funding it is likely that a more qualitative approach is needed in order to capture all concerns.

After the mitigation measures, this net risk was moderate with a cautious appetite.

Public Service Delivery and Operations (Appetite: Receptive)

This remained a major delivery risk. While programmatic support has ended and the SOPs have been signed for the HSAs, there remains a reputational risk if HSAs are not maintained adequately, and have not been implemented.

BEK is aware that maintenance costs for the foreseeable future are partially covered by WFP and partners (sufficiently for business purposes). After mitigation, the net risk is moderate with a receptive appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

During this Annual Review Period (April 2024-March 2025) the SDR programme spent £13,842,319.63 million:

1. Start Fund: £597,713
2. JRAP: £13,225,000[21]
  [21] This includes support to the RCO
3. (FCDO) Programme Funded position: £19,606.63

Start Fund Nepal: 1st April 2024 - 31st March 2025 (Total MoU value for this period: £970,000)

The MoU for this partnership with Save the Children UK and the Start Fund Nepal Secretariat was hosted by Care Nepal. As agreed in the MoU, £770,000 was released in this review period to respond to small and medium scale emergencies. On top of this, an addition of £200,000 was provided to respond to the Jajarkot earthquake. The programme was due to end in March 2024, but with an MoU amendment this programme was (at no-cost) extended until March 2025 to allow for a smooth transition to a new phase under the RAIN programme.

During this review period, advance payments were made to SC-UK to enable rapid access to funding by implementing NGOs to deliver emergency response.

Allocation to Start Fund Nepal members (national, international and local NGOs) responding to disasters was delivered swiftly after receiving the fund transfer request. Quarterly reports were provided on time, and subsequent tranches were released by FCDO based on spend records. The total spend during this review period was £597,713.

An audit for this component is due in June 2025 to cover two financial years. BEK will ensure that annual audits are carried out for the successor programme RAIN.

Joint Recovery Action Plan: 1st April 2024 – 31st March 2025 (Total MoU Value: £12,725,000)

The Joint Programme was funded through the Nepal MPTF, which uses the pass-through fund management modality. The UNDP Multi-Partner Trust Fund Office acted as the Administrative Agent (AA) of the Fund. Each of the following participating UN agencies receiving funds had signed a standard Memorandum of Understanding with the AA.

- WFP (Nutrition and food security) - £7,000,000
- UNICEF (WASH) - £2,400,000
- UNICEF (Protection) - £440,000
- UNICEF (Nutrition) - £100,000
- IOM (Shelter) - £2,000,000
- UNFPA (Protection) - £560,000
Additional funding was provided for the flood response for £225,000 which was implemented by UNICEF as well as WHO.

Each of the Participating UN Organisations (PUNO) assumed full programmatic and financial accountability for the funds disbursed to it by the Administrative Agent of the Nepal Multi-Partner Trust Fund Office. The FCDO team regularly and closely monitored the spend of JRAP funds through the participating UN agencies. The fortnightly (for three months) and monthly (thereafter) meetings with the FCDO were crucial for delivery at pace and shared discussion on risks. Participating UN agency team members also attested to the strength of this one-UN working with close donor engagement. Likewise, the close coordination on the ground with regular field monitoring was essential for delivery.

Following the submission of the final financial report, which is due in June 2025 as per the MoU, any remaining balance of agency funds shall be refunded to the (MPTF) Fund and subsequently to FCDO.

Support to UN RCO: 1st April 2024 – 31st March 2025 (Total MoU Value: £500,000)

JRAP was governed by a Steering Committee made up of the Resident Coordinator, Heads of Agencies of participating UN agencies and FCDO, which provided strategic direction and oversight. The Convening Agency (the RCO) was responsible for coordinating the programmatic aspects, and the Administrative Agent was responsible for financial administration, while each participating UN organisation had programmatic and financial responsibility for the funds disbursed to it.

The RCO convened quarterly meetings with participating agencies to track progress, flag emerging issues and capture important learning. Regular progress updates were provided to FCDO. The final report is expected in June 2025.

Programme Funded Position (Total Value: £19,606.63)

In order to deliver quality programming and oversight, FCDO funded a country-based staff position in order to deliver SDR programme effectively. This role has ensured the programme remained compliant and accurate in its delivery and has provided an essential role in SDR’s effective delivery.

Date of last narrative financial report	JRAP: Final financial report date is expected to be June as per the MoU / START: 4th February 2025	Date of last audit report	JRAP: Based on the participating UN agencies audit publication dates / START: Due in June 2025

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

4 monitoring field missions were carried out for JRAP as part of this review period: May and June 2024 and September/October and November 2024, which included monitoring and spot checks.

Monitoring for START fund relied on partner checks and indirect reporting.

In relation to evidence and data informing the programme, Start Fund Nepal collected beneficiary data (disaggregated gender and disability data) to inform programming with gender, social inclusion and disability considerations. SFN conducted regular peer-to-peer learning reviews with partners (once every two months) and used evidence from post-distribution monitoring and real-time humanitarian monitoring to adapt live programming based on the context, needs and gaps to ensure timely humanitarian support to impacted and at-risk communities.

Evidence and learning from SFN was used to design the final phase that focused on engagement with communities, and local government where activities implemented by civil society are needs based responding to the gaps before and ahead of small to medium scale disasters.

Accountability to Affected Populations (AAP)

JRAP’s AAP approach, outlined through four rounds of reporting, offered a robust methodology to ensure affected communities provided feedback on the programme and the response overall[22]. Overall, the earthquake’s impact on livelihoods was severe, with 85% of respondents experiencing complete or partial disruption. The loss of assets, such as homes and livestock, was a major challenge, and 41% of respondents lacked strategies to cope with their losses. Many expressed a need for financial support to rebuild their lives, with some considering loans, migration, or alternative livelihoods.
[22] The methodology for the JRAP component of the programme focused on a questionnaire as part of a community perception survey. Community consultations were undertaken to identify key concerns and issues in the affected areas. Four consultations were held with affected individuals, allowing them to contribute directly to the design and framing of survey questions, ensuring that the questionnaire addressed relevant community priorities. The survey utilised a mixed-methods approach, incorporating both quantitative and qualitative data collection. In total, 1,500 household interviews were conducted across 42 wards in 13 municipalities within Jajarkot and Rukkum districts. This was complemented by 8 focus group discussions (4 in each district) and six key informant interviews with government officials, local NGOs, and community volunteers, capturing a diverse range of perspectives and insights. A total of 35 enumerators were trained on the survey ethics, methodologies, and specific questionnaires. A dedicated session for enumerators that focused on interacting with Persons with Disabilities (PWDs) was conducted, led by an expert from the disability committee within the Ministry of Women, Children, and Senior Citizens. This training placed a strong emphasis on adapting communication styles and approaches to suit the specific needs of respondents. Additionally, an individual with experience in conducting focus group discussions, who is associated with Organisations of Persons with Disabilities (OPD), was included in the team to facilitate the Focus Group Discussions with People with Disabilities (PWDs). The data for each of the four rounds was collected over the course of 16 days, from 1500 respondents, using KoBo Toolbox installed on mobile tablets.

Water supply, roads, and school infrastructure were identified as the most critical community reconstruction needs. Only 10% of respondents were fully satisfied with the availability of clean drinking water, and 41% were dissatisfied. Food security was also a concern, with only 31% of respondents reporting that they met their daily food needs.

The findings reveal varying levels of confidence among respondents regarding whether assistance reaches those who need it the most (although the participation in the community perception survey was not restricted to beneficiaries of the JRAP Project: all the individuals affected by the earthquake in Jajarkot and Rukum West were randomly selected).

Only 12% felt they were fully confident that aid was distributed appropriately, suggesting that few believe the system effectively prioritises the most vulnerable. A larger proportion, (56%), felt that assistance somewhat reaches those in need, while 28% believed it does not adequately do so. 4% expressed complete doubt, believing aid fails entirely to reach its intended beneficiaries, highlighting concerns about trust and fairness in the distribution process.

The data highlighted a strong perception that political interference is the primary reason assistance does not reach those most in need, with 48% of respondents identifying it as a major barrier.
Another significant concern was that aid distribution favours those with access to influential networks or connections.

Learning

The SDR programme has closed all major components, and in its final year was used to deliver BEK’s significant (£13m) early recovery support following the Jajarkot earthquake.

The Climate and Resilience Team along with BEK cluster leads on protection, WASH, nutrition and shelter ensured lessons were learned, and recommended improvements on ways of working to be effectively implemented in this final phase and can be applied to future programmes.

Progress against recommendations from 2024:

Recommendation 1: / BEK should continue to work with WFP and donors (USAID, DFAT and ECHO) to jointly advocate for and work towards the responsible transition of the Humanitarian Staging Areas (HSAs) to the Government of Nepal (GoN). This will include constructive engagement with government stakeholders (MoHA/NDRRMA) to help facilitate endorsement of the relevant policies.
(1). Progress observed SDR AR 2024: / BEK has continued to advocate and work with WFP and key donors over the reporting period. The SOPs have been endorsed, however, the full transition of Humanitarian Staging Areas to the Government of Nepal has not yet been achieved (presenting a reputational risk).
Recommendation 2.1 / Work closely with the Evidence and Knowledge Hub and the Governance and Service Delivery Team to agree on principles for federal, provincial and local engagement and work jointly across geographies on providing technical assistance to build institutional capacity on disaster risk management as part of joined-up work while starting the new climate and disaster resilience programme (RAIN) ensuring that coordination, collaboration, and coherence is also informed by gender, disability and social inclusion. Ensure that interventions at the federal, provincial, and local levels are proportionately focused and informed by evidence and contextual analysis.
Recommendation 2:2 / Consider lessons from PIF and NURP to design an optimal contract modality for future programmes offering technical assistance to strengthen systems. Outcome-based contracts are a better model in the next phase of programming (for RAIN), where the focus will shift from policy development to implementation helping GoN’s utilise its own fiscal resources, ensuring that the chosen contract modality allows for clear oversight of expenses.
(2.1 & 2.2). Progress observed SDR AR 2024: / Lessons have clearly been identified and applied to future programmes (notably RAIN) in order to ensure technical assistance and capacity-building. Lessons have also been applied by BEK on contract management. Interventions have been driven by evidence and context analysis (primarily by the delivery partners).
Recommendation 3 / Access contributions to the UN and GoN’s Joint Recovery Action Plan (JRAP) for the Jajarkot earthquake are practical where realistic activities can be delivered on time. Ensure that agencies also respond to the recommendations from the internal MPTF COVID-19 review (on joined up, timeliness, appropriateness and quality delivery of humanitarian interventions) and IAD recommendations on having safeguards to mitigate risk against safeguarding, fraud, corruption, diversion of funds and collusion whilst selecting beneficiaries. BEK will reflect on the lessons from the MPTF review and recommendations from IAD to ensure that all pertinent programmatic risks are audited during field missions and prior to mobilising the new programme. BEK will ensure that all the IAD and UN MPTF recommendations are implemented and tracked consistently for FY 24/25.
(3). Progress observed SDR AR 2024: / Agencies have clearly achieved the recommendations set out in the MPTF COVID-19 review, and as a result have delivered a more effective and coordinated response, within a challenging timeframe. The utilisation of an external (to BEK) review has enhanced the delivery of recommendations. / BEK ensured all recommendations from IAD were delivered, outlined in the 2024 Annual Review of SDR, as well as through funding agreements in 2024/25.
Recommendation 4: / Consider recommendations from NURP’s Project Completion Review during the inception phase of Green Growth Nepal programme to build the delivery model for the cities component. In addition to recommendation 3 above, these include: (i) strategically involving provincial governments; (ii) ensuring there is a robust approach to cluster local governments around investments agreed with the GGN steering committee; (iii) helping municipalities to diversify their financing base for climate resilient infrastructure in cities (iv) making the most of cross BEK working and synergy with other programmes working in the same geographies.
(4). Progress observed SDR AR 2024: / Although not directly linked to the final year of this project, lessons from this recommendation were successfully used to inform the Cities component for ‘Green Growth Nepal’: DevTracker Programme GB-GOV-1-301260

ANNEXES
Output Indicators 1.1 and 1.2 Food Security Infographics