## Annual Review Template

Title: Public Finance Management Multi-Donor Trust Fund – Phase II
Programme Value £ (full life): £4.52m		Review date: Oct-Nov25
Programme Code : 300007	AMP start date: 6/12/2017	AMP end date: 31/01/2028

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	B	B	B	A	A	A	A	A
Risk Rating	Moderate	Moderate/ High	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004272.odt
DevTracker Link to results framework:	AMP Programme Documents Library - Transparency Files - All Documents (TBC)

A. SUMMARY AND OVERVIEW

Description of programme

This annual review took place within the context of a changed ODA landscape. With FCDO’s four shifts – moving from donor to investor, service delivery to system support, grants to expertise, and international intervention to local leadership – we expect our partners to manage and spend their own resources more effectively. That means supporting our government partners to make the most of their own public finances. This programme also contributes to FCDO’s commitment to investing in multilateral mechanisms that strengthen the core systems underpinning government delivery.

The PFM Multi-Donor Trust Fund Phase II (2017–2028), with financial investments made in earlier FY (2018 & 2019), supports PFM reforms in Nepal. It backs system strengthening through a trust fund approach with the Government of Nepal (GoN) and other development partners. It puts the GoN in the lead of its own reforms and places a premium on strategic engagement, e.g. focusing on influencing the process and priorities a new PFM Reform Strategy 2025-2030 – the first in the federal context – being as key activity in 2025. In addition, the PFM MDTF II helps the British Embassy Kathmandu (BEK) manage fiduciary risks and broader PFM activities.

PFM MDTF II has two components: (1) Nepal Multi-Donor Trust Fund programme implemented by the World Bank (WB MDTF) until January 2028; and (2) PFM support facility (PFMSF) for programmes providing financial aid and strategic PFM support to GoN implemented by Alinea from July 2024 until March 2026.

In addition, Nepal underwent significant political upheaval, with the September Gen Z movement attempting to put accountability and transparency back at the centre of politics in Nepal. The Gen Z movement in September 2025 added political uncertainty ahead of the 2026 elections and beyond, but with their demands for accountability may also create an opportunity to advance locally grounded transparency, accountability, and anti-corruption efforts. Despite this uncertainty, 2025 has been a year of strategic progress for PFM MDTF II. The foundation for future reforms was laid with the PFM Reform Strategy (2025-2030) approved by GoN on 27 Aug 2025, just before the Gen Z movement. The approval of the Strategy has enabled the Bank to work collaboratively with the GoN and DPs to develop a new Public Financial Management for Development Effectiveness Project (PFMDEP) and agree to develop a Fiscal Federalism Roadmap which will support implementation of the Strategy. Analytical work has examined how to strengthen accountability mechanisms, improve capital expenditure, and conducting a Public Finance Review have been implemented. Additionally, through the PFM Support Facility, efforts concentrated on strengthening partnerships and delivering tailored technical assistance to the Government of Nepal (GoN) and BEK on key PFM areas, including provincial public expenditure review, legal instruments for LGs, and audit for improved accountability fiduciary assessments.
While Public Expenditure and Financial Accountability assessment scores suggest gradual progress, trends across indicators are mixed: six have improved, seven have declined, and fifteen remain broadly stable, Nepal’s public finance issues remain significant. Fiscal and governance problems continued, such as lower transfers from the federal government and more audit issues at the local level, which made it harder to plan and deliver services. Nepal’s fiscal performance remains marked by prudence and robust revenue collection but faces persistent structural challenges. Revenue execution fell below 80% in FY2022/23 and FY2023/24, compared to an average of over 90% between FY2012/13 and FY2021/22. On the expenditure side, overall budget execution remained below 80%, with capital spending execution dropping below 65% and averaging only 60% from FY2019/20 to FY2023/24[1]. Weak capital expenditure has constrained infrastructure development, reducing Nepal’s public capital stock to approximately 50% of GDP by 2019 (PIMA 2021), limiting growth prospects.
[1] Source for revenue and expenditure data: The Government of Nepal’s Budget Speech for FY2025/26
As Nepal navigates a political transition, the need to strengthen transparency and institutional accountability is more urgent than ever. Persistent weaknesses in state capacity, coupled with governance gaps and corruption risks, have constrained economic development, job creation, and the delivery of essential public services. These systemic challenges have eroded citizens’ trust and weakened the social contract.

Summary supporting narrative for the overall score in this review

The overall score for this Annual Review is ‘A’, reflecting that the programme has met most key milestones and overall performance has aligned with expectations. Despite slow progress during the reporting period caused by high staff turnover, bureaucratic delays, and political disruptions; Nepal achieved a major milestone: the finalisation of the PFM Reform Strategy 2025–2030, developed through consultations with over 700 stakeholders. This achievement demonstrates clear government ownership and provides a roadmap for advancing institutional reform. Combined with greater public pressure for accountability and stronger service delivery, this may create additional reform incentives to progress relevant reforms.

Further progress was marked by the approval of the PFM Reform Operational Guidelines and the Public Finance Management Development Effectiveness Programme (PFMDEP), which together strengthen the framework for implementing the Strategy’s action plans. The PFM MDTF II continues to lay the foundation for addressing systemic PFM challenges by supporting reforms aimed at strengthening fiscal discipline, improving resource allocation, and enhancing accountability across all tiers of government.

While the programme’s limited implementation window of two years for the WB MDTF continued progress along with better prioritisation will enable delivery of key results.

Major lessons and recommendations for the year ahead

Lesson learned

Working through multilaterals to influence strategic reforms requires patience but can pay off if incentives align. FCDO’s shift from a donor to an investor highlights the importance of BEK focusing on how we can best leverage the PFM MDTF II and the relationships surrounding it. Exerting strategic influence over PFM policy frameworks enables us to shape systemic reforms, align incentives, and strengthen fiscal discipline and accountability. For example, the Gen Z movement provided an opportunity to influence WB to adopt greater integration of transparency and accountability measures in the next project phase.

Early and continuous government Involvement during design, drafting, and finalisation significantly improves validation, acceptability, and smooth completion of outputs. Financial Comptroller General Office (FCGO’s) involvement in the SuTRA V2.0 assessment and MoFAGA’s leadership in developing legal instruments ensured timely and efficient delivery. Likewise, collaboration on the development of the M&E framework for the PFM Reform Strategy strengthened BEK’s relationships with Ministry of Finance (MoF) and opened doors for future reforms.

Local level partnerships help embed and create demand for reforms. Collaborating with key local actors such as National Association of Rural Municipalities in Nepal (NARMIN) and Municipal Association of Nepal (MuAN) helped create strong ownership and accelerated processes. For example, NARMIN led the dissemination of legal reviews and supported PFMSF in conducting provincial consultations for SuTRA V2.0 functionality assessment, while MuAN integrated lessons from local government (LG) interactions into its broader activities.

Designing and managing demand led flexible instruments showed the need for careful implementation and calibration of the real demand, particularly in politically sensitive and fast-changing contexts. Flexibility is vital but it comes with trade-offs. These instruments often take more time to set up and manage – yet this extra time helps build deeper understanding and better alignment with policy priorities.

Policy engagement requires direct involvement of BEK and should not be delegated entirely to an implementing partner. This speaks well to FCDO’s shift from grants to expertise where FCDO uses its expertise more directly to influence policy. While the Public Financial Management Support Facility (PFMSF) supplemented BEK’s own TA well, the experience also highlighted that achieving strategic objectives such as strengthening relationships with the Ministry of Finance and key line ministries to ensure coherence and alignment across the BEK portfolio depends on active engagement from BEK staff. The emphasis, therefore, should be on clearly distinguishing where BEK’s leadership and convening role is essential, and where the strategic use of supplier‑provided expertise continues to add value.

Recommendations

To implement the PFM Reform Strategy successfully, the MoF should lead with a clear, well-sequenced and prioritised plan, and work closely with provincial and local governments and DPs. Immediate focus should be on improving public procurement, enhancing budget credibility, and improving capital budget execution across all tiers of government, while maintaining fiscal discipline. The World Bank team should engage with Government of Nepal counterparts to identify immediate needs and agree on next steps. [Responsible: World Bank MDTF team with Fiscal Federalism Coordination Division (FFCD). Timeframe: 2nd quarter of 2026]

To ensure the success of the WB MDTF’s final initiative, the PFM Development Effectiveness Project (PFMDEP) must deliver accelerated support within the remaining two years before closure in January 2028. Strategic leadership from the World Bank and MoF will be critical, alongside timely implementation and rigorous oversight, to achieve results and sustain reform momentum. [Responsible: WB MDTF team and FFCD. Timeframe: ongoing]

With PFMDEP now approved, update outcome and output indicators for PFM MDTF II in alignment with its results framework, and update underpinning assumptions. During this exercise, BEK should set clear targets for PFM priorities in support of its approach of PFM for wider BEK strategic outcomes focused on system strengthening. Lessons from both the World Bank MDTF and the PFM Facility will inform and shape this approach. [Responsible: BEK Governance team with WB MDTF team, including sector colleagues. Timeframe: 2nd quarter of 2026]

  - BEK future engagement with World Bank should focus less on shaping the PFM-MDTF and more on how BEK can strategically use expertise and TA to complement WB efforts. This will rebalance BEK’s investment and allow for more strategic use of BEK expertise. To support this, shift the monitoring framework for the PFM-MDTF should be simplified. BEK’s focus will be on reforms that enable GoN to improve budget execution, e.g. procurement, intergovernmental fiscal transfers, and system strengthening. (Responsible: BEK Governance Team together with sector colleagues and multilateral leads Timeframe: 2nd Quarter of 2026)

BEK’s future engagement on PFM should consider the value of demand led flexible instruments like PFM Support Facility but BEK should set out clear governance and decision-making mechanisms, defined roles, and realistic timelines. Flexibility takes time, that time can be used strategically to improve contextual understanding and strengthen alignment with policy objectives. (Responsible: Governance team; Timeframe: 1st quarter of 2026)
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme impact, as outlined in the original Business case (BC), is “an effective Public Financial Management system that facilitates the delivery of better public services to improve the lives of the people of Nepal”. The three outcomes envisioned in the BC are:

Outcome 1 – Strengthened efficiency and results orientation of the budget cycle a national and sub-national level.
Outcome 2 – PFM reform streamlined for federal context.
Outcome 3 – Enhanced accountability in PFM systems.

The overall logic of the Theory of Change (ToC) remains valid, but some underlying assumptions need adjustment to reflect recent contextual changes. These include the approval of the PFM Reform Strategy and Operational Guidelines, the BEK portfolio reset, and shifts in the development landscape, including USAID’s closure. This will help prioritise and address the finding of a previous Annual Review that PFM MDTF II outcome indicators are too high-level.

Nepal’s Public Financial Management (PFM) reforms are key to improving public services and governance. The original business case aimed to build a strong PFM system that helps deliver better services and improve people’s lives. Its outcomes making the budget process more efficient, adapting reforms to the federal system, and improving accountability are still important. However, recent reviews show mixed progress. While accounting and reconciliation have improved, big challenges remain in budget classification, transparency, and public access to information. Budget preparation and execution are weak, and there are gaps in planning, procurement, internal controls, and oversight. Gender and climate issues are also not well included in budgeting and reporting.

To tackle these challenges, Nepal’s 16th Plan (2024/25–2028/29) prioritises PFM reforms aimed at increasing resource mobilisation, improving capital spending, and ensuring fiscal discipline. Building on this foundation, the Government has introduced its third PFM Reform Strategy 2025–2030 – the first in a federal context – which sets out a detailed roadmap to strengthen budget reliability, enhance revenue management, improve coordination across all levels of government, and reinforce debt and asset management as well as external oversight. The strategy places strong emphasis on transparency, citizen engagement, and integrating gender and climate considerations. These commitments are reflected in the FY2025/26 budget speech, supported by ongoing efforts to mobilise resources for implementation.

Looking ahead, BEK will explore a new ‘enabler’ approach to PFM, working even more directly on challenges that affect BEK’s priority sectors. Lessons from past programmes, global best practices and recent FCDO PFM best buys[2] will guide this approach to make reforms more effective and sustainable.
[2] FCDO PFM and Tax Best Buys paper (launch in 2026) sets out that it is the sequencing and complementary of reform packages that makes all the difference. It provides sector-specific insights—covering PFM and tax in health, education, and climate—and emphasizes the need for deeper engagement with policy teams to disseminate evidence and assess its implications for institutional and systems strengthening.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress toward programme outcomes continues to be slowed by major challenges, including frequent staff changes, bureaucratic delays, and political disruptions. That said, working politically requires navigating this context in a way that paves the way for agreement on reforms that can actually be implemented and have less chance of being obstructed by politically motivated opposition. In this context, the PFM Reform Strategy 2025–2030 is more than just a document, it is a key step toward fixing these problems. The Strategy shows strong government commitment and provides a clear plan for reform. Its potential for impact is even greater now that the PFM Reform Operational Guidelines and the Public Finance Management Development Effectiveness Programme (PFMDEP) have both been approved. Together they create a solid framework for turning plans into action. Although the programme has a short implementation window of two years, steady progress on this path will help deliver important results and lay the groundwork for long-term system change.
The outcome indicators assess whether core PFM systems are improving in practice and becoming more sustainable. While progress has been incremental and constrained by capacity and political factors, recent reform frameworks have helped clarify reform direction. Overall, the indicators demonstrate modest but meaningful progress toward long‑term system strengthening.
Looking ahead BEK will focus on:
Leveraging the World Bank relationships to drive strategic prioritisation and sequencing, the programme will turn strategy into measurable results by working closely with the MoF and the World Bank, emphasising action plans that are properly sequenced, delivered timely, and use digital solutions to make reforms sustainable. Extra efforts will be made to ensure that opportunities are taken to advance accountability in the new evolving context.

Focusing our efforts where they have most Impact on BEK outcomes. PFM is foundational to achieving BEK priorities such as the shift from service delivery to system strengthening because effective resource allocation and execution directly determine service delivery outcomes and system resilience. Reforms in taxation and procurement are also necessary to drive inclusive economic growth and create jobs. We will also look into eco-economics and see whether green taxation can help address Nepal’s climate change challenges.

Reducing the complexity in the log frame and refining outcome areas to focus on priority policy results, with clearer emphasis on measurable improvements such as budget execution.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
With FCDO’s four shifts – moving from donor to investor, service delivery to system support, grants to expertise, and international intervention to local leadership – we expect partners to manage and spend their own resources more effectively. This programme exemplifies FCDO’s commitment to investing in multilateral mechanisms that strengthen the core systems underpinning government delivery. This allows us to focus on strategic priorities, share risks with partners, and influence the reforms most critical to our sectoral investments. Improving our partners’ public financial management (PFM) systems remains essential. PFM within BEK’s portfolio has enabled us to channel funds through government systems to support development priorities until now. While our emphasis has always been on how PFM lays the foundation for stronger service delivery systems; this is now more critical than ever. With ODA contractions in 2025 across a number of priority sectors due to USAID withdrawal, the GoN is experiencing a constrained fiscal space that makes it even more important to maximise the impact of public finances. Within BEK’s reset ODA portfolio and reducing financial Aid, PFM will remain a key enabler for economic transformation, human capital development, and climate finance.

PFM will continue to be a key enabler for priority sectors such as health, education, and climate finance and for promoting inclusive economic growth. This change follows FCDO’s global shift from financial aid and service delivery toward system transformation and accountability. Fiscal federalism remains at the core of this approach, supported by efforts to improve transparency, manage risks, and safeguard UK’s last tranches of financial aid through integrated fiduciary risk assessments.
Continuing PFM MDTF II support at a time where a new Strategy with wide ownership sets a clear strategic direction is therefore a good investment and warranted in the context of the wider BEK portfolio reset. The MDTF’s approach of working through multilateral strategic partnerships and focus on strengthening system rather than direct service delivery fits well with BEK’s new strategy. It provides good value for money and boosts UK influence in Nepal’s governance and reform efforts, even with limited ODA funds. The remaining MDTF phase is essential to consolidate foundational work, ensure system sustainability, and maintain the momentum necessary for achieving long‑term outcomes.
## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Execution rate of capital budget reaches 50% at the end of second trimester and 90% at the end of the year
Output number:		1.1	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1.1 Credible Medium Term Expenditure Framework (MTEF) in place at federal level and basic guidelines on MTEF available at Sub-National Government (SNG) level	WB PFMDEP supports the improvement of the Medium-Term Expenditure Framework (MTEF) and annual budget procedures by addressing gaps identified in the 2024 PEFA Assessment (such as fiscal forecasting, climate alignment, and public access to budget information).	Moderately did not meet expectation (B) / The approved PFMDEP includes a component that supports improving MTEF and annual budget procedures by addressing gaps identified by PEFA assessment 2024.
1.1.2 Basic procurement documents and guidelines developed for SNGs (out of a master list of sub-national level documents to be prepared)	WB PFMDEP focuses on ensuring the preparation and enforcement of a Procurement Procedures Manual that aligns with the Public Procurement Act and Regulations addressing gaps identified by PEFA and CRPFM assessments 2024.	Moderately did not meet expectation (B) / The approved PFMDEP includes a component that supports procurement procedures addressing gaps identified by PEFA assessment 2024 and implementation started
1.1.4 Level of technical and institutional capacities of NNRFC for the effective performance of its role in the Intergovernmental Fiscal Transfers System (IGFT).	The Capacity Development Needs Assessment (CDNA) finds important gaps in how the NNRFC works and helps create a budgeted action plan to improve its rules, work processes, and technical skills so it can better carry out its duties under the constitution.	Met expectation (A) / CDNA identified the significant gaps and prepared detailed capacity enhancement action plan.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scores an ‘B’. This year milestones primarily measure whether the World Bank successfully negotiated a new project, the PFMDEP, which was aligned with the strategic priorities identified in the PFM Reform Strategy and issues highlighted in the 2024 PEFA Assessment. While the milestones were met, they could have been more ambitious given that the Strategy itself has wide political buy-in. That said, achieving them is still significant and a necessary foundation for future reforms. Although the PFM Reform Strategy was delayed, the World Bank kept things moving by finalising the PFM Reform Operational Guidelines and the Project Appraisal Document (PAD) at the same time, ensuring institutional arrangements were ready. Collaboration with the Fiscal Federalism Coordination Division (FFCD) guaranteed subnational input, while early procurement planning and retroactive financing were approved.
On Indicator 1.1.1, in addition to ensuring this priority formed part of the PFMDEP, the World Bank has now agreed with the implementing agency, National Planning Commission’s (NPC), to start implementation of this activity. An ongoing discussion between MoF and the National Planning Commission (NPC) about whether to keep MTEF separately or incorporate into Line Ministry Budget Information System (LMBIS), which may take some time to reach an agreement to move things forward.
On Indicator 1.1.2, in addition to ensuring this priority formed part of PFMDEP, the World Bank has started together with implementing agency the implementation of this activity. Through technical assistance, the World Bank has already started supporting PPMO by reviewing procurement guidelines developed by USAID to ensure alignment and avoid duplication. Risks remain, such as slow government procedures, staff turnover, and caution due to anti-corruption measures, which could cause delays. Recent staffing changes in PPMO mean the World Bank must work closely with the new team to get them up to speed, while ensuring they are focused on system strengthening.

On Indicator 1.1.4, while some institutional challenges faced by the Nepal Natural Resources Fiscal Council (NNRFC) are beyond the control of this project, the Capacity Development Needs Assessment (CDNA) has identified significant gaps that can be addressed. A detailed Capacity Enhancement Action Plan across all three organisational pillars – systems, financial, and human resources – has been produced. Some of the recommendations on regulatory framework reforms and organisational design may prove harder to address but an improved understanding of the needs will make policy discussions on NNRFC’s constitutional mandate, ability to influence the fiscal transfers system, and organisational design more effective. Demonstrating intention to actively use the assessment, NNRFC has requested a Nepali translation of the report, which will be handed over in December.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For this reporting period milestone indicator 1. 1.1, 1.1.2 and 1.1.3, has been updated for Y8 & Y9 based on AR recommendation; draft PFMDEP results framework and analytical work delivered through WB.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR – See Annex.

Lesson learned:

Working through multilaterals to influence strategic reforms requires patience but pays off. FCDO’s shift from a donor to an investor highlights the importance of BEK focusing on how we can best leverage the PFM MDTF II and the relationships surrounding it. Exerting strategic influence over PFM policy frameworks enables us to shape systemic reforms, align incentives, and strengthen fiscal discipline and accountability.

Recommendations:

- To ensure the success of the WB MDTF’s final initiative, the PFM Development and Effectiveness Project (PFMDEP) must deliver accelerated support within the remaining two years before closure in January 2028. Strategic leadership from the World Bank and MoF will be critical, alongside timely implementation and rigorous oversight, to achieve results and sustain reform momentum. (Responsible: WB MDTF team and FFCD. Timeframe: ongoing)
- BEK future engagement with World Bank should focus less on shaping the PFM-MDTF and more on how BEK can strategically use expertise and TA to complement WB efforts. This will rebalance BEK’s investment and allow for more strategic use of BEK expertise. To support this, shift the monitoring framework for the PFM-MDTF should be simplified. BEK’s focus will be on reforms that enable GoN to improve budget execution, e.g. procurement, intergovernmental fiscal transfers, and system strengthening. (Responsible: BEK Governance Team together with sector colleagues and multilateral leads Timeframe: 2nd Quarter of 2026).

Output Title	PFM Reform Strategy in the federalism context established
Output number:		2.1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1.2 No of National and Sub-national PEFA / assessment conducted	'The PEFA Assessment for the Gandaki Province completed, including the PEFA Check, and the report published. / To enhance the capacity of federal and subnational governments to conduct PEFA Assessments as a self-assessment, a tailored PEFA training module specific to Nepal developed, and a pilot training session conducted.	Met expectation (A) / Gandaki PEFA assessment completed and published. / PEFA training module developed, pilot training session conducted, and module handed over to government.
2.1.3 The extent to which the Framework for medium-term Public Financial Management (PFM) Reforms within a federal context developed supported with thorough analysis.	The Cabinet approved the PFM Reform Strategy 2025-30 (Aug 2025), aimed at enhancing the credibility of the PFM system, building upon the findings of PEFA Assessment and developed in consultation with provincial and local governments. / Establish good practices in fiscal federalism over the medium term, the Ministry of Finance approved a concept note for the development of a Fiscal Federalism Roadmap, and fieldwork subsequently commenced Aug 2025. / The Concept Note for the Public Finance Review, aimed at informing how fiscal policy can promote green and resilient growth in Nepal, agreed upon with the government and development partners, and data collection commenced Aug 2025. / The Capital Expenditure Effectiveness Analysis study, analysing the bottlenecks in capital budget execution, published, and an action plan to address the identified issues collaboratively agreed upon with the government.	Moderately did not meet expectation (B) PFM reform strategy approved in Aug 2025. / Fiscal Federalism Roadmap – Preliminary activities were initiated; the roadmap development is on hold due to the political events in September 2025 and government changes. / Public Finance Review – moving ahead with data collection and some initial analysis. / Capital Expenditure Analysis has been conducted, and final report launched in Nov 2025.
2.1.4 Extent to which effective and inclusive institutional arrangements to implement PFM reforms in a federal context are established and operational.	The Government of Nepal established a dedicated PFM Reform Unit within the Ministry of Finance to coordinate PFM reforms within a federal context. / The Government of Nepal established the PFM Reform Coordination Mechanism, which includes representation from subnational governments in the PFM Reform Steering Committee and the formation of a Technical Committee comprising representatives from all three tiers of government. / The Minister of Finance approve the Operational Guidelines to operationalize the PFM Reform Coordination Mechanism, ensuring representation from subnational governments.	Met expectation (A) / PFM reform unit established in MoF. / The Government of Nepal has established the PFM Reform Coordination Mechanism, incorporating subnational representation in the Steering Committee and forming a Technical Committee with members from all three tiers of government / PFM Reform Operational Guidelines, 2025 approved establishing a clear institutional framework and defining roles, responsibilities, and coordination mechanisms in federal context.

Briefly describe the output’s activities and provide supporting narrative for the score.

The output scores an ‘A’. Overall, there has been good progress against indicators 2.1.1 and 2.1.3 but some activity under 2.1.2 indicator were delayed due to the Gen Z movement in September and its aftermath.

On Indicator 2.1.2, The Gandaki Province PEFA Assessment[3] was completed and launched on May 10, 2025, marking Nepal’s first provincial-level PEFA and earning PEFA Check endorsement for compliance with global standards. The report provides a credible baseline for subnational PFM performance and demonstrates political commitment, with provincial leadership pledging to prepare a PFM Reform Action Plan.
[3] The full report is publicly accessible on the PEFA website at: https://www.pefa.org/node/5238

Summary of Gandaki PEFA Scores

A tailored PEFA training module for Nepal was jointly developed by the World Bank and the Asian Development Bank (ADB). This module is designed to foster sustainable and continuous learning among government personnel at all administrative levels regarding the PEFA framework and key PFM topics. A national pilot launch was conducted from March 2 to 7, 2025, engaging over forty officials from federal, provincial, and local governments, as well as representatives from the Institute of Chartered Accountants of Nepal. The training provided a comprehensive examination of the PEFA framework as it applies to Nepal’s context. Post-training participant feedback confirmed improved understanding of PEFA principles and also fed into the final module which was formally handed over to the Government of Nepal on June 30, 2025.

On Indicator 2.1.3, The approval of the Public Financial Management Reform Strategy (PFMRS) 2025–2030[4] by the Cabinet in August 2025 is a major achievement for Nepal’s PFM reform agenda. Although delayed, delivering an inclusive Strategy that took the needs and perspectives of subnational governments into account was a major priority for BEK. The Strategy, shaped through consultations with over 700 stakeholders, now sets a roadmap for better budgeting, risk management, procurement, and gender & climate focused. Its adoption reflects a degree of political will, but turning plans into action will be the real test. Quickly developing the implementation plan is crucial to maintaining momentum. The FY2025/26 budget speech commits to implementing the PFM Reform Strategy and strengthening allocation efficiency and budget discipline in public spending. The government is currently looking for resources to support the implementation of the Strategy.
[4] https://mof.gov.np/content/1630/the-third-public-financial-management-improve-national/

Progress on analytical milestones has been mixed. The Capital Expenditure Effectiveness (Capex) Analysis was launched on November 13, 2025, as a special topic of the WB Nepal Development Update (NDU). This assessment examined key obstacles that hinder implementation progress and disbursement for selected infrastructure projects, including those under the government’s National Pride Projects. The analysis highlighted challenges and recommendations across the entire project cycle, and some of its recommendations are being included as prior actions[5] in the Policy Based Lending (PBL) being prepared under the Mutual Reliance Framework together with ADB, the first in a series of joint budget support operations.
[5] The Capex reforms being proposed are listed below, subject to change as part of the preparation of the policy-based budget support operation. - Amend Public Procurement Act (PPA) regulations to raise approval thresholds; introduce lowest evaluated bid criteria; define abnormally low bids; revise contract variation and termination clauses. - Publish simplified virement guidelines. - Launch digital platform for forest clearance and mandate tree census during Environmental Impact Assessment (EIA).

The Public Finance Review (PFR) was delayed due to political transitions and significant events in September 2025, and the Fiscal Federalism Roadmap (FFR) remains on hold due to the same. While progress is being made on initiating the PFR, it is not appropriate to advance the FFR under an interim government with a limited mandate. It has now been agreed to replace it with a Political Economy Analysis (PEA) of the feasibility and viability of strategic reforms in public financial management (PFM), fiscal policy, the business environment, and service delivery. These are all areas where risks have intensified amid political and institutional volatility. The analysis is expected to help identify tractable areas for reform, and opportunities arisen from the new political context, especially on accountability and transparency.

On Indicator 2.1.3, after some delay, a dedicated PFM Reform Unit has been set up in the MoF, along with a PFM Reform Coordination Mechanism. Both the Steering Committee and the Technical Committee includes members from all three tiers of government. These arrangements are now formalised through the PFM Reform Operational Guidelines 2025, approved by the MoF, providing a clear framework for coordination and implementation. This achievement creates a strong foundation for inclusive and well-coordinated reforms.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For this reporting period milestone indicator 2. 1.2, 2.1.3 and 2.1.4, has been updated for Y8 & Y9 based on AR recommendation; draft PFMDEP results framework and analytical work delivered through WB.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR – See Annex.

Lesson learned:

Limited institutional capacity can be mitigated but not resolved: Limited capacity within Fiscal Federalism Coordination Division (FFCD) significantly delayed approval and initiation of the PFM Reform Strategy. Early risk management and strong support mechanisms proved essential for overcoming operational delays and ensuring sustainability thorough clear prioritisation, sequencing of reforms, and a results‑oriented framework.

Political dynamics must inform the policy dialogue, seizing opportunities while recognising risks: Government changes following political events in September 2025 created uncertainty ahead of the 2026 elections. At the same time, these developments provided an opportunity to expand dialogue on transparency, accountability, and anti-corruption.

Recommendation:

To implement the PFM Reform Strategy successfully, the MoF should lead with a clear, well-sequenced and prioritised plan, and work closely with provincial and local governments and DPs. Immediate focus should be on improving public procurement, enhancing budget credibility, and improving capital budget execution across all tiers of government, while maintaining fiscal discipline. The World Bank team should engage with Government of Nepal counterparts to identify immediate needs and agree on next steps. [Responsible: World Bank MDTF team with Fiscal Federalism Coordination Division (FFCD). Timeframe: 2nd quarter of 2026]

Output Title	Strengthened OAG capacity to deliver on its mandate in compliance with International Standard of Supreme Audit Institutions (ISSA)I
Output number:		3.1	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1.4 Development of risk-focused external audit reporting mechanism	WB PFMDEP supports the design of a risk-focused external audit reporting mechanism to strengthen public expenditure management and accountability and improves how audits are planned, reported, and followed up.	Moderately did not meet expectation (B) / The approved PFMDEP includes a component that supports the design of a risk-focused external audit reporting mechanism to strengthen public expenditure management and accountability.

Briefly describe the output’s activities and provide supporting narrative for the score.

On Indicator 3.1.4, output is rated ‘B’. With approval of the PFMDEP, the milestone has been achieved. The milestone was realistic but insufficiently stretching. The World Bank has now agreed with the implementing agency, OAG’s to initiate implementation of this activity. The component aims to update external audit guidelines, introduce risk-based reporting formats, and link National Audit Management System (NAMS) with Public Accounts Committee (PAC) Management Information System for improved follow-up. Given technical complexity, limited audit capacity, and political uncertainty, it is critical that implementation moves swiftly to ensure these reforms translate into operational improvements within the programme timeline.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For this reporting period, indicator 3.1.1 was closed as it’s no longer funded under MDTF and a new indicator 3.1.4. added with assumption to reflect new activity under PFMDEP.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

This year’s recommendation, as per output 1.1

Output Title	Increased capacity of Parliamentary Accounts Committee and Finance Committee for assessing public expenditure quality and impact
Output number:		3.3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.3.1 Evidence of effective audit follow up	To improve disbursement and strengthen institutional accountability, the WB PFM for Development Effectiveness project supports the development of Standard Operating Procedures (SoPs) for the Public Accounts Committee (PAC), along with enhanced integration of the National Audit Management System (NAMS) and PAC–MIS interface.	Moderately did not meet expectation (B) / The approved PFMDEP includes a component that supports the development of SoPs for the PAC, along with enhanced integration of the NAMS and PAC–MIS interface.

Briefly describe the output’s activities and provide supporting narrative for the score.

On Indicator 3.3.1, output is rated ‘B’. The milestone to strengthen legislative oversight through the development of risk-focused SOPs for the Public Accounts Committee (PAC) has been approved. The SOPs aim to standardise PAC procedures and help PACs do risk-based follow-up on audit findings and create seamless data exchange between audit and legislative systems. The World Bank has now started with GoN agency PAC’s the implementation of this activity. Key challenges include technical complexity in system integration, limited capacity for risk-based oversight, and slow government processes compounded by political uncertainty. It is critical that implementation moves swiftly to translate these institutional and IT enhancements into operational improvements and restore public trust in oversight mechanisms.
Given the increased focus on accountability, there are opportunities to accelerate progress under this output. Last year, PFM support facility had done a quick mapping exercise on current resources and capabilities of PAC (including SNGs). At the federal level, the PAC is currently not functional because parliament has been dissolved. The previous practice of appointing opposition MPs as PAC chairs has been discontinued, with chairs now often from the ruling party. This hampers their ability to provide real checks and balances and makes investment in capacity building less strategic. Providing some more institutional support to the secretariat for PACs, including on using data and evidence and accessing tech solutions, could be explored. Under another programme, BEK is working on accountability monitoring, which could be expanded to include monitoring of progress on audit recommendations and the activities of PACs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For this reporting period milestone update for Y8 & Y9 based on AR recommendation and the draft PFMDEP results framework.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR – See Annex.
Recommendations
BEK should explore whether the renewed emphasis on accountability provides opportunity to support citizens monitoring of the operation the OAG and the PACs. The Issues Based Approach projects have already experimented with tech-driven accountability platforms, but more efforts may be needed to institutionalise these. (Responsible: BEK Governance Team; Timeframe: By March 2026)

Output Title	Delivery of high-quality analysis of fiduciary and corruption risks in key sectors in Nepal and increase in capacity to support effective PFM systems.
Output number:		4.1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1.1 No of Fiduciary Risk Assessment and/or Annual Statements of Progress are completed and lessons learned captured.	Up to 6 FRAs/ASP, similar assessments, knowledge products, or learning activities carried out (e.g. fund flow, fiduciary risk management, SNG systems) / Number of BEK programmes (at least 2) that reference or incorporate findings from relevant knowledge, assessments and learning	Met expectation A / LISP ASP completed / PFM and Fiscal Federalism Synthesis / - Draft Fund flow analysis and recommendations / - Enhancing FRM approach paper / - Provincial Public Expenditure Review / - Study of fiscal laws / - On-demand support on LISP operational guidelines, ongoing LISP support
4.1.2 Level of skills increased at Federal and SNGs developed to support effective PFM systems.	Complete 4 capacity or system enhancement interventions (at least 2 focused on SNGs) / At least one key capacity and one key system enhancement recommendations are operationalised effectively by SNGs	Met expectation (A) / - M&E support to PFM reform strategy / - SuTRA enhancement: a) functionality assessment and b) matching grant functionality / - LG accountability and audit arrears settlement, a) high level dialogues, b) key legal instruments drafted / - Support to MoF on operationalisation of LMBIS system - for crucial budget period / Ongoing: School audit (ICAN), LG audit arrears settlement - Audio/Visuals)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output scores an ‘A’, There has been significant progress through the Public Financial Management Support Facility (PFMSF), which provided flexible support to the GoN in advancing PFM reforms and strengthening fiscal federalism. Major milestones include the development of an M&E framework for the PFM Reform Strategy, assessment of Sub-National Treasury Regulatory Application (SuTRA) functionality, and completion of integrative public finance analysis at the provincial level. A key achievement was the drafting of legal instruments critical for settling audit arrears at the local government level, which currently amount to NPR 210 billion[6], an issue widely cited as a governance challenge. The PFM support Facility also supported BEK to think differently about risks, for example distinguishing between a purely compliance-based approach to one emphasizing propriety and risk appetite. This reinforced the need to support system strengthening, not just managing fiduciary risk.
[6] https://www.fcgo.gov.np/content/1/consolidated-financial-statements/

On indicator 4.1.1. The synthesis report on BEK’s work in PFM and fiscal federalism was finalised with recommendations for future programming. It aligns interventions, informs BEK’s strategy, and complements PMEL’s synthesis work by covering gaps in analysis on PFM and fiscal federalism. Key progress included draft report on funds flow options for financial assistance and advancing fiduciary risk management, and an integrative public finance analysis in Karnali Province. Findings were shared with provincial government (included Chief minister, ministers and senior officials). These learnings are used to shape a provincial budget calendar and investment priorities for projects to strengthen fiscal discipline and improve resource allocation. A knowledge sharing event with BEK promoted a shift from a regulatory to a propriety-based approach to fiduciary risk management and initiated discussions on defining risk appetite. The Annual Statement of Progress (ASP) for the Local Infrastructure Support Programme (LISP) is due to be completed in December 2025. The LISP ASP integrates key fiduciary risk management learnings, particularly the focus on propriety and risk appetite, to strengthen programme integrity. Similarly, adding the matching grant reporting functionality improves financial reporting for BEK sector priorities in infrastructure LISP financial aid reporting. Due to ODA budget cuts and BEK portfolio reset, the Integrated Fiduciary Risk Assessment (FRA) of the three spheres of government was deferred earlier and will now start in December 2025.

On indicator 4.1.2. In this review period, PFMSF supported a Monitoring and Evaluation (M&E) technical expert to develop the Theory of Change and M&E Framework for the PFM Reform Strategy. BEK’s engagement helped include measurement of subnational PFM reform actions and a repeat request for support has recently received to support the development of a comprehensive M&E action plan and build M&E capacity within the MoF. The SuTRA V2.0 functionality assessment was completed. The proposed enhancements expand SuTRA’s scope to include extra budgetary units (EBUs) and public schools, improving governance and accountability of a critical sector. Ownership was secured through multiple consultations with FCGO leadership and LG representatives, resulting in broad acceptance of the proposed design. Matching grant reporting functionality was added to SuTRA in part to support BEK sector priorities in infrastructure, and Institute of Chartered Accountants of Nepal (ICAN’s) work on standardizing school financial statements will be incorporated for consolidated reporting.

With respect to direct support to local governments, three model legal instruments were drafted and endorsed by MoFAGA, shared widely, and one has ministerial approval. To do this, PFMSF worked very closely with the National Association of Rural Municipalities in Nepal (NARMIN) and Municipal Association of Nepal (MuAN) which helped create strong ownership and accelerated processes. Two workshops with oversight agencies and 70 local governments were conducted to enhance understanding of audit arrears and address practical challenges, leading to better governance and fiscal management. A pilot in Shivapuri Rural Municipality tested adoption, with audio-visual materials in development for wider rollout. Efforts also include improving school audits, standardising financial statements, and supporting federal budget preparation and SuTRA enhancements.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For this reporting period milestone update for Y8 based on AR recommendation and PFM facility workplan and assumption added.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR – See Annex.

Lesson learned:

Local level partnerships help embed and create demand for reforms. Collaborating with key local actors such as NARMIN and MuAN helped create strong ownership and accelerated processes. For example, NARMIN led the dissemination of legal reviews and supported PFMSF in conducting provincial consultations for SuTRA V2.0 functionality assessment, while MuAN integrated lessons from local government (LG) interactions into its broader activities.

Early and continuous government Involvement during design, drafting, and finalisation significantly improves validation, acceptability, and smooth completion of outputs. Financial Comptroller General Office (FCGO’s) involvement in the SuTRA V2.0 assessment and MoFAGA’s leadership in developing legal instruments ensured timely and efficient delivery. Likewise, collaboration on the development of the M&E framework for the PFM Reform Strategy strengthened BEK’s relationships with Ministry of Finance (MoF) and opened doors for future reforms.

Designing and managing demand led flexible instruments showed the need for careful implementation and calibration of the real demand, particularly in politically sensitive and fast-changing contexts. Flexibility is vital but it comes with trade-offs. These instruments often take more time to set up and manage – yet this extra time helps build deeper understanding and better alignment with policy priorities.

Policy engagement requires direct involvement of BEK and should not be exclusively contracted out to an implementing partner. This speaks well to FCDO’s shift from grants to expertise where FCDO uses its expertise more directly to influence policy. While the PFMSF supplemented BEK’s own TA well, the experience also highlighted that achieving strategic objectives such as strengthening relationships with the MoF and key line ministries to ensure coherence and alignment across the BEK portfolio depends on active engagement from BEK staff. The emphasis, therefore, should be on clearly distinguishing where BEK’s leadership & convening role is essential, where the strategic use of supplier provided expertise continues to add value.

Flexibility enhances responsiveness and credibility: Built in flexibility within PFM Support Facility allowed timely support to the MoF’s Line Ministry Budget Information System (LMBIS) during a critical budget making phase, reinforcing the value of demand led flexible programming.

Recommendations:

This output will end in Mar 2026. BEK’s future engagement on PFM should consider the value of demand led flexible instruments like PFM Support Facility but BEK should set out clear governance and decision-making mechanisms, defined roles, and realistic timelines. Flexibility takes time, that time can be used strategically to improve contextual understanding and strengthen alignment with policy objective. (Responsible: Governance team; Timeframe: 1st quarter of 2026)
## D: VALUE FOR MONEY

Key cost drivers and performance and VfM performance compared to the original VfM proposition in the business case

The original business case for PFM MDTF II set out a clear VFM proposition, emphasising lean inputs, agile delivery, system-level outcomes, and subnational equity. The preferred delivery route via the World Bank-managed MDTF was selected for its proven track record, robust fiduciary controls, and ability to leverage donor coordination for greater efficiency and effectiveness. The business case anticipated that the MDTF would deliver economy through competitive procurement, capped fee rates, and a strong mix of local and international expertise; efficiency through reduced duplication and harmonised donor efforts; effectiveness by supporting government-led reforms; and equity by targeting system improvements that benefit all tiers of government and marginalised groups.

The main cost drivers for the MDTF were specialist technical assistance and consultancy inputs for the development of the PFM Reform Strategy 2025–2030, Nepal’s first subnational PEFA assessment in Gandaki Province, and technical support to the National Natural Resource and Fiscal Commission (NNRFC), including the review of the Fiscal Equalisation Grant formula and a Capacity Development Needs Assessment. These activities required extensive consultations across federal, provincial, and local levels. For PFMSF, costs were concentrated in technical support to government systems, legal drafting, fiduciary risk analysis, and operational delivery. The extension of PFMSF to March 2026 was accompanied by a £300,000 budget uplift and tighter commercial controls including milestone-based disbursements and KPI-linked fees.

Performance against the original VfM proposition has varied. On the PFMSF, Economy was achieved through maintaining consultant fee rates within agreed caps and increasing reliance on national expertise. The Facility achieved an 80:20 national-to-international consultant/expert ratio as against a 60:40 target that was set. leading to reduced overheads. The MDTF pooled mechanism helped avoid duplication and reduce transaction costs compared to bilateral delivery, while PFMSF’s consolidated fiduciary risk assessments and technical assistance under one supplier resulted in lower procurement overheads. Additionally, operational efficiencies were realised through reduced travel costs (up to 60%); management costs held below the 10% ceiling and shared office arrangements.

Efficiency gains were realised in MDTF’s production of common goods such as the PFM Reform Strategy, Gandaki PEFA, and PEFA training module. Furthermore, the PFMSF milestone-based payments and adaptive management approach strengthened efficient spending and resource reallocation. It was noted that some efficiency challenges such as delays in the legal reform workstreams and slow uptake of IT systems at subnational level arose, mainly due to government delays. These were outside the project’s control but offer useful lessons for future programming.

Effectiveness was demonstrated through outputs that provided the foundation for systemic reform, including Gandaki PEFA completion, PEFA-Check endorsement, finalisation and approval of the PFM Reform Strategy. PFMSF provided targeted support to government priorities, including budget preparation, audit reform, and contributed to the development of an M&E strategy for the PFM Reform Strategy. However, effectiveness gains were constrained by political turnover, delays in cabinet approval of the strategy, and weak coordination across tiers of government which slowed progress on institutionalising reforms and operationalising tools that were developed.

Equity considerations were embedded across both components. For the MDTF, the Gandaki subnational PEFA assessment examined how the provincial government addressed equity by reviewing budget allocations to women and vulnerable groups, assessing ministry targets for reaching women, and analysing funding for initiatives such as maternal health and girls’ education. This ensured that equity and gender considerations were reflected in both the assessment methodology and its evaluation of public spending. PFMSF maintained a strong gender balance within its team, with women accounting for around 40–42% of long-term staff days. Project interventions largely targeted local government areas and provinces where data indicated fiscal disparities, limited access to resources, and minimal PFM-related support. For example, Karnali Province, one of the lowest revenue generating provinces, received targeted assistance. Engagement with local associations ensured inclusive participation of elected representatives and administrative leaders from diverse municipalities, strengthening equitable access to PFM reforms and governance improvements

Cost-effectiveness - during the review period has been influenced by implementation delays and the continued reliance on technical assistance. The MDTF approach provides efficiency through pooled resources and shared expertise, but progress from reform design to implementation has been slower than anticipated. The World Bank has maintained programme continuity and supported the development of key reform frameworks, though challenges related to decision‑making, staffing continuity and adaptive management have affected efficiency. Overall, the programme’s value for money largely reflects its role in establishing essential reform foundations, but stronger prioritisation and focus on implementation will be important to improve efficiency and enhance value for money going forward.

Overall, progress was slower in certain areas due to contextual challenges. Despite this, the programme maintained a credible platform for PFM reform and fiduciary risk work, consistent with its purpose of supporting governance and mitigating risks across BEK’s portfolio. Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, there is sufficient evidence for the programme to continue.

E: RISK

Overview of risk management

The overall risk level of the PFM MDTF II programme in this reporting period remains moderate after mitigation, with all risks within BEK’s risk appetite. The programme risk register indicates a diverse risk profile with major risks in Strategy and Context and Policy & Programme Delivery, moderate risks in Financial & Fiduciary, and minor risks in Public Service Delivery & Operations, Safeguarding, and Reputational areas.

BEK has continued its strong risk management practices by updating the programme risk register monthly and reviewing risk appetite quarterly in the Aid Management Platform (AMP), while ensuring consistent follow-up on mitigation measures. Alinea submits updated risk registers in accordance with FCDO requirements and includes them in quarterly progress reports. Risks are actively monitored through team meetings, field visits, and email correspondence, and remain a standing agenda item in monthly partner meetings. Additionally, the WB team will highlight any risks and address them in technical meetings as needed and also maintains risk information in its six-monthly reports to ensure timely communication and response to emerging challenges.

There are two risks rated major in this programme – strategy and context and delivery. On strategy and context, Political uncertainty in Nepal, including instability of the current interim government and uncertainty about upcoming elections, could slow down or disrupt PFMSF activities. Government functions may be suspended or redirected during the election period, delaying progress towards outcomes. Commitment to federalism is inconsistent, making reforms at the local level harder to achieve. Procurement delays caused by strict anti-corruption measures have already affected projects like the Revenue Management Information System (RMIS) enhancement, which now depends on donor funding. This has created risks of delays, reputational issues, and weaker accountability. On delivery, challenges include frequent staff transfers, limited technical capacity, and poor coordination among development partners, which reduce continuity and ownership of reforms. At present, Nepal is also vulnerable to compound risks around the possibility of political or even constitutional crisis, a significant natural disaster, and further contraction in ODA or changes in donor priorities which can threaten long-term reform efforts and create new unforeseen fiscal pressures and demands on public finances. To manage these risks, the programme uses political analysis, high-level engagement, emergency protocols, adaptive workplans, and advocacy for longer staff tenures. It also focuses on building capacity, keeping strong documentation, and integrating gender and social inclusion principles to make the programme more resilient.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

This is the 8th Annual Review of the PFM MDTF II programme done primarily through a desk-based assessment following a more in-depth review last year. The programme is delivered by the World Bank, which also manages contributions from development partners such as the UK, USAID, Norway, Switzerland, Australia and the EU, and Alinea who implements the PFM Support Facility.

The Alinea International Ltd. contract was signed in July 2024, with amendments in January, March, and June to extend time and costs until March 2026. This extension for the PFMSF project aims to strengthen results by continuing support for ongoing and completed activities, applying lessons from earlier phases, and delivering quick, high-impact actions that offer strong value for money. It will also use remaining funds to provide on-demand support to BEK and create opportunities to share learning widely with BEK teams, other FCDO-funded programmes for better coordination, and the broader donor community engaged in PFM and fiscal federalism.
Component 1 (WB MDTFII) Partnership and Delivery Performance
The World Bank demonstrated strong leadership and worked closely with DPs to keep things transparent and aligned. It organised several technical review meetings on anti-corruption reforms, fiscal federalism, and analytical work, and collaborated with partners like ADB and IMF. Concerns remain about the pace and quality of delivery, but performance has improved moderately as described under relevant outputs. Financial management was strong, with US$18.9M disbursed out of US$21.1M pledged and US$12.6M available for future commitments. To deliver the MDTF’s final initiative successfully, BEK future engagement with World Bank should focus less on shaping the PFM-MDTF and more on how BEK can strategically use expertise and TA to complement WB efforts. This will rebalance BEK’s investment and allow for more strategic use of BEK expertise. The World Bank must accelerate the PFMDEP rollout over the next two years. This requires clear priorities, faster action to remove barriers, and front-loading resources where possible. Strong leadership and effective risk management will be key to achieving results and keeping reforms on track beyond MDTF closure.

Component 2 (PFM Facility) – Alinea: Partnership and Delivery Performance

The project amendment signed during this period extended the contract to March 2026, reflecting BEK’s confidence in delivery. The supplier has shown strong programme management and collaboration throughout the reporting period, maintaining regular communication with BEK through meetings, timely reporting, and scenario-based planning. Strategic partnerships with NARMIN, MuAN, and ICAN have helped accelerate delivery and strengthen local accountability, enabling quick implementation of activities such as SuTRA functionality assessment and matching grant reporting functionality, legal drafting, and school audit reforms while building government ownership. Although delays occurred due to MoF approvals and other contextual challenges, partners adapted timelines to keep progress on track. Key lessons include the importance of early stakeholder engagement, flexibility, and leveraging local associations like NARMIN and MuAN for sustainability and value for money.

Delivery performance has improved overall, with major outputs achieved under revised timelines, including an M&E framework for the PFM Reform Strategy (2025–2030), SuTRA functionality assessment and matching grant reporting functionality, and legal instruments for audit arrears management. Technical assistance to NNRFC and support for BEK programmes like LISP (Local Infrastructure Support Programme and Nepal Health Sector Support Programme) and NHS-SP strengthened coherence in fiduciary risk mitigation. During this reporting period, financial management remained average, with £300,648.38 spent from the remaining £600k budget. Risk management was proactive, supported by the Monitoring, Reporting, and Learning framework. However, in the first two quarters, delays in meeting minutes, reports, and financial forecasts created bottlenecks. These were addressed through fortnightly meetings and later streamlined to monthly sessions, improving communication and reducing administrative burden while maintaining oversight of technical and financial performance.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

This review was undertaken in November 2025 by the BEK Governance Adviser (PRO) and two Programme Managers. It was primarily desk-based, complemented by discussions with delivery partners and a detailed review of programme documentation, including narrative and financial reports, meeting records, and other relevant evidence.

Monitoring approaches differed slightly across the two programme components. For the MDTF, the World Bank submitted two progress reports and convened regular technical meetings, including the July 2025 Programme Coordination Committee which endorsed priorities, reviewed outputs (federal and subnational PEFA assessments), progress on the PFM Reform Strategy, and preparatory work for the PFMDEP. With the reform strategy now approved and PFMDEP underway, more frequent engagement with DPs either at working or technical levels will be critical to delivery and progress monitoring.

PFMSF monitoring was primarily through quarterly reports, fortnightly and then monthly technical meetings with BEK and field-level reviews. Provincial consultations and high-level dialogues shaped certain delivery decisions, such as piloting audit arrears settlement using audio-visual tools. Given the short-term nature of PFMSF, output-level monitoring was initially agreed. As outcome-level results began to emerge, the project introduced outcome tracking and outcome level results have already been discussed in the above sections.

Evidence
Some key evidence generated within the review period include:

Through the PFMSF
Completion of SuTRA V2.0 functionality assessment: This was a review of SuTRA’s architecture and included stakeholder consultations with recommendations for efficiency and integration provided. The assessment identified technical enhancements, including the integration of matching grant functionality and improvements in financial reporting and system integration. These recommendations aim to strengthen the traceability of intergovernmental fiscal transfers and support more robust financial management at the local level.
Draft funds flow analysis and fiduciary risk study completed: The study and analysis outline options for financial aid modalities and recommend a portfolio-based approach to managing fiduciary risk. These findings provide an evidence base that can support BEK’s consideration of delivery routes and risk appetite as partnership models evolve.

Through the MDTF
Completion of Federal and Gandaki PEFA Assessments with PEFA Check Validation: Supported by the WB, the federal PEFA Assessment which incorporated Climate and Gender modules and the Gandaki sub-national assessment were completed and validated These assessments strengthen justification for targeted interventions under the PFM Reform Strategy and supports donor engagement at sub-national level.
Fiscal Equalization Grants formula review was completed, and the revisions are expected to improve transparency, reduce fiscal disparities among local governments while remaining within national fiscal limits.

Learning

Learning was captured and shared through structured processes, including technical meetings with BEK, formal reports, and targeted learning events such as fiduciary risk management and fund flow analysis sessions. These mechanisms supported reflection on delivery, triangulation of evidence from stakeholder consultations, and integration of lessons into subsequent activities.

A synthesis of over 25 BEK studies on PFM and fiscal federalism provided a consolidated evidence base with recommendations useful for other workstreams and the wider portfolio. It highlighted the need for politically informed, flexible approaches, stronger internal coordination, and a focus on system strengthening, citizen accountability, and understanding corruption trends.

Through PFMSF, the LISP Annual Strategic Performance review assessed progress and risks using programme data and consultations. It identified improvements in financial management and planning, as well as gaps such as limited local ownership and fragmented project selection. These findings can inform future programme design and resource allocation, and lessons can be applied to strengthen governance and delivery across BEK-supported work

During the period under review, some broad lessons identified include.

For the programme - flexibility and early engagement with key institutions have been vital for delivery as activities embedded within government systems progressed despite political uncertainty, while those reliant on provincial appetite stalled. Realistic timelines and contingency planning are essential for contracting government entities, given approval complexities. Catalytic, high-VfM interventions that leverage existing systems and relationships have proven most effective.

For the wider FCDO and development work - system-strengthening and integration with government processes offer greater resilience than standalone interventions. Fiduciary risk management requires a portfolio approach balancing delivery with governance objectives. Lastly, while PFMSF’s work has been impressive it also demonstrates that the full benefits of a flexible support facility can only be realised through long-term programming. Short-term facilities, while useful for bridging gaps, cannot fully embed systemic change.

Date of last MDTFII report – Jan to June 2025	Received on 17/09/2025	Date of last audited annual statement	N/A as the arrangement is a Trust Fund managed by the World Bank, and the contract is with Alinea International.
Date of last narrative Quarterly report – July to September 2025	Received on 17/10/2025
Date of last narrative financial report	Received on 20/10/2025

Annex. Progress on recommendations from previous annual review

Recommendations from 2024 Annual Review	Progress	Action
Output 1.1
PFM MDTF II team to update the output indicators and milestones. This should be done together with WB and DPs in alignment with the results framework for new WB MDTF programme (next phase of IPFMRP). WB has shared the draft concept note for the new project at the end of November; approval is expected by Mar 2025.	Action completed	Due to delay in PFMDEP approval indicator milestone was updated in alignment with the draft results framework.
PFM MDTF II team to revise this output description as described in the next phase of IPFMRP programme.	Action completed	Due to delay in PFMDEP approval indicator milestone was updated in alignment with the draft results framework.
The Sahakarya programme should consider lessons from this output and design practical outputs and outcomes that can be achieved by the programme as they start implementation.	No longer applicable	N/a. Due to ODA cuts and BEK portfolio reset Sahakarya never started.
Output 2.1.
PFM MDTF II team to continue engaging through WB MDTF and PFM facility in shaping the PFM Reform Strategy to ensure it is fit for purpose. The engagement should also include influencing GoN to make considerations of the Gender Responsive & Climate Response PEFA 2024 in the next reporting period.	Action Completed	Cabinet approved the inclusive PFM Reform Strategy in August 2025.
BEK through the PFM facility to provide technical assistance to GoN to develop a sound and robust M&E framework for operationalizing the PFM Reform Strategy in the next reporting period.	Action Completed	PFM Support Facility provided support to develop the Theory of Change and M&E Framework for the Public Financial Management (PFM) Reform Strategy. Support for M&E action plans has now been requested.
Output 3.3
BEK team to engage with WB MDTF, ensuring WB MDTF programme (next phase of IPFMRP) considers support to strengthen oversight mechanisms and coordination between oversight agencies. In addition, using the PFM facility to find opportunities to strategically support PAC.	Action completed	PFMDEP have considered activities that support to strengthen oversight mechanisms and coordination mechanisms. It also supports the in developing SoP for PAC.
Output 4.1
PFM MDTF II through the PFM facility to continue providing fiduciary risk management support to BEK and gathering lessons for Sahakarya programme in the next reporting period	Action completed/ ongoing	The PFM Support Facility provided fiduciary risk management for BEK (LISP, Samartha).
PFM MDTF II through the PFM facility to provide technical support based on agreed areas of intervention in the next reporting period.	Action complete/ ongoing	The PFM Support facility is providing analytical support to BEK including on broader PFM landscape in Nepal and fiduciary risks.