Programme Completion Review

Title: Strengthening Foundations of Federalism in Nepal (SFN)
Final Programme Spend £ (full life): £16.2 million	Review Date:	May 2025
Programme Code: 300009	Start Date: 13/12/2019	End Date: 31/03/2025

Summary of Programme Performance

Year	2020	2021	2022	2023	2024	2025
Programme Score	A	B	A	A	A	A
Residual Risk Exposure Rating	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/D0004935.odt / DevTracker Programme GB-GOV-1-300009 Documents
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/D0005715.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The Strengthening Foundations of Federalism Programme in Nepal (SFN) intended to make contributions to establishing the foundations for federalism. In the period of the programme, Nepal’s federalism was in its foundational phase where new institutions (rules of the game), new state structures (e.g. provincial and local governments), and relationships were being formed. Throughout its lifetime, SFN sought out opportunities to nudge Nepal’s transition towards transformational change and the consolidation of federalism, but its pace remained commensurate with the pace of change accepted by the various stakeholders. At the outset, SFN aimed to make core contributions to the following by supporting the Provincial and Local Government Support Programme (PLGSP):
1. Strengthen the ‘architecture’ of federalism in Nepal, including inter-governmental coordination mechanisms.
2. Strengthen new institutions and organisational structures at provincial and local level, such as public financial management, revenue transfer systems and standards for transparency and accountability.
3. Build the capacity of thousands of newly elected local government leaders, including thousands of elected women and political leaders and civil officials from marginalized groups.

Initially, SFN only intended to fund PLGSP, which was designed at a time where Nepal had just begun its journey to implement federalism. The programme started in 2019, after the first elections were held under the 2015 Constitution that made Nepal a federal democratic republic, in late 2017. These elections established the first ever democratic institutions at federal, provincial and local levels. Throughout the duration of SFN fluctuating political commitment to federalism and political instability have been the norm. Aside from the change of political leadership resulting from the 2022 elections, the interim periods have been marked by constant instability and changes in political leadership. For example, despite only one election since 2017, Nepal’s Prime Minister has changed six times and in BEK’s three priority provinces, (Lumbini, Madhesh and Karnali), there have been a total of 12 different Chief Ministers[1]. This reflects that Nepal’s political settlement is still evolving and being continuously contested. In addition, the political culture is dominated by patronage and elite deals. Nepal’s elites remain exceptionally factionalised; elite factionalism is the highest it’s been since the end of the conflict in 2006.[2]
[1] Strengthening Foundations of Federalism in Nepal (SFN) End of Programme Review (EPR), Adam Smith International (ASI), August 2025, p. 12
[2] Since the introduction of federalism in 2017, Nepal has scored 8.8 on “factionalised elites” in the Fragile States Index, the highest it’s been since 2006. (Source: Country Dashboard | Fragile States Index)

SFN, founded as it originally was on PLGSP, was an extremely ambitious programme that reflected the expectation of strong Government of Nepal leadership in implementing federalism at pace. As such its outcomes were that i) government institutions and intergovernmental mechanisms at all levels would be fully functioning, ii) provincial and local governments efficient, effective, inclusive and accountable institutions, and iii) elected representatives and civil servants able to serve citizens to their satisfaction within 5 years. In reality, political commitment to federalism fluctuated, which significantly impacted on what PLGSP was able to deliver.

FCDO picked up on this challenge early and led a multi-year exercise to reshape PLGSP and enable it to better navigate the political realities. Following initial delays caused by COVID-19, FCDO led on shaping a midterm review in 2022 that set the basis for a significant reprogramming of PLGSP. In 2023-24, PLGSP underwent a transitional year where significant changes were made to its governance and ways of operating. The renamed Provincial and Local Governance Strengthening Programme, Phase Two (PLGSP-II) will have devolved governance structures putting provinces in charge of their own plans and budgets, and be supported by higher quality technical assistance that will focus on how to transform Nepal’s systems and processes, rather than providing programme implementation support.

FCDO also added new interventions to SFN to adapt to this changing and challenging context. Additional interventions were part of a strategy to strategically shape PLGSP’s ways of working and improve influencing strategies, including more effective approaches to technical assistance, more empowered and accountable provincial and local governments (PLGs), and improved intergovernmental relations. These included supplementary technical assistance to government at all levels, research and evidence generation, and in SFN’s final year an issues-based programming pilot to test new ways of working politically on Nepal’s systemic challenges. Additions included:

- 2020: The 2nd Phase of a complementary technical assistance programme called Coherence[3] was initiated which provided mentoring support to elected officials in select local governments and demand-based technical assistance to MoFAGA and provincial governments. This also had a strong learning element to help better understand how federalism was evolving, such as a study of local governments were functioning[4].
  [3] Implemented by International Institute for Democracy and Electoral Assistance (IIDEA)
  [4] Local Government Mapping Study, IIDEA, 2023
- 2023: The Provincial Engagement Facility (PEF) to be implemented under the Coherence Programme
- 2024: The Collaborative Governance Pilot (colloquially the Sahakarya Pilot) that aimed to test a new issued-based approach in Nepal.

These programmatic investments were always accompanied by influencing work such as shaping the direction PLGSP, lobbying on key issues and legislation, sometimes jointly with other Development Partners (DPs)[5], and a focus on using learning to influence others’ ways of working.
[5] This was only formally measured since 2023 when an output indicator to this effect was added to the logframe.
An independent End of Programme Review (EPR) acknowledged both successes and contextual limitations of SFN in its assessment against the OECD-DAC’s evaluation criteria[6]. It found that although SFN remained highly relevant and had a high degree of coherence, it delivered partial effectiveness, with overall a poorer performance of PLGSP which had been significantly affected by political economy factors surrounding the continued political contestations over the implementation of federalism. It assessed that SFN was partially impactful and has generated partial sustainability.
[6] EPR, p. 2-3

Table 1. EPR Assessment Summary against OECD DAC Evaluation Criteria

Overall, SFN scores A reflecting the EPR conclusion that it “has made a significant contribution to creating an enabling environment for sustaining current and future outcomes through the institutionalisation of governance processes at the Provincial and Local Government levels.”[7] Although a very ambitious programme, it has delivered well on all its outputs and partially achieved progress towards all outcomes. While a big investment made in PLGSP (57% of programme spend) was negatively impacted by delays caused by COVID-19, fluctuating political commitment to federalism, and strong systemic incentives against its full implementation, the SFN adapted well to this context and successfully navigated the political economy of federalism. In its final years, the learning generated and influence built through the programme was able to significantly shape the redesign of PLGSP-II which now provides a clear foundation for acceleration of the federalisation process. There is anecdotal evidence that this redesign is already achieving impact, for example on strengthening provincial government autonomy. SFN also influenced BEK programmes designs so that they reflect learnings and can deliver better governance impact.
[7] EPR, p. 33-34

That said, sustainability of all these changes will be dependent on a continued political commitment to a federal system of governance. This commitment varies and analysts and poll data do not offer a unified view on this. Some surveys some highlight that there is a generational gap, with the younger generations lending strong support for federalism while others highlight the increasing appeal of a Hindu monarchy. Nepal will have to walk this balance for years to come, as recent pro-monarchy protests have made clear.

SFN was expected to have been followed by a new programme called Sahakarya (Collaboration) – Promoting Collaboration and Democratic Accountability to Strengthen Federalism in Nepal, but in light of the reduction in ODA from 0.5% GNI to 0.3%, this programme will now not go ahead. Nevertheless, lessons from SFN remain informative for continuation of governance impact through other programmes in Nepal as well as in other countries.

Major lessons learned, evidence generated and recommendations

The main lessons generated by this programme are:

Political economy dynamics affecting FCDO outcomes needs to be well-understood and navigated for a programme to succeed. To do this, it is important for FCDO to deepen its engagement with both formal and informal actors that affect the political economy dynamics. The establishment of Provincial Leads and Engagement Facilities in priority provinces to better understand how provincial and national politics interact is an important step.

Adaptation to and innovation in a changing context is critical for maintaining relevance and chances of success. SFN proved adept at adapting and adding new programme components as the environment changed but was less able to change the ways in which PLGSP was implemented. SFN also experimented and placed bets more widely at different points of the programme, which was effective at seizing emerging opportunities and building new partnerships.

Setting out more intentional influencing strategies and priorities and more effective ways of measuring their impact would have been beneficial both to maintain BEK’s focus and evidence its impact. In addition, finding better ways to measure the result of influencing efforts is important.

Aligning a Theory of Change to government systems can present challenges for its utility. While external exercises may not have been value for money, internal exercise to refresh TOCs can help interrogate assumptions and be a critical tool to help document and advance shared understanding of what a programme is intended to deliver.

Means of verification for outcome indicators should be assessed in annual reviews, and if necessary, indicators changed. At design stage, SFN relied on PLGSP indicators but a failure to establish reliable mechanisms for continuing to measure them, measurements of those indicators had to rely on proxy measures.

Logframes (or other results frameworks) should be used to maintain strategic intent, while recording incremental progress. In early years, SFN’s logframe outputs documented what could have been better described as milestones towards a strategic intent. This confused inputs with outputs and outputs with milestones and made it harder to judge whether SFN was going in the right direction.

Priority recommendations for BEK going forward include:

- BEK should continue to innovate and experiment with different approaches to driving change. IBA holds promise, but must be underpinned by both sufficient staff resources, commitment to continue to engage, to support local leadership and localisation, and to place bets that may not yield return but generates learning. Action: Governance Team to continue to test the use of IBA in Nepal and work with senior leadership to integrate IBA into ways of working across the portfolio by April 2026.
- BEK should invest in Thinking and Working Politically (TWP) and find ways to integrate applied Political Economy Analysis (PEA) in all its programmes. With programme successes relying heavily on successfully navigating complex social, political and economic incentives, it is critical for BEK to understand the political economy surrounding the desired change better and to adapt programmes accordingly. It is important to incorporate TWP from the very beginning and combine different tools, including influencing and using policy levers to drive change. Action: BEK co-production process to incorporate TWP and governance tools to set incentives and measure impact by April 2026.

Capacity building interventions should be designed with political constraints in mind and impact should be measured. Programmes that invest in capacity building should first analyse the reasons for the capacity gaps, identify approaches for addressing them where possible, and establish ways of measuring impact of those interventions. This requires smart TA[8] that is incentives not to deliver capacity building interventions, but to work with the politics of the relevant institution. Baselines should be set and post-intervention evaluation methodologies implemented. Action: Governance audit / scan tool to incorporate smart TA and how to recommend measurements of capacity building.
[8] See Understanding and using smart technical assistance, FCDO, April 2025

BEK should invest in how to move from GEDSI mainstreaming to norms transformation across its portfolio. This should include reviewing and deepening implementation of the BEK GEDSI Strategy across the portfolio, to make sure that approaches take into account the evidence on Thinking and Working Politically and social norms change. Action: BEK’s GEDSI Group to review the BEK GEDSI Strategy and portfolio reset to embed TWP and transformative norms principles.

BEK should deepen its engagement with provincial and local level assembly committees, particularly those with a relevance for BEK portfolio outcomes. Assembly committees play critical roles in policy formulation and accountability, and are generally more stable than government ministries, but remain in their formative stages, so may offer a higher return on investment. This is especially important given the persistent challenges of executive-dominated decision-making and the lack of robust accountability mechanisms at the sub-national level. Working with deputy chairs/mayors who head committees at the local level also contributes to the twin goals of inclusion and accountability. Action: The PEA Group to take this forward in subnational stakeholder mapping.

BEK should strengthen its Whole of Society Approach and continue to invest in informal policy dialogue alongside bilateral relationships with a wider range of stakeholders. This can be done by identifying which policy issues have social and political mobilisation and identifying who has the convening power to attract policy makers. Continuation of the issues-based approach, PEF and sector programmes all have a role to play. Action: The portfolio reset to incorporate the principle of integrating a Whole of Society Approach.

See full list of PCR recommendations at Annex A. All recommendations from the 2023 Annual review have been or are on track to be fully implemented (see Annex B).

How this report was conducted
This Programme Completion Report (PCR) covers the entire programme period and replaces the 2024 annual review in line with FCDO guidelines. This report was produced by members of the British Embassy Kathmandu Governance Team, drawing on an independent End of Programme Review (EPR). In writing this report, BEK staff drew on their existing knowledge of Nepal, SFN and its operating environment, and wider research and evidence.

The EPR was commissioned to enhance the evidence base for the PCR. The EPR assessed cumulative achievements, generated and synthesised evidence, identified lessons learned, and provide recommendations for future governance programming in Nepal.[9] The independent review team conducted an extensive literature review, consultations with programme stakeholders, including visits to BEK’s three priority provinces and one additional province for comparison, and followed the OECD DAC framework for evaluation assessing SFN for relevance, coherence, effectiveness, efficiency, impact and sustainability.
[9] EPR, August 2025

This PCR has some limitations because consolidated reporting is not yet available from all implementing partners, and data sources, in particular for outcome indicators, are not accessible. Where possible, alternative data sources have been used.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	GBP 22 million (original BC) / GBP 25.5 million (first BC addendum) / GBP 25.5 million (second BC addendum)	GBP 16.2 million (out of GBP 25.5 million)
Timeframe	Original BC – January 2019 till July 2023 / First BC addendum – January 2019 till July 2023 (cost extension of GBP 3.5m) / Second BC addendum – July 2023 till March 2025 (no-cost, time extension of 20 months)	Total programme timeframe is 74 months (6 years and 2 months)
Outcomes	Government institutions and intergovernmental mechanism at all levels are fully functioning in support of federal governance as per the constitution. / Provincial and local governments have efficient, effective, inclusive and accountable institutions. / Elected representatives and civil servants at provincial and local governments are capacitated to serve citizens to their satisfaction.	Partly achieved / Partly achieved / Partly achieved

Overall assessment of programme outcomes, sustainability and VfM

Nepal’s transition from an extremely centralised unitary system of government to a radically decentralised federal system of government is, according to some experts, unmatched in ambition globally. With its long-standing tradition of “a centralized, direct central-to-local governance model”, Nepal’s shift to federalism is not just a structural but a “deep institutional and cultural” transition.[10] SFN was intended to support this radical restructuring of the state and from the outset set its ambition commensurate with this aim, with a Theory of Change that envisaged this ambitious political project being delivered within five years. It was always understood by FCDO that PLGSP was one vehicle for driving this transformation process, and that its aims and objectives were highly ambitious[11]. That said, a decision was made to base SFN’s own Theory of Change and results framework on PLGSP’s, in an attempt to align and promote ownership. It was envisaged that SFN would help lay the foundations for federalism, after which the system of government would move onto a transformational and then institutionalisation phase. In the spirit of that process of change, overall SFN has largely delivered what it intended but PLGSP in particular progressed less than originally envisaged. SFN was intended to contribute towards the functionality of institutions at federal, provincial and local level, including intergovernmental mechanisms.
[10] Draft Capacity Assessment of Provincial and Local Governments (PLGs) and Partnership Mapping, Geopolicity Inc., June 2025
[11] Analysts have claimed that it may take a decade or two to mature. (Source: Ibid)

The End of Programme Review found that SFN successfully adapted to a changing context and adopted a Thinking and Working Politically approach by increasing its focus on influencing work and adding new programming modalities. Particularly successful at this was the Coherence and Sahakarya Pilot components because “Coherence and the Sahakarya Pilot were more successful in navigating the political economy given the basis of their support was opportunistic and based on entry points identified through political economy analysis”[12]. This improved SFN’s value for money. Initially SFN’s focused on consolidation of certain reforms, but overtime it became evident that these reforms would be so influenced by the political economy surrounding them, that there was a need to shift SFN’s emphasis and the understanding of VFM. Over time, SFN therefore developed a more sophisticated approach to VFM, though this was not consistently measured. Especially in later years, FCDO made a shift in how it managed and leveraged SFN:
[12] EPR, p. 4
- Engagement on PLGSP shifted from a transactional approach using PLGSP and relationships with MoFAGA and Provincial and Local Governments (PLGs) to focus on delivery of certain activities to a more strategic engagement on how PLGSP’s could be used to empower, not just capacitate, PLGs. BEK drove a redesign of PLGSP, with an explicit objective to restructure the governance of PLGSP so that it would empower provincial and local governments (PLGs) and bring onboard the Office of the Prime Minister and Council of Ministers (OPMCM) to drive the stalled progress on intergovernmental relations.
- Recognising the value of norming new institutional relationships and mandates, BEK also made an intentional shift to more engagement with provincial institutions, as evidenced through a changed role of Provincial Engagement Facility (PEF) from late 2023, assigning senior BEK staff leads for provinces and adoption of a BEK Subnational Engagement Strategy in 2024.
- BEK also actively used SFN to drive improvements across the BEK portfolio. The Coherence component, for example, influenced BEK sector work, for example championing more LG discretion in implementation of health outcomes through more flexible conditional grants.
- The Sahakarya Pilot allowed for experimenting a more whole-of-society, less state-centric approach to driving change, which in quite a short period of time proved its ability to unlock “stuck” policy issues, such as adoption of key provincial legislation and clearing long-standing audit arrears. While it is judged too early to assess the real performance and impact of the Issues-Based Approach (IBA) piloted under the Sahakarya Pilot, the EFR concluded that “Innovation is required to support federalism from various angles such as use of an issue-based approach, investment in generation of knowledge materials in various categories and sub-categories to understand and support federalism”[13].
  [13] EPR, p. 40

As a political project, federalism and its implementation was intended to improve people’s experiences of service delivery and inclusion, so SFN’s internal results framework reflected this ambition. While there have been some improvements across all three outcomes, it is important to acknowledge that disaggregating how much of this was contributed by SFN is not possible. That said, it is possible to consider SFN as greasing the cogs of federalism, perhaps at times nudging catalytic progress that might not have happened without it. A shared issue across the outcome indicators originally chosen is that reliable means of verification were not identified at the outset and are now not all available[14]. Therefore, the analysis below has been enriched by other data, using international indices.
[14] Indicators were largely drawn from PLGSP’s Results Framework, but since PLGSP has not been fully evaluated because it is continuing for another 5 years, data is not consistently available.

This data points to a new system of governance where the foundations have been laid, but social and political norms are yet to fully transform institutional and behavioural practices. In terms of contributions to the outcome, the EPR found that “SFN demonstrated partial effectiveness. While the PLGSP component, which accounted for 57% of the total programme expenditure, faced significant challenges in delivering institutional outcomes and inclusive governance, the Coherence programme and Sahakarya Pilot together accounting for 29.9% and 11.5% of the expenditure respectively showed greater adaptability, contextual responsiveness, and stronger engagement in gender and social inclusion.”.[15] Another assessment found that PLGSP has “strengthened the foundations of federalism and promoted more effective governance.”[16]
[15] EPR, p. 2-3
[16] Draft Capacity Assessment of Provincial and Local Governments (PLGs) and Partnership Mapping, Geopolicity Inc., June 2025

OUTCOME 1: Government institutions and intergovernmental mechanism at all levels are fully functioning in support of federal governance as per the constitution.

Partly achieved. While government institutions are settling in and visibly delivering, many challenges remain and progress on intergovernmental mechanisms has been slower than hoped.

Indicator	Baseline / target	Target	Achievement
1.1 # of intergovernmental issues discussed in intergovernmental mechanisms (interprovincial coordination council at OPMCM and Provincial Coordination Council at OCMCM) and potential resolution of the issues	0	45	Achieved. Around 30 meetings were held and it is reasonable to assume that each discussed at least 2 issues[17].
1.2 Citizens who strongly agree that they have equal access to basic services (social security, health, education, water, electricity and protection from disaster). / Proxy indicators / 1.2.1: Presence of public services. / 1.2.2: Perceptions in improvement of ease of access and provision of health care, education, electricity. water. / 1.2.3: Perceptions in improvements of ease of receiving social security services from local governments.	SS:56%, H:40%, E:44%, WE:30%, PD:14%	SS:70%, H:60%, E:60%, WE:50%, PD:50%	Partly achieved. / 1.2.1 Nepal’s score has improved from 6.9 in 2018 to 6.8 in 2024.[18] / 1.2.2: / Health care 5.6% points / Education 12.6% points / Electricity 4.4% points / Drinking water 6.2% points / 1.2.3: 3.7% point decline
[17] The bodies convened were the National Coordination Council (3); the Intergovernmental Fiscal Council (9); and the Inter-Provisional Coordination Councils in all seven provinces (15+).
[18] Services included are the provision of essential services, such as health, education, water and sanitation, transport infrastructure, electricity and power, and internet and connectivity. (Source: Global Data | Fragile States Index)

For indicator 1.1, it is clear that formal interprovincial mechanisms have been more active than intergovernmental (IGR) – between federal and provincial governments – mechanisms. The seven Provincial Coordination Councils (PPCs) have met regularly, and the formal Chief Ministers Forum has also been active and proved a useful policy forum. For example, CMs in these forums were able to agree on a list of priorities for lobbying the PM[19]. On IGR, the Interprovincial Coordination Council (ICC), chaired by the Prime Minister and comprising Chief Ministers and key federal ministers, has been inactive since April 2019, after meeting just for the second time. In the absence of functioning formal mechanisms, informal ad hoc meetings have been held between the PM and CMs – these have been politically driven, not convened by PLGSP and notably lack the legislative authority vested in the ICC.
[19] For example, on police legislation and control over the designation of provincial secretaries. This has led to a change in how provincial secretaries are placed, which is now more within the control of Provincial Governments.

In the absence of functioning constitutionally mandated IGR mechanisms, PLGSP programme governance structures have made a contribution to IGR. The PLGSP National Steering Committee (NSC) convened by the Minister of the Ministry of Federal and General Administration (MoFAGA), have acted as a convener for federal and provincial governments and provided an avenue for provincial governments to raise their voices. The PLGSP NSC has met a total of five times, since 2022 with participation from Provincial Principal Secretaries and since 2023 with participation of Chief Ministers[20]. The February 2025 PLGSP NSC had an additional day where policy priorities like the passing of the Federal Civil Service Bill were debated, which may have helped pave the way for its passing in June 2025, one and half year after it was first tabled. In conclusion, SFN, by supporting PLGSP, substituted for lack of functioning constitutionally mandated IGR mechanisms but made a limited contribution to their functionality. This was in part because PLGSP Phase One was not designed to involve an active role by the Office of the Prime Minister and Council of Ministers (OPMCM). Under BEK Development Partner Group leadership, this was rectified in the new Programme Document adopted in 2024, which spelt out a clear role and responsibility of OPMCM.
[20] NSCs in October 2023, June 2024, February 2025 and May 2025 were all attended by one or more Chief Ministers.

On indicator 1.2, there is no consistent measure of equal access to services and proximate data paints an inconsistent picture. The Fragile State Index noted a very modest improvement in presence of public services during the programme period, but interestingly a spike in 2022 and then a drop down to almost 2019 levels in 2024.[21] In general perceptions of ease of access to services is high and improving but the latest data is from 2022[22]. Perceptions of ease of access to services, across a wide range of services provided by local governments these are generally high, with above 85% reporting ease of access to a variety of services[23]. In particular, improvements have been noted in water, health care, electricity and drinking water[24] but there has been a drop in perceptions of ease of access to social security.[25]
[21] Services included are the provision of essential services, such as health, education, water and sanitation, transport infrastructure, electricity and power, and internet and connectivity. (Source: Global Data | Fragile States Index)
[22] The Asia Foundation’s Survey of the Nepali People for 2025 is expected published in early 2026.
[23] Survey of the Nepali People 2022, The Asia Foundation, p. 44
[24] Perceptions of ease of access was measured as part of asking about reason for optimism. (Source: Survey of the Nepali People 2022, The Asia Foundation, p. 14-16)
[25] Survey of the Nepali People 2025, The Asia Foundation, p. 44

OUTCOME 2: Provincial and local governments have efficient, effective, inclusive and accountable institutions.

Partly achieved. The development of subnational government capacities is mixed with local government perceived to be more trustworthy than provincial government institutions.

Indicator	Baseline / target	Target	Achievement
2.1 Proportion of Population who believe decision making is inclusive and responsive by sex, age and disability (SDG ref 16.7.2) / Proxy indicators / 2.1.1: Public trust in provincial and local governments. / 2.1.2: Public perception of government effectiveness.	Respondents: / 49.6 % with disability / 56.8 % female / 52.1 % age 16 and above / Inclusive infrastructure: / 83.8 % with disability / 70.5 % female / 62.7 % age 16 and above / Accessibility of LG officials: / 48.4 % with disability / 47.4 % female / 44.3 % age 16 and above / Inclusive environment: / 18.8 % with disability / 20.6 % female / 20.6 % age 16 and above / (FY 2020/21)	30% more population believe decision making is inclusive and responsive	Partly achieved. / 2.1.1: People report high levels of trust in wards (79.2%) and municipalities (75.1%) in 2022 but there has been a 10.1% point decline in people who trust provincial government (51.6%) since 2018.[26] / 2.1.2: Nepal has improved its percentile rank from 13.33 in 2019 to 21.70 in 2023.[27]
2.2 Citizens received efficient and timely public services from local governments / Proxy indicators / 2.2.1: Extent to which people think local body restructuring has improved service delivery. / 2.2.2: Corruption Perception Index score.	Convenient Public service = 33.3 % / Promptness in public service = 23.7 % / Satisfaction from public service = 56.4 % / (FY 2020/21) (Corruption index score). / Base Value = 29 % (NGS P 50)	20% more citizens received efficient and timely service; 10% decrease in peoples’ perception on corruption	Partly achieved. / 2.2.1: There is an increase in 9.2% points in people who believe local body restructuring has improved service delivery.[28] / 2.2.2: CPI score in 2024 is same (34) as in 2019.[29]
2.3 Mechanism to hold public office accountable (social audit, public hearing and users committee NNGS 2018 adopted). / Proxy indicators / 2.3.1: % of people who report that a public hearing has taken place in their local government in past year / 2.3.2: % of people who report having participated in a public hearing in past year	% of Population who have not heard about social audit: 44%, Public Hearing: 37%, User Committees: 22%	% of Population who have not heard about social audit: 20%, Public Hearing: 20%, User Committees: 10%	Partly achieved. / 2.3.1: 13.3% point increase since 2018 / 2.3.2: 4.9% point increase but from a low base of 1.7 in 2018
2.4 Open Local/Provincial Government Account (OLPGA) System Developed	0	-	Not measured. Government dropped plans for this, so this indicator is no longer relevant.
[26] In 2018, 45.2% believed that local body restructuring had improved service delivery; by 2022 this had risen to 54.4%. (Source: Survey of the Nepali People 2022, The Asia Foundation, p. 40-41)
[27] Percentile Rank (0-100) indicates rank of country among all countries in the world. 0 corresponds to lowest rank and 100 corresponds to highest rank. (World Bank Governance Indicators: https://www.worldbank.org/en/publication/worldwide-governance-indicators)
[28] In 2018, 45.2% believed that local body restructuring had improved service delivery; by 2022 this had risen to 54.4%. (Source: Survey of the Nepali People 2022, The Asia Foundation, p. 38)
[29] While there has been a slight increase in the score since 2018 (from 31) to 34 in 2024, the period also reflects setbacks and so the score remains the same at beginning and end of programme. (Corruption Perception Index 2024, Transparency International, https://www.transparency.org/en/cpi/2024/index/npl)

Although high levels of trust in local governments and wards with a 76.9% and 79.2% of people surveyed reporting trust in them in 2022 respectively, only 51.6% trust provincial governments and only 56.2% the federal government. [30] It appears that the closer a government is to the people the more trusted they are. The differences in trust levels between local and provincial governments is in part due to the political economy of Nepal’s state development. Local government structures are not entirely new with such structures delivering services under the unitary system as well (Village Development Committees). What is new is that they are democratically elected. In contrast, provincial governments are a completely new tier of governance in Nepal borne out of demands for more representative and devolved politics and a state structure that takes Nepal’s diverse population groups into account and addresses historic marginalisation. In addition, the federal government resource transfers to local governments remain extensive and often come with strings attached, in form of conditional grants. While conditional grants in the budget has remained fairly constant at an average of 63.8% between 2022-24[31], equalisation grants – over which LGs have discretion – have reduced from 10.27% in FY2018-19 to 8.34% in FY2023-24[32]. The proxy indicators do not measure aspects of inclusion as the original indicators had been intended. The original selection of indicators reflects that federalism was introduced in Nepal in order to make the state more inclusive, more responsive to the diversity of the population, and more accountable in order to address historic and entrenched patterns of discrimination and social, economic and political exclusion. Therefore, extent of inclusion remains an important measure of the success of federalism so is discussed in some detail below.
[30] Generally, people report high levels of trust in state institutions with security forces and the public service commission scoring the highest (approx. 90%) in 2027, 2018 and 2022. (Source: Survey of the Nepali People 2022, The Asia Foundation, p. 40-41).
[31] Conditional grants to LGs average 63.8% of their budgets, with a very minimal decrease in last few years FY2022-23: 64.6%; FY23-24: 63.2%; FY2024-25: 63.5%. (Source: Red Book, Ministry of Finance)
[32] Fiscal federalism update

On inclusion, while women representation has improved (see below under outcome 3), the majority groups remain overrepresented in all state institutions. SFN funded research found that in one province, certain minority groups were better represented in the provincial assembly than in provincial government while others did better in provincial government.[33] There is no reliable data on how this affects decision making or people’s perceptions of decision making.
[33] In Lumbini, Tharus comprise 14.3% of the population, holds 16.9% of seats in the provincial assembly but only 12.16 of ministerial posts in the provincial government, while Madhesis comprise 15.47% of the population, holds 10.34% of PA seats but 12.16% ministerial posts. Dalits and Muslims remains the most underrepresented. (Source: Inclusive practices in Lumbini Province: An Analysis from Marginalized Communities’ Perspective, Dignity Initiative, March 2025)

In some contrast to this, on accountability in terms of system strengthening huge progress has been made in laying the foundations with a new local accounting system (SuTRA)[34], rules and regulations for public hearings, and performance reporting through the Local Government Institutional Self-Assessment to all 753 LGs. That said, only 20% believe that at least one public hearing had been held in the past year[35] and SFN funded research has pointed to the fact that one of the formal mechanisms for holding Local Governments to account for delivery, User Committees, are highly politicised and a source of patronage not transparency and accountability[36].
[34] While also funded by BEK, SuTRA was implemented under a different programme.
[35] Survey of the Nepali People 2022, The Asia Foundation, p. 68-69
[36] Local Government Mapping Study, IIDEA, 2023

Outcome 3: Elected representatives and civil servants at provincial and local governments are capacitated to serve citizens to their satisfaction.

Partly achieved. While huge investments have been made in capacitating provincial and local governments, social and political norms continue to prevent their full potential. People are increasingly satisfied with the provision of public services, and women and Dalit representation in LG structures have without a doubt improved but meaningful representation and participation in decision making remains a challenge due to deeply entrenched patriarchal and harmful social norms and social, cultural and political practices.

Indicator	Baseline / target	Target	Achievement
3.1 Proportion of population satisfied with their last experience of public services (Ref SDG 16.6.2)	15% of population fully satisfied	30% of population fully satisfied	Partly achieved. Data for the indicator not available. / Proxy. An average of a 13% point rise in people who think local conditions have improved between 2017-2022.
3.2 Women and Citizens from disadvantaged group empowered to participate in decision making process of local government	4.75%	25%	Partly achieved. Data on extent of empowerment not available. / Proxy. Representation of women in federal government and provincial assemblies have improved, but declined in local governments and issues remain with representation translating into influence on decision-making.

On public satisfaction, local governments in particular are making a difference to people’s lives and citizens report real improvements in local conditions between 2017 and 2022, with an average of a 13% rise in people who think local conditions have improved. The starkest differences are in Bagmati and Madhesh province where there is a 25.6% and 21.7% rise respectively. That said, in all provinces, although there is overall progress in the 2017-2022 period, in all but one province, 2020 figures were higher than 2022 figures higher than in 2017 and 2018. According to the Nepal Voluntary National Review of the SDG 2024, there is some progress in achieving targets related to effective institutions (SDG 16.6), but it is not consistent. The indicator on good governance has seen good progress, while the indicator on corruption has remained stagnant in 2019-24 period and others have gotten marginally worse.[37] It is also likely that confusion about roles and mandates remain and can be expected to negatively impact the quality and value for money of services.
[37] Nepal Voluntary National Review of the SDGs, 2024, p. 115.

On inclusion of women, while formal political representation of women has improved, meaningful participation and influence continues to be hindered by social norms, informal ways of working[38], and the increasing cost of politics[39].  Although Nepal’s state institutions and elected bodies have seen an increase in representation of women[40], various studies point to an either stagnant or downward trend on inclusion of women in decision-making[41]. On political inclusion, the 2017 elections represented a leap in women representation in local governments with almost 50% of municipal positions – mostly Deputy Mayors – held by women. Unfortunately, it was not fully sustained in the 2022 elections and declined by 20%[42], in part due to political parties “gaming” nominations after a decision by two major parties to contest elections as a coalition. Nepal Voluntary National Review (VNR) of the SDG 2024 “detailing SDG 16 targets indicates that women’s representation in national, provincial and local legislatures is 33.6%, 34.5% and 40.9% respectively, showing improvements in representation but not necessarily empowerment within executive decision spaces”.[43]
[38] Local Government Mapping Study, IIDEA, 2023
[39] Cost of Politics and its Impact on Inclusive Political Participation and Socio-Economic Development in Nepal, Democracy Resource Centre Nepal, March 2025
[40] Women in the civil service is increasing now at 28%; women in provincial assemblies average 36% (note no data available for Madhesh, source: EPR, ASI, p. 9); women in local governments decreased slightly in 2022 elections in part due to coalition politics (Source: Coalition and Women’s Political Representation in Nepal, Yale, funded by FCDO through RENT, 2024).
[41] Nepal Voluntary National Review of the SDGs, National Planning Commission, June 2024, p. 115.
[42] Coalition and Women’s Political Representation in Nepal, Yale, funded by FCDO through RENT, 2024
[43] EPR, p. 32

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

SFN’s Theory of Change is based on the PLGSP Theory of Change which was developed collaboratively with the 5 development partners funding PLGSP, design consultants and Government officials[44]. SFN’s outcome statements and measurements were also drawn from this exercise, reflecting the intention to align to government systems. Unfortunately means of verifying progress against the outcome indicators were not available at the end of the programme, in part, because PLGSP’s own M&E system did not deliver as envisaged.
[44] SFN Business Case, 2019

The TOC was highly complex and founded on a set of assumptions underpinning it that did not all fully hold. These were:

The Government of Nepal can manage delivery of a complex governance programme. Based on former experiences of managing large governance programmes in a unitary state system, it was judged that the Ministry of Federal and General Administration (MoFAGA) was capable of managing PLGSP. A risk considered at the time was that this was very different to managing one in a new federal governance structure. To some extent this assumption held, but an undocumented assumption was also made that MoFAGA was – or would become – supportive of decentralisation of authority. This expectation proved misplaced with very strong political and institutional incentives to retain centralised control, expressed in different ways. For example, PLGSP’s programme governance structure did not actually promote devolution of decision-making. This became a major delivery problem for PLGSP. Nor were the deliverables, particularly on intergovernmental relations, within the mandate of MoFAGA and PLGs. Without formal means to engage with the OPMCM it was difficult for PLGSP to make an impact on IGR. PLGSP’s Midterm Review concluded that too much top-down management and control by MoFAGA impacted on both the speed and quality of delivery[45].
[45] PLGSP Midterm Review, 2022

Capacity development can strengthen the core functions of newly established sub-national governments. Evidence for this continues to be mixed, as also mentioned in the Business Case. The experience of PLGSP showed that capacity-building can only go so far and that the wider political economy and institutional context to a large extent determines behavioural outcomes. That said, the most recent Capacity Needs Assessment reflects on the significant progress on capacitating provincial and local government but also points improvements that can be made to accelerate this, notably through strategic investment in digital governance[46].
[46] Draft Capacity Assessment of Provincial and Local Governments (PLGs) and Partnership Mapping, Geopolicity Inc., June 2025

Decentralisation/devolution is more effective when functions are well matched with funds and appropriately skilled numbers of staff. This assumption had strong evidence to support it, but in reality while functions were devolved, funds did not match functions and delays in passing the legislation to set up provincial civil services meant that 33.8% of positions have remained vacant or held by staff with little incentives to drive delivery[47]. While fiscal federalism is advancing in Nepal, there continues to be issues with devolution of budgets and decision-making powers to PLGs. As the Federal Government has sought to match national priorities and accountability of PLGs with a strong desire from PLGs to have more autonomy fiscal federalism holds the key to unlocking the continued contestation over resource distribution.
[47] Nepal Public Service Commission, 65th Annual Report, 2023-24

Decentralisation/devolution can support (a) state legitimacy and (b) service delivery. Although cited with mixed evidence, this appears to have held true in the Nepali context. Research has found that electing representatives from historically marginalised groups can positively affect service delivery, and that if people believe a state to deliver something, they are more inclined to both access the service and invest in improving its quality.[48]
[48] Evidence on Nepal’s Federal Transition: Inclusion, Stability, and State Capacity, RENT, Yale University, April 2025 (forthcoming)

BEK’s internal results framework (the logical framework) went through extensive changes over the years but the Theory of Change was never updated and nor did these changes specifically alter the fundamental intervention logic.

An independent End of Programme Review sought to retrospectively reconstruct the TOC as follows:

Figure 1. SFN Theory of Change

BEK used the logical framework flexibly for management purposes and each year revised it considerably to capture what had already been achieved[49]. The outputs were used to describe what might more appropriately have been captured as annual milestones[50], so it is difficult to establish the strategic intent and track cumulative progress towards that intent over time. In its final two years of the programme, SFN had the following outputs:
[49] In earlier years, substantial logframe changes averaged 8 per year (2021:4, 2022: 12, 2023: 9), while in its final year only 1 change was made (2024).
[50] This approach was also reflected in the sheer number of outputs: 2020 (8), 2021 (10), 2022 (9) while in 2023 and 2024 it was (5) and (6) respectively.

- Output 1. Provincial Centres for Good Governance (PCGGs) made operational to deliver capacity development services (consistent since 2019)
- Output 2. Local Governments systems mainstream GESI in their service delivery (added in 2020)
- Output 3. Government of Nepal benefitting from UK engagement at federal and provincial levels, and from the UK driving forward DP coherence (added in 2022)
- Output 4. Local governments supported to practice deliberative (formal, evidence based and reasoned, inclusive and collective) decision-making processes to become more (added in 2021)
- Output 5. Citizens and non-state actors work together with government institutions to identify and resolve critical development policy problems (added in 2022)
- Output 6. PLGSP adopts a federalized governance structure and decision making to deliver quality capacity services to provinces and local government (added in 2023)

Output 1 and 2 were initially meant to reflect both the UK’s focus areas but also that it was judged that the functioning of PCGGs would be a good proxy indicator for whether or not state restructuring was advancing. It was thought that their role in building the capacity of provincial and local civil servants and elected representatives would be critical to whether they would be able to carry out their new responsibilities, and that PCGGs provided a good measurement of whether the commitment to federalism was maintained. Combined with an influencing objective that was not properly captured in the results framework, namely, to push for the passing of the Federal Civil Service Act, the PCGGs were assumed to be catalytic for federalism. To some extent this assumption held true. This is evidenced by the slow passing of PCGG Acts in Provinces, their politicisation in some, and the enduring debate about the Federal Civil Service Bill, which has only just passed the Committee stage – 8 years into the federal transition[51]. It is thus clear that the future of the civil service has been central to the political struggle for federalism.
[51] The Federal Civil Service Bill was passed by the State Affairs and Good Governance Parliamentary Committee on 16 May 2025.

Output 2 and 4 can be said to measure whether local governments, and citizen’s relationships with the state, is changing. The demand for federalism came out of a dissatisfaction with representation and access to public services for minorities and historically marginalised groups. While GESI remains a priority for the UK, this focus was also intended to help ascertain whether federalism is working for inclusion. Output 5 concerns itself more with how citizens interact with the state to influence policy and development outcomes. The assumption is that if service delivery becomes more accessible and decision-making becomes more inclusive and deliberative, federalism is delivering on inclusion and becoming embedded. As the discussion on outcomes above sets out, this assumption has partly been realised. Historically marginalised groups as well as the younger generation express the most support for federalism, underscoring the fact that its promise to deliver on inclusion is a continued motivational factor.

Output 3 and 5 reflect the importance of influencing work and were added in 2022 and 2024 respectively, to capture the extent to which BEK was leveraging influence through SFN.

Lessons

Aligning a Theory of Change to government systems can provide challenges for its utility. While external exercises may not have been value for money, internal exercise to refresh TOCs can help interrogate assumptions and be a critical tool to help document and advance shared understanding of what a programme is intended to deliver.

Means of verification for outcome indicators should be assessed in all annual reviews, and if necessary, indicators changed. At design stage, SFN relied on PLGSP indicators but a failure to establish reliable mechanisms for continuing to measure them, measurements of those indicators had to rely on proxy measures.

Logframes (or other results frameworks) should be used to maintain strategic intent, while recording incremental progress. In early years, SFN’s logframe outputs documented what could have been better described as milestones towards an strategic intent. This confused inputs with outputs and outputs with milestones and made it harder to judge whether SFN was going in the right direction.

Adaptation to and innovation in a changing context is critical for maintaining relevance and chances of success. SFN proved adept at adapting and adding new programme components as the environment changed but was less able to change the ways in which PLGSP was implemented. SFN also experimented and placed bets more widely at different points of the programme, which was effective at seizing emerging opportunities and building new partnerships.

Setting out more intentional influencing strategies and priorities and more effective ways of measuring their impact would have been beneficial both to maintain BEK’s focus and evidence its impact. In addition, finding better ways to measure the result of influencing efforts is important.

Recommendations

BEK should continue to innovate and experiment with different approaches to driving change. IBA holds promise, but must be underpinned by both sufficient staff resources, commitment to continue to engage, to support local leadership and localisation, and to place bets that may not yield return but generates learning. Action: Governance Team to continue to test the use of IBA in Nepal and work with senior leadership to integrate IBA into ways of working across the portfolio by April 2026.

BEK should use tools of TOC and results frameworks to drive performance and generate shared understanding of strategic intent. Better use of TOC revisions and results frameworks (e.g. logframes or adaptive results frameworks) will help BEK measure its impact. Action: ACE to conduct review of use of results frameworks and make detailed recommendations, by April 2026.

Output level recommendations are listed under each output. See Annex A for an overview of all PCR recommendations.

## C: Detailed Output Assessment

Output Number and Title		1 - PCGGs made operational to deliver capacity development services
Output Score		B
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
# of trained staff in PCGG (disaggregated by GESI and types of thematic areas)	This indicator was added in 2021 once the PCGG were operational. Target initially set for 2023 only, but when PLGSP transitional year was agreed a higher final target was added.		Train 109 PCGG Staff	Partially achieved. Data on specific PCGG staff is not accessible but in 2023, 72 had been trained.
# of PCGG established through provincial legislations	This indicator has remained since start of programme and original target was for it to be achieved in year 2. Annual targets were then revised down to 3 and 4 in 2022 and 2023 respectively.		7	Partially achieved. 5 of 7 PCGGs have Acts while in remaining 2 they operate based on ordinances.
# Number of Training packages developed by the PCGGs	This indicator was added in 2023 and final target remained same.		7	Exceeded. 62[52]
[52] These include: 5 modules on Public Finance Management (PFM), 6 modules on Gender Equality and Social Inclusion (GESI), 3 modules on ICT and e-Governance, 1 module on accountability, 12 in-service training modules, 17 pre-service training modules, 1 module on legal issues, 11 modules on service delivery improvement, 6 modules on federalism and other topics. (Source: PLGSP Annual Report 2023-24)

As set out above, this output is used as a proxy measure for the extent to which state restructuring is advancing and embedding, in particular whether provinces have increased autonomy. Provincial Centres for Good Governance (PCGGs, provincial training institutes) were considered essential for building the capacity of provincial and local government to deliver as per their mandates. While targets have almost all been met, they are only quantitative in nature and doesn’t capture a qualitative assessment of PCGGs. PCGGs have become an embedded feature of the capacity building landscape, they have not been fully consolidated, nor resourced to be the centres of excellence they were envisaged to be. In addition, it is evident from the frequent changing and revising down of milestones that the pace of the changes has been a lot slower than anticipated. This output therefore scores B.

In the final year of SFN, one more PCGG achieved the status of operating on a sustainable and legitimate legislative basis (Lumbini), leaving just two provinces (Madhesh and Bagmati) operating them on the basis of executive orders. This reflects continued political resistance to devolving training institutions and the inability of political parties to forge the necessary consensus in the remaining provinces. The fact that this process was so resisted and PCGGs in a sense became a “political battleground” lends credibility to SFN’s assumption that PCGGs would result in a catalytic change in federalism. The capacity and operating space of PCGGs across provinces varies, with some more active than others, so whether this catalytic impact will be fully realised remains to be seen.

PCGGs are also delivering capacity building. In 2023 alone, 62 training packages were developed. PLGSP has trained 82,540 elected representatives and officials through various mechanisms, 53,785 public officials which represents more than 100% of provincial and local officials, indicating that some have been trained more than once. Of those officials trained only 22% were women, which falls short of their proportion of 28.2% overall.[53] PLGSP has had excellent training coverage but questions have been raised whether training delivery at times overshadowed broader institutional reform objectives[54].
[53] According to latest Public Service Commission figures there are 82,627 approved posts in provincial and local governments but only 43,819 of them are filled. (Women in civil service data source: Bureaucracy, Power, and Civil Service Reform in Nepal (forthcoming), Policy Entrepreneurs Inc, 2025). (Training data source: PLGSP Compiled Report 2019-2024).
[54] EPR, p. 27

Lessons learned through this output, and recommendations for future programming
As a measure of public sector effectiveness, the focus on capacity building of provincial and local government officials and representatives made sense, but it also became clear that the dependencies – the enabling legal framework – had enormous impact on the achievement. BEK was aware of this and invested significant amounts of lobbying on discussing, in particular, the importance of passing the PCGG Acts and the Federal Civil Service Act with government counterparts. However, it was only in the later years of SFN that relationships broadened sufficiently to better understand the blockages and resistance. This was done through adopting a whole-of-society, less state-centric approach, leading to a better understanding of the incentive structures and relationships that drive or stall progress.

Beyond a recognition that the issues were very political and hotly contested, BEK’s understanding of these forces was not deep which negatively affected the political influencing strategy. For example, it was only in the last year of the programme, that BEK commissioned research into the political economy of the civil service, that led to an understanding of the ways in which incentives, interests and relationships affect process outcomes in the civil service. The study identified the importance of actors that BEK had hitherto not engaged with (e.g. the unions) or thought as organized with high mobilizational power (e.g. diverse competing bureaucratic cadre groups). It also informed on the nature of provincial bureaucracy, particularly it identified bureaucratic cadres who were comparatively invested in the provinces and who were not. The study also busted some myths about the nature of resistance to reform within the civil service. For example, it found that senior bureaucrats, who had been the main target of BEK lobbying, feel least threatened by the proposed changes, while the more junior ranks – who hold informal mobilizational power through unions and hidden formal (e.g. legislative drafting) power – are more resistant.[55] Additionally and importantly, the study highlighted time-sensitivity and the importance of staying updated on the political economy in relation to the area where the reform is being pursued. For example, investing in informing and influencing the Employee Adjustment Act 2019 would have positively affected sub-national bureaucratic capacity with high VfM than any other comparable interventions. The EPR also echoed the need for embedding political economy analysis in PLGSP.[56]
[55] Bureaucracy, Power, and Civil Service Reform in Nepal (forthcoming), Policy Entrepreneurs Inc, 2025
[56] EPR, p. 40

Lessons
Pushing policy reforms requires deep technical knowledge and evolving and timely understanding of both the issues at hand and the wider political, institutional and social contexts within which policy decisions and processes are embedded. Lobbying and influencing work that relies on broad messaging have a role to play to create the space for dialogue at the more senior levels, but it is equally important to be able to understand power dynamics, identify the key actors, and spaces of mobilization beyond the ones commonly seen at surface. This requires staying updated on the political economy and a multi-stakeholder approach to promoting change and considerable investment of time and resources, but as will be discussed under output 5 is central to effective influencing of policy reform.

Capacity gaps are often symptoms and results of political choices and so cannot be addressed by investments in capacity building alone. Without navigating the power and interests of key stakeholders, investments in capacity building are unlikely to yield the desired results (e.g. improved capacity, strengthened systems, changed behaviours). It is therefore critical to build coalition of reformers within, be active in the policy influencing space where those political choices are made, e.g. to staff a particular function and with whom (federal or provincial civil servant), and seek to influence the institutional rules of the game, e.g. through influencing policies, laws and regulations that guide and incentivise behaviours.

Recommendations
BEK should continue to invest in understanding how to best support the implementation of federalism and monitor BEK contributions to the consolidation of this new system of governance. Even outside an investment in PLGSP, BEK can structure its portfolio to deliver governance and federalism impact. Maximising and monitoring this can be done through integrated governance ways of working and developing an effective tool to capture governance impact across BEK’s portfolio. Action: Governance Team to design governance audit / scan tool to implement this across BEK’s portfolio by June 2026.

BEK should invest in Thinking and Working Politically (TWP) and find ways to integrate applied Political Economy Analysis (PEA) in all its programmes. With programme successes relying heavily on successfully navigating complex social, political and economic incentives, it is critical for BEK to understand the political economy surrounding the desired change better and to adapt programmes accordingly. It is important to incorporate TWP from the very beginning and combine different tools, including influencing and using policy levers to drive change. This can be done through smarter TA and convening of political and stakeholder groups with an interest in the desired change. Action: BEK co-production process to incorporate TWP and governance tools to set incentives and measure impact by April 2026.

Capacity building interventions should be designed with political constraints in mind and impact should be measured. Programmes that invest in capacity building should first analyse the reasons for the capacity gaps, identify approaches for addressing them where possible, and establish ways of measuring impact of those interventions. This requires smart TA[57] that is incentives not to deliver capacity building interventions, but to work with the politics of the relevant institution. Baselines should be set and post-intervention evaluation methodologies implemented. Action: Governance audit / scan tool to incorporate smart TA and how to recommend measurements of capacity building.
[57] See Understanding and using smart technical assistance, FCDO, April 2025

Output Number and Title		2 - Local Governments systems mainstream GESI in their service delivery
Output Score		B
Impact weighting (%)		15%	Impact weighting revised since last AR?	Yes from 20% to 15%

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
% PGs and LGs have endorsed a GESI strategy with oversight committee and gender responsive budgeting (MoFAGA will provide model GESI strategy for the LGs)	Original target in 2020 was for 6 of 7 PGs and 70% of LGs, in 2021 this was revised to 100% of both PGs and LGs, and in 2022 downwards to 70% of both PGs and LGs. In 2023 current end target was set.		100% of PGs and 70% of LGs	Partially achieved. 100% of PGs and 57.24% of LGs
% LGs have adopted code of conduct to control exploitation and including sexual harassment (% of LGs have adopted code of conduct to control exploitation and including sexual harassment)	Original year 1 milestone was 80% but in 2021 this was revised to 75% in year 3 and 10% in final year. In 2023 this was revised down to 75% in year 3 and 80% in final year.		80%	Not achieved. 17.72%
% of LGs adopted child, senior citizen and differently able person friendly governance policy	This indicator was added in 2021 with a final target of 100% which was revised down to 50% in 2022.		50% LGs	Partially achieved. 22.71%

As discussed above, the introduction of federalism in Nepal arose out of a demand for better representation and a more inclusive state. This output seeks to ensure that GESI is mainstreamed in subnational government processes and functions by ensuring that GESI tools and practices are embedded from the outset. This was important foundational work to set new provincial and local governments on the right path but insufficient to drive behavioural change. Over the lifetime of the programme, the GESI targets have been revised several times, reflecting that progress was slower than anticipated, and concerns have also been raised about both the quality and the level of implementation of the various tools and policies. While the target of one indicator has been almost fully achieved, one other target is almost 50% achieved and another is substantially not achieved. This output therefore scores B.

Based on data from the PLGSP Compiled Report (2019-2024), all provinces have passed their respective GESI strategies and policies. GESI audits were conducted by 77 PG agencies and 482 LGs across Nepal. However, only 431 LGs – representing 57.24% - have formally endorsed their GESI strategies, falling short of the programme’s target of 70%. The adoption of accompanying policies intended to operationalise GESI strategies such as a code of conduct addressing workplace sexual harassment and a child, senior citizen and differently able person friendly governance policy fell well below expected targets.

Although PLGSP has been positively acknowledged for its attempt to mainstream GESI[58], this points to a well-documented challenge with the GESI work in PLGSP, which is that moving from development of strategies, policies and plans to implementation and real change for people has been difficult[59]. There was also some evidence that these strategies were not sufficiently tailored but rather developed with limited consultation and reference to local challenges.[60] The Development Partner Group recognised these challenges and made “transformational GESI” a central priority for the reprogramming of PLGSP.[61] The reprogrammed PLGSP is clear in its intentions to shift the approach, but it remains to be seen whether or not it will be able to stimulate the norms changes necessary to influence behaviours sustainably. An “Assessment for Advancing Gender Equality and Social Inclusion in Provincial and Local Governance Strengthening Programme (PLGSP)” is expected to complete in early 2026, and will be a key touchstone for realising the potential of this reprogramming investment.
[58] It was noted that PLGSP used 7 of 11 common approaches to mainstreaming. (Source: British Embassy Kathmandu Gender Equality and Social Inclusion Research Project: Stage 3 | Deep Dive Case Studies, Adam Smith International, 2024)
[59] See PLGSP Midterm Review, SFN End of Programme Review, and ASI Deep Dive Case Studies.
[60] EPR, p. 5
[61] Through a process led by BEK, the DP Group agreed 9 priorities for reprogramming. One of them was: “PLGSP should consolidate the lessons and gains on GESI mainstreaming and shift the focus to gender transformative programming with an emphasis on behavioural change”. (Source: Provincial and Local Governance Support Program (PLGSP) Reprogramming Core Principles and Priorities, December 2023)

Lessons learned through this output, and recommendations for future programming
Focusing on policy changes such as those driven by PLGSP can be an important, but insufficient, component of driving behavioural change within public institutions. PLGSP’s initial focus on laying the foundations supporting policy, strategy and action plan development and resource allocations are an essential step but to drive behavioural change requires much broader and deeper action. Inevitably, public institutions reflect the norms of wider society but differ in the sense that they have a duty-bearer role of promoting constitutional and human rights. The prevalence of strong patriarchal norms helps to explain why PLGSP fell so much below its GESI targets, and also constrains what can be achieved through a programme like PLGSP. While DPs were very focused on moving from GESI mainstreaming to norms transformation, this was a difficult shift to secure in PLGSP’s first phase. However, this was acknowledged in the design of the proposed successor programme to SFN - Sahakarya, which aimed to specifically work on advancing women in politics – and also in the redesign of PLGSP which seeks to chart a path from GESI mainstreaming to transformation. It is important to invest in understanding what can shift exclusionary behaviours within public institutions and how these interact with wider society so that GESI strategies can move to implementation.

Research has shown the importance of engaging politically with women’s rights organisations and coalitions is critical, and that formal coalitions and frameworks have clear limitations, particularly in deeply patriarchal societies.[62] Likewise, social norms research has demonstrated that norms change can occur when men are encouraged to support norms changes and norm breakers are respected and visible, which means that there could be an important role for public and elected officials to play. Social norms research also shows that working within the nexus of intergenerational norms conflict can help stimulate shifts.[63] Nepal is seeing some of this with prominent politicians and public figures challenging the gender norms they see as limiting their careers[64]. Focusing more on promoting the norms breaking aspects of career paths of women within the political parties and the civil service might have done more to promote GESI than the investment in developing strategies and plans.
[62] “The general finding therefore is that engaging in informal or ‘backstage politics’ is equally - if not more - important than formal channels of engagement in these contexts. Policy change relies heavily on informal relationships rather than formal citizen state engagements, or interactions of civil society organizations and the organizations of the state.” Working Politically Behind Red Lines: Structure and agency in a comparative study of women’s coalitions in Egypt and Jordan by Mariz Tadros, Development Leadership Programme, February 2011, p. iii
[63] See various Gender and Adolescence Gender Evidence (GAGE) products, including “Positioning GAGE evidence on masculinities”, January 2020
[64] For example, in early 2025, Sumana Shrestha, the Joint Secretary General of the Rastriya Swatantra Party resigned citing lack of fairness in progression within her party, and Additional Health Secretary Sangita Kaushal Mishra resigned over not being appointed Secretary.

Recommendations
BEK should invest in how to move from GEDSI mainstreaming to norms transformation across its portfolio. This should include reviewing and deepening implementation of the BEK GEDSI Strategy across the portfolio, to make sure that approaches take into account the evidence on Thinking and Working Politically and social norms change. Action: BEK’s GEDSI Group to review the BEK GEDSI Strategy and portfolio reset to embed TWP and transformative norms principles.

BEK should leverage its expertise and engage with UNDP and UN Women to influence the PLGSP funded “Gender Assessment” and explore how their support, particularly in areas such as institutional capacity, gender responsive budgeting, and social norms change, can complement UK objectives supporting inclusion and governance reform. This will enable UK shape the direction of PLGSP and other reform initiatives. Action: BEK’s Social Development Advisers to continue to engage to both understand institutional constraints and provide thought leadership.

Output Number and Title		3 - Government of Nepal benefitting from UK engagement at federal and provincial levels, and from the UK driving forward Development Partner (DP) coherence
Output Score		A
Impact weighting (%)		20%	Impact weighting revised since last AR?	Yes revised from 25%

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
BEK continues to influence other DPs on strategic policy issues [Federal Civil Service Act and other key federal laws]	No change.		At least 4 (quarterly DP meeting)	Exceeded. BEK chaired 8 DP Group mtgs[65], represented DPs in 7 PLGSP Reprogramming Working Group mtgs; shared 3 studies with DPs[66].
BEK engages with the provinces and federal government on political devolution and legislative frameworks [Provincial Civil Service Commissions and Acts]	This was revised up from 3 when the transitional year was agreed.		At least 6 high level (strategic and policy) engagements/meetings at federal and provincial levels (e.g. passing of civil service and PCGG acts, donor coherence, devolution of programme implementation, and substantive reprogramming of PLGSP and TA)	Exceeded. In final year alone, at least 10 such engagements were held[67].
Evidence of improved coherence between BEK and provincial governments, BEK and implementing partners and BEK and other development partners in the provinces as a result of facilitation of provincial engagement by PEF.	No change.		a. 3 engagements facilitated by PEF among BEK implementing partners; b. 10 engagements between BEK or implementing partners and provincial government and stakeholders; c. 3 engagements between development partners	Achieved. / a. PEF supported 3 IP Roundtables and led a provincial level process. / b. 12 PEF provincial learning sessions with BEK implementing partners and PG, and support to 1 Horizons event in Madhesh. / c. 6 BEK engagements with DPs facilitated by PEF.
SFN MEL supports BEK engagement on federalism [# political economy analysis and evidence pieces on federalism, provincial and local governance; sharing and evidence of uptake by BEK programme and management]	In 2022, this indicator was added but a similar function was reflected under Output 7 indicator 7.2 “# of studies and thought leadership pieces on federalisation, constitution and democratic processes conducted through IDEA/Coherence programme as ‘critical friends’ to BEK and PLGSP”. Cumulative target takes this indicator into account.		Cumulative target: 2+10=12	Achieved. Previous year targets were met. In final year, focus shifted to contributions to BEK’s subnational engagement strategy formulation and implementation. In addition, 12 monthly provincial PEAs were conducted.
[65] 6 as Chair until handed over to SDC from Augst 2024, and 2 as Co-chair.
[66] These were: Local Government Mapping Study by IIDEA, Cost of Politics by Democracy Resource Centre Nepal, Bureaucracy, Power and Civil Service Reform by Policy Entrepreneurs Inc
[67] Messaging through 3 National Steering Committees and at 2 Minister and several Chief Minister meetings; and 2 joint visits to Lumbini and Madhesh with MoFAGA officials.

This output was added in 2022, reflecting the ambition to incentivise donor coordination and measure BEK’s influencing and knowledge production and dissemination efforts. The indicators used to measure progress under this output focus on activities such as meetings and knowledge production, and do not capture the impact of these engagements. For example, indicator 3.1 and 3.2 were both exceeded within the first few months of 2024. That said, the EPR found that “BEK has played a pivotal role in influencing strategic policy discussions and enhancing coordination among development partners (DPs) to support federalism”[68]. While the tools and indicators used to measure influencing lack depth, this output scores A reflecting that the UK is seen as an essential influencer in the federalism space and the approaches adopted by Development Partners[69].
[68] EPR, p. 30
[69] Anecdotal evidence suggests that the UK punched significantly above its weight with, for example, only a GBP 9m investment in PLGSP.

With respect to driving development partner coherence, BEK played a crucial and influential role as the chair of the PLGSP Development Partner (DP) Group from 2019-2023 and co-chair from 2023-2025[70]. The EPR found that BEK had been “instrumental” in driving the process of reprogramming PLGSP[71], which is expected to significantly improve PLGSP’s chances of success (see output 6). The investment in a programme funded adviser proved useful for building the required relationships with federal, provincial and local government counterparts, and engaging in programme monitoring. At times this could be at the cost of a more strategic focus. Therefore, following the 2023 annual review, BEK decided to focus more on strategic engagements with less focus on PLGSP implementation, which in any case was limited during the transitional year. In July 2024, BEK also stepped down as Chair but continued as Co-chair until FCDO’s decision to withdraw from PLGSP in April 2025.
[70] Anecdotal evidence points to some stakeholders believing this influence being disproportional to the level of funding the UK was disbursing, sugging that BEK was able to “punch above its weight”.
[71] “BEK facilitated key engagements with federal and provincial stakeholders, including MoFAGA, OPMCM, MoF, FCGO, NPC, OAG, and NNRFC, and led the prioritisation process among DPs to make sure a more coherent and strategic approach to the PLGSP reprogramming efforts. This process was instrumental in aligning DP interventions with evolving governance needs and proved more complex than merely organising consultation meetings” (Source: EPR, ASI, May 2025, p. 30)

SFN was less successful in influencing the Nepali policy landscape and engage with a wide range of stakeholders to drive policy change and reform. PLGSP was not able to become the anticipated locus of policy discussions about federalism, with intergovernmental output least successful and the governance structure largely inactive, and / or focused on programmatic, not policy issues[72]. In the last two years of SFN that started to change, in part because the political context was conducive. Of the 5 National Steering Committees (NSC), 3 happened in the last two years with consistent attendance from some Chief Ministers[73]. The 5th NSC in February 2025 included a day’s closed discussion on policy issues and involved OPMCM, finally elevating PLGSP to a policy forum.
[72] PLGSP Mid Term Review, May 2022
[73] In October 2023, one Chief Minister (CM) attended for the first time, while in 2024 NSCs 1-3 CMs were generally present. The 5 NSC meetings took place in December 2021, July 2022, October 2023, June 2024, and February 2025.
On the DP side, BEK led important shifts to build more provincial ownership and autonomy and focus more on provincial level policy engagements, successfully getting the DP Group to agree seven priorities for the reprogramming and adopt a Provincial Leads model with each DP responsible for different provinces. Internally, BEK also made efforts to refocus from intensive federal level engagement to the subnational level, and a critical investment made in better understanding and resourcing that engagement through the Provincial Engagement Facility. That said, until 2024 SFN’s focus was very state-centric and therefore opportunities were missed to stimulate change (see output 5). A new governance programme was designed incorporating these lessons, proposing a much more multi-stakeholder approach to change.[74].
[74] This was also in line with analysis invested in by SFN about how to promote change in Nepal.

SFN’s contribution to producing and disseminating knowledge to inform policy and programming has been significant. In particular, International IDEA was an important knowledge partner throughout SFN’s programme period. Improving understanding of how provincial and local governments were supposed to work and how they actually work are among some of the key contributions. A Provincial Givens study looked at the mandates of provincial governments and informed BEK’s intentional shift to more engagement with provincial institutions, as evidenced through a changed role of Provincial Engagement Facility (PEF) from late 2023, assigning senior BEK staff leads for provinces and adoption of a BEK Subnational Engagement Strategy in 2024. Similarly, a Local Government Mapping Study (LGMS) informed BEK and DP thinking on the role of conditional grants in limiting the accountability and ultimately incentives for LGs to deliver. Specifically, it informed BEK discussions with the World Bank who has recommended to shift to the use of sectoral block grants to avoid the excessive earmarking of conditional grants[75] and the narrowing of User Committees mandates under the Local Infrastructure Support Programme to mitigate against corruption. Some of this influence is still unfolding. For example, in early 2024 SFN commissioned a power mapping analysis of the civil service to help understand how significant bureaucratic instability and prolonged delay of the Federal Civil Service Act could be unlocked. While it was only shared with the Federalism Working Group in May 2025, it is clear that there is potential and interest for this to really shift how DPs engage with the policy environment[76].
[75] Nepal Fiscal Federalism Update 2023, May 2023, World Bank
[76] This research showed how the three different streams (civil, health, parliamentary) are both separate but intertwined, and made clear the strong role of politically affiliated unions in driving re-centralisation and resistance to reform. It also pointed to the strong role of bureaucrats in drafting laws – a conflation of executive power that ultimately reduces democratic accountability. (Source: Bureaucracy, Power and Civil Service Reform, Policy Entrepreneurs Inc, forthcoming).

With respect to influencing BEK’s sector programme implementation and ways of working, SFN was crucial to documenting BEK’s evolving understanding of the context. The LGMS for example set out how LGs actually work, and provided a lot of in-depth analysis of the role of financing flows, the limited role of formal decision-making structures, and continued elite capture. Combined with efforts to shift BEK’s approach to system strengthening, SFN was critical to integrating governance approaches to BEK’s sector programmes[77]. In addition, PEF’s work on analysing provincial mandates and legitimacy informed BEK’s wider approach on increasing its engagement with provincial policy landscape, formulated in a new Subnational Engagement Strategy in 2024. Engagement continued to be informed by provincial political economy analysis. BEK received this monthly analysis from PEF but they were more akin to provincial context monitoring, and it is difficult to measure how they informed BEK engagement.
[77] In 2024, a number of internal system strengthening workshops were organised by BEK’s Portfolio Monitoring, Evaluation Learning (PMEL) partner, which combined governance analysis from Nepal with an introduction to broader theoretical concepts around system strengthening.

Lessons learned through this output, and recommendations for future programming

Being a core funder of PLGSP positioned BEK to influence key stakeholders, but did not always provide the fora needed for politically astute influencing. BEK was initially too focused on driving PLGSP as a programme vehicle, not a tool to achieve policy change, and could have struck a better balance earlier between the more transactional work of getting the programme to deliver activities and the more strategic, transformative work of influencing the wider policy landscape. With UK investment in PLGSP now withdrawn, it is even more pertinent for BEK to consider how to position itself as an influencer, thought-leader, and convener on federalism and wider governance issues.

Recommendations

To drive more TWP Ways of Working (WoW) across BEK’s portfolio, BEK should invest in policy influencing on areas that support portfolio impact. Across its portfolio, BEK should map, widen and measure its stakeholder engagement and develop and implement an influencing strategy across its portfolio targeted a wide range of stakeholders at the multilateral, federal, provincial and local levels, using measurable indicators to track progress[78]. This should be informed by ongoing political economy analysis and be driven by understanding of what factors affect the transition from plans and strategies to actual change, and be resourced accordingly, e.g. through the strategic use of both technical and senior staff and PEF at the subnational level. Action: Strategy Team to conduct multilateral and bilateral mapping and PEA Group to lead on subnational mapping, for development of influencing strategies.
[78] FCDO’s Monitoring and Evaluating Influencing Toolkit

BEK should strengthen its reputation as a thought leader by continuing to invest in governance research and dialogue. To maintain influence, it is critical that BEK designs the next generation of research to take into account the new ODA landscape. Research could focus on how to drive a localisation agenda and the role of externals in stimulating change through coalition building and issues-based approaches. BEK should also consider a stronger role as a convener on governance issues. Action: Governance Team to propose areas for future research that are grounded in knowledge gaps and influencing goals.

Output Number and Title		4 - Local governments supported to practice deliberative (formal, evidence based and reasoned, inclusive and collective) decision-making processes to become more transparent, inclusive, responsive and accountable to all citizens
Output Score		A
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
Number of strategic dialogues that improves multistakeholder understanding and engagement on constitutional principles of devolution of function, mandates and resources to local and provincial governments.	No change.		Cumulative target 20 (annual targets in brackets)	Partially Achieved. 18 / Y2 – 1 (1) / Y3 – 7 (10) / Y4 – 5 (4) / Y5 – 5 (5)
Number of local governments supported on planning and law making using deliberative, participative and evidence-based processes.	No change.		Cumulative target 14 (annual targets in brackets)	Achieved. 14 / Y2 – 0 (3) / Y3 – 2 (3) / Y4 – 1 (3) / Y5 – 9 LG planning processes, 2 law-making processes (5)
# of outcome stories (stories of change) on the concept of public deliberation understood and/or used by the ERs developed for liberating and integrating learning in to PCGGs	No change.		Cumulative target 20 (annual targets in brackets)	Exceeded. 21 / Y2 – 2 (2) / Y3 – 11 (10) / Y4 – 8 (3) / Y5 – 8 (3 sectoral learnings)

Originally intended as an accompaniment to PLGSP, the Coherence Programme has been operating since 2018, with its 2nd Phase implemented under SFN. In total, Coherence supported 21 local governments mostly in BE’s three priority provinces, Lumbini, Madhesh, and Karnali, but also one in Gandaki and one in Bagmati. Most were supported for an average of 2 years, but in a few places the support extended to 4-5 years[79]. While performance has fluctuated over the years and some questions about scalability and continued relevance of the approach remain, the cumulative impact of Coherence is substantial, while admittedly difficult to quantify. As Coherence evolved it positioned IIDEA as an essential knowledge partner for both BEK and government counterparts and influenced ways of working and thinking (discussed under output 3). For these reasons, as well as delivering well against logframe targets this output scores A.
[79] Sanibheri, Simta and Bhagwatimai in Karnali were supported for 4-5 years and Surunga and Pipara in Madhesh for 4 years

The core objective of Coherence was to pilot a mentorship approach to building the capacity of local nascent governments (the first ones only being formed in 2017). In later phases, the mentoring approach was also applied to NARMIN (the rural municipality association), and in its final year, also to the provincial level with support to PCGGs in Madhesh and Karnali. Mentoring involved the deployment of young graduates embedded with organisations for extended periods of time, where they focused on supporting processes and facilitating dialogue. This modality took time to gain favour, and sometimes capacity substitution was necessary to build the trust and relationship required with local representatives and officials. However, Coherence mentors maintained their focus, sometimes in the face of intense pressures and political disagreements. The EPR cites Coherence as enabling the Karnali Province Training Academy (PCCG) to effectively train and help LGs develop strategic plans and found that the mentoring approach helped elected representatives and ward officials better understand their governance roles, reinforcing PLGSP’s capacity-building.[80] In addition, the concept of mentoring has become widely accepted as an effective technical assistance tool. This is evidenced by the fact PLGSP now intends to replicate and upscale the mentorship approach.
[80] EPR, p. 21 and 40

In part because Coherence operated in such local contexts and on processes whereby outcomes are not tangible or visible, it has been difficult to measure the impact of mentors on shifting the political culture which is heavily dominated by informality. Embracing this informality but spotting opportunities where this could be made more inclusive has been a central objective of the dialogues to support deliberative and inclusive decision-making. The EPR found that “these dialogues played a crucial role in enhancing stakeholder engagement with governments and amplifying the voices of women and excluded groups in select LGs”.[81] In Coherence LGs, elected representatives increasingly took part in executive committee meetings and steps towards more meaningful participation were observed[82]. Mentors placed significant emphasis on supporting women elected representatives, including Vice Chairs whose formal roles are extensive but are often sidestepped in informal processes. In short, shifting a highly informal political culture infused with deeply entrenched patriarchal norms cannot be done through technical assistance, but there is evidence that agency and voice can to some extent be increased[83].
[81] EPR, p. 29
[82] Draft Support to Emerging Democratic Governance and Strengthening Foundations of Federalism in Nepal SFN (initially PLGSP) Effectiveness (Coherence) Annual Report, IIDEA 2024-2025, August 2025, p. 22
[83] “These dialogues played a crucial role in enhancing stakeholder engagement with governments and amplifying the voices of women and excluded groups in select LGs.“ (Source: EPR, p. 29)

Coherence also provided good examples of the importance of thinking and working politically. For example, the focus on supporting the deliberative processes in local governments, that is the quality of discussions, not just the formal structures meant that Coherence operated within and alongside politics. Local governments are often considered delivery agencies, e.g. of services, as evidenced by the extensive use of conditional grants, but as elected bodies they are essentially political bodies. Coherence was central to shifting BEK thinking about the role and mandates of LGs, and understand the accountability deficits that can be created by taking a projects and results driven approach to change. One example is[84]:
Thinking and Working Politically
“The programme also effectively challenged a growing trend: the technocratization of periodic planning. Financial incentives from donors and government programs had gradually shifted the purpose of periodic plans from being political instruments to being overly technical ones. This created a self-perpetuating cycle where more funds were funnelled into hiring technical experts, which in turn emphasized technical content over local political relevance.”
[84] Coherence Annual Report, IIDEA, June 2025, p. 19

This is an important illustration of how TA can inadvertently become ineffective. If, for example, TA is provided in a way that does not involve the relevant stakeholders in development of plans and strategies, it will negatively impact implementation. PLGSP, for example, did not consistently involve elected representatives in the development of strategies, undermining their roles and leading to poor implementation[85].
[85] EPR, p. 39.

Finally on strengthening the understanding or elected representatives of the value of deliberation and integrating learning into PCGGs, Coherence played “a crucial role as a learning component, reinforcing PLGSP’s capacity-building efforts …. [and] helped ERs and ward officials better understand their governance roles”[86]. Coherence also successfully collaborated with the Karnali PCGG (Karnali Provincial Training Academy) to adopt the mentorship approach which they plan to use as a key capacity-building tool in their work to support LGs. Karnali PCGG extended the mentoring approach to three more LGs for periodic plan development. However, this was less effective, mainly because the support was not demand-driven and lacked a proper needs assessment. In addition, the ”Coherence mentorship approach has now been adopted by the GoN and is expected to be rolled out under reprogrammed PLGSP to about half of Nepal’s LGs”[87].
[86] EPR, p. 21
[87] EPR, p. 21

Lessons learned through this output, and recommendations for future programming
A key challenge for Coherence was to navigate the interplay between the formal and the informal. Coherence mentors were initially focused on improving representation and participation in formally mandated committees and structures. However, it became apparent that even though these were held, decisions were made elsewhere outside informal structures. It became apparent that to increase voice and agency of women and those excluded it was important to also support them to operate in informal spaces. It should not be assumed that informality is necessarily exclusionary, but access to informal settings can be difficult for some social groups, e.g. women or lower caste. Therefore, system strengthening should focus on helping to make formal processes function while at the same time, capacitating stakeholders to effectively participate in informal decision-making. As have also been seen in PLGSP, focusing purely on formal processes creates incentives for “tick boxing” – adopting but not implementing plans, minuting decisions that were made elsewhere, and measuring inclusion by counting numbers present even if they did not influence or speak. When strengthening systems it is critical to consider the role of the formal as well as the informal practices.

Recommendations

BEK should improve its understanding of the interaction between informality and exclusion, and norm good practices in local governments. This means greater investment in how things actually function, rather than how they should function, and working iteratively with those structures to shift incentives to act and make decisions within formal functions. For example, to slowly help confer power onto formal roles and structures, BEK should norm engaging with the people whose mandate our discussions (e.g. Deputy Mayors on budgetary, planning and monitoring issues because they are supposed to chair those committees). Action: Governance audit / scan tool to propose improved BEK WoW with local governments.

BEK should continue to invest in mentoring, but it is important that it is based on a realistic assessment of needs and ownership as well as understanding of the local politics. Moving towards more transformational TA approaches, BEK should ensure that its TA to local governments is tailored to local needs and understand that these are not constant but evolve and interact with the daily context. Effective TA cannot be designed in advance but should evolve over time based on application of soft, over technical, skills and iterative political economy analysis in action. It is also important to prioritise engagement with local institutions (CSOs, universities, media and informal community groups) to embed TA approach within the community, enabling locally driven solutions and reducing reliance on external support once BEK’s involvement concludes. Action: Governance audit / scan tool to recommend effective TA approaches.

Output Number and Title		5 - Citizens and non-state actors work together with government institutions to identify and resolve critical development policy problems
Output Score		A+
Impact weighting (%)		15%	Impact weighting revised since last AR?	No change

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
# of collaborative processes (e.g. government planning, co-creation of projects) facilitated and # of partnerships created (between and among government and civil societies) to demonstrate the value of collaborative governance for wider stakeholder buy-in of governance processes and outcomes.	No change.		At least 4 collaborative processes. / At least 9 partnerships in 3 priority provinces.	Exceeded. / 6 issues engaged via collaborative processes[88] and 11 partnerships fostered[89]
# thematic and process related learning products lead to consultation and uptake of collaborative approach in development programming of BEK and development partners.	No change.		At least 4 learning focused quarterly reports that meets BEK lead advisor, PRO and SRO expectation with evidence of adaptive management. / 3 learning reports and discussion on (devolution, inclusion and viability of IBA and process). At least 1 evidence of uptake by other BEK programme.	Achieved (on track to be). All 4 quarterly reports focused on iterative learning; and 2 learning reports disseminated while the cumulative learning report remains in draft. It is too early to fully gauge evidence uptake in BEK programmes but wider FCDO interest in the Nepal experience is promising.
[88] These included: 1. Socio-economic impact of Migration (Madhesh); 2. Muslim socio-economic issues (Madhesh); 3. Dalit empowerment (Madhesh); 4. Effective functioning of Provincial Assembly Committees (Lumbini); 5. Empowerment of Deputy Mayors in LGs (Lumbini); 6. Promotion of Economic Growth (Karnali)
[89] These included: 1. Gandaki-Lumbini provinces signing of MoU; 2. 14 Deputy mayors/chairs network in Lumbini; 3. Provincial committee and Dayitwa collaboration on embedded fellows; 4. Madhesh based CSOs partnership for Muslim dialogues; 5. CSOs and Madhesh for post-legislative scrutiny of the Dalit Act; 6. CSOs + Provincial Education Ministries + Planning Commission for Education Policy (Madhesh); 7. Linking Lumbini province's government information officers and media personnel + CSOs; 8. Global Center for Climate and Security Governance (GCSG) partnership with provincial government on climate governance and financing; 9. KU-NCC, academia, LGs, and PG collaborated dialogues on intergovernmental coordination, coordination, resource distribution related themes; 10. Federalism and Localisation + provincial governments partnered dialogues in the provinces; 11. Lumbini Provincial Assembly and Lumbini students as part of Assembly-excursion study trip.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
SFN’s final year was the Sahakarya Pilot’s only year of operation. This limited the time it had to generate impact, and the chosen indicators reflected this level of ambition. With such short time, it had not been expected that the Pilot would deliver real change, but it did (see below). Given that its operating modality (Issues-Based Approach, IBA) had not been widely used in Nepal before, and that internally as well as externally this was a learning journey, the Pilot delivered some impressive results and produced a vast amount of learning about the potential of this kind of approach in Nepal. It also proved that IBA is a relevant modality in Nepal, it delivered real progress on resolving knotty issues, and it generated learning that is relevant for both BEK and beyond. The EPR found that it is critical to continue to invest in innovative approaches to support the consolidation of federalism in Nepal[90]. For these reasons this output scores A+.
[90] EPR, p. 42
The aim of the Sahakarya Pilot was to foster collaborative partnerships amongst a diverse range of stakeholders to drive a particular change. Given the limited time frame, the scope was not left completely open but focused in on promoting “inclusion” and “provincial legitimacy”. To this end, the Pilot invested in small but multiple collaborative bets and partnerships and exceeded its targets of collaborative processes and partnerships. The IBA issues and interventions detailed below were also selected and refined in each province following collaborative and iterative process based on local demand and analysis of the viability of addressing the issue (e.g. through political economy analysis). Additionally, in designing these interventions, some combination of citizen-groups, CSOs, and state institutions were mobilized.
These partnerships delivered real impact, including resolving Lumbini province’s audit arrears from the last six years, convening forums to draft and finalize key provincial plans, bills and policies such as Education Policy in Madhesh, Integrated Industry Management Bill, Lumbini Province Research and Training Institute Bill. In addition, the Pilot delivered on horizonal intergovernmental relations by supporting the process that led to the signing of a 21-point MoU between Lumbini and Gandaki provinces for interprovincial coordination on economic development.
In terms of generating learning, the Pilot only partially achieved its targets within the programme period but is on track to do so. This in part reflected a decision by BEK to allow the Pilot to operate until the very end of the programme timeline (end March) to allow as much time as possible for changes to take hold and learning to be generated. Given the short duration, the influence of the Sahakarya Pilot and the IBA method it championed is still too early to assess. However, early indications show some promise. Learning from the Pilot’s focus on local-level committees has helped influence LISP to consider investing in monitoring committees of LGs, which are chaired by the (usually female) Deputy Mayor. In addition, the IBA method championed by the Pilot has found a solid footing, influencing thinking within BEK and the wider FCDO network.
Lessons learned through this output, and recommendations for future programming

A key learning from the Pilot is that local context and the very different political context in each province matters[91]. While this is common knowledge, not all programmes have the flexibility and management arrangements to respond well to it. The Pilot’s theme selection in each province was shaped through a collaborative process involving contextual gap identification, scoping research, stakeholder consultations, and local political economy analysis. This ensured that the issues prioritized were not only contextually relevant but also reflected the interests and incentives of local actors.
[91] Provincial Political Economy Analysis commissioned under the RENT Political Settlement Research programme sets out the very different contexts of BEK’s three priority provinces (Source: Policy Entrepreneurs Inc, 2025)

In Madhesh Province, the focus gravitated toward inclusion, with interventions involving marginalized communities at the centre. Key initiatives included the Muslim Dialogue Series across four geographic clusters, the development of the provincial education policy, Post-Legislative Scrutiny (PLS) of the Dalit Empowerment Act, and the design of an immersion course on inclusive policymaking. The partnership model here was distinctively citizen- and non-state actor–led, with CSOs such as Dalit Sarokar Manch, North South Collectives, Hamro Abhiyan, and Rural Development Center playing a central role. These actors led issue identification and community engagement, while the state was selectively engaged when opportunities for policy influence emerged—such as in the drafting of the education policy or the PLS of the Dalit Empowerment Act.

In contrast, Lumbini and Karnali Provinces prioritized interventions that were more state-centric. In Lumbini, the dual focus on governance and inclusion-related themes translated into interventions aimed at strengthening provincial assembly committees, enhancing female leadership at both provincial and local levels, and improving inter-governmental coordination. In Karnali, the emphasis was on economic growth, with initiatives such as the Economic Growth Dialogue Series and support for the periodic planning process. This state-centric engagement was complemented by efforts to link these institutions with citizens and non-state actors—for example, through embedded policy fellows supporting parliamentary communities, student engagement with the Provincial Assembly, linking deputy mayor networks with local non-profit, and media-CSO collaborations.

This differentiated partnership approach—non-state actor–focused in Madhesh and state institution–led in Lumbini and Karnali—allowed Sahakarya Pilot to tailor its strategies to the political and institutional realities of each province. It also enabled a balance between long-term structural change and short-term policy wins. While Madhesh’s approach laid the groundwork for deeper inclusion and civic engagement, Lumbini and Karnali’s state-focused strategies allowed for quicker technical adaptations and policy progress. Future engagement in these provinces will gain from balancing engagement with citizen networks, CSOs, and state actors, thereby filling the existing gap.

- IBA is low-cost and VfM. The Pilot was small and agile, with its biggest investment in people and relationships. Low-cost methods like “tea” and “shuttle” diplomacy delivered high returns.
- Unlearning development orthodoxy is hard. Shifting away from donor-driven, patron-client dynamics takes time and effort.
- Need some direction. Total openness—“work on anything”—isn’t always practical. The Sahakarya Pilot focused on inclusion and legitimacy, with flexibility on how to get there.
- Working with antagonists takes courage. Building trust in a context of distrust requires patience, soft skills, and long-term commitment.
- Our incentives matter. Issues-Based Approaches (IBA) don’t align well with rigid KPIs or results-based payments. It needs flexible frameworks that allow adaptation and real-time decision-making.
- We have to take less credit. Supporting local leadership and letting local actors lead means stepping back. Sometimes, the UK’s role is best played quietly to allow sensitive political processes to unfold.

Recommendations
BEK should continue to invest in this whole-of-society approach and work with stakeholders to drive forward change that already has a level of social and political mobilisation. To achieve policy change, we need to go beyond government, especially important at the subnational level where BEK programmes focus on service delivery. This is not only good value for money, it is also aligned with a new focus on the importance of localisation and problem-solving partnerships. Action: Governance Team to initiate IBA projects to continue to develop this methodology, including a learning journey for BEK on how to use IBA to drive outcomes.

BEK should deepen its engagement with provincial and local level assembly committees, particularly those with a relevance for BEK portfolio outcomes. Assembly committees play critical roles in policy formulation and accountability, and are generally more stable than government ministries, but remain in their formative stages, so offer a higher return on investment. This is especially important given the persistent challenges of executive-dominated decision-making and the lack of robust accountability mechanisms at the sub-national level. Working with provincial committees facilitates engagement across diverse sectoral issues, and engaging deputy chairs/mayors who head committees at the local level contributes to the twin goals of promoting inclusion and accountability. Action: The PEA Group to take this forward in subnational stakeholder mapping.

Before agreeing to any technical support to a provincial government institution, it is essential to assess the political economy drivers and inclusion challenges. Questions to ask are i) whose interest the given support would serve, and how they are positioned in the wider provincial landscape; ii) whether there is sufficient time to meaningfully engage citizens and non-state actors, address structural issues, prepare the product collaboratively, and iii) whether the support offers a potential for sustainable change. Action: The PEA Group to take this forward in subnational stakeholder mapping and WoW.

Output Number and Title	6 - PLGSP adopts a federalized governance structure and decision making to deliver quality capacity services to provinces and local government
Output Score	A
Impact weighting (%)	10%		Impact weighting revised since last AR?	New output.

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Level of political endorsement of a new PLGSP approach		No change.	# Redesigned PLGSP Programme Document endorsed by NEC and Approved by NSC	Achieved. Endorsed by NSC on 29 June 2024, by Cabinet in October 2024, and reaffirmed by NSC in 3 February 2025.
Evidence of PLGSP new governance structure being federalised and more inclusive		No change.	1 National Steering Committee meeting, 1 Federalism Coordination Committee, 1 Technical Assistance Committee, 7 Provincial Steering Committees, 7 Provincial Technical Assistance Committees	Partially achieved. Some of PLSGPs national level coordination structures (NSC, TACS) are functional but the FCC and provincial level structures are not yet active.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
This output was added following the 2023 Annual Review to reflect the significant investment needed in the reprogramming process for PLGSP. While there have been some delays in operationalising the new design of PLGSP, the reprogrammed Programme Document sets out the parameters for a PLGSP that empowers PLGs to, deliver real change, and provides more opportunities for policy engagement. BEK was essential to delivering this reprogramming, leading the PLGSP DP Group to agree 7 priorities for the process, which were all largely delivered. On balance, although one indicator achievement has been delayed, this output therefore scores A.

BEK’s leadership of the prioritisation and negotiation process was “instrumental in aligning DP interventions with evolving governance needs”. 7 priorities were agreed for the reprogramming process[92] and shared with PLGSP stakeholders[93]. These were largely met with the biggest shifts summarised in the table below:
[92] Provincial and Local Governance Support Program (PLGSP) Reprogramming Core Principles and Priorities December 12, 2023
[93] This included an official letter to MoFAGA as well as several presentations.
1. PLGSP should federalize its governance structure, maintaining mechanisms for national strategic oversight but devolve decision-making and accountability to provinces.
2. PLGSP must have a more streamlined and inclusive national governance mechanism that represents all relevant stakeholders, including Local Governments.
3. PLGSP’s scope of engagement, resources and capacity development initiatives should be tailored to the operating environment for reforms and prioritize work to progress key enabling legislation.
4. PLGSP should strongly focus on strengthening Intergovernmental Relations (IGR) across the three spheres of government.
5. PLGSP’s TA should be owned by government units benefiting from it and be transformational and highly skilled, supporting both capacity development as well as strategic reform dialogues.
6. PLGSP should do more to make its GESI efforts transformational.
7. The Innovative Partnership Fund Guidelines should be revised, and diligently implemented with projects selected for their innovation and contribution to intergovernmental collaboration.

Table 2. PLGSP Reprogramming Key Changes[94]
[94] Adapted from FCDO Business Case for a new integrated governance programme, Sahakarya [Collaboration], October 2024

PLGSP Key Lessons / MoFAGA not able to impact wider political environment to make it more conducive to intended outcomes of PLGSP / Decision-making centralised at federal level, stifled autonomy and timely implementation, and technical assistance accountability was only to MoFAGA / New provincial bodies unable to become institutionalised due to delays in adopting appropriate legislative framework / Too much focus on “producing” tools and products (strategies, plans, policies) for local / Capacity building (CB) of individuals did not yield sufficient organisational change / GESI approach did not sufficiently support behavioural change[95] / Government units reliant on technical assistance (TA) to perform basic functions (capacity-substitution)	PLGSP II Reprogramming Response / Stakeholders widened and OPMCM brought onboard as lead and cost centre for intergovernmental relations outcome / Governance structure, including TA accountability, federalised with a lead role for PGs to develop, implement, and be accountable for provincial plans and results / Renewed emphasis on working across political spectrum, including with federal and provincial assemblies, and with PGs to progress / More emphasis on quality, adaptation to context, and actual implementation, including monitoring / More focus on CB modalities (e.g. learning approaches) and institutional partnerships for learning / GESI now embedded across PLGSP II and intersectionalities analysed but more transformative approaches will be needed / Implementation support will be downsized with about 50% from the outset and be gradually phased out
[95] PLGSP performed comparatively well on GESI mainstreaming, with a clear emphasis on GESI strategies, earmarked budgets for GESI, and inclusive analysis and consultations to inform policy. However, like most other BEK programmes, PLGSP prioritised government actions and not a wider societal engagement that is needed to transform attitudes and behaviours. (Source: Gender Equality and Inclusion Mainstreaming Research, Adam Smith International, April 2024)

While formally adopted by the NSC in June 2024, there were delays to operationalising this approach, in part because of different approaches to whether or not formal Cabinet approval was also required. In tandem, all DPs were bilaterally negotiating extensions to existing agreements or in case of BEK and UNDP, new programming frameworks based on the new PLGSP Programme Document. During this time, DPs intensified provincial engagement setting out to counterparts that the reprogrammed PLGSP presented real opportunities for PLGs to lead strategy and implementation. The first reconstituted National Steering Committee met in February 2025 but provincial governance structures are yet to be fully activated. There is anecdotal evidence that the new design is shifting incentives, with Chief Ministers more engaged in discussions and provincial officials more seized of the opportunity they have to drive their priorities and plans[96].
[96] Evidenced by active participation of Chief Ministers in February and May 2025 NSCs, and interactions with provincial officials in Gandaki in a joint MoFAGA / DP visit in late March 2025.

Lessons learned through this output, and recommendations for future programming
Driving DP coherence is time consuming, even when like-minded DPs broadly agree, and there could be better ways of having policy impact than through a programme governance structure. As discussed under output 3, the PLGSP governance structure did not really function as a policy forum, with more informal structures like ad hoc meetings Chief Ministers organised by CMs themselves taking precedence. SFN’s later investments in informal policy dialogue (discussed under output 4 and 5) appear more promising, with an emphasis on identifying and supporting those with convening power and enough political neutrality or balance to attract the relevant policy makers. While funding PLGSP positioned BEK to influence its strategic direction, there are potentially more effective ways of having policy impact. To ensure the sustainability of the investment in reprogramming PLGSP, it is important that BEK remains engaged with the process of federalism and using all levers to influence outcomes.

BEK should strengthen its Whole of Society Approach and continue to invest in informal policy dialogue alongside bilateral relationships with a wider range of stakeholders. This can be done by identifying which policy issues have social and political mobilisation and identifying who has the convening power to attract policy makers. Continuation of the issues-based approach, PEF and sector programmes all have a role to play. Action: The portfolio reset to incorporate the principle of integrating a Whole of Society Approach.

BEK should influence PLGSP through subnational engagement and actively engage in provincial coordination and learning structures for technical assistance. The reprogrammed PLGSP provides for a role for UNDP to convene stakeholders to share, coordinate and learn about effective TA approaches. BEK can leverage impact beyond its bilateral investments by seeking to influence the TA approaches of others, and maintain its own relationships, e.g. with PCGGs and Office of the Chief Minister and Council of Ministers. Action: BEK’s subnational engagement work to continue to prioritise lesson learning and sharing with relevant stakeholders, e.g. through the Federalism Working Group and relevant provincial fora.

D: Value for Money

 VfM performance compared to the original VfM proposition in the business case

The original value for money proposition was about the consolidation of certain reforms, but overtime it became evident that these reforms would be so influenced by the political economy surrounding them, that there was a need to shift SFN’s emphasis and the understanding of VFM. Over time, SFN therefore developed a more sophisticated approach to VFM, though this was not consistently measured.

SFN’s original VFM proposition was based on PLGSP, which in the end accounted for 57% of SFN spend. Originally, a key premise of investing in PLGSP was that the scale of the interventions would realise VFM benefits in that it would result in strengthened systems . To a large extent this held true. PLGSP reached almost every federal, provincial and local government stakeholder and laid the foundations for evolving practices based on model laws, regulations, support to policy development (e.g. GESI), and systems that keep government running (IT, accounting etc)[97].
[97] At the LG level, “the institutionalisation of national tools such as LISA, FRA, MTEF, SuTRA, PAMS, and PIMS, which are now relatively fully functional and integrated into the local governance system is a success due to the comprehensive training provided to LG officials and ICT officials/departments”. (Source: EPR, p. 36)

The original PLGSP business case sets out 4 stages of value for money (VFM) progression, and set the target to achieve VFM between stage A and B[98].
[98] Nepal Provincial and Local Government Support Programme (PLGSP) Business Case, 2018, p. 37

Figure 2. SFN BC Value for Money Proposition

The is assessed as having performed satisfactorily against the original expectation. In 2023, it was assessed that the programme had reached Stage A and was proceeding towards Stage B but also highlighted that a VFM framework with clear metrics to track progress was never developed[99]. In an attempt to close this gap, a VFM assessment was commission in 2024 which found that SFN was moving through the stages described[100]. The EPR found that SFN still had work to do to reach stage B suggesting that SFN has fallen a bit short of its original target.[101] That said, there is some evidence to support a more positive assessment. For example, in Gandaki local governments exceeded the co-financing requirement of 35% for Innovative Partnership Fund projects with 10% points[102]. In Karnali, the Provincial Government has invested over Rupees 150,000,000 (GBP 820k) in the PCGG and in Lumbini, the Provincial Government’s share of funding for the PCGG has grown steadily, suggesting increased ownership and sustainability of these new institutions[103].
[99] This was highlighted by the 2023 Annual Review.
[100] SFN Value for Money Assessment, FCDO Economist, 2024
[101] EPR, p. 38
[102] EPR, p. 36
[103] Figures provided by PEF Lumbini.

Table 3. Lumbini Provincial Government Spending on PCGG

Nepali Fiscal year	Provincial Government in Rupees	PLGSP in Rupees	Provincial Government % share
Ju21-Jul22	78,000,000	193,350,000	29
Ju22-Jul23	73,396,000	82,097,000	47
Ju23-Jul24	84,500,000	51,665,000	62

As the programme evolved, it was clear that PLGSP would benefit from supplementary investments, that could help sustain changes but also introduce more attention to the behavioural and cultural changes necessary for real impact. Despite the original VFM proposition being only concerned with PLGSP, the VFM analysis below concerns itself with all components of SFN.

While the EPR judged SFN to have demonstrated “partial effectiveness”, this varied across SFN with PLGSP proving less effective than Coherence and the Sahakarya Pilot. This shows that SFN’s adaptation and shifts enabled it to make increasingly meaningful contributions to intended outcomes. A value for money proposition emerged that to increase VFM, SFN needed to employ a wide range of tools and programming strategies. The programme successfully adapted to the evolving context, with adequate tools in place to make informed decisions. It is therefore judged that SFN has delivered an improvement in value for money steadily throughout the programme period.

An important part of promoting value for money in SFN has been to adopt and champion Thinking and Working Politically. Again, as mentioned above Coherence and Sahakarya Pilot components were particularly successful at this.

Economy (Key cost drivers)
The main cost driver across all components SFN has been staff salaries and consultancy fees. That said, costs and models varied, and some provided better economy than others. All PLGSP’s federal and provincial cost units (PCU, PCGG, PPIUs and FCGO) followed standard government rates for subsistence allowance, travel and other services, but UNDP TA staffs’ salaries and consultancy costs were significantly higher than the government counterparts. In contrast, Coherence’s mentorship model is widely acknowledged be both innovative and cost-effective, in terms of utilising local graduates (reduced logistical costs) for monthly mentor remuneration as highlighted in the EPR. With respect to the use of consultants, some components were more reliant on international consultancy inputs than others (e.g. Coherence), while some offered greater localisation value (PLGSP and the Pilot). Each had benefits and drawbacks, with risks to manage around cost-effectiveness. Similarly, the key cost drivers of the Sahakarya Pilot were pool of experts/consultants spread across IIDEA, The Asia Foundation (TAF) and the Westminster Foundation for Democracy (WFD). SFN also provided funding to a range of civil society and research organisations which were engaged based on their area of expertise and influencing capacity. Other cost drivers were research studies, dialogues with stakeholders, facilitation sessions of learnings at provinces, including orientations to civil society organisations and mentoring support to marginalised women leaders.

Efficiency (Input vs. Output)
The EPR rated SFN “partially efficient” reflecting complexity of both programme intentions and delivery structures. Three key efficiency markers are considered below: 1) extent to which programme delivery structures were efficient, 2) level of coherence, and 3) stability in relationships.

Efficiency of programme implementation structures. Initially, PLGSP’s delivery structures were very complex and top-heavy. They involved the collation of plans from seven provinces and consolidation of those into one single Annual Strategic Implementation Plan, which then had to be approved by the National Steering Committee. This was not efficient and proved a key determinant of poor budget execution and implementation rates (see Programme Management Section). While this improved over the years, PLGSP Phase Two introduced provincial planning and decision-making structures, and more rationalised programme delivery units.

The reimbursement expenditure modality for all PLGSP’s financial aid (FA) disbursements to MoFAGA, recognised as an 'on-budget-on-treasury' approach, has been a notable VFM enabling strategy. Throughout the programme duration FCDO has ensured assurances for all FA payments, based on the Financial Monitoring Reports (FMRs) submitted by the Provincial Coordination Unit (PCU) established in the MoFAGA. Royal Norwegian Embassy (RNE) team has quality assured all FMRs under PLGSP phase one, to ensure financial oversight, minimising misuse of funds.

Coherence. The EPR rated SFN “high” on coherence. This reflects that SFN demonstrated high levels of internal coherence with complementarity both actively sought and achieved across components. It also highlighted high levels of coherence with BEK programmes working on service delivery (Samartha, LISP), building institutional capacity (NURP, PFM-MTDF), and generating research and evidence (E4D). In addition, SFN demonstrated “high coherence” with other DP programmes. The “high relevance” of SFN combined with these levels of complementarity has contributed to SFN’s efficiency. [104]
[104] EPR, p. 2

The horizontal and integrated coordination between JFA DPs has been highly functional throughout the programme. Joint positions and messages were the norm, and helped more efficiently engage with federal government stakeholders. Recently, BEK has initiated that this practice is replicated at the subnational level with the newDP Provincial Lead approach. This will ensure better contextual understanding and more consistent and unified representation, intended to reduce and elevate dialogue to a more strategic level based on streamlined partnership between the Provincial Government and the Lead DP in a given province.

Stability in relationships. A key efficiency challenge for SFN has been the constant change-over of staff in government institutions. This has affected all elements of SFN that has worked with government, affecting continuity of relationships and dialogue. Coherence had to invest significant amounts of time in building learning relationships[105], PEF “struggled to maintain continuity and build sustained relationships due to frequent changes in provincial governments”[106], and BEK itself invested significant amounts of time in engaging with frequently changing government officials for steering programme implementation and obtaining necessary approvals.
[105] Draft Support to Emerging Democratic Governance and Strengthening Foundations of Federalism in Nepal SFN (initially PLGSP) Effectiveness (Coherence) Annual Report, IIDEA 2024-2025, August 2025
[106] EPR, p. 1

Effectiveness (Output Vs. Outcomes)
As mentioned in the TOC analysis, SFN has made progress towards all 3 outcomes, which have all been partly achieved. Driving these results has been a combination of good linkages between some outputs and outcomes, adaptation over the course of the programme to complement existing investments, and environmental factors beyond the programme’s control.

Coherence in particular proved instrumental to supporting investment. Delivery modalities like mentorship, working directly with provincial institutions like the PCGGs, where PEF have helped translate outputs to outcomes. Coherence also made a contribution on Inter-Governmental Relations, supporting NARMIN (the rural municipality association) to develop a strategic vision to shift from donor dependency to institutional advocacy. It also supported more participatory practices and clearer understanding of its representative role within NARMIN, which has made it a more effective and visible member in PLGSP programme governance structures. Likewise, Coherence elevated the efficiency and autonomy of Karnali Provincial Training Academy (KPTA).

PEF and the Sahakarya Pilot also underpinned these changes by focusing explicitly on the subnational level. PEF has delivered as a cross-office resource by integrating functions to streamline partnerships, subnational support, and greater coherence between BEK’s evidence and knowledge work and strategic engagements. The Sahakarya Pilot likewise worked on issues that already had traction and some level of social and political mobilisation to maximise return on investment. This proved highly effective in unlocking processes other wise stuck (e.g. cleared 6 years of audit arrears in Lumbini).

Equity (Fair distribution of benefits)
SFN had as an explicit intention to work on inclusion and prioritise GESI. Equity can be measured by considering 1) targeting ratio, 2) actual distribution of benefits, and 3) efforts to ensure equitable distribution of benefits, e.g. GESI mainstreaming.

Targeting ratio. While there has been a specific commitment to target women, efforts to target marginalised groups have been less successful. By far the largest investment under SFN has been in training of civil servants and elected representatives. PLGSP has trained 82,540 elected representatives and officials, including 21,552 women. Of those officials trained only 22% were women, which falls short of their proportion of 28.2% overall.[107] PLGSP’s ratio of GESI expenditure has been rising – in 2022-23 it was 27.72% of PLGSP total expenditure[108] and in 2023-24 it was 41.03%[109]. Both Coherence and Sahakarya Pilot made significant efforts to target marginalised groups. The drafting and passing of Dalit Acts in two provinces have been supported, and Coherence mentors specifically focused on women from marginalised groups. IIDEA is also the only implementing partner to focus intentionally on recruiting diverse staff:
[107] According to latest Public Service Commission figures there are 82,627 approved posts in provincial and local governments but only 43,819 of them are filled. (Women in civil service data source: Bureaucracy, Power, and Civil Service Reform in Nepal (forthcoming), Policy Entrepreneurs Inc, 2025). (Training data source: PLGSP Compiled Report 2019-2024).
[108] SFN Annual Review 2023
[109] PLGSP Annual Report 2023-24, October 2024

Table 2. Overview of Ethnicity of Coherence staff
Count of Caste/Ethnicity
In this way SFN demonstrating some good practices that can be replicated in other BEK programmes by attempting diversity within implementation structures. Of 41 mentors and staff operating in Coherence’s final year, 22 were male and 19 female. There is some evidence that this has contributed to greater impact with the deployment of female mentors boosting confidence of female elected representatives in raising concerns and being vocal by gaining required skills, knowledge and capacity[110]. Additionally, given inclusion was a core principle of Sahakarya Pilot, the same was seen in the implementation structures. This was evident with diverse range of local networks and CSOs partnered, severely minimizing Kathmandu-centric expert models, and inclusive dialogue design.
[110] Coherence Booklet, May 2025

Distribution of benefits. There is no accessible data on the ethnic and caste composition of the civil service, or service seekers and their level of access to services. It is therefore difficult to assess whether the distribution of benefits have been equitable. As mentioned in the TOC section, there is a perception that services are better, and that local governments are making a difference to people’s lives. While there is good data on the increased representation of women in politics, it is more difficult to measure whether this has led to more inclusive decision-making, or indeed improved outcomes for women.

GESI mainstreaming. SFN has made considerable efforts to mainstream GESI in all its approaches. This is discussed under each output. Of particular mention is the Sahakarya Pilot’s specific focus on inclusion, which included support to Dalit Acts in two provinces, and support to women political leaders including Deputy Mayors (in Lumbini) and women Provincial Assembly members (Social Development Committee in Karnali) in improve understanding of their capacities and increase their influence. It also included dialogue with Muslim and Matahar Dalit communities in Madhesh about their socio-economic challenges – engagement with these two communities which are among the most marginalised in all of Nepal, had to be iterative and on their terms to build the necessary trust (the discussions were held in the community itself).

Lessons
It has been acknowledged that the complexity of the programme attributing to diverse stakeholders, intangible outcomes and adaptive implementation have affected development of a VFM framework. While the importance of a VFM framework with outcome-level metrics at the outset is clear, an approach should be in place to track progresses overtime to impart the programme’s real effectiveness and resilience. It would enable to demonstrate how the programme adapted, evolved and matured through complexities, challenges and opportunities.

It is imperative to develop a VFM framework at the outset of a programme. This should include metrics that can be tracked and measured over time, as well as opportunities for adapting it as and when the programme adapts.

Recommendations
BEK should invest in analysis that can improve measurements of levels of equity across its programmes and in Nepal. At a minimum, BEK should set up a consistent monitoring system of staffing composition in its implementing partners and downstream partners. The long-term goal should be to work with relevant state institutions to set up systems to measure this, but given the controversy surrounding the census work, this is not likely to be possible in the short-term. One entry point may be to work with Provincial Governments to better understand different groups’ level of representation in state structures and access to services. This can also help develop a measure of whether federalism is working for inclusion in Nepal – the development of new Provincial Civil Services, for example, provides an opportune moment. Action: GEDSI Group to revisit the GEDSI Strategy and Action plan to include this.

All programmes should have a VFM framework with clear metrics that measure progress over time. The original business case set out a clear value for money proposition, which was helpful in assessing this over time but VFM metrics were never agreed or mechanisms set up for tracking them. While this was sought rectified in 2024, it was judged too late in the programme and decided to draw on different sources as available for the end of programme assessment. Action: BEK’s Portfolio VFM Group to ensure that all BEK programmes have clear VFM propositions and metrics to track over the lifetime of the programme by April 2026.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating of the programme remained at Major throughout the programme period, predominantly driven by the political instability and fluctuating political commitment to federalism. Frequent government staffs’ turnover, ineffective intergovernmental relationships, especially between federal and provincial governments but also including coordination between federal ministries on federal reform policy, and limited fiscal federalism continue to negatively affect the strategic objectives of the programme, across all components.

With respect to risk management, the programme employed a wide range of risk mitigation tools discussed under each of the risk categories below. Risks were regularly reviewed and the programme remained compliant with due diligence assessments of Coherence and Sahakarya Pilot throughout the programme period. Tailored assessments to focus on relevant areas like Ability to Deliver and Downstream Partners were also done based on the unique scopes of Coherence and the Pilot, avoiding “one-size-fits-all” approach. The assessment has enabled to reinforce systematic risk management of safeguarding issues embedding proactive (less reactive), accountable and resilient implementation.

SFN’s risk profile remained fairly constant over the lifetime of the programme, with a few risks escalated and approved as above BEK’s risk appetite. While mitigation strategies were largely effective, SFN’s operating environment was highly risky and politically contentious, so some risks were not possible to effectively mitigate.

SFN’s Risk Appetite
The most difficult risks to effectively mitigate were Strategy and Contextual risks, with a decision made to remain receptive to these. Likewise, on Reputational, Policy and Programme Delivery and Financial and Fiduciary risks, it was decided to retain a receptive risk appetite. This was largely due to a recognition that the federalisation process is fraught with political interests, and new institutions weaker in their capacity to deliver and manage finances. In short, to support institution building and system strengthening of an entirely new governance system, you have to accept some risk.

As the figure of SFN’s risk distribution demonstrates, many risks crowded in the major and possible area, but all were managed within the SFN risk appetite (the dotted line). This reflects both a heightened level of risk appetite and effective mitigation strategies.

Figure 2. SFN Risk Profile

Risk Category: Strategy and Contextual
Net risk appetite – Receptive
The wider context presented a number of risks to SFN – the potential of natural disasters materialised in the form of COVID-19 which caused a lot of delays. Additionally, the fluctuating commitment to federalism and weak intergovernmental relations presented obstacles to progress on policy and law formulation (e.g. the Federal Civil Service Act), and progress towards programme outcomes. While SFN influenced this environment to some extent (see output 3), it was beyond the programmes and its main stakeholders and BEK’s control to mitigate this risk. Instead, the programme invested in understanding these constraints to inform better programming modalities with higher chances of success (e.g. Sahakarya Pilot).

Risk Category: Policy and Programme Delivery
Net risk appetite – Receptive
Aside from the wider political risks of fluctuating commitment to federalism, the frequent turnover of government staffs, low spending capacity of PLGSP implementation units, and slow decentralisation of powers to sub-national governments were major constant challenges throughout the programme. This risk proved very difficult for BEK to mitigate and necessitated significant amount of human resource commitment to maintain relationships. In 2024, BEK commissioned a study of the civil service to better understand the patterns of transfers and the Federal Civil Service Act, but this was arguably too little too late. The most effective mitigation strategy was stability in BEK staffing (a programme funded adviser continued throughout the programme which was essential to relationship management) and the Provincial Engagement Facility, which enabled frequent subnational engagements with rotating staff. In addition, the reprogramming of PLGSP with its focus on devolving governance structures should become a major part of managing this risk. Advocating for the passing of the Federal Civil Service Bill was another mitigation tool, but this was not very effectively employed. The Bill has been much delayed but a positive shift happened in May 2025 with the State Affairs and Good Governance Committee of the House of Representatives passing the Bill.

Risk Category: Financial and Fiduciary
Net risk appetite – Receptive
PLGSP has been significantly challenged by fiduciary risks related to likelihood of misutilisation of resources, largely triggered by systemic vulnerabilities in Nepal’s public financial management (PFM) systems at both federal and subnational levels. This risk operated at higher level than BEK’s risk appetite for Cautious/Moderate, in order for the programme to allow space for financial aid to PLGs, whose system strengthening was an important programme objective. PLGs were new, nascent and initially without financial accounting systems. In later years, analysis pointed to same level of weakness in federal, provincial and local government system so in effect the risk was not higher operating at PLG level[111]. Multiple levels of safeguards and risk mitigation measures were used including: i) a Joint Financing Arrangement (JFA) between the DPs and the GoN that spelt out role of Financial Monitoring Reports (FMRs) to provide annual thematic and sectoral spending data, promote Fiduciary Risk Reduction Action Plan (FRRAP), including the Financial Management Improvement Plan (FMIP); ii) the use of reimbursable financial aid modality which ensured verified expenditures before disbursements; iii) Regular reviews of of FMRs, annual Fiduciary Risk Assessments (FRAs) and consecutive Annual Statements of Progress (ASPs) as guided by the PrOF, with all FMRs have been independently reviewed by external experts from Royal Norwegian Embassy; iv) Third-party annual monitoring by the supreme audit institution, Office of the Auditor General of Nepal (OAGN) for integrity and financial oversight of PLGSP functioning as “on-budget, on-treasury” flagship programme; and v) Joint monitoring visits and spot checks by Development Partners (DPs), including monitoring measures for IPF projects.
[111] Integrated Fiduciary Risk Assessment, 2024

While the risk of corruption and misutilisation of funds in PLGSP is real, the programme has considerably taken thorough and timely measures to mitigate corruption risks. In October 2023, allegations of bribery surfaced online, which involved PLGSP stakeholders (PCGG) of Lumbini and Madhesh provinces. Investigations led by MoFAGA/PCU confirmed that no formal evidence of fund mismanagement was found and that PLGSP funds were unaffected. Nevertheless, stronger engagements between MoFAGA/PCU and provinces were initiated to reinforce zero-tolerance on fraud and strengthen compliance. Moreover, JFA DPs initiated discussions on fiduciary risk and MoFAGA committed to progress on Fiduciary Risk Assessment Action Plan (FRAAP).

Risk Category: Public Service Delivery & Operations
Net risk appetite – Receptive
The COVID-19 pandemic significantly disrupted SFN’s internal operations. Repeated drawdowns of UK-based staffs and restrictions on field monitoring visits hindered the programme’s ability to oversee and influence implementation on the ground. The programme efficiently adapted by increasing virtual engagement with stakeholders, including Development Partners (DPs) and the Ministry of Federal Affairs and General Administration (MoFAGA). All coordination meetings shifted to virtual platforms (Microsoft Teams and Zoom) with key monitoring efforts via PEF for oversight and accountability.

Risk Category: Reputational
Net risk appetite – Receptive
PLGSP has been constantly exposed to significant reputational and operational risks driven by corruption. Such incidents are highly likely to severely undermine credibility and effectiveness of the programme, adversely impacting governance reform in Nepal, and tarnishing the UK's reputation both domestically and internationally. While some allegations have transpired (see above under Financial and Fiduciary risk), these did not lead to significant reputational issues and were managed collaboratively with other DPs, this sharing the risk. Delays to signing an MOU for SFN’s successor programme, which ultimately led to FCDO’s withdrawal from PLGSP, drew criticism and scrutiny from various stakeholders. This will initially weaken BEK’s influence within the DP community and government stakeholders, who likely to perceive FCDO as inconsistent partner in Nepal’s federal transition.

Risk Category: Safeguarding
Net risk appetite – Cautious
Nepal’s context with a highly patriarchal culture and harmful social norms presents all programmes with significant safeguarding risks. This is a risk that cannot be fully mitigated. In SFN, PLGSP and Coherence were most susceptible to these because they supported government systems beyond BEK’s control and employed young people in remote places, respectively. These safeguarding risks, including potential incidents of discrimination, sexual exploitation, abuse, and harassment (SEAH) remained throughout the programme period. Under PLGSP all implementing units and TA providers were required to have safeguarding policies with adequate whistleblowing and incident reporting mechanisms. Efforts were made to ensure that Coherence, too, had sufficient safeguarding mechanisms in place (training, reporting, whistleblowing), though this did not receive much attention until SFN’s final years. In 2024, safeguarding focused monitoring visits revealed that issues had arisen in some LGs, and although appropriate action had been taken they had not been reported to BEK. To strengthen mitigation, BEK led on negotiating additional safeguarding measures in the Joint Financing Agreement for PLGSP.

Another dimension of safeguarding risks is unequal access to support for elected leaders and staffs from marginalised castes and ethnic groups. Significant concerns relate to systematic barriers and fragile enabling environment discouraging them from reporting issues and seeking support. As mentioned above, there is little data on to what extent this risk is being effectively monitored and managed in Nepal.

Risk Category: People
Net risk appetite – Receptive
The quality of TA staff and their enhanced technical coordination capacity has been a constant challenge with PLGSP. This was linked to Terms and Conditions as well as the operating space afforded to TA staff. In 2023-24, PLGSP underwent thorough redesign of TA positions, leading to a decision to full re-recruit for Phase Two process. All development partners actively engaged with the UNDP in the recruitment process as observers during the development of terms of reference/job description and enrolment of key transformative TA roles. Collective efforts were put into influence the MoFAGA to support the process of timely recruitment, induction and deployment of new team at various subnational implementation units across seven provinces. The results of this is yet to be seen as the new TA staff have only been in place since April.

Partnership Principles
SFN has been informed by the annual Partnership Principles assessment, which has generally remained on a stable or slightly improving trajectory. The assessment of GoN’s commitment reflects a medium commitment across four thematic areas, remaining consistent in the past four years. The overall trajectory demonstrates positivity in fiduciary and accountability aspects, but there are risks related to public sector effectiveness and value for money. Key risk highlighted is political instability, vulnerable GoN coalitions continuing to affect delivery. Nevertheless, the 2024 assessment states a stable trajectory, with areas of increasing risks to be monitored closely.

Fiduciary risk assessment (FRA) of PLGSP was conducted in 2020, followed by the first Annual Statement of Progress (ASP) in 2022. The second ASP conducted in 2023 states that the overall level of fiduciary risk is “Major”, with “Moderate” residual risk, and the status of risk for each category remained “Stable”.

2023 Annual Statement of Progress results

	Risk rating/Status	Assessment
Current level of fiduciary risk and direction of travel since last ASP	Major/Stable	The overall fiduciary risk for PLGSP programme and for IPF as of January 2024 is assessed to be Major. This represents a trajectory of no change compared to the 2022 ASP/FRA.
Specific assessment of corruption risk and direction of travel since last ASP	Severe/Stable	The corruption risk continues to be Severe with a trajectory of no change.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

The total business case value of the programme is £25.5 million, which includes an additional £3.5 million through an addendum. The programme started in late 2019 and ended in March 2025. The programme has six separate components and the overall expenditure during this programme period was approximately £16.2 million or 63.55% of overall programme value. The overall expenditure breakdown of this programme is provided below. The graphic below illustrates the total expenditure of each component. The detail is complemented by timelines of each component for clarity.

Figure 3. Component wise expenditure breakdown

Component 1 – Provincial and Local Governance Support Programme (PLGSP). An agreement was signed in 2019 between the FCDO (then DFID) and the Government of Nepal including UNDP technical assistance. The financial aid (FA) to GoN, is ‘on-budget-on-treasury’, but the TA support is ‘off-budget-on-treasury’. A major part of this programme supported the Provincial and Local Governance Support Programme (PLGSP) together with the European Union (EU), the Swiss Agency for Development and Cooperation (SDC), the Government of Norway, the Government of Nepal, and the United Nations. The total funding is approx. £86.41 million ($116 million), with £14 million allocated for technical assistance. The FCDO’s contribution was 28% of the total budget under the Joint Funding Agreement (JFA). MoFAGA maintained the Foreign Currency Account at the Nepal Rastra Bank (Central Bank) and the FCDO reimbursed its proportional amount only after Financial Monitoring Report, Quality Assurance (QA) verification.

In the first year, PLGSP focused on setting up the programme, building systems, signing agreements with provinces, selecting UNDP for technical support, and handing over training centres. Progress was made, but COVID-19 caused delays, especially in hiring the staff. However, the implementation resumed as the lockdown eased out. The programme management aspect of PLGSP has been challenging in terms of delays in reporting (FMR). It required substantive time of BEK programme team to pursue and guide the PCU team on FMR, particularly when UNDP TA team were disbanded during PLGSP phase one end. The financial performance has been low in terms of budget allocation vs. absorption. The table below demonstrates cumulative PLGSP spend for phase one, which is 42.22% only. However, the burn rate gained momentum starting 2021 FY increasing to 68% in 2023-24. This still remains below the GoN overall budget execution rate of 81% in 2023-24, indicating that – as was picked up by the MTR – that PLGSP governance structure was heavily centralised and required central MoFAGA approvals not just for budgets but for actual spend. This was not conducive to timely spend and was changed for PLGSP-II.

Table 4. PLGSP Budgets and Execution Rates Per Year

Component 2 – Programme Funded Advisory Post (PFP). The programme funded a Provincial and Local Governance Advisor who supported BEK and DPs on programme and political analysis and relationship building. This role served two main purposes: 1) to help manage the complexity of the programme given its wide technical scope, many stakeholders, and involvement of all 7 provinces and 753 local governments and 2) to ensure the programme’s work aligned with FCDO’s broader goals of supporting federalism and public sector reform. It represented only 1% of the overall programme expenditure.

Component 3 – Coherence. The original agreement with the International IDEA (IIDEA) was signed in 2020 for £3.1 million. This agreement was later extended in 2023 to £5.1 million to “support to democratic governance and effectiveness of PLGSP to adapt to political changes and support federalism phase II”. The extension also included the Provincial Engagement Facility (PEF) which was added in October 2023.

The success of this component relied on ability of young mentors to build relationships and adapt to a changing and politically charged environment. For example, despite COVID-19 disruptions, the programme adapted well and continued the activities and continued supporting LGs. After local elections in 2022, mentors had to build relationships with newly elected officials.

The Coherence programme also adapted and responded to BEK’s requests for learning and programme design support and maintained a strong working relationship with MoFAGA. In October 2023, a new PEF was launched in Karnali, Lumbini, and Madhesh to support BEK’s work and guide future programmes.

Component 4, The EFO – There was no expenditure made under this component as the agreement was signed between FCDO (earlier DFID) and the World Bank in 2018 from the previous PLGSP programme. The EFO led by the World Bank and funded by the UK and Switzerland, supported Nepal’s move to federalism by strengthening institutions and promoting economic development. It helped assess local government needs, organized international learning visits, and coordinated donor efforts through platforms like the Federalism Working Group (FWG) and Nepal Federalism Support Platform (NFSP). There were plans to continue the initiative through new PLGSP. However, since the Memorandum of Understanding (MoU) was not signed, the EFO concluded in 2021 but the FWG continued to support Nepal’s federal transition through regular coordination and shared strategies.

Component 5 – M&E
The objective of this component was to make sure that independent Monitoring and Evaluation (M&E) assessed SFN’s effectiveness, compliance, and risk management. Two separate contracts were awarded under this component: one to Oxford Policy Management (OPM), and one to PricewaterhouseCoopers Pvt. Ltd (PwC). OPM was responsible for assessing the programme’s progress against the outcomes and outputs outlined in the Programme Business Case and the updated logframe. This included alignment with the PLGSP Results Framework, indicators agreed upon by MoFAGA and development partners, the revised MEL framework, baseline data, and relevant results from other components of the Business Case. PwC (through Adam Smith International (ASI)) did an End of Programme Review to assess the progress of SFN against the impacts, outcomes, and outputs set out in the SFN Business Case. The outcome of these reviews was to assess the programme’s performance and determine whether it had achieved its overall goal as outlined in the Business Case.

Component 6 – the Sahakarya Pilot. An accountable grant agreement for the project was signed in December 2023 till March 2025 with a budget of £1.8 million. It was added as a separate part of the SFN programme after a no-cost extension of the programme business case was approved. This pilot aimed to deliver a learning framework and was jointly implemented by three international organisations, namely International IDEA, the Asia Foundation (TAF), and Westminster Foundation for Democracy (WFD).

On the quality of partnerships, relationships with MoFAGA and DPs under PLGSP were good but challenging at times due to frequent changes in staff, in particular in MoFAGA. Relationships with PLGs were significantly strengthened by the presence of the programme funded advisor. The relationship with IIDEA was excellent with mutual understanding built over a number of years and sustained across internal staffing changes.

On quality of financial management, PLGSP financial management remained difficult throughout, but the risk and burden was partially shared with other DPs. From a VFM perspective, IIDEA team performed well with 70% of overall project budget allocated for direct programme activities and no changes to the admin costs and indirect overheads agreed at the outset. On financial management, however, accurate and timely financial forecasting was a challenge throughout. Earlier trends in slippage in spend patterns suddenly changed in the final six months, causing difficulties for FCDO portfolio wide forecasting. This was particularly the case for the Sahakarya Pilot, but not exclusively.

SFN’s delivery chain mapping revealed complex delivery structures but enabled risk identification and management at all levels. Below is the mapping for Coherence and Sahakarya Pilot programmes, which were both implemented by IIDEA. This tool helped us to identify the downstream partners, see the flow of funds from donors to beneficiaries and supported the management of fiduciary risk.

Figure 4. SFN Delivery Chain Mapping

Monitoring
As mentioned, SFN adapted well to contextual changes and added components to improve its effectiveness in face of improved understanding of a changing context. Although SFN was not designed as an adaptive programme but it became apparent that active context monitoring and frequent adaptation would be necessary for SFN to deliver. A range of tools was used for this including analysis of How Change Happens in Nepal and increased use of political economy analysis in action methods. That said, because SFN was not set up as an adaptive programme and measuring according to a standard logframe that was updated on an annual basis, it did not achieve its full potential as an adaptive programme.

Rather, BEK employed the usual tools for monitoring, but throughout the programme placed a significant emphasis on field monitoring and engagement at the provincial level. Initially this engagement focused a lot on government actors, but as SFN adapted and expanded its approach to governance beyond working just with the state, this engagement also widened.

IIDEA regularly shared narrative reporting, financial forecasts, reports and audit reports, while for PLGSP these were only available annually and in line with GoN reporting cycle. These often came late and this sometimes proved challenging for FCDO’s own internal and disbursement requirements

As mentioned above, in the latter two years of the programme BEK made a more concerted effort to manage safeguarding risks, e.g. conducting spot checks, supporting IIDEA to develop better procedures, and integrating relevant provisions in the Joint Financing Arrangements for PLGSP. Both IIDEA management and field staff had opportunity to attend a Safeguarding (SEAH) session at their premises delivered by BEK Safeguarding specialists. This aimed to promote a safe, respectful, and accountable environment for everyone involved in the programme. It also ensured that all participants understood their rights and responsibilities and know how to respond appropriately to any safeguarding concerns arose. Subsequently, IIDEA formed an internal committee to develop SEAH guidelines.

Evaluation
On evaluation it has proved particularly difficult to evaluate SFN impact. This is because the PLGSP Results Framework was not properly followed by GoN to consistently measure indicators. For other components, like Coherence, no baseline was established at the outset against which to measure progress. That said, PLGSP and other components have all undergone rigorous reviews, so there is a lot of learning and evidence to base assessments of progress on. These documents formed the literature review basis for the End of Programme Review conducted in 2025.

The table below summarises the latest information narrative, financial and audit report from partners in 2024-25.

Date of last narrative financial report – Coherence	26th February 2025	Date of last Audit Report – IIDEA	11th September 2024
Date of last Quarterly Report – Sahakarya Pilot	24th March 2025	Annual Report 24/25 – IIDEA (DRAFT)	19th May 2025
Date of financial report - PLGSP	27th February 2025	Audit Report	Due date in September 2025