Programme Completion Review

Title: Stopping Abuse and Female Exploitation (SAFE), Zimbabwe
Final Programme Spend £ (full life): £8,206,524.68	Review Date:	February 2025
Programme Code: [AMP ID#] 300024	Start Date: 15th April 2019	End Date: 10th April 2025

Summary of Programme Performance

Year	2020	2021	2022	2023	2024	2025
Programme Score	B	A	A+	A+	A+	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://iati.fcdo.gov.uk/iati_documents/57941024.odt
DevTracker Links to all logframes used during programme lifetime:	https://iati.fcdo.gov.uk/iati_documents/90000694.xlsx

A. Summary and Overview

Description of the programme and what it has achieved

The Stopping Abuse and Female Exploitation (SAFE) programme (2019-2025) aimed to improve understanding of how to prevent and respond to gender-based violence (GBV) in Zimbabwe, creating a scalable programming model and building an evidence base on what works to prevent violence. The programme’s original timescale was 2019-2023. It was extended until 2025 to enable the implementation of a fourth cohort partnering with the World Food Programme (WFP), and to allow the production of a range of learning and guidance materials.

The programme has performed well throughout its life, in the face of several contextual challenges. SAFE has resulted in multiple positive impacts in the communities it worked in, including on protective factors against GBV. Participants across all SAFE studies reported better communication, joint decision-making in households and more gender equitable attitudes at endline. SAFE also generated a range of valuable learning on GBV prevention, and the model presents a strong basis for further iteration and adaption. As such, the programme strongly met the objectives defined in its business case.

Given changes in UK Official Development Assistance (ODA) funding, the aims of SAFE were altered in the first two years of inception. The programme’s budget was reduced from £12 million to £7.2 million, and was later increased to £8 million. Several elements were downscaled- for example, the duration of the social empowerment curriculum was shortened, and the number of districts in which the programme would be implemented was halved, and the evaluation budget was also reduced which meant the design no longer incorporated a control group. In addition, SAFE was impacted by Covid-19 and programme funding was used to fund a technical assistance facility in 2020, supporting government infrastructure in responding to increased rates of GBV at this time. This facility was highly successful and widely used. However, this reduced the programme budget available for core programme activities, and design and implementation added to the programme’s timeframe. The changes to SAFE as a result of contextual challenges following the approval of the business case should be taken into account when assessing the programme’s performance against business case metrics.

The core programme began implementation in 2021. Over the course of the following four years, the programme worked with four cohorts. Cohort one, two and three were each delivered in Chikomba and Mwenezi (rural areas), and in Chiredzi (an urban area). Cohort four consisted of implementation only in Chiredzi. An additional nuance was that in Chiredzi, across all four cohorts, the programme intervention was delivered to households receiving cash-based transfers from WFP. For each of the four cohorts, programme activities lasted for 4-8 months, depending on circumstances at the time of implementation. Between each cohort there was a period of learning and adaptation, during which the programme reflected on what had worked well, and what could be improved. The programme then made changes to delivery in subsequent cohorts. This iterative approach to programme delivery is impressive, enabling the programme to embed learning at its heart.

The programme involved two work strands:
- SAFE Communities (SAFE-C): implementation of community-level programming for the prevention of and response to GBV. This strand was delivered by a consortium led by Ecorys, with Social Development Direct providing technical support.
- SAFE Evaluation and Learning Unit (ELU): independent research and evaluation of the programme, and the production of new evidence on the drivers of violence and what works to prevent it in Zimbabwe. This strand was managed by Tetra Tech.

Key activities under the SAFE C work strand included:
- Formation of Toose Internal Savings and Loans (TISAL) groups.
- Delivery of an economic empowerment curriculum for TISAL group members.
- Delivery of a social empowerment curriculum known as ‘Toose’ for TISAL group members and their intimate partners.
- Delivery of GBV response services.
- Provision of cash based transfers to Chiredzi cohort, funded through the separate FCDO programme, ZHARP.

The formation of TISALs was the first step in the programme. The majority of TISALs throughout the programme were women-only groups, reflecting learning from early cohorts. TISAL members received an economic empowerment curriculum, covering topics such as business management and marketing. The curriculum was delivered by a different local partner in each district- Caritas in Chikomba; the Mwenezi Development Training Centre in Mwenezi; and Plan International in Chiredzi. Members were encouraged and supported to identify income generating activities (IGAs), and withdraw realistic loans from their TISAL to carry out these IGAs. The aim of the economic element of the programme was to improve household economic security, thereby reducing the food insecurity and poverty which are common drivers of violence. In Chiredzi, this aim was further complemented by delivering the programme to recipients of WFP cash-based transfers.

Women involved in TISAL groups, along with their partners, then received a social empowerment curriculum, known as ‘Toose’. This was delivered by the same local partners in each district as the economic curriculum. The curriculum consisted of 7-9 sessions, covering topics such as power dynamics and family visioning. Sessions explicitly covering intimate partner violence were added to the curriculum in cohort three, following learning from the earlier cohorts. The aim of the social element of the programme was to improve gender equality within households and communities, and to reduce rates of intimate partner violence (IPV).

Community diffusion of the lessons from both the economic and social elements of the programme was a significant part of the programme. Implementing partners were a key part of structured diffusion. Peer facilitators also played an important role. As participants in early cohorts of the programme, peer facilitators were trained by implementing partners to work with them in delivering sessions to later cohorts and therefore had a good understanding of the programme’s aims and messaging. All programme participants, including those not formally peer facilitators, were known as ‘champions’, and encouraged to share the programme’s messaging within their communities.

GBV response was the final key element of the programme. Across the programme lifespan, Musasa, an established Zimbabwean women’s rights organisation (WRO), was funded to scale up pre-existing response services in the relevant districts. These services included a toll-free helpline, physical shelters, and one-stop mobile services. SAFE also supported Musasa to establish Gender Community Based Clubs (GCBCs). These GCBCs consisted of community volunteers who acted as referral systems and points of contact for survivors of violence. GCBCs were trained by Musasa to understand the GBV response services available in each district, and to direct survivors of violence towards them. In 2024, the programme provided funding for bicycles for GCBC members, which enabled GCBCs to transport survivors to service centres.

Through the ELU, a significant amount of research and learning was produced by the programme, including multiple deep-dive studies as well as a quantitative endline study in 2024/2025. The endline study does provide some evidence around the impact of the programme, but it must be noted that the study methodology faced limitations. The endline study was a pre-post assessment of participants in cohorts one and two only, and they were only surveyed one to two years after they finished the programme. Additionally, there was no control group to capture the likely increase in GBV across Zimbabwe in 2024 given the severe drought and resultant food insecurity. As such, in this report, the endline findings are balanced with learning from the other qualitative studies conducted during the programme lifecycle, as well as learning from programme partners and beneficiaries.

The body of learning and evidence produced by the programme indicates that SAFE had positive impacts in multiple areas. There were significant improvements in the wellbeing of family units, with participants reporting better communication, joint decision-making in households and more gender equitable attitudes at endline. These are important protective factors against GBV. Quality of parenting also improved, with the majority of participants reporting reduced conflict between parents and children during qualitative studies. These findings are supported by reflections from beneficiaries, shared during a field visit conducted as part of this PCR. Participants identified improvements in communication as a major benefit of the programme. Several male participants reflected that the programme had helped them to move away from using ‘power over’ their wives, and encouraged them to use ‘power with’. Learning on power dynamics was referenced by multiple participants as a particularly important part of the programme. Several participants reflected that the programme had ‘changed our lives’ and ‘uplifted the family’.

However, the endline study found that the programme in these first two cohorts may not have been successful in decreasing rates of IPV, as there was a small but significant increase in IPV in households, which was driven mainly by increasing food insecurity. This is pertinent given that the endline was conducted during the 2024 El Nino drought. There was however a reduction in IPV on some measures of severe IPV, and the mean number of IPV acts experienced by women in the past year did decrease. Overall, there are several possible explanations for the lack of clear reduction in IPV in the endline study. It is possible that participants had built better relationships with evaluators at the time of the endline, and therefore were more willing to share their experiences than they were in the baseline, meaning that the baseline may have underestimated rates of violence. It is possible that rates of IPV increased more significantly within communities in the same districts who did not participate in the programme (a real likelihood given the 2024 El Nino drought), and that SAFE therefore had a protective impact. The endline study found that IPV only increased in households that experienced increased food insecurity, highlighting the importance of addressing both. It is also possible that the design and / or implementation of SAFE required adjustments to genuinely have a positive effect on IPV, although it must be noted that the endline only looked at the first two cohorts and IPV was more explicitly address in the following two cohorts. One particular area of learning in the endline study was the need to extend the social empowerment curriculum and include a reflection session following the IPV-focused session to truly embed learning and positive change.

There is also evidence from across the ELU’s studies, that whilst SAFE generated positive outcomes in some attitudes around gender, it may not have been fully gender transformative. SAFE raised awareness of gender norms, but was not successful in fully changing them. Qualitative data from beneficiaries suggests some cases where female participants changed their behaviour upon learning about the triggers of violence and household conflict, becoming more compliant with their husband’s wishes. Whilst this may have reduced violence and improved family wellbeing, it does not reflect a change in gender norms or an increase in gender equality. Similarly, whilst many programme participants identified increased marital intimacy as a positive impact of the programme, it was apparent in some beneficiary engagement sessions that women did not feel confident or comfortable denying their husband’s requests for sex. This highlights the reality of limitations to fully shifting social norms through one programme, and SAFE needs to be understood as one positive input into a complex system. The communities in which the programme operated are highly patriarchal, with significant levels of gender inequality. In this context, changes in the behaviour of male participants, such as doing more of the household chores, are significant.

A further consideration is that comms and branding about SAFE positioned it as a family wellbeing programme. This approach enabled the successful engagement of male participants, who would have been unlikely to participate as fully in a gender transformation programme or a programme purely seen as a women’s rights initiative. However, this framing may have limited the programme’s ability to achieve further impact in terms of gender transformation and women’s empowerment. This highlights the delicate balance between encouraging men’s participation whilst fully targeting women’s empowerment.

Major lessons learned, evidence generated and recommendations

Lessons learned:
1. There are limits to fully shifting underlying gender norms through one intervention, and SAFE needs to be understood as one positive input into a complex system. Gender transformation takes significant time and requires economic, social and cultural changes. The SAFE programme developed an approach that improved family dynamics and was protective against GBV, but the learning suggested that this 6-8 months intervention may not have fully transformed underlying social and gender norms in programme communities.
2. Investing in the capacity of implementing partners is critical. Quality of implementation in different cohorts was heavily influenced by the implementing partner delivering the sessions. Partners should have themselves gone through a gender transformative journey, be comfortable with gender equality principles, and have experience in delivering GBV programming. Investing in high-quality, intensive training, and supporting implementing partners throughout programme delivery, is crucial for success.
3. Framing is important to ensure the engagement of men and boys- but needs to be balanced with a women’s empowerment focus. Framing SAFE as a family wellbeing programme was positive for community engagement, particularly for ensuring the participation of men. It is likely that participation rates for men would have been lower if the programme had been framed as a gender equality or GBV prevention initiative. However, this framing should not lead to a reduction in focus on women's empowerment.
4. Relationships between and within programme consortia are vital for success. FCDO should consider how it can incentivise positive working relationships between programme partners throughout the lifespan of the programme, to bring together important international technical expertise, whilst ensuring that this is carefully grounded in local contextual understanding.

Evidence generated (further information can be found here and here):
1. Strong linkages between the economic and social empowerment elements of a GBV intervention are key to success. The economic element of SAFE provided an opportunity for participants to put into practice their learning from the social empowerment curriculum, such as visioning and power dynamics. TISALs and in Chiredzi, cash based transfers, provided the household economic security needed to focus on social change. The two elements of the programme were mutually reinforcing, and should be implemented together.
2. Reflections on power dynamics are necessary for transformative change. Beneficiary feedback consistently indicated that learning about power dynamics had a significant impact on them, and encouraged them to change their behaviour. This element of the programme was still having an impact after the first two cohorts had graduated, indicating that it is critical to programme sustainability.
3. Adaptations are needed for different types of households. Qualitative evidence from implementing partners indicated that the SAFE approach was most effective for couples living in the same house. Other household models, such as female headed or polygamous households, were less engaged with SAFE, and the programme had fewer impacts on them. Significant adaptation would be needed to implement SAFE with different types of households.
4. Training, guidance, and structure is needed to ensure that community diffusion is successful. Relying on unstructured community diffusion can mean that unintended messages are shared, reducing the impact of an intervention at a community level. Successful community diffusion is an important part of achieving impact beyond a household level, and a structured approach, with training, guidance, and ongoing monitoring and support, is necessary to achieved this.
5. Cash based transfers (CBT) make a significant impact to the effect of TISALs in particular. Across all the SAFE studies, there is consistent evidence that CBT was successful in mitigating economic stress and strengthening the ability to direct money into TISAL savings that could then be converted into loans and income generating activities. Layering GBV interventions on top of other economic empowerment interventions such as cash-based transfers can have a multiplying effect.

Recommendations:
1. The FCDO should continue to look for opportunities to partner in the implementation of the SAFE model in Zimbabwe. This could include developing new partnerships with mining organisations (given mines are known GBV hotspots) or other NGOs to take forward the SAFE approach. Given the current ODA cuts experienced by bilateral donors in Zimbabwe, emphasis should be on harnessing new sources of support and financing, including from the private sector.
2. SAFE’s iterative model of delivery should be replicated. SAFE’s commitment to learning and adaptation allowed the programme to change and grow throughout its lifecycle, as evidence was generated. This led to increased effectiveness over time, and is impressive. This model should be considered across FCDO social development programming, and should be replicated in any future implementations of SAFE.

How this report was conducted

This review was led by a Social Development Affiliate external to the programme, who worked alongside the Senior Responsible Owner (SRO) and lead adviser over a two-week period in January-February 2025. The review process involved a field visit to Chiredzi to interview beneficiaries and implementing partners, as well as interviews with members of SAFE-C, ELU, and WFP. Attendance at a two-day learning and adaptation workshop was also involved, and a review of key documentation, including the business case and previous annual reviews, was carried out. Programme partners were also given the opportunity to comment on a draft of the report.

Actions following approval of this report

SAFE completes against a context of significant ODA cuts by a range of bilateral donors. As such, the FCDO is considering ways to better support sustainable financing to GBV response and prevention in Zimbabwe, including through supporting women’s rights organisations to better tap into individual giving and private sector financing. Alongside this, the originators of SAFE continue to explore opportunities to implement SAFE in other parts of Zimbabwe, including in mining communities which are known GBV hotspots.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£12m (business case) / £7.2m (inception) / £8m (post extension)	[To complete]
Timeframe	4 years: April 2019 – April 2023	6 years: April 2019 – April 2025
Outcomes	Outcome 1: Strengthened community-based and national prevention and response to VAWC in Zimbabwe.	Achieved (A)
	Outcome 2: Well-evidenced community-based and national prevention and response model to VAWC in Zimbabwe.	Achieved (A)

Overall assessment of programme outcomes, sustainability and VfM

The business case identified the two outcome statements presented in the table above, and further work on a theory of change broke these outcomes into five outcome indicators. This section discusses evidence against the two outcome statements, and the section below considers the five outcome indicators.

SAFE achieved against Outcome Statement 1. As a prevention model, there is substantive evidence of participants using non-violent methods to resolve household conflict since the start of their involvement in the programme, and changing their behaviour within the household. These are all protective factors against GBV and suggest the beginning of gender transformation. However, the endline study of cohorts 1 and 2 presented mixed results, with an increase in IPV amongst beneficiaries, largely driven by economic insecurity, but some reduction in severe IPV, particularly among beneficiaries with low to medium food insecurity. There were limitations to this study which mean it needs to be considered alongside other sources of evidence. On balance, the evidence suggests that the programme did have multiple positive impacts and is an effective model of violence prevention.

In terms of GBV response, SAFE has consistently exceeded expectations for engaging with survivors of violence, surpassing baseline results and indicating that community level response services have been strengthened. The endline evaluation showed that SAFE had resulted in an increase in the number of survivors of violence seeking help, an increase in knowledge about what services are available, and a decrease in barriers to accessing services. However, there was some evidence of persistent normative barriers to seeking help- such as shame, stigma and fear of consequences.

SAFE has also achieved Outcome Statement 2. Numerous lessons have been learned, and good evidence has been produced which has been published in several impact and learning briefs . This will be useful in strengthening GBV prevention in Zimbabwe, and will contribute to the global evidence base. The SAFE model has been well documented, with the programme team finalising the implementation manuals and videos of each of the Toose sessions in the programme’s final months. The programme’s partnership with the World Food Programme has been innovative and has further expanded the evidence base in terms of layering GBV prevention and response onto resilience and humanitarian programming. The programme team has engaged closely with a range of stakeholders to share evidence from and promote the programme, including with the national government, UN Agencies, local and international NGOs and other GBV technical experts.

Ensuring the long-term sustainability of the programme by engaging other donors and partners in the model has been a priority in its final year of operation. The programme has focused heavily on producing guidance for other implementing partners, to ensure that the programme’s methodology is replicable in an ethical, effective manner. Conversations with a range of partners on taking forward the model have shown promising initial results. One of the most promising routes to sustainability was working with Musasa, the implementing partner for the response element of the programme, to build their capacity and ability to adapt and implement SAFE. However, given recent USAID funding cuts which severally impacted Musasa, there will not be an immediate opportunity for Musasa to begin implementation of SAFE, although there remain several other potential opportunities which may yet materialise. Additionally, there is promising progress on a partnership with a platinum mine to implement Toose using their Corporate Social Responsibility budget. The collaboration and engagement with WFP at the national and regional level was excellent, and WFP continues to input Toose into its proposals for new funding.

The SAFE programme has demonstrated good value for money throughout its life. In each year, the majority of programme spend has been on delivery of core activities. Staff costs have been the next largest expenditure category, followed by monitoring and evaluation. Total costs per participant are not available for SAFE given the piloting and learning approach, which was much broader than pure programme implementation, so it is difficult to compare the overall cost to other GBV interventions. Established GBV interventions working in communities can cost as little as $4 per participant, however this requires the intervention to have been extensively tested and evaluated in previous iterations. Small group interventions which are more innovative can cost approximately $300 per participant. A cost effectiveness study should be part of future iterations of SAFE in order to effectively compare costs with other GBV prevention models.
[note] https://www.whatworks.co.za/documents/publications/426-cost-effectiveness25-03-22web/file

It is also important to consider the impact of the cash based transfer which WFP provided to programme participants in Chiredzi across all the cohorts. The cash transfer of $13 per person in a household every month had a positive impact on the performance of TISALs- participants receiving the cash based transfer were more likely to spend their TISAL loan on IGAs than on household essentials, and took out larger loans. In Chiredzi, where participants received a cash transfer, the average loan amount was $77.26, whereas in Mwenezi, where participants did not receive a cash transfer, the average loan was $34.55. Whilst this difference cannot be solely attributed to the cash transfer, it is significant nonetheless. Qualitative feedback from beneficiaries and programme partners indicates that the cash transfer was a significant element in improving household economic security, a key aim of the programme. The cash transfer therefore represents positive value for money, and should be carefully considered in further iterations of SAFE.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The programme’s results framework was first finalised in July 2021. It must be noted that whilst the logframe was subject to regular review, it was nevertheless difficult to fully capture the more normative ambitions of the programme such as changes in women’s agency and empowerment. The programme’s theory of change (ToC) has largely remained constant throughout the programme’s lifespan. The ToC impact was to reduce to prevalence of GBV and improve family wellbeing. The ToC identified five outcome indicators which would achieve this impact:
1. Households are more able to manage economic stress.
2. Intimate partner and family relationships are more gender equitable, and do not resort to violence to resolve conflict.
3. Members of focal communities express desire to live the Toose way.
4. Increased access to essential GBV services by women and adolescent girls.
5. SAFE model and its effectiveness are well documented for learning and replication by other actors.

The central hypothesis of the ToC was that to reduce GBV, changes are needed at the household level (via the Toose social empowerment curriculum and the formation of TISALs), and at the community level (via diffusion from Toose participants and key influencers). Working to tackle barriers preventing survivors from accessing support services, and generating evidence and learning to inform implementation, are other key pillars. Based on the latest evidence from the field of GBV prevention, the ToC remains valid.

The endline provided mixed evidence around SAFE achieving its primary impact in the ToC, given that the prevalence of IPV appeared to increase among some programme participants, particularly where economic insecurity increased, and there was some evidence of continued controlling behaviour by men and corporal punishment against children. There was however a reduction in IPV severity at endline, and the mean number of IPV acts experienced by women in the past year did reduce amongst programme participants.

In relation to the five Outcomes, SAFE was most successful in achieving three of them (1, 4 and 5). Economic stress (Outcome 1) emerged as a key factor influencing IPV outcomes. Women in households where food security improved or remained stable were less likely to report IPV, whereas those experiencing greater food insecurity at endline reported increased IPV across all measures. While SAFE’s economic activity, TISALs, did not fully mitigate economic shocks (including the 2024 El Nino drought), an association was found between women taking multiple loans and reduced severity of IPV - suggesting that access to financial resources may contribute to lowering stress-related triggers of violence. These findings reinforce the importance of integrating economic empowerment initiatives into GBV prevention programming.

The programme showed strong positive impacts on household wellbeing (Outcome 2), for example, improved ability to meet essential needs, stronger shared household visions, greater joint decision-making, and increased men’s contribution to domestic labour. These changes were particularly prominent where women participated in the programme alongside their male partners, reinforcing the importance of couple-based interventions. However, there were more modest shifts in terms of women’s empowerment and improvements in gender equitable behaviour did not always translate into greater agency for women. This pattern has been observed throughout SAFE’s evaluation cycle. Earlier studies found that behaviour change often remained conditional on practical benefits to the household, and that power remained concentrated with men. Despite changes in behaviour, underlying attitudes and norms - particularly around gender roles, infidelity, and male authority - were more resistant to change. This points to the limitations of the programme in transforming gender norms at scale.

In terms of Outcome 3, beneficiaries expressed some challenges related to community support (such as negativity around men carrying out “feminine” chores). Challenges with unstructured community diffusion may have played a role in this, as there is evidence of misinterpreted or incorrect messaging on some occasions. More structured diffusion, with a defined strategy, guidance and monitoring, could have increased the programme’s impacts at a community level. Future adaptations to SAFE could consider how to expand changes beyond households to communities, such as further engagement of faith and community leaders.

There is also evidence that SAFE contributed to improved awareness of GBV and availability of services (Outcome 4), particularly through the work of GCBCs and Musasa. Participants’ confidence in supporting survivors increased, perceived barriers to access declined, and actual help-seeking behaviour improved across some indicators. However, it must be noted that normative barriers - such as shame, stigma and fear of consequences – appeared to persist at endline.

Finally, in terms of Outcome 5, SAFE generated significant learning, which has been well documented and will contribute to the global evidence base. A range of partners have been engaged on numerous occasions about the approach, and there are several potential opportunities to take forward the programme with NGO and private sector actors.

## C: Detailed Output Assessment

The outputs for the SAFE programme have been adapted over its lifespan, with Output 4 and 5 added in 2022 and 2023 respectively. Similarly, logframe targets have been updated throughout the programme to reflect changing contextual circumstances and the addition of new partners, such as WFP in the final year. This output assessment is therefore primarily narrative based.

Output Number and Title	1- Households work together to improve their economic security and to improve gender equality within the household to reduce violence
Output Score	A
Impact weighting (%)	40	Impact weighting revised since last AR?	No

Output Indicator	Final Result	Narrative
Output Indicator 1.1: / Number and proportion of TISAL participants / trained in Toose methodology, / disaggregated by district, sex and disability status.	Achieved	SAFE consistently exceeded its targets each year for this indicator, with the vast majority of TISAL participants also being trained in Toose methodology. This was broadly equal across all three districts, and across all four cohorts. Rates of male participation remained relatively high. Ensuring the participation of participants with disabilities was a priority for the programme.
Output Indicator 1.2: / Proportion of TISAL group members / i) taking a loan / (ii) reporting using their / loan for productive / activities, disaggregated / by district, sex and / disability status.	Achieved	SAFE consistently exceeded its targets each year for this indicator. In the majority of cohorts, 100% of TISAL members took a loan and used it for productive activities. This was largely equal across districts. Male and female participants were equally likely to take a loan in early cohorts, however in later cohorts TISAL groups were restricted to women only or men only groups to reflect learning from experiences of mixed gender groups.
Output Indicator 1.3: / Proportion of Toose / groups demonstrating an understanding of gender roles / and behaviours, and/or harmful behaviours supported by / qualitative evidence, / including from women / with disabilities.	Partially Achieved	SAFE consistently exceeded its targets each year for this indicator. In the majority of cohorts, 100% of Toose participants demonstrated a greater understanding of gender roles and behaviours. The most common changes in understanding related to household decision making and chore distribution. Women with disabilities demonstrated similar increased understanding of gender roles as a result of their participation in Toose. / However, qualitative evidence suggests that there was less understanding of harmful behaviours and their impact, but that understanding still increased over the course of the programme. The endline and other deep dive studies showed that there were limits to how far the programme could shift underlying gender norms.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The SAFE programme consistently achieved the indicators under this output throughout its lifespan. Through the formation of TISALs, the delivery of an economic empowerment curriculum, and the provision of cash based transfers, SAFE improved economic security. The programme also improved the distribution of gender roles within households, with male participants more likely to recognise the domestic burdens experienced by their wives and more likely to engage in household chores. In addition, the formation of TISALs had positive unintended impacts, such as enhanced community cohesion and increased social capital for participants.

However, achievements against targets under this output need to be nuanced by the qualitative research and the final endline study which showed that the programme was not completely successful in delivering full gender transformation in relation to economic empowerment. For example, in some cases, the programme may have further embedded existing discriminatory gender norms in relation to decision-making around economic resources. Several female participants reported becoming more compliant with their husband’s wishes once they learnt that conflict can be a driver of violence. Qualitative data indicated that increases in instances of joint decision making were often the result of men allowing their wives to make decisions in their absence, or involving them in decisions which women saw as minor, with men retaining the final say. Similarly, the endline study found that although there were improvements in household decision-making, these shifts may not have resulted in stronger decision-making power or greater agency for women.

Lessons learned through this output, and recommendations for future programming

Indicators should be carefully selected to ensure that they reflect the intended output (or the output statement must be revised to narrowly capture what the indicators are measuring). Whilst SAFE exceeded all of the indicators for output 1, it was difficult to objectively measure the more normative goals of this output around women’s agency and empowerment. This makes it difficult to score the programme accurately against this output. The results framework for future programming should be carefully reviewed to ensure that indicators are reflective of outputs.

Output Number and Title	2- Communities take action to promote gender equality and the prevention of GBV affecting women and girls
Output Score	A
Impact weighting (%)	15	Impact weighting revised since last AR?	No

Output Indicator	Final Result	Narrative
Output Indicator 2.1 / Number of discussions or community conversations held by Toose Peer / Facilitators to promote gender equality and the prevention of GBV affecting women and girls disaggregated by district / and supported by qualitative evidence.	Achieved	SAFE consistently exceeded targets for this indicator throughout the life of the programme. Peer facilitators (graduates from early cohorts who assisted the delivery of the Toose curriculum in later cohorts) held far more conversations within their communities than expected. The number of conversations held was roughly equal in Chikomba and Chiredzi, but significantly lower in Mwenezi. The reasons for this variation across districts are not clear. However, the community diffusion study in 2024 suggested that some of these conversations may have included misinterpreted messages.
Output Indicator 2.2 / Number of people outside of their household, with whom Toose champions share Toose knowledge / and tools, disaggregated by district.	Achieved	SAFE met targets for this indicator throughout the programme. Toose champions (all previous programme participants) held conversations with other members of their community about the programme. The number of people reached was largely equal across all three districts. As well as formal conversations, community members seeing the improvements in quality of life among Toose participants was also significant. Qualitative evidence suggests that ‘leading by example’ was a significant factor in sharing Toose knowledge within communities. However, as with the previous indicator, the community diffusion study indicated some instances of incorrect messaging by Toose champions.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

SAFE consistently achieved the indicators of this Output throughout its life. Community diffusion was an important component of the programme, and both peer facilitators and champions facilitated a large number of conversations related to the programme’s themes. A qualitative study focused on the community diffusion component of SAFE found that this component did lead to more equitable division of roles and collaboration within the household.

However, findings against this Output must be nuanced by the qualitative evidence which suggested that some of these discussions may have involved inappropriate or incorrect messaging. For example, some of these discussions included messages such as that women denying men sex can cause violence, or that women complying with men’s demands reduced household conflict. These messages did not promote gender equality within communities. This suggests that SAFE’s community diffusion approach was perhaps too unstructured even with a community diffusion guide. Ongoing monitoring of messaging and support to volunteers can help ensure integrity of messaging.

Lessons learned through this output, and recommendations for future programming

1. As with Output 1, there are some challenges in fully capturing the success of this component with objective and measurable targets. Whilst SAFE achieved all of the indicators for Output 2, it may not have fully achieved the underlying goals of the output and qualitative evidence provides nuance when evaluating this Output.
2. Ongoing monitoring of messaging and support to volunteers involved in the community diffusion can help ensure integrity of messaging. A greater focus on community activism could have an impact on change beyond a household level. Further engagement of key community figures, such as faith leaders, in promoting the lessons from Toose could help the SAFE model achieve broader change, and has been a successful part of other GBV prevention programmes
3. Building on the impacts of ‘leading by example’ could share SAFE messaging with a broader audience. Profiling the lives of SAFE participants via social media or within the community could promote broader change and make the SAFE model more sustainable.

Output Number and Title	3- Women and adolescent girls use available GBV services
Output Score	A+
Impact weighting (%)	15	Impact weighting revised since last AR?	No

Output Indicator	Final Result	Narrative
Output Indicator 3.1: Number of / survivors who use GBV response / services by type (CBC, / accompaniment, transport services, / One Stop Shop, shelter, medical, / justice), disaggregated by district, / age (adult/under 18), disability.	Overachieved	SAFE far exceeded targets for this indicator throughout the course of the programme. In some years, the programme reached more than triple the target for survivors using response services. The most common services used were counselling and mobile one stop centres.
Output Indicator 3.2: Number of / people reached through Gender / Community Based Club community / Actions	Overachieved	SAFE far exceeded targets for this indicator throughout the course of the programme. GCBCs were very successful in supporting survivors within their communities, and in referring them to a range of appropriate services.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Current global evidence suggests that implementing programming on GBV will increase demand for response services, due to both increased awareness of what violence looks like, and backlash. In order to ensure that programmes are ethical, GBV response services should always be provided alongside prevention programmes. SAFE complied with this evidence by funding a women’s rights organisation, Musasa, to scale-up their existing GBV response services, and to support GCBC volunteers within communities.

SAFE largely achieved this output. Women and girls in programme districts used available GBV services in large numbers, and the endline study confirmed an increase in help seeking. Qualitative evidence suggests that the programme increased awareness of response services available in each district, and of how to access them. GCBCs were a particularly important part of this. GCBCs also played a key role in ‘myth busting’ about GBV services, for example by explaining that a survivor seeking support did not necessarily mean that their partner would be arrested. Even after the programme stopped operating, qualitative evidence indicates that GCBCs remain well known within their communities, and are still asked for support and advice.

However, there was some evidence that a few GCBC members have played a role in misinterpreting and miscommunicating key messages from the programme, limiting the impact of community diffusion as outlined above. Whilst the GCBC training and coordination mechanisms were adapted following this finding, further monitoring and ongoing support to these volunteers may have been beneficial.

Some male programme participants reflected that they had initially been reluctant to join the programme due to the involvement of Musasa. It is possible that as a women’s rights organisation, Musasa is seen as promoting gender equality and gender transformation to a degree that is uncomfortable for male community members. It is also possible that men assumed that they would be arrested for violence if survivors sought support from Musasa. Future adaptations of SAFE should consider the perceptions surrounding WROs and GBV response organisations, and include actions to dispel misconceptions from the beginning of implementation.

Lessons learned through this output, and recommendations for future programming

1. Increased integration of response and prevention components could increase accurate community diffusion, and enhance the impact of both elements. Although SAFE did have a GCBC present at Toose sessions, GCBCs could have benefitted from further training on prevention as well as response. Likewise, training facilitators on GBV response services could have provided more opportunities to share information with participants. This lesson was reflected in the final year of the programme, where GCBCs were trained together with Toose facilitators.
2. Further consideration of different needs for different groups could help SAFE enhance its ‘Leave No-One Behind’ (LNOB) aims. Whilst SAFE explicitly considered the needs of people with disabilities, there is little evidence that the needs of other marginalised groups, such as LGBT+ people, were considered (although it must be noted that the LNOB agenda was specifically informed by a contextual analysis). LGBT+ people often face more and specific challenges in accessing GBV response services. Considering these challenges, and adapting response services to reflect them, would make the programme more inclusive.

Output Number and Title	4- SAFE partners learn from, generate and disseminate relevant evidence on GBV and vulnerability in Zimbabwe
Output Score	A
Impact weighting (%)	15	Impact weighting revised since last AR?	No

Output Indicator	Final Result	Narrative
4.1 Number of evidence products that / contribute to the national, regional and / global evidence base on (i) drivers of GBV / in Zimbabwe, (ii) what works to prevent / GBV in Zimbabwe and (iii) how to scale up quality GBV programming in Zimbabwe, including for different marginalised groups, (iv) understanding poverty dynamics	Achieved	SAFE has produced a number of evidence products over the course of the programme, meeting targets for this indicator. The ELU work strand has been particularly successful in producing research on the drivers of violence in Zimbabwe, including reflections on poverty dynamics, and on lessons learned about what worked and did not work within the programme.
4.2 Number of learning activities and / events held with external GBV / stakeholders including in Zimbabwe and / internationally	Achieved	SAFE has undertaken a range of external learning activities to promote evidence produced by the programme, particularly in the last year. The programme has taken advantage of international themes, such as 16 Days of Activism to Prevent GBV, to present its findings in webinars, and has been involved in the biannual Sexual Violence Research Initiative.
4.3 Number of internal learning events to / share and uptake learning generated / through the SAFE programme	Achieved	SAFE has undertaken learning events to promote the programme’s evidence internally. The programme has held several learning and adaptation workshops with all partners to share findings and reflections, including from the ELU.
4.4 WFP to 1) engage local networks to / share findings and lessons learned, 2) / engage global networks for potential / further piloting or uptake of the Toose / methodology, and 3) Showcase project / success and lessons learned internally / and externally, through a variety of / existing platforms	Achieved	WFP has been active throughout the last year of the programme’s life in sharing findings. Key WFP staff members have engaged with partners in Zimbabwe to promote SAFE and its findings, for example during the “Group of Friends on Protection and Accountability” visit in September 2024, and other events (such as the National Dissemination Event, the Close-Out event, and the 16 Days of Activism panel). WFP has also engaged other WFP country offices, in different countries and at the centre, to provoke consideration of Toose. Unfortunately, given a global WFP travel ban introduced in February 2025 as part of global efficiency measures, WFP was not able to take forward a workshop on SAFE to other WFP offices that was planned for March 2025.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

SAFE has achieved this output. All partners have been engaged in learning from the programme throughout its life, and have played a role in generating evidence on GBV in Zimbabwe. Partners have also been closely involved in disseminating this evidence, with WFP playing a particularly significant role in the final year of the programme. A variety of evidence products have been produced on VAWG in Zimbabwe; key lessons and recommendations from the SAFE programme have been documented; and a range of events have been held for both external and FCDO audiences to share learning from the programme. Through this learning, capacity has been built in new partners (such as WFP, Musasa) to take forward implementation of the model, and there is ongoing interest in the approach from other INGOs and the Government of Zimbabwe.

There have however been some delays in the production of key documents, particularly on the manuals to guide other partners in implementing SAFE in other contexts. This has delayed the dissemination of evidence to the fullest extent possible.

Lessons learned through this output, and recommendations for future programming

SAFE’s iterative model to delivery built around learning and adaptation was impressive. Careful consideration around the sequencing of evidence and learning products is required to ensure that evidence can be fully embedded into programme design and adaption. Strong programme management is then required to deliver evidence in a timely manner.

Output Number and Title	5- Provisions in place for Toose to continue beyond end of programme
Output Score	A
Impact weighting (%)	15	Impact weighting revised since last AR?	No

Output Indicator	Final Result	Narrative
5.1 A ‘tested standard package’ is / defined, agreed and delivered. / Routes for future use and investment / of this package are proactively / explored. A responsible exit strategy / is in place and is understood by / communities and implementing / partners.	Achieved	SAFE has met targets for this indicator in the final year of the programme’s life. A technical package has been drafted by the programme team, and shared with a range of stakeholders. The programme team, FCDO, and WFP have explored a number of routes for future investment, with a range of partners. Several dissemination events occurred in the final year of the programme, alongside a number of ongoing bilateral engagements with other donor, private sector actors, civil society and GoZ. These conversations are ongoing, and will likely continue beyond the life of the programme. WFP has played a particularly significant role in promoting SAFE and exploring future investment.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

SAFE has achieved this output. This output has been a significant focus for the programme in its final year of implementation. The programme team (WFP and SAFE-C) have worked closely together to develop and agree a ‘standard package’ which will allow other partners to adopt and implement the SAFE programme. Programme management issues such as the lack of a robust workplan has led to delays in producing this package, which has had implications for quality and quality assurance. However, the final package was produced and published for others to access at programme closure. The final package was professional and highly visually engaging. Videos of each of the social empowerment sessions were also produced and will add significant value for future replication of the approach.

It is not yet clear whether other development actors will take up Toose and implement it in other contexts, although there remains significant interest. The shifts in the funding landscape are pertinent, for example, both Musasa and WFP’s plans to implement Toose in future iterations have been affected by USAID cuts. Nevertheless, there remain several potential opportunities with other partners that continue to be explored, including a partnership with a platinum mine.

Lessons learned through this output, and recommendations for future programming

At programme closure, results suggest strong value in replicating the Toose model, but that further adaptation may be needed to enhance its impact on IPV. The strong linkage between IPV and economic security also suggest that when Toose is implemented among highly vulnerable households, food assistance programming and enhancing economic stability is vital. Any future iterations would benefit from being slightly longer and having a rigorous analysis on the model’s impact on IPV levels (e.g. through a randomised control trial).

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The original business case value for the SAFE programme was £12m. Due to reductions in ODA spend from 0.7% of GDP to 0.5%, and the resulting cuts to FCDO programming, the business case value was reduced to £7.2m. This required changes to the programme design. The programme was extended in 2023 by 18 months and the value increased to £8.2m, to allow time for knowledge generation and to implement another cohort working closely with WFP. Changes in the programme’s value were very difficult for partners, and their success in re-designing the programme within new financial constraints has been impressive.

The cost of each element of the programme are outlined below. The elements of the programme have cost a consistent amount across different years of the programme lifecycle, and were broadly the same across districts. The cost of training peer facilitators is not included in the table below, given that it is not possible to get an accurate breakdown by facilitator. But the aggregate figure suggests this may have been higher than the business case benchmark, and further adaptations of SAFE should investigate whether using peer facilitators delivers the best value for money. In addition to the elements below, WFP provided a cash based transfer of $13 per person in a household every month to women SAFE participants in Chiredzi across all four cohorts. Feedback from programme partners and beneficiaries has suggested that the cash-based transfer has been critical to improving household economic security, a key element of the programme’s theory of change. Participants receiving the cash transfer were more likely to use loans from their TISALs on IGAs, rather than on purchasing food and household essentials similar to participants in other cohorts.

Element	Cost per Participant (approx.)			Business Case Benchmark
	Year 2	Year 3	Year 4
Setting up TISAL group	£53	£58	£58	£67
Training TISAL participants in Toose social empowerment curriculum	£61	£58	£59	£67
TISAL participants taking a loan	£66	£61	£56	£96
Setting up and supporting a GCBC	£26	£31	£7	£25
Survivor using GBV response service	£76	£39	£40	£106

The main cost driver throughout the programme has been direct programme activities. Staff costs were the second cost driver, followed by monitoring and evaluation. The programme has demonstrated good value for money throughout its life. Examples of the ‘5 Es’ include:
- Economy: programme partners used free venues to deliver curriculum sessions wherever possible; vehicles and journeys were shared between implementing partners.
- Efficiency: multiple activities were often delivered in one day, reducing the overall costs of field visits; food and workshop materials were purchased in bulk to reduce cost per item.
- Effectiveness: the programme had multiple positive impacts in communities, including improved family wellbeing and better quality of life.
- Equity: ‘Leave No-One Behind’ has been a core focus for the programme, and it has performed strongly on disability inclusion in particular.
- Overall cost effectiveness: cost per participant has not been calculated, but rough estimates suggest that SAFE does not cost significantly more than other comparable GBV interventions. Spend on this programme has contributed to the FCDO’s development priority, and has directly supported women and girls.

E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The programme’s risk rating has mostly remained moderate throughout its life, and was moderate in the past year. Programme partners have regularly reviewed and updated a shared risk register, and monthly working group meetings included discussion on risks. FCDO has maintained a separate risk register for the programme, which was reviewed and updated at least once per quarter.

Risks associated with contextual challenges have been significant throughout the programme lifecycle. Drought and extreme weather, and the impacts on both programme delivery and on beneficiaries, has been a continuous risk throughout the programme. Similarly, risks around partner coordination and engagement have been common throughout the programme, particularly in the final year when a new partnership agreement with WFP went into place. In the last year, the programme identified several new risks relating to sustainability and responsible exit, reflective of the programme lifecycle. These risks have been effectively managed by the programme team and have now been downgraded.

The management of risks around fraud and safeguarding is a concern in SAFE’s risk management. The programme has reported no instances of fraud and only one issue of safeguarding- which was not directly related to the programme. It is generally accepted within the management of ODA programmes that fraud and safeguarding issues will occur at some stage, and partners are encouraged to be open with FCDO about these instances. Whilst the lack of issues reported in the SAFE programme may be initially seen as a positive, it may reflect issues in programme partner’s approach to identifying and managing fraud and safeguarding risks. This should be carefully considered in future programming.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

The SAFE programme involved two commercial contracts: one with Ecorys, and one with Tetra Tech. Both partners overall delivered the programme effectively, and all KPIs have been met. Despite significant contextual challenges, all elements of SAFE were delivered, mostly on time and within budget. Economy and efficiency were considered throughout the programme, though the focus on VfM on the part of consortium leads could have been improved. FCDO managed the programme well overall, though staffing changes were challenging.

The consortia broadly worked well together throughout the lifespan of the programme, although there were some challenges both within and between consortia, particularly given staff were not always based in-country. Contributions from different partners may not have been equally valued, and the role of technical inputs appeared at times to have been undervalued and potentially under-utilised. Similarly, the importance of evaluation and the role of the ELU was at times dismissed, which impacted the programme’s ability to learn and adapt according to the evidence coming out of implementation. However, these observations must be nuanced by the budget and timeline constraints which at times prevented full implementation of international best practice, and also the importance of ground realities to feasibly implementing all learning. There was also room for optimising the sequencing of evaluative activities and implementation, and this remains a lesson for the FCDO. Better working relationships may also have been facilitated through increased in-country presence of staff working on the ELU and technical team. In future iterations of similar programmes, FCDO should be very mindful of its role in relationship management.

Tetra Tech have been an effective partner throughout the life of the programme. Reporting was submitted on time throughout the life of the programme, and Tetra Tech were able to respond promptly and in detail to questions from FCDO. However, this efficient programme management may at times have resulted in too narrow a focus on agreed deliverables which limited the opportunity for the ELU to genuinely impact the overall programme direction.

Ecorys have delivered the programme effectively, however, there have been some programme management issues. Ecorys and SAFE-C have not always produced detailed workplans, which in some cases led to key programme materials being delayed or produced to insufficient quality. However, it must be noted that this was an adaptive programme, and regular changing demands along with contextual changes added to the programme management challenges. Staff changes at both FCDO and Ecorys played a significant role in programme management issues. The loss of institutional memory was a problem throughout the programme. For future programmes, FCDO should prioritise the SRO role and ensure as much continuity as possible in the programme team.

In its final few years of operation, SAFE partnered with the Zimbabwe Humanitarian and Resilience Programme (ZHARP), an FCDO-funded humanitarian programme delivering cash and vouchers to food insecure households in urban areas. This partnership was governed by a Letter of Agreement between FCDO and WFP, which largely worked effectively. Relationships and programme management with WFP have been mostly positive, although WFP does not have the same reporting requirements as other partners, which makes it challenging for the FCDO to fully track detailed spend.

Programme-level approach to monitoring and evaluation

SAFE has conducted extensive monitoring and evaluation throughout its life, as summarised in Figure 1 below. The SAFE-C team carried out regular field visits to engage with implementing partners, beneficiaries, and stakeholders throughout the life of the programme. This included conducting learning workshops with local partners and beneficiaries following the completion of each cohort. These have been complemented by visits from FCDO where appropriate.

The SAFE methodology has been evaluated throughout by the ELU team, whose role has focused on producing learning from the programme. This has been effective, and the programme has produced a large body of evidence on both the drivers of GBV in Zimbabwe, and on lessons learned from SAFE. This evidence will make a significant contribution to the global evidence base. The impact of the ELU’s work has been somewhat constrained by the lack of funding to undertake a full baseline and endline evaluation. Both the baseline and the endline were only conducted for the first two cohorts, and without a control group, making it difficult to fully evaluate the impact of the programme as a whole. This should be considered in future programming, and funding should be included for a full baseline and endline, ideally including a control community.

SAFE has adopted an iterative approach to programme management throughout its lifecycle, embedding evaluation into its core operations. Between each cohort, programme partners in the consortium engaged in extensive learning and adaptation conversations to discuss what worked and what didn’t. Based on this learning, the programme made changes to the design of the intervention for the next cohort. This iterative approach was highly valued by programme partners, and has played a key role in the generation of evidence from the programme.

Figure 1: SAFE Learning and Evaluation over Programme Lifecycle

Date of last narrative financial report		Date of last audited annual statement