Programme Completion Review

Title: Strengthening Malawi’s Education System (SMES)
Final Programme Spend £ (full life): £49,300,988.91	Review Date:	30 September 2025
Programme Code: 300075	Start Date: / 18/07/2018	End Date: / 30/06/2025

Summary of Programme Performance

Year	2019	2020	2021	2022	2023	2024
Programme Score	A	A	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Major	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	DevTracker Programme GB-GOV-1-300075 Documents
DevTracker Links to all logframes used during programme lifetime:	DevTracker Programme GB-GOV-1-300075 Documents

List of Acronyms

BHC – British High Commission
CAMFED – Campaign for Female Education
CPD – Continuing Professional Development
DQAS – Directorate for Quality Assurance and Standards
DTED – Directorate of Teacher Education and Development
EMIS – Education Management Information System
EYOS – Equivalent Years of Schooling
FCDO – Foreign Commonwealth and Development Office
GESD – Governance to Enable Service Delivery
GPE – Global Partnership for Education
LAYS – Learning Adjusted Years of Schooling
LGAP – Local Governance Accountability Programme
MIE – The Malawi Institute of Education
MoE – Ministry of Education
M&E – Monitoring and Evaluation
NMCRP – National Mathematics Curriculum Reform Programme
PbR – Payment by Results
SMES – Strengthening Malawi’s Education System
TLC – Teacher Learning Circle
TLMs – Teaching and Learning Materials
VfM – Value for Money

A. Summary and Overview

Description of the programme and what it has achieved

The Strengthening Malawi’s Education Systems (SMES) programme was a seven-year UK-funded intervention (2018–2025) aimed at improving foundational learning outcomes in Malawi, particularly early-grade mathematics, and strengthening’ education governance. Its most significant achievement was the design, piloting, and national scale-up of the National Mathematics Curriculum Reform Programme (NMCRP, formerly National Numeracy Programme), a structured pedagogy reform that introduced a new national curriculum, teacher training and learner workbooks for all children in Standards (Grades) 1-4. This component has been shown to be one of the most effective early numeracy reforms delivered at-scale in a developing country context with the potential to more than double the number of 10-year-olds with basic maths skills in Malawi.

Programme components
SMES was built on three core pillars: strengthened governance, quality, and equity. In its early years, the programme focused on governance and equity through investments in USAID’s Local Governance Accountability Programme (LGAP, £12m) and support for marginalised girls through CAMFED (£7m). LGAP worked directly with district level councils and staff to facilitate the implementation of Malawi’s decentralisation agenda, with the aim to help districts improve education delivery with existing resources. CAMFED reached over 23,000 girls with a tailored package of materials and financial support, and mentored more than half a million children to encourage primary school completion and transition to secondary. From 2022 onward, the governance pillar continued with a small strategic investment (£1.2m) into the World Bank Governance to Enabling Services Delivery (GESD) programme, a pay for performance programme that rewards districts for results in service delivery including education. SMES’ overall focus however shifted toward improving learning outcomes, with over £25 million invested in the NMCRP—representing more than half of SMES’s total budget and 90% of spending in the final three years. The NMCRP will therefore be the focus of this Programme Completion Review (PCR).

Programme achievements
The programme met or exceeded most of the output targets, with measurable achievements in outcomes. By 2025, nearly 3 million children have been reached with the new mathematics curriculum, formally adopted by the Ministry of Education (MoE). An independent impact evaluation found that one year of exposure to the NMCRP equated to 1.5 years of learning under the previous curriculum, and the intervention can thus be categorised as a “mega buy” in terms of cost-effectiveness, as per the original DFID Best Buys paper (see section D for details).

The mentorship programme implemented through CAMFED’s mentorship model was scaled by the Global Partnership for Education (GPE) to half of the country. The governance support strengthened district governance of education, for example through an HR audit that identified ghost teachers (LGAP), and Payment by Results (PbR) incentives aligned with the key governance and accountability bottlenecks (GESD). The British High Commission (BHC) played a key role in convening partners and aligning efforts, a contribution that was widely recognised.

These results were achieved despite a challenging operating context marked by macroeconomic instability, COVID, high inflation, ODA reductions and climate shocks, including cyclones and droughts that disrupted schooling and exacerbated food insecurity. The programme laid a strong foundation for a proposed second phase focused on institutionalising the maths reform and deepening impact. Reductions in UK ODA funding mean that this next phase should focus on building off this strong foundation and using UK technical capacity to achieve a sustainable impact that does not require long-term funding. This PCR captures key lessons and recommendations to guide that shift.

Major lessons learned, evidence generated and recommendations

Technical expertise alone is not enough. The programme provided deep technical expertise in mathematics from top experts in both Malawi and the UK. However, the NMRCP succeeded not only because of its structured pedagogy design (a Great Buy), but because it was aligned with MoE priorities, with strong MoE ownership, and supported by a coalition of partners working under a shared vision. The BHC’s role as a trusted convener helped ensure reforms were locally owned and not externally imposed. With champions across departments, including the Directorate for Quality Assurance and Standards (DQAS), the Directorate for Teacher Education and Development (DTED) and the Malawi Institute for Development (MIE – the parastatal curriculum development centre), the buy-in is likely to withstand changes in Government.
[note] GEEAP, 2023, Cost-effective approaches to improving global learning.

Pull not push – the power of incentive-driven reform. Support to the GESD programme showed that when district and national systems are incentivised to focus on learning outcomes, progress is possible. The GESD focused on improving the efficiency of domestic financing at district level and helped lay the groundwork for the World Bank’s PbR programme and for the GPE domestic financing triggers. However, aligning incentives across different levels of government is complex and requires sustained engagement to maintain momentum.

Focused reform can catalyse broader system change. The NMCRP showed that a focused reform—anchored in one subject—can catalyse broader system change. Mathematics became a practical entry point for demonstrating how the education system could function more effectively.

Inclusive education requires complementary investments The evaluation showed that learning gains were concentrated among less disadvantaged learners. Children from the poorest households, often absent due to hunger or other barriers, saw limited gains. Interestingly, numeracy gains were stronger for students in Standards 3 and 4, suggesting that the programme disproportionately helped students with stronger baseline skills. This underscores that quality-focused reforms alone won’t reach all learners without also addressing barriers to access and equity.

True transformation takes time. Teachers are still adjusting to the new curriculum and need ongoing support to become fully confident and deliver effectively. Encouragingly, other funders—including the Prevail Foundation and GPE—have, with FCDO support, committed to supporting evidence-based continuous professional development (CPD) for teachers, helping sustain momentum and deepen impact.

Sustainable reform requires further investments. To ensure institutionalisation of the reform, further support is required to help the Government transition from single-use workbooks to standard textbooks that can be sustained and are more affordable. The Government is keen to make the transition considering reduced donor funding to the sector, and FCDO’s second phase of support will be critical to ensure the transition is evidence based and that other challenges to maximise reform impact (e.g. CPD see section C) are addressed through GPE funding and other donor and partner support.

Key recommendations:
As FCDO transitions from financing service delivery to providing strategic technical assistance for systems reform, the following recommendations should guide future engagement:

1. Support an evidence-based transition to a more affordable approach. This includes supporting the transition from single-use workbooks to standard textbooks that can be sustained by the Government. Continued engagement, informed by political economy analysis, will be essential to ensure the continued institutionalisation of the mathematics reform.
2. Promote sustainability through co-financing models. The Ministry of Education should be supported to blend domestic, multilateral, and philanthropic resources to maintain momentum and reduce reliance on external funding in the future.
3. Continue catalytic support for results-based systems. Strengthening governance and accountability at the district level remains critical but requires long-term commitment and engagement to embed these approaches effectively.
4. Maintain UK technical engagement in foundational learning. Even with reductions to 0.3 of ODA, the UK can continue to play a strategic role through targeted technical assistance and UK expertise. This should include remedial approaches that help students who fall behind as well as supporting a consistent approach to student assessments.
5. Explore opportunities to leverage climate finance. Malawi should seek catalytic support to access Global Climate Fund (GCF) resources to build climate resilience within the education system.
6. Strengthen national capacity for planning and delivery. Given the challenges around EMIS data accuracy and the untested capacity of national systems to lead large-scale printing and distribution, targeted technical assistance in planning, budgeting, and logistics could help ensure long-term sustainability of reforms.

How this report was conducted

This PCR was prepared by the BHC education team in Lilongwe, drawing on the programme’s Annual Reviews from 2021 to 2024, implementer reports, MoE reports, the programme logframe, and the business case for the proposed follow-on programme. The team also reviewed the independent impact evaluation of the NMRCP.

The review process involved triangulating internal assessments with external evidence and feedback from key stakeholders, including the MoE, implementing partners, and other development partners. The analysis was informed by regular monitoring data, field visits, and structured reflections on lessons learned.

Actions following approval of this report

Following approval of this report, the team will complete final financial reconciliations and asset disposal in line with standard procedures.

Looking ahead, the BHC will continue to engage closely with the MoE and key partners to ensure that upcoming investments—particularly from the Prevail Foundation and GPE— can build on the NMRCP foundations. This includes ensuring coherence in CPD for teachers, alignment with the broader curriculum reform (including pre-primary), and avoiding the risk of parallel or conflicting messages reaching schools.

The BHC education adviser will continue to support the MoE in implementing the recommendations outlined in this report, including efforts to develop sustainable co-financing models that blend domestic resources, multilateral funding, and a gradual transition to a less resource-intensive phase of the reform.

B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£37.5 million	£49.3 million
Timeframe	2018-2024	2018-2025
Outcomes	Outcome statement did not change: Improved service delivery that ensures more girls and boys – especially from disadvantaged backgrounds – progress through and complete primary school with measurable improvements in learning outcomes. / Starting Point Final Result (and Indicator Change) / % of children in lower primary with improved maths scores Baseline (2016): 37% (Std 4, Malawi Longitudinal School Survey (MLSS) data); Initial target: move from 37% to 41% Indicator changed: Shifted from MLSS survey to ad-hoc rigorous impact evaluations due end of MLSS as a representative survey and need for stronger attribution to FCDO-funded National Numeracy. / Final Result: Impact evaluation showed gains of 0.2–0.3 standard deviations (SD) in average learning outcomes in pilot phase; 0.19 SD in final phase—while the latter is slightly below target (ranging 0.2-0.32 across Stds 1-4), it is equivalent to half a year of additional learning. / % of girls with improved scores in CAMFED-supported districts Baseline (2020): 73% pass primary exam (first year of available data); Target: any improvement. Indicator unchanged until 2022 when it closed / Final Result: 76% in 2021, 78% in 2022. Component closed after 2022, but improvements likely reflect broader systemic trends. Disadvantaged girls still had low pass rates (e.g., 35% in Chikwawa). / % of children reaching Std 4 and 8 without repeating Baseline: 32% (Std 4), 10% (Std 8) based on MLSS survey Indicator changed: MLSS discontinued; replaced with EMIS-based survival and repetition rates to ensure data reliability. / Final Result: Survival to Std 5: 70% (up from 61% in 2020) Survival to Std 8: 40% (up from 36%) Repetition rates (S1–S4): Increased slightly from 2020 to 2024 but still over 30% in Std 1. / Big picture of high repetition rates and drop-outs in lower primary remain unchanged. / Local Authority Performance Scores Baseline (2018): Composite District Capacity Index = 129 Final Result: Index rose to 151 by 2022 (target 157). When support shifted to the World Bank, the indicator changed to "% of districts improving education service delivery in Local Authority Performance Assessment": 2022: 41% → 2023: 36% → 2024: 80% (target 50%)

Overall assessment of programme outcomes, sustainability and VfM

SMES scored an A in all Annual Reviews and achieved significant strategic wins at the outcome level. The NMCRP is one of the most effective early numeracy at-scale reforms in Low- and Middle-Income Countries (LMICs). An independent impact evaluation found that one year of exposure to the NMCRP was equivalent to 1.5 years of learning under the previous curriculum. While transparent costing is hard to find in other evaluations, limiting cost-effectiveness comparisons, the NMCRP meets UK Best Buys description of a “mega-buy” (see section D).

Going forward, the average cost of the intervention will continue to decrease. The only recurrent costs are the workbooks (printing and delivery estimated at £2.2m per year in direct costs – approximately 0.36% of the education budget) and the training of the new teachers entering the system. Instead of training new teachers every year through a centralised model, the MoE has opted for investing in high quality CPD for all teachers through decentralised modalities. This will be system-wide and likely to attract co-funding from World Bank, GPE and the Prevail Fund, a private foundation interested in multiplying the impact of the NMRCP. The cost of the workbooks will also be reduced as MoE transitions to a more sustainable textbook model. Nonetheless, risks remain regarding the Government’s ability to absorb the cost in its domestic budget.

The investment in CPD is likely to multiply the impact of the programme. While teachers are implementing the curriculum, they are currently doing so mechanically and need to build further confidence in some of the new material and ways of teaching it (see discussion on 4.1 output). Continued BHC engagement will however be critical for sustainability of the reform.

For the governance and equity pillars, SMES did not fully achieve the transformative scope envisioned in the theory of change (ToC). Please refer to the section below and the 2021-2024 Annual Reviews for further details on these components.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators

The original ToC is outlined in the graph below and the yellow textboxes more accurately describe what was achieved at the intermediate outcomes level. In part, this is a scale and depth issue: the CAMFED investment (£7m over three years), for example, was unlikely to cause an entire education system to be more equitable. COVID hit the most disadvantaged girls the hardest, and the targeted support helped these girls to not fall further behind as opposed to being truly transformative and leading to system-level outcomes.

In terms of governance, the LGAP created helpful infrastructure for improving efficiency and saw notable improvements in human resource management at district level (timely payroll processing, needs-based teacher redeployment and identification of ghost teachers). However, the LGAP was not sufficiently rooted in the political economy of incentives and at times pushed technical solutions on grounds that were not ready, for example, setting up a performance system for teachers that was not used, and hence prevented outputs from translating into outcomes.

The GESD investments led to e.g. improved documentation at district level, particularly maintenance of up to-date and complete teacher deployment schedule, teacher allocation, and availability of a head teacher in all schools. Notably, the GESD had to start with the very foundations of governance before shifting to service delivery: districts were not keeping the paperwork necessary to conduct an audit, and only now the basic public financial management is mature enough to shift attention to better service delivery in education and health. A lack of clear lines of accountability between districts and national level has also prevented fully effective teacher management and has resulted in limited monitoring of teacher attendance, conduct, or equitable distribution within districts.

But there are also successes: refocusing NMRCP allowed for the depth and scale needed for system-wide impact. The results financing from the World Bank was designed with support from a small BHC technical investment, which improved efficiency of this $100m investment and thus helped lay the foundations for more efficient service delivery, utilising political economy to create incentives.

Theory of Change for SMES- with 2025 updates in yellow
C
Malawian citizens have the foundations and skills to fulfil their potential and contribute towards national development
Improved service delivery that ensures more girls and boys – especially from disadvantaged backgrounds – progress through and complete primary school with measurable improvements in learning outcomes
Improved teaching of core foundation subjects
World Bank with more capacity to improve school-based management and use results based financing to improve service delivery

Districts with the financial and human resource capacity to manage service delivery (including education), holding service providers to account
Strengthening public services
- Capacity building districts
- Additional resources (people, scoping) to strengthen World Bank support to the Malawi Government
- Research

Reaching the marginalised
What
CAMFED’s learner guides to support girls complete primary school and transition to secondary

Improving quality of teaching
What
Technical assistance to government agencies including curriculum, standards, teacher education, basic education unit on numeracy and remedial education

Outputs
Int. outcomes
C
C

C

C
C

C

Impact
strong
limited
weak
Evidence
Targeted support to disadvantaged girls to complete primary and transition to secondary
Equitable education system that supports marginalised girls
Inputs
Teachers and schools supported to deliver quality numeracy instruction at the right level in lower primary school
Improved effectiveness of national reforms
Better education data available on quality and efficiency of school system to inform planning, target setting and policy

Mathematics component theory of change

Outcome

More accurately: improving quality of teaching and learning in mathematics
More accurately: mitigated negative impacts of COVID on most vulnerable girls and communities.
More accurately: set up conditions for better efficiency and accountability of districts
More accurately: improved teaching of mathematics foundations
The mathematics component’s ToC is shown below. This was largely achieved with three caveats: 1) not all children are learning from this new curriculum. The most vulnerable are not benefitting enough, likely due to initial disadvantages that prevent them from attending or learning. Complimentary investments through the SCALE CMP will partly address this by supporting remediation approaches to ensure all learners can catch up. 2) The transformation has not yet reached its full potential and effective CPD will help teachers to teach better. 3) Systemic challenges such as student absenteeism and large class sizes may continue to impact both teaching and learning.

## C: Detailed Output Assessment

This PCR focuses on those outputs active in the last year of the programme as set out in the table below:

Output #	Output name	Status	Weighting in final year
Output 4.1	Teacher Training (National Numeracy Reform)	Concluded in July 2025	33%
Output 4.2	Teaching and Learning Materials (National Numeracy Reform)		33%
Output 4.3	Institutionalisation and Embedding in government systems (National Numeracy Reform)		34%

A summary of closed outputs is provided below. Please see previous Annual Reviews for further details.

Output	Output name	Status	Output summary
Output 1	Districts with the financial and human resource capacity to manage service delivery (including education), holding service providers to account	Closed Nov 2024.	Governance support was initially channelled through the larger Local Government Accountability Programme, which delivered mixed results. Technical assistance support was then provided to the World Bank’s Governance to Enable Service Delivery project. This has shown promising results and is now continued through a separate governance programme.
Output 2	Higher quality and more politically informed WB programming on service delivery	Closed in 2022
Output 3	Better education data available on quality and efficiency of school system to inform planning, target setting and policy	Closed in 2022	This component had some success in informing the design of World Bank education programming, but was otherwise limited in is impact.
Output 5	More disadvantaged girls complete primary and transition to secondary	Closed in 2022	Although successful, the cost of this intervention was high and justified on equity grounds. The context of COVID and climate shocks meant that drop-outs increased during this period, reducing the impact. The mentoring aspect of this has been picked up to be funded by the Global Partnership for Education.

Output Number and Title	Output 4.1 Teacher Training (National Numeracy Reform)
Output Score	A+
Impact weighting (%)	33%		Impact weighting revised since last AR?	Yes, up 3 percentage points

Output Indicator	Starting Target	Final Logframe Target		Final Result Achieved
4.1a Improvement in teachers’ effectiveness	(August 2020) / Development underway for: (i) revised curriculum outline; (ii) revised S1-4 T&L materials; (iii) teacher training methodology approaches for piloting;	1. In 75% of classroom observations, teachers are using the workbook and most students have a workbook / 2. 50% of observed mathematics lessons where teachers demonstrate partially effective or effective quality of numeracy teaching. / 3. 50% of observed lessons with satisfactory or effective quality of learning.		1. In 98% of classroom observations, teachers are using the workbook and most students have a workbook / 2. 71% of observed mathematics lessons where teachers demonstrate partially effective or effective quality of numeracy teaching / 3. 75% of observed lessons with satisfactory or effective quality of learning.
4.1b / TLC frequency and attendance	(August 2022) / 80% (160/200) schools in the pilot phase	60% of government primary schools in Malawi conduct 1 TLC per month on numeracy (based on sample), attended by 70% of target teachers.		66% of government primary schools in Malawi conduct 1 TLC per month on numeracy (based on sample), attended by 70% of target teachers.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score

Teacher training under the NMCRP has evolved from a programme-led initiative into a MoE-led reform, with training now fully embedded within MoE structures. The MoE has led the national rollout of the revised mathematics curriculum, with over 30,000 teachers trained in the final year alone. The programme exceeded its logframe targets: 98% of observed classrooms showed workbook use, 71% demonstrated effective teaching, and 75% showed satisfactory learning quality. Teacher Learning Circle (TLC - school-based CPD sessions) implementation also surpassed expectations, with 66% of schools conducting monthly sessions attended by 70% of teachers.

The programme’s adaptive approach responded to both technical and logistical challenges. The model shifted from cascade training (delivery through layers of trainers) to zonal-level delivery for all teachers, based on feedback from the field. Face-to-face training was prioritised over peer-led TLCs to ensure quality and consistency. The programme also addressed pedagogical gaps, moving beyond content delivery to focus on how teachers teach—emphasising modelling, practice, and conceptual understanding. Innovations from the ground were embraced, notably the evolution of master trainers into mentors and coaches, demonstrating how system actors can drive change when empowered.

The programme has built substantial capacity within the education system. Over 450 master trainers have been trained, with many receiving 9 to 25 days of training and at least 7 weeks of practical experience. These trainers are now embedded in over a third of Malawi’s zones and have become a valuable resource, each reaching about 80 teachers (total of 36,000 teachers in S1-4). Their expertise is being leveraged to support CPD activities to strengthen teaching capacity across Malawi, and they will be integrated into the forthcoming GPE CPD component.

Lessons learned through this output, and recommendations for future programming

While teachers are consistently using the new curriculum, many still struggle to adapt instruction to learner needs or foster conceptual understanding. These insights have directly informed the design of the next phase of CPD (funded by other partners), which will focus on improving pedagogical depth and supporting teachers through coaching.

The NMCRP has demonstrated that large-scale, system-led reform is possible with government ownership and targeted technical assistance. A key lesson is that sustainable change requires time, iteration, and deep alignment with institutional processes to build national capacity and legitimacy. The emergence of master trainers as mentors and CPD leaders, and the MoE’s integration of these roles into future GPE-funded CPD structures, reflects the institutionalisation of this expertise within the system. Any future support should focus on consolidating the reform across all parts of the system, including strengthening school-based CPD and aligning pre-service training with the revised curriculum.

Output Number and Title		Output 4.2 Teacher and Learning Materials (National Numeracy Reform)
Output Score		A
Impact weighting (%)		33%		Impact weighting revised since last AR?		Yes, up 3 percentage points

Output Indicator	Starting Target		Final Logframe Target		Final Result Achieved
4.2a / Materials printed, distributed and endorsed by the MoE	(August 2022) / 2,000 teacher guides and 453,000 learner workbooks printed and distributed to the 200 schools in the pilot during the 2022 school year (approx. 151,000 per school term)		All children have books for S1 and S2 for all 3 terms in the 24/25 academic year		Distribution compared to learner numbers: / Number of learners Enrolment based on EMIS 24/25 data # books distributed (avg/ term) Difference / Std 1 1,084,540 1,088,183 3,643 / Std 2 869,587 889,925 20,338 / 7,270,800 workbooks and 91,539 teacher guides delivered for Standards 1-4.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score

The programme successfully delivered over 7.3 million learner workbooks for the 2025/26 school year to all government primary schools. Monitoring by MoE officials showed that in 98% of classrooms and the majority of children had access to a workbook during unannounced visits, demonstrating good retention of books.

The workbooks underwent significant revisions, starting with Standard 1 in 2022, based on feedback from teachers, parents, and MoE officials. Led by the Malawi Institute of Education (MIE), with support from White Rose and Cambridge Education, the materials were simplified, better structured according to latest pedagogical research, and reviewed for inclusivity. Revised versions for Standards 2–4 were completed by March 2025, and a syllabus overview for Standards 5–8 was finalised in May.
[note] A UK organisation leading in early maths and supporting the implementation of the UK curriculum in the large majority of UK state schools

Printing and distribution processes were refined to improve cost-efficiency and reliability. Enhancements included colour printing, durable binding, plastic sleeves, and large-print versions for visually impaired learners. After testing multiple distribution models (e.g. MoE Supplies Unit, Track and Trace system, district-led distribution), a private provider was found to be the most reliable and cost-effective.

To support a wider national reform, the programme shifted from a project-led count of enrolled children to an EMIS-based approach for planning workbook distribution. Over two years, the MoE and Cambridge Education collaborated to use EMIS census data—adjusted for population growth and verified in a sample district—to estimate enrolments. This marked a major improvement from previous methods, which relied on headteachers who often over-reported to receive more books. For 2025/26, the approach was refined further by applying district-specific growth rates instead of a flat national adjustment, reflecting regional variations.

Lessons learned through this output, and recommendations for future programming

Key challenges included workbook loss or damage and instances of materials being sold to private schools by head teachers and PEAs. These were addressed by marking free versions clearly “Not for Sale”, improving access to legal private-market editions via a WhatsApp catalogue, and strengthening accountability with MoE and MIE.

The endline survey showed that almost all teachers utilised the teacher guides and learner workbooks to guide lesson delivery. However, an audit of student workbooks highlighted that not all of the workbook content was actively utilised, indicating that some topics may not have been covered.
[note] The endline noted that 95% of observed teachers used the workbooks during the lesson.

As discussed under the teacher training section, the teacher guide could be improved to better support teachers. There is a delicate balance between ensuring clarity/simplicity versus sufficient detail on what an effective lesson looks like. If funding allows, revising the teacher guides to add further detail on good pedagogy may support a transition away from traditional and less effective teaching approaches, such as chanting and memorisation.

MoE has also shown strong ownership over the workbooks, but transitioning to more sustainable learner resources, such as textbooks, should be explored as a core part of the next phase of FCDO support. There is significant MoE interest in this, including a swift transition to textbooks as broader donor funding to education is decreasing. FCDO should work closely with MoE to ensure options are rigorously tested and effective, help identify resources to cater for the requirements and build consensus on the way forward.

The EMIS-based planning model has proven effective, though gaps remain in national capacity for printing and distribution. Strategic technical assistance could help MoE strengthen planning, budgeting, and logistics for future scale-up.

Output Title		Output 4.3 Institutionalisation and embedding in government systems
Output Score		A
Impact weighting (%)		34%	Impact weighting revised since last AR?		Yes, up 4 percentage points

Output Indicator	Starting Target		Final Logframe Target	Final Result Achieved
4.3a / Sustainability plan is implemented	(August 2023) / Sustainability plan is endorsed by MoE and FCDO		7 priority actions on the sustainability plan are complete	Completed: / Priority Action 1: EMIS-based identification of books to print tested and lessons disseminated / Priority Action 2: Standards 5 – 8 numeracy syllabus outline complete / Priority Action 3: Standards 3 and 4 numeracy curriculum approved by MoE / Priority Action 4: Cadre of experts to champion reforms and act as resource established / Priority Action 5: PEAs trained on monitoring tools and school support approach / Priority Action 6: District and central MoE oriented on accessing and using data platform / Priority Action 7: PEA monitoring approach and system endorsed by DQAS
4.4b / Evidence that programme is adapting	(August 2023) / Evaluations and research outputs collected and published online.		Final report on institutionalisation and embedding in MoE systems complete	Report completed and submitted to FCDO in June 2025

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score

Although institutionalisation was initially treated as a separate workstream, it ultimately became integral to the overall reform approach. The programme began with plans to revise the curriculum, pilot it for a year, scale up the next, and then hand over to the Government. By year two, this timeline proved unrealistic for genuine systems strengthening. A more gradual, embedded approach was adopted in 2022, expanding the pilot from 200 to 1,111 schools (20% of government schools), with full national rollout planned for 2024/25. Stakeholder buy-in was strong, and the reform was widely seen as ready for scale-up. The MIE praised the teacher guides and learner workbooks as among the best produced in the country. In May 2025, the Minister of Education referred to the mathematics reform as the “first born child” of the broader curriculum review.

A major achievement was the introduction of real-time data capture. The NMRPC piloted a dashboard now adopted and hosted by the MoE. Primary Education Advisors (PEAs) collect data on attendance, materials, teaching quality, and learner progress. District Education Officers review this data termly to inform actions. Initiated at MoE’s request for improved accountability, the dashboard was co-designed and scaled nationally after a successful three-month trial. By March 2025, data was available for two-thirds of schools (n=3,968), achieved without extra funding, devices, or incentives for PEAs.

Challenges remain: the dashboard needs better integration into government ICT systems, and PEAs require further training for effective classroom observation. Non-monetary incentives and district-level accountability also need strengthening. The MoE has included these needs—ICT upgrades, PEA training, simplified observation tools, and motorbikes—in the CPD component of the GPE grant, which FCDO helped ensure through support to shape the GPE Partnership Compact and grant application. Districts with low submission rates are being followed up, while compliant PEAs are being recognised.

Lessons learned through this output, and recommendations for future programming

The dashboard originated from a concept note by the MoE’s Department for Quality Assurance and Standards, with collaborative support from BHC and Cambridge Education. The programme’s success stemmed from adaptive, responsive collaboration, even if it meant compromising on data depth for sustainability.

CPD is central to institutionalising reform. Continued collaboration with partners like Prevail and the World Bank/GPE is essential and the UK should utilise its influence to promote technically sound and politically feasible approaches.
While a sustainability challenge, workbooks were crucial for guiding teachers through the transition. At £2m/year, they are cost-effective but not affordable for the MoE. The BHC had planned a second phase of support to ensure an evidence-based transition to a more sustainable textbook approach. Going forward the Education Adviser should explore BHC or partner-funded research-backed pathways for this transition.

D: Value for Money

VfM performance compared to the original VfM proposition in the business case

The original VfM proposition in the business case was centred around the costs and benefits of improving learning outcomes, strengthening local capacity and accountability and providing targeted support to disadvantaged girls. Key metrics were Progress against log frame output indicators relative to budget performance, Cost per teacher trained and Savings at local council level due to LGAP activities. While some indicators changed (e.g. LGAP indicators due to closure of LGAP), SMES performed well across VfM metrics. In terms of Equity, benefits were expected to disproportionately accrue to marginalised groups in society, including girls, women and people living with disabilities. As noted in sections A and B, for NMRCP this did not hold true. Please refer back to section B for changes to the original ToC.

This section outlines VfM performance of NMRCP, please refer to the 2022 Annual Review for detailed VfM analysis of the support to CAMFED, the 2021 Annual Review and the Malawi Local Government Accountability and Performance Final Report 2023 for VfM assessment of the LGAP and the 2023-2024 Annual Reviews and the Final Synthesis Report – Local Authority Performance Assessment 2022/2023 for GESD.
[note] The report states that “LGAP demonstrates VfM by way of improvement in almost all LGAP VfM indicators”, p.89.

Effectiveness
As noted in section B, the NMCRP is one of the most effective early numeracy at-scale reforms in LMICs. According to the endline evaluation, students in treatment schools showed a 0.19 standard deviation improvement in overall numeracy—equivalent to 0.56 Malawi Equivalent Years of Schooling (EYOS) and 0.25 Learning Adjusted Years of Schooling (LAYS). In other words, one year of exposure to the NMCRP is equivalent to 1.5 years of learning under the previous curriculum. Teaching quality also improved significantly, with an 18% increase over the control group in a composite index of instructional practices (0.12 increase on a 0–1 scale).

The Best Buys paper describes “Mega-buys” as “programmes that can provide as much learning as would be achieved from 1 year in the highest quality education systems (one Learning Adjusted Year of Schooling or LAYS) for as little as £0.2-£20”. The impact evaluation found that the programme delivered on average 0.25 LAYS for £5. This means that £20 can deliver 1 LAYS, hence enough to be categorised as a “mega buy” category of cost-effectiveness.

Efficiency
1. Teacher Training: The programme developed a strong teacher training model that emphasises effective lesson delivery. In 2024/25, over 25,000 Standard 1 and 2 teachers received seven days of face-to-face training, delivered before each term to align with new curriculum materials. This was made possible through co-created training content, strategic planning by national trainers, and a well-supported cadre of master trainers.
2. Fidelity of Implementation: Between November and May 2025, 98% of observed lessons showed fidelity—teachers using workbooks and most students having access to books. Student usage of books still presents a challenge and the endline noted that on average 51% of pages had all exercises attempted, suggesting only a slight majority of workbook content was being actively utilised.
3. Quality of Teaching: By 2025, 71% of observed mathematics lessons demonstrated partially or fully effective numeracy instruction, based on system-generated data. While data collection methods evolved across Annual Reviews—due to refinements in indicator tracking and the shift from programme-led to system-led processes—the 2025 results compare well with previous pilot data (61% and 70%). This consistency suggests the programme maintained high teaching standards even as it scaled, avoiding the typical “voltage drop” in quality that often accompanies reduced oversight.
4. Teacher Learning Circles (TLCs): In 2025, 66% of government primary schools held monthly numeracy-focused TLCs, with 70% of target teachers participating—based on sample data. This was achieved despite limited investment: only 1.5 days of training for school managers and a manual were provided. In contrast, the 2024 target was less ambitious (two TLCs per term) and relied solely on prior training from 2023. The strong uptake and consistent implementation reflect the programme’s success in fostering intrinsic motivation among school leaders and teachers, enabling sustained professional development with minimal external support.
5. Systems strengthening: The approaches and practices have been embedded in the education system, leaving a legacy of improved system efficiency.

Economy
The cost per teacher per training day steadily declined from £35.09 in 2021 to £15.97 in 2024, with a slight increase forecasted to £19.17 in 2024/25 due to revised Daily Subsistence Allowance (DSA) rates. This downward trend was driven by:
- Streamlining the training model: shifting from a cascade approach (delivery through layers of trainers) to zone-based delivery by Master Trainers.
- Reducing face-to-face training days from 15 in 2021 to 9 in 2024.
- Improved planning and execution.
- Achieving economies of scale: numbers of teachers trained rose from 1,850 in 2021 to 26,487 in 2024.
- Strategic trainer selection and investment in master trainers, enhancing system capacity while lowering delivery costs.

Teaching and Learning Materials (TLMs) also became more cost-effective through iterative design and sourcing. A supplier in India provided consistent, low-cost printing and shipping. The average unit cost of learner workbooks dropped from £0.44 in 2022 to £0.13–£0.21 in 2025, depending on term and inclusion of protective sleeves. Specifications improved over time, with more durable materials and added features like rain-resistant sleeves.

Programme management costs remained stable at 21–23% of total costs per quarter from pilot to scale-up. This was achieved by leveraging national systems and relying on a lean team of technical advisers for delivery.

Equity
The endline evaluation showed that the programme improved early grade mathematics outcomes equally for girls and boys. However, children with the lowest initial scores and those from the most disadvantaged backgrounds benefitted the least. This aligns with previous findings that extreme poverty and chronic food insecurity limit the impact of school-based interventions for the poorest learners.

To address equity gaps, the curriculum and teaching materials were designed to incorporate inclusive approaches. Other targeted support included Teacher Learning Circles, structured lesson plans (lessons included differentiated support strategies for struggling students and extension activities for those making better progress), and special educational needs (SEN) training. The programme trained 155 specialist teachers and distributed 3,450 large print workbooks to learners with visual impairments.

Additionally, BHC secured funding through the SCALE CMP to design a scalable remediation programme, intended to be adopted by the World Bank GPE. This approach supports marginalised learners by focusing on foundational skills rather than curriculum pacing.

Sustainability
Key elements contributing to sustainability include:
- Government ownership and institutionalisation: Led by the MoE, the programme is embedded within national systems, with strong collaboration across departments like DQAS, MIE, and Directorate of Teacher Training and Development (DTED.
- Teacher training and professional development: A cadre of master trainers has been developed to deliver ongoing professional development, strengthening the education system’s internal capacity.
- System-based planning for TLMs: The programme piloted a data-driven process using EMIS to estimate workbook printing needs, which was shared with MoE directorates as a scalable planning model.
- Government-led monitoring: A low-cost, zonal-level monitoring system was co-designed with DQAS, now covering over 60% of schools and being integrated into MoE ICT systems.
- Evidence-based approach: The programme uses rigorous evaluation findings to inform policy, training, and community engagement, fostering a culture of continuous improvement.

E: Risk

Overview of programme risk
The programme maintained a moderate overall risk rating throughout its lifespan, with a temporary elevation to major in 2022 due to policy changes to DSAs and political tensions around the reform. These risks were mitigated through contract amendments, cost adjustments, and transferring technical leadership to MoE and MIE, allowing the rating to return to moderate from 2023 onward. The programme closed with a moderate rating, supported by strong endline evaluation results and institutional maturity.

Strategic and contextual risks—such as climate shocks, COVID, inflation, and food insecurity—intensified in 2023–2025, driven by cyclones and USAID’s exit from complementary literacy programming. Mitigating actions included CAMFED’s introduction of Academic Clinics to support the most disadvantaged girls to catch up post COVID school closures. Hunger-related absenteeism, with over 28% of children missing school daily, was escalated to the Development Director. Mitigation included £3m in lean season support via the World Food Programme and donor engagement to strengthen food security responses.

Policy and programme delivery risks were managed within BHC’s receptive appetite. Risks around sustainability, training quality, and institutional clarity were addressed through adaptive programming, leadership transitions, and strengthened government ownership. Safeguarding risks, initially rated major, were reduced through proactive measures such as training, reporting mechanisms, and improved payment systems that enable teachers to return home safely every evening. However, risks remained in remote training settings and were mitigated through FCDO bespoke training of the programme’s safeguarding coordinator, safeguarding and child protection best practices integrated into training of master training and teachers, awareness campaigns including posters in classrooms, safeguarding annual letters, and due diligence assessments.

Financial and fiduciary risks rose to major in 2025 due to increased DSA rates announced in December 2024 and incidents of mandate fraud. These were addressed through supplier system upgrades, verification processes, and fraud awareness efforts. Risks related to workbook misuse were mitigated by allowing MIE to sell copies and launching community awareness campaigns.

In 2021, following CAMFED’s difficulties in forecasting within 5% variance, management KPIs were introduced. Meetings were held at the end of each month to provide feedback on performance and discuss controls for accurate forecasting. This process stopped in August 2022 after CAMFED registered improvements for more than three months. Overall, financial risks were managed within BHC’s cautious appetite, with partners demonstrating compliance and timely reporting.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues

Over six years, the programme underwent two Business Case addendums and four contract extensions to accommodate adaptive programming, budget cuts, and COVID-19 delays. Supplier engagement was strong, with milestone-based payments incentivising quality delivery and value for money. Quarterly KPIs assessed delivery, milestone quality, and financial management, consistently scoring “Approaching Target.” Open Book Accounting was upheld, and profit declarations showed no concerns. Delays in DSA payments during teacher training were a recurring challenge, particularly in remote areas, requiring a balance between oversight and timely disbursement.

Narrative and financial reporting were timely and of high quality, with most suppliers submitting quarterly reports within 2–4 weeks and annual audited financial statements. Financial management was robust, with 100% of the £49.2m ODA budget spent. Fraud cases were addressed promptly, with recoveries of £104k in 2025 and £20k in 2024. Overall forecasting accuracy remained within a 5% variance, and invoices were detailed and transparent. Asset management was efficient, with six vehicles repurposed from closed programmes, saving over £300,000.

Risk management was proactive, with regular updates to delivery chain maps and escalation of major risks. Partners participated in fortnightly and quarterly risk dialogues, maintaining updated registers and testing mitigation measures. FCDO supported adaptive responses and required Statements of Assurance from suppliers.

Economy was demonstrated by declining unit costs: teacher training dropped from £35.09 to £15.97, and workbooks from £0.44 to £0.16. Programme management costs also fell from 40% to 35% of the total budget. A key lesson is that adaptive contracts should include sufficient time buffers to accommodate emerging needs and ensure flexibility throughout implementation.
Breakdown of spend by component:
Programme component	GBP £
Maths Curriculum Reform	26,561,483.16
LGAP	12,000,000.00
CAMFED	6,999,586.74
WB EFO	3,605,705.42
Edtech Hub (M&E)	30,072.00
Total spend	49,196,847.32

Programme-level approach to monitoring and evaluation

The programme adopted a layered M&E approach that evolved over time, combining system-led data, partner reporting, field visits, beneficiary feedback, and third-party evaluations. Early pilot results showed promising learning gains after just nine months, but the accompanying process evaluation highlighted the need for more agile beneficiary feedback mechanisms. This led to a shift toward real-time monitoring, blending dashboard data with qualitative insights, including ethnographic research by the EdTech Hub (co-funded by the Gates Foundation) that informed improvements to workbooks and teacher guides, as well as the development of the dashboard.

As the programme matured, M&E efforts focused on systems integration. The dashboard was embedded into government routines, with PEAs collecting and reviewing data at district level. While this reduced data precision, it strengthened institutional ownership and sustainability. The dashboard also supported logframe reporting, reinforcing its role as a central monitoring tool within the national education system.

Qualitative monitoring was strong, with fortnightly check-ins and pulse surveys informing real-time adaptations—such as addressing material leakage through launching a WhatsApp catalogue. A rigorous RCT conducted by the University of Oregon, co-funded by Prevail and pro bono work by the University’s economics researchers, confirmed the programme’s effectiveness at scale, though results likely underestimated impact beyond Standard 1 due to timing of material updates. Findings were widely disseminated through national and international platforms, including at top-tier academic venues such as the What Works for Global Education conference at Oxford University (2024) and seminars in U.S. economics departments. A companion implementation paper—authored by the education adviser, implementation team leader, and MoE lead—is underway, capturing the programme’s adaptive journey and lessons learned. Its abstract has been accepted at The Education and Development Forum (UKFIET) and the Gates Foundation has expressed interest in including the findings in their “Science of Teaching” database.

Date of last narrative financial report	30/06/2025	Date of last audited annual statement	25/01/2025 / Audit report covering March 2023-February 2024. Audit covering up to February 2025 is in progress.