## Annual Review

Title: Cross-Border: Conflict Evidence, Policy and Trends (XCEPT)
Programme Value £ (full life): £36.8m		Review date:
Programme Code: 300100	AMP start date: / 26 March 2018	AMP end date: 28 / February 2027

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A+	A+	A+	A+	A+
Risk Rating	Major	Major	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	All published documents
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

The Cross-Border Conflict Evidence, Policy and Trends (XCEPT) programme delivers high quality research on current transnational conflicts and analyses conflict responses to tackle cross-border challenges. It also researches the drivers of violent and peaceful behaviour and what works to address psychosocial needs in conflict settings.

XCEPT provides public good and responsive research to inform the policy and operations of FCDO, HMG and beyond. XCEPT helps the UK to work more effectively to address long term drivers of conflict, it supports development of new responses to transnational conflict challenges and fills wider international evidence gaps. It enables southern partners to deliver quality research in challenging contexts. It is delivered through three components, plus an FCDO Project-Funded Post (PFP) Conflict Adviser. The Research and Evidence Directorate (RED) of the Foreign, Commonwealth and Development Office (FCDO) has allocated £36.8m to XCEPT over nine years (2018-2027).

	Funding Modality & Partners (lead in bold)	Timescale & Budget
Component 1 (C1): / Local Research Network (LRN)	Accountable Grant / The Asia Foundation (TAF), Rift Valley Institute (RVI), Malcolm H. Kerr Carnegie Middle East Center (MKCMEC)	March 2018 – February 2027 / £10m
Component 2 (C2): / Cross-Border Conflict and International Conflict Response	Research Programme Consortium / Chemonics International, The Royal Institute of International Affairs (Chatham House - CH), Conciliation Resources (CR)	May 2020 – / February 2027 / £17.70m
Component 3 (C3): / Understanding Drivers of Violent & Peaceful Behaviour	Research Programme Consortium / Chemonics International, Kings College London (KCL)	April 2020 – / February 2027 / £8.62m
Programme Funded Post (C4)	FCDO staff member who links the programme to FCDO country teams and other HMG departments including Cabinet Office and Ministry of Defence	March 2018 – Feb 2027 / £0.51

Summary supporting narrative for the overall score in this review

Context and background:

This was the last year of XCEPT’s original programme phase. During the reporting period, a costed extension was agreed extending delivery by two years to February 2027. The extension simplified the programme’s delivery model, including the decision to end the Accountable Grant Agreement (C1) in FY25/26, and close the contract with Chatham House under C2. This was a year of transition as the programme redesigned aspects of delivery, including scaling up the XCEPT Research Fund (XRF), developed plans for research synthesis and publication legacy, and moved into a second phase of the Kings College London (KCL) research on violent and peaceful behaviours (C3). The team delivered on these processes while continuing ongoing research and new research commissioning.

There were some delays to deliverables this year, including completing annual review recommendations from 2024 and refining the XRF strategy for the addendum period. However, the level and complexity of work during the reporting period was significant. The recruitment of three XCEPT Research Fellows and continued effort from the implementing team meant the year ended strongly with an ambitious plan for the final phase of the programme.

Going forward XCEPT will focus on comparative research, synthesis, and sustainability, with continued commitment to locally grounded research. XCEPT is on track to reap the significant investment made this year to ensure lasting conceptual and instrumental impact beyond 2027, when it will have been delivering research for nearly nine years.

Key findings:

Overall, the review found that XCEPT continues to deliver high-quality, policy relevant research that supports UK government priorities and wider international needs. Interviews highlighted the extent to which XCEPT research is valued by a range of stakeholders across HMG and beyond. Highlights over the reporting period include the following (more in Sections B and C):

Research on Yemen enabled HMG conversations with a range of international partners and led to joint policy with allies. Findings formed the basis of cross-Whitehall analytical and scenarios papers on Yemen and the Houthis.

Research on Sudan’s gold sector influenced the framing of side events to the FCDO Sudan Conference, including a conflict resolution roundtable; and findings were included in an FCDO paper circulated to the Foreign Secretary in advance of the conference.

Research on instability in Coastal West Africa facilitated the UK’s coordination role through joint initiatives such as the Coastal States Stability Mechanism, supporting a more joined-up international response. Findings informed Government of the Netherlands’ policy and assistance objectives in the region; shaped cross-border security cooperation between Ghana’s Boundary Commission and counterparts in Cote d’Ivoire, Togo, and Burkina Faso.

Community-led research along Somalia borders influenced Somalia Stability Fund approaches in contexts with a limited state presence but persistent social order.

XCEPT research is increasingly cited across academic and grey literature, with 270 citations this year across components, exceeding expectations. XCEPT produced 14 academic articles over the reporting period, including Borders of Conflict: Navigating Policy in a Transnational Ecosystem a special issue of Global Policy that features 10 articles exploring the transnational dynamics of authority and violence in Africa and the MENA region; plus three journal articles and a book chapter published by KCL.

XCEPT delivered a range of high-level, impactful policy meetings and events, including: convening 50 senior policy makers from multiple countries, including the UK Special Representative for Sudan, for a cross-component workshop on Eastern Sudan; briefings on Yemen to the US Assistant Secretary of State for Near East Affairs, the US Special Envoy to Yemen, the Special Envoy of the UN Secretary-General for Yemen, and UN Security Council member state delegations; and a Carnegie researcher presenting research findings in a closed UN Commission of Inquiry meeting on Syria.

The C1 accountable grant ends in FY25/26. An external review of the LRN found that C1 strengthened capacity of researchers through a range of initiatives, including serving as a platform for building meaningful connections between researchers and with policy makers; supporting visibility and credibility; and through developing on-the-job skills.

Major lessons learned this year:

Lesson 1: Challenges and delays in producing an updated plan for the XCEPT Research Fund (XRF): As part of business case addendum discussions, XCEPT was asked to further develop the XRF research strategy for commissioning from FY25/26 onward based on assessment of XCEPT’s body of work so far and broader research gaps. Initial outputs did not meet FCDO expectations. This was partly due to challenges arising from XCEPT’s three component structure and the breadth of research to be consolidated under the C2 XRF; previous years’ challenges in recruiting an academic Research Director[1]; and delays in appointing XCEPT Research Fellows. This became an increasing risk to programme delivery. In March 2025, the implementing team, including three new XRF Research Fellows, presented an updated approach to XRF commissioning which gave FCDO confidence in XCEPT’s future direction. It underscored the importance of having the right expertise in place to deliver XCEPT’s conceptual and instrumental impact over its final two years, and the value of clear communication between FCDO and XCEPT. Going forward there needs to be a careful balancing of effort across multiple strands of work to achieve the objectives outlined in the refined strategy.
[1] Recruitment challenges led to XCEPT’s research leadership group in Sept. 2023 concluding that no single Research Director could represent the programme; RED supported this decision and approved a decision to instead work towards recruiting three Research Fellows to align with the future direction of the programme.

Lesson 2: Consistent engagement between researchers and policy teams and variation in types of outputs. Interviews flagged that some researchers are more engaged with policy and programme teams than others. Discussion revealed 'best practice' approaches, where researchers engaged FCDO early in design to identify research ‘policy threads’; maintained engagement throughout, presenting early findings where possible; varied products and briefing formats to engage working level colleagues as well as senior audiences; and maintained engagement post-completion to support uptake.

XCEPT practice to engage FCDO throughout the research lifecycle was further reinforced in response to last year's AR recommendation on research 'co-creation'. However, some interviewees highlighted remaining differences in the way researchers engaged. Interviews also highlighted that while high-level workshops and convenings played an important role, smaller, bespoke discussions could sometimes be more impactful. Colleagues noted that occasionally they received very short notice invites to external events where XCEPT was presenting, which made it very hard to attend. XCEPT should aim to embed ‘best practice’ engagement across all awards, reflecting on how change happens within HMG. Work done this year to refresh the XHMG Advisory Group (XHAG) approach will support this. Overall, a combination of outputs, sustained relationships and engagements are most likely to lead to outcome level change. This will be explored further this year through R1.

Lesson 3: High level policy priorities are hard to influence, even with well-timed evidence. Over the reporting period, XCEPT delivered a range of well-timed outputs on high priority themes, including Sudan, Gaza, and migration. Interviews highlighted the challenge of influencing UK policy and programming on such high-priority areas. Research on high-profile or fast-moving contexts often needs to add new empirics to show relevance to the debate. The implementing team and FCDO should continue to reflect on and learn from how change happens in HMG, including the timeframes within which outputs lead to outcome and impact level change; and to interrogate this as Outcome change is developed in partnership with the third-party evaluator, Agulhas (see R1).

Lesson 4: Researchers from the Global South supported through applied research experience. A review of the Local Research Network (C1) found that researcher capacity was supported best by hands-on work opportunities. The review also highlighted the value of networking and working across different regions. The XRF can continue to support capacity by ensuring researchers from the Global South can access funding opportunities and are given platforms to showcase their research and engage in conferences and events (see R5).

Lesson 5: XCEPT effectively manages duty of care and delivery risks in volatile contexts. Instability in Lebanon and South Sudan affected KCL research, but decisions were made quickly to ensure duty of care was upheld and adjustments made to the delivery model to ensure research could continue safely. XCEPT kept FCDO well-informed throughout the process. KCL highlighted the robust support received from Chemonics in risk management and flagged that KCL’s wider risk assessment processes had been updated to align with Chemonics’ ‘enabling’ and ‘intelligent’ approach.

Lesson 6: Demand for XCEPT expertise outstrips programme capacity to respond, risking unmanageable workloads and requiring careful prioritisation. This year it has been challenging to prioritise engagements and commissions that have potential to influence HMG policy and programming. This is in part due to the continuing volatile global context and ongoing changes within FCDO. Occasionally, the implementing and programme team have jointly decided not to engage where there would be negative implications for other areas of delivery. This will need to be monitored through the final years of the programme to ensure the implementing team can deliver the highest priority work to achieve its intended outcomes and impact by 2027, while avoiding overstretch of personnel and resources. See L2 and L3.

Lesson 7: Pressure to hit logframe targets has occasionally impacted quality of research outputs. Interviews raised a concern that a focus on meeting logframe targets had on occasion led to researchers submitting work before it was ready. While the logframe is an important measure of programme progress, it should not result in rushed delivery or come at the expense of quality. See R2 on the logframe and the need to ensure programme ambition is appropriate while also incentivising quality deliverables.

Recommendations for the year ahead:

R1: Programme impact and research legacy. For the final two years of the programme XCEPT will need to balance responsive, policy relevant engagement and research with conceptual, comparative, and synthesis outputs that support the programme’s research legacy. It will also be increasingly important to demonstrate programme impact with measurable change at Impact and Outcome levels. There are added pressures to demonstrate ODA programme contributions to real-world change in the context of shifting aid architecture worldwide and the UK’s move to reduce ODA to 0.3% of GNI.
- In line with last year’s AR recommendation, which was delayed to incorporate findings of XCEPT’s external third-party evaluation, by September XCEPT should review the Theory of Change to make outcome-level change pathways clearer and articulate the different ways and types of outputs and activities that combine to produce strong research influencing examples.
- By October, XCEPT should review the monitoring and evaluation (M&E) framework and identify ways to strengthen feedback loops between researchers, policy makers, and wider stakeholders to better track this Outcome level change.
- By November, the implementing team should produce a plan for the different types and balance of impact the programme will achieve by closure, using the previously shared Impact Wheel; alongside a publication strategy that aligns with this plan. These should support programme delivery and sustainability and reinforce thematic convergence across programme components.
R2: Update the logframe in line with XCEPT’s strategy for the addendum period, ensuring appropriate ambition for the next year of delivery. By September:
- At impact level, develop new indicators to ensure the programme is tracking both conceptual and instrumental impact over the final two years, including where XCEPT research has made policy and programming more effective at supporting peace.
- Drawing on work to define outcome level change pathways (R1), XCEPT should review outcome statements and indicators to reflect the different ways and pathways that change happens; plus update citation targets, benchmarking against other RED programmes.
- Reduce the number of outputs following the closure of C1/Output 3 and increase the weighting of Output 4 (the XRF). Incorporate select Output 3 indicators into Output 4 to track the number of researchers from the Global South who lead or co-author XRF research, and their levels of engagement in XCEPT programme events and conferences.
- For all Outputs, review programme targets for the next year to ensure a good level of ambition considering it will be the final full year of delivery, but that output quantity does not come at the expense of quality (see L7).
R3: Consistent engagement across HMG on new commissions and ongoing research. Linked to Lesson 2, XCEPT should aim to embed ‘best practice’ engagement approaches across XRF awards. Through the renewed XHAG, ensure systematic engagement with HMG especially in relation to commissions and newly conceived work on policy responses and synthesis. This should be implemented alongside a renewed emphasis on ensuring HMG departments beyond FCDO are included in research presentations, and continued consideration of getting the ‘right people in the room’ [XCEPT, FCDO, ongoing].

R4: Responding to spending review and managing budget uncertainty. As the UK progresses through the second spending review (SR) period and related budget uncertainty, the programme team and implementing partner will need to continually manage the risk of unconfirmed programme funding until the programme-level implications of the Spending Review are known later in FY25/26. We recommend a standing agenda item on the programme six-weekly management meetings to review XRF budget and liabilities for FY26/27 [XCEPT, FCDO, ongoing].

R5: Continued emphasis on localising research. With the closure of the accountable grant (C1) it remains important for XCEPT to ensure researchers from the Global South can capitalise on research opportunities through the XRF. The programme should identify opportunities for Global South researchers, including from the LRN, to engage in research development and lead or co-author research, as appropriate [XCEPT, ongoing].

Ongoing recommendations from the previous Annual Review 2024:

R6: Continued collaboration with RED programmes. XCEPT should continue their proactive approach to complementary research and uptake with other RED-funded programmes, including PeaceRep, SOC ACE, ReCIPE, SPRiNG, and SPARC [XCEPT, ongoing].

R7: Ensure XRF risk management approach is proportionate and meaningful. While KCL highlighted the value of XCEPT’s robust risk management approach, smaller partners have continued to feel overburdened by process. Build on progress already made in streamlining processes where possible, applying them proportionately to partners based on research scope and team capacity, without compromising on quality [XCEPT, ongoing].

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The XCEPT programme continues to be guided by the Results Framework. Programme outputs cover the following themes:
1. Research: Policy-relevant research, evidence and recommendations are generated and documented about conflict-affected borderlands, cross-border and regional conflict dynamics, drivers of violent and peaceful behaviour, and associated policy responses.
2. Policy Engagement: Engagement with a policy audience at key stages, from research design to dissemination, to build ownership and improve research uptake.
3. Networks: Establishing and expanding a cross-regional network of local researchers and research organisations capable of undertaking field work in sensitive border areas, through knowledge exchange events and training / capacity-building opportunities (C1).
4. XCEPT Research Fund (XRF): The XRF makes awards to relevant downstream research and XCEPT-related awardees of value to the programme (C2).

In 2023, XCEPT revised the Theory of Change (ToC) and logframe to better capture progress toward research and policy impact (see Figure 1). The 2024 Annual Review recommended updates to the ToC and logframe at Output and Outcome levels. XCEPT revised the Output indicators and targets, adding an indicator to distinguish between academic and journal publications (1.1) and other peer-reviewed research reports (1.2.1) published in non-academic fora, to align the logframe with other programmes in the Politics, Conflict and Humanitarian (PCH) research commissioning team. Outcome-level changes were not completed within this review. A mid-term programme evaluation was taking place in parallel, so the team agreed with FCDO to postpone the broader ToC update to incorporate the findings of this evaluation alongside updates to the Outcome indicators.

Figure 1: XCEPT Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

XCEPT’s Impact Statement is ‘Policies and programmes have a more effective influence/impact on fostering peaceful behaviour and addressing violence and conflict.’

Indicator 1: Frequency and intensity of violence in research countries / research areas*	According to the Global Peace Index, the average level of global peacefulness declined by 0.56% over the past year. A total of 97 countries experienced increased levels of conflict this year. The Middle East and North Africa (MENA) and Horn of Africa regions continue to be the least peaceful regions globally, with Yemen, Sudan, South Sudan, and Syria among the most affected. In Asia, Afghanistan and Myanmar are ranked among those least peaceful countries. / ACLED reports an increase in global conflict: 25% increase in political violence incidents recorded in 2024. Of the 10 countries listed by ALCED to be witnessing ‘extreme violence’, three are in Africa (Nigeria, Sudan, and Cameroon), three are in the Middle East (Palestine, Lebanon, and Syria), and one in Asia (Myanmar).
Indicator 2: Ranking of research countries on the Global Peace Index*	The Global Peace Index cites Yemen, Sudan, South Sudan, Afghanistan, and Ukraine among the five least peaceful countries in 2024, and Democratic Republic of the Congo, Russia, Syria, Israel, and Somalia among the top ten.

* XCEPT’s logframe commits to tracking these indicators to show trajectories but not setting milestones, as they are affected by factors beyond the programme’s control. See R2 on updating Impact indicators to make these more related to XCEPT programme research.

Outcome Indicator 1: Number of cases where XCEPT research influences policy, programme design or implementation (assessed through tangible examples)

	Target (cumulative)	Achieved (cumulative)
Milestone 1&2 (2019, 2020)	Too early for milestones	NA
Milestone 3 (2021)	Total: 3 / C1: 3; C2/C3: not set	Total: 3 / C1: 3
Milestone 4 (2022)	Total: 5 / C1: 5; C2/C3: not set	Total: 10 / C1: 5; C2: 5; C3: 0
Milestone 5 (2023)	Total: 9 / C1: 7; C2: 1; C3: 1	Total: 19 / C1: 9; C2: 8; C3: 2
Milestone 6 (March 2024)	Total: 28 / C1: 12; C2: 12; C3: 4	Total: 29 / C1: 13; C2: 12; C3: 4
Milestone 7 (March 2025)	Total: 40 (11 this year) / C1: 16 (3); C2: 12 (6); C3: 4 (2)	Moderately exceeded / Total: 44 (15 this year) / C1: 17 (4), C2: 21 (9); C3: 6 (2)

Outcome Indicator 2: Influencing the policy debate. # of citations of XCEPT research and research outputs in the academic literature, grey literature, and the media

	Target (cumulative)	Achieved (cumulative)
Milestone 6 (March 2024)	Total: 40 / C1: 25; C2/C3: 15	Total: 169 / C1: 115; C2/C3: 54
Milestone 7 (March 2025)	Total: 214 (45 this year) / C1: 143 (25); C2/C3: 74 (20)	Substantially exceeded / Total: 439 (270 this year) / C1: 319 (204); C2: 91 (48); C3: 29 (18)

XCEPT remains on track to deliver the programme outcome: FCDO, HMG and partners are better informed and better able to use project-generated evidence to adjust intervention strategies and policies to address conflict and instability more effectively. There was a robust process to review and agree the list of outcome stories. The 15 stories counted this year are the strongest examples and often contain multiple individual instances of influencing different policies or programmes within one story. There were several influencing highlights:

XRF Yemen: Research on Yemen allowed HMG to have informed, fact-based conversations on sensitive issues with international partners and develop joint policy with allies. The research formed the basis of xWhitehall analytical and scenarios papers on Yemen and the Houthis. By engaging across a range of teams, the research showed relevance to wider regional developments, informing HMG policy and multilateral diplomacy. Phase II has been initiated with significant engagement from policy teams.

Chatham House Sudan Research: Research led by Ahmed Soliman on Sudan’s gold sector contributed to a gathering consensus in FCDO that Sudan is an internationalised conflict affected by transnational flows of resources, materiel and people, and resolution will be contingent on a macro regional political settlement. It provided evidence for officials to use when discussing sensitive policy towards the UAE’s role in the conflict. HMA to UAE, Edward Hobart, engaged directly with Ahmed’s analysis on Abu Dhabi’s and Dubai’s relative political and economic engagement in the Horn, showing the importance of detailed direct discussions, as well as larger briefings on top-level findings. The research informed the framing of March side events to the UK’s Sudan conference, including a conflict resolution roundtable that involved XCEPT researchers. FCDO colleagues drew on roundtable discussions and XCEPT analysis to draft a paper that highlighted the importance of Sudan’s gold in conflict resolution. The paper was circulated widely in advance of the conference, including to the Foreign Secretary.

Chatham House research on the Axis of Resistance: Chatham House research on the ‘Axis of Resistance’ fed into the development of the Lebanon JACS through multiple briefings and engagements with BE Beirut. This research, alongside complementary conversations with experts from Carnegie Middle East Center on the sophistication and adaptability of the Hezbollah networks, supported FCDO’s look beyond geographic and thematic silos to the broader international and UK implications of ‘Axis of Resistance’ global networks. RAs commented that the research has become part of internal MENA reading lists, and that the body of XCEPT research is helping RAs build knowledge across the organisation.

XRF research on stability and livelihoods in Coastal West Africa and the Sahel borderlands: Research facilitated engagement between governments and development partners in the region and enhanced the UK’s coordination role among regional donors, such as through the Coastal States Stability Mechanism, to support a joined-up international response. Findings supported donor assistance efforts to reduce instability along Ghana's borders and informed Ghanaian engagement with neighbouring states on cross-border cooperation. The researchers' openness to feedback and willingness to make their work relevant to policy and programme questions was highlighted as enhancing the influence of the research overall.

XRF community-led research along Kenya-Somalia borders: Research led to conversations within HMG on what constitutes social order and the variable effects of donor-supported state strengthening efforts. Findings shaped Somalia Stability Fund planning, informing approaches in contexts where state presence was limited but order persisted. Following the XCEPT-funded pilot, the community reflections process continued with the support of the European Civil Protection and Humanitarian Aid Operations (ECHO) to enable continued engagement of and dialogue among communities in new locations along the Kenya-Somalia border.

RVI research on ‘Ethiopia’s Red Sea Politics: Corridors, Ports and Security in the Horn of Africa’: This research influenced the design of the TradeMark Africa project and led to a shift from the long-term position of providing technical assistance (TA) to the government of Ethiopia, to working directly with private sector actors in both Ethiopia and Somaliland. The research offered explanation for why TA and engagement with the government was not translating into a strong government commitment to reform, and recommended refocussing on the private sector. This was implemented by BE Addis, and they are expecting to save significant time and money with this approach (we will continue to monitor). The research led to the Embassy convening a development partner group on trade and logistics to share the research findings with wider partners.

KCL research on trauma and the drivers of violent and peaceful behaviour: Findings on trauma, PTSD and psycho-social support will be included in an internal FCDO guidance note on mental health and psychosocial support in in emergencies. We will continue to monitor the effectiveness of these new approaches.

Outcome Indicator 2: C1 research outputs have been cited 319 times since 2018 (45% in academic literature, 48% in grey literature). Highlights include RVI’s Moving Towards Markets: Cash, Commodification and Conflict, cited in 41 publications; MKCMEC’s The Egypt-Sudan Border: A Story of Unfulfilled Promise, referenced in 24; and Trade in the Sulu Archipelago: Informal economies amidst maritime security challenges, cited 11 times. C1 work also was cited in official documents of Canada, Denmark, Austria, Italy, France, Iraq, the Philippines, the EU, and the UN. This level of citation is good considering C1 has published primarily in non-academic fora.

C2 and C3 research, which began publishing a after C1, has been cited 120 times across academic and grey literature and media. Highlights include Alcis’ research report on Afghanistan, Changing the rules of the game, which has been cited 12 times across different media; Chatham House research which has been referenced in papers published by the UK Government, EU, and UN; and the most cited C3 publication, KCL’s 2022 briefing note, The role of trauma and mental health in violent extremism, cited 8 times in academic literature. While these numbers are more limited, this reflects a new emphasis on academic publications, and we would expect citation levels to increase in the final two years.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

XCEPT continues to deliver high-quality, policy relevant research that supports UK government priorities. Interviews highlighted the extent to which XCEPT research is valued by a range of stakeholders across HMG and beyond. XCEPT is moving into the final two years of delivery with a focus on comparative research, synthesis, and sustainability. Significant investment has been made this year to deliver a credible plan for programme conceptual and instrumental impact. There is a real risk that reduced funding could undermine this impact and the VfM of RED’s total investment in XCEPT at a critical point. For these reasons there is a very strong case for the programme to continue based in its own merits, in the context of previous investment, and in relation to the wider portfolio.

Progress against recommendations from last year’s annual review

R1	Consolidate and synthesise key research findings across C1 and C2: As C1 (TAF, Carnegie and RVI) and C2 (Chemonics, CH, CR) partners enter their final programme year, XCEPT should build on consultation among the Research Leadership Group (RLG) to date to offer consolidated presentation of cross-cutting research findings and lessons. Where previous research has produced context-specific findings relating to particular conflicts, synthesis work provides an opportunity to draw out the wider implications of these studies to develop broader theoretical conclusions which can be applied across a range of geographical contexts. The RLG should develop and begin implementation of a plan for presenting synthesised findings in events and outputs by the end of Q2.
	Partially met. XCEPT partners did not produce a plan for synthesis and commissioning that was in line with RED expectations within this timeframe. In July 2024 the programme team convened to discuss future XRF research questions and outlined the C2 approach to XRF commissioning and synthesis in a follow up presentation in October, but these did not initially meet expectations. In early 2025, C2 delivered an evidence review to inform research direction and commissioning and initial outputs were shared with FCDO/RED in February 2025, followed by a workshop in early March. FCDO/RED approved the synthesis and strategic direction on 7 March 2025. C1 partners produced a synthesis of key evidence since 2018, including a think piece published by RVI, a synthesis paper published by TAF, and three regional pieces on Asia, the Horn of Africa and Levant.
R2	Accelerate the appointment of thematic XRF Fellows: XCEPT efforts to recruit a programme-wide Research Director highlighted the difficulty of identifying a single expert to serve the varied XCEPT research areas. FCDO and XCEPT thus agreed to appoint subject-specific experts to advance research under XRF themes to be pursued from FY 24/25. The XRF should progress appointment of at least two thematic Fellows by the end of Q2.
	Partially met. Three XRF Fellows were selected in Q3 through competitive solicitation: Tobias Ide (Conflict and Climate), Erica Gaston (Borderlands/Conflict Connectors), and Tobias Hagmann (Borderlands). The Fellows began work in FY 24/25 at LOE levels based on availability and their proposed scope.
R3	Review the Theory of Change and logframe to make outcome-level change pathway even clearer and refine indicators to reflect this: As XCEPT transitions to consolidate its research and expand the XRF, with a particular focus on what works to respond to conflict, uptake among practitioners will be key. The Outcome statement and indicators would benefit from breaking down the different ways and pathways for change to better track and learn from how uptake and influence is happening in practice. This is also an opportunity to review the Impact indicators, including to understand the conceptual impact the programme is having. A range of other logframe changes at output level are also recommended elsewhere in this document, including reviewing the output weighting attached to the XRF. A review and update of the logframe should be done by the end of Q2/start of Q3.
	Not met, ongoing. This recommendation was not completed in the reporting period. Logframe output indicators were revised in October 2024, with further updates to Indicator 1.1 and cumulative baselines and targets in January 2025. These included rewording Indicators 1.1 and 1.2 and introducing 1.2.1 and 1.2.2 to distinguish academic outputs from externally peer-reviewed research reports. XCEPT’s third-party evaluator is completing a mid-term review of XCEPT in Q1 of FY 25/26, including review of the ToC and Outcome indicators, so Outcome level changes were delayed to ensure ToC adjustments reflected this evaluation. Impact indicators were not reviewed. See this year’s R1 and R2.
R4	Maximise research uptake by improving the accessibility of research to practitioners tackling live problems: XCEPT can increase uptake by improving the accessibility of existing research, for example by making it clearer where past research products are relevant to current policy or programme challenges. Providing forward looks categorised by geographies and themes would also help practitioners to track what research is in the pipeline; allowing website users to access existing products by theme and see the most important papers or briefs up front would also be beneficial. The programme SRO and Lead Adviser can play a role in amplifying past and upcoming research with HMG stakeholders.
	Met, ongoing. To support visibility of upcoming research, XCEPT shares digests for MENA and Africa, listing research by geography and theme and including a section on future research. The website search function has been updated to make it easier to filter content by theme, geography, type of output, and publication date – improving accessibility and user experience. XRF projects also now have individual pages on the website, making it easier for stakeholders to track ongoing and planned work. While XCEPT engages relevant FCDO officers at the outset of each project, and awards typically include interim briefings to ensure officers can apply emerging findings, interviews highlighted variation in the engagement between research projects. See this year’s R3.
R5	Optimise the policy relevance of new research by having greater engagement with relevant HMG stakeholders during the process of research design: XCEPT delivery partners and HMG officials both expressed an appetite for more opportunities for co-creation of research themes and ongoing engagement with the researchers through design to findings and dissemination. The programme SRO and Lead Adviser can support in facilitating such opportunities where possible, by connecting lead researchers with relevant teams; XCEPT partners can also use these opportunities to build and deepen their networks for continued engagement. The programme should track progress by adapting output indicator 2.1 to more clearly distinguish between policy meetings which are focused on dissemination and those which are part of early-stage engagement in research design.
	Met, ongoing. XCEPT routinely shares project proposals with HMG for review and feedback and regular check-ins with FCDO/RED are used as an opportunity to update on the research pipeline and solicit guidance on HMG stakeholders best placed to engage on planned and ongoing research, including to join evaluation and review panels, which has proved effective. This will be continued in the current year through the refreshed approach to the XHAG and can be reviewed in this year’s R3. FCDO agreed with XCEPT that it would be most sensible for Output indicator 2.1 to not be adapted to include policy meetings that discuss early-stage engagement related to research design. Instead, the team will continue to report on such engagements through XCEPT’s narrative quarterly reporting.
R6	Review the format and utility of the Cross-HMG Advisory Group (XHAG): The XHAG was intended to provide a sounding board for XCEPT research direction and uptake, with diverse representation across geographies and thematic areas. As XRF commissioning increasingly focuses on the themes developed by the RLG, XCEPT and FCDO should review the utility of the broad-based XHAG and consider a more flexible, thematically driven approach to cross-HMG strategic engagement, producing a plan for refining or restructuring the XHAG by the end of Q2. This plan should consider opportunities for tapping into existing cross-HMG governance structures relating to the three research themes. It should also ensure that any future advisory group or groups have clear terms of reference.
	Partially met, ongoing: Meetings of the XHAG were postponed in FY 24/25 during programme-wide synthesis and review of XCEPT research and planning for XRF commissioning. This approach was agreed between XCEPT and FCDO to optimise XHAG engagement and ensure effective contributions by relevant XHAG members according to the programme’s reformulated thematic priorities. See this year’s R3.
R7	Expand cross-Component research dissemination. As C1 (TAF, RVI and Carnegie) and C2 (Chemonics, CH, CR) partners advance toward completion of XCEPT research in FY 24/25, XCEPT should capitalise on research complementarity to expand cross-Component coordinated public engagement. Good progress has been made toward this objective in the last two performance years, and XCEPT is positioned to enhance research impact through greater collaboration in the final year of partner research. This could include joint panel discussions or private briefings and cross-Component workshops or convenings. The programme should aim to deliver joint presentations in at least three conferences; three joint briefings; and a synthesis of research that brings together the findings from complementary research on borderlands.
	Met: XCEPT partners from all three components have collaborated on a range of conferences and events, including the MENA research conference in October 2024, C1’s LRN Workshop, a policy workshop on Eastern Sudan in Nairobi in November 2024, and a range of external conferences and media engagements.
R8	Strengthen collaboration and coordination with other FCDO RED-funded programmes: The portfolio of FCDO-funded research in fragile and conflict-affected situations offers an opportunity for greater collaboration across RED programmes. Supported by the PRO and SRO, XCEPT should explore avenues for complementary research and uptake with other RED-funded programmes such as PeaceRep, SOC ACE, and SPARC. Lessons from XCEPT’s work to strengthen the LRN should also be fed into RED’s working group on capacity strengthening.
	Met, ongoing: XCEPT has coordinated with other RED programmes, including inviting PeaceRep participants to relevant briefings, participating in a ReCIPE programme workshop, inviting SOC ACE researchers to participate in the MENA conference in June 2024, and collaborating with SPARC on their conflict and climate research strand. This engagement should continue. See this AR’s recommendation 7.
R9	Produce a review of the LRN, including Output 3’s contribution to Outcome level change. Consider mechanisms to ensure sustainability beyond C1 funding: C1 partners should review and document the achievements and outputs of the LRN in a short report, including lessons learned about approaches to localisation and inclusion, and research methodologies. This should include an assessment of whether the research network and researcher capacity has been strengthened, and how this is translating into benefits for developing countries and wider research. The report should also outline mechanisms to support the sustainability of the Network beyond March 2025, including integrating local research approaches within FCDO RED beyond the XCEPT programme. This could include establishing virtual networking platforms so that researchers can continue to work together without requiring the involvement of TAF, RVI and MKCMEC.
	Met. A review of the LRN was delivered by Humanitarian Advisory Group and GLOW Consultants, producing an internal report and a public briefing note. The LRN review outlined possible options for supporting global south research capacity beyond the close of C1 which are being considered for the coming two years.
R10	Promote increased local researcher participation in uptake events: Considerable practical challenges remain for local researchers seeking to access research and dissemination activities in the Global North. To support and derive the benefits of including the perspectives of local researchers in uptake, FCDO and XCEPT team should work together to learn from other research programmes and identify creative solutions which help local researchers to overcome or work around hurdles which limit participation.
	Met. XCEPT continues to prioritise the inclusion of local researchers across its events, with researchers presenting remotely when in-person attendance is not possible. For reasons outside of programme control, C1 local researchers continue to face challenges in travelling to in-person research dissemination events due to visa restrictions. Programme teams have engaged with FCDO in advance of events to support visa application processes, but due to firewalls between post and visa teams this does not always have the required impact.
R11	Expand capacity building for Global South researchers and organisations. The XRF is committed to supporting researchers and research institutions in the Global South, but doing so requires significant time and resource. The XRF should develop a capacity-building plan to ensure its support is as targeted and effective as possible. This plan should include consideration of how to reduce the bureaucratic burden for local researchers and organisations supported through the Fund to ensure that the requirements placed on them are proportionate whilst maintaining strong administrative standards.
	Partially met. XCEPT reviewed the capacity building approach within the XRF for Global South researchers and organisations. This included a feedback survey and reflection sessions with current and past awardees, as well as a review of previous XCEPT approaches. The capacity building plan will be completed alongside the broader XRF commissioning strategy in early FY26/26.
R12	Review risk management approach for the XRF. The planned expansion of the XRF carries potential risks, as XCEPT will be working with a range of new partners delivering research in complex conflict-affected contexts. Possible challenges for the XCEPT team include ensuring consistent research quality across the grants, and managing risks around awardees conducting research on sensitive issues. XCEPT should review its approach to risk management for the XRF to reflect the planned expansion and associated risks. The approach should ensure risk assessment is proportionate and meaningful, tailored to the nature of the research and focused on identifying practical risk mitigation measures
	Met, ongoing. Chemonics reviewed their XRF risk management and sought feedback from awardees and internal teams, as well as a review of organisational tools and policies within Chemonics teams. Improvements have been implemented including updates to XRF management procedures and HR policies. Heavy due diligence processes were flagged in AR interviews again this year, so this work should be considered ongoing to ensure this remains proportionate. A summary of this review was included as part of the Annual Report. See this year’s recommendation 7 for more.
R13	A detailed Value for Money framework to be developed in Q2 to allow VFM to be more systematically tracked over the coming year. Based on the FCDO’s 5E’s principles, a detailed framework with quantifiable and qualitative examples should be developed, so that a clear VfM argument can be made for the work of XCEPT.
	Partially met. This framework was completed in Q4 in agreement with FCDO and has been used to inform this AR.

## C DETAILED OUTPUT SCORING

Output Title	Research: Policy-relevant research, evidence and recommendations are generated and documented about conflict-affected borderlands, cross-border and regional conflict dynamics, drivers of violent and peaceful behaviour, and associated policy responses.
Output number:		1	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicators	2025 Milestones / (cumulative)	Progress
1.1 Academic outputs. # high-quality, externally peer reviewed academic, externally published journal articles, books, chapters, special issue contributions, and equivalents.	Total: 18 (14) / C1: 1 (0) / C2: 10 (10) / C3: 7 (4)	Met. Total: 18 (14 this year) / C1: 1 (0 this year) / C2: 10 (10 this year) / C3: 7 (4 this year)
1.2.1 Research Reports (>5000 words). # high-quality, externally peer reviewed research reports published in non-academic fora.	Total: 93 (14 this year) / C1: 58 (9) / C2: 33 (5) / C3: 2 (0)	Substantially exceeded Total: 105 (26 this year) / C1: 66 (17 this year) / C2: 37 (9 this year) / C3: 2 (0 this year)
1.2.2 Briefing notes / Working papers / Datasets: # short policy-focused papers based on XCEPT research; papers documenting exploratory and/or preparatory research (working papers, scoping papers, background papers); and data sets: new data made available to different audiences. Broken down by type.	Total: 190 (36 this year) / C1: 89 (12) / C2: 78 (20) / C3: 23 (4)	Moderately exceeded. Total: 201 (47 this year) – see supporting narrative / C1: 99 (22 this year) / C2: 78 (20 this year) / C3: 24 (5 this year)
1.3 Blogs / articles / multimedia. # research outputs other than full-length research reports, policy briefs or research papers. Includes blog posts, news releases, podcasts, photo essays etc. Broken down by type.	Total: 311 (67 this FY) / C1: 133 (17) / C2: 100 (35) / C3: 78 (15)	Met. Total: 313 (69 this FY) / C1: 134 (18 this year) / C2: 99 (34 this year) / C3: 80 (17 this year)

Briefly describe the output’s activities and provide supporting narrative for the score.

C1 substantially exceeded targets against Output 1.2.1 and 1.2.2; C2 and C3 largely met expectations against Output 1 indicators, apart from Indicator 1.2.1, where C2 exceeded expectations. Across the Outputs, targets for C1 were set during annual work planning in late 2023 and were not revised following the last annual review. While C1 targets included growth over programme years, there may have been justification to review the workplan and increase targets following the 2024 AR, reflecting the component’s final delivery year. Nevertheless, for Output 1.2.1, C1’s achievement of 17 reports is significantly more than their achievement last year (seven reports); and C1 delivered a significant number of briefing notes and working papers (1.2.2) this year. Overall, we judge this output to have moderately exceeded expectations overall.

This year XCEPT reported separately the number of published academic outputs (1.1). Other long form, peer-reviewed research reports published in non-academic fora were still counted in 1.2.1. While it will not be appropriate to publish all XCEPT research in academic journals, it is helpful to see the balance between academic and other published research. The programme produced 40 long form research outputs (1.1, and 1.2.1), 47 accompanying policy briefs or working papers, and 69 accompanying blogs, articles and multimedia content (1.3). This is an appropriate balance given the level of effort required for each, and the varied audiences being reached. Indicator 1.3 examples show how varied formats can effectively influence policy debates and public discourse on high priority themes. XCEPT’s publication strategy and the balance of outputs should be reviewed in the upcoming year as part of a review of the overall strategy for achieving programme impact (see R1).

Indicator 1.1: XCEPT published 14 academic outputs this year, meeting the milestone for this indicator. Only four academic outputs were published previously by XCEPT between 2018-2024, so this represents a significant increase in programme ambition. Chatham House published a special issue in Global Policy on “Borders of Conflict: Navigating Policy in a Transnational Ecosystem,” exploring the transnational dynamics of authority and violence in Africa and MENA, containing10 articles. KCL published three articles and a book chapter which cover Iraq, Syria and Lebanon in Studies in Conflict and Terrorism, Mediterranean Politics, and Conflict, Security and Development. This is a good achievement this year given the quality of journals and the prominence of authors from the Global South.

This year XCEPT also submitted several articles that are in various stages of journal review, including 11 manuscripts from local authors via gender equality and social inclusion (GESI) XRF awards.[2] XCEPT articles have been accepted to Conflict, Security and Development, Civil Wars, Development and Change, and Syria Studies journals. These have not been counted in the above logframe but give an indication of the programme’s increased effort toward publishing in academic forums this year.
[2] The GESI awards examine the ways women and girls engage in, and are affected by, conflict and peacebuilding activities in East and West Africa, Asia and the Levant. The research will provide evidence-based recommendations to inform a deeper understanding of the varied and complex gendered, intersectional and normative factors contributing to sustaining cycles of conflict as well as brokering sustainable peace.

Indicator 1.2.1: XCEPT published 26 research reports in the past year substantially exceeding the milestone for this indicator. Although targets might have benefitted from being reviewed as noted above, this is still a strong publication level. Highlights include:

- A research report by TAF’s partner in Bangladesh, the Centre for Peace and Justice (CPJ) at BRAC University, proposing a new policy and legislative approach to supporting refugee rights; MKCMEC published "Double Dealers: Lebanon and the Risks of Captagon Trafficking" by Mohanad Hage Ali; and RVI's research paper, “Ethiopia’s Red Sea Politics: Corridors, Ports and Security in the Horn of Africa,” based on a Memorandum of Understanding granting Ethiopia sea access in exchange for recognising Somaliland.
- Chatham House released capstone reports on their three case studies: "Gold and the war in Sudan: How regional solutions can support an end to conflict" by Ahmed Soliman and Dr. Suliman Baldo. David King, Economic Lead at the British Office Sudan, commenting it was the “best [he’d] seen on the sector in Sudan so far”; research on human smuggling through Libya culminated in the paper "How Migrant Smuggling has Fuelled Conflict in Libya", briefings informed UNSMIL’s approach to illicit trade; and "Shape-shifting Axis of Resistance" by Haid Haid, Hayder Al Shakeri, and Renad Mansour, showed how the Axis of resistance uses financial flows to evade traditional boundaries.

Indicator 1.2.2: XCEPT produced 47 briefing notes, working papers, and long-read articles in the programme year, moderately exceeding the milestone for this indicator. As above, C1 produced the most 1.2.2 outputs of all three partners, with C2 and C3 largely meeting their targets. Highlights include:

- C1’s Ibrahim Jalal's papers on Houthi ties to external actors led to numerous private briefings, including invitations to an EU Track II conference. Hesham Alghannam's article on Syria's use of Captagon received over 27,000 views. RVI published analyses on cross-border dynamics in the Horn of Africa, including studies on water, oil, and debt on the Sudan-South Sudan borderlands, and informal trade in Kenya. TAF partner Kachinland Research Centre produced a series on Myanmar’s Northern Borderlands.
- XRF awardee PRIO published five case studies and a summary brief on mediation in regionalised intra-state conflicts, prompting engagement with FCDO and academia.
- KCL research on Syria's new leadership shaped international understanding and policy approaches. A Foreign Affairs article on engaging with Syria’s new leadership received positive feedback from experts and prompted outreach from various international bodies, including the UK CT Police and the UN Office of Counter Terrorism.

Indicator 1.3: XCEPT produced 69 blogs, articles, podcasts, explainer videos, and animations in the programme year, slightly exceeding the milestone of 67 for this indicator. XCEPT continued to leverage major events to produce additional content for its website and social media, including talking head videos and podcasts from the MENA conference and GESI workshop. Highlights include:

- TAF collaborated with CPJ in Bangladesh to produce a documentary on community-based participatory research methods. The research lead was invited to discuss the work on the Climate Diplomacy podcast, hosted by German climate security think tank, Adelphi.
- Chatham House’s interactive articles on how supply chains fuel transnational conflict in the Middle East; and how conflict in Libya facilitated transnational expansion of migrant smuggling and trafficking.
- KCL featured in a Hidden Brain podcast episode with 3 million listens, leading to an invitation to contribute to Pearson's Social Psychology textbook. Nils Mallock’s article in The Conversation on Israel-Gaza became the outlet’s most read, leading to discussions at the Munich Security Conference and wide media coverage in German outlets.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The XCEPT logframe now only counts outputs once they have been published. Previously, in agreement with FCDO, XCEPT counted research paper outputs at the point that they were submitted to FCDO. This has been updated to align XCEPT with the rest of PCH programming.

Output 1 was also updated to include a category (1.1) for academic outputs (e.g., journal articles, book chapters and monographs). This was also to align XCEPT with other programmes in the PCH portfolio. Previously, academic outputs were counted alongside other high-quality, peer-reviewed outputs issued by think tanks and other research organisations. These outputs are now captured under indicator 1.2.1. Other research outputs, such as policy briefing notes, working papers, evidence reviews, background or scoping papers, and data sets are now included under indicator 1.2.2. Outputs from earlier programme years have been re-categorised to reflect these adjustments, and the revised totals presented here.

Lessons learned this year and recommendations for the year ahead – see front section.

Output Title	Policy engagement: Engagement with a policy audience at key stages from research design to dissemination, to build ownership and improve research uptake
Output number:		2	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicators	2025 Milestones / (cumulative)	Progress
2.1 Policy meetings. Number of meetings, briefing sessions and tailored presentations of research plans and/or research findings held with policy makers.	Total: 429 (85 this year) / C1: 177 (15 this FY) / C2: 173 (50 this FY) / C3: 79 (20 this FY)	Substantially exceeded: 481 Total (137 this year) / C1: 209 (47 this year) / C2: 177 (54 this year) / C3: 94 (35 this year) / C0 [x-component]: 1 (1 this year)
2.2 Public events. Number of public events to present research to a broader audience (panels, presentation at conferences, major workshops, etc.). (Disaggregated by whether the event is organised by XCEPT or externally)	Total: 125 (39 this year) C1: 47 (6 this FY) C2: 49 (17 this FY) C3: 27 (14 this FY) / C0: 2 (2 this year)	Moderately exceeded: 142 Total (56 this year) / C1: 63 (22 this year) / C2: 48 (16 this year) / C3: 27 (14 this year) / C0: 4 (4 this year)
2.3 Online views. Relative change in # of page views on the XCEPT website (and absolute number). Social media. Relative change in # of engagements and with XCEPT content across XCEPT social media (and absolute number). Newsletter. Relative change in # of XCEPT Newsletter subscribers (and absolute no.).	Website: + 4% (from 74,174 views [so target is 77,141]) / Social media: + 5% (on 7339 engagements [target: 7706]) / Newsletter: + 10% (on 1175 subscribers, [target: 1,293])	Substantially exceeded for website: 94,000 page views on the XCEPT website this year (up 27% from FY23/24). / Not met for social media: 1619 engagements across XCEPT’s Twitter/X and LinkedIn this year (down 78% from FY23/24). 125,474 impressions across XCEPT’s Twitter/X and LinkedIn this year (down 3% from FY23/24). / Moderately exceeded for newsletter: 1,391 newsletter subscribers this year (up 18% from FY23/24).

Briefly describe the output’s activities and provide supporting narrative for the score.

XCEPT moderately and substantially exceeded targets across all but one Output 2 indicator. Noting C1 targets were not revised since December 2023, we judge XCEPT to have moderately exceeded expectations for this output overall, with an impressive range of high level and impactful meetings and events over the course of the year.

Indicator 2.1: XCEPT substantially exceeded the milestone for this indicator, with 137 policy meetings this year against a target of 85. Additional meetings were largely driven by C1 partners, who substantially exceeded their target (which as noted, could have usefully been revised upward). These numbers also reflect previous year’s recommendations to increase HMG engagement at all stages of design. Highlights include:

Eastern Sudan: In November 2024, Chemonics partnered with Rift Valley Institute and Chatham House to host a conference in Nairobi on Eastern Sudan. The event, convened collaboratively with British Office Sudan (BOS), drew 50 policymakers and experts from multiple countries, including the UK Special Representative for Sudan. BOS and RA colleagues highlighted the success of the event, commending the quality of attendance and discussion. XCEPT led a follow-up briefing in February 2025. These events catalysed conversations on protection in the Sudan conflict, improved coordination between BOS and other diplomatic missions, and led to a strong Sudan research pipeline for XCEPT.

Syria: A MKCMEC researcher participated in a closed UN Commission of Inquiry meeting on Syria in June 2024, presenting the team's research on external actors. In February 2025, the researcher contributed to an elite EUISS workshop alongside senior EU policymakers including EEAS Managing Director Helene Le Gal and EUSR Sven Koopmans. The concept of 'cantonisation' was adopted in the discussion agenda. He delivered a 10-minute intervention on Syrian trends followed by policy discussion, with his recommendations shared afterward with EUISS.

Yemen: The XRF-funded Yemen research contributed to policy deliberations in various policy spheres, including through briefings to UK, US and UN policy leads on Yemen, other UN Security Council member states, and senior World Bank officials working on Fragility, Conflict, and Violence. The work enabled cross-government discussion of complex conflict drivers.

Indicator 2.2: XCEPT research was presented in 56 public research convenings this year, moderately exceeding the milestone for this indicator. As above, C1 targets were not revised in-year and have been substantially exceeded. While the C2 specific target was not met this year, C2 played the leading role in cross-component events, which were exceeded overall this year. Highlights include, panels at the 2024 Stockholm Forum on Peace and Development, the 2024 International Anti-Corruption Conference, a Wilton Park conference linked to King’s College London research (with accompanying event report), the Fragile Lives conference, and the Conflict Research Society Conference. This year also saw cross-component collaboration in four different events: the XCEPT MENA Conference, Fragile Lives, IACC, a panel at PeaceCon; and cross-programme engagement with RED-funded research programmes PeaceRep, SPARC, ReCIPE, Beyond Compliance and SOC-ACE.

Indicator 2.3: This year the XCEPT website recorded 94,000 total page views, marking a 27% increase on the previous year, substantially exceeding the logframe target. Posts highlighting funding opportunities through the XRF were the most popular, with the request for applications on research on conflict and climate receiving 6,729 views. Social media impressions decreased by 3%, to 156,474, while engagements decreased significantly by 78% to 1,619. This likely reflects changes in social media habits due to changes in the way that X operates; the trend has been seen across other programmes in PCH. XCEPT continued to issue monthly newsletters and has seen its subscriber base grow by 18%, to 1391, exceeding the target for the year.

Partner websites and social media remain a primary avenue for research dissemination and public outreach: the MKCMEC report “Double Dealers; Lebanon and the Risks of Captagon Trafficking”, released in March 2025, received 16,754 page views. On social media, posts on MKCMEC’s capstone report “Borders Without a Nation: Syria, Outside Powers, and Open-Ended Instability”, were viewed by 191,907 people (122,655 on Facebook, 69,252 on Instagram). The Chatham House report “Gold and the war in Sudan: How regional solutions can support an end to conflict”, published in March 2025, saw over 3,600 readers across 109 countries within the first week; at the time of writing, it was ranked as the top Google result for the search term “Gold Sudan.” New episodes of KCL’s Breaking Cycles of Conflict podcast series have reached 30,000 listens over the past year. The most popular episode – featuring Nafees Hamid and Dr. Hannes Rusch on the logic of intergroup conflict – garnered over 8,500 listens across SoundCloud and Spotify. XCEPT research was also featured in major news outlets such as Foreign Affairs, The Guardian, The Conversation, The Diplomat, Bangladeshi broadcaster BTV, German broadcaster ARD, and French weekly magazine Paris Match. Nafees Hamid’s appearance on the Hidden Brain podcast “Out of the Rabbit Hole” drew three million listens. Inna and Craig’s article on Mosul was named one of Peacebuilding journal’s most impactful, with social media shares reaching over half a million followers.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The 23/24 Annual Review recommended adjusting Output indicator 2.1 to distinguish between policy meetings which are focused on dissemination and those which are part of early-stage engagement in research design. It was agreed with FCDO/RED that Output indicator 2.1 would not be adapted in this way; instead, the team would continue to report on early-design engagements through XCEPT’s narrative quarterly reporting. XCEPT therefore continues to reflect under indicator 2.1 ‘policy meetings’ and engagements that are conducted for the primary purpose of research dissemination and uptake.

Lessons learned and recommendations for the year ahead – see front section.

Output Title	Networks: Establishment and expansion of a x-regional network of local researchers and research organisations capable of undertaking field work in sensitive border areas, through knowledge exchange events and training / capacity-building opportunities
Output number:		3	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicators	2025 Milestones	Progress
3.1 Number of knowledge and learning events organised for researchers from the Global South (cumulative)	Total: 25 (4)	Substantially exceeded. Total: 73 (52 this year)
3.2 Number of researchers from the global South benefiting from knowledge and learning events (disaggregated region by gender – cumulative)	Total: 367 (110); 40% women	Substantially exceeded. Total: 605 (348 this year); 50.7% women
3.3 a) Total number of researchers from the global South involved in X-Border research	Total: 150; year-on-year increase in % of women	Substantially exceeded. Total: 219 (55 this year); 37.8% women (34.7% last yr)
3.3 b) Total number of researchers from the global South leading X-Border research (disaggregated by region and gender)	Total: 52; year on year increase in % of women	Moderately exceeded. Total: 73 (21 this year); 39.4% women (28.84% last year)
3.3 c) # new researchers from the Global South involved in X-Border research	This year: 15; minimum 40% women	Met. 16 new researchers this year; 43.7% women
3.4 Professional development of local researchers supported by programme. Measured using tool and metric developed for XCEPT and tangible research outcomes (papers researcher/written, presentations delivered) as well as researchers' own perception; confidence in research skills etc.	75%	Substantially exceeded. / 98% (of 35 respondents)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 targets were set in late 2023 for the remainder of C1 delivery and were not revised following the last AR. This means targets were low compared to last year’s achievements, especially for indicators 3.3 a) and b). They were also set prior to the creation of the Women Researchers Fellowship which increased achievements across all indicators, especially 3.1. Considering this and the balance of achievements this year compared to previous years, we judge the output to have moderately exceeded expectations overall.

The accountable grant, delivered by C1 partners is coming to an end in FY25/26. Linked to this, and in response to recommendation 6 from last Annual Review, C1 partners contracted external partners Humanitarian Advisory Group (HAG) and GLOW Consultants to produce an internal and published review of the LRN. The review found that C1 has contributed to strengthening the capacity of local researchers through a diverse range of initiatives, including serving as a platform for building meaningful connections between researchers and with policy makers; supporting their visibility and credibility; and through developing on-the-job skills. The review found that most capacity building benefits were achieved through applied research experience, rather than structured training.

As C1 draws to a close, the LRN review should underpin XCEPT’s investment in the most impactful approaches to supporting Global South research capacity. The review highlighted that providing local researchers with opportunities to conduct and lead research, offering platforms to showcase their work, and opportunities to engage in events and present at conferences were the most impactful ways to support development, visibility and credibility. As C2 commissions research through the XRF, it will be essential to continue to offer these opportunities to support Global South expertise. The public briefing note can be found here: Localisation of Research and Evidence Generation in Conflict-Affected Borderlands.

Indicator 3.1 and 3.2: C1 delivered 52 knowledge and learning events over the reporting period, which benefitted 348 researchers. More than 50% of the researchers were women. C1 partners held two cross-regional in-person events this programme year, with the purpose of strengthening cross-C1 learning, strengthening the LRN (LRN), building synthesis outputs together, and validating findings from the LRN review. Highlights included:

- From 29 April to 1 May 2024, C1 held a three-day workshop in Bangkok, Thailand, bringing together 42 participants from the LRN. The event was the first in-person meeting of the LRN since early 2020 and first gathering of the Women Researchers Fellows.
- In February, C1 partners and researchers came together in Naivasha, Kenya to take stock of the programme achievements and milestones in 2024/2025 and reflect on key lessons since inception. Programme staff from TAF, RVI and MCKCMEC convened to discuss a roadmap to project closeout, including finalising ongoing deliverables and the reporting plans. FCDO and Chemonics also participated, helping to ensure relationships with LRN members, including Women Researchers Fellows, were solidified prior to C1’s close.

Indicator 3.3: Over the reporting period 55 researchers from the Global South were involved in cross-border research as part of C1 (37.8% women); of this 55, 21 led research (39.4% women), and 16 were new to the programme. A major achievement this year has been C1’s support to six early career researchers through the Women Researcher Fellows Programme. The six fellows, Htoo Htet Naing (Myanmar), Faryal Khan (Pakistan), Hilina Berhanu (Ethiopia), Moneera Yassien (Sudan), Ilyssa Yahmi (Algeria), and Salma Daoudi (Morocco), conducted independent research projects on XCEPT priority themes and geographies. These early career researchers published in international outlets, presented research at international conferences, and have been invited to work on additional professional research programmes following the XCEPT fellowship.

Indicator 3.4: This year, 97% of respondents confirmed that their participation in XCEPT contributed to skills development. The Local Researcher Capacity Monitoring Survey annually tracks the programme’s effectiveness in supporting local researcher professional development. The survey highlighted a range of areas where respondents saw improvement: 68% highlighted improvements in writing for a policy audience; 65% reported improved research methods; 47% reported enhanced skills in analysing and interpreting data; 44% in public speaking; and 41% in understanding research ethics. All respondents reflected positively on their overall experience with XCEPT, noting that their involvement has contributed meaningfully to their professional development and career growth.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

With C1 closing in the upcoming financial year, this output should be removed and incorporated into Output 4 on the XCEPT Research Fund, which will be the primary research commissioning vehicle going forward. Lessons from the LRN review should be incorporated in the XRF’s approach to commissioning to ensure researchers from the Global South continue to benefit from the opportunities XCEPT provides.

Lessons learned and recommendations for the year ahead – see front section.

Output Title	XCEPT Research Fund: The Fund is established and makes efficient awards to relevant downstream research and XCEPT-related awardees of value to the programme.
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	2025 Milestones (cumulative)	Progress (cumulative)
4.1. # of awards made.	C2: 62 (10 this year)	Moderately exceeded: 68 (16 this year)
4.2. % of awards led by, and meaningfully contributed to by, Global South researchers/organisations, with contribution referring to at least one third of the value of the award.	C2: 33%	Met: 33% (23 awards in total)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output indicator 4.1 moderately exceeded the milestone for this year, and indicator 4.2 met the milestone for this year. Considering the challenges of producing a plan for the XRF over the reporting period (detailed in Lesson 1 and below), we judge this output to have met expectations overall.

Over the next two years of the programme the XRF will serve as the primary mechanism for commissioning and contracting new research for XCEPT, marking a shift in the way the programme operates. Research delivered through the XRF will be responsible for delivering the programme’s consolidated impact, building on the body of research to date across C1 and C2, and leveraging and sustaining the networks created through the programme, notably the C1 LRN. We therefore recommend increasing the weighting and ambition of milestones against this indicator for future years.

Following the last annual review and as part of business case and contract addendum discussions during the reporting period, XCEPT was asked to produce an updated XRF strategy for commissioning that further developed future XRF research themes and questions, underpinned by an assessment of research gaps and clearly building on the body of work and USP of XCEPT so far. There were delays in producing a strategy that met FCDO expectations, and this became an increasing risk to programme delivery. The issues that arose partly reflected the lack of a shared analytical framework from earlier stages of the programme; the challenge of XCEPT’s three component structure and breadth of research to be built on; previous years’ challenges and delays in recruiting an academic Research Director[3]; and delays in appointing XCEPT Research Fellows. In this reporting year, the team recruited three research fellows to work with the implementing team on the three priority thematic areas for the XRF going forward, and this has markedly improved synthesis plans, XRF research planning and coherence. In early March 2025, XCEPT presented an updated approach to commissioning through the XRF to ensure both conceptual and instrumental impact over the final two years of the programme. This gave FCDO confidence in the future direction of the programme as it moves into the Addendum phase.
[3] Recruitment challenges led to XCEPT’s research leadership group in Sept. 2023 concluding that no single Research Director could represent the programme; RED and XCEPT decided to instead recruit three Research Fellows to align with approved XRF workstreams. Recruitment of those Fellows was then delayed over subsequent quarters.

Indicator 4.1: Over this reporting period the XRF made 16 new awards, substantially exceeding the target for the year. XCEPT closed 19 awards, 13 of which were projects addressing GESI issues following an open call last year. The XRF has continued to commission projects in areas of established strength, for example on Yemen, Sudan, in participatory action research, and on understanding checkpoint dynamics and armed actor control in borderlands. The XRF has also launched new research on conflict and climate, through a major award to NUPI and in collaboration with the new Conflict and Climate Fellow. The XRF maintained flexibility to respond to evolving policy needs, such as the XCEPT-hosted workshop on Eastern Sudan and rapidly commissioned of follow-up research.

Indicator 4.2: This year, researchers and organisations from the Global South led or contributed to 33% of awards under the XRF, meeting the target for this year. Highlights include Daniel Agbiboa’s follow on research on insurgents in the Lake Chad Basin; and a new award with local organisation, Karamoja Herders of the Horn and partner, Friends of Lake Turkana, building on earlier research with IDS while deepening local academic ownership. Across the XRF, partnerships with Global South organisations played a central role in knowledge generation and capacity strengthening. In South Sudan, Queen’s University Ontario trained researchers from STEWARDWOMEN in sensemaking methodologies, supporting a community-led inquiry; in the DRC, Canada’s York University collaboration with SOFEPADI enhanced local research skills and contributed to psychosocial support for displaced women; and in Bangladesh, BICC’s project involved five local researchers, two with no previous research experience, fostering professional growth. The XRF created platforms for researchers from the Global South to lead and share their work. This included centring local voices at the XCEPT MENA Conference, XCEPT workshops on West Africa, Eastern Sudan, and on Gender and Inclusion; and including local voices in panels at international events such as the Stockholm Forum on Peace and Development and Fragile Lives. These engagements amplified local perspectives and fostered direct connections between Global South researchers and other Northern and Southern academics and policymakers, strengthening their role in shaping research agendas and responses to conflict.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

We recommend increasing the weighting and ambition of milestones against this indicator for future years. Maintaining a high proportion of engagement and delivery by researchers from the Global South also remains important and this should include opportunities for the LRN engaged under C1. This should continue to be tracked as part of Output 4. Going forward, the programme should incorporate indicators from Output 3 to track the total number of researchers from the Global South involved in or leading research through the XRF, disaggregating current Output 4.2 into to sub indicators.

Lessons learned and recommendations for the year ahead – see front section.

D: VALUE FOR MONEY

Key cost drivers and performance

The programme has been operating since 2018 and the key cost drivers from the Business Case remain valid. These are: the cost of research personnel, uptake activities, management and monitoring costs. Chemonics/TAF developed a VFM Framework in February 2025, which has been used as the basis for providing quantifiable and qualifiable evidence of VfM delivery and to clearly show the impacts, outcomes and outputs of the programme. This included a workshop attended by FCDO PM and Research Manager who provided input to its development. The framework will be revisited following this AR to consider whether updates are needed. Whilst the framework has only been in place a short time, its development significantly strengthened the programmes approach and understanding of VfM.

Economy

XCEPT conducts thorough budget reviews for each award and contract, evaluating VfM and assessing the researcher level of experience and fee rates, which are compared to their benchmark rates. XCEPT negotiates rates to align with internal benchmarks ensuring parity across the project teams. All contracted work is agreed with phased delivery schedules covering time and quality standards.

On the research fund (XRF), the team review all proposed costs against the researcher’s experience, input level/fee, research objectives and workplan. This often involves adjustments to agree the final budget and can result in savings. For example, budget savings of £190,000 were achieved across two large awards in Africa in FY 24/25.

Chemonics XCEPT bring in personnel to work on activities that are required intermittently, in order to reduce the project’s full time staffing needs. This includes:
  - Using an established pool of vetted editors and graphic designers on flexible contracts, ensuring timely, consistent and high-quality editing of programme publications and briefing materials.
  - Filling short-term needs for technical guidance on select awards, to support research synthesis and development, to expand public communications and to support Fund management. Engaging external experts on a fixed scope of work and level of input against benchmarked rates keeps costs to a minimum.

TAF conducted a competitive tender for their LRN review in response to last year’s recommendation 9. From 35 applications four were shortlisted for interview. The joint HAG and GLOW bid scored highest overall. Although it was the most expensive at £48k TAF negotiated their budget down to £25K reaching agreement within the required delivery requirements.

TAF meets ad hoc project needs from existing systems and staff availability across their organisation rather than outsourcing or recruiting. TAF’s regional team has a range of skilled and trusted designers and editors that are available to fill key roles on ‘Indefinite Delivery, Indefinite Quantity’ (IDIQ) contracts when necessary. Those engaged on IDIQs include professionals from the Global North and South.

Efficiency

XCEPT partners met or exceeded all output targets for the year demonstrating the efficient use of programme resources and strong performance in outputs, policy engagement, and network development as evidenced above. In research development, C2 and C1 partners supported awardees and LRN members with a track record of high-quality delivery and research impact to undertake new research that expands their contribution to key programme themes.

The XRF (C2) approved researchers, previously selected through open competition, to develop and expand on prior work and advance core XCEPT themes e.g. focussing on research along the Kenya/Uganda and in the Lake Chad Basin. This maintained project momentum, as it retained the same contacts/networks. The XRF also solicited proposals from C1 researchers whose work aligns with XRF thematic direction, including research on South Sudan and armed actor checkpoints in borderlands saving time with those working in the same themes.

Each XRF award is overseen by a Senior Research Manager (SRM) responsible for technical delivery, with the Fund team providing additional oversight on finance and compliance. Regular check-ins on progress help identify delays and/or risks that could impact on delivery early and capitalise on emerging opportunities. These meetings, either monthly or aligned to delivery of milestones allow adjustments to be made early to ensure achievement of the planned outputs and are further supported with quarterly reporting from awardees leading into impact assessment, and learning.

C1 partners held regular coordination meetings to track project progress and make adjustments as needed to initiate any action necessary to ensure successful delivery. For instance, two project timelines and contracts were revised due to the political unrest in Bangladesh but with support from TAF, both research projects were delivered on time and achieved strong domestic engagement.

Effectiveness

C1 and C2 re-invested in researchers whose work advanced programme impact. XCEPT used HMG and other stakeholder engagements to help identify areas for research uptake, as well as potential areas for expansion. XCEPT research is also being increasingly cited in grey, academic literature, and the media. XCEPT research has numerous examples of COM-B change (Capability, Opportunity, Motivation – Behaviour) to demonstrate VfM and key examples are highlighted below:

Behavioural Change: XCEPT evidence on cross-border and transnational conflict was applied by HMG and other policy stakeholders in multiple ways this year, including in JACS on Lebanon and Ghana; BE Tripoli’s conflict assessment; as the basis for analytical and policy papers on Yemen and Sudan; and informing Somalia Stability Fund decisions on how to approach in different contexts. KCL (C3) research on trauma, memory and conflict featured at a Wilton Park/FCDO workshop, prompting the FCDO Iraq team to work with KCL to consider how to inject the research findings into programming.

Capacity Change, Capability: XCEPT research has been lauded by UK and other government and multilateral stakeholders for improving understanding of cross-border conflict and borderland dynamics and filling critical evidence gaps. Examples include XRF research by Alcis and David Mansfield on cross-border violence between Iran and Afghanistan, Chatham House research on Sudan’s Gold and the Axis of Resistance (C2), KCL research on Syria’s new leadership and the Taliban (C3), RVI research Ethiopia and Red Sea trade corridors, and MKCMEC research on Saudia Arabia and Salafism (C1).

Capacity Change, Opportunity: XCEPT's research on Coastal West Africa was key to a more joined up policy response: XCEPT’s investment positioned the UK to advance analytic coordination among international donors, helping to strengthen joint initiatives like the Coastal States Stability Mechanism. UK bilateral partners and regional governments noted the application of the research findings in ministerial briefings and in dialogue with regional neighbours. C1’s participation in a FriEnt Berlin workshop led to research being included in submissions to and representations at COP29.

Capacity Change, Motivation: XCEPT research and its tailored approach to uptake, particularly among policy actors motivated stakeholders to apply XCEPT evidence. Examples include: UN and OECD sought to incorporate XRF research on the Lake Chad Basin in their analysis; XRF research by PRIO on mediation in internationalised conflicts prompted FCDO mediation experts to stress the importance of integrating rigorous analysis into mediation practice and better understanding how UK involvement influences dynamics; and research by XRF awardee the University of Western Ontario prompted interest across among judges, lawyers, diplomats and civil society representatives in the Hague to apply best practices on the use of technology to investigate conflict-related sexual violence surfaced by the research.

Equity

XCEPT has applied expertise in gender, equality and social inclusion (GESI) to ensure equitable research and programme activities, informing design and delivery based on effective practices, and identifying and engaging targeted stakeholders in a human-centred and accessible manner. The XRF review of risk management and capacity-building strategies to enhance its approach to equitable research led to practical improvements, including policy updates, HR enhancements, and refined management procedures.

C1 partners invested in increasing women’s participation in research on fragile and conflict-affected areas, significantly increasing the number and capacity of women researchers. Initiatives like the Women Researchers' Fellowship have boosted female representation, with half of Global South researchers in training events since 2018 being women, exceeding the 40% target. The percentage of women researchers leading C1 projects rose by over 10% in the past year, with nearly two in every five leaders being women. For the C2 XRF, 40% of projects are led or co-led by women.

The XRF continues to invest in GESI focused research; the XRF completed 13 awards in FY24-25 with an explicit focus on GESI issues linked to the transnational dimensions of conflict. Where relevant, the XRF brought on external GESI experts in a short-term capacity to support awardees in strengthening their work.

XCEPT prioritises featuring local researchers in policy meetings and events, such as the October 2024 MENA Conference and the XCEPT Sudan Workshop, to elevate local voices and strengthen their roles in shaping research agendas.

XCEPT uptake and communications approaches are designed to make research as accessible as possible. C2 research on East Africa used animated videos to bring research findings to communities in safe, relatable ways, sparking dialogue and a strong sense of ownership. C1 partners used video podcasts, documentaries and personal stories to tell impactful stories about the LRN. XCEPT research disseminated in local languages helped local researchers gain traction and enhanced research use. A range of written and video outputs were disseminated in Arabic, French, and Bangla this year.

Cost-Effectiveness

XCEPT has produced stronger outcomes this year and has met or exceeded all output targets for the year demonstrating the efficient use of programme resources in balancing the aim to achieve value for money while aiming high to keep the project networks feeding into HMG and other parties’ needs.

XCEPT has generated policy interest and engagement, built research networks, and created a body of knowledge and evidence demonstrating a strong commitment to value for money. Chemonics and The Asia Foundation have demonstrated their commitment to VFM bringing out strong examples against each of the four key areas (Economy, Efficiency, Effectiveness and Equity) for the betterment of the research. The regular engagement with FCDO and other key actors in the field has been maintained throughout, providing efficient use of funds whilst increasing involvement of southern researchers to increase returns on equity considerations.

Instrumental Impact:
- FCDO gained value from two XCEPT convenings on Eastern Sudan which offered an opportunity to develop a common analytic picture and discuss policy challenges with key UK counterparts. Sudan research also informed at a private FCDO roundtable in late March in preparation for the Foreign Secretary’s April Ministerial on Sudan.
- Chatham House’s September 2024 research workshop on conflict response provided policy lessons and informed their capstone policy paper published in June 2025.

Conceptual Impact:
- XCEPT’s Lake Chad Basin research influenced UN and OECD studies on civilian roles in weak-state security. The findings were incorporated into a database used by scholars and practitioners.
- CH research on transnational dynamics of authority and violence was shared with policy actors and experts in a November 2024 workshop and underpinned CH research and subsequent public and private engagement. C1 work has been cited in official government documents of Canada, Denmark, Austria, Italy, France, Iraq and the Philippines, as well as the EU.

Capacity Building Impact:
- The LRN significantly strengthened capacity of local researchers in FY24/25, (25 C1 events for 348 Global South researchers with a 60% women’s participation rate) and generating opportunities for them to build their skills and careers.
- LRN alumni now work for the International Crisis Group and UN Women and undertaken doctoral research in the UK and Canada.
- The February 2025 XRF GESI workshop brought together 40 XRF and LRN researchers from five continents, enabling discussion on gender in global security and the need to elevate local, underrepresented voices in research.

Enduring Connectivity Impact:
- The LRN review highlighted the value of networking opportunities afforded by XCEPT and provided recommendations for sustaining the work into the next phase.
- C1 supported six women researchers through a dedicated fellowship in FY 24/25 enabling growth in their research field and developing leadership and collaboration opportunities.
- XRF (C2) participation in the final C1 convening in Kenya helped generate opportunity for ongoing C1 LRN researcher involvement in XCEPT research.
- KCL’s work on sacred values has spurred collaboration with the Berghof Foundation, UN offices and other organisations keen to incorporate key concepts from neuroscience into conflict mediation and peacebuilding.

XCEPT is delivering high-quality, policy relevant research which is valued by a range of stakeholders across HMG and beyond. They are achieving project outcomes (research being used to address conflict and instability more effectively, high recognition of publications in the field) whilst minimising costs without impacting the effectiveness or equity of the programme. Through careful analysis, the programme has demonstrated a commitment to value for money throughout the programme cycle, representing an efficient and effective investment of taxpayers’ funds.

Assessment of whether the programme continues to represent value for money

Overall the programme continues to represent VfM: programme processes, including XRF commissioning and award management, have been tested and refined to deliver multiple, sizeable research awards which deliver tangible outputs, leading to stronger outcomes.

E: RISK

Overview of risk management: The overall risk of this project post-mitigation is Major as it has been since the project started.

Strategy & Context	Policy and Programme Delivery	Safeguarding	Public Service Delivery & Operations	Financial & Fiduciary	Reputational	People
Major/ Possible	Major/ / Possible	Moderate/ / Possible	Moderate/ / Possible	Moderate/ / Unlikely	Moderate/ / Possible	Moderate/ / Unlikely

Programme risks are continuously assessed and updated. A new risk was added this year under ‘Reputational’ section (see below). All overall risks are within FCDO’s risk appetite, and any higher risks are escalated in line with procedures. Current key risks are summarised below. The current key risks are summarised below:

Risks	Mitigation measures
Strategy & Context
Volatile security situation disrupts research - Evolving conflict in research locations could lead to impact on programme delivery (MAJOR)	Remains stable at Major. XCEPT research operates in volatile areas. Security incidents in FY2024-25 caused moderate disruption, including researcher displacement. All personnel remained safe due to effective risk protocols and strong partner coordination. / Bangladesh: Following the collapse of the government (Aug 24) TAF worked with partner CPJ to ensure the safety of researchers and minimise disruptions to fieldwork. / Lebanon: The MENA conference was moved from Beirut to London due to regional instability, MKCMEC's workshop on illicit activity and drugs was moved from Beirut to Istanbul due to tensions between Iran, Israel and Hezbollah and KCL’s Impact of Trauma Survey (IoTS) was put on hold while addressed contingency options, Oct 24. / Myanmar: TAF arranged remote participation for Htoo Htet in the Women Researchers' Fellowship as travel from Rakhine State was impossible. Kachinland Research Centre faced an internet blackout (Aug 24) requiring researchers to travel long distances although TAF adjusted plans to meet delivery schedules. / Sudan's conflict limited Chatham House (C2) field data collection. RVI researchers faced challenges in West Darfur, Chad and Libya borderlands, eventually cancelling research In South Sudan, KCL closely monitored partner activities during violent incidents in November and March limiting fieldwork to urban and semi-urban areas in late 2024. / TAF and Chemonics closely coordinate with research partners to monitor high-risk environments and implement risk mitigation for field travel. / All research teams receive context-specific security training and support. XRF evaluates awardees' security, safeguarding, risk management, and duty-of-care protocols during the award assessment process. / Partners and awardees conduct security risk assessments before fieldwork, identifying risks and mitigation measures which Chemonics reviews and offers additional support where required. / Delays are addressed by using local partners, remote collection, avoiding insecure areas, and operating from safer alternative locations. / XCEPT regularly reviews plans with partners and stakeholders, adjusting activity sequences to prioritize research in more stable areas or on less sensitive topics when necessary. XCEPT continues to update RED on major security and safety risks.
Policy and Programme Delivery
Partner outputs do not meet appropriate standard of quality expected by the programme, resulting in failures of research delivery and programme impact (MODERATE)	Stable at Moderate. / Research quality across Components reflects agreed-upon criteria for rigour, based on the Frascati Manual, PRoF and through regular review. / XRF awardees needing additional support are subject to close oversight, tailored guidance, and editorial support. In the event of underperformance, an improvement plan is created, with clear timelines and standards for delivery. / C1 partners produce yearly workplans for approval by FCDO, engage regularly during the research process with FCDO in London and post, and circulate drafts for comment.
Delays to field data collection and changes to research design affect programme timelines / (MAJOR)	Stable at Major. / Chemonics XCEPT regularly engages with partners and XRF awardees on work planning, providing guidance and support as needed in response to field and project delivery challenges. / New crises in key programme geographies caused some delays in research and alteration in research plans. / The XRF awards have regular awardee check-ins that enable the team to proactively review awardee progress toward FY output targets and contract obligations, advising on alternative work planning as needed. / C1 research operates on yearly timeframes. Partners engage regularly with downstream researchers to ensure work is on track, deploying mitigation measures early to address major delays.
Safeguarding
Research in conflict-affected situations raises serious ethical and human rights challenges (MAJOR)	Stable at Major. / C2/C3 partners and XRF awardees conduct a risk assessment prior to commencing research and each round of data collection. This risk assessment is reviewed by Chemonics XCEPT programme team, security team and Safeguarding Lead to sense check and provide further advise and recommendations. / Review of XRF awardee research plans includes scrutiny of research design and data collection. Ethics and safeguarding risks and mitigation measures are considered as part of this review. All XRF awardees commit to XCEPT’s safeguarding policy. / C1 partners uphold PSEAH and child safety standards, coaching downstream partners on ethics. A GEDSI training was delivered to LRN researchers in May 2024. Risks are monitored throughout implementation, though some residual risk remains due to power imbalances in research.
Financial and Fiduciary
Poor forecasting and process delays (MODERATE)	Stable at Moderate. / C2/C3 partners and awardees are often subject to organisational procedures that delay research delivery and operations, raising spend and forecasting risks. Chemonics XCEPT mitigates this through routine engagement with partners and regular check-ins with awardees, alongside monthly progress reports to discuss workplan progress and adjustments, as needed. Where relevant, risks are shared with RED. / C1 conducts weekly internal updates on financial and programme monitoring, monthly detailed check ins on previous month spending and forecasting, and quarterly reports and as needed ad-hoc updates from major partners on spend and future projections. / Ongoing budget uncertainty and delays in funding confirmation by FCDO pending the outcome of the spending review has disrupted partners approach to the programme and confirmation of workplans. This has made it difficult to forecast expenditure accurately and commit to future activities, with knock-on effects on the programme’s ability to maintain a smooth operational flow leading from one financial year to the next. This may impact implementation of planned activities and affect achieving outcomes and deliverables.
Reputational
Researchers / or research organisations may not readily disclose activities that could affect XCEPT’s reputation as an independent research programme funded by the UK Government / (MODERATE)	Remains / stable at Moderate / Chemonics XCEPT programme management team conducts expanded due diligence on all C2/C3 partners and XRF awardees. All undergo thorough due diligence, including reference checks and online searches of all named personnel in proposals. / TAF conducts a thorough due diligence check on partners including compliance with stringent donor requirements, such as undertaking an anti-terrorist check and checking potential awardees against the US Excluded Parties List System.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

This programme is delivered through three components:
- Component 1, Accountable Grant with The Asia Foundation (TAF) – LRN, (March 2018 to February 2027 - £10m [ending FY25/26])
- Component 2, Contract with Chemonics – Cross-Border Conflict Evidence, Policy and Trends (XCEPT) research programme Lot 1, (May 2020 to February 2027 - £17.70m)
- Component 3, Contract with Chemonics – Cross-Border Conflict Evidence, Policy and Trends (XCEPT) research programme Lot 2, (April 2020 to February 2027 - £8.62m)

Programme delivery is monitored through meetings every three weeks between the partners and FCDO, where programme updates, finance and risk management are all discussed to ensure that we are delivering effectively.

TAF and Chemonics continue to deliver their quarterly narrative and financial reports on time and of high quality. Both partners employ transparent and efficient financial and project management processes to track performance against workplans, logframe and budgets. Chemonics has also met the key performance measures in the contract. The management teams communicate frequently with their partners and XRF awardees to ensure high performance standards, careful financial management and timely delivery. Risks and issues that arise are managed proactively and in partnership with downstream partners. As relevant, these are escalated to RED.

Chemonics XCEPT reviewed and revised their due diligence processes during FY 24/25 which strengthened them further and resulted in the addition of further online checks of all contracted individuals and organisations.

Approval for the XCEPT contract extension through to February 2027 was received in December 2024. The ongoing budget uncertainty from the current spending review impacted on research and programme planning for this year and future years. The delays experienced in finalising the contract amendment required reaching agreement on planning and budget projections to meet the aims of the extension without knowing the budget that would be available. FCDO and Chemonics agreed to a reasonable expenditure plan that would be revisited after the outcome of the spending review is announced.

Chemonics worked with partners and FCDO to refine programme planning and budgeting for the extension phase. C2 and C3 met contract break-clause requirements when the XCEPT research direction was agreed in March 2025.

	Component 1	Component 2*	Component 3*	Total
FY 2024/2025 budget	£2,100,000	£3,210,021.28	£1,339,643.00	£6,649,664.28
Spend to December 2025	£1,340,493	£1,669,710.75	£744,769.40	£3,754,973.15
Spend for January-March 2025	£678,585	£1,377,239.01	£535,102.24	£2,590,926.25
Total Spend	£2,019,078	£3,046.949.76	£1,279,871.64	£6,345,899.40
Difference	£80,922 / underspend	£163,071.52 underspend	£59,771.36 underspend	£303,764.88

*There are performance-based payment mechanisms within the two Chemonics contracts tied to Key Performance Indicators (KPIs). Should performance not be of an agreed standard 10% of fees can be withheld and only paid once issues are resolved. In FY 2024/2025, no fees were withheld.

The C1 Accountable Grant (TAF) budget was underspent in 2024-25 but this has been tentatively approved for carry forward into FY25/26, dependent on the outcome of the SR.

On the C2/C3 contracts the 2024-25 budget was underspent with the balance tentatively approved for carry forward into FY25/26, dependent on the outcome of the SR. Underspend was driven in part by context-driven shifts in research planning, illness within the team, a consultant not invoicing on time, and savings on the XRF from researchers not meeting planned spend or failing to invoice.

Chemonics and TAF have provided their asset registers. The C2 register is waiting on items purchased under the research fund being logged and will provide that as soon as possible.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

FCDO has regular meetings with both TAF and Chemonics and meets periodically as a group to discuss progress, follow up on Annual Review recommendations and for work planning, including cross-programme activities or communications. XHAG Meetings were paused during programme planning for the costed extension. A reformatted XHAG will reconvene in Q1 of FY25/26 to better align with XCEPT’s thematic research streams (see recommendations).

In the context of global changing aid architecture and the UK’s move to reduce aid spending to 0.3% of GNI, there are increasing pressures to show real-world impact of UK investments. For the year ahead recommendation 1 is linked to M&E to ensure a programme plan for delivering impact, and to strengthen outcome level change tracking.

As discussed in Output 3, TAF contracted external partners Humanitarian Advisory Group (HAG) and GLOW Consultants to review the LRN approach Findings were presented to FCDO, XCEPT and researchers at a validation workshop in February 2025; an internal report was shared in March 2025. A policy brief also published on the XCEPT website in March 2025.

The mid-term review of the programme began in early 2025, later than planned due to programme adjustments arising from the pandemic and the war in Ukraine. The review undertaken by Agulhas is examining outcomes and outputs across the programme to offer recommendations to inform the final phase of research. The final report is due in Q1 FY 25/26.

This Annual Review was written by the Programme Manager and PRO drawing upon the partners’ annual and quarterly reporting; meetings with Chemonics, Kings College London, and XRF Awardee; and feedback from colleagues in FCDO and other select stakeholders.

Evidence

XCEPT provides external, independent, rigorous research with a long-term funding commitment that allows it to produce a large body of evidence over time as a global public good. XCEPT directly informs FCDO and HMG strategy, policy, operations and programming, with impact around the world. Where possible and applicable, data and evidence is disaggregated by age, gender and disability, and the gender of researchers forms part of regular monitoring.

Learning

Lessons from the implementation of the programme over the course of the past year are articulated at the front of the Annual Review. The main learning from XCEPT is the research and evidence itself, which is shared in journal articles, newsletters and websites, academic conferences, and policy engagement. This is contributing to shaping the field as laid out earlier in this Annual Review.

Date of last narrative financial report	C1: 29 May 2025 / Chemonics (C2/C3): 14 May 2025	Date of last audited annual statement	C1: Accounts published 23 January 2025. / Not required for C2/C3 as they are contracts