ADDENDUM TO BUSINESS CASE

INCLUDING FOR BRIDGE FUNDING AND COST EXTENSION

SUMMARY INFORMATION
Project Name	Cross-Border: Conflict Evidence, Policy and Trends (XCEPT)
Country or region targeted	Global / multi-country research. Middle East and North Africa, Horn of Africa, West Africa, Afghanistan and Ukraine
Type of cost extension (if applicable)	Cost extension
Original project budget	£29 million
Original project start and end dates	1 October 2017 – 1 October 2024 / In June 2022 the programme was extended until 28 February 2027 via a no-cost extension to account for FCDO’s requirement to lower annual spend. Funded research currently ends March 2025.
Cost extension value (if applicable)	£9,341,226
New reduced budget (if applicable)
New project end date (if applicable)	N/A end date will remain 28 February 2027.
Business Case Quest Document No.	https://iati.fcdo.gov.uk/iati_documents/18779806.odt

INFORMATION
What is the project’s purpose?
The intended outcome of XCEPT is that: / FCDO, HMG and partners are better informed and better able to use programme-generated evidence to adjust intervention strategies and polices to address conflict and instability more effectively. / Conflict is worsening and becoming more deadly. In 2022, there were 55 violent conflicts and a 97% increase in deaths on the previous year. By 2023 that rose to 59 conflicts, the highest number since the data collection’s starting point in 1946. Among these, the most long running and destructive conflicts are hybrid conflicts which contain ‘internal’ and ‘external’ dimensions, for example Sudan, Syria, Yemen and Somalia. Their complex and prevalent transnational aspects make them particularly resistant to conflict resolution efforts, as well as producing multiple spillover and diffusion effects which are challenging for policy actors to respond to coherently. Civilians, particularly women and girls, bear the brunt.[1] / Conflicts are complex systems that connect across borders, intertwining the licit and illicit, formal and informal. These dynamics rarely adhere to state borders, but too often conflict is understood and addressed at the state level. This misses key transnational dynamics that fuel and enable conflict, and potential opportunities to promote peace and stability. / Internationalised conflicts have a direct impact on the UK, threatening economic growth and national security by disrupting access to markets, supply chains and energy routes, creating the conditions for organised crime, extremism and terrorism to flourish, displacing populations and fuelling irregular migration. Violent conflict contributes to poverty by causing damage to infrastructure, institutions and production; destroying assets and the environment; breaking up communities and social networks; forcing displacement, increasing unemployment and inflation. In conflict, ODA is diverted to manage the consequences of conflict and respond to humanitarian need, rather than advancing development goals. / Understanding what drives and prevents conflict is fundamental to UK government objectives to reduce poverty and retain a liveable planet. Research on cross-border conflict is needed to underpin the UK’s foreign policy and programming. This will help the UK work more effectively to address long term drivers of instability, help fill evidence gaps on emerging transnational conflict issues such as conflict and climate, and support the UK and its partners to develop new responses to cross-border and transnational conflict challenges. / The XCEPT programme is a high-profile research partnership between FCDO and Chemonics UK, working with UK and international researchers and institutions, that produces independent, rigorous, peer-reviewed research on: / the transnational dimensions of conflict and international conflict responses; and / the drivers of violent and peaceful behaviour. / Performance to date / XCEPT provides high-quality, responsive, policy relevant conflict research and advice to HMG and partners. XCEPT supports RED’s engagement across FCDO, bringing senior policy and programme colleagues together with researchers to ensure decisions in conflict and crisis contexts are evidence based. XCEPT supports UK engagement across governments by generating a shared understanding of conflict contexts with likeminded partners. The XCEPT programme has achieved A+ scores for high-quality, impactful delivery since 2021. XCEPT’s flexible, adaptive approach to delivery ensures that programme research informs policymaking and conflict response within a shifting geopolitical context. Policy stakeholders interviewed as part of the 2024 annual review underlined the relevance of the XCEPT research, with the programme’s transnational lens filling a conceptual gap and adding depth to understanding of conflict dynamics across Asia, Africa, and the Middle East. The latest review contains a range of examples of outcome-level change, where research has influenced policy and practice, underscoring the value of the programme. / Examples of XCEPT research and impact: / Research into conflict-affected borderlands in East and the Horn of Africa was incorporated into UK programming.[2] It formed the basis of the first-ever Integrated Security Fund (ISF) regional programme worth over £10m. The research is being used by HMG leaders in the region (e.g., Horn of Africa Envoy and Political Counsellor to Sudan) to shape the international community’s strategy to food security in Sudan and engagement with the Ethiopian Government on the Sudan conflict. / Elevated local voices to deepen insights on cross-border conflict and promoted locally driven responses. XCEPT’s community-led research along the Kenya-Uganda border mobilised communities, spurred national-level engagement with local actors, and fed into ministerial meetings in host countries. This accelerated cross-border interventions to address persistent insecurity, including a draft resource sharing agreement between the two states. In May 2023, a Ugandan Minister praised the usefulness of the XCEPT briefing note for its framing of the issues. / XCEPT research on memory, violence, and post conflict reconstruction in Iraq informed post-conflict reconstruction within the UK-led multi-donor Partnership for a Resilient Ukraine. / However, the global conflict context has shifted radically since XCEPT’s design: / Globalisation, technological developments and climate change have increased the international reach of malign state actors, organised crime groups, and violent extremist organisations. At the same time, conflicts and peace efforts are increasingly fragmented and multipolar, making effective response more challenging. / Africa’s most protracted conflict hotspots are increasingly characterised by porous borders, transnational violent extremist groups, climate threats, and the presence of foreign security providers such as Russia Corps. A series of coups in West Africa and the Sahel has worsened instability and challenged regional response mechanisms. Global geopolitical competition is playing out more acutely, whilst borderland regions have increasingly become ‘hotspots’ in these proxy wars. / Internationalised and regional conflict in the Middle East has escalated and is affecting other regions. The war in Israel/Gaza is spilling over into Lebanon, drawing in Iran, and adding to the crisis in Sudan, further destabilising the Red Sea and Horn of Africa regions. For the ninth consecutive year, transnational extremist group IS/Daesh killed the most civilians worldwide in one-sided violence. / The rise in food and fuel prices worldwide has shown the far-reaching impact of the war in Ukraine. Russia is increasingly pursuing its goals via engagement in other conflicts, such as Sudan, Yemen, Syria, Somalia, and across the Middle East. / There has been a step change in climate urgency with the risk average temperatures could exceed 1.5 degrees above pre-industrial levels in 2024. Climate change exacerbates resource scarcity, uncertainty, and perceptions of insecurity; it is increasingly acknowledged as a “risk-multiplier” in unstable and conflict contexts. / Borderland regions have become increasingly vulnerable to food, price and climate shocks, creating strong pressures for outmigration, whilst states are under pressure to securitise and fence ‘troublesome’ border zones. / While many of these phenomena have long antecedents, it has become increasingly clear that conflict and hard security have become more prominent factors in the choices that the UK faces, characterised by multipolarity and geopolitical fragmentation. While state threats are not new, the severity of the risks posed has grown because of the increased competition between major powers and the combination of the use of new digital technologies with more traditional capabilities deployed to destabilise other countries. Increased geopolitical competition and growing interconnectivity between different regions, events and movements has narrowed the apparent divide between security issues in unstable countries and domestic national security issues in the UK, presenting challenges for coherent responses.
What is the objective of the cost extension or other changes?
This extension meets UK and global evidence demands on complex, transnational conflicts at a time when the number of conflicts is highest since 1946, and the impact of conflict stretches further than ever, in an increasingly interconnected world. / There is insufficient understanding of how to respond to this increasingly complex and multi-layered landscape. Policy makers and programme teams too often approach conflict and instability from a state-centric perspective. This represents an increasingly important area for RED’s research that explicitly aims to enable more integrated understanding to develop improved responses. These issues lead to a set of potential research questions that are important globally and for HMG, such as: / How can we better predict and mitigate potential spillover effects from conflicts and factors contributing to conflict, such as climate change, political instability, foreign information manipulation and interference? / How are malign state and non-state actors using new technologies and more traditional capabilities in their efforts to destabilise countries and regions? How can technology be deployed to more effectively counter these effects? / How can more inclusive development and security policies help promote sustainable livelihoods and stability for borderland communities? / How can HMG and its partners respond more effectively to the transnational licit and illicit economies fuelling and enabling conflict and instability, for example the use of economic incentives? / How can the green transition be harnessed for peace and stability outcomes in fragile and conflict-affected border regions, and what works to support climate adaptation and mitigation in those regions? / This XCEPT extension will build on existing research, and develop new research, on: / Transnational Conflict: Expand research on the transnational nature of conflict and conflict responses, including policy relevant analysis on borderlands, conflict enablers, and conflict and climate. / Violent and Peaceful Behaviour: Deepen and build out the analysis of violent and peaceful behaviours to answer questions about resilience and protective factors that buffer some from resurgent violence and cycles of conflict. / New Frontiers: Flexible resource to generate evidence on the new frontiers of cross-border and transnational conflict, in line with the government’s emerging priorities. / Across all three themes: / Research and evidence will be independent, rigorous and peer reviewed to ensure strong accountability, ensure research is in the public good, and is aimed at ensuring HMG and partners are delivering more effective international responses to conflict. / RED Senior Research Fellow expertise will help ensure new research areas respond to recognised academic gaps, working to identify where FCDO funded research brings particular advantage. / The Programme Funded Post will drive quality integration of learning into FCDO. / 1. Transnational conflict: / During the first phase of XCEPT, the Chemonics-led consortium delivered research on transnational conflict focused on conflict-affected borderlands and what connects conflicts across borders and regions. XCEPT identified three thematic areas under which to consolidate new research on transnational conflict in Component 2 of a costed extension: i) stability and governance in borderlands, ii) conflict enablers, and iii) conflict and climate. Research commissioned under these themes will build on research from the first phase: / Stability and governance in borderlands / XCEPT’s first phase challenged the characterisation of borderlands as ungoverned hinterlands, showing they are often centres of gravity where complex geographical, political, and social dynamics impact the state centre and regionally. / XCEPT analysis identified factors contributing to instability and violence in border regions; as well as the hybrid governance systems in borderland regions where traditional lines of authority operate alongside formal institutions, and how these can navigate the encroachment of non-state actors operating across borders. / Next phase: this will build evidence for more effective and better integrated security, development, and peacebuilding interventions in borderlands to reduce conflict. / Cross-Border conflict enablers / XCEPT research to looked to understand the complex conflict systems and war economies that drive transnational instability and link structural and direct violence. Research identified nodes of power and influence across borders, and how conflict actors exploit resources, trade, transit hubs, border crossings, and checkpoints. / Next phase: research will build understanding of how licit and illicit activities intersect in conflict-affected areas and how responses can limit the exploitation of these sources of revenue and power. Research will support decision makers to better anticipate the ways protracted conflict and instability (and donor and state interventions) can precipitate shifts in war economies and exacerbate negative trends. Research will also explore how transnational conflict actors mobilise support by manipulating grievances among marginalised communities, including online. / Cross-border conflict and climate / Research on the link between climate change, conflict, and peacebuilding has not been central to XCEPT research to date. Yet, these inherently cross-border challenges have appeared time and again as a salient factor in driving conflict. / XCEPT research reinforces a gap in this field: interventions to address conflict rarely include climate objectives or consider environmental issues– and vice versa. / Next phase: recognising the links between conflict and climate as an established area, XCEPT research will seek to address the evidence gap in the types of interventions that will break circles of mutually aggravating climate and conflict threats and vulnerabilities. XCEPT’s new research will address the cross-border, transnational nature of the problem, building on XCEPT’s core mandate and strengths. This will build on a conflict-climate commission launched this financial year. / 2. Drivers of violent and peaceful behaviour / King’s College London (KCL) leads XCEPT research on the implications of conflict-related trauma and mental health, memory, narratives, and perceptions for propensities and attitudes to violence and reconciliation and prospects for preventing resurgent conflict. In the first phase of research XCEPT addressed the question “what are the pathways to violent and peaceful behaviour?”. This included in-depth interviews and survey responses from Iraq, Lebanon, Turkey, and South Sudan. / Early findings supported the idea of ‘cycles of violence’ with a range of factors that predict violent extremist attitudes or feelings of vengeance, alongside potential ‘protective factors’, such as trust in institutions and other groups in society. / Research generated important lessons for engaging with trauma, memories, and cultural heritage in peacebuilding and conflict recovery, including findings that traumatic experiences can be linked to extremism and violence at household, community, and societal levels; and scalable mental health interventions have the potential to address conflict trauma and help break cycles of violence. / In the next phase: KCL will deepen analysis with questions about resilience and protective factors that buffer some individuals and communities from resurgent violence and cycles of conflict. Extension research will explore the role of trust between individuals, groups, elites, and institutions: how trust manifests in various contexts, under what conditions trust impacts behavioural outcomes related to conflict, and how (lack of) trust in institutions affects and is affected by trauma, mental health, social dynamics, and cognitive dispositions. Experimental study designs will push analyses beyond complex correlations to determining the causal role of key factors in the development of attitudes to violent and peaceful behaviour. / 3. New frontiers of conflict research: / The next phase of XCEPT will include an allocation of up to £1.5m to fund new academic research which responds to HMG priorities and emerging issues related to cross-border and transnational conflict. This will enable exploratory work to do one or more of the following: respond to new and emerging issues not currently part of XCEPT’s research portfolio but of interest to HMG; support new government priorities not originally part of XCEPT; and help to identify emerging themes for the future phase of RED’s conflict research. / Research could include questions such as: / How can we better predict and mitigate potential cross-border effects of conflicts and factors contributing to conflict, such as climate change, political instability, foreign information manipulation and interference? / How are malign state and non-state actors using new technologies and more traditional capabilities in their efforts to destabilise countries and regions? How can technology be deployed to more effectively counter these effects? / Delivery choices will be decided by RED’s Deputy Director, Research and Technology Department and the programme SRO, but could include an accountable grant with an academic institution/s or research partner/programme to explore a specific theme or question; extension of an existing partnership or commissioning a new partnership through the XCEPT XRF; or partnering with another programme within RED or FCDO to develop and commission new work as part of the existing XCEPT contract.
What is the additional and total support the UK will provide?
The UK will provide an additional £9,341,226, bringing the programme total to £38,341,226. The XCEPT programme budget is currently comprised of three components, plus a programme-funded post. In the extension, two components’ budgets will increase to continue research for two years; the programme-funded post will also be extended for two years. An additional component will be added on new frontiers of conflict research. / Original Grant/Contract Values FY20-25 (£) Value of extension FY25-27 (£) / Component 1 - Accountable Grant. Transnational Conflict 10,000,000 0 / Component 2 – Research Programme Consortium (RPC). Transnational Conflict (Chemonics) 12,772,499 4,930,000 / Component 3 - RPC. Violent and Peaceful Behaviour (Kings) 5,772,499 2,842,000 / Component 4 – New Frontiers of Conflict Research (Delivery model to be confirmed) 0 1,500,000 / Programme Funded Post 455,002 68,728 / Total 29,000,000 9,341,226 / The tables below show programme spend rate since FY 20/21, spend rates of Components 2 and 3, and the proposed spend rate of all extended components. To note: between March 2020 and March 2024, planned programme spend was deferred due to FCDO’s budget prioritisation exercise, so programme spend was lower than planned. Totals do not include spend between 2018-2020 nor £10m from Component 1, which is not being extended / Table: Spend per component per year for total project value of programme / XCEPT spend and forecast profile (since FY2020/21) / FY 2020/21 2021/22 2022/23 2023/24 2024/25 2025/26 2026/27 TOTAL / Budget (£m) 1.81 2.80 4.63 4.14 4.82 5.47*^ 3.86 27.53 / Component 2 – transnational conflict / FY 2020/21 2021/22 2022/23 2023/24 2024/25 2025/26 2026/27 TOTAL / Budget (£m) 1.1 1.9 2.74 2.82 3.4 3.3* 1.63 16.89 / Component 3 – violent and peaceful behaviour / FY 2020/21 2021/22 2022/23 2023/24 2024/25 2025/26 2026/27 TOTAL / Budget (£m) 0.65 0.84 1.81 1.28 1.34 1.34* 1.4 8.66 / Component 4 – new frontiers in conflict research / FY 2020/21 2021/22 2022/23 2023/24 2024/25 2025/26 2026/27 TOTAL / Budget (£m) 0.75* 0.75 1.50 / Programme Funded Post / FY 2020/21 2021/22 2022/23 2023/24 2024/25 2025/26 2026/27 TOTAL / Budget (£k) 58.4 64.1 75.8 35.1 83.4 83.4 83.4* 483.6 / * year in which the next phase of funding would begin. / ^ dependent on forecasting, contract negotiations, and emerging issues in C4. / Table: Overview of programme activity completion, by component and delivery partner: / FY 23-24 FY 24/25 FY 25-26 FY 26-27 / Q1Q2Q3Q4 Q1Q2Q3Q4 Q1Q2Q3Q4 Q1Q2Q3Q4 / Local Research Network (C1) / Conciliation Resources (C2) / Chatham House (C2) / XCEPT Research Fund (C2) / King's College London (C3) / New Frontiers Research (C4) / Programme Funded Role / XCEPT has had a programme-funded Conflict Adviser since its inception, in recognition of its complexity and sensitivity. The extension will continue to fund a Grade 7 Conflict Adviser who will be the programme’s Lead Adviser, and serve as the PRO. The Adviser will be overseen by a Grade 6 SRO (Conflict Research Lead in RED). The position ensures the programme can respond rapidly to emerging conflict issues and support high-impact uptake. / The cost of extending this role for two years is £166k, however there are remaining funds in this budget line, so only £68k is required for this extension. We continue to judge that a programme-funded post offers better VfM than an outsourced alternative. The sensitivity of XCEPT’s subject matter and high-risk locations where research is being carried out require FCDO leadership to manage and mitigate risks. While delivery partners can effectively manage elements of this, they are not always best placed to judge what may represent a reputational, political, or other risk to HMG. Strong risk management continues to be a programme priority.
What are the expected results?
While the approach to delivering the programme’s intended outputs will remain largely constant, developing rigorous and independent public good research on its core themes, the next phase will focus on driving results at the outcome and impact level. XCEPT will do this by deepening its focus on research synthesis and drawing out comparative and cross-programme findings to deliver a lasting intellectual legacy; and through well-communicated policy-relevant research that explicitly addresses questions on more effective responses to cross-border and transnational conflict. XCEPT will also produce evidence on new and emerging frontiers within its overall scope as a programme. / Research findings will be shared through a range of products: / Monographs (at least one) and special issues for each research theme. / Research Reports: Journal articles or peer reviewed research reports. / Policy briefs: Tailored policy recommendations for HMG based on research; and short papers on exploratory or preparatory research (scoping, background papers). / Blogs/articles/multimedia: Dissemination of research to reach new audiences within and outside of HMG and promote uptake. Channels include: XCEPT and partner websites; XCEPT newsletter; targeted emails; traditional and social media; podcasts and videos; and meetings, briefings and events. / Events for experts and practitioners: Partner-run regular events to disseminate research, generate policy discussion, and promote research uptake. Varied format including small roundtables (15-30 participants, under the Chatham House rule) and HMG-only sessions to large regional conferences and livestreamed events. / International fora: Researchers presenting at international meetings focused on peace and stability, e.g., World Bank Fragility Forum, SIPRI Security Forum, COP. / Through these outputs, the extension will focus on delivering policy impact and uptake, and a strong intellectual legacy. We will define and agree the precise number and balance of outputs between the SRO and delivery partners and will track this rigorously throughout the life of the programme, building on lessons from the first phase on the types of outputs that most effectively lead to outcome change. / Conflict patterns and trends shift: the XCEPT research fund (XRF) and New Frontiers component (C4) will give the programme agility and flexibility to adapt its research direction, including delivering research and evidence that serves policy needs. The research questions in this addendum are indicative and will be subject to further development in consultation with RED and X-HMG. They may also be adjusted according to changing conflict contexts.
What is the approach to implementation?
Components / XCEPT’s first phase was delivered through one Accountable Grant (AG) and two Research Programme Consortiums (RPC). In the extension the implementation model will be simplified to provide more efficient delivery and better VfM. / First Phase Extension / Component 1 / Transnational Conflict Lead: The Asia Foundation (AG) / Delivery model: Partnership with Rift Valley Institute, Carnegie Middle East Center Not being extended / Component 2 / Transnational Conflict Lead: Chemonics UK (RPC) / Delivery model: Partnership with Chatham House and Conciliation Resources, and Chemonics UK-led XCEPT Research Fund (XRF) Lead: Chemonics UK (RPC) / Delivery model: Chemonics UK-led XCEPT Research Fund (XRF) / Component 3 / Drivers of violent and peaceful behaviour Lead: Chemonics UK (RPC) / Delivery model: Partnership with King’s College London Lead: Chemonics UK (RPC) / Delivery model: Partnership with King’s College London / Component 4 / New Frontiers in Conflict Research Lead and delivery model to be determined in consultation with Deputy Director, Team Lead and Programme SRO / Contracting arrangements / Component 2 (C2) Transnational Conflict, and Component 3 (C3) Drivers of violent and peaceful behaviour will be continued in the extension. C2 and C3 will continue to be contracted separately as they address distinct research subjects (transnational conflict / violent and peaceful behaviour). The programme will be delivered by the same two implementing partners (Chemonics UK [C2], and KCL [C3]). Chemonics UK will continue to provide programme management, quality assurance and research uptake support across components. Contracting will include a break clause linked to completion of programme milestones by March 2025, including consolidation and synthesis of research findings, refining XRF theme research questions to respond to gaps in the conflict research field, and recruiting the XRF Fellows to lead the three priority themes. / Component 1 will not be continued. Component 4 (C4) will be developed to address new frontiers in conflict research. C4 contracting arrangements will be determined in consultation with RED leadership teams and the Programme SRO. / XCEPT Research Fund (XRF) / XCEPT Annual Reviews showed the XRF to be the highest-performing aspect of C2, delivered by Chemonics UK. It has demonstrated agility and VfM, undertaking research on emerging issues and responding to the highly dynamic nature of conflict. In the extension new research will be commissioned through the XRF, the primary means of C2 delivery. / The XRF funds organisations and individual researchers to conduct research on the key themes outlined above, including cross-cutting themes of gender equality and social inclusion (GESI). The XRF will build a balanced portfolio of smaller awards for short evidence reviews or work on a specific theme, and larger awards to develop a body of work under a single theme or on complementary issue sets. / The XRF will continue to prioritise awards to organisations and researchers based in the Global South or with demonstrated commitment to featuring Global South researchers, supporting research capacity, and system strengthening. XCEPT will support awardees to use newer technologies such as remote sensing, signal tracking, and open-source intelligence. Solicitation will take place through a combination of open competition, limited competition and direct awards. Details of the XRF management can be shared on request. / XRF Research Fellows / XRF Fellows will be recruited for the three thematic areas of focus for XRF research. They will be experts in their fields and will be offered one-year awards to undertake independent research, support research development and commissioning, and lead on XCEPT research uptake in their areas of expertise. As appropriate, XCEPT will “buy out” the time of Fellows to enable them to focus on authoring research and supporting XRF research commissioning and uptake. Successful Fellows may be eligible for a fellowship extension. / Timing / During 2020-2023 the XRF budget allocation was 50% less than planned due to ODA cuts. From March 2024 onwards the XRF will operate at a level closer to that of the original implementation plan and budget. Research delivery from the first phase will be completed during FY 2025/26; new research from the proposed uplift of £9.34m will begin during FY 2025/26 and continue to March 2027. / Early confirmation of the costed extension will ensure sufficient time for XCEPT programme leads to develop impactful and VfM commissions for FY 2025/26, when the programme is expected to deliver a significant body of research. A costed extension for C3 would overlap with the current programme and budget, enabling new pieces of research to start as current research is still on-going. C4 will begin April 2025. / Coordination and Advisory / During its first phase, an XCEPT HMG Advisory Group (XHAG) was established to adviser on research direction, relevance, and uptake. The XHAG comprised members from across FCDO and departments including the Cabinet Office, Home Office and MoD. Learning from the first phase has shown that both the programme and XHAG stakeholders would be better served by a more targeted advisory model, enabling focussed attention on bounded thematic areas within XCEPT’s broad research mandate. / In the next phase, small HMG advisory groups will be established for the three pillars of C2 research and a separate advisory group for C3 and C4. This will ensure that the advisory groups are more expert and targeted. Key HMG stakeholders will be represented in these groups (e.g., OCSM, RAs, ISF, climate specialists, Open-Source Unit, MOD, Cabinet Office and behavioural science specialists). / Value for Money / XCEPT Annual Reviews find that the programme represents good value for money. In the extension VfM would be increased by reducing the number of partners and the amount of staff time spent on cross-programme coordination. The table below presents a summary: / Economy / Chemonics XCEPT is supported by its Programme Management Centre of Excellence, for finance and administrative support. This pooled resource allows XCEPT to draw on these skills as needed, saving project time, reducing staff costs and resource overheads. In the first phase, this saved £325,113 across several roles which were not charged to the programme. / XCEPT uses benchmarking to secure sustained VfM. When negotiating XRF award agreements, an applicant’s best and final offer is compared against the relevant commissioning market for research. The budget is negotiated to ensure costs are reasonable, flexible, allowable, comply with FCDO policies, and properly enable the proposed technical activities. / XCEPT adapted XRF commissioning processes to enable awards to individual researchers as well as organisations. Awards to individual researchers eliminate organisational overhead costs. Individual researcher fee rates are benchmarked against market rates. / Efficiency / The Chemonics XCEPT team oversees all XRF awards, with core team members managing multiple awards simultaneously. This optimises the use of resources, enables lessons learning across awards, and allows the team to flex as award requirements demand. / The London-based Chemonics XCEPT team collaborates with other Chemonics programmes managing funds, enabling continual learning and adaptation. XRF ability to capitalise on Chemonics programme management resources allows the XCEPT team to spend more time designing and managing research. / The XRF often invests in smaller initial awards, scaling up or extending if the first project proves successful. This minimises risk, builds strong research partnerships, and reduces transaction costs. / Effectiveness / XCEPT is on track to deliver its outcome effectively: XCEPT generates academic, policy relevant research outputs to inform HMG and partners on cross-border conflict dynamics, and influence changes to policies and programmes to address conflict and instability more effectively (see pg. 2-3). / Research on medicine as a conflict commodity in Iraq was instrumental to HMG agenda-setting on policy engagements with the Iraqi government; and findings on the trade-offs of stabilisation, security, and migration responses from research on the sesame trade, gold mining, and people smuggling in the Horn of Africa were incorporated into policy and programme planning by HMG. / Ongoing consultation and engagement with FCDO and other key stakeholders across the network ensure XCEPT research remains policy relevant and attuned to stakeholder needs. Policy meetings and public events targets were exceeded in FY23/24, with dissemination and events tailored to promote policy uptake in line with the theory of change. / Equity / XRF research commissioning targets Global South applicants and includes capacity building, as needed. This ensures that a significant proportion of XCEPT research is led by Global South researchers. XCEPT achieved a high proportion of Global South representation (84%) in the open competition for women and girls’ research. Global South research targets are included in the logframe. / XRF awards are designed to promote equity and inclusivity. XCEPT assesses all applications and research plans with a GESI lens and works with winning applicants to ensure GESI sensitivity. / Through the XRF, 18 of the 38 awards in FY 23/24 were led or co-led by women researchers. / Research findings are made available in a variety of open-access formats to ensure accessibility to different groups, including through translation, image-rich reports, and podcasts. / Cost effectiveness / XCEPT works across multiple UK foreign policy priorities and insights are regularly used to inform policy in priority countries, including promoting stability in the Middle East; addressing the conflict in Ukraine; tackling transnational threats (SOC, CVE) which affect the UK’s interests; addressing drivers of migration; and increasing effectiveness of development efforts by preventing and responding to conflict. / Effective VfM considerations have kept costs low, while delivering high quality outputs. Evidence that XCEPT research outputs have effectively influenced policy debates and stakeholders in and outside of HMG mean programme cost effectiveness us high. / Consultation / The Lead Adviser regularly consults with HMG stakeholders to ensure that the programme is producing original research that is filling evidence gaps. This addendum is the result of iterative consultation with key stakeholders in HMG, including: colleagues from OCSM, Open-Source Unit, Behavioural Scientists, RED climate advisers, Research Analysts, Illicit Finance and Anti-Corruption teams, RED economics advisers, and advisers at posts in which XCEPT has undertaken research in MENA, East Africa, West Africa, Ukraine, Afghanistan, Pakistan and Myanmar. The Lead Adviser also consulted colleagues in MoD, particularly country-specific Defence Attaches and Defence Intelligence. / Chemonics and partner researchers consult across HMG to gain insight into UK research needs and priorities and to shape research design and commissioning. Relevant analysts, conflict advisors and country teams are engaged at design and implementation based on the geographic and thematic focus of the research, and their advice and participation are solicited in support of policy-focussed research uptake. XCEPT programme and research leads also engage with leads from ISF, Transnational Threats and State Threats units. / Risks / A full examination of risks and mitigations can be shared on request. The most significant risks in the extension are consistent with the original Business Case. They include: / Changing conflict dynamics in fragile and conflict-affected situations could impact programme delivery. / Shifts in HMG priorities due to emerging conflicts and crises alter policy stakeholder priorities and impact capacity to engage with research. / Research activities or findings generate media attention critical of HMG and XCEPT or raise barriers to ongoing or future data collection. / Insufficiently context-sensitive approach to conducting, disseminating research could exacerbate existing tensions and unnecessarily raise the programme’s local profile. / Gender Equality / XCEPT complies with the Gender Equality Act and supports commitments in the UK’s Women, Peace and Security National Action Plan (NAP) 2023-2027. FCDO’s Procurement and Commercial Department confirmed that Chemonics complied with 100% of FCDO’s Code of Conduct. XCEPT’s GESI approach is guided by a rubric developed by the Gender Working Group of the Oxfam Research Network[3], which considers how research can challenge structural and systemic power imbalances that reinforce social and gender inequities. The aim is to support GESI-transformative research and build an evidence base to inform long-term changes in gender relations and norms, roles, and inequalities. XCEPT research to date incorporates gender-sensitivity considerations into design and planning and a GESI lens is applied across all research proposals, including through targeted studies.[4] / Building on the success of XCEPT’s community-led research, in which marginalised communities and voices lead the research process, additional funds will be earmarked for local research led by diverse researchers and social groups. / Counter Terrorism and Security Act / Chemonics, and their partners comply with FCDO mandatory standards on counterterrorism. The partners follow UK guidelines on the Counter Terrorism and Security Act 2015 and FCDO checks at annual meetings that the programme’s research complies with the UK’s policy and funding rules regarding counter terrorist financing.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The proposed extension remains close in design to the original business case, however, it uses recommendations from annual reviews and lessons learned to deliver a more efficient, effective and nuanced programme design. It also acknowledges the merger of FCO and DFID, changes in geopolitics, and advances in conflict research methods. / Theory of Change / Over the course of the programme, XCEPT has revised its ToC to provide more detail and enable impact to be measured through capacity and behaviour change of research stakeholders. The ToC has been designed alongside a revised Monitoring and Evaluation Framework centred around how change occurs in knowledge generation, uptake, and policy. The revised ToC will be carried into the extension and can be shared on request. / Removal of one component / The original business case included three components: one accountable grant and two RPCs. This dispersed approach was deemed be inefficient, requiring significant management oversight from FCDO and time-consuming coordination processes. In the extension it is proposed that only the two RPC components will continue, and the accountable grant work will not be extended. Partners from the accountable grant will be eligible for funding through the XRF should they choose to apply. Both RPCs are led by the same partner (Chemonics UK), which facilitates coordination and streamlines management. / Expanded grants facility (XRF) / In the extension, C2 of the programme will discontinue fixed partnerships and will deliver research solely through XRF commissioning, supported by XCEPT Research Fellows. / Geographies / The 2018 business case cites Middle East, Asia, and the Horn of Africa as XCEPT’s geographic focus, based on protracted instability at that time. The past five years have seen geopolitical shifts and the emergence of two conflicts with wide ranging affects: Ukraine and Israel/Gaza. Increased violence in West and Central Africa, including recent military coups, raises the risk of broader instability and conflict overspill. The extension will continue to focus on the original geographies, adding West and Central Africa and the Middle East to the regions under study. Exact countries of research will be determined by emerging conflict dynamics at the time of implementation and grant proposals. Heads of Missions will be consulted and buy-in from post will be a prerequisite prior to initiating research.
[1] UCDP - Uppsala Conflict Data Program (uu.se)
[2] Illicit Flows Fuelling Conflict in the Tri-Border - XCEPT (xcept-research.org); The ‘conflict economy’ of sesame in Ethiopia and Sudan - XCEPT (xcept-research.org); War and the borderland: Northern Bahr el Ghazal during the Sudan conflict - XCEPT (xcept-research.org).https://www.xcept-research.org/publication/war-and-the-borderland-northern-bahr-el-ghazal-during-the-sudan-conflict/
[3] Integrating Gender in Research Planning, Oxfam
[4] Varied examples can be found here: https://www.xcept-research.org/publications/