## Core indicators
XCEPT LOGICAL FRAMEWORK
Accurate per figures in final version of AR 24/25
COSTED EXTENSION - FY 25/26 onwards
IMPACT | Impact Indicator 1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) | Assumptions | Impact Indicator 1 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL) | Assumptions
Policies and programmes have a more effective influence/impact on fostering peaceful behaviour and addressing violence and conflict | Frequency and intensity of violence in research countries / research areas | Planned | No milestones/targets. The project will monitor evolution over time based on sources indicated below, with the understanding that the project's ultimate impacts on actual violence levels are dependent on external factors that are outside of the project's control | [7 empty] | Progress against Impact-level indicators will be monitored with the understanding that the project's ultimate impacts on actual violence levels and GPI ranking are dependent on external factors that are outside of the project's control | Number of cases of significant instrumental impact (where XCEPT has influenced an actor in a conflict response setting as a result of which there was a positive change in the context); OR conceptual impact (changing ways of thinking at scale or at a significant level, leading to wider scholarship, public debate, or significant peace actors adopting XCEPT thinking in approaches or strategies); OR networks and connectivity impact (e.g., evidence of significant, wide-ranging and durable impact from building and strengthening connections and networks); OR capacity building impact (evidence of significant, wide-ranging and durable impact from building researchers' capacity to conduct or socialise their research, etc.) Note: To meet the bar for significance, scale, and durability at the impact level, the change would be expected to reflect the approach or thinking of an organisation vs that of a department or team, for example. | Planned | No pre-defined target; to be assessed annually against narrative impact stories. | No pre-defined target; to be assessed annually against narrative impact stories. |  | Progress against Impact-level indicators will be monitored with the understanding that the project's ultimate impacts are dependent on external factors that are outside of the project's control
Achieved
Source
Various, including both quantitative (e.g UCDP, ACLED, Global Burden of Armed Violence, National VIMS datasets when available) and qualitative (e.g. ICG CrisisWatch, programme Risk Matrix, local security reports)
| Impact Indicator 2 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL)
| Ranking of research countries on the Global Peace Index | Planned | No milestones/targets. The project will monitor evolution over time based on sources indicated below, with the understanding that the project's ultimate impacts on GPI rankings are dependent on external factors that are outside of the project's control
Achieved
Source
|  |  | Global Peace Index (Institute for Economics and Peace) | [9 empty] | Achieved | Total: 1 C1: 0 C2: 1 C3: 0
OUTCOME | Outcome Indicator 1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) | Assumptions | Outcome Indicator 1 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL) | Assumptions
FCDO, HMG and partners are better informed and better able to use project-generated evidence to adjust intervention strategies and policies to address conflict and instability more effectively. | Policy uptake. # of cases where XCEPT research influences policy, programme design or implementation (assessed through tangible examples). | Planned (cumulative) | Too early for milestone | Too early for milestone | C1: 3 C2/C3: Too early for milestone | C1: 5 C2/C3: Too early for milestone | C1: 7 C2: 1 C3: 1 | Total: 28 C1: 12 (3 this FY) C2: 12 (4 this FY) C3: 4 (2 this FY) | Total: 40 (11 this FY) C1: 16 (3 this FY) C2: 18 (6 this FY) C3: 6 (2 this FY) | TBD | Researched topics and areas remain priorities for HMG, international donors and other stakeholders. There is sufficient consistency in research and policy priorities to allow for adequate planning and implementation. | Research uptake: Number of cases of instrumental change (where XCEPT research influences policy, deliberations, programme design or implementation); OR conceptual change (changing ways of thinking in scholarship or public debate, or informing peace actor analysis or strategies); Assessed through tangible examples. Disaggregated by HMG vs other significant stakeholders (e.g., multilateral actors, regional bodies, NGOs, etc.) | Planned (cumulative) | Total: 52 (8 this FY) C1: 17 (0 this FY) C2: 27 (6 this FY) C3: 8 (2 this FY) | Total: 64 (8 this FY) C1: 18 (0 this FY) C2: 35 (6 this FY) C3: 11 (2 this FY) | TBD | Researched topics and areas remain priorities for HMG, international donors and other stakeholders. There is sufficient consistency in research and policy priorities to allow for adequate planning and implementation.
|  | Achieved (cumulative) |  |  | C1: 3 | C1: 5 C2: 5 | C1: 9 C2: 8 C3: 2 | Total: 29 C1: 13 (4) C2: 12 (4) C3: 4 (2) | Total: 44 (15 this FY) C1: 17 (4 this FY) C2: 21 (9 this FY) C3: 6 (2 this FY) | TBD |  |  | Achieved (cumulative) | Total: 56 (12 this year) C1: 18 (1) C2: 29 (8) C3: 9 (3) | Total: C1: C2: C3: | TBD
|  |  | Source | [9 empty] | Source
|  |  | XCEPT Policy Uptake Case Studies / Review of publicly available policy documents from HMG and development partners / Feedback from HMG and development partners / | [9 empty] | XCEPT Research Uptake Case Studies / Review of publicly available policy documents from HMG and development partners, media, scholarship / Feedback from HMG, development partners, scholars
| Outcome Indicator 2 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Outcome Indicator 2 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Influencing the policy debate. # of citations of XCEPT research and research outputs in the academic literature, grey literature, and the media | Planned (cumulative) | The project will report yearly figures but no milestones targets are set (no solid reference for setting targets) |  |  |  |  | Total: 40 C1: 25 C2/C3: 15 | Total: 214 (45 this FY) C1:140 (25 this FY) C2/C3: 74 (20 this FY) | TBD |  | Research uptake. # of citations of XCEPT research and research outputs in the academic literature, grey literature, and Southern and Northern media Disaggregated by academic vs grey lit and media citations. | Planned (cumulative) | Total: 529 (90 this FY) C1: Tracked, but no target. C2/C3: 210 (90 this FY) | Total: 691 (130 this FY) C1: Tracked, but no target. C2/C3: 372 (130 this FY) | TBD
|  | Achieved (cumulative) | [5 empty] | Total: 169 C1: 115 C2/C3: 54 | Total: 439 (270 this FY) C1: 319 (204 this FY) C2/C3: 120 (66 this FY) | TBD |  |  | Achieved (cumulative) | Total: 561 (122 this FY) C1: 546 (227 this FY) C2/C3: 242 (122 this FY) | Total: C1: C2/C3: | TBD
|  |  | Source | [9 empty] | Source
|  |  | Data collated annually from citation search software such as Publish or Perish, and consortium members' own research will be used to track this indicator | [9 empty] | Data collated annually from citation search software such as Google Scholar, Publish or Perish, and consortium members' own research will be used to track this indicator
[12 empty] | Outcome Indicator 3 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
[12 empty] | Influencing public debate. # of features in major events, media and periodicals centring on or delivered by XCEPT research(ers), including invited interventions at significant events, commentaries and interviews in major web, print and broadcast outlets, features in print, web, and broadcast media based on significant engagement with researchers, etc. Note: To qualify, podcasts, web and print outlets should have reach at least in the hundreds of thousands, e.g., major newspapers (FT, WSJ, Times, Guardian, etc.), periodicals and magazines (Economist, Foreign Affairs, The Conversation, New Lines Magazine, etc.). | Planned (cumulative) | Total: 4 (4 this FY) C1: NA C2/C3: 4 | Total: 20 (6 this FY) C1: NA C2/C3: 20 (6 this FY) | TBD
[13 empty] | Achieved (cumulative) | Total: 14 (14 this FY) C1: 0 (0) C2: 10 (10) C3: 4 (4) | Total: C1: C2/C3: | TBD
Data collated annually from consortium members' and awardees' reporting, verified against media references, invitations, etc.
INPUTS (£) | FCDO (£) |  |  |  | Govt (£) | Other (£) | Total (£) | Total (£) | FCDO SHARE (%) |  |  | FCDO (£)
INPUTS (HR) | FCDO (FTEs) | [10 empty] | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) | Assumptions | [5 empty] | Assumptions
Research: Policy-relevant research, evidence and recommendations are generated and documented about conflict-affected borderlands, cross-border and regional conflict dynamics, drivers of violent and peaceful behaviour, and associated policy responses. | Research Reports (> 5,000 words). # journal articles or peer reviewed research reports | Planned (cumulative) |  | C1: 6 | C1: 19 Total (6 per partner + 1 joint) C2/C3: Too early for milestone | Total: 28 C1: 27 C2: 1 C3: Too early for milestone | Total: 62 C1: 34 C2: 12 C3: 2 | Total: 101 C1: 51 (6 this FY) C2: 34 (20 this FY) C3: 16 (9 this FY) | Target: 141 C1: 61 (9 this FY) C2: 59 (28 this FY) C3: 21 (7 this FY) | Target: 141 C1: 61 C2: 59 C3: 21 | All consortium members are able to conduct research across planned research sites. They are able to adapt plans to respond to unforeseen political developments or other complications resulting in a high level of risk to consortium members, their local partners or individual researchers. Research reports include long-form research reports, journal articles and edited books. Policy briefs are typically up to 2,500 words. Working papers/research papers are typically between 3,000 and 20,000 words, prepared as drafts and reflecting analysis or elements of XCEPT research findings (interim or final) in pre-publication form. We assume the 'blog pieces/articles' category will be flexibly interpreted to include novel and alternative presentation and research communication formats and activities. | NO LONGER USED |  |  |  |  | All consortium members are able to conduct research across planned research sites. They are able to adapt plans to respond to unforeseen political developments or other complications resulting in a high level of risk to consortium members, their local partners or individual researchers. Research reports include long-form research reports, journal articles and edited books. Policy briefs are typically up to 2,500 words. Working papers/research papers are typically between 3,000 and 20,000 words, prepared as drafts and reflecting analysis or elements of XCEPT research findings (interim or final) in pre-publication form. We assume the 'blog pieces/articles' category will be flexibly interpreted to include novel and alternative presentation and research communication formats and activities.
|  | Achieved (cumulative) |  | C1: 7 Total = AFRICA - 3 / ASIA - 2 / MENA - 2 | C1: 20 Total = AFRICA - 7 / ASIA - 5 / MENA - 8 C2: 2 [LSE] | Total: 42 (21 this year) C1: 32 TOTAL (12 this year) = AFRICA - 13 / ASIA - 7 / MENA - 12 C2: 10 TOTAL (8 this year) = AFRICA - 1 / MENA - 8 | Total: 64 (22 this year) C1: 45 TOTAL (13 this year) C2: 14 TOTAL (4 this year) C3: 7 (7 this year) | Total: 97 (31) C1: 52 (7) C2: 31 (17) C3: 14 (7)
Source
Quarterly progress reports / Project website(s)
| Output Indicator 1.1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 1.1 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Academic outputs. # high-quality academic, externally published journal articles, books, chapters, special volume contributions, and equivalents. | Planned (cumulative) | [6 empty] | Total: 18 (14 this FY) C1: 1 (0 this FY) C2: 10 (10 this FY) C3: 7 (4 this FY) | TBD |  | Academic outputs. # high-quality academic, externally published journal articles, books, chapters, special volume contributions, and equivalents. Disaggregated by Global South (co-)authorship. | Planned (cumulative) | Total: 30 (12 this FY) C1: 1 (0 this FY) C2: 20 (10 this FY) C3: 9 (2 this FY) | Total: 43 (14 this FY) C1: 1 (0 this FY) C2: 32 (12 this FY) C3: 10 (2 this FY) | TBD
|  | Achieved (cumulative) | [5 empty] | Total: 5 C1: 1 C2: 0 C3: 4 | Total: 18 (14 this FY) C1: 1(0 this FY) C2: 10(10 this FY) C3: 7(4 this FY) | TBD |  |  | Achieved (cumulative) | Total: 29 (11 this FY) C1: 1 (0 this FY) C2: 20 (10 this FY / 6 GS) C3: 8 (1 this FY / 0 GS) | Total: C1: C2: C3: | TBD
|  | Source | [10 empty] | Source
|  | Quarterly progress reports / Project website(s) | [10 empty] | Quarterly progress reports / Project website(s)
| Output Indicator 1.2.1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 1.2.1 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Research Reports (>5000 words). # high-quality, externally peer reviewed research reports published in non-academic fora. | Planned (cumulative) | [6 empty] | Total: 93 (14 this FY) C1: 58 (9 this FY) C2: 33 (5 this FY) C3: 2 (0this FY) | TBD |  | Research Reports (>5000 words). # high-quality, externally peer reviewed research reports published in non-academic fora. Disaggregated by Global South (co-)authorship. | Planned (cumulative) | Total: 116 (11 this FY) C1: 66 (0 this FY) C2: 47 (10 this FY) C3: 3 (1 this FY) | Total: 130 (13 this FY) C1: 69 (0 this FY) C2: 57 (12 this FY) C3: 4 (1 this FY) | TBD
|  | Achieved (cumulative) | [5 empty] | Total: 80 C1: 49 C2: 28 C3: 2 | Total: 105 (26 this FY) C1: 66 (17 this FY) C2: 37 (9 this FY) C3: 2 (0 this FY) | TBD |  |  | Achieved (cumulative) | Total: 117 (12 this FY) C1: 69 (3 this FY / 2 GS) C2: 45 (8 this FY / 0 GS) C3: 3 (1 this FY / 0 GS) | Total: C1: C2: C3: | TBD
|  | Source | [10 empty] | Source
|  | Quarterly progress reports / Project website(s) | [10 empty] | Quarterly progress reports / Project website(s)
| Output Indicator 1.2.2 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 1.2.2 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Briefing notes / Working papers / Datasets: # short policy-focused papers based on XCEPT research; papers documenting exploratory and/or preparatory research (working papers, scoping papers, background papers); and data sets: new data made available to different audiences. Broken down by type. | Planned (cumulative) |  | C1: 9 (3 per partner) | C1: 33 Total (11 per partner) C2/C3: Too early for milestone | Total: 77 C1: 51 C2: 18 C3: 8 | C1: 60 C2: 35 C3: 10 | Total: 152 C1: 79 (9 this FY) C2: 55 (15 this FY) C3: 18 (8 this FY) | Total: 190 (36 this FY) C1: 89 (12 this FY) C2: 78 (20 this FY) C3: 23 (4 this FY) | TBD |  | Briefing notes / Working papers / Datasets: # short policy-focused papers based on XCEPT research; papers documenting exploratory and/or preparatory research (working papers, scoping papers, background papers); and data sets: new data made available to different audiences. Disaggregated by Global South (co-)authorship. | Planned (cumulative) | Total: 229 (28 this FY) C1: 99 (0 this FY) C2: 96 (18 this FY) C3: 34 (10 this FY) | Total: 269 (33 this FY) C1: 101 (0 this FY) C2: 126 (25 this FY) C3: 42 (8 this FY) | TBD
|  | Achieved (cumulative) | C1: AFRICA - 0 ASIA - 2 background papers; MENA - 3 scoping papers | C1: 22 TOTAL = AFRICA - 5 policy briefs / 5 thematic papers / 1 technical report; ASIA - 4 papers/ 2 background papers; MENA - 5 scoping papers | C1: 42 TOTAL = AFRICA - 8 research papers/ 6 policy briefs / 3 thematic papers / 1 technical report; ASIA - 4 policy briefs/ 6 papers/ 2 background papers; MENA - 12 articles, 2 scoping papers C2: 6 (Tigray) [+ 2 RAPID] | Total: 91 (41 this year) C1: 59 TOTAL (15 this year) = AFRICA - 10 research papers/ 10 policy briefs / 3 thematic papers / 1 technical report; ASIA - 11 policy briefs/ 8 papers/ 2 background papers; MENA - 12 articles, 2 scoping papers C2: 28 TOTAL (22 this year) = 24 policy briefs; 4 research papers C3: 4 TOTAL (4 this year) = 1 policy brief; 3 research papers | Total: 120 (29 this year) C1: 70 TOTAL (11 this year) C2: 40 TOTAL (12 this year) C3: 10 TOTAL (6 this year) | Total: 154 (34) C1: 77 (7) C2: 58 (18) C3: 19 (9) | Total: 201 (47 this FY) C1: 99 (22 this FY) C2: 78 (20 this FY) C3: 24 (5 this FY) | TBD |  |  | Achieved (cumulative) | Total: 236 (35 this FY) C1: 101 (2 this FY / 1 GS) C2: 101 (23 this FY / 13 GS) C3: 34 (10 this FY / 0 GS) | Total: C1: C2: C3: | TBD
|  | Source | [10 empty] | Source
|  | Quarterly progress reports / Project website(s) | [10 empty] | Quarterly progress reports / Project website(s)
| Output Indicator 1.3 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 1.3 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Blogs / articles / multimedia. # research outputs other than full-length research reports, policy briefs or research papers. Includes blog posts, news releases, podcasts, photo essays etc. Broken down by type. | Planned (cumulative) |  | C1: 11 (3 per partner plus 2 joint) | C1: 31 Total (9 per partner + 4 joint) C2/C3: Too early for milestone | Total: 98 C1: 79 C2: 14 C3: 5 | C1: 93 C2: 27 C3: 36 | Total: 241 C1: 116 (14 this FY) C2: 60 (31 this FY) C3: 65 (25 this FY) | Total: 311 (67 this FY) C1: 133 (17 this FY) C2: 100 (35 this FY) C3: 78 (15 this FY) | TBD |  | Blogs / articles / multimedia. # research outputs other than full-length research reports, policy briefs or research papers. Includes blog posts, news releases, podcasts, photo essays etc. Disaggregated by Global South (co-)authorship. | Planned (cumulative) | Total: 348 (35 this FY) C1: 134 (0 this FY) C2: 121 (22 this FY) C3: 93 (13 this FY) | Total: 387 (33 this FY) C1: 140 (0 this FY) C2: 142 (25 this FY) C3: 105 (8 this FY) | TBD
|  | Achieved (cumulative) | MENA - 7 blogs | C1: 28 Total = AFRICA - 4 blogs ; ASIA - 3 blogs ; MENA - 20 blogs and photo-essays; Joint – 1 | C1: 65 TOTAL = AFRICA 4 articles / 4 blogs / 4 podcasts ; ASIA - 11 articles, 7 blogs (incl. 1 podcast), 1 program snapshot/video; MENA - 30 blogs, photo-essays and interviews; 4 joint | Total: 103 (38 this year) C1: 80 TOTAL (15 this year) = AFRICA 4 articles / 7 blogs / 4 podcasts ; ASIA - 12 articles, 10 blogs (incl. 2 podcast, 1 microsite), 1 program snapshot/video; MENA - 36 blogs, photo-essays and interviews; 6 joint C2: 8 TOTAL (8 this year) = 3 blogs; 1 data viz.; 1 op-ed; 3 podcasts C3: 15 TOTAL (15 this year) = 10 blogs; 5 podcasts | Total: 170 (67 this year) C1: 101 TOTAL (22 this year) C2: 29 TOTAL (21 this year) C3: 40 TOTAL (25 this year) | Total: 244 (74) C1: 116 (15) C2: 65 (36) C3: 63 (23) | Total: 313 (69 this FY) C1: 134 (18 this FY) C2: 99 (34 this FY) C3: 80 (17 this FY) | TBD |  |  | Achieved (cumulative) | Total: 354 (41 this FY) C1: 140 (6 this FY / 5 GS) C2: 117 (18 this FY / 6 GS) C3: 97 (17 this FY / 3 GS) | Total: C1: C2: C3: | TBD
|  | Source | [10 empty] | Source
|  | Quarterly progress reports / Project website(s) | [10 empty] | Quarterly progress reports / Project website(s)
INPUTS (£) | FCDO (£) |  |  |  | Govt (£) | Other (£) | Total (£) | Total (£) | FCDO SHARE (%) |  |  | FCDO (£)
INPUTS (HR) | FCDO (FTEs) | [10 empty] | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) | Assumptions | Output Indicator 2.1 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL) | Assumptions
Policy engagement: Engagement with a policy audience at key stages from research design to dissemination, in order to build ownership and improve research uptake | Policy meetings. # meetings, briefing sessions and tailored presentations of research plans and/or research findings held with policy makers. | Planned (cumulative) |  | C1: 18 Total (6 per partner) | C1: 36 total (14 per partner) C2: 10 C3: 6 | Total: 109 C1: 68 Total C2: 25 C3: 16 | C1: 80 Total C2: 48 C3: 26 | Total: 324 C1: 143 (12 this FY) C2: 125 (47 this FY) C3: 56 (20 this FY) | Total: 429 (85 this FY) C1: 177 (15 this FY) C2: 173 (50 this FY) C3: 79 (20 this FY) | TBD | Engagement early on with policymakers, government officials and other stakeholders will increase the likelihood of research uptake downstream. So will tailoring dissemination to the policy priorities of specific stakeholders. | # meetings, briefing sessions and tailored presentations of research findings held with policy makers. Disaggregated by Global South participation. | Planned (cumulative) | Total: 552 (70 this FY) C1: 209 (0 this FY) C2: 217 (40 this FY) C3: 125 (30 this FY) C0: 1 (0 this FY) | Total: 638 (57 this FY) C1: 213 (2 this FY) C2: 265 (35 this FY) C3: 159 (20 this FY) C0: 1 (0 this FY) | TBD | Engagement early on with policymakers, government officials and other stakeholders will increase the likelihood of research uptake downstream. So will tailoring dissemination to the policy priorities of specific stakeholders.
|  | Achieved (cumulative) |  | C1: 22 Total (AFRICA - 6 meetings / attendance 130 ASIA - 10 meetings / attendance 70 MENA - 6 meetings / attendance 40) | C1: Target exceeded - 56 Total Africa - 18 meetings / 310 attendance Asia - 26 meetings / 146 attendance MENA -16 meetings / 129 attendance C2: 25 meetings / 300+ attendees C3: 14 meetings / 45 attendees C2/C3: 19 meetings / 75 attendees | Total: 168 (72 this year) C1: Target exceeded - 88 Total Africa - 21 meetings / 322 attendance Asia - 45 meetings / 297 attendance MENA - 22 meetings / 179 attendance C2: 55 meetings (30 this year) / 401 attendees C3: 25 meetings (11 this year) / 51 attendees | Total: 245 (77 this year) C1: 131 TOTAL (43 this year) C2: 78 TOTAL (23 this year) C3: 36 TOTAL (11 this year) | Total: 344 (99) C1: 162 (31) C2: 123 (45) C3: 59 (23) | Total: 482 (138 this FY) C1: 209 (47 this FY) C2: 177 (54 this FY) C3: 95 (36 this FY) C0: 1 (1 this FY) | TBD |  |  | Achieved (cumulative) | Total: 581 (99 this FY) C1: : 211 (2 this FY / 1 GS) C2: 230 (53 this FY / 5 GS) C3: 139 (44 this FY / 1 GS) C0: 1 (0 this FY / 0 GS) | Total: C1: C2: C3: | TBD
|  | Source | [10 empty] | Source
|  | Quarterly progress reports | [10 empty] | Quarterly progress reports
| Output Indicator 2.2 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 2.2 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Public events. # public events to present research to a broader audience (panels, presentation at conferences, major workshops, etc.). (Disaggregated by whether the event is organised by XCEPT or externally) | Planned (cumulative) |  | C1: Total 4 (1 event per partner + 1 joint event) | C1: 11 Total (3 events per partner + 2 joint events) C2/C3: Too early for milestone | Total: 23 C1: 18 C2: 4 C3: 1 | C1: Total 22 C2: 12 C3: 4 | Total: 72 (39 this FY) C1: 29 (4 this FY) C2: 30 (18 this FY) C3: 13 (9 this FY) | Total: 125 (39 this FY) C1: 47 (6 this FY) C2: 49 (17 this FY) C3: 27 (14 this FY) C0/Cross-component: 2 (2 this FY) | TBD |  | Public events. # public events to present research to a broader audience (panels, presentation at conferences, major workshops, etc.). Disaggregated by whether the event is organised by XCEPT or externally. Disaggregated by Global South participation. | Planned (cumulative) | Total: 170 (27 this FY) C1: 63 (0 this FY) C2: 62 (13 this FY) C3: 40 (13 this FY) C0/Cross-component: 5 (1 this FY) | Total: 215 (30 this FY) C1: 66 (0 this FY) C2: 94 (20 this FY) C3: 49 (9 this FY) C0/Cross-component: 6 (1 this FY) | TBD
|  | Achieved (cumulative) |  | C1: Total 5 (AFRICA - 3 events / attendance 200 ASIA - 1 event / attendance 50 MENA - 1 event / attendance 80) | C1: Target exceeded - 14 Total: Africa - 7 Asia - 3 MENA - 3 Joint - 1 | Total: 24 (10 this year) C1: Target met - 18 Total (4 this year): Africa - 9 Asia - 4 MENA - 4 Joint - 1 C2: 5 (5 this year) C3: 1 (1 this year) | Total: 41 (17 this year) C1: 25 TOTAL (7 this year) C2: 12 TOTAL (7 this year) C3: 4 TOTAL (3 this year) | Total: 86 (45) C1: 41 (16) C2: 32 (20) C3: 13 (9) | Total: 143 (57 this FY) C1: 63 (22 this FY) C2: 49 (17 this FY) C3: 27 (14 this FY) C0/Cross-component: 4 (4 this FY) | TBD |  |  | Achieved (cumulative) | Total: 185 (42 this FY) C1: 66 (3 this FY / 2 GS) C2: 74 (25 this FY / 10 GS) C3: 40 (13 this FY / 0 GS) C0: 5 (1 this FY / 1 GS) | Total: C1: C2: C3: C0: | TBD
|  | Source | [10 empty] | Source
|  | Quarterly progress reports | [10 empty] | Quarterly progress reports
| Output Indicator 2.3 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 2.3 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| Online views. Relative change in # of page views on the XCEPT website (and absolute number). Social media. Relative change in # of engagements and impressions with XCEPT social media (and absolute number). Newsletter. Relative change in # of XCEPT Newsletter subscribers (and absolute number). | Planned (cumulative) |  | C1: 900 combined total of publication downloads = 300 per partner | C1: 3,800 total downloads (6 reports with 200+ downloads per partner + 1 joint) C2/C3: Too early for milestone | Total: 5400 downloads C1: 5400 total downloads (27 reports with 200+ downloads) C2/C3: Too early for milestone [unchanged] | C1: 6800 total downloads (34 reports with 200+ downloads) C2: 300 total downloads (combined from partner website and XCEPT website) C3: Too early for milestone | Online views: 5% increase (from baseline of 48,000 in 22/23) Social media: 6% increase (from 550 engagements in 22/23 [and 92,000 impressions]) Newsletter: 10% increase (from 735) | Online views: 4% increase Social media: 5% increase Newsletter: 10% increase | TBD |  | Online views. Relative change in # of page views on the XCEPT website (and absolute number). Social media. Relative change in # of engagements and impressions with XCEPT social media (and absolute number). Newsletter. Relative change in # of XCEPT Newsletter subscribers (and absolute number). | Planned (cumulative) | Online views: 4% increase Social media: 5% increase Newsletter: 10% increase | Online views: 4% increase (174,720 page views) Social media: 5% increase (10,056 engagements) Newsletter: 10% increase (1937 subscribers) | TBD
|  | Achieved (cumulative) |  | C1: TOTAL = 1125 AFRICA - Downloads 622 total / 155 average; Views 2525 total / 420 average ASIA - Downloads total 503 / 125 average; Unique page views 345 total; Impressions (LI, FB, Twitter) 16,467 total / 4116 average MENA - Views 17,325 total / 1314 average; FB reaches: 792,542 total / 61,585) | C1: Target Met – 3,936 Total (2,811 this year) Asia – 2,059 downloads MENA – 1,877 downloads Africa – 9,682 views total (RVI does not measure downloads) 3936 TOTAL AFRICA 9682 views total / 403 average; ASIA - 2059 total downloads; 171 average; Blog unique page views 2496; Social Media impressions 17849 / 1983 average; MENA - Total downloads 1877 Unique PageViews: 109,874 total / 20,418 average; FB reach: 5,961,425 total / 887,796 average | Total: 8014 (4078 this year) C1: Target Exceeded - 8014 total (4078 this year) Report Downloads - 8014 Asia- 3106 MENA- 4753 Africa - 777 (RVI does not measure downloads) Page views - 283,066 Asia - 3505 MENA - 275,969 Africa - 13,991 Social media: Asia- 31,419 MENA-12,985,996 FB reach Africa- 75,160 Impressions, 2,406 engagements C2/C3: Total views of XCEPT website: 33,000+ Views of C2/C3 webpages: 1,000+ 77,000 Twitter Impressions 17,885 LinkedIn Impressions | Total: 12,718 (4,704 this year) Online views: 68,000+ page views on XCEPT website (35,000+ this year); 44,000+ page views of XCEPT content on partner websites. Social media: 1M+ impressions (950,000 this year). This includes 234,000 impressions on XCEPT’s Twitter and LinkedIn (139,000 this year). | Website: 74,174 page views on the XCEPT website this year. This is an increase of 54% on FY22/23. Social media: 7,339 engagements across XCEPT’s Twitter/X and LinkedIn this year. This is an increase of 1,241% on FY22/23. 161,701 impressions across XCEPT’s Twitter/X and LinkedIn this year. This is a 75% increase on FY22/23. Newsletter: 1,175 newsletter subscribers this year. This is an increase of 59% on FY22/23. | Website: 94,000 page views on the XCEPT website this year (up 27% from FY23/24). Social media: 1619 engagements across XCEPT’s Twitter/X and LinkedIn this year (down 78% from FY23/24). 125,474 impressions across XCEPT’s Twitter/X and LinkedIn this year (down 3% from FY23/24). Newsletter: 1,391 newsletter subscribers this year (up 18% from FY23/24). | TBD |  |  | Achieved (cumulative) | Website: 168,000 page views on the XCEPT website this year (up 79% from FY24/25). Social media: 9,577 engagements across XCEPT’s Twitter/X and LinkedIn this year (up 492% from FY24/25). 155,897 impressions across XCEPT’s Twitter/X and LinkedIn this year (up 24% from FY24/25). Newsletter: 1,761 newsletter subscribers this year (up 27% from FY24/25). | Website: Social media: Newsletter: | TBD
|  | Achieved (cumulative) | [10 empty] | Source
|  | Website(s) traffic statistics | [10 empty] | Website(s) traffic statistics
INPUTS (£) | FCDO (£) |  |  |  | Govt (£) | Other (£) | Total (£) | Total (£) | FCDO SHARE (%) |  |  | FCDO (£)
INPUTS (HR) | FCDO (FTEs) | [10 empty] | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) | Assumptions |  |  |  |  | Target (TOTAL) | Assumptions
NETWORKS. Establishment and expansion of a cross-regional network of local researchers and research organizations capable of undertaking field work in sensitive border areas, through knowledge exchange events and training / capacity-building opportunities | # knowledge and learning activities for researchers from the Global South | Planned (cumulative) | C1: 3 | C1: 6 | C1: 9 | C1: 8 | C1: 12 | C1: 17 | C1: 25 | TBD | Consortium members are able to identify local research partners capable to meet the quality standards required by the project's audience in all research areas, noting that the project's objectives emphasize timeliness and quality of deliver over capacity investments | C1 discontinued - Output 3 no longer applicable. |  |  |  |  | Consortium members are able to identify local research partners capable to meet the quality standards required by the project's audience in all research areas, noting that the project's objectives emphasize timeliness and quality of deliver over capacity investments
|  | Achieved (cumulative) | C1: 3 | C1: 4 | C1: 4 | C1: 5 | C1: 11 (6 this year) | C1: 21 | C1: 73 (52 this FY) | TBD
Source
Quarterly progress reports
| Output Indicator 3.2 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL)
| # times researchers from the Global South have benefited from knowledge and learning activities (disaggregated by region and gender) | Planned (cumulative) | No milestone set | C1: 120 Total (40 per region - 40% female) | C1: 140 Total (46 per region - 40% female) | C1: 136 Total (40% female) | C1: 148 Total (40% female) | C1: 267 Total (40% female) | C1: 367 Total (40% female) | TBD
|  | Achieved (cumulative) | C1: 65 (13f/52m) | C1: 124 (35% female) | C1: 124 (35% female) | C1: 126 (37% female) (46 female) | C1: 197 Total (71 this year) (38% female) | C1: 257 (36.57% female) | C1: 605 (348 this FY) (50.7% female) | TBD
Source
Quarterly progress reports
| Output Indicator 3.3 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL)
| a) # researchers from the Global South involved in X-Border research b) # researchers from the Global South leading X-Border research c) # new researchers from the Global South involved in X-Border research | Planned (cumulative) | No milestone set | C1: a) Total 60 = 20 per region (Min. 40% female) b) Total 12 = 4 per region (Min. 40% female) | C1: a) Total 72 = 24 per region (Min. 40% female) b) Total 15 = 5 per region (Min. 40% female) | C1: a) Total 92 (Min. 40% female). b) Total 36 (Min. 40% female) | C1: a) Total 95 (Min. 40% female) b) Total 39 (Min. 40% female) | C1: a) Total 130 (year-on-year increase in % of women) b) Total 45 (year on year increase in % of women) c) Total 15 (Min. 40%) | C1: a) Total 150 (year-on-year increase in % of women) b) Total 52 (year on year increase in % of women) c) Total 15 (Min. 40%) | TBD
|  | Achieved (cumulative) | C1: AFRICA - 11 (3f/8m) / leading 2 ( 0f/2m) ASIA - 18 (14f/4m) / leading 4 (4f/0m)) - MENA - 12 (4f/8m) / leading 7 (2f/5m) | C1: a) Total 61, 35% Female AFRICA - 20 (4f/16m), ASIA - 22 (16f/6m) MENA - 19 (2f/17m) b) Total 15, 40% Female AFRICA - 2 (0f/2m) ASIA - 6 (5f/1m) - MENA - 7 (1f/6m) | C1: a) Total 86, 33% Female AFRICA - 21 (4f/17m), ASIA - 46 (24f/22m), MENA - 19 (2f/17m) b) Total 30, 37% Female AFRICA - 3 (1f/2m) ASIA - 19 (9f/10m), MENA - 8 (1f/7m) | C1: a) Total 99, 34% Female AFRICA - 21 (4F/17M) ASIA - 55 (28f/27m) MENA - 23 (2f/21m) b) Total 35, 34% Female AFRICA - 6 (1f/5m) ASIA - 21 (10f/11m) MENA - 8 (1f/7m) | C1: a) Total 117 (18 new this year), 33% female b) Total 40 (5 new this year), 33% female | a) 164 (increase to 34.7% from 33% last year) b) 52 (decrease to 28.84% from 33% last year) c) 24 (58%) | C1: a) Total 219 (increase to 37.8%% from 34.7% last year) b) Total 72 (increase to 39.4% from 28.84% last year) c) Total 16 (43.7% women) | TBD
Source
Quarterly progress reports
| Output Indicator 3.4 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL)
| Percentage of researchers from the Global South reporting an increase in capacity of core professional skills (Research Methods, Analysing and interpreting data, research ethics, writing for a policy audience, and public speaking). | Planned (cumulative) |  | No milestone - tool in developmental stage | C1: Year-on-year increase in the average skills level of researchers with the program for more than one year (question 2g) | C1: Year-on-year increase in the average skills level of researchers with the program for more than one year (question 2g) | C1: Year-on-year increase in the average skills level of researchers with the program for more than one year (question 2g) | C1: 70% | C1: 75% | TBD
|  | Achieved (cumulative) |  |  | C1: Research Methods 3.74, Analysing and interpreting data 3.86, Research ethics 4.08, Writing for a policy audience 3.39, Public speaking 3.93 AFRICA: Research methods 4.06, Analysing and interpreting data 3.81, Research ethics 4.19, Writing for a policy audience 3.63, Public speaking 4.44 ASIA: Research methods 3.79, Analysing and interpreting data 3.78, Research ethics 3.81, Writing for a policy audience 3.41, Public speaking 3.71 MENA: Research methods 3.38, Analysing and interpreting data 4, Research ethics 4.25, Writing for a policy audience 3.13, Public speaking 3.63 | C1: Research Methods 4.06 (+0.32), Analysing and interpreting data 3.83 (-0.03), Research ethics 4.13 (+0.05), Writing for a policy audience 3.34 (-0.05), Public speaking 3.73 (-0.20) AFRICA: Research methods 4.00, Analysing and interpreting data 3.67, Research ethics 4.33, Writing for a policy audience 3.33, Public speaking 4.00 ASIA: Research methods 4.2, Analysing and interpreting data 3.8, Research ethics 4.3, Writing for a policy audience 3.1, Public speaking 3.6 MENA: Research methods 4.0, Analysing and interpreting data 4.0, Research ethics 3.8, Writing for a policy audience 3.6, Public speaking 3.6 | C1: Overall minor decrease in average skill by 0.21/5: Research Methods 3.64 (-0.42) Analysing and interpreting data 3.46 (-0.37) Research ethics 4.05 (-0.08) Writing for a policy audience 3.06 (-0.28) Public speaking 3.82 (+0.09) | C1: 89.3% said that their participation in the X-Border project contributed to their professional development, with an average increase across the core professional skills of +0.19 out of 5 | C1: 93% | TBD
Source
Professional development monitoring forms (filled yearly by researchers)
INPUTS (£) | FCDO (£) |  |  |  | Govt (£) | Other (£) | Total (£) | Total (£) | FCDO SHARE (%) |  |  | FCDO (£)
INPUTS (HR) | FCDO (FTEs) | [10 empty] | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) | Assumptions | Output Indicator 4.1 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL) | Assumptions
XCEPT Research Fund: The Fund is established and makes efficient awards to relevant downstream research and XCEPT-related awardees of value to the programme. | # of awards made | Planned (cumulative) |  |  | Too early for milestone | C2: 3 | C2: 15 | C2: 48 (22 this FY) | C2: 62 (10 this FY) | TBD | - that Fund budget is available for disbursement to downstream awardees in line with planned expenditure. - that sufficient adequate quality research organisations/institutions and researchers are avaialble in the Global South and show interest in Fund opportunities. | # of awards made | Planned (cumulative) | C2: 103 (35 this FY) | C2: 107 (0 this FY) | TBD | - that Fund budget is available for disbursement to downstream awardees in line with planned expenditure. - that sufficient adequate quality research organisations/institutions and researchers are avaialble in the Global South and show interest in Fund opportunities.
|  | Achieved (cumulative) |  |  | C2: 4 | C2: 8 (4 this FY) | C2: 26 (18 this year) | C2: 52 (26 this year) | C2: 68 (16 this FY) | TBD |  |  | Achieved (cumulative) | C2: 107 (39 this FY) | C2: | TBD
Source
Quarterly progress reports
| Output Indicator 4.2 |  | Milestone 1 (March 2019) | Milestone 2 (March 2020) | Milestone 3 (March 2021) | Milestone 4 (March 2022) | Milestone 5 (March 2023) | Milestone 6 (March 2024) | Milestone 7 (March 2025) | Target (TOTAL) |  | Output Indicator 4.2 |  | Milestone 8 (March 2026) | Milestone 9 (February 2027) | Target (TOTAL)
| % of awards led by, or meaningfully contributed to by, Global South researchers/organisations | Planned (cumulative) |  |  | Too early for milestone | C2: 10% | C2: 20% | C2: 33% | C2: 33% | TBD |  | % of awards led by, or meaningfully contributed to by, Global South researchers/organisations. Disaggregated by Global South PI/Co-PI vs meaningful contribution. | Planned (cumulative) | C2: 33% | NA | TBD
|  | Achieved (cumulative) |  |  |  | C2: 14% | C2: 27% | C2: 40% (21 awards in total, 14 this year) | C2: 33% | TBD |  |  | Achieved (cumulative) | C2: 28% (30 awards) 18 awards (17%) have had a Global South PI / Co-PI |  | TBD
Source
Quarterly progress reports
Quarterly progress reports
INPUTS (£) | FCDO (£) |  |  |  | Govt (£) | Other (£) | Total (£) | Total (£) | FCDO SHARE (%) |  |  | FCDO (£)
INPUTS (HR) | FCDO (FTEs) | [10 empty] | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indicator 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Output indicator 1.1 | Milestone 3 amended from "16 (5 per partner + 1 joint)" to "19 (6 per partner + 1 joint)" | Adrian Morel | 2020-05-05
2 | Output indicator 1.1 | Milestone 4 amended from "26 (8 per partner + 2 joint)" to "32 (10 per partner + 2 joint)" | Adrian Morel | 2020-05-05
3 | Output indicator 1.1 | Milestone 5 amended from "39 (12 per partner + 3 joint)" to "45 (14 per partner + 3 joint)" | Adrian Morel | 2020-05-05
4 | Output indicator 1.1 | (TOTAL) amended from "39 (12 per partner + 3 joint)" to "45 (14 per partner + 3 joint)" | Adrian Morel | 2020-05-05
5 | Output indicator 1.2 | Milestone 3 amended from "21 (7 per partner)" to "33 (11 per partner)" | Adrian Morel | 2020-05-05
6 | Output indicator 1.2 | Milestone 4 amended from "33 (11 per partner)" to "51 (17 per partner)" | Adrian Morel | 2020-05-05
7 | Output indicator 1.2 | Milestone 5 amended from "45 (15 per partner)" to "69 (23 per partner)" | Adrian Morel | 2020-05-05
8 | Output indicator 1.2 | Target (TOTAL) amended from "45 (15 per partner)" to "45 (14 per partner + 3 joint)" | Adrian Morel | 2020-05-05
9 | Output indicator 1.3 | Milestone 3 amended from "27 (AFRICA - 7 ; ASIA - 7 ; MENA - 9; Joint - 4)" to "31 (9 per partner + 4 joint)" | Adrian Morel | 2020-05-05
10 | Output indicator 1.3 | Milestone 4 amended from "45 (AFRICA - 12 ; ASIA - 12 ; MENA - 15; Joint - 6)" to "54 (16 per partner + 6 joint)" | Adrian Morel | 2020-05-05
11 | Output indicator 1.3 | Milestone 5 amended from "63 (AFRICA - 17 ; ASIA - 17 ; MENA - 21; Joint - 8)" to "80 (24 per partner + 8 joint)" | Adrian Morel | 2020-05-05
12 | Output indicator 1.3 | Target (TOTAL) amended from "63 (AFRICA - 17 ; ASIA - 17 ; MENA - 21; Joint - 8)" to "80 (24 per partner + 8 joint)" | Adrian Morel | 2020-05-05
13 | Output indicator 1.4 | Indicator amended from "Online views and downloads. Aggregated # of page views and publication downloads. Social media reaches/impressions. Broken down by region" to "Downloads. Aggregated # of publication downloads. Broken down by region" | Adrian Morel | 2020-05-05
14 | Output indicator 1.4 | Milestone 3 amended from "5700 Total (Per partner: 5 research reports with 200+ downloads each / 9 policy briefs/research papers with 100+ downloads each)" to "3800 total downloads (6 reports with 200+ downloads per partner + 1 joint)" | Adrian Morel | 2020-05-05
15 | Output indicator 1.4 | Milestone 4 amended from "8100 Total (Per partner: 8 research reports with 200+ downloads each /11 policy briefs/research papers with 100+ downloads each)" to "6400 total downloads (10 reports with 200+ downloads per partner + 2 joint)" | Adrian Morel | 2020-05-05
16 | Output indicator 1.4 | Milestone 5 amended from "11700 Total (Per partner: 12 research reports with 200+ downloads each /15 policy briefs/research papers with 100+ downloads each)" to "9000 total downloads (14 reports with 200+ downloads per partner + 3 joint)" | Adrian Morel | 2020-05-05
17 | Output indicator 1.4 | Target (TOTAL) amended from "11700 Total (Per partner: 12 research reports with 200+ downloads each /15 policy briefs/research papers with 100+ downloads each)" to "9000 total downloads (14 reports with 200+ downloads per partner + 3 joint)" | Adrian Morel | 2020-05-05
18 | Output indicator 2.1 | Milestone 3 changed from "36 Total (12 per partner)" to 42 Total (14 per partner) | Adrian Morel | 2020-05-05
19 | Output indicator 2.1 | Milestone 4 changed from "54 Total (18 per partner)" to "66 Total (22 per partner)" | Adrian Morel | 2020-05-05
20 | Output indicator 2.1 | Milestone 5 amended from "72 Total (24 per partner)" to "90 Total (30 per partner)" | Adrian Morel | 2020-05-05
21 | Output indicator 2.1 | Target (TOTAL) amended from "72 Total (24 per partner)" to "90 Total (30 per partner)" | Adrian Morel | 2020-05-05
22 | Output indicator 2.2 | Indicator amended from "# public dissemination events held to present research findngs to a broader audience including policy makers (and attendance figures). Broken down by region" to "# public online or offline dissemination events held to present research findngs to a broader audience including policy makers (and attendance figures). Broken down by region. " | Adrian Morel | 2020-05-05
23 | Output indicator 2.2 | Milestone 3 amended from "Total 7 (2 events per partner + 2 joint events)" to "Total 11 (3 events per partner + 2 joint events)" | Adrian Morel | 2020-05-05
24 | Output indicator 2.2 | Milestone 4 amended from "Total 12 (3 events per partner + 3 joint events)" to "Total 18 (5 events per partner + 3 joint events)" | Adrian Morel | 2020-05-05
25 | Output indicator 2.2 | Milestone 5 amended from "Total 16 (4 events per partner + 4 joint events)" to "Total 25 (7 events per partner + 4 joint events)" | Adrian Morel | 2020-05-05
26 | Output indicator 2.2 | Target (Total) amended from "Total 16 (4 events per partner + 4 joint events)" to "Total 25 (7 events per partner + 4 joint events)" | Adrian Morel | 2020-05-05
27 | Output Indicator 3.2 | Target per region corrected from "(40 per region)" to "(46 per region)" for Y3, "(53 per region)" for Y4, and "(60 per region)" for Y5 and total | Nathan Shea | 2021-02-19
28 | Output Indicator 3.4 | Indicator added for Y3-5: "Year-on-year increase in the average skills level of researchers with the program for more than one year (question 2g)" | Nathan Shea | 2021-02-19
29 | Impact statement | Language amended from "Improved response to conflict and instability in border areas by DFID/HMG and partners contributes to reduced conflict and violence in Africa, MENA and Asia" to "Policies and programmes have a more effective influence/impact on fostering peaceful behaviour and addressing violence and conflict". This wording is less focused on borderlands and also updates language to FCDO. | Charlie de Rivaz | 2021-10-12
30 | Throughout | Language amended to replace ‘X-Border’ with ‘XCEPT’ to ensure the work of all three components is represented by the logframe indicators. For example, Outcome indicator 1 changes from ‘# of documented cases of X-Border research findings referenced’ to ‘# of documented cases of XCEPT research findings referenced’. | Charlie de Rivaz | 2021-10-12
31 | Outcome statement | Language amended from "DFID" to "FCDO". | Charlie de Rivaz | 2021-10-12
32 | Outcome indicator 1 | Milestone 3 targets added for C2 and C3: "Too early for milestone" | Charlie de Rivaz | 2021-10-12
33 | Outcome indicator 1 | Milestone 4 targets added for C2 (1) and C3 (1). | Charlie de Rivaz | 2021-10-12
34 | Outcome indicator 1 | Milestone 5 targets added for C2 (1) and C3 (1). | Charlie de Rivaz | 2021-10-12
35 | Outcome indicator 1 | Milestone 6 targets added for C2 (3) and C3 (3). | Charlie de Rivaz | 2021-10-12
36 | Outcome indicator 1 | Milestone 7 targets added for C2 (6) and C3 (5). | Charlie de Rivaz | 2021-10-12
37 | Outcome indicator 1 | Milestone TOTAL targets added for C2 (6) and C3 (5). | Charlie de Rivaz | 2021-10-12
38 | Output indicators | Language amended across all indicators to remove ‘broken down by region’. As C2 and C3 are less regionally focused, we recommend removing this requirement from the wording, although C1 can still provide this information if desired. | Charlie de Rivaz | 2021-10-12
39 | Output 1 statement | Language amended from "Production of high quality, policy-oriented research on the conflict-affected borderlands of Africa, the Middle East and Asia" to "Policy-relevant research, evidence and recommendations are generated and documented about conflict-affected borderlands, cross-border and regional conflict dynamics, drivers of violent and peaceful behaviour, and associated policy responses.". This new wording includes C2 and C3 themes. | Charlie de Rivaz | 2021-10-12
40 | Output 1 assumptions | Language added to assumptions: "Research reports include long-form research reports, journal articles and edited books. Policy briefs are typically up to 2,500 words. Working papers/research papers are typically between 3,000 and 20,000 words, prepared as drafts and reflecting analysis or elements of XCEPT research findings (interim or final) in pre-publication form. We assume the 'blog pieces/articles' category will be flexibly interpreted to include novel and alternative presentation and research communication formats and activities."
41 | Output indicator 1.1 | Milestone 3 targets added for C2 and C3: "Too early for milestone" | Charlie de Rivaz | 2021-10-12
42 | Output indicator 1.1 | Milestone 4 targets added for C2 (1) and C3 (too early for milestone). Note, C2 figure was revised down from 5 due to budget deferral for FY 21/22. | Charlie de Rivaz | 2021-10-12
43 | Output indicator 1.1 | Milestone 5 targets added for C2 (14) and C3 (too early for milestone). | Charlie de Rivaz | 2021-10-12
44 | Output indicator 1.1 | Milestone 6 targets added for C2 (18) and C3 (6). Note, C2 figure revised down from 20 and C3 figure down from 10 due to re-planning. | Charlie de Rivaz | 2021-10-12
45 | Output indicator 1.1 | Milestone 7 targets added for C2 (23) and C3 (16). Note, C2 figure revised down from 24 due to re-planning. | Charlie de Rivaz | 2021-10-12
46 | Output indicator 1.1 | Milestone TOTAL targets added for C2 (23) and C3 (16). Note, C2 figure revised down from 24 due to re-planning. | Charlie de Rivaz | 2021-10-12
47 | Output Indicator 1.2 | Requirement for these to be "Broken down by region" removed, given C2 and C3 are less regionally focused than C1. | Charlie de Rivaz | 2021-10-12
48 | Output indicator 1.2 | Milestone 3 targets added for C2 and C3: "Too early for milestone" | Charlie de Rivaz | 2021-10-12
49 | Output indicator 1.2 | Milestone 4 targets added for C2 (18) and C3 (8). Note, C2 figure revised down from 30 and C3 figure down from 13 due to budget deferral for FY 21/22. | Charlie de Rivaz | 2021-10-12
50 | Output indicator 1.2 | Milestone 5 targets added for C2 (45) and C3 (36). Note, C2 figure revised down from 50 due to knock-on effect of FY 21/22 budget deferral. | Charlie de Rivaz | 2021-10-12
51 | Output indicator 1.2 | Milestone 6 targets added for C2 (65) and C3 (36). Note, C2 figure revised down from 70 due to re-planning. | Charlie de Rivaz | 2021-10-12
52 | Output indicator 1.2 | Milestone 7 targets added for C2 (74) and C3 (47). Note, C3 figure revised down from 50 due to re-planning. | Charlie de Rivaz | 2021-10-12
53 | Output indicator 1.2 | Milestone TOTAL targets added for C2 (74) and C3 (47). Note, C2 figure revised down from 75 and C3 figure down from 50 due to re-planning. | Charlie de Rivaz | 2021-10-12
54 | Output indicator 1.3 | Language amended from "Number of published blog pieces and articles, broken down by region" to "Number of research outputs other than full-length research reports, policy briefs or research papers. Includes blog posts, news releases, podcasts, photo essays etc. Broken down by type" This is because outputs such as podcasts and videos should also be recorded, and this output seems the most logical place to include them. | Charlie de Rivaz | 2021-10-12
55 | Output indicator 1.3 | Milestone 3 targets added for C2 and C3: "Too early for milestone" | Charlie de Rivaz | 2021-10-12
56 | Output indicator 1.3 | Milestone 4 targets added for C2 (14) and C3 (5). Note, C2 figure revised down from 20 due to budget deferral for FY 21/22. | Charlie de Rivaz | 2021-10-12
57 | Output indicator 1.3 | Milestone 5 targets added for C2 (40) and C3 (36). Note, C2 figure revised down from 50 due to knock-on effect of FY 21/22 budget deferral. | Charlie de Rivaz | 2021-10-12
58 | Output indicator 1.3 | Milestone 6 targets added for C2 (60) and C3 (70). Note, C2 figure revised down from 70 due to re-planning. C3 figure revised down from 125 due to counting mistake in the previous iteration of the logframe. | Charlie de Rivaz | 2021-10-12
59 | Output indicator 1.3 | Milestone 7 targets added for C2 (85) and C3 (95). Note, C3 figure revised down from 185 due to counting mistake in the previous iteration of the logframe. | Charlie de Rivaz | 2021-10-12
60 | Output indicator 1.3 | Milestone TOTAL targets added for C2 (85) and C3 (95). Note, C3 figure revised down from 185 due to counting mistake in the previous iteration of the logframe. | Charlie de Rivaz | 2021-10-12
61 | Output indicator 1.4 | Indicator 1.4 moved to sitting under Output 2, as indicator 2.3. This is because it is more appropriate as an indicator of uptake. | Charlie de Rivaz | 2021-10-12
62 | Output indicator 2.1 | Milestone 3 targets added for C2 (10) and C3 (6). | Charlie de Rivaz | 2021-10-12
63 | Output indicator 2.1 | Milestone 4 targets added for C2 (25) and C3 (16). Note, C2 figure revised down from 55 due to budget deferral for FY 21/22. | Charlie de Rivaz | 2021-10-12
64 | Output indicator 2.1 | Milestone 5 targets added for C2 (70) and C3 (26). Note, C2 figure revised down from 85 due to knock-on effect of FY 21/22 budget deferral. | Charlie de Rivaz | 2021-10-12
65 | Output indicator 2.1 | Milestone 6 targets added for C2 (110) and C3 (37). Note, C2 figure revised down from 125 due to re-planning. | Charlie de Rivaz | 2021-10-12
66 | Output indicator 2.1 | Milestone 7 targets added for C2 (140) and C3 (43). Note, C2 figure revised down from 150 due to re-planning. | Charlie de Rivaz | 2021-10-12
67 | Output indicator 2.1 | Milestone TOTAL targets added for C2 (140) and C3 (43). Note, C2 figure revised down from 150 due to re-planning. | Charlie de Rivaz | 2021-10-12
68 | Output indicator 2.2 | Milestone 3 targets added for C2 and C3: "too early for milestone". | Charlie de Rivaz | 2021-10-12
69 | Output indicator 2.2 | Milestone 4 targets added for C2 (4) and C3 (1). Note, C2 figure revised down from 9 due to budget deferral for FY 21/22. | Charlie de Rivaz | 2021-10-12
70 | Output indicator 2.2 | Milestone 5 targets added for C2 (20) and C3 (4). Note, C2 figure revised down from 23 due to knock-on effect of FY 21/22 budget deferral. | Charlie de Rivaz | 2021-10-12
71 | Output indicator 2.2 | Milestone 6 targets added for C2 (28) and C3 (8). Note, C2 figure revised down from 33 due to re-planning. | Charlie de Rivaz | 2021-10-12
72 | Output indicator 2.2 | Milestone 7 targets added for C2 (34) and C3 (9). Note, C2 figure revised down from 37 and C3 figure revised down from 10 due to re-planning. | Charlie de Rivaz | 2021-10-12
73 | Output indicator 2.2 | Milestone TOTAL targets added for C2 (34) and C3 (9). Note, C2 figure revised down from 37 and C3 figure revised down from 10 due to re-planning. | Charlie de Rivaz | 2021-10-12
74 | Output indicator 2.3 | This indicator moved here from being Output indicator 1.4. | Charlie de Rivaz | 2021-10-12
75 | Output indicator 2.3 | Milestone 3 and Milestone 4 targets added for C2 and C3: "too early for milestone". | Charlie de Rivaz | 2021-10-12
76 | Output indicator 2.3 | Milestone 5 targets added for C2 ("600 total downloads (3 reports with 200+ downloads combined from partner website and XCEPT website)") and C3 ("Too early for milestone"). Note, C2 figure revised down from "1,581 total downloads" due to knock-on effect of FY 21/22 budget deferral. | Charlie de Rivaz | 2021-10-12
77 | Output indicator 2.3 | Milestone 6 targets added for C2 ("3,200 total downloads (13 reports with 200+ downloads combined from partner and XCEPT website, plus figure from previous year)") and C3 ("1,200 total downloads (6 journal articles with 200+ downloads combined from academic and XCEPT website)"). Note, C2 figure revised down from "5,257 total downloads" and C3 revised down from "1,932 total downloads" due to knock-on effect of FY 21/22 budget deferral. | Charlie de Rivaz | 2021-10-12
78 | Output indicator 2.3 | Milestone 7 targets added for C2 ("5,600 total downloads (4 reports with 200+ downloads combined from partner and XCEPT website, plus figure from previous year)") and C3 ("3,200 total downloads (10 journal articles with 200+ downloads combined from academic and XCEPT website, plus figure from previous year)"). Note, C2 figure revised down from "9,336 total downloads" and C3 revised down from "3,108 total downloads" due to revised approach to counting downloads. | Charlie de Rivaz | 2021-10-12
79 | Output indicator 2.3 | Milestone TOTAL targets added for C2 ("5,600 total downloads") and C3 ("3,200 total downloads"). Note, C2 figure revised down from "9,336 total downloads" and C3 revised down from "3,108 total downloads" due to revised approach to counting downloads. | Charlie de Rivaz | 2021-10-12
80 | Output 4 | This output and associated indicators and targets added to the logframe. Indicaotrs amended in consult with FCDO on 3 November. | Charlie de Rivaz | 2021-11-05
81 | Output indicator 4.1 | Milestone 4 target revised down from 5 to 2 due to budget deferral for FY 21/22. | Charlie de Rivaz | 2021-10-12
82 | Output indicator 4.3 | Language amended to remove "disaggregated by region". This is less relevant for C2 than for C1. | Charlie de Rivaz | 2021-10-12
83 | Outcome indicator 1 | Milestone 4 target for C1 revised down from 6 to 5 due to budget deferral for FY 21/22. | Nathan Shea | 2021-10-15
84 | Outcome indicator 1 | Milestone 5 target for C1 revised down from 9 to 7 due to budget deferral for FY 22/23 | Nathan Shea | 2021-10-15
85 | Outcome indicator 1 | Milestone TOTAL target for C1 revised down from 9 to 7 due to budget deferral | Nathan Shea | 2021-10-15
86 | Output indicator 1.1 | Milestone 4 target for C1 revised down from 32 to 27 due to budget deferral for FY 21/22 | Nathan Shea | 2021-10-15
87 | Output indicator 1.1 | Milestone 5 target for C1 revised down from 45 to 34 due to budget deferral for FY22/23 | Nathan Shea | 2021-10-15
88 | Output indicator 1.1 | Milestone TOTAL target for C1 revised down from 45 to 34 due to budget deferral | Nathan Shea | 2021-10-15
89 | Output indicator 1.2 | Milestone 5 target for C1 revised down from 69 to 60 due to budget deferral for FY22/23 | Nathan Shea | 2021-10-15
90 | Output indicator 1.2 | Milestone TOTAL target for C1 revised down from 69 to 60 due to budget deferral | Nathan Shea | 2021-10-15
91 | Output indicator 1.3 | Milestone 4 target for C1 revised up from 54 to 79 | Nathan Shea | 2021-10-15
92 | Output indicator 1.3 | Milestone 5 target for C1 revised up from 80 to 93 | Nathan Shea | 2021-10-15
93 | Output indicator 1.3 | Milestone TOTAL target for C1 revised up from 80 to 93 | Nathan Shea | 2021-10-15
94 | Output indicator 2.1 | Milestone 4 target for C1 revised up from 66 to 68 | Nathan Shea | 2021-10-15
95 | Output indicator 2.1 | Milestone 5 target for C1 revised down from 90 to 80 due to budget deferral for FY22/23 | Nathan Shea | 2021-10-15
96 | Output indicator 2.1 | Milestone TOTAL target for C1 revised down from 90 to 80 due to anticipated budget deferral | Nathan Shea | 2021-10-15
97 | Output indicator 2.2 | Milestone 5 target for C1 revised down from 25 to 22 due to budget deferral for FY22/23 | Nathan Shea | 2021-10-15
98 | Output indicator 2.2 | Milestone TOTAL target for C1 revised down from 25 to 22 due to anticipated budget deferral | Nathan Shea | 2021-10-15
99 | Output indicator 2.3 | Milestone 4 target for C1 revised down from 6400 to 5400 due to budget deferral for FY21/22 | Nathan Shea | 2021-10-15
100 | Output indicator 2.3 | Milestone 5 target for C1 revised down from 9000 to 6800 due to budget deferral for FY22/23 | Nathan Shea | 2021-10-15
101 | Output indicator 2.3 | Milestone TOTAL target for C1 revised down from 9000 to 6800 due to budget deferral | Nathan Shea | 2021-10-15
102 | Output indicator 3.1 | Language amended from "events" to "activities". Change made to reflect existing and ongoing limitations on international travel and budget deferral. | Charlie de Rivaz | 2021-11-05
103 | Output indicator 3.2 | Language amended from "events" to "activities". Change made to reflect existing and ongoing limitations on international travel and budget deferral | Charlie de Rivaz | 2021-11-05
104 | Output indicator 3.4 | Language amended from "Professional development of local researchers supported by programme. Measured using tool and metric devloped for XCEPT and tangible research outcomes (papers researcher/written, presentations delivered) as well as researchers' own perception; confidence in research skills etc." to "Year on year increase in the average self-reported capacity of researchers from the Global South in core professional skills (Research Methods, Analysing and interpreting data, research ethics, writing for a policy audience, and public speaking)." Change made to properly reflect the targets being measured by the indicator. | Nathan Shea | 2021-10-15
105 | Output indicator 3.1 | Milestone 4 target revised down from 12 to 8 due to budget deferral for FY 21/22 and revised scope for indicator | Nathan Shea | 2021-10-15
106 | Output indicator 3.1 | Milestone 5 target revised down from 15 to 12 due to budget degeral for FY22/23 | Nathan Shea | 2021-10-15
107 | Output indicator 3.1 | Milestone TOTAL target revised down from 15 to 12 due to budget degeral | Nathan Shea | 2021-10-15
108 | Output indicator 3.2 | Milestone 4 target revised down from 160 to 136 due to budget deferral for FY21/22 | Nathan Shea | 2021-10-15
109 | Output indicator 3.2 | Milestone 5 target revised down from 180 to 148 due to budget deferral for FY22/23 | Nathan Shea | 2021-10-15
110 | Output indicator 3.2 | Milestone TOTAL target revised down from 180 to 148 due to budget deferral | Nathan Shea | 2021-10-15
111 | Output indicator 3.3 | Milestone 4 target revised up from 84 to 92 and milestone target for gender revised up from 18 to 36 | Nathan Shea | 2021-10-15
112 | Output indicator 3.3 | Milestone 5 target revised up from 90 to 95 and target re gender revised up from 21 to 39 | Nathan Shea | 2021-10-15
113 | Output indicator 3.3 | Milestone TOTAL target revised up from 90 to 95 and milestone target re gender revised up from 21 to 39 | Nathan Shea | 2021-10-15
114 | Impact indicator 1 | Language for source data amended from "UCDP / ACLED / Global Burden of Armed Violence / National VIMS datasets when available" to "Various, including both quantitative (e.g UCDP, ACLED, Global Burden of Armed Violence, National VIMS datasets when available) and qualitative (e.g. ICG CrisisWatch, programme Risk Matrix, local security reports)". Change made to reflect the diversity of data used to monitor violence | Nathan Shea | 2021-10-15
115 | Outcome indicator 1 Source Language | Language changed from "X-border" to "XCEPT" | Charlie de Rivaz | 2021-11-05
116 | Output indicator 1.1 | Milestone 5 target for C2 revised down from 14 to 12, based on budget deferral leaving C2 at 46% of its original budget for FY 22/23 | Mette Bastholm | 2023-06-22
117 | Output indicator 1.1 | Milestone 5 target for C3 revised up from 0 to 2 as several briefs/research papers will be converted to peer-reviewed research reports | Mette Bastholm | 2023-06-22
118 | Output indicator 1.2 | Milestone 5 targets for C2 revised down from 45 to 35 based on budget deferral | Mette Bastholm | 2023-06-22
119 | Output indicator 1.2 | Milestone 5 targets for C3 revised down from 17 to 10 as several briefs/research papers will be converted to peer-reviewed research reports | Mette Bastholm | 2023-06-22
120 | Output indicator 1.3 | Milestone 5 targets for C2 revised down from 40 to 27 based on budget deferrals | Mette Bastholm | 2023-06-22
121 | Output indicator 2.1 | Milestone 5 targets for C2 revised down from 70 to 48 based on budget deferrals | Mette Bastholm | 2023-06-22
122 | Output indicator 2.2 | Milestone 5 targets for C2 revised down from 20 to 12 based on budget deferrals | Mette Bastholm | 2023-06-22
123 | Output indicator 2.3 | Milestone 5 targets for C2 revised down from 600 to 300 based on budget deferrals | Mette Bastholm | 2023-06-22
124 | Output indicator 4.1 | The wording of Output Indicator 4.1 was changed from “# of successfully closed (completed) awards” to “# of awards made”. This was done to incentivise taking the time to do research well, rather than hurrying to complete awards at the expense of research quality. | Mette Bastholm | 2023-06-22
125 | Output indicator 4.1 | Milestone 5 target changed from 15 awards completed to 15 awards made, given change in language and 75% reduction in size of Fund for the year | Mette Bastholm | 2023-06-22
126 | Output indicator 4.2 | Milestone 5 target revised down from 25% to 20% to reflect changes to the Fund's commissioning strategy as a result of the reduction in the Fund's size | Mette Bastholm | 2023-06-22
127 | Output indicator 1.1 | Wording changed from ‘# published research reports, including peer-reviewed journal articles and edited volumes’ to ‘# journal articles or peer reviewed research reports’ to indicate compliance with Frascati standards | Mette Bastholm | 2023-06-22
128 | Outcome indicator 1 | Wording changed from "Policy uptake. # of documented cases of XCEPT research findings referenced in policy / strategy documents, or otherwise informing interventions, strategy or policy by HMG, other donors, and national governments" to "Policy uptake. # of cases where XCEPT research influences policy, programme design or implementation (assessed through tangible examples)" to simplify the wording, per FCDO guidance. Cases to include HMG and/or other major development partners and stakeholders, such as other donors, national governments, multilateral agencies, major NGOs, etc. | Charlie de Rivaz | 2023-09-29
129 | Outcome indicator 1 | Milestone 6 target increased from 6 to 28 to better reflect expected impact. | Charlie de Rivaz | 2023-09-29
130 | Outcome indicator 1 | Milestone 7 target increased from 11 to 39 to better reflect expected impact. | Charlie de Rivaz | 2023-09-29
131 | Outcome indicator 2 | Wording changed from "Influencing the policy debate. # of citations of XCEPT research and research outputs in the academic literature, grey literature, and the media / social media" to "Influencing the policy debate. # of citations of XCEPT research and research outputs in the academic literature, grey literature, and the media" to remove mention of social media. | Charlie de Rivaz | 2023-09-29
132 | Output indicator 1.1 | Milestone 6 target increased from 58 to 101 to reflect that C1 is continuing as part of the programme and to increase targets for C2 and C3. | Charlie de Rivaz | 2023-09-29
133 | Output indicator 1.1 | Milestone 7 target increased from 73 to 145 to reflect that C1 is continuing as part of the programme and to increase targets for C2 and C3. | Charlie de Rivaz | 2023-09-29
134 | Output indicator 1.2 | Wording changed from "Policy briefs: set of tailored policy recommendations based on XCEPT research / Research papers: Short papers documenting exploratory research and/or preparatory research (scoping papers, background papers). Broken down by type." to "Briefing notes: short policy-focused papers based on XCEPT research / Research papers: Short papers documenting exploratory research and/or preparatory research (scoping papers, background papers) / Datasets: new data made available to different audiences. Broken down by type" to include datasets. | Charlie de Rivaz | 2023-09-29
135 | Output indicator 1.2 | Milestone 6 target decreased from 161 to 152 to reflect upgrading of several outputs from 1.2 to 1.1 for both C2 and C3. | Charlie de Rivaz | 2023-09-29
136 | Output indicator 1.2 | Milestone 7 target increased from 181 to 192 to reflect that C1 is continuing as part of the programme. Total number is increasing despite upgrading of 1.2s to 1.1s for several C2/C3 outputs. | Charlie de Rivaz | 2023-09-29
137 | Output indicator 1.3 | Milestone 6 target increased from 223 to 241 to reflect that C1 is continuing as part of the programme. Target for C2 has increased; while target for C3 has decreased by 5. | Charlie de Rivaz | 2023-09-29
138 | Output indicator 1.3 | Milestone 7 target increased from 273 to 323 to reflect that C1 is continuing as part of the programme. Target for C2 has increased; while target for C3 has decreased by 5. | Charlie de Rivaz | 2023-09-29
139 | Output indicator 2.1 | Wording changed from "Policy meetings. # meetings, briefing sessions and tailored presentations of research plans and/or research findings held with policy makers (and attendance figures)." to "Policy meetings. # meetings, briefing sessions and tailored presentations of research plans and/or research findings held with policy makers." to remove requirement to list attendance figures, as these are not a good measure of impact. | Charlie de Rivaz | 2023-09-29
140 | Output indicator 2.1 | Milestone 6 target increased from 227 to 324 to reflect that C1 is continuing as part of the programme and more ambitious targets across all components. | Charlie de Rivaz | 2023-09-29
141 | Output indicator 2.1 | Milestone 7 target increased from 263 to 409 to reflect that C1 is continuing as part of the programme and more ambitious targets across all components. | Charlie de Rivaz | 2023-09-29
142 | Output indicator 2.2 | Wording changed from "Public events. # public dissemination events held to present research findings to a broader audience including policymakers (and attendance figures)." to "Public events. # public events to present research to a broader audience (panels, presentation at conferences, major workshops, etc.). (Disaggregated by whether the event is organised by XCEPT or externally)" to include presentations at conferences in indicator. Language added to require disaggregation by who hosted the event, whether XCEPT or external, to ensure there is balance of XCEPT-hosted vs. exteernal events. | Charlie de Rivaz | 2023-09-29
143 | Output indicator 2.2 | Milestone 6 target increased from 38 to 77 to reflect that C1 is continuing as part of the programme and more ambitious targets across all components. | Charlie de Rivaz | 2023-09-29
144 | Output indicator 2.2 | Milestone 7 target increased from 65 to 107 to reflect that C1 is continuing as part of the programme and more ambitious targets across all components. | Charlie de Rivaz | 2023-09-29
145 | Output indicator 2.3 | Wording changed from "Online views and downloads. Aggregated # of page views and publication downloads. Social media reaches/impressions" to "Online views. Relative change in # of page views on the XCEPT website (and absolute number). / Social media. Relative change in # of engagements with XCEPT social media (and absolute number). / Newsletter. Relative change in # of XCEPT Newsletter subscribers (and absolute number)." to focus solely on XCEPT-controlled channels, to change to capturing relative change, and to introduce an indicator related to the XCEPT Newsletter. | Charlie de Rivaz | 2023-09-29
146 | Output indicator 2.3 | Milestone 6 target adjusted to relative change: Online views: 5% increase (from 48,000 views) / Social media: 6% increase (from 550 engagements) / Newsletter: 10% increase (from 735 subscribers). | Charlie de Rivaz | 2023-09-29
147 | Output indicator 2.3 | Milestone 7 target adjusted to relative change: Online views: 4% increase / Social media: 5% increase / Newsletter: 10% increase. | Charlie de Rivaz | 2023-09-29
148 | Output indicator 4.1 | Milestone 3 achieved target corrected from 1 to 4. This had not been corrected after the indicator wording was changed in FY22/23. | Charlie de Rivaz | 2023-09-29
149 | Output indicator 4.1 | Milestone 4 achieved target corrected from 3 to 8. This had not been corrected after the indicator wording was changed in FY22/23. | Charlie de Rivaz | 2023-09-29
150 | Output indicator 4.1 | Milestone 5 achieved target corrected from 21 to 26. This had not been corrected after the indicator wording was changed in FY22/23. | Charlie de Rivaz | 2023-09-29
151 | Output indicator 4.1 | Milestone 6 target increased from 20 to 48 to reflect more ambitious target for C2. | Charlie de Rivaz | 2023-09-29
152 | Output indicator 4.1 | Milestone 7 target increased from 26 to 68 to reflect more ambitious target for C2. | Charlie de Rivaz | 2023-09-29
153 | Output indicator 4.2 | Wording changed from "% of awards led by, and meaningfully contributed to by, Global South researchers/organisations, with contribution referring to at least one third of the value of the award." to "% of awards led by, or meaningfully contributed to by, Global South researchers/organisations" to simplify indicator and reflect new approach to measuring Global South participation and equitable partnerships. More detail included in Annex X. | Charlie de Rivaz | 2023-09-29
154 | Output indicator 3.1 | Milestone 6 target was set at 17 and milestone 7 target was set at 25 | Tabea Campbell Pauli | 2023-09-29
155 | Output indicator 3.2 | Milestone 6 target was set at 267 (40% female) and milestone 7 target was set at 367 (40% female) | Tabea Campbell Pauli | 2023-09-29
156 | Output indicator 3.3 | Added dimension "c) # new researchers from the Global South involved in X-Border research" | Tabea Campbell Pauli | 2023-09-29
157 | Output indicator 3.3 | Milestone 6 was set at: a) Total 130 (year-on-year increase in % of women) b) Total 45 (year on year increase in % of women) c) Total 15 (Min. 40%)" Milestone 7 was set at "C1: a) Total 150 (year-on-year increase in % of women) b) Total 52 (year on year increase in % of women) c) Total 15 (Min. 40%)" | Tabea Campbell Pauli | 2023-09-29
158 | Output indicator 3.4 | Wording changed from "Year on year increase in the average self-reported capacity of researchers from the Global South in core professional skills (Research Methods, Analysing and interpreting data, research ethics, writing for a policy audience, and public speaking)." to "Percentage of researchers from the Global South reporting an increase in capacity of core professional skills (Research Methods, Analysing and interpreting data, research ethics, writing for a policy audience, and public speaking)." | Tabea Campbell Pauli | 2023-09-29
159 | Output indicator 3.4 | Milestone 6 was set at 70% and milestone 7 was set at 75% | Tabea Campbell Pauli | 2023-09-29
160 | Outcome indicator 2 | Milestone 6 was set at 25 (10 for C1 and 15 for C2/C3) | Tabea Campbell Pauli | 2023-10-12
161 | Outcome indicator 2 | Milestone 7 was set at 60 (15 for C1 and 25 for C2/C3) | Tabea Campbell Pauli | 2023-10-12
162 | Milestone 6 | Added the figures achieved for Milestone 6 across all outcomes and outputs | Charlie de Rivaz | 2024-08-06
163 | Output indicators | Revised cumulative targets to correct mistake where 24/25 annual targets had been added to previous cumulative targets vs cumulatively achieved. | Mette Bastholm | 2024-09-01
164 | Output indicator 1.1 | Milestone 7 C2 target increased from 25 to 28, reflecting CH wrap-up | Mette Bastholm | 2024-09-01
165 | Output indicator 1.1 | Milestone 7 C3 target reduced from 10 to 7; 3 outputs pushed to next year due to IoTS delays | Mette Bastholm | 2024-09-01
166 | Output indicator 1.2 | Milestone 7 C3 target reduced from 8 to 4, due to change in counting practice (upon publication rather than submission) and IoTS delay | Mette Bastholm | 2024-09-01
167 | Output indicator 1.3 | Milestone 7 C3 target reduced from 25 to 15, due to change in counting practice (upon publication rather than submission) and IoTS delay | Mette Bastholm | 2024-09-01
168 | Output indicator 2.2 | Milestone 7 C2 target reduced from 20 to 17, primarily due to C2 contributions to cross-component events | Mette Bastholm | 2024-09-01
169 | Output indicator 2.2 | Milestone 7 C3 target increased from 9 to 14, reflecting more ambitious expectations for conference presentations | Mette Bastholm | 2024-09-01
170 | Output indicator 2.2 | Milestone 7 C0/cross-component target added | Mette Bastholm | 2024-09-01
171 | Output indicator 4.1 | Milestone 7 reduced from 20 to 10, reflecting decision to award only one large climate and conflict award and pause in planned borderlands call for proposals | Mette Bastholm | 2024-09-01
172 | Output indicator 4.2 | Milestone 7 reduced from 50% to 33%, similar to previous year, primarily reflecting decision to award only one large climate and conflict award | Mette Bastholm | 2024-09-01
172 | Output indicator 3.2 | Wording changed to "# times researchers from the Global South have benefited from knowledge and learning activities (disaggregated by region and gender)" | Tabea Campbell Pauli | 2024-09-01
173 | Output indicator 1.1 | New 1.1 section inserted to provide fresh baseline and targets for significantly redefined indicator. | Mette Bastholm | 2025-01-27
174 | Output indicator 1.2.1 | New indicator with fresh baseline and targets inserted, reflecting splitting of original indicator 1.1 outputs. | Mette Bastholm | 2025-01-27
175 | Output Indicator 1.2.2 | Original indicator 1.2 renamed, reflecting split of original indicator 1.1 and creation of indicator 1.2.1 | Mette Bastholm | 2025-01-27
176 | Milestone 7 | Added the figures achieved for Milestone 7 across all outcomes and outputs | Charlie de Rivaz | 2025-07-15
177 | Outcome indicator 2 | The achieved total for milestone 6 (March 2024) was corrected to 169 (from 172), and the achieved total for C1 to 115 (from 118), now reflecting the figure reported in the AR word doc. | Charlie de Rivaz | 2025-08-28
178 | Outcome and Outputs | The ahieved total for Milestone 8 (March 2026) for all Outcomes and Outputs was updated to reflect what was reported in the final version of the Annual Review 25/26. | Charlie de Rivaz | 2026-07-21
179 | Outcome and Outputs | The Milestone targets for Milestone 9 (February 2027) for all Outcomes and Outputs were updated in agreement with FCDO. It was agreed that there would be no new targets for Output 4 (Fund) as no new projects will be commissioned in the final year through the XRF. | Charlie de Rivaz | 2026-08-11
180 | Milestone targets | The due date for all Milestone 9 targets was updated from March 2027 to February 2027 to reflect the end date of the programme. | Charlie de Rivaz | 2026-08-11

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.