## Logical Framework - Dec 2021
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in target districts living below the national poverty line | Planned |  | 64.41 |  |  |  |  | 5% decrease from baseline |  | The % below the national poverty line accoring to the IHS4 are Phalombe: 83.2, Chikwawa 63.2, Balaka 61.3, and Mangochi 59.5. The weighted average for the four districts 64.41. The target has been set at a 5% decrease from the baseline at the end of the programme. Triangulation of data from similiar national programmes and survey shows that at most 5% decrease is attainable. The programme does not expect significant change by 2021 in the targeted population but will review data for IHS5 and replace the baseline with those figures for accuracy; therefore,no target has been set for Milestone 2 . Data for 2023 is expected from IHS6. It was agreed that the final reporting will fall outside the programme timeline. The programme will use any interim poverty data that becomes available to course correct.
Achieved
Source
NSO IHS data (available every 3 years). If WB Implement SWIFT we may be able to get more regular data points
| Impact Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) |  | Comments on Indicators and Targets
| Difference in difference comparison of targeted TAs and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) | Planned |  | - | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs |  | 2019 MVAC results will be used for baseline. The programme aims to maintain greater than or equal to IPC Baseline figures; the data will be used to make a difference in difference comparison betweeen PROSPER TA's and non PROSPER TA's to ascertain the effect of the programme. The programme will strive to have this percentage decrease beyond zero (into negative %).
|  | Achieved |  |  | -0.19 | -0.19 | -11.67
Source
MVAC annual assessments (annual - usulaly available in August)
OUTCOME | Outcome Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Strengthened resilience of the targeted poor and vulnerable households to withstand current and future weather and climate related shocks and stresses | Number of people whose resilience has been improved as a result of project support (ICF KPI 4)* *Using Resilience Index | Planned | 0 | From Resilience Index | Not yet measurable | Baselines and milestones established | 20% of households | 30% of households | 35% of households | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts. | Outcome Indicator 1 - Targets for number improving resilience will be set after baseline figures for the resilience index indicators are available. This is dependant on IFPRI baseline data which is expected between December 2019 and end of January 2020. Based on the baseline, the programme calculate anticipated numbers of households with improvemed resilience each year and set yearly milestones. Outcome Indicator 2 - GBP 7.28m is based on the incremental income attributable to PROSPER Markets work.This could be as a result of interventions for inputs, services or markets availed to participants. Estimates for cumulative increase in income from PROSPER INGO interventions (CSA, input fairs, livestock, irrigation)will be calculated from the % increase in yield sold as surplus. Targets for this will be calculated using IFPRI baseline results on current farmer yield in the targeted districts once baseline data is available. SU/SI are expected to increase yields and have sufficient surplus to sell. Outcome Indicator 3: The CARI index will be used: it is a composite indicator including Food Consumption Score, Food Expenditure Share and Livelihood Coping Strategies. The calculation provides a representative estimate of food insecurity within the targetted population. Targets are awaiting IFPRI and WFP - CSP baseline results. Outcome indicator 4: For the targets PROSPER will calculate the change in yield based on a difference in difference comparison between the control and treatment arms of the Impact Evaluation. Target set by Year 4 as 35% increase, with 10% gain in Year 1, Year 2 and Year 3, and 15% gain in Year 4.
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. Baseline = 11%(n)( PROSPER 2020 Annual survey) | Data not available
Source
Annual Programme Surveys
| Outcome Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Cumulative aggregate increase in income among poor people | Planned | 0 | IFPRI(Annual farm+ non farm income per capita)= MK 8,466 | Not yet measurable | Baselines and milestones established | GBP 3.52m | GBP 5.2m | GBP 7.28m *
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. GBP; 2,208,388 (Male;1,147,607, Female;1,060,780); Kadale 2020 assessment | GBP 6.42m
Source
Annual Programme Surveys
| Outcome Indicator 3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| % Households classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) - Using CARI index | Planned | 0 | IFPRI=55.1%, WFP=58.4% | Not yet measurable | - | 60% | 63% | 66%
|  | Achieved | 0 |  | Not yet measurable | WFP PDM survey=54% (Balaka, Chikwawa, Mangochi and Phalombe) | Data not available
Source
Annual Programme Surveys
| Outcome Indicator 4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Difference in difference comparison of change in yield of maize and other crops against the baseline figure in PROSPER and non-PROSPER target areas | Planned | 0 | (0%)IFPRI: Average Maize Yield=1,110 Kgs for treatment, 1311 Kgs for non PROSPER areas | Not yet measurable | 10% | 20% | 30% | 35%
|  | Achieved | 0 |  | Not yet measurable | PROSPER 2020 Annual survey = 760 kgs/ha for PROSPER treatment areas. 560 kg/ha median. | Data not available
Source
Annual Programme Surveys
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£)
| 90500000 |  | 0 | 0 |  |  |  | 90,5000,00
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Intensified and diversified agricultural production and improved nutrition for targeted vulnerable communities. | Percentage househods implementing Climate Smart Agriculture (CSA) practices | Planned | See tab | 0 | 42,525 individuals have received training in CSA | 21262.5 | 55% | 70% | 75% | Programme delivery can sustain current rate of progress with scale out of VSL and CSA technologies; cascade model of extension is effective; basic seed is available to enhance local seed supply for diverse crops, infromation is available from national meterological services that is relevant and of sufficient quality to disseminate. | Output 1.1 Milestones have been calculated as follows: The programme anticipates that for Milestone 1 60% of cohort 1 beneficiaries will implement at least 2 of the promoted pracrices, consecutively in YR 2 60% of Cohort 1 and 50% of Cohort 2 should see the benefits of using promoted GAPs, in Yr 3 75% of cohort 1 and 60% of cohort 2 should continue implementing 2 or more technologies and at the end of the programme, it is anticipated that 85% of cohort 1 and 75% of cohort 2 should be applying the technologies.These targets include HH also reached under the FFS where it is expected 50% of HH will implement CSA. Output Indictor 1.2: Targets based on numbers of farmers reached through the FFS model to improve extension services. Output Indictor 1.3: Indicator will capture both number of programme participants disaggregated by sex and hectares under production in the targeted irrigation schemes receiving PROSPER support. Collecting area under production and dissagregating it by sex allows for consideration of intra-household gender nuances of ownership, access and distribution of resources. Output Indictors 1.4 The indicators should be revisited when the baseline is set to ensure they are ambitious yet achievable. The target is set at 50% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence more than half of the population in PROSPER areas -- both men and women influencing the MAD for women in the household. Output Indicator 1.5: The target is set at 40% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence households in the PROSPER areas -- with more ground needing to be gained for young children's MAD. Output Indicator 1.6 These targets includes only SU beneficiaries. Milestone 1 is caculated based on 45% of SU (cohort 1), Milestone 2 ad 3 are 100% of SU (cohort 1 and cohort 2) while Milestone 4 is 55% of SU (cohort 2 only as cohort 1 subsidised inputs will phase out in Year 4)..
|  | Achieved | See tab |  | 78,253 (47,063F, 31,190M) individuals were trained in CSA practises | 37% (34,965hh - 12,587 FHH, 22,378 MHH) adopting CSA (6 or more practices), PROSPER 2020 Annual survey | Data not available - Annual Survey not undertaken due to ODA cuts | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Programme Annual Survey
| Output Indicator 1.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage farmers who report improvements in extension services received (by type of extension provider: public, community-based, private) | Planned | See tab | 49.5% of farmers receiving services | First cohort of FFS master training complete and FFS established in PROSPER areas Lead farmer training complete Private sector extension activities complete | 27000 | 47.87% | 51% - Milestone and targets need updating by April 2022 to take into account budget reduction | 53% - Milestone and targets need updating by April 2022 to take into account budget reduction
|  | Achieved | See tab |  | Completed | 30,240 The Annual Survey also found 49.5% of respondents reported receiving extension services. Of these, 64% reported improved extension services - which equates to a result of 32% when applied to whole population. So applying the 32% to the 94,500 farmers gives us 30,240 | Data not available - Annual Survey not undertaken due to ODA cuts
|  | Source |  |  | Source
Programme Annual Survey
| Output Indicator 1.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Hectares of farm land under irrigation (disaggregated by size of scheme, type of technology) | Planned | See tab | 0 | Agreement with PumpAid in place Feasibility assessments and planning for irrigation schemes in identified areas complete | Irrigation activities underway for winter cropping season. Baseline and milestones established. | 303.4 | 612.6 - Milestone and targets need updating by April 2022 to take into account budget reduction | 612.6 - Milestone and targets need updating by April 2022 to take into account budget reduction
|  | Achieved | See tab |  | Completed | Completed Baseline established at 12.6hectares | 379.94
|  | Source |  |  | Source
Programme Annual Survey
| Output Indicator 1.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of women between 15-49 reaching the minimum dietary diversity score | Planned | See tab | 0 | Mapping and reactivated SBCC district/TA and villlage structures Strengthen ANCCs and VNCC | Mapping and reactivated SBCC district/TA and villlage structures Strengthen ANCCs and VNCC | 38% | 43% - Milestone and targets need updating by April 2022 to take into account budget reduction | 50% - Milestone and targets need updating by April 2022 to take into account budget reduction and targets need updating before March 2022 to take into account budget reduction
|  | Achieved | See tab |  | Completed. Baseline established at 26% | Completed. WFP PDM survey = 27% | Data not available - Annual Survey not undertaken due to ODA cuts
Source
IFPRI/WFP CSP Baseline/SMART Surveys/UN Consortium October Survey
| Output Indicator 1.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage children 6-23 months consuming a minimum acceptable diet (MAD) | Planned | See tab | 0 | Nutrition sensitive social protection intervention designed Pregnant and lactating SCTP benficiaries targetted | Nutrition sensitive social protection intervention designed Pregnant and lactating SCTP benficiaries targetted | 10% | 15% - Milestone and targets need updating by April 2022 to take into account budget reduction | 20% - Milestone and targets need updating by April 2022 to take into account budget reduction
|  | Achieved | See tab |  | Completed. Baseline established at 3.5% | Completed. WFP PDM survey = 7.9% | Data not available - Annual Survey not undertaken due to ODA cuts
Source
IFPRI/WFP CSP Baseline/SMART Surveys/UN Consortium October Survey
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Number of farmers that received agricultural inputs to promote increased productivity during the reporting year - Annual target | Planned | See tab | 0 | 27337.5 | 27337.5 | 60750 | 60750 | 33412.5
|  | Achieved | See tab |  | 26,458 (16,984F, 9,474M) farmers | 26,458 (16,984F, 9,474M) farmers | 59,822 (34,691F; 25,131M) | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
[5 empty] | Source |  |  |  |  | RISK RATING
|  | Routine Programme Data Records | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 19000000 |  | 0 | 0 |  |  |  | 19000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 2 | Output Indicator 2.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Enhanced and inclusive access to the productive resources necessary to develop increased, secure and predictable incomes. | Number of market system actors that invest in pro-poor business models | Planned | See tab | 0 | 4 | 4 | 8 | 10 | 12 | New climate resilient business opportunities are viable in the project context; Market actors respond positively to incentives unlocked by PROSPER and are willing to absorb and act on new knowledge and business practices. Insurance products are afffordable and lead to producers being less risk averse in their decision making and increase investment | Output 2.1 : Targets are cumulative based on a total of 12 private sector stakeholders, including 4 in Year 1, with additional 4 in Year 2, 2 in Year 3, and 2 in Year 4. Output 2.2 Target of 94,500 is the total number of people reached by Kadale inputs and services interventions. This number is then reduced by 16.66666%* to discount the poor people who have accessed and used the inputs, but have not experienced income change as a result of this input access/use. Therefore, reducing the output target of 94,500 by 16.66666% we get Kadale's target on outcome level of 78,750 (then counting each individual as a head of a household to align with NGO targets for households). *The discount of 16.66666% is based on findings from MOST. Output 2.3 Target based on total population reached through VSL activities. This group is expected to benefit from at least one financial product the programme is offering through CUMO work.
|  | Achieved | See tab |  | 5 | 5 | 10 | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Quarterly reports from implementing agencies
| Output Indicator 2.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of poor people with increased access to productivity or income enhancing inputs or services /markets | Planned | See tab | 0 | 15000 | 15000 | 73000 | 83000 | 94500
|  | Achieved | See tab |  | 59,069 (24,708F, 34,361M) poor people | 63,802 (27,142F, 36,661M) poor people | 108,042 (59,988F, 57,054M) | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output indicator 2.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Number of households with access to financial services as a result of DFID support (DFID Global Indicator List) | Planned | See tab | 0 | 20250 | 20250 | 40500 | 60750 | 60750
|  | Achieved | See tab |  | 72,276 (21,663M, 50,613F) households | 72,276 (21,663M, 50,613F) households | 60670 | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 8500000 |  | 0 | 0 |  |  |  | 7500000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Vulnerable households and communities in targeted areas have reduced exposure to drought and floods | Number of people supported by DFID programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines | Planned Direct | See tab | 0 | 313240 | 313240 | 541930 | 541930 | 541930 | Cooperation with District Natural Resource teams, technical skills in catchment planning and irrigation scheme development are available, timely procurement of materials for implementation of works during appropriate seasons; institutions established by the programme for managing water and forest are functional and equitable. Humanitarian stakeholders willing to be coordinated; appropriate insitutitional arrangements can be established to enable rapid response. | Output 3.1 Indicator will track direct and indirect individuals receiving high and medium intensity support respectively. Targets for direct beneficiaries based on total number of individuals receiving direct support from PROSPER (123,166 HH * 4.4 individuals per HH). Year 1 targets based on Cohort 1 of 45% of SU/SO plus all HI in Year 1, adding Cohort 2 of 55% of SO/SU in Year 2 to reach 100% of SU/SO. Target maintained for four years. Indirect beneficiaries calculated based on population within the target PROSPER TA who will benefit from PROSPER activities and institutional capacity building at TA level but are not direct programme beneficaries. Data taken from NSO 2018 Census, including population totals and annual population growth rates. Output 3.2 Milestones calculated based on estimation of 200 ha per watershed, with 14 watersheds targeted within NGO programme - included forest areas and beneficiary fields (watershed delineation completed June 2019). INGO reaching a total of 2,800ha and UN 6,992 ha. Targets are based on the amount of land wherein restorative measures are planned based on resources allocated. Output 3.3 Target is expected to be 100% of the HH identified in need of assistance. Output 3.4 Target percentage expected to increase as more people are reached by shock responsive social protection. This indicator will be measured according to the use of government social protection systems where money is also channeled through government. This is only taking into consideration districts above 20% IPC and these targets are subject to be revised based on donor funding via government and the appropriateness of cash as a modality each year. This indicator covers the entire country, not just the four PROSPER districts because it is linked to the crisis modifier. Output 3.5 Milestones will be calculated based on the risk assesment and risk mapping to identify the population being supported by mitigation works
|  | Planned Indirect | See tab | 0 | 715961 | 715961 | 507303 | 527914 | 549119
|  | Achieved Direct | See tab |  | 355,039 direct (180,001F, 175,038M) | 355,039 direct (180,001F, 175,038M) | 435,960 (221,032F, 214,928M) | Milestone and targets need updating by April 2022 to take into account budget reduction | Milestone and targets need updating by April 2022 to take into account budget reduction
|  | Achieved Indirect | See tab |  | 516,648 indirect (261,941F, 254,707M) | 516,648 indirect (261,941F, 254,707M) | 647,320 (323,121F, 314,999M)
Source
Quarterly reports from implementing agencies
| Output Indicator 3.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved | Planned | See tab | 0 | 4400 | 4400 | 3400 | 6792 -Milestone and targets need updating by April 2022 to take into account budget reduction | 9792 - Milestone and targets need updating by April 2022 to take into account budget reduction
|  | Achieved | See tab |  | 5799 | 5799 | 14190
Source
Programme Data, delineation, hotspot mapping and follow up measurement (remote sensing and other tools)
| Output Indicator 3.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of people reached during the lean season response with cash transfers - Annual target | Planned | 150000 |  | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 500000 | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020) | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020)
|  | Achieved | 134400 |  | 155,000 people reached | 155,000 people reached | 488340
Source
MVAC
| Output Indicator 3.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Planned | See tab | 0 | 20% | 20% | 30% | 40% | 50%
|  | Achieved | See tab |  | 35.09% | 35.09% | 45.01%
Source
MVAC and UBR data
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Household(s) using EWS and climate information for floods and droughts to reduce risks to their lives and or property | Planned | See tab | 0 | 32516 | 32516 | 65032 | 97548 | 162579
|  | Achieved | See tab |  | 28,666HH (9,780M and 18,886F) | 28,666HH (9,780M and 18,886F) | Data not available - Annual Survey not undertaken due to ODA cuts
|  | Source | [7 empty] | RISK RATING
|  | Impact Survey , District Reports | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| £22,000,000 (+£20million crises modifer) |  | 0 | 0 |  |  |  | £22,000,000 (+£20million crises modifer) | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 4 | Output Indicator 4.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. | Number of districts with integrated coordination, monitoring and social accountability systems for social protection/resilience and emergency interventions | Planned | See tab | 0 | 2 | 2 | 4 | 4 | 4 | Combined efforts of partners on district capacity strengthening will have measurable effects Coordination of PROSPER partners will enable coordination across all actors and empower districts to gain greater capacity for integrated coordination Combined efforts of BRACC partners on district capacity strengthening will have measurable effects Shock-responsive social protection will have demonstrable positive outcomes from the 2019 season that will encourage systems investment in subsequent years | Output 5.1 Qualitative survey of district stakeholders on the existence and quality of integrated coordination, monitoring systems and social accountability systems for a) social protection b) resilience programmes and c) emergency interventions. Output 5.2 The process will involve collection of baseline data against all 8 targets of the Sendai framework, setting up of data collection systems and systematic collection of data to track progress in implementing the Sendai framework for DRR. This work will be linked to MGDS and National resilience strategy. Currently 9 districts in Malawi meet this criteria, but none are the four PROSPER districts. Output 5.3 Targets set to achieve beyond 4 PROSPER for lean-season : Key shock responsive features include : 1) preparednessof the service provider, 2) developed targeting procedure 3) scalable data management systems 4) scalable grievances mechanisms 5) processes informing or triggering a scale-up 6) clarification of funding channels 7) a developed communication strategy for a scale-up 8) a developed M&E Framework
|  | Achieved | See tab |  | 2 | 2 | 4
Source
Partner reports; District Coordinator reports
| Output Indicator 4.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of districts development plans that implement local disaster risk reduction strategies in line with the Sendai Framework for Disaster Risk Reduction 2015-2030 | Planned | See tab | 0 | - | 1 | 4 | 4 | 4
|  | Achieved | See tab |  | - | 1 | 2
Source
Reports submitted by the Government of Malawi to inform the accomplishment of Sendai Framework reporting
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Number of shock-responsive features of key social protection programmes put in place within the Malawi social protection programme (preparedness) | Planned | See tab | 1 | 2 | 2 | 4 | 5 | 6
|  | Achieved | See tab |  | 2 | 2 | 4
|  | Source | [7 empty] | RISK RATING
|  | MNSSP Reporting cycles, program reports, donors reports | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 3000000 |  | 0 | 0 |  |  |  | 3000000 | 100
INPUTS (HR) | DFID (FTEs)
3
OUTPUT 5 | Output Indicator 5.1 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22) |  | Assumptions
A strengthened and more shock sensitive social protection system | No districts where 50% of SCTP and PWP beneficiary households received their transfers through e-payments | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 1 | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | In 4 districts beneficiary households in at least one traditional authority have received their transfer through e-payments at least once | 7 districts |  | Existsing strong political will to reduce extremen poverty Funding for social protection programmes is available on time at central and district level. Public Works with the focus on watershed manage-ment continues. Line Ministries and donors remain interested in improv-ing coordination and harmonization in the area of social protection.
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Completed | Completed | Partially completed | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Analysis of payment data in SCT and PW MIS
| Output Indicator 5.2 |  | Inception (06/19) | Milestone 1 (03/20) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
| No districts where 70% of the total complaints submitted have been closed according to the guidelines. | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 0 | Magomero training course for extension workers is developed Outline of the Implementation Manual has been agreed Harmonized greivance and redress mechanisms developed | Maglomero training course for extension workers is developed Outline of the Implementation Manual has been agreed Harmonized greivance and redress mechanisms developed | Grievance and Redress mech-anism awareness and sensitization is undertaken in 2 districts and District officers are trained on complaint mecha-nism | 3
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Patrially completed | Patrially completed | Partially completed | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Analysis of GRM data
| Output Indicator 5.3 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
| No. of additional social protection beneficiary households (out of which at least 55 % are female-headed house-holds) twhich are purposively linked to complementary interventions (e.g. livelihood projects and nutri-tion-sensitive interventions) through tools developed by the programme. | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 0 | Development of a project implementation manual Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | Development of a project implementation manual Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | 2000 | 10000
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Partially completed | Partially completed | 2373 hh | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Analysis of SCT and PWP MIS and Unified Beneficiary Registry (UBR)
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
5 | No of micro–watersheds where watershed rehabilitation activities have been implemented by communities as part of Public Works activities and according to the implementation plan, e.g. Village Action Plan (VAP). | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 8 | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 12 | 24
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Partially completed | Partially completed | 12 | No longer appplicaple. Activity terminated early due to ODA cuts.
|  | Source | [7 empty] | RISK RATING
|  | Analysis of register for peo-ple regarding number of days and number of volunteers in the micro-catchments; Documentation of completed activities by community wa-tershed committees and comparison with the imple-mentation plan (e.g. VAP). | [7 empty] | HIGH
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| 5000000 |  | Germany £7,158,160 | 0 | EU :£2,681,431 |  |  | 14839591 | 34
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 6 | Output Indicator 6.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods | No of people with livelhood co-benefits from improved forest management | Planned | See tab | 0 | DCA agreed with USAID African Parks Baseline Assesment Report completed; and livelihoods projects in each park identified. | MCHF NR based value chains have been analysed and early stage innoavtors identified and selected | 5000 | 15000 | 20000 | Natural resource based entreprises can be identified and create sufficient incentives for improved forest management Co-management agreements can be agreed between private sector, communities and local authorities in targeted landscapes
|  | Achieved | See tab |  | Completed | Partially completed | 1802
Source
Quarterly reports from implementing agencies
| Output Indicator 6.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| No hectares of degraded landscapes under improved management | Planned | See tab | 0 | 0 | MCHF Target landscapes identify and delineated, restoration opportunites assessed | 0 | 3500 | 5000
|  | Achieved | See tab |  | 0 | Completed | Interim indicaotrs completed
Source
Quarterly reports from implementing agencies
| Output Indicator 6.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Tons of sustainable charcoal or alternative biomass energy produced | Planned | See tab | 0 | 0 | PEA on charcoal value chain completed | 0 | 0 | 4000
|  | Achieved | See tab |  | 0 | Partially completed | Interim indicaotrs completed
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output Indicator 6.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Planned | See tab | 0 | 0 | Finance and investment for FE and AE sectors mobilised through programme and non programme sources | 0 | TBD by March 2021 | $2million
|  | Achieved | See tab |  | 0 | Completed | Interim indicaotrs completed
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 5000000 |  | 0 | 0 |  |  |  | 5000000 | 100
INPUTS (HR) | DFID (FTEs)
2.5
OUTPUT 7 | Output Indicator 7.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions
More effective, coordinated and targeted, Government and donor investments | No. of politically responsive technical assistance workstreams developed and under active implementation using adaptive management principles | Planned | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) | 0 | Contract with KPM has been awarded Handover of evaluation activities complete Contract inception phase activities on track | Contract with KPM has been awarded Handover of evaluation activities complete Contract inception phase activities on track | National Green climate conference Adaptation and resilience project database and COP26 brief COP26 Communications activities | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021 | Opportunities for TA are identified; Sufficient senior level support from DFID and UK Diplomatic Representation is available to shape influential workstreams; There is enough political feedback and flexibility in contracting to enable the facility to be responsive to the most relevant opportunities.
|  | Achieved | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) |  | Completed | Completed | Completed | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
IFPRI project reports/ Final ToRs
| Output Indicator 7.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| # of days of technical assistance provided / average fee rate per day in £ | Planned | Impact Evaluation design complete and QA'd by EQUALs Baseline survey complete | 0 | Baseline survey analysis completed and outcome milestones agreed Resilience learning event completed Programme governance agreed and have met at least once | Baseline survey analysis completed and outcome milestones agreed Resilience learning event completed Programme governance agreed and have met at least once | Process evaluation Final Evaluation Policy briefs | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021
|  | Achieved | Impact Evaluation design complete and submitted to EQUALs Baseline survey not yet complete (expected August) |  | Completed | Completed | Completed | No longer appplicaple. Activity terminated early due to ODA cuts. | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
IFPRI project reports
IMPACT WEIGHTING (%) | Output Indicator 7.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
10 | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 10 (monthly maize market reports, rapid analytics, policy brief) | 12 | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | TBD once KPM implementation ammendment agreed - April 2021
|  | Achieved | 12 |  | 24 | 24 | 19
|  | Source | [7 empty] | RISK RATING
|  | IFPRI project reports | [7 empty] | HIGH
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 8000000 |  | 0 | 0 |  |  |  | 8000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
Note on I61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to check with WFP if the PDM survey will be done
Note on I107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to include new figures of number of people to be reached for 2022/2023
Note on J112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: maintain target?
Note on B132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Modify the indicator to Number of Districts with functional disaster information management system

## Change Frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Impact Indicator 1 | Midline milestones and targets added | Christina Connolly | 2018-04-17
2 | Impact indicator 2 | Midline milestones and targets added | Christina Connolly | 2018-04-17
3 | Outcome indicator 1 | Targets added. Reduction from 1.7million to 1.3million due to change in household size being used (target of 300,000households set out in the BC remains the same) | Christina Connolly | 2018-04-17
4 | Output 1 | Inception phase milestones added in separate tab | Christina Connolly | 2018-04-17
5 | Output 2 | Inception phase milestones added in separate tab | Christina Connolly | 2018-04-17
6 | Output 3 | Inception phase milestones added in separate tab | Christina Connolly | 2018-04-17
7 | Output 3 | Targets for lean season response from BC added into the logframe | Christina Connolly | 2018-04-17
8 | Output 4 | Inception phase milestones added Milestones and targets from GIZ proposal added into logframe. Suboutputs in GIZ proposal have been allocated across the 4 indicators for Milestone 1 | Christina Connolly | 2018-04-17
9 | Output 5 | Inception phase and year 1 milestones added | Christina Connolly | 2018-04-17
10 | Impact Indicator 2 | Percentage of the population in targeted districts falling within level three and above of the Integrated Food Security Phase Clarification (IPC) level 3 (stressed). | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
11 | Outcome Indicators 2-7 | These indicators were removed (see additions in ID 19-21) | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
12 | Output 1 | Split into two outputs: 1. Intensified and diversified agricultural production and improved nutrition for targeted vulnerable households 2. Enhanced and inclusive access to markets and the productive resources necessary to develop increased secure and predictable incomes for targeted households. New output indicators added under both outputs (see ID 22 to 41) | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
13 | Output 2 | Split into two outputs: 3. Vulnerable households and communities in targeted areas have reduced exposure to drought and floods 6. Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods - this is added as Output 6 in the lograme New output indicators added under both outputs (see ID 42 to 59) | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
14 | Output 3 | Wordiing changed to 4. Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. New output indicators added under both outputs | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
15 | Output 4 | Wording changed to 5. A strengthened and more shock sensitive social protection system No change to indicators | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
16 | Output 5 | Wording changed to 7. More effective, coordinated and targeted, Government and donor investments No change to indicators | Christina Connolly | 17/07/2019 (recommendation of Annual Review)
17 | Impact Indicator 1 | Source changes to IHS data. Milestones and targets adjusted to align with when IHS data is available, and what is we think is achievabe within programme lifetime | Christina Connolly | 2019-12-03
18 | Impact Indicator 2 | Wording changed slightly to 'Percentage difference between the population in targeted Traditional Authorities classified as being in Integrated Phase Classification Phase 3 (Crisis) or higher vs the population classified as being in IPC Phase 3 in non-targeted Traditional Authorities' to better capture difference between project and non-project TAs. Milestones added. | Christina Connolly | 2019-12-03
19 | Outcome indicator 2 | Added - Cumulative aggregate increase in income among poor people | Christina Connolly | 2019-12-03
20 | Outcome indicator 3 | Added - Household(s) classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) | Christina Connolly | 2019-12-03
21 | Outcome indicator 4 | Added - % change in yield of maize and other crops against the baseline figure in PROSPER and non-PROSPER target areas | Christina Connolly | 2019-12-03
22 | Output indicator 1.1 | Chanegd to Number of households implementing Climate Smart Agriculture (CSA) practices | Christina Connolly | 2019-12-03
23 | Output indicator 1.1 | Milestones and targets added | Christina Connolly | 2019-12-03
24 | Output indicator 1.2 | Changed to Number of farmers who report improvements in extension services received (by type of extension provider: public, community-based, private) | Christina Connolly | 2019-12-03
25 | Output indicator 1.2 | Milestones and targets added | Christina Connolly | 2019-12-03
26 | Output indicator 1.3 | Changed to Hectares of farm land under irrigation (disaggregated by size of scheme, type of technology) | Christina Connolly | 2019-12-03
27 | Output indicator 1.3 | Milestones and targets added | Christina Connolly | 2019-12-03
28 | Output indicator 1.4 | Changed to Percentage of women between 15-49 reaching the minimum dietary diversity score | Christina Connolly | 2019-12-03
29 | Output indicator 1.4 | Milestones and targets added | Christina Connolly | 2019-12-03
30 | Output indicator 1.5 | Changed to Percentage of children 6-23 months consuming a minimum acceptable diet (MAD) | Christina Connolly | 2019-12-03
31 | Output indicator 1.5 | Milestones and targets added | Christina Connolly | 2019-12-03
32 | Output indicator 1.6 | Changed to Number of farmers that received agricultural inputs to promote increased productivity during the reporting year | Christina Connolly | 2019-12-03
33 | Output indicator 1.6 | Milestones and targets added | Christina Connolly | 2019-12-03
34 | Output indicator 1.7 | Removed | Christina Connolly | 2019-12-03
35 | Output indicator 1.8 | Removed | Christina Connolly | 2019-12-03
36 | Output indicator 2.1 | Changed to Number of market system actors that invest in pro-poor business models | Christina Connolly | 2019-12-03
37 | Output indicator 2.1 | Milestones and targets added | Christina Connolly | 2019-12-03
38 | Output indicator 2.2 | Changed to Number of poor people with increased access to productivity or income enhancing inputs or services /markets | Christina Connolly | 2019-12-03
39 | Output indicator 2.2 | Milestones and targets added | Christina Connolly | 2019-12-03
40 | Output indicator 2.3 | Changed to Number of households with access to financial services as a result of DFID support (DFID Global Indicator List) | Christina Connolly | 2019-12-03
41 | Output indicator 2.3 | Milestones and targets added | Christina Connolly | 2019-12-03
42 | Output indicator 2.4 | Removed | Christina Connolly | 2019-12-03
43 | Output indicator 2.5 | Removed | Christina Connolly | 2019-12-03
44 | Output indicator 2.6 | Removed | Christina Connolly | 2019-12-03
45 | Output indicator 2.7 | Removed | Christina Connolly | 2019-12-03
46 | Output indicator 3.1 | Changed to Number of people supported by DFID programmes to cope with the effects of climate change | Christina Connolly | 2019-12-05
47 | Output indicator 3.1 | Milestones and targets added | Christina Connolly | 2019-12-05
48 | Output indicator 3.2 | Changed to Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved. | Christina Connolly | 2019-12-05
49 | Output indicator 3.2 | Milestones and targets added | Christina Connolly | 2019-12-05
50 | Output indicator 3.3 | Changed to Number of people reached during the lean season response with cash transfers | Christina Connolly | 2019-12-05
51 | Output indicator 3.3 | Milestones and targets added | Christina Connolly | 2019-12-05
52 | Output indicator 3.4 | Changed to Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Christina Connolly | 2019-12-05
53 | Output indicator 3.4 | Milestones and targets added | Christina Connolly | 2019-12-05
54 | Output indicator 3.5 | Changed to Percentage of targetted population with improved access to EWS | Christina Connolly | 2019-12-05
55 | Output indicator 3.5 | Milestones and targets added | Christina Connolly | 2019-12-05
56 | Output indicator 6.1 | New indicator, milestones and targets added No of people with livelhood co-benefits from improved forest management | Christina Connolly | 2019-12-12
57 | Output indicator 6.2 | New indicator, targets added No hectares of degraded landscapes under improved management | Christina Connolly | 2019-12-12
58 | Output indicator 6.3 | New indicator, targets added Tons of sustainable charcoal produced
59 | Output indicator 6.4 | New indicator, and targets added Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Christina Connolly | 2019-12-12
60 | Output indicator 7.1 | Milestone 1 added | Christina Connolly | 2019-12-12
61 | Output 5 | Additional milestones added for 2020 | Christina Connolly | 2019-12-23
62 | Output indicator 5.2 | Wording changed very slightly to 'No districts where 70% of the total complaints submitted have been closed according to the guidelines'. | Christina Connolly | 2020-01-13
62 | Output indicator 5.4 | Wording simplified to 'No of micro–watersheds where watershed rehabilitation activities have been implemented by communities as part of Public Works activities and according to the implementation plan, e.g. Village Action Plan (VAP)' | Christina Connolly | 2020-01-13
63 | Outcome Indicators 2-7 | Baselines and milestones updated | Christina Connolly | 2020-06-22
64 | 03/2020 Milestones | Updated with achieved results | Christina Connolly | 2020-06-22
65 | Outcome Indicator 1 | Milestone 8/2020 complete - Baselines and milestones added - final target reduced from 800,000 to XX (refelction of more rigours resilience thresholds and following the ICF KPI4 methodology) | Christina Connolly | 2020-12-30
66 | Outcome Indicator 2 | Milestone 8/2020 complete - Baselines and milestones added - final target increased from GBP 6.5million to GBP 7.28million | Christina Connolly | 2020-12-30
67 | Outcome Indicator 3 | 8/2020 milestone added | Christina Connolly | 2020-12-30
68 | Outcome Indicator 4 | 8/2020 milestone added | Christina Connolly | 2020-12-30
69 | Output indicator 1.1 | 8/2020 milestone added | Christina Connolly | 2020-12-30
70 | Output indicator 1.1 | Milestones and targets changed to % of total households rathen than number of households as being measured from annual survey | Christina Connolly | 2020-12-30
71 | Output indicator 1.2 | 8/2020 milestone added | Christina Connolly | 2020-12-30
72 | Output indicator 1.2 | Milestones and targets changed to % of total households rathen than number of individuals as being measured from annual survey | Christina Connolly | 2020-12-30
73 | Output indicator 1.3 | 8/2020 milestone added - Baselines and milestones added - final target reduced from 21,000 to 612.60 | Christina Connolly | 2020-12-30
74 | Output indicator 1.4 | 8/2020 milestone added | Christina Connolly | 2020-12-30
75 | Output indicator 1.4 | Milestones and targets reduced from 27,32,40% to 10,15 and 20% to reflect updated national statistics and reality of what is achievable | Christina Connolly | 2020-12-30
76 | Output indicator 2.2 | 8/2020 milestone updated based on improved data | Christina Connolly | 2020-12-30
77 | Output indicator 2.2 | 2021 and 2022 updated. | Christina Connolly | 2020-12-30
78 | Output indicator 3.2 | 2021 milestone reduced from 5400 to 3400 hecatares due to Covid related budget constraints reducing these activities | Christina Connolly | 2020-12-30
79 | Output indicators 6.1-6.4 | 8/2020 milestone added | Christina Connolly | 2020-12-30
80 | Output 5 | All indicators updated with achieved results for the 8/21 milestone | Christina Connolly | 17/12/2021
81 | Output 5 | All milestones for 2022 and beyond greyed out as activity termintated | Christina Connolly | 17/12/2021
82 | Output 6 | All indicators updated with milestones (as agreed in Annual work plan and monitoring plan) and the achieved results for the 8/21 milestone | Christina Connolly | 17/12/2021
83 | Indicator 6.3 | Indicator working changed to 'Tons of sustainable charcoal or alternative biomass energy produced' to better align to MCHF indicator | Christina Connolly | 17/12/2021
84 | Indicator 7.1 and 7.2 | Indicator milestones and results updated | Christina Connolly | 17/12/2021
85 | Output indicator 1.1 and 1.2 | Changed to % rather than actual numbers as described in Annual Review of Jan 2021 | Christina Connolly | 17/12/2021
86 | Output 1 indicators 1.1-1.6 | All indicators updated with achieved results for the 8/21 milestone | Christina Connolly | 17/12/2021
87 | Output Indicators 2.1-2.3 | All indicators updated with achieved results for the 8/21 milestone | Christina Connolly | 17/12/2021
88 | Output Indicators 2.1-2.3 | All milestones for 2022 and beyond greyed out as activity termintated | Christina Connolly | 17/12/2021
89 | Output Indicators 3.1-3.5 | All indicators updated with achieved results for the 8/21 milestone | Christina Connolly | 17/12/2021
90 | Output Indicators 4.1-4.3 | All indicators updated with achieved results for the 8/21 milestone | Christina Connolly | 17/12/2021
92 | Impact indicator 2 | Updated with achieved results | Christina Connolly | 17/12/2021
93 | Outcome indicators | Updated with achieved results where data available. | Christina Connolly | 17/12/2021
94 | Outcome indicator 1 | The method and means of verification changed, it will follow WFP's methodology | Giles Henley | 2022-11-10
95 | Outcome indicator 2 | Removed and replaced with: Percentage of women between 15-49 reaching the minimum dietary diversity score | Giles Henley | 2022-11-10
96 | Outcome Indicator 2 | Milestones and target added | Giles Henley | 2022-11-10
| Outcome Indicator 4 | Indicator kept but it will be reported by FAO and WFP rather than through BRACC Hub Annual Survey | Giles Henley | 2022-11-10
97 | Outcome Indicator 5 | Upgraded from output indicator: Percentage of children 6-23 months consuming a minimum acceptable diet (MAD) | Giles Henley | 2022-11-10
98 | Outcome Indicator 5 | Milestones and target added | Giles Henley | 2022-11-10
99 | Output Indicator 1.1 | Reduced 2022 and 2023 targets to 50% | Giles Henley | 2022-11-10
100 | Output Indicator 1.3 | Target raised from 102 to 117 for 2023 | Giles Henley | 2022-11-10
101 | Output Indicator 1.4 | Indicator removed at output level and upgraded to outcome level | Giles Henley | 2022-11-10
102 | Output Indicator 1.6 | Indicator removed | Giles Henley | 2022-11-10
103 | Output Indicator 1.7 | Indicator removed | Giles Henley | 2022-11-10
104 | Output Indicator 2.1 | Indicator removed | Giles Henley | 2022-11-10
105 | Output Indicator 2.2 | Indicator removed | Giles Henley | 2022-11-10
106 | Output indicator 3.1 | The number of direct beneficiaries has reduced (from 541930 to 313429) while indirect has risen (from 516,648 to 759,852). | Giles Henley | 2022-11-10
107 | Output Indicator 3.2 | Target raised from 9,792 to 12,264 hectares | Giles Henley | 2022-11-10
108 | Output Indicator 3.5 | Indicator removed | Giles Henley | 2022-11-10
109 | Output Indicator 3.9 | Indicator removed | Giles Henley | 2022-11-10
107 | Output Indicator 4.2 | Indicator changed to "Number of Districts with functional Disaster Information Management System" | Giles Henley | 2022-11-10
108 | Output Indicator 5.1-5.4 | Removed due to ODA cuts | Giles Henley | 2022-10-04
109 | Output Indicator 7.1-7.2 | Removed due to ODA cuts | Giles Henley | 2022-10-04
110 | Outcome Indicator 1 | Method and means of verification changed. To follow WFP's methodology | Giles Henley | 2023-04-01
111 | Outcome Indicator 2 | Original Indicator removed. Replaced with: Percentage of women between 15-49 reaching the minimum dietary diversity score | Giles Henley | 2023-04-01
112 | Outcome Indicator 4 | Indicator kept but this is now reported upon by FAO and WFP for the farmers they support, rather than through BRACC Hub Annual Survey | Giles Henley | 2023-04-01
113 | Outcome Indicator 5 | Upgraded the outcome from output indicator: Percentage of children 6-23 months consuming a minimum acceptable diet (MAD) | Giles Henley | 2023-04-01
114 | Output Indicator 1.1 | 2022 and 2023 targets increased from 50% to 70% and 75% | Giles Henley | 2023-04-01
115 | Output Indicator 1.2 | Source changed to WFP/FAO annual survey and programme reports | Giles Henley | 2023-04-01
116 | Output Indicator 1.3 | Target for 2023 changed to 117 from 102 | Giles Henley | 2023-04-01
117 | Output Indicator 1.4 | Output removed at output level and upgraded to an outcome indicator | Giles Henley | 2023-04-01
118 | Output Indicator 1.5 | Output removed at output level and upgraded to an outcome indicator | Giles Henley | 2023-04-01
119 | Output indicator 2.1 | Removed. Previously reported by INGO | Giles Henley | 2023-04-01
120 | Output indicator 2.2 | Removed. Previously reported by INGO |  | 2023-04-01
121 | Output indicator 2.3 | Added new indicators. Removed opening of back accounts for lean season support as an indicator |  | 2023-04-01
122 | Output indicator 3.1 | Milestone revised to: 313,429 (Direct beneficiaries); 759,852 (Indirect beneficiaries) |  | 2023-04-01
123 | Output indicator 3.6 | New Indicator, targets added for 2023 Number of people with access to a flood evacuation centre during a flood occurrence | Giles Henley | 2023-04-01
124 | Output indicator 4.2 | Changed to Number of Districts with functional Disaster Information Management System
125 | Outcome Indicator 2 | Indicator removed since it was reported by UN Partners | Giles Henley | 2024-10-09
126 | Outcome Indicator 4 | Indicator removed since it was reported by UN Partners | Giles Henley | 2024-10-09
127 | Outcome Indicator 5 | Indicator removed since it was reported by UN Partners | Giles Henley | 2024-10-09
128 | Outcome Indicator 6 | Outcome Indicator added | Giles Henley | 2024-10-09
129 | Output Indicator 1.1 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
130 | Output Indicator 1.2 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
131 | Output Indicator 1.3 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
132 | Output Indicator 2.1 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
133 | Output 3.1 | Indicator removed due to closure of MCHF by USAID | Giles Henley | 2025-05-06
134 | Output Indicator 3.2 | Indicator removed due to closure of MCHF by USAID | Giles Henley | 2025-05-06
135 | Output Indicator 3.3 | Indicator removed due to closure of MCHF by USAID | Giles Henley | 2025-05-06
136 | Output Indicator 3.5 | Indicator removed due to closure of MCHF by USAID | Giles Henley | 2025-05-06
137 | Output Indicator 3.6 | Indicator removed since PROSPER has ended | Giles Henley | 2025-05-06
138 | Output Indicator 3.7 | Indicator removed due to closure of MCHF by USAID | Giles Henley | 2024-10-09
| Output Indicator 3.8 | Continued indicator from MDTF | Giles Henley
139 | Output Indicator 4.1 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
140 | Output Indicator 4.2 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
141 | Output Indicator 4.3 | Indicator removed since PROSPER has ended | Giles Henley | 2024-10-09
142 | Output indicator 5.5 | Output Indicator added during MCHF extension period | Giles Henley | 2024-10-09
143 | Output Indicator 5.7 | Output Indicator added during MCHF extension period | Giles Henley | 2024-10-09
144 | Output Indicator 6.2 | Added new indicator from PFP | Giles Henley
FEB 2025 (NEW INDICATORS)
145 | Output Indicator 1.6 | New indicator from PREPARE project | Giles Henley | 2025-02-01
146 | Output Indicator 1.7 | New indicator from PREPARE project | Giles Henley | 2025-02-02
147 | Output Indicator 1.8 | New Indicator from PREPARE Project | Giles Henley | 2025-02-03
148 | Output Indicator 1.9 | New Indicator from El Nino Project | Giles Henley | 2025-02-04
149 | Output Indicator 1.10 | New Indicator from El Nino Project | Giles Henley | 2025-02-05
2025-12-01
150 | Outcome 1a | Changed the outcome from number of people to percentage | Giles Henley | 2025-12-22
151 | Outcome 1b | Included the new outcome indicator from the NGO activities | Giles Henley | 2025-12-05
152 | Outcome 3 | Added Public Works Programme beneficiary to the indicator | Giles Henley
153 | Output 1 Indicator Name | Rephrased the output and added "have great capacity to recover from floods and droughts (this includes cash transfer and EWS) " and also specified who is contributing to this output | Giles Henley | 2025-12-05
154 | Output 1.1 | Changed the target for 12/25 from 4,950,607 to 334,104 because we have removed the cash transfer and public works beneficiaries under MDTF which could not be contributed to FCDO funding alone since it is a trust fund. Instead we have included the NGO and WFP targets only | Giles Henley | 2026-12-09
155 | Output 1.2 | Specified who is contributing to the output | Giles Henley | 2025-12-09
156 | Output 1.4b | Indicator removed from Output 2 to output 1.4b | Giles Henley | 2025-12-09
157 | Output 1.5 | Added new target for 2026 from WFP | Giles Henley | 2025-12-09
158 | Output 1.9 | Removed as it is not reported under PREPARE or current WFP Programme | Giles Henley | 2025-12-09
159 | Output 1.11 | Indicator removed from Output 3.8 to Output 1.11 | Giles Henley | 2025-12-09
160 | Output 1.12-1.14 | New output indicators added from the NGO consortium work | Giles Henley | 2025-12-09
161 | Output 2.1 | Output indicator added from the NGO logframe | Giles Henley | 2025-12-09
162 | Output 2.2 | Output indicator added from WFP component | Giles Henley | 2025-12-09
163 | Output 3.1-3.9 | Removed the indicator since MCHF ended | Giles Henley | 2025-12-11
164 | Output 4.3 | Added new indicator and target for Tetra tech

## Logical Framework-Dec 2024
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumptions | Comments on Indicators and Targets
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in target districts living below the national poverty line | Planned |  | 64.41 |  |  |  |  | 2.5% decrease | 2.5% decrease | 3.0% decrease | 4.0% decrease |  | The % below the national poverty line accoring to the IHS4 are Phalombe: 83.2, Chikwawa 63.2, Balaka 61.3, and Mangochi 59.5. The weighted average for the four districts 64.41. The target has been set at a 5% decrease from the baseline at the end of the programme. Triangulation of data from similiar national programmes and survey shows that at most 5% decrease is attainable. The programme does not expect significant change by 2021 in the targeted population but will review data for IHS5 and replace the baseline with those figures for accuracy; therefore,no target has been set for Milestone 2 . Data for 2023 is expected from IHS6. It was agreed that the final reporting will fall outside the programme timeline. The programme will use any interim poverty data that becomes available to course correct.
Achieved
Source
NSO IHS data (available every 3 years). If WB Implement SWIFT we may be able to get more regular data points
| Impact Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets
| Difference in difference comparison of targeted TAs and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) | Planned |  | - | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs |  | 2019 MVAC results will be used for baseline. The programme aims to maintain greater than or equal to IPC Baseline figures; the data will be used to make a difference in difference comparison betweeen PROSPER TA's and non PROSPER TA's to ascertain the effect of the programme. The programme will strive to have this percentage decrease beyond zero (into negative %). he aggregate is an increase of the total caseload of households classified as being in IPC phase 3 and this is as a result of the impacts of the tropical storms Freddy, Ana and Gombe including, late onset of rains and dry spells which resulted in significant drop in crop losses in targetted TAs. It was also driven by high inflatio, high global food and fuel prices and the devaluation of the Malawi kwacha in May 2022. The increase means that more people were classifies as being food insecure in PROSPER targeted TAs.
|  | Achieved |  |  | -0.19 | -0.19 | -11.67 | -84% | 28.20 percentage higher in PROSPER TAs than non-PROSPER Tas | -28.2%
Source
MVAC annual assessments (annual - usulaly available in August)
OUTCOME | Outcome Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumptions | Comments on Indicators and Targets
Strengthened resilience of the targeted poor and vulnerable households to withstand current and future weather and climate related shocks and stresses | Number of people whose resilience has been improved as a result of project support (ICF KPI 4)* *Using WFP Methodology | Planned | 0 | From Resilience Index | Not yet measurable | Baselines and milestones established | 20% of households | 30% of households | 35% of households | 35% households | 90% | 100% | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts. | Outcome Indicator 1 - Targets for number improving resilience will be set after baseline figures for the resilience index indicators are available. This is dependant on IFPRI baseline data which is expected between December 2019 and end of January 2020. Based on the baseline, the programme calculate anticipated numbers of households with improvemed resilience each year and set yearly milestones. Outcome Indicator 2 - GBP 7.28m is based on the incremental income attributable to PROSPER Markets work.This could be as a result of interventions for inputs, services or markets availed to participants. Estimates for cumulative increase in income from PROSPER INGO interventions (CSA, input fairs, livestock, irrigation)will be calculated from the % increase in yield sold as surplus. Targets for this will be calculated using IFPRI baseline results on current farmer yield in the targeted districts once baseline data is available. SU/SI are expected to increase yields and have sufficient surplus to sell. Outcome Indicator 3: The CARI index will be used: it is a composite indicator including Food Consumption Score, Food Expenditure Share and Livelihood Coping Strategies. The calculation provides a representative estimate of food insecurity within the targetted population. Targets are awaiting IFPRI and WFP - CSP baseline results. Outcome indicator 4: For the targets PROSPER will calculate the change in yield based on a difference in difference comparison between the control and treatment arms of the Impact Evaluation. Target set by Year 4 as 35% increase, with 10% gain in Year 1, Year 2 and Year 3, and 15% gain in Year 4.
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. Baseline = 11%(n)( PROSPER 2020 Annual survey) | 25% | 25% | 72.8% (Medium CRCS-55.2%, and High CRCS-17.6%) | 81% (Medium CRCS-58%, and High CRCS-23%)
Source
WFP's survey-using their methodology
| Outcome Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (10/20) | Milestone 3 (10/21) | Milestone 4 (10/22) | Target (10/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Percentage of women between 15-49 reaching the minimum dietary diversity score | Planned | 0 | WFP baseline=26% |  | 26% | 38% | 43% | 50% | 50%
|  | Achieved | 0 |  |  | (29%, WFP PDM Survey) | (27%, WFP PDM Survey) **Same figure as October 2022, as this is when the annual survey was completed | 15% | 36.4% | 37%
Source
WFP CSP Baseline/SMART Surveys
| Outcome Indicator 3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| % Households classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) - Using CARI index | Planned | 0 | IFPRI=55.1%, WFP=58.4% | Not yet measurable | - | 60% | 63% | 66% | 66% | 68% | 70%
|  | Achieved | 0 |  | Not yet measurable | WFP PDM survey=54% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=78% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=62% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=53% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=39%
Source
UN Survey, WFP CSP Baseline
| Outcome Indicator 4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Difference in difference comparison of change in yield of maize and other crops against the baseline figure in PROSPER and non-PROSPER target areas | Planned | 0 | (0%)IFPRI: Average Maize Yield=1,110 Kgs for treatment, 1311 Kgs for non PROSPER areas | Not yet measurable | 10% | 20% | 30% | 35% | 35%
|  | Achieved | 0 |  | Not yet measurable | PROSPER 2020 Annual survey = 760 kgs/ha for PROSPER treatment areas. 560 kg/ha median. | 949kg/ha Average Maize Yield for PROSPER treatment areas | 36% (a measure of households reporting over 200kg of maize harvested, which was 36%) | 24% (a measure of households reporting over 200kg of maize harvested, which was 24%) | 23% (a measure of households reporting over 200kg of maize harvested, which was 23%)
Source
FAO and WFP Surveys
| Outcome Indicator 5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Percentage of children 6-23 months consuming a minimum acceptable diet (MAD) | Planned |  | WFP baseline=3.5% |  | 5% | 10% | 15% | 20% | 20%
|  | Achieved |  | N/A |  | (7.9% WFP PDM Survey) | (4.5% WFP PDM Survey) | (3.6% WFP PDM Survey) | 5.6% | 5.6% (WFP PDM Survey)
Source
IFPRI/WFP CSP Baseline/Smart Surveys/UN Consortium Survey
| Outcome Indicator 6 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (12/24) | Milestone (12/25) | Milestone (06/26)
| Proportion of Social Cash Transfers project beneficiary households with an improved food consumption score (Percentage) | Planned |  | 51.6 |  |  |  |  | 47.9 | 47.9 | 60 | 75
|  | Achieved | [6 empty] | 41.9 | 65.4
Source
INPUTS (£) |  | World Bank Baseline, Midterm and Endline Survey
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumption | Comments on Indicators and Targets
Intensified and diversified agricultural production and improved nutrition for targeted vulnerable communities. | Percentage households implementing Climate Smart Agriculture (CSA) practices | Planned | See tab | 0 | 42,525 individuals have received training in CSA | 21262.5 | 55% | 50% | 75% | 75% |  |  | Programme delivery can sustain current rate of progress with scale out of VSL and CSA technologies; cascade model of extension is effective; basic seed is available to enhance local seed supply for diverse crops, infromation is available from national meterological services that is relevant and of sufficient quality to disseminate. | Output 1.1 Milestones have been calculated as follows: The programme anticipates that for Milestone 1 60% of cohort 1 beneficiaries will implement at least 2 of the promoted pracrices, consecutively in YR 2 60% of Cohort 1 and 50% of Cohort 2 should see the benefits of using promoted GAPs, in Yr 3 75% of cohort 1 and 60% of cohort 2 should continue implementing 2 or more technologies and at the end of the programme, it is anticipated that 85% of cohort 1 and 75% of cohort 2 should be applying the technologies.These targets include HH also reached under the FFS where it is expected 50% of HH will implement CSA. Indicator to be measured based on 3 out of these factors: 1. Practice of Integrated Pest Management (IPM) 2. Inter-cropping with legumes, in maize fields. 3. Planting perennials and agroforestry species in crop fields. 4. Planting adaptive crop varieties (early maturing, drought tolerant.) 5. Conservation Agriculture (minimum tillage, mulching and use of herbicides). 6. Use improved storage facilities for the harvest. 7. Manure collection and production from livestock. 8. Use of disease resistant breeds under livestock. 9. Engaging in irrigation crop production. Output Indictor 1.2: Targets based on numbers of farmers reached through the FFS model to improve extension services. Output Indictor 1.3: Indicator will capture both number of programme participants disaggregated by sex and hectares under production in the targeted irrigation schemes receiving PROSPER support. Collecting area under production and dissagregating it by sex allows for consideration of intra-household gender nuances of ownership, access and distribution of resources. Output Indictors 1.4 The indicators should be revisited when the baseline is set to ensure they are ambitious yet achievable. The target is set at 50% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence more than half of the population in PROSPER areas -- both men and women influencing the MAD for women in the household. Output Indicator 1.5: The target is set at 40% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence households in the PROSPER areas -- with more ground needing to be gained for young children's MAD. Output Indicator 1.6 These targets includes only SU beneficiaries. Milestone 1 is caculated based on 45% of SU (cohort 1), Milestone 2 ad 3 are 100% of SU (cohort 1 and cohort 2) while Milestone 4 is 55% of SU (cohort 2 only as cohort 1 subsidised inputs will phase out in Year 4)..
|  | Achieved | See tab |  | 78,253 (47,063F, 31,190M) individuals were trained in CSA practises | 37% (34,965hh - 12,587 FHH, 22,378 MHH) adopting CSA (6 or more practices), PROSPER 2020 Annual survey | Data not available - Annual Survey not undertaken due to ODA cuts | 74.6% adopted CSA (3 or more practices) | 72% adopted CSA (3 or more practices) | 74%
Source
WFP/FAO annual survey
| Output Indicator 1.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Percentage farmers who report improvements in extension services received (by type of extension provider: public, community-based, private) | Planned | See tab | 49.5% of farmers receiving services | First cohort of FFS master training complete and FFS established in PROSPER areas Lead farmer training complete Private sector extension activities complete | 27000 | 47.87% | 51% | 90% | 90%
|  | Achieved | See tab |  | Completed | 30,240 The Annual Survey also found 49.5% of respondents reported receiving extension services. Of these, 64% reported improved extension services - which equates to a result of 32% when applied to whole population. So applying the 32% to the 94,500 farmers gives us 30,240 | Data not available - Annual Survey not undertaken due to ODA cuts | 89% Annual assessment survey findings, Dec 2022. As PROSPER has currently trained 2,404 community-based facilitators (CBFs) through farmers field schools, the outreach in terms of improved extension services has increased in the project locations. These CBFs are directly providing extension support to approximately 70,000 farmers | 92.8% With the provision of mobility support through bicycles and also provision of training materials to Community Based Facilitators (CBFs) in all project locations, the programme maximized the reach to follower farmers with extension services. FAO managed to train over 2,400 CBF who are supporting in the provision of extension services under the supervision of the 60 Master Trainers (MTs) also trained under the programme | 74.1%
|  | Source |  |  | Source
Partner's survey (WFP/FAO)
| Output Indicator 1.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Hectares of farm land under irrigation (disaggregated by size of scheme, type of technology) | Planned | See tab | 0 | Agreement with PumpAid in place Feasibility assessments and planning for irrigation schemes in identified areas complete | Irrigation activities underway for winter cropping season. Baseline and milestones established. | 303.4 | 102 | 117 | 117
|  | Achieved | See tab |  | Completed | Completed Baseline established at 12.6hectares | 379.94 | 52 | 205.81 | 229.8HA (52.0HA WFP; 177.8ha FAO)
|  | Source |  |  | Source
Programme Annual Survey
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 19000000 |  | 0 | 0 |  |  |  | 19000000 | 100
INPUTS (HR) | FCDO (FTEs)
3.5
IMPACT WEIGHTING (%)
Output 2 | Output indicator 2.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
Enhanced and inclusive access to the productive resources necessary to develop increased, secure and predictable incomes. | Number of households/individuals with access to financial services as a result of FCDO support (FCDO Global Indicator List) | Planned | See tab | 0 | 20250 | 20250 | 40500 | 20000 | 30700 | 30700
|  | Achieved | See tab |  | 72,276 (21,663M, 50,613F) households | 72,276 (21,663M, 50,613F) households | 60670 | 25,867 (16,520F, 9,347M) | 31,135 (26,391F, 3,744M) | 31,135 (26,391F; 3,744M)
|  | Source | [10 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [10 empty] | MEDIUM
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 8500000 |  | 0 | 0 |  |  |  | 7500000 | 100
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumption | Comments on Indicators and Targets
Vulnerable households and communities in targeted areas have reduced exposure to drought and floods | Number of people supported by FCDO programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines | Planned Direct | See tab | 0 | 313240 | 313240 | 541930 | 541930 | 313429 | 313429 |  |  | Cooperation with District Natural Resource teams, technical skills in catchment planning and irrigation scheme development are available, timely procurement of materials for implementation of works during appropriate seasons; institutions established by the programme for managing water and forest are functional and equitable. Humanitarian stakeholders willing to be coordinated; appropriate insitutitional arrangements can be established to enable rapid response. | Output 3.1 Indicator will track direct and indirect individuals receiving high and medium intensity support respectively. Targets for direct beneficiaries based on total number of individuals receiving direct support from PROSPER (123,166 HH * 4.4 individuals per HH). Year 1 targets based on Cohort 1 of 45% of SU/SO plus all HI in Year 1, adding Cohort 2 of 55% of SO/SU in Year 2 to reach 100% of SU/SO. Target maintained for four years. Indirect beneficiaries calculated based on population within the target PROSPER TA who will benefit from PROSPER activities and institutional capacity building at TA level but are not direct programme beneficaries. Data taken from NSO 2018 Census, including population totals and annual population growth rates. Output 3.2 Milestones calculated based on estimation of 200 ha per watershed, with 14 watersheds targeted within NGO programme - included forest areas and beneficiary fields (watershed delineation completed June 2019). INGO reaching a total of 2,800ha and UN 6,992 ha. Targets are based on the amount of land wherein restorative measures are planned based on resources allocated. Output 3.3 Target is expected to be 100% of the HH identified in need of assistance. Output 3.4 Target percentage expected to increase as more people are reached by shock responsive social protection. This indicator will be measured according to the use of government social protection systems where money is also channeled through government. This is only taking into consideration districts above 20% IPC and these targets are subject to be revised based on donor funding via government and the appropriateness of cash as a modality each year. This indicator covers the entire country, not just the four PROSPER districts because it is linked to the crisis modifier. Output 3.5 Milestones will be calculated based on the risk assesment and risk mapping to identify the population being supported by mitigation works
|  | Planned Indirect | See tab | 0 | 715961 | 715961 | 507303 | 527914 | 759852 | 759852
|  | Achieved Direct | See tab |  | 355,039 direct (180,001F, 175,038M) | 355,039 direct (180,001F, 175,038M) | 435,960 (221,032F, 214,928M) | 305,833 (178,826F; 127,007M)7, | 305,833 (178,826F; 127,007M) | 305814 (178,826F; 127,007M)
|  | Achieved Indirect | See tab |  | 516,648 indirect (261,941F, 254,707M) | 516,648 indirect (261,941F, 254,707M) | 647,320 (323,121F, 314,999M) | 759,852 (391,324F; 368,528M) | 759,852 (391,324F; 368,528M) | 759,852 (391,324F; 368,528M)
Source
Quarterly reports from implementing agencies
| Output Indicator 3.2 |  | Inception (06/19) | Baseline | Milestone 1(03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Milestone (08/23) | Target (08/24) | Milestone (12/25) | Milestone (06/26)
| Number and total value of matching grants disbursed to targeted FFS with support from FCDO | Planned |  | 0 | 0 | 0 | 0 | 0 | MWK360,850,000 | MWK360,850,000
|  | Achieved | [6 empty] | MWK283,419,152 | MWK575,315,148
Source
Programme Data, Annual Assessments Report by FAO
| Output Indicator 3.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved | Planned | See tab | 0 | 4400 | 4400 | 3400 | 4792 | 12264 | 12264
|  | Achieved | See tab |  | 5799 | 5799 | 14190 | 3011 | 10866 | 12337.6
Source
Programme Data, delineation, hotspot mapping and follow up measurement (remote sensing and other tools)
| Output Indicator 3.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people reached during the lean season response with cash transfers - Annual target | Planned | 150000 |  | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 500000 | 409239 | 363943 | 100%
|  | Achieved | 134400 |  | 155,000 people reached | 155,000 people reached | 488340 | 168,246 (82,439M; 85,807F) | 363,943 (175,573M, 188,570F) | 372274
Source
MVAC
| Output Indicator 3.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Planned | See tab | 0 | 20% | 20% | 30% | 40% | 50% | 50%
|  | Achieved | See tab |  | 35.09% | 35.09% | 45.01% | 27% | 90% | 92%
Source
MVAC and UBR data
| Output Indicator 3.6 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people with access to flood evacuation centres during a flood occurrence | Planned | See tab |  |  |  |  | 2400 | 2400 | 2400
|  | Achieved | See tab |  |  |  |  | 1995 | 4650 | 4424
Source:
Impact Survey, District Reports
| Output Indicator 3.7 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people benefiting from the cash-based interventions (Number of people) | Planned |  | 122682 |  |  |  | 126000 | 258000 | 1724873
|  | Achieved | [6 empty] | 128451 | 1371914
Source
Regular monitoring (through MIS)-Annual
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
|  |  | 0 | 0 |  |  |  |  | 100% |  |  |  | Assumptions | Comments on Indicators and Targets
INPUTS (HR) | FCDO (FTEs) | [11 empty] | Combined efforts of partners on district capacity strengthening will have measurable effects Coordination of PROSPER partners will enable coordination across all actors and empower districts to gain greater capacity for integrated coordination Combined efforts of BRACC partners on district capacity strengthening will have measurable effects Shock-responsive social protection will have demonstrable positive outcomes from the 2019 season that will encourage systems investment in subsequent years | Output 5.1 Qualitative survey of district stakeholders on the existence and quality of integrated coordination, monitoring systems and social accountability systems for a) social protection b) resilience programmes and c) emergency interventions. Output 5.2 The process will involve collection of baseline data against all 8 targets of the Sendai framework, setting up of data collection systems and systematic collection of data to track progress in implementing the Sendai framework for DRR. This work will be linked to MGDS and National resilience strategy. Currently 9 districts in Malawi meet this criteria, but none are the four PROSPER districts. Output 5.3 Targets set to achieve beyond 4 PROSPER for lean-season : Key shock responsive features include : 1) preparednessof the service provider, 2) developed targeting procedure 3) scalable data management systems 4) scalable grievances mechanisms 5) processes informing or triggering a scale-up 6) clarification of funding channels 7) a developed communication strategy for a scale-up 8) a developed M&E Framework
IMPACT WEIGHTING (%)
25
OUTPUT 4 | Output Indicator 4.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. | Number of districts with integrated coordination, monitoring and social accountability systems for social protection/resilience and emergency interventions | Planned | See tab | 0 | 2 | 2 | 4 | 4 | 4 | 4
|  | Achieved | See tab |  | 2 | 2 | 4 | 6 | 4 | 6
Source
Partner reports; District Coordinator reports
| Output Indicator 4.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of Districts with functional Disaster Information Management System | Planned | See tab | 0 | - | 1 | 4 | 4 | 4 | 4
|  | Achieved | See tab |  | - | 1 | 4 | 4 | 4 | 9
|  | Source | [10 empty] | RISK RATING
|  | Reports submitted by the Government of Malawi to inform the accomplishment of Sendai Framework reporting | [10 empty] | MEDIUM
| Output Indicator 4.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of shock-responsive features of key social protection programmes put in place within the Malawi social protection programme (preparedness) | Planned | See tab | 1 | 2 | 2 | 4 | 5 | 6 | 6
|  | Achieved | See tab |  | 2 | 2 | 4 | 5 | 4 | 4
Source
MNSSP Reporting cycles, program reports, donors reports
IMPACT WEIGHTING (%)
5
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 3000000 |  | 0 | 0 |  |  |  | 3000000 | 100
INPUTS (HR) | FCDO (FTEs)
3
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) | Other (£) |  |  | Total (£) | FCDO SHARE (%) |  |  |  |  | Assumptions
| 5000000 |  | Germany £7,158,160 | 0 | EU :£2,681,431 |  |  | 14839591 | 34 |  |  |  |  | Natural resource based entreprises can be identified and create sufficient incentives for improved forest management Co-management agreements can be agreed between private sector, communities and local authorities in targeted landscapes
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 5 | Output Indicator 5.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods | No of people with livelihood co-benefits from improved forest management | Planned | See tab | 0 | DCA agreed with USAID African Parks Baseline Assesment Report completed; and livelihoods projects in each park identified. | MCHF NR based value chains have been analysed and early stage innoavtors identified and selected | 5000 | 15000 | 96000 | 30000 | 29000 | 16000
|  | Achieved | See tab |  | Completed | Partially completed | 1802 | 29950 | 95078 (45,643M, 49,434F) | 35,896 (17,343M; 18,553F)
Source
Quarterly reports from implementing agencies
| Output Indicator 5.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| No hectares of degraded landscapes under improved management | Planned | See tab | 0 | 0 | MCHF Target landscapes identify and delineated, restoration opportunites assessed | 0 | 3500 | 10000 | 7500 | 3000 | 2000
|  | Achieved | See tab |  | 0 | Completed | Interim indicators completed | 9026 | 14720 | 9845
Source
Quarterly reports from implementing agencies
| Output Indicator 5.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Tons of sustainable charcoal or alternative biomass energy produced | Planned | See tab | 0 | 0 | PEA on charcoal value chain completed | 0 | 0 | 4000 | 1000 | 700 | 500
|  | Achieved | See tab |  | 0 | Partially completed | Interim indicators completed | 1500 | 536.80MT | 722.7MT
|  | Source | [10 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [10 empty] | MEDIUM
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
20 | Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Planned | See tab | 0 | 0 | Finance and investment for FE and AE sectors mobilised through programme and non programme sources | 0 | $2million | $4million | $3.65 million | $2m | $1.3m
|  | Achieved | See tab |  | 0 | Completed | Interim indicators completed | $2.756million | $5,459,201 | $3,97 million
Source
Quarterly reports from implementing agencies
| Output Indicator 5.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people and social institutions with improved access to clean energy as a result of ICF (KPI 2) (Report will be on Number of People) | Planned | [8 empty] | 13372 | 4011
Achieved
Source
MCHF Annual Report
| Output Indicator 5.6 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Hectares of land that have received sustainable land management practices as a result of ICF (ICF KPI 17) | Planned | [5 empty] | 18087.77 | 25881.68 | 29060 | 1800 | 1200
|  | Achieved | [5 empty] | 29518 | 31192 | 28745
Source
MCHF annual reports
| Output Indicator 5.7 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Tonnes of greenhouse gases reduced or avoided as a result of International Climate Finance (KPI 6) | Planned | [8 empty] | 557766.6 | 559411.2
Achieved
Source
MCHF Annual Report
| Output Indicator 5.8 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of direct project beneficiaries of Enhanced Public Works Programme | Planned |  | 0 |  |  |  | 435000 | 520000 | 2340000 | 2400000 | 2600000
|  | Achieved | [6 empty] | 362450 | 2270920
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%) |  |  |  | Assumptions
| 5000000 |  | 0 | 0 |  |  |  | 5000000 | 100 |  |  |  | Opportunities for TA are identified; There is enough political feedback and flexibility in contracting to enable the facility to be responsive to the most relevant opportunities.
INPUTS (HR) | FCDO (FTEs)
2.5
RISK RATING
OUTPUT 6 | Output Indicator 6.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | HIGH
More effective, coordinated and targeted, Government and donor investments | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 10 (monthly maize market reports, rapid analytics, policy brief) | 12 | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief)
|  | Achieved | 12 |  | 24 | 24 | 19 | 19 | 19
IMPACT WEIGHTING (%)
5 | Source
IFPRI Project Reports
| Output Indicator 6.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| # of disaster preparedness and response official releases the PFP influenced through technical advice | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 8000000 |  | 0 | 0 |  |  |  | 8000000 | 100
INPUTS (HR) | FCDO (FTEs)
3.5

## Logical Framework-Feb-Dec 2025
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumptions | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in target districts living below the national poverty line | Planned |  | 64.41 |  |  |  |  | 2.5% decrease | 2.5% decrease | 3.0% decrease | 4.0% decrease | The programme will use any interim poverty data that becomes available to report on results. Due to the recurrent cyclones and disasters affecting Malawi, we don't anticipate the poverty levels to decrease beyond the 2.5% | We propose to keep monitoring this impact in the same target districts as PROSPER because SSRLP programmes are in the same districts. Data for this indicator should become available in May 2025 through IHS survey results.
Achieved
Source
NSO IHS data (available every 3 years). If WB Implement SWIFT we may be able to get more regular data points
| Impact Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Difference in difference comparison of targeted TAs and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) | Planned |  | - | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs |  | We propose to keep monitoring this impact in the same target districts as PROSPER because SSRLP programmes are in the same districts.
|  | Achieved |  |  | -0.19 | -0.19 | -11.67 | -84% | 28.20 percentage higher in PROSPER TAs than non-PROSPER Tas | -28.2%
Source
MVAC annual assessments (annual - usulaly available in August)
OUTCOME | Outcome Indicator 1a |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumptions | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
Strengthened resilience of the targeted poor and vulnerable households to withstand current and future weather and climate related shocks and stresses | Percentage of people whose resilience has been improved as a result of project support (ICF KPI 4)* *Using WFP Methodology | Planned | 0 | From Resilience Index | Not yet measurable | Baselines and milestones established | 20% of households | 30% of households | 35% of households | 35% households | 90% | 100% |  | This will continue to be reported on under WFP related work under PROSPER (resilience)
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. Baseline = 11%(n)( PROSPER 2020 Annual survey) | 25% | 25% | 72.8% (Medium CRCS-55.2%, and High CRCS-17.6%) | 81% (Medium CRCS-58%, and High CRCS-23%)
Source
WFP's survey-using their methodology
| Outcome Indicator 1b |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26) | Assumptions
| % of people of all genders that have used their increased capacities for resilience and adaptation to the effects of climate change (NGO Consortium) | Planned | [8 empty] | 30% | 60% | Community Engagement and Participation 1.Communities are willing and able to actively participate in preparedness and recovery planning. 2. Local knowledge and traditional coping mechanisms are integrated into resilience strategies.
|  | Achieved | [8 empty] | 43%
Source
Monitoring survey/Endline Report
| Outcome Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (12/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| % Households classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) - Using CARI index (WFP) | Planned | 0 | IFPRI=55.1%, WFP=58.4% | Not yet measurable | - | 60% | 63% | 66% | 66% | 68% | 70% |  | This will continue to be reported by SSRLP because they also use the same WFP methodology to collect the data
|  | Achieved | 0 |  | Not yet measurable | WFP PDM survey=54% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=78% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=62% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=53% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=39% | 41%-SSRLP Midline Report
Source
| Outcome Indicator 3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (12/24) | Milestone (12/25) | Milestone (12/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Proportion of Social Cash Transfer and Public Works Programme project beneficiary households with an improved food consumption score (Percentage) (World Bank/WFP) | Planned |  | 51.6 |  |  |  |  | 47.9 | 47.9 | 60 (World Bank) 95% (WFP) | 75 |  | This is a new outcome indicator included from the SSRLP social protection programme
|  | Achieved | [6 empty] | 41.9 | 65.4 | 65% (World Bank) 82% (WFP)
Source
Monitoring survey/Endline Report
INPUTS (£)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumption | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
Vulnerable households and communities in targeted areas have reduced exposure and have great capacity to recover from floods and droughts (this includes cash transfer and EWS) | Number of people supported by FCDO programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines (contributed by WFP and NGO) | Planned Direct | See tab | 0 | 313240 | 313240 | 541930 | 541930 | 313429 | 303838 | 334104 |  | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts. |  | This indicator will continue to be reported on by WFP El Nino, NGO Consortium. This will compose of beneficiaries from; WFP- lean season response-(71579) cash for work (25,074); NGO's- cash transfer (57,474), artisan builders trained (450); CSA (51,727); people covered by early warning systems (127,800) | This indicator will continue to be reported on by WFP (PREPARE), NGO Consortium. This will compose of beneficiaries from WFP-refugee support (58,773), In kind assistance (1,693,562); NGO's- ), cash transfers (320,049)
|  | Planned Indirect | See tab | 0 | 715961 | 715961 | 507303 | 527914 | 759852 | 759852 | 43300
|  | Achieved Direct | See tab |  | 355,039 direct (180,001F, 175,038M) | 355,039 direct (180,001F, 175,038M) | 435,960 (221,032F, 214,928M) | 305,833 (178,826F; 127,007M)7, | 305,833 (178,826F; 127,007M) | 305814 (178,826F; 127,007M) | 342556 (170,929F; 171,672M)
|  | Achieved Indirect | See tab |  | 516,648 indirect (261,941F, 254,707M) | 516,648 indirect (261,941F, 254,707M) | 647,320 (323,121F, 314,999M) | 759,852 (391,324F; 368,528M) | 759,852 (391,324F; 368,528M) | 759,852 (391,324F; 368,528M) | 43300 (22,083F; 21,217M)
Source
Quarterly reports from implementing agencies
| Output Indicator 1.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Number of people reached during the lean season response with cash transfers - Annual target (from WFP and NGOs for FY2025) | Planned | 150000 |  | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 500000 | 409239 | 363943 | 100% | 100% | 100% |  | This will continue to be reported against an annual humanitarian response allocation
|  | Achieved | 134400 |  | 155,000 people reached | 155,000 people reached | 488340 | 168,246 (82,439M; 85,807F) | 363,943 (175,573M, 188,570F) | 372274 | 129053
Source
MVAC
| Output Indicator 1.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Planned | See tab | 0 | 20% | 20% | 30% | 40% | 50% | 50% | 95% | 100% |  | This will continue to be reported against an annual humanitarian response allocation
|  | Achieved | See tab |  | 35.09% | 35.09% | 45.01% | 27% | 90% | 92% | 62%
Source
MVAC and UBR data
| Output Indicator 1.4a |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Number of people benefiting from the cash-based interventions (Number of people) (World Bank) | Planned |  | 122682 |  |  |  | 126000 | 258000 | 1724873 | 1000000 | 1183691 |  | This is a new indicator which has started in 2024 and will continue to be reported through MDTF
|  | Achieved | [6 empty] | 128451 | 1371914 | 999514 (544,464F; 455,050M)
Source
Regular monitoring (through MIS)-Annual
| Output Indicator 1.4b |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people using digitally enabled services during social cash transfer and public works programme (World Bank) | Planned | [8 empty] | 3400000 | 3690000
|  | Achieved | [8 empty] | 2,659,158 (1,299,369M; 1,359,789F)
Source
World Bank Annual Report/Logframe
| Output Indicator 1.5 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Number of refugees receiving unconditional cash assistance (PREPARE AND CURRENT WFP PROGRAMME) | Planned | [8 empty] | 57000 | 58773
|  | Achieved | [8 empty] | 55,190 (28,656F; 26,534M)
Source
World Bank Annual Report
| Output Indicator 1.6 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of kits procured and prepositioned in number of sites-PREPARE ONLY | Planned | [8 empty] | 15000
|  | Achieved | [8 empty] | 15000
Source
WFP Reports
| Output Indicator 1.7 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people engaged in capacity strengthening activities-(PREPARE ONLY) | Planned | [8 empty] | 30
|  | Achieved | [8 empty] | 91 (41F; 50M)
Source
WFP Reports
| Output Indicator 1.8 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of partners utilising storage services for prepositioning (PREPARE ONLY) | Planned | [8 empty] | 10
|  | Achieved | [8 empty] | 4
Source
WFP Reports
| Output Indicator 1.9 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Percentage of timely in-kind transfers reaching beneficiaries per month (PREPARE/CURRENT WFP) | Planned | [8 empty] | 95
Achieved
Source
WFP Reports
| Output Indicator 1.10 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26) |  | Comments
| Number of people receiving food in-kind assistance (disaggregated by gender and disability) (WFP El Nino Response/2025 PROJECT) | Planned | [8 empty] | 465000 | 846781 |  | WFP will report on how many have received food in kind assistance by December. The total target was 1,693,562 but it has been divided into 2
|  | Achieved | [8 empty] | 465000
Source
WFP Reports
| Output Indicator 1.11 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (12/26)
| Number of beneficiaries of productive inclusion programmes (World Bank) | Planned | [5 empty] | 435000 | 520000 | 2340000 | 2400000 | 2400000
|  | Achieved | [6 empty] | 362450 | 2270920 | 2,067,277 (988,132F; 1,079,145M)
Source
| Output Indicator 1.12 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26)
| Percentage of Agricultural inputs provided in line with pre-defined performance criteria (distribution conducted in time for planting season; correct quantity of items received; able to travel to/from distribution point within daylight; waiting time less than 2 hours; items provided safely; no difficulties in accessing distribution/items) (NGO consortium) | Planned | [8 empty] | 85% | 90% | Adaptation measures promoted are context-appropriate and perceived as relevant by project participants. Agricultural seasons and planting calendars are accurately forecasted and adhered to in planning. Procurement, logistics, and transport systems function effectively and on time. Suppliers and implementing partners adhere to quality and performance standards. Community members are willing to participate in the management and oversight of CDFs. Local authorities and communities actively participate in the rehabilitation process and take ownership of maintenance post-project. Water sources are sufficient and reliable
|  | Achieved | [8 empty] | 71.2%
Source
Post dstribution monitoring report
| Output Indicator 1.13 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26)
| Number of Community Disaster Funds (CDFs) established and fully operational (NGO consortium) | Planned | [8 empty] | 7 | 11
|  | Achieved | [8 empty] | 6
Source
Programme reports, CDF monitoring tool
| Output Indicator 1.14 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26)
| Number of irrigation schemes rehabilitated or improved (NGO consortium) | Planned | [8 empty] | 4 | 12
|  | Achieved | [8 empty] | 5
Source
Programme reports, site monitoring, procurement and finance documentation
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
|  |  | 0 | 0 |  |  |  |  | 100% |  |  |  |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
INPUTS (HR) | FCDO (FTEs) | [12 empty] | This is a new indicator under SSRLP that will be included
IMPACT WEIGHTING (%)
90
OUTPUT 2 | Output Indicator 2.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26) | Assumptions
Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. | Number of partners_LNGOs reporting improved knowledge in emergency management (NGO Consortium) | Planned | See tab | [7 empty] | 5 | 10
|  | Achieved | [8 empty] | 0
Source
Pre/Post trainings assessment/Endline Report
| Output Indicator 2.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (03/26) | Assumptions
| Number of districts supported with training and engagement on revised AA, EOC and emergency response coordination SOPs to enhance their capacity for emergency response (WFP Current Project) | Planned | [8 empty] | 2 | 4
|  | Achieved | [8 empty] | 9
Source
WFP/Partner Reports
IMPACT WEIGHTING (%)
5
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
|  |  | 0 | 0
INPUTS (HR) | FCDO (FTEs)
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) | Other (£) |  |  | Total (£) | FCDO SHARE (%) |  |  |  |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
0
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumptions | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods | No of people with livelihood co-benefits from improved forest management | Planned | See tab | 0 | DCA agreed with USAID African Parks Baseline Assesment Report completed; and livelihoods projects in each park identified. | MCHF NR based value chains have been analysed and early stage innoavtors identified and selected | 5000 | 15000 | 96000 | 30000 | 29000 | 16000
|  | Achieved | See tab |  | Completed | Partially completed | 1802 | 29950 | 95078 (45,643M, 49,434F) | 35,896 (17,343M; 18,553F)
Source
Quarterly reports from implementing agencies
| Output Indicator 3.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| No hectares of degraded landscapes under improved management | Planned | See tab | 0 | 0 | MCHF Target landscapes identify and delineated, restoration opportunites assessed | 0 | 3500 | 10000 | 7500 | 3000 | 2000
|  | Achieved | See tab |  | 0 | Completed | Interim indicators completed | 9026 | 14720 | 9845
Source
Quarterly reports from implementing agencies
| Output Indicator 3.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Tons of sustainable charcoal or alternative biomass energy produced | Planned | See tab | 0 | 0 | PEA on charcoal value chain completed | 0 | 0 | 4000 | 1000 | 700 | 500 |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
|  | Achieved | See tab |  | 0 | Partially completed | Interim indicators completed | 1500 | 536.80MT | 722.7MT
|  | Source | [10 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [10 empty] | MEDIUM
| Output Indicator 3.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Planned | See tab | 0 | 0 | Finance and investment for FE and AE sectors mobilised through programme and non programme sources | 0 | $2million | $4million | $3.65 million | $2m | $1.3m |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
|  | Achieved | See tab |  | 0 | Completed | Interim indicators completed | $2.756million | $5,459,201 | $3,97 million |  |  |  | New indicator and will be reported in 2025 under MCHF
Source
|  | Quarterly reports from implementing agencies | [10 empty] | RISK RATING
HIGH
| Output Indicator 3.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Number of people and social institutions with improved access to clean energy as a result of ICF (KPI 2) (Report will be on Number of People) | Planned | [8 empty] | 13372 | 4011 |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
Achieved
Source
MCHF Annual Report
| Output Indicator 3.6 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Hectares of land that have received sustainable land management practices as a result of ICF (ICF KPI 17) | Planned | [5 empty] | 18087.77 | 25881.68 | 29060 | 1800 | 1200 |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
|  | Achieved | [5 empty] | 29518 | 31192 | 28745 |  |  |  | New indicator and will be reported in 2025 under MCHF
Source
MCHF annual reports
| Output Indicator 3.7 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Tonnes of greenhouse gases reduced or avoided as a result of International Climate Finance (KPI 6) | Planned | [8 empty] | 557766.6 | 559411.2 |  | New Indicator under SSRLP
Achieved
Source
MCHF Annual Report
| Output Indicator 3.8 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) |  | Comments on Indicators and Targets (2024) | Comments on Indicators and Targets (2025) | Comments on Indicators and Targets (2026)
| Number of beneficiaries of productive inclusion programmes | Planned |  | 0 |  |  |  | 435000 | 520000 | 2340000 | 2400000 | 2600000
|  | Achieved | [6 empty] | 362450 | 2270920
Source
World Bank Report
| Output Indicator 3.9 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26)
| Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved | Planned | See tab | 0 | 4400 | 4400 | 3400 | 4792 | 12264 | 12264 | 13000 | 13900
|  | Achieved | See tab |  | 5799 | 5799 | 14190 | 3011 | 10866 | 12337.6
Source
Programme Data, delineation, hotspot mapping and follow up measurement (remote sensing and other tools)
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 5000000 |  | 0 | 0 |  |  |  | 5000000 | 100
INPUTS (HR) | FCDO (FTEs) | [12 empty] | Comments on Indicators and Targets | Comments on Indicators and Targets | Comments on Indicators and Targets
2.5
IMPACT WEIGHTING (%)
OUTPUT 4 | Output Indicator 4.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (06/26) | Assumptions | Comments on Indicators and Targets | Comments on Indicators and Targets | Comments on Indicators and Targets
More effective, coordinated and targeted, Government and donor investments | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 10 (monthly maize market reports, rapid analytics, policy brief) | 12 | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 19 | 20
|  | Achieved | 12 |  | 24 | 24 | 19 | 19 | 19 | 19 | 20 |  |  | New Indicator to be reported in 2025 for the PFP post
Source
IFPRI Project Reports
| Output Indicator 4.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (12/26)
| # of disaster preparedness and response official releases the PFP influenced through technical advice | Planned | [8 empty] | 6 | 8
|  | Achieved | [8 empty] | 2
Source
Press releases, speeches, articles
| Output Indicator 4.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Milestone (08/24) | Milestone (12/25) | Milestone (12/26)
| # of summaries and learning products and reports developed as part of close out activities for MCHF | Planned | [8 empty] | 4 | 3
|  | Achieved | [8 empty] | 4
Source
Survey Reports, summaries of key findings,
IMPACT WEIGHTING (%)
5
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
|  |  | 0 | 0
INPUTS (HR) | FCDO (FTEs)

## Logical Framework - Dec 2020
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in target districts living below the national poverty line | Planned |  | 64.41 |  |  |  |  | 5% decrease from baseline |  | The % below the national poverty line accoring to the IHS4 are Phalombe: 83.2, Chikwawa 63.2, Balaka 61.3, and Mangochi 59.5. The weighted average for the four districts 64.41. The target has been set at a 5% decrease from the baseline at the end of the programme. Triangulation of data from similiar national programmes and survey shows that at most 5% decrease is attainable. The programme does not expect significant change by 2021 in the targeted population but will review data for IHS5 and replace the baseline with those figures for accuracy; therefore,no target has been set for Milestone 2 . Data for 2023 is expected from IHS6. It was agreed that the final reporting will fall outside the programme timeline. The programme will use any interim poverty data that becomes available to course correct.
Achieved
Source
NSO IHS data (available every 3 years). If WB Implement SWIFT we may be able to get more regular data points
| Impact Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) |  | Comments on Indicators and Targets
| Difference in difference comparison of targeted TAs and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) | Planned |  | - | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs |  | 2019 MVAC results will be used for baseline. The programme aims to maintain greater than or equal to IPC Baseline figures; the data will be used to make a difference in difference comparison betweeen PROSPER TA's and non PROSPER TA's to ascertain the effect of the programme. The programme will strive to have this percentage decrease beyond zero (into negative %).
|  | Achieved |  |  | -0.19 | -0.19
Source
MVAC annual assessments (annual - usulaly available in August)
OUTCOME | Outcome Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Strengthened resilience of the targeted poor and vulnerable households to withstand current and future weather and climate related shocks and stresses | Number of people whose resilience has been improved as a result of project support (ICF KPI 4)* *Using Resilience Index | Planned | 0 | From Resilience Index | Not yet measurable | Baselines and milestones established | 20% of households | 30% of households | 35% of households | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts. | Outcome Indicator 1 - Targets for number improving resilience will be set after baseline figures for the resilience index indicators are available. This is dependant on IFPRI baseline data which is expected between December 2019 and end of January 2020. Based on the baseline, the programme calculate anticipated numbers of households with improvemed resilience each year and set yearly milestones. Outcome Indicator 2 - GBP 7.28m is based on the incremental income attributable to PROSPER Markets work.This could be as a result of interventions for inputs, services or markets availed to participants. Estimates for cumulative increase in income from PROSPER INGO interventions (CSA, input fairs, livestock, irrigation)will be calculated from the % increase in yield sold as surplus. Targets for this will be calculated using IFPRI baseline results on current farmer yield in the targeted districts once baseline data is available. SU/SI are expected to increase yields and have sufficient surplus to sell. Outcome Indicator 3: The CARI index will be used: it is a composite indicator including Food Consumption Score, Food Expenditure Share and Livelihood Coping Strategies. The calculation provides a representative estimate of food insecurity within the targetted population. Targets are awaiting IFPRI and WFP - CSP baseline results. Outcome indicator 4: For the targets PROSPER will calculate the change in yield based on a difference in difference comparison between the control and treatment arms of the Impact Evaluation. Target set by Year 4 as 35% increase, with 10% gain in Year 1, Year 2 and Year 3, and 15% gain in Year 4.
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. Baseline = 11%(n)( PROSPER 2020 Annual survey)
Source
Annual Programme Surveys
| Outcome Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Cumulative aggregate increase in income among poor people | Planned | 0 | IFPRI(Annual farm+ non farm income per capita)= MK 8,466 | Not yet measurable | Baselines and milestones established | GBP 3.52m | GBP 5.2m | GBP 7.28m *
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. GBP; 2,208,388 (Male;1,147,607, Female;1,060,780); Kadale 2020 assessment
Source
Annual Programme Surveys
| Outcome Indicator 3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| % Households classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) - Using CARI index | Planned | 0 | IFPRI=55.1%, WFP=58.4% | Not yet measurable | - | 60% | 63% | 66%
|  | Achieved | 0 |  | Not yet measurable | WFP PDM survey=54% (Balaka, Chikwawa, Mangochi and Phalombe)
Source
Annual Programme Surveys
| Outcome Indicator 4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Difference in difference comparison of change in yield of maize and other crops against the baseline figure in PROSPER and non-PROSPER target areas | Planned | 0 | (0%)IFPRI: Average Maize Yield=1,110 Kgs for treatment, 1311 Kgs for non PROSPER areas | Not yet measurable | 10% | 20% | 30% | 35%
|  | Achieved | 0 |  | Not yet measurable | PROSPER 2020 Annual survey = 760 kgs/ha for PROSPER treatment areas. 560 kg/ha median.
Source
Annual Programme Surveys
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£)
| 90500000 |  | 0 | 0 |  |  |  | 90,5000,00
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Intensified and diversified agricultural production and improved nutrition for targeted vulnerable communities. | Number of households implementing Climate Smart Agriculture (CSA) practices | Planned | See tab | 0 | 42,525 individuals have received training in CSA | 21262.5 | 55% | 70% | 75% | Programme delivery can sustain current rate of progress with scale out of VSL and CSA technologies; cascade model of extension is effective; basic seed is available to enhance local seed supply for diverse crops, infromation is available from national meterological services that is relevant and of sufficient quality to disseminate. | Output 1.1 Milestones have been calculated as follows: The programme anticipates that for Milestone 1 60% of cohort 1 beneficiaries will implement at least 2 of the promoted pracrices, consecutively in YR 2 60% of Cohort 1 and 50% of Cohort 2 should see the benefits of using promoted GAPs, in Yr 3 75% of cohort 1 and 60% of cohort 2 should continue implementing 2 or more technologies and at the end of the programme, it is anticipated that 85% of cohort 1 and 75% of cohort 2 should be applying the technologies.These targets include HH also reached under the FFS where it is expected 50% of HH will implement CSA. Output Indictor 1.2: Targets based on numbers of farmers reached through the FFS model to improve extension services. Output Indictor 1.3: Indicator will capture both number of programme participants disaggregated by sex and hectares under production in the targeted irrigation schemes receiving PROSPER support. Collecting area under production and dissagregating it by sex allows for consideration of intra-household gender nuances of ownership, access and distribution of resources. Output Indictors 1.4 The indicators should be revisited when the baseline is set to ensure they are ambitious yet achievable. The target is set at 50% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence more than half of the population in PROSPER areas -- both men and women influencing the MAD for women in the household. Output Indicator 1.5: The target is set at 40% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence households in the PROSPER areas -- with more ground needing to be gained for young children's MAD. Output Indicator 1.6 These targets includes only SU beneficiaries. Milestone 1 is caculated based on 45% of SU (cohort 1), Milestone 2 ad 3 are 100% of SU (cohort 1 and cohort 2) while Milestone 4 is 55% of SU (cohort 2 only as cohort 1 subsidised inputs will phase out in Year 4)..
|  | Achieved | See tab |  | 78,253 (47,063F, 31,190M) individuals were trained in CSA practises | 37% (34,965hh - 12,587 FHH, 22,378 MHH) adopting CSA (6 or more practices), PROSPER 2020 Annual survey
Source
Programme Annual Survey
| Output Indicator 1.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of farmers who report improvements in extension services received (by type of extension provider: public, community-based, private) | Planned | See tab | 49.5% of farmers receiving services | First cohort of FFS master training complete and FFS established in PROSPER areas Lead farmer training complete Private sector extension activities complete | 27000 | 47.87% | 50.55% | 53.23%
|  | Achieved | See tab |  | Completed | 30,240 The Annual Survey also found 49.5% of respondents reported receiving extension services. Of these, 64% reported improved extension services - which equates to a result of 32% when applied to whole population. So applying the 32% to the 94,500 farmers gives us 30,240
|  | Source |  |  | Source
Programme Annual Survey
| Output Indicator 1.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Hectares of farm land under irrigation (disaggregated by size of scheme, type of technology) | Planned | See tab | 0 | Agreement with PumpAid in place Feasibility assessments and planning for irrigation schemes in identified areas complete | Irrigation activities underway for winter cropping season. Baseline and milestones established. | 303.4 | 612.6 | 612.6
|  | Achieved | See tab |  | Completed | Completed Baseline established at 12.6hectares
|  | Source |  |  | Source
Programme Annual Survey
| Output Indicator 1.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of women between 15-49 reaching the minimum dietary diversity score | Planned | See tab | 0 | Mapping and reactivated SBCC district/TA and villlage structures Strengthen ANCCs and VNCC | Mapping and reactivated SBCC district/TA and villlage structures Strengthen ANCCs and VNCC | 38% | 43% | 50%
|  | Achieved | See tab |  | Completed. Baseline established at 26% | Completed. WFP PDM survey = 27%
Source
IFPRI/WFP CSP Baseline/SMART Surveys/UN Consortium October Survey
| Output Indicator 1.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage children 6-23 months consuming a minimum acceptable diet (MAD) | Planned | See tab | 0 | Nutrition sensitive social protection intervention designed Pregnant and lactating SCTP benficiaries targetted | Nutrition sensitive social protection intervention designed Pregnant and lactating SCTP benficiaries targetted | 10% | 15% | 20%
|  | Achieved | See tab |  | Completed. Baseline established at 3.5% | Completed. WFP PDM survey = 7.9%
Source
IFPRI/WFP CSP Baseline/SMART Surveys/UN Consortium October Survey
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Number of farmers that received agricultural inputs to promote increased productivity during the reporting year - Annual target | Planned | See tab | 0 | 27337.5 | 27337.5 | 60750 | 60750 | 33412.5
|  | Achieved | See tab |  | 26,458 (16,984F, 9,474M) farmers | 26,458 (16,984F, 9,474M) farmers
[5 empty] | Source |  |  |  |  | RISK RATING
|  | Routine Programme Data Records | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 19000000 |  | 0 | 0 |  |  |  | 19000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 2 | Output Indicator 2.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Enhanced and inclusive access to the productive resources necessary to develop increased, secure and predictable incomes. | Number of market system actors that invest in pro-poor business models | Planned | See tab | 0 | 4 | 4 | 8 | 10 | 12 | New climate resilient business opportunities are viable in the project context; Market actors respond positively to incentives unlocked by PROSPER and are willing to absorb and act on new knowledge and business practices. Insurance products are afffordable and lead to producers being less risk averse in their decision making and increase investment | Output 2.1 : Targets are cumulative based on a total of 12 private sector stakeholders, including 4 in Year 1, with additional 4 in Year 2, 2 in Year 3, and 2 in Year 4. Output 2.2 Target of 94,500 is the total number of people reached by Kadale inputs and services interventions. This number is then reduced by 16.66666%* to discount the poor people who have accessed and used the inputs, but have not experienced income change as a result of this input access/use. Therefore, reducing the output target of 94,500 by 16.66666% we get Kadale's target on outcome level of 78,750 (then counting each individual as a head of a household to align with NGO targets for households). *The discount of 16.66666% is based on findings from MOST. Output 2.3 Target based on total population reached through VSL activities. This group is expected to benefit from at least one financial product the programme is offering through CUMO work.
|  | Achieved | See tab |  | 5 | 5
Source
Quarterly reports from implementing agencies
| Output Indicator 2.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of poor people with increased access to productivity or income enhancing inputs or services /markets | Planned | See tab | 0 | 15000 | 15000 | 73000 | 83000 | 94500
|  | Achieved | See tab |  | 59,069 (24,708F, 34,361M) poor people | 63,802 (27,142F, 36,661M) poor people
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output indicator 2.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Number of households with access to financial services as a result of DFID support (DFID Global Indicator List) | Planned | See tab | 0 | 20250 | 20250 | 40500 | 60750 | 60750
|  | Achieved | See tab |  | 72,276 (21,663M, 50,613F) households | 72,276 (21,663M, 50,613F) households
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 8500000 |  | 0 | 0 |  |  |  | 7500000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Vulnerable households and communities in targeted areas have reduced exposure to drought and floods | Number of people supported by DFID programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines | Planned Direct | See tab | 0 | 313240 | 313240 | 541930 | 541930 | 541930 | Cooperation with District Natural Resource teams, technical skills in catchment planning and irrigation scheme development are available, timely procurement of materials for implementation of works during appropriate seasons; institutions established by the programme for managing water and forest are functional and equitable. Humanitarian stakeholders willing to be coordinated; appropriate insitutitional arrangements can be established to enable rapid response. | Output 3.1 Indicator will track direct and indirect individuals receiving high and medium intensity support respectively. Targets for direct beneficiaries based on total number of individuals receiving direct support from PROSPER (123,166 HH * 4.4 individuals per HH). Year 1 targets based on Cohort 1 of 45% of SU/SO plus all HI in Year 1, adding Cohort 2 of 55% of SO/SU in Year 2 to reach 100% of SU/SO. Target maintained for four years. Indirect beneficiaries calculated based on population within the target PROSPER TA who will benefit from PROSPER activities and institutional capacity building at TA level but are not direct programme beneficaries. Data taken from NSO 2018 Census, including population totals and annual population growth rates. Output 3.2 Milestones calculated based on estimation of 200 ha per watershed, with 14 watersheds targeted within NGO programme - included forest areas and beneficiary fields (watershed delineation completed June 2019). INGO reaching a total of 2,800ha and UN 6,992 ha. Targets are based on the amount of land wherein restorative measures are planned based on resources allocated. Output 3.3 Target is expected to be 100% of the HH identified in need of assistance. Output 3.4 Target percentage expected to increase as more people are reached by shock responsive social protection. This indicator will be measured according to the use of government social protection systems where money is also channeled through government. This is only taking into consideration districts above 20% IPC and these targets are subject to be revised based on donor funding via government and the appropriateness of cash as a modality each year. This indicator covers the entire country, not just the four PROSPER districts because it is linked to the crisis modifier. Output 3.5 Milestones will be calculated based on the risk assesment and risk mapping to identify the population being supported by mitigation works
|  | Planned Indirect | See tab | 0 | 715961 | 715961 | 507303 | 527914 | 549119
|  | Achieved Direct | See tab |  | 355,039 direct (180,001F, 175,038M) | 355,039 direct (180,001F, 175,038M)
|  | Achieved Indirect | See tab |  | 516,648 indirect (261,941F, 254,707M) | 516,648 indirect (261,941F, 254,707M)
Source
Quarterly reports from implementing agencies
| Output Indicator 3.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved | Planned | See tab | 0 | 4400 | 4400 | 3400 | 6792 | 9792
|  | Achieved | See tab |  | 5799 | 5799
Source
Programme Data, delineation, hotspot mapping and follow up measurement (remote sensing and other tools)
| Output Indicator 3.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of people reached during the lean season response with cash transfers - Annual target | Planned | 150000 |  | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020) | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020) | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020)
|  | Achieved | 134400 |  | 155,000 people reached | 155,000 people reached
Source
MVAC
| Output Indicator 3.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Planned | See tab | 0 | 20% | 20% | 30% | 40% | 50%
|  | Achieved | See tab |  | 35.09% | 35.09%
Source
MVAC and UBR data
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Household(s) using EWS and climate information for floods and droughts to reduce risks to their lives and or property | Planned | See tab | 0 | 32516 | 32516 | 65032 | 97548 | 162579
|  | Achieved | See tab |  | 28,666HH (9,780M and 18,886F) | 28,666HH (9,780M and 18,886F)
|  | Source | [7 empty] | RISK RATING
|  | Impact Survey , District Reports | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| £22,000,000 (+£20million crises modifer) |  | 0 | 0 |  |  |  | £22,000,000 (+£20million crises modifer) | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 4 | Output Indicator 4.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. | Number of districts with integrated coordination, monitoring and social accountability systems for social protection/resilience and emergency interventions | Planned | See tab | 0 | 2 | 2 | 4 | 4 | 4 | Combined efforts of partners on district capacity strengthening will have measurable effects Coordination of PROSPER partners will enable coordination across all actors and empower districts to gain greater capacity for integrated coordination Combined efforts of BRACC partners on district capacity strengthening will have measurable effects Shock-responsive social protection will have demonstrable positive outcomes from the 2019 season that will encourage systems investment in subsequent years | Output 5.1 Qualitative survey of district stakeholders on the existence and quality of integrated coordination, monitoring systems and social accountability systems for a) social protection b) resilience programmes and c) emergency interventions. Output 5.2 The process will involve collection of baseline data against all 8 targets of the Sendai framework, setting up of data collection systems and systematic collection of data to track progress in implementing the Sendai framework for DRR. This work will be linked to MGDS and National resilience strategy. Currently 9 districts in Malawi meet this criteria, but none are the four PROSPER districts. Output 5.3 Targets set to achieve beyond 4 PROSPER for lean-season : Key shock responsive features include : 1) preparednessof the service provider, 2) developed targeting procedure 3) scalable data management systems 4) scalable grievances mechanisms 5) processes informing or triggering a scale-up 6) clarification of funding channels 7) a developed communication strategy for a scale-up 8) a developed M&E Framework
|  | Achieved | See tab |  | 2 | 2
Source
Partner reports; District Coordinator reports
| Output Indicator 4.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of districts development plans that implement local disaster risk reduction strategies in line with the Sendai Framework for Disaster Risk Reduction 2015-2030 | Planned | See tab | 0 | - | 1 | 4 | 4 | 4
|  | Achieved | See tab |  | - | 1
Source
Reports submitted by the Government of Malawi to inform the accomplishment of Sendai Framework reporting
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Number of shock-responsive features of key social protection programmes put in place within the Malawi social protection programme (preparedness) | Planned | See tab | 1 | 2 | 2 | 3 | 5 | 6
|  | Achieved | See tab |  | 2 | 2
|  | Source | [7 empty] | RISK RATING
|  | MNSSP Reporting cycles, program reports, donors reports | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 3000000 |  | 0 | 0 |  |  |  | 3000000 | 100
INPUTS (HR) | DFID (FTEs)
3
OUTPUT 5 | Output Indicator 5.1 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22) |  | Assumptions
A strengthened and more shock sensitive social protection system | No districts where 50% of SCTP and PWP beneficiary households received their transfers through e-payments | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 1 | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | In 4 districts beneficiary households in at least one traditional authority have received their transfer through e-payments at least once | 7 districts |  | Existsing strong political will to reduce extremen poverty Funding for social protection programmes is available on time at central and district level. Public Works with the focus on watershed manage-ment continues. Line Ministries and donors remain interested in improv-ing coordination and harmonization in the area of social protection.
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Completed | Completed
Source
Analysis of payment data in SCT and PW MIS
| Output Indicator 5.2 |  | Inception (06/19) | Milestone 1 (03/20) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
| No districts where 70% of the total complaints submitted have been closed according to the guidelines. | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 0 | Magomero training course for extension workers is developed Outline of the Implementation Manual has been agreed Harmonized greivance and redress mechanisms developed | Maglomero training course for extension workers is developed Outline of the Implementation Manual has been agreed Harmonized greivance and redress mechanisms developed | Grievance and Redress mech-anism awareness and sensitization is undertaken in 2 districts and District officers are trained on complaint mecha-nism | 3
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Patrially completed | Patrially completed |  | No longer appplicaple. Activity terminated early due to ODA cuts.
Source
Analysis of GRM data
| Output Indicator 5.3 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
| No. of additional social protection beneficiary households (out of which at least 55 % are female-headed house-holds) twhich are purposively linked to complementary interventions (e.g. livelihood projects and nutri-tion-sensitive interventions) through tools developed by the programme. | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 0 | Development of a project implementation manual Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | Development of a project implementation manual Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | 2000 | 10000
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Partially completed | Partially completed | 2373 hh
Source
Analysis of SCT and PWP MIS and Unified Beneficiary Registry (UBR)
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
5 | No of micro–watersheds where watershed rehabilitation activities have been implemented by communities as part of Public Works activities and according to the implementation plan, e.g. Village Action Plan (VAP). | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 8 | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 12 | 24
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Partially completed | Partially completed |  | No longer appplicaple. Activity terminated early due to ODA cuts.
|  | Source | [7 empty] | RISK RATING
|  | Analysis of register for peo-ple regarding number of days and number of volunteers in the micro-catchments; Documentation of completed activities by community wa-tershed committees and comparison with the imple-mentation plan (e.g. VAP). | [7 empty] | HIGH
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| 5000000 |  | Germany £7,158,160 | 0 | EU :£2,681,431 |  |  | 14839591 | 34
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 6 | Output Indicator 6.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods | No of people with livelhood co-benefits from improved forest management | Planned | See tab | 0 | DCA agreed with USAID African Parks Baseline Assesment Report completed; and livelihoods projects in each park identified. | MCHF NR based value chains have been analysed and early stage innoavtors identified and selected | TBD by March 2021 | Milestones set annually in December 2021 | 70000 | Natural resource based entreprises can be identified and create sufficient incentives for improved forest management Co-management agreements can be agreed between private sector, communities and local authorities in targeted landscapes
|  | Achieved | See tab |  | Completed | Partially completed
Source
Quarterly reports from implementing agencies
| Output Indicator 6.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| No hectares of degraded landscapes under improved management | Planned | See tab | 0 | 0 | MCHF Target landscapes identify and delineated, restoration opportunites assessed | TBD by March 2021 | TBD by March 2021 | 16000
|  | Achieved | See tab |  | 0 | Completed
Source
Quarterly reports from implementing agencies
| Output Indicator 6.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Tons of sustainable charcoal produced | Planned | See tab | 0 | 0 | PEA on charcoal value chain completed | TBD by March 2021 | TBD by March 2021 | 11000
|  | Achieved | See tab |  | 0 | Partially completed
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output Indicator 6.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Planned | See tab | 0 | 0 | Finance and investment for FE and AE sectors mobilised through programme and non programme sources | TBD by March 2021 | TBD by March 2021 | $2million
|  | Achieved | See tab |  | 0 | Completed
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 5000000 |  | 0 | 0 |  |  |  | 5000000 | 100
INPUTS (HR) | DFID (FTEs)
2.5
OUTPUT 7 | Output Indicator 7.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions
More effective, coordinated and targeted, Government and donor investments | No. of politically responsive technical assistance workstreams developed and under active implementation using adaptive management principles | Planned | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) | 0 | Contract with KPM has been awarded Handover of evaluation activities complete Contract inception phase activities on track | Contract with KPM has been awarded Handover of evaluation activities complete Contract inception phase activities on track | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021 | Opportunities for TA are identified; Sufficient senior level support from DFID and UK Diplomatic Representation is available to shape influential workstreams; There is enough political feedback and flexibility in contracting to enable the facility to be responsive to the most relevant opportunities.
|  | Achieved | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) |  | Completed | Completed
Source
IFPRI project reports/ Final ToRs
| Output Indicator 7.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| # of days of technical assistance provided / average fee rate per day in £ | Planned | Impact Evaluation design complete and QA'd by EQUALs Baseline survey complete | 0 | Baseline survey analysis completed and outcome milestones agreed Resilience learning event completed Programme governance agreed and have met at least once | Baseline survey analysis completed and outcome milestones agreed Resilience learning event completed Programme governance agreed and have met at least once | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021
|  | Achieved | Impact Evaluation design complete and submitted to EQUALs Baseline survey not yet complete (expected August) |  | Completed | Completed
Source
IFPRI project reports
IMPACT WEIGHTING (%) | Output Indicator 7.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
10 | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 10 (monthly maize market reports, rapid analytics, policy brief) | 12 | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | TBD once KPM implementation ammendment agreed - April 2021 | TBD once KPM implementation ammendment agreed - April 2021
|  | Achieved | 12 |  | 24 | 24
|  | Source | [7 empty] | RISK RATING
|  | IFPRI project reports | [7 empty] | HIGH
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 8000000 |  | 0 | 0 |  |  |  | 8000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5

## Logical Framework - June 2020
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in target districts living below the national poverty line | Planned |  | 64.41 |  |  |  |  | 5% decrease from baseline |  | The % below the national poverty line accoring to the IHS4 are Phalombe: 83.2, Chikwawa 63.2, Balaka 61.3, and Mangochi 59.5. The weighted average for the four districts 64.41. The target has been set at a 5% decrease from the baseline at the end of the programme. Triangulation of data from similiar national programmes and survey shows that at most 5% decrease is attainable. The programme does not expect significant change by 2021 in the targeted population but will review data for IHS5 and replace the baseline with those figures for accuracy; therefore,no target has been set for Milestone 2 . Data for 2023 is expected from IHS6. It was agreed that the final reporting will fall outside the programme timeline. The programme will use any interim poverty data that becomes available to course correct.
Achieved
Source
NSO IHS data (available every 3 years). If WB Implement SWIFT we may be able to get more regular data points
| Impact Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) |  | Comments on Indicators and Targets
| Difference in difference comparison of targeted TAs and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) | Planned |  | - | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs |  | 2019 MVAC results will be used for baseline. The programme aims to maintain greater than or equal to IPC Baseline figures; the data will be used to make a difference in difference comparison betweeen PROSPER TA's and non PROSPER TA's to ascertain the effect of the programme. The programme will strive to have this percentage decrease beyond zero (into negative %).
|  | Achieved |  |  | -0.19
Source
MVAC annual assessments (annual - usulaly available in August)
OUTCOME | Outcome Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Strengthened resilience of the targeted poor and vulnerable households to withstand current and future weather and climate related shocks and stresses | Number of people whose resilience has been improved as a result of project support (ICF KPI 4)* *Using Resilience Index | Planned | 0 | From Resilience Index | Not yet measurable | Baslines and milestones establihed | TBD | TBD | 800000 | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts. | Outcome Indicator 1 - Targets for number improving resilience will be set after baseline figures for the resilience index indicators are available. This is dependant on IFPRI baseline data which is expected between December 2019 and end of January 2020. Based on the baseline, the programme calculate anticipated numbers of households with improvemed resilience each year and set yearly milestones. Outcome Indicator 2 - GBP 6.5m is based on the incremental income attributable to PROSPER Markets work.This could be as a result of interventions for inputs, services or markets availed to participants. Estimates for cumulative increase in income from PROSPER INGO interventions (CSA, input fairs, livestock, irrigation)will be calculated from the % increase in yield sold as surplus. Targets for this will be calculated using IFPRI baseline results on current farmer yield in the targeted districts once baseline data is available. SU/SI are expected to increase yields and have sufficient surplus to sell. Outcome Indicator 3: The CARI index will be used: it is a composite indicator including Food Consumption Score, Food Expenditure Share and Livelihood Coping Strategies. The calculation provides a representative estimate of food insecurity within the targetted population. Targets are awaiting IFPRI and WFP - CSP baseline results. Outcome indicator 4: For the targets PROSPER will calculate the change in yield based on a difference in difference comparison between the control and treatment arms of the Impact Evaluation. Target set by Year 4 as 35% increase, with 10% gain in Year 1, Year 2 and Year 3, and 15% gain in Year 4.
|  | Achieved | 0 |  | Not yet measurable
Source
Annual Programme Surveys
| Outcome Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Cumulative aggregate increase in income among poor people | Planned | 0 | IFPRI(Annual farm+ non farm income per capita)= MK 8,466 | Not yet measurable | Baslines and milestones establihed | TBD | TBD | GBP 6.5m *
|  | Achieved | 0 |  | Not yet measurable
Source
Annual Programme Surveys
| Outcome Indicator 3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| % Households classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) - Using CARI index | Planned | 0 | IFPRI=55.1%, WFP=58.4% | Not yet measurable | - | 60% | 63% | 66%
|  | Achieved | 0 |  | Not yet measurable
Source
Annual Programme Surveys
| Outcome Indicator 4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Difference in difference comparison of change in yield of maize and other crops against the baseline figure in PROSPER and non-PROSPER target areas | Planned | 0 | (0%)IFPRI: Average Maize Yield=1,110 Kgs for treatment, 1311 Kgs for non PROSPER areas | Not yet measurable | 10% | 20% | 30% | 35%
|  | Achieved | 0 |  | Not yet measurable
Source
Annual Programme Surveys
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£)
| 90500000 |  | 0 | 0 |  |  |  | 90,5000,00
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Intensified and diversified agricultural production and improved nutrition for targeted vulnerable communities. | Number of households implementing Climate Smart Agriculture (CSA) practices | Planned | See tab | 0 | 42,525 individuals have received training in CSA | 21262.5 | 51502.5 | 63078.75 | 75127.5 | Programme delivery can sustain current rate of progress with scale out of VSL and CSA technologies; cascade model of extension is effective; basic seed is available to enhance local seed supply for diverse crops, infromation is available from national meterological services that is relevant and of sufficient quality to disseminate. | Output 1.1 Milestones have been calculated as follows: The programme anticipates that for Milestone 1 60% of cohort 1 beneficiaries will implement at least 2 of the promoted pracrices, consecutively in YR 2 60% of Cohort 1 and 50% of Cohort 2 should see the benefits of using promoted GAPs, in Yr 3 75% of cohort 1 and 60% of cohort 2 should continue implementing 2 or more technologies and at the end of the programme, it is anticipated that 85% of cohort 1 and 75% of cohort 2 should be applying the technologies.These targets include HH also reached under the FFS where it is expected 50% of HH will implement CSA. Output Indictor 1.2: Targets based on numbers of farmers reached through the FFS model to improve extension services. Output Indictor 1.3: Indicator will capture both number of programme participants disaggregated by sex and hectares under production in the targeted irrigation schemes receiving PROSPER support. Collecting area under production and dissagregating it by sex allows for consideration of intra-household gender nuances of ownership, access and distribution of resources. Output Indictors 1.4 The indicators should be revisited when the baseline is set to ensure they are ambitious yet achievable. The target is set at 50% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence more than half of the population in PROSPER areas -- both men and women influencing the MAD for women in the household. Output Indicator 1.5: The target is set at 40% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence households in the PROSPER areas -- with more ground needing to be gained for young children's MAD. Output Indicator 1.6 These targets includes only SU beneficiaries. Milestone 1 is caculated based on 45% of SU (cohort 1), Milestone 2 ad 3 are 100% of SU (cohort 1 and cohort 2) while Milestone 4 is 55% of SU (cohort 2 only as cohort 1 subsidised inputs will phase out in Year 4)..
|  | Achieved | See tab |  | 78,253 (47,063F, 31,190M) individuals were trained in CSA practises
Source
Programme Annual Survey
| Output Indicator 1.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of farmers who report improvements in extension services received (by type of extension provider: public, community-based, private) | Planned | See tab | 0 | First cohort of FFS master training complete and FFS established in PROSPER areas Lead farmer training complete Private sector extension activities complete | 27000 | 54000 | 81000 | 108000
|  | Achieved | See tab |  | Completed
|  | Source |  |  | Source
Programme Annual Survey
| Output Indicator 1.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Hectares of farm land under irrigation (disaggregated by size of scheme, type of technology) | Planned | See tab | 0 | Agreement with PumpAid in place Feasibility assessments and planning for irrigation schemes in identified areas complete | Irrigation activities underway for winter cropping season. Baseline and milestones established. | TBD | TBD | At least 21,000
|  | Achieved | See tab |  | Completed
|  | Source |  |  | Source
Programme Annual Survey
| Output Indicator 1.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of women between 15-49 reaching the minimum dietary diversity score | Planned | See tab | 0 | Mapping and reactivated SBCC district/TA and villlage structures Strengthen ANCCs and VNCC | Mapping and reactivated SBCC district/TA and villlage structures Strengthen ANCCs and VNCC | 38% | 43% | 50%
|  | Achieved | See tab |  | Completed. Baseline established at 26%
Source
IFPRI/WFP CSP Baseline/SMART Surveys/UN Consortium October Survey
| Output Indicator 1.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage children 6-23 months consuming a minimum acceptable diet (MAD) | Planned | See tab | 0 | Nutrition sensitive social protection intervention designed Pregnant and lactating SCTP benficiaries targetted | Nutrition sensitive social protection intervention designed Pregnant and lactating SCTP benficiaries targetted | 27% | 32% | 40%
|  | Achieved | See tab |  | Completed. Baseline established at 18%
Source
IFPRI/WFP CSP Baseline/SMART Surveys/UN Consortium October Survey
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Number of farmers that received agricultural inputs to promote increased productivity during the reporting year - Annual target | Planned | See tab | 0 | 27337.5 | 27337.5 | 60750 | 60750 | 33412.5
|  | Achieved | See tab |  | 26,458 (16,984F, 9,474M) farmers
[5 empty] | Source |  |  |  |  | RISK RATING
|  | Routine Programme Data Records | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 19000000 |  | 0 | 0 |  |  |  | 19000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 2 | Output Indicator 2.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Enhanced and inclusive access to the productive resources necessary to develop increased, secure and predictable incomes. | Number of market system actors that invest in pro-poor business models | Planned | See tab | 0 | 4 | 4 | 8 | 10 | 12 | New climate resilient business opportunities are viable in the project context; Market actors respond positively to incentives unlocked by PROSPER and are willing to absorb and act on new knowledge and business practices. Insurance products are afffordable and lead to producers being less risk averse in their decision making and increase investment | Output 2.1 : Targets are cumulative based on a total of 12 private sector stakeholders, including 4 in Year 1, with additional 4 in Year 2, 2 in Year 3, and 2 in Year 4. Output 2.2 Target of 94,500 is the total number of people reached by Kadale inputs and services interventions. This number is then reduced by 16.66666%* to discount the poor people who have accessed and used the inputs, but have not experienced income change as a result of this input access/use. Therefore, reducing the output target of 94,500 by 16.66666% we get Kadale's target on outcome level of 78,750 (then counting each individual as a head of a household to align with NGO targets for households). *The discount of 16.66666% is based on findings from MOST. Output 2.3 Target based on total population reached through VSL activities. This group is expected to benefit from at least one financial product the programme is offering through CUMO work.
|  | Achieved | See tab |  | 5
Source
Quarterly reports from implementing agencies
| Output Indicator 2.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of poor people with increased access to productivity or income enhancing inputs or services /markets | Planned | See tab | 0 | 15000 | 15000 | 24000 | 55000 | 94500
|  | Achieved | See tab |  | 59,069 (24,708F, 34,361M) poor people
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output indicator 2.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Number of households with access to financial services as a result of DFID support (DFID Global Indicator List) | Planned | See tab | 0 | 20250 | 20250 | 40500 | 60750 | 60750
|  | Achieved | See tab |  | 72,276 (21,663M, 50,613F) households
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 8500000 |  | 0 | 0 |  |  |  | 7500000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Vulnerable households and communities in targeted areas have reduced exposure to drought and floods | Number of people supported by DFID programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines | Planned Direct | See tab | 0 | 313240 | 313240 | 541930 | 541930 | 541930 | Cooperation with District Natural Resource teams, technical skills in catchment planning and irrigation scheme development are available, timely procurement of materials for implementation of works during appropriate seasons; institutions established by the programme for managing water and forest are functional and equitable. Humanitarian stakeholders willing to be coordinated; appropriate insitutitional arrangements can be established to enable rapid response. | Output 3.1 Indicator will track direct and indirect individuals receiving high and medium intensity support respectively. Targets for direct beneficiaries based on total number of individuals receiving direct support from PROSPER (123,166 HH * 4.4 individuals per HH). Year 1 targets based on Cohort 1 of 45% of SU/SO plus all HI in Year 1, adding Cohort 2 of 55% of SO/SU in Year 2 to reach 100% of SU/SO. Target maintained for four years. Indirect beneficiaries calculated based on population within the target PROSPER TA who will benefit from PROSPER activities and institutional capacity building at TA level but are not direct programme beneficaries. Data taken from NSO 2018 Census, including population totals and annual population growth rates. Output 3.2 Milestones calculated based on estimation of 200 ha per watershed, with 14 watersheds targeted within NGO programme - included forest areas and beneficiary fields (watershed delineation completed June 2019). INGO reaching a total of 2,800ha and UN 6,992 ha. Targets are based on the amount of land wherein restorative measures are planned based on resources allocated. Output 3.3 Target is expected to be 100% of the HH identified in need of assistance. Output 3.4 Target percentage expected to increase as more people are reached by shock responsive social protection. This indicator will be measured according to the use of government social protection systems where money is also channeled through government. This is only taking into consideration districts above 20% IPC and these targets are subject to be revised based on donor funding via government and the appropriateness of cash as a modality each year. This indicator covers the entire country, not just the four PROSPER districts because it is linked to the crisis modifier. Output 3.5 Milestones will be calculated based on the risk assesment and risk mapping to identify the population being supported by mitigation works
|  | Planned Indirect | See tab | 0 | 715961 | 715961 | 507303 | 527914 | 549119
|  | Achieved Direct | See tab |  | 355,039 direct (180,001F, 175,038M)
|  | Achieved Indirect | See tab |  | 516,648 indirect (261,941F, 254,707M)
Source
Quarterly reports from implementing agencies
| Output Indicator 3.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved | Planned | See tab | 0 | 4400 | 4400 | 5400 | 6792 | 9792
|  | Achieved | See tab |  | 5799
Source
Programme Data, delineation, hotspot mapping and follow up measurement (remote sensing and other tools)
| Output Indicator 3.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of people reached during the lean season response with cash transfers - Annual target | Planned | 150000 |  | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020) | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020) | Numbers of people reached and policy objectives will be determined for each season once MVAC figures are known (July 2020)
|  | Achieved | 134400 |  | 155,000 people reached
Source
MVAC
| Output Indicator 3.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Planned | See tab | 0 | 20% | 20% | 30% | 40% | 50%
|  | Achieved | See tab |  | 35.09%
Source
MVAC and UBR data
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
25 | Household(s) using EWS and climate information for floods and droughts to reduce risks to their lives and or property | Planned | See tab | 0 | 32516 | 32516 | 65032 | 97548 | 162579
|  | Achieved | See tab |  | 28,666HH (9,780M and 18,886F)
|  | Source | [7 empty] | RISK RATING
|  | Impact Survey , District Reports | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| £22,000,000 (+£20million crises modifer) |  | 0 | 0 |  |  |  | £22,000,000 (+£20million crises modifer) | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 4 | Output Indicator 4.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. | Number of districts with integrated coordination, monitoring and social accountability systems for social protection/resilience and emergency interventions | Planned | See tab | 0 | 2 | 2 | 4 | 4 | 4 | Combined efforts of partners on district capacity strengthening will have measurable effects Coordination of PROSPER partners will enable coordination across all actors and empower districts to gain greater capacity for integrated coordination Combined efforts of BRACC partners on district capacity strengthening will have measurable effects Shock-responsive social protection will have demonstrable positive outcomes from the 2019 season that will encourage systems investment in subsequent years | Output 5.1 Qualitative survey of district stakeholders on the existence and quality of integrated coordination, monitoring systems and social accountability systems for a) social protection b) resilience programmes and c) emergency interventions. Output 5.2 The process will involve collection of baseline data against all 8 targets of the Sendai framework, setting up of data collection systems and systematic collection of data to track progress in implementing the Sendai framework for DRR. This work will be linked to MGDS and National resilience strategy. Currently 9 districts in Malawi meet this criteria, but none are the four PROSPER districts. Output 5.3 Targets set to achieve beyond 4 PROSPER for lean-season : Key shock responsive features include : 1) preparednessof the service provider, 2) developed targeting procedure 3) scalable data management systems 4) scalable grievances mechanisms 5) processes informing or triggering a scale-up 6) clarification of funding channels 7) a developed communication strategy for a scale-up 8) a developed M&E Framework
|  | Achieved | See tab |  | 2
Source
Partner reports; District Coordinator reports
| Output Indicator 4.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of districts development plans that implement local disaster risk reduction strategies in line with the Sendai Framework for Disaster Risk Reduction 2015-2030 | Planned | See tab | 0 | - | 2 | 4 | 4 | 4
|  | Achieved | See tab |  | -
Source
Reports submitted by the Government of Malawi to inform the accomplishment of Sendai Framework reporting
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Number of shock-responsive features of key social protection programmes put in place within the Malawi social protection programme (preparedness) | Planned | See tab | 1 | 2 | 2 | 3 | 5 | 6
|  | Achieved | See tab |  | 2
|  | Source | [7 empty] | RISK RATING
|  | MNSSP Reporting cycles, program reports, donors reports | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 3000000 |  | 0 | 0 |  |  |  | 3000000 | 100
INPUTS (HR) | DFID (FTEs)
3
OUTPUT 5 | Output Indicator 5.1 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22) |  | Assumptions
A strengthened and more shock sensitive social protection system | No districts where 50% of SCTP and PWP beneficiary households received their transfers through e-payments | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 1 | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | In 4 districts beneficiary households in at least one traditional authority have received their transfer through e-payments at least once | 7 districts |  | Existsing strong political will to reduce extremen poverty Funding for social protection programmes is available on time at central and district level. Public Works with the focus on watershed manage-ment continues. Line Ministries and donors remain interested in improv-ing coordination and harmonization in the area of social protection.
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Completed
Source
Analysis of payment data in SCT and PW MIS
| Output Indicator 5.2 |  | Inception (06/19) | Milestone 1 (03/20) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
| No districts where 70% of the total complaints submitted have been closed according to the guidelines. | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 0 | Magomero training course for extension workers is developed Outline of the Implementation Manual has been agreed Harmonized greivance and redress mechanisms developed | Maglomero training course for extension workers is developed Outline of the Implementation Manual has been agreed Harmonized greivance and redress mechanisms developed | Grievance and Redress mech-anism awareness and sensitization is undertaken in 2 districts and District officers are trained on complaint mecha-nism | 3
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Patrially completed
Source
Analysis of GRM data
| Output Indicator 5.3 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
| No. of additional social protection beneficiary households (out of which at least 55 % are female-headed house-holds) twhich are purposively linked to complementary interventions (e.g. livelihood projects and nutri-tion-sensitive interventions) through tools developed by the programme. | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 0 | Development of a project implementation manual Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | Development of a project implementation manual Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | 2000 | 10000
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Patrially completed
Source
Analysis of SCT and PWP MIS and Unified Beneficiary Registry (UBR)
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Inception (06/19) | Baseline (09/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Target (08/22)
5 | No of micro–watersheds where watershed rehabilitation activities have been implemented by communities as part of Public Works activities and according to the implementation plan, e.g. Village Action Plan (VAP). | Planned | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 8 | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 12 | 24
|  | Achieved | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019 |  | Patrially completed
|  | Source | [7 empty] | RISK RATING
|  | Analysis of register for peo-ple regarding number of days and number of volunteers in the micro-catchments; Documentation of completed activities by community wa-tershed committees and comparison with the imple-mentation plan (e.g. VAP). | [7 empty] | HIGH
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| 5000000 |  | Germany £7,158,160 | 0 | EU :£2,681,431 |  |  | 14839591 | 34
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 6 | Output Indicator 6.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods | No of people with livelhood co-benefits from improved forest management | Planned | See tab | 0 | DCA agreed with USAID African Parks Baseline Assesment Report completed; and livelihoods projects in each park identified. | MCHF NR based value chains have been analysed and early stage innoavtors identified and selected | Milestones set annually in December 2020 | Milestones set annually in December 2021 | 70000 | Natural resource based entreprises can be identified and create sufficient incentives for improved forest management Co-management agreements can be agreed between private sector, communities and local authorities in targeted landscapes
|  | Achieved | See tab |  | Completed
Source
Quarterly reports from implementing agencies
| Output Indicator 6.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| No hectares of degraded landscapes under improved management | Planned | See tab | 0 | 0 | MCHF Target landscapes identify and delineated, restoration opportunites assessed | Milestones set annually in December 2020 | Milestones set annually in December 2021 | 16000
|  | Achieved | See tab |  | 0
Source
Quarterly reports from implementing agencies
| Output Indicator 6.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Tons of sustainable charcoal produced | Planned | See tab | 0 | 0 | PEA on charcoal value chain completed | Milestones set annually in December 2020 | Milestones set annually in December 2021 | 11000
|  | Achieved | See tab |  | 0
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output Indicator 6.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Planned | See tab | 0 | 0 | Finance and investment for FE and AE sectors mobilised through programme and non programme sources | Milestones set annually in December 2020 | Milestones set annually in December 2021 | $2million
|  | Achieved | See tab |  | 0
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 5000000 |  | 0 | 0 |  |  |  | 5000000 | 100
INPUTS (HR) | DFID (FTEs)
2.5
OUTPUT 7 | Output Indicator 7.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions
More effective, coordinated and targeted, Government and donor investments | No. of politically responsive technical assistance workstreams developed and under active implementation using adaptive management principles | Planned | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) | 0 | Contract with KPM has been awarded Handover of evaluation activities complete Contract inception phase activities on track | Contract with KPM has been awarded Handover of evaluation activities complete Contract inception phase activities on track | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured | Opportunities for TA are identified; Sufficient senior level support from DFID and UK Diplomatic Representation is available to shape influential workstreams; There is enough political feedback and flexibility in contracting to enable the facility to be responsive to the most relevant opportunities.
|  | Achieved | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) |  | Completed
Source
IFPRI project reports/ Final ToRs
| Output Indicator 7.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| # of days of technical assistance provided / average fee rate per day in £ | Planned | Impact Evaluation design complete and QA'd by EQUALs Baseline survey complete | 0 | Baseline survey analysis completed and outcome milestones agreed Resilience learning event completed Programme governance agreed and have met at least once | Baseline survey analysis completed and outcome milestones agreed Resilience learning event completed Programme governance agreed and have met at least once | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured
|  | Achieved | Impact Evaluation design complete and submitted to EQUALs Baseline survey not yet complete (expected August) |  | Completed
Source
IFPRI project reports
IMPACT WEIGHTING (%) | Output Indicator 7.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
10 | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 10 (monthly maize market reports, rapid analytics, policy brief) | 12 | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | TBD once longer KPM procured | TBD once longer KPM procured | TBD once longer KPM procured
|  | Achieved | 12 |  | 24
|  | Source | [7 empty] | RISK RATING
|  | IFPRI project reports | [7 empty] | HIGH
INPUTS (£) | DFID (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | DFID SHARE (%)
| 8000000 |  | 0 | 0 |  |  |  | 8000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
| O)utput 1 | 19
| Output 2 | 8.5
| Output 3 | 22
| Crisis modiifer | 20
| Output 4 | 3
| Output 5 | 5
| Output 6 | 5
| Output 7 | 8

## Logical Framework - Inception
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in atarget districts living below the national poverty line of less than $1 a day | Planned | TBD during baseline survey | 0 | Will not be collected | 5% decrease (TBD during baseline) | Will not be collected | 10% decrease (TBD during baseline)
|  | Achieved |  | 0
Source
Programme baseline survey/Mid line survey/ end line survey
| Impact Indicator 2 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| % of targeted households passing through 12 months where all household members eat two meals a day with food from their own production or purchased with their own funds | Planned | TBD during baseline survey | 0 | Will not be collected | 20% increase (TBD during baseline) | Will not be collected | 40% increase (TBD during baseline)
|  | Achieved |  | 0
Source
IFPRI led Programme baseline survey/Mid line survey/ end line survey. Will not be collected annually.
OUTCOME | Outcome Indicator 1 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023) | Assumptions
Strengthened resilience of the targeted 300,000 poor and vulnerable households (around 1.7million people) to withstand current and future weather and climate related shocks and stresses | Number of people whose resilience has been improved as a result of project support (ICF KPI 4) | Planned | 0 | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | 1300000 | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts.
|  | Achieved |  | 0
Source
Resilience index to be developed during inception phase according to ICF methodological guidance. Data to come from baseline household survey. Likely to include the requirement to adopt multiple interventions that show use of weather or early warning data, livelihood diversification, adoption of CSA practices and increases in assets and savings)
| Outcome Indicator 2 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Value of assets held by beneficiaries and average difference between programme beneficiaries and matched non-beneficiaries (Baseline MKW values, disagregated by cash savings, productive assets, total values disaggregated by gender of household head) | Planned | TBD during baselines survey | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | 0
Source
Household survey;impact assessment design
| Outcome Indicator 3 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Value of crop produced by programme beneficiaries and matched non-beneficiaries (disagregated by gender of household head) (Baseline MKW values, disagregated by gender of household head); % of the value of crops produced coming from maize. | Planned | TBD during baselines survey | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | 0
Source
Household survey;impact assessment design
| Outcome Indicator 4 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| % of direct beneficiary households who report using long-term, seasonal, or short-term weather information to inform livelihood decisions | Planned | TBD during baselines survey | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | 0
Source
Household survey;impact assessment design
| Outcome Indicator 5 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| % of households engaged in off-farm business (disagregated by gender of household head and gender of main business owner within household) | Planned | TBD during baselines survey | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | 0
Source
Household survey;impact assessment design
| Outcome Indicator 6 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Percentage of households receiving humanitarian assisstance (recorded as MVAC beneficiary) in operational areas compared to those in matched areas not under the prgoramme or other similar interventions | Planned | TBD during baselines survey | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | 0
Source
Household survey;impact assessment design
| Outcome Indicator 7 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Level of influence of the programme on key Government and other donor investment decisions at district and national level | Planned | TBD during baselines survey | 0 | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | 0
Source
A rubric setting out the changes expected across different policy areas of interest will be developed and progress measured qualitatively using that rubric
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£)
| 70000000 |  | 0 | 0 |  |  | 70000000
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023) | Assumption
At least 300,000 households supported to build assets, access more diverse income streams, and improve their capacity to adapt to long-term climate changes | Number of people supported to cope with the effects of climate change (Disaggregated by gender of hh head/gender of registered individual beneficiary and by Social Protection status - i.e. social cash transfer or public works beneficiaries) (ICF KPI 1) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | 300,000 HH | Programme delivery can sustain current rate of progress with scale out of VSL and CSA technologies; basic seed is available to enhance local seed supply for diverse crops, new climate resilient business opportunities are viable in the project context; infromation is available from national meterological services that is relevant and of sufficient quality to disseminate.
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 1.2 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Number of direct beneficiaries (individuals) participating in Village Savings and Loans Schemes supported by the project (disaggregated by gender) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 1.3 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Number of direct beneficiaries (individuals) supported with training and information about climate smart agricultural techniques and linked to sources of relevant seed (disaggregated by gender) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 1.4 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Number of direct beneficiaries (individuals) supported to develop a new climate resilient business opportunities (disaggregated by gender) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 1.5 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Number of women and men participating in activities designed to promote gender equality in intra-household decision making focused on both social and economic factors. Number of GVH covered by activities to monitor and raise awareness of risk factors for women and girls (e.g. Violence against women, early marriage) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 1.6 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| Level of feedback from community / social accountability mechanisms that is collected and extent to which it influences programme implementation | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Rubric to be developed in inception phase and in conjunction with implementing agencies
| Output Indicator 1.7 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| £ per beneficiary reached with VSL, agriculture, business development, weather forecast | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
IMPACT WEIGHTING (%) | Output Indicator 1.8 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
25 | % direct beneficiary households regularly receiving short-term and seasonal weather forecasts, engaging in participatory scenario planning and aware of long-term climate change trends | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
|  | Source | [6 empty] | RISK RATING
|  | Household survey | [6 empty] | LOW
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| 20000000 |  | 0 | 0 |  |  | 20000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023) | Assumptions
At least 300,000 vulnerable households have reduced exposure to drought and floods because natural resources are managed sustainably | # of hectares covered by catchment management plans supported by this programme (disagregated by those under implementation) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase | Cooperation with District Natural Resource teams engaged in national public works planning is feasible, technical skills in catchment planning and irrigation scheme development are available, timely procurement of materials for implementation of works during appropriate seasons; institutions established by the programme for managing water and forest are functional and equitable.
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 2.2 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| # of individuals remunerated for labour on catchment implementation (disagregated by programme managed/public works programme leveraged) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 2.3 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| # of District Government natural resource teams provided with technical support and social accountability processes to improve delivery under the national PW programme | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | 10
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 2.4 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| # of hectares under irrigation schemes supported by the programme (disagregated by rehabilitated and newly developed schemes) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 2.5 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| # of beneficiary households supported to access irrigation or farming on protected dambo land (disagregated by gender of household head and registered beneficiary) | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
| Output Indicator 2.6 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| # of indirect beneficiaries benefitting from reduced exposure to shocks through living in improved catchments | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
Programme monitoring records
IMPACT WEIGHTING (%) | Output Indicator 2.7 |  | Baseline (July 2019) | Inception milestones) (June 2019 | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
25 | £ per hectare afforested; £ per hectare under irrigation/household in irrigation farming; £ per km of bund constructed, £ per m3 gulley rehabilitated. | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
|  | Source | [6 empty] | RISK RATING
|  | Programme monitoring records | [6 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| 20000000 |  | 0 | 0 |  |  | 20000000 | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023) | Assumption
Vulnerable districts implement contingency planning, early warning systems, improved assessment of humanitarian need and response simulations resulting in faster and better targeted response to shocks | No of GVHs with both a functional Civil Protection Committee and functional EWS | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase | ADDRMOs are retained in the civil service; delivery agent has sufficient credibility with the District to engage them in the design and implementation of the plans and contingency mechanisms; other humanitarian stakeholders willing to be coordinated; appropriate insitutitional arrangements can be established to enable rapid response.
|  | Achieved |  | See tab
Source
Definition to be agreed in programme inception and monitored by the M&E agency in a separate institution sample survey
| Output Indicator 3.2 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| No of districts with an improved Disaster Risk Management system, including increased capacity to manage pre-positioned supplies, enhanced staff skills for improved assessment and response management. | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | 6
|  | Achieved |  | See tab
Source
Definition to be agreed in programme inception and monitored by the M&E agency in a separate institution sample survey
| Output Indicator 3.3 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| No of districts in which Government / other stakeholders delivering response to rapid onset crises within 24 hours and/or response to slow-onset crises using 'resilient response' approaches on a timely basis | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | 6
|  | Achieved |  | See tab
Source
"Resilient response" to include support to reducing food aid requirements and to be defined in inception phase; monitoring to come from M&E Agency institution sample survey
| Output Indicator 3.4 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| £ per CPC supported | Planned | 0 | Inception phase activities completed (see sebarate tab) | TBD in inception phase | TBD in inception phase | TBD in inception phase | TBD in inception phase
|  | Achieved |  | See tab
Source
"Resilient response" to include support to reducing food aid requirements and to be defined in inception phase; monitoring to come from M&E Agency institution sample survey
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
25 | No. of people/year supported with DFID-funded shock response/ £ per beneficiary | Planned | 0 | 150000 | 150000 | 150000 | 150000 | 150000
|  | Achieved |  | 134400
|  | Source | [6 empty] | RISK RATING
|  | Partner reporting | [6 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| £19,200,000 (£14million of which is shock response) |  | £19,200,000 (£14million of which is shock response) | 0 |  |  | £19,200,000 (£14million of which is shock response) | 100
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 4 | Output Indicator 4.1 |  | Baseline ( September 2018) | Inception/Mobilisation phase (June 2019) | Milestone 1 (Sept 2019) | Milestone 2 (Sept 2020) | Target (Sept 2021) |  | Assumptions
The system for the implementation of the MNSSP II is strengthened and more shock sensitive | No districts where 50% of SCTP and PWP beneficiary households received their transfers through e-payments | Planned | 1 | MOU with GIZ in place Joint GIZ, EU, DFID programme launch | MNSSP II implementation plan complete UBR data sharing app developed SOPs for scaleable harminized e-payment mechanism developed ToRs for social protection commitees adopted | In 4 districts beneficiary households in at least one traditional authority have received their transfer through e-payments at least once | 7 |  | Existsing strong political will to reduce extremen poverty Funding for social protection programmes is available on time at central and district level. Public Works with the focus on watershed manage-ment continues. Line Ministries and donors remain interested in improv-ing coordination and harmonization in the area of social protection.
|  | Achieved |  | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019
Source
Analysis of payment data in SCT and PW MIS
| Output Indicator 4.2 |  | Baseline ( September 2018) | Inception/Mobilisation phase (June 2019) | Milestone 1 (Sept 2019) | Milestone 2 (Sept 2020) | Target (Sept 2021)
| No districts where 70% of the total complaints (by gender) submitted have been closed according to the guidelines. | Planned | 0 | 0 MOU with GIZ in place Joint GIZ, EU, DFID programme launch | Maglomero training course for extension workers is developed Outline of the Implementation Manual has been agreed | Grievance and Redress mech-anism awareness and sensitization is undertaken in 2 districts and District officers are trained on complaint mecha-nism | 3
|  | Achieved |  | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019
Source
Analysis of GRM data
| Output Indicator 4.3 |  | Baseline ( September 2018) | Inception/Mobilisation phase (June 2019) | Milestone 1 (Sept 2019) | Milestone 2 (Sept 2020) | Target (Sept 2021)
| No. of additional social protection beneficiary households (out of which at least 55 % are female-headed house-holds) twhich are purposively linked to complementary interventions (e.g. livelihood projects and nutri-tion-sensitive interventions) through tools developed by the programme. | Planned | 0 | 0 MOU with GIZ in place Joint GIZ, EU, DFID programme launch | Electronic tool for district development planning developed and being used Districts supported with instruments and guidelines on graduation pathways | 2000 | 10000
|  | Achieved |  | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019
Source
Analysis of SCT and PWP MIS and Unified Beneficiary Registry (UBR)
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline ( September 2018) | Inception/Mobilisation phase (June 2019) | Milestone 1 (Sept 2019) | Milestone 2 (Sept 2020) | Target (Sept 2021)
15 | Community ownership of community assets created under public works is enhanced - measured through no of micro–watersheds where watershed rehabilitation activities have been implemented by communities in addition to the Public Works activities according to the implementation plan, e.g. Village Action Plan (VAP). | Planned | 8 | 8 MOU with GIZ in place Joint GIZ, EU, DFID programme launch | 9 watershed management commiitees are established and trained on watershed management and CC adaptation | 12 | 24
|  | Achieved |  | MOU with GIZ in place Joint GIZ, EU, DFID programme launched in May 2019
|  | Source | [6 empty] | RISK RATING
|  | Analysis of register for peo-ple regarding number of days and number of volunteers in the micro-catchments; Documentation of completed activities by community wa-tershed committees and comparison with the imple-mentation plan (e.g. VAP). | [6 empty] | HIGH
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 5000000 |  | 0 | Germany £7,158,160 | EU :£2,681,431 |  | 14839591 | 34
INPUTS (HR) | DFID (FTEs)
3.5
OUTPUT 5 | Output Indicator 4.1 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023) | Assumptions
DFID, Government and donor investment is better targeted to climate resilience | No. of politically responsive technical assistance workstreams developed and under active implementation using adaptive management principles | Planned | 0 | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete) | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured | Opportunities are identified; sufficient senior level support from DFID and UK Diplomatic Representation is available to shape influential workstreams; there is enough political feedback and flexibility in contracting to enable the facility to be responsive to the most relevant opportunities.
|  | Achieved |  | AG awarded to IFPRI to serve as interim KPM Procurement of long term policy and knowedge manager underway (TORs complete)
Source
IFPRI project reports/Final ToRs
| Output Indicator 4.2 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
| # of days of technical assistance provided / average fee rate per day in £ | Planned | 0 | Impact Evaluation design complete and QA'd by EQUALs Baseline survey complete | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured
|  | Achieved |  | Impact Evaluation design complete and submitted to EQUALs Baseline survey not yet complete (expected August)
Source
IFPRI project reports
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (July 2019) | Inception/Mobilisation phase (June 2019) | Milestone 1 (April 2020) | Milestone 2 (April 2021) | Milestone 3 (April 2022) | Target (April 2023)
10 | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 0 | 10 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | TBD once longter KPM procured | TBD once longter KPM procured | TBD once longter KPM procured
|  | Achieved |  | 12
|  | Source | [6 empty] | RISK RATING
|  | IFPRI project reports | [6 empty] | HIGH
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | Total (£) | DFID SHARE (%)
| 4800000 |  | 0 | 0 |  |  | 0 | 100
INPUTS (HR) | DFID (FTEs)
3.5

## Inception phase milestones
Inception/mobilisation Phase for Output 1, 2 and 3
Inception Phase Activities as outlined in the BC | Milestone for end of inception phase (end March 2019) | Achieved
Procurement of partners | Call for proposals run and agreements in place with partners | Completed
Start-Up Activities | Develop and sign consortium accountable grant agreements with downstream partners. Recruit and induct staff. | Almost complete - Agreements signed; and most staff recruited, but some positions not yet in post (expected by end July)
Government engagement | Engagement and consultation with National and district level government | Completed; and ongoing
Orientation and Design Refinement Workshop | All BRACC consortium members to participate in a design workshop to expand on key areas including: coordination, M&E, Complaints and Feedback Response Mechanisms (CFRMs), targeting, packages of interventions by household category, community engagement processes, graduation linkages, integration of MSD across all household categories. | Completed
Confirm Programme Locations | Confirm target TA/GVHs and watersheds | Completed - but there were large delays
Confirm Intervention packages | Using evidence from Malawi and globally, all BRACC consortium members will finalize intervention packages to be implementedby the programme.. For innovative interventions, BRACC will clearly set out an approach to monitoring success; and scaling up what works and stopping what doesn’t. | Completed
Targeting: | BRACC will work with component 4 to outline, refine and implement targeting approach | Targetting not yet completed (expected by end July)
CFRMs | Establish and/or strengthen CFRMs for the BRACC programme | Completed
M&E | Develop consistent tools, M&E framework, and procedures across the BRACC programme in collaboration with IFPRI. Agreeing Value for Money indicators to be tracked on an annual basis | Not yet complete (expected be end July)
Governance arrangements | Establish standard operating procedures (SOPs) which clarify the roles of each of the partners for M&E, CFRM, targeting etc…. Agree internal and external structures and prepare Terms of reference for each committee | Not yet complete (expected be end July)
Explore linkages with other DFID programmes | In particular Bwith the Violence Against Women and Girls (VAWG) to ensure BRACC has a strong approach to tackling GBV issues; and new transparency and accountability programme (TRACTION) to enable BRACC to draw on additional political economy analysis, and inform how BRACC might support wider ‘coalitions for change’ to tackle intractable issues such as maize market/seed reforms; and DFID work and advice on disaster risk financing, provided by the new UK/WB Centre for Global Disaster Prevention. | Completed; and ongoing
Programme activities | Conduct initial activities to facilitate the implementation of the package of interventions at the start of Year 1 (commencing from 01 Apr 2019). These will include activities such as mapping business opportunities and identifying initial portfolios of private sector partners and actions; watershed mapping, assessments and planning through participatory community based approaches, consultation with district government and local leaders, sensitisation and orientation of target communities to the programme (conducted hand in hand with the targeting exercises), and procurement of programme assets to support implementation. | Completed

## Logical Framework-2023
PROJECT NAME | Breaking the cycle of crises in Malawi
IMPACT | Impact Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
A reduction in extreme poverty and an end to the recurrent cycle of hunger and humanitarian assistance in Malawi | Percentage of the population in target districts living below the national poverty line | Planned |  | 64.41 |  |  |  |  | 2.5% decrease |  | The % below the national poverty line accoring to the IHS4 are Phalombe: 83.2, Chikwawa 63.2, Balaka 61.3, and Mangochi 59.5. The weighted average for the four districts 64.41. The target has been set at a 5% decrease from the baseline at the end of the programme. Triangulation of data from similiar national programmes and survey shows that at most 5% decrease is attainable. The programme does not expect significant change by 2021 in the targeted population but will review data for IHS5 and replace the baseline with those figures for accuracy; therefore,no target has been set for Milestone 2 . Data for 2023 is expected from IHS6. It was agreed that the final reporting will fall outside the programme timeline. The programme will use any interim poverty data that becomes available to course correct.
Achieved
Source
NSO IHS data (available every 3 years). If WB Implement SWIFT we may be able to get more regular data points
| Impact Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) |  | Comments on Indicators and Targets
| Difference in difference comparison of targeted TAs and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) | Planned |  | - | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs | % change in PROSPER TA always < Non PROSPER TAs |  | 2019 MVAC results will be used for baseline. The programme aims to maintain greater than or equal to IPC Baseline figures; the data will be used to make a difference in difference comparison betweeen PROSPER TA's and non PROSPER TA's to ascertain the effect of the programme. The programme will strive to have this percentage decrease beyond zero (into negative %).
|  | Achieved |  |  | -0.19 | -0.19 | -11.67 | -84%
Source
MVAC annual assessments (annual - usulaly available in August)
OUTCOME | Outcome Indicator 1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Strengthened resilience of the targeted poor and vulnerable households to withstand current and future weather and climate related shocks and stresses | Number of people whose resilience has been improved as a result of project support (ICF KPI 4)* *Using WFP Methodology | Planned | 0 | From Resilience Index | Not yet measurable | Baselines and milestones established | 20% of households | 30% of households | 35% of households | Resilience interventions are adopted by programme beneficiaries and result in their ability to retain assets, increase crop production and run sustainable businesses. Households find the available climate and weather information accessible, timely and relevant for their production decisions. Households have the knowledge/labour/capital requirements to implement these decisions. Humanitarian response decisions are not unduely influenced by political priorities obscuring programme impacts. | Outcome Indicator 1 - Targets for number improving resilience will be set after baseline figures for the resilience index indicators are available. This is dependant on IFPRI baseline data which is expected between December 2019 and end of January 2020. Based on the baseline, the programme calculate anticipated numbers of households with improvemed resilience each year and set yearly milestones. Outcome Indicator 2 - GBP 7.28m is based on the incremental income attributable to PROSPER Markets work.This could be as a result of interventions for inputs, services or markets availed to participants. Estimates for cumulative increase in income from PROSPER INGO interventions (CSA, input fairs, livestock, irrigation)will be calculated from the % increase in yield sold as surplus. Targets for this will be calculated using IFPRI baseline results on current farmer yield in the targeted districts once baseline data is available. SU/SI are expected to increase yields and have sufficient surplus to sell. Outcome Indicator 3: The CARI index will be used: it is a composite indicator including Food Consumption Score, Food Expenditure Share and Livelihood Coping Strategies. The calculation provides a representative estimate of food insecurity within the targetted population. Targets are awaiting IFPRI and WFP - CSP baseline results. Outcome indicator 4: For the targets PROSPER will calculate the change in yield based on a difference in difference comparison between the control and treatment arms of the Impact Evaluation. Target set by Year 4 as 35% increase, with 10% gain in Year 1, Year 2 and Year 3, and 15% gain in Year 4.
|  | Achieved | 0 |  | Not yet measurable | Baselines and milestones established. Baseline = 11%(n)( PROSPER 2020 Annual survey) | 25% | 25% | 72.8%
Source
WFP's survey-using their methodology
| Outcome Indicator 2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (10/20) | Milestone 3 (10/21) | Milestone 4 (10/22) | Target (10/23)
| Percentage of women between 15-49 reaching the minimum dietary diversity score | Planned | 0 | WFP baseline=26% |  | 26% | 38% | 43% | 50%
|  | Achieved | 0 |  |  | (29%, WFP PDM Survey) | (27%, WFP PDM Survey) **Same figure as October 2022, as this is when the annual survey was completed | 15% | 36%
Source
WFP CSP Baseline/SMART Surveys
| Outcome Indicator 3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| % Households classified as being marginally food secure or food secure, disaggregated by group (marginally and food secure) - Using CARI index | Planned | 0 | IFPRI=55.1%, WFP=58.4% | Not yet measurable | - | 60% | 63% | 66%
|  | Achieved | 0 |  | Not yet measurable | WFP PDM survey=54% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=78% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=62% (Balaka, Chikwawa, Mangochi and Phalombe) | WFP PDM Survey=53% (Balaka, Chikwawa, Mangochi and Phalombe)
Source
UN Survey, WFP CSP Baseline
| Outcome Indicator 4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Difference in difference comparison of change in yield of maize and other crops against the baseline figure in PROSPER and non-PROSPER target areas | Planned | 0 | (0%)IFPRI: Average Maize Yield=1,110 Kgs for treatment, 1311 Kgs for non PROSPER areas | Not yet measurable | 10% | 20% | 30% | 35%
|  | Achieved | 0 |  | Not yet measurable | PROSPER 2020 Annual survey = 760 kgs/ha for PROSPER treatment areas. 560 kg/ha median. | 949kg/ha Average Maize Yield for PROSPER treatment areas | 36% (a measure of households reporting over 200kg of maize harvested, which was 36%) | 24% (a measure of households reporting over 200kg of maize harvested, which was 24%)
Source
FAO and WFP Surveys
| Outcome Indicator 5 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of children 6-23 months consuming a minimum acceptable diet (MAD) | Planned |  | WFP baseline=3.5% |  | 5% | 10% | 15% | 20%
|  | Achieved |  | N/A |  | (7.9% WFP PDM Survey) | (4.5% WFP PDM Survey) | (3.6% WFP PDM Survey) | 5.6%
Source
IFPRI/WFP CSP Baseline/Smart Surveys/UN Consortium Survey
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (£)
| 90500000 |  | 0 | 0 |  |  |  | 90,5000,00
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 1 | Output Indicator 1.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Intensified and diversified agricultural production and improved nutrition for targeted vulnerable communities. | Percentage househods implementing Climate Smart Agriculture (CSA) practices | Planned | See tab | 0 | 42,525 individuals have received training in CSA | 21262.5 | 55% | 50% | 75% | Programme delivery can sustain current rate of progress with scale out of VSL and CSA technologies; cascade model of extension is effective; basic seed is available to enhance local seed supply for diverse crops, infromation is available from national meterological services that is relevant and of sufficient quality to disseminate. | Output 1.1 Milestones have been calculated as follows: The programme anticipates that for Milestone 1 60% of cohort 1 beneficiaries will implement at least 2 of the promoted pracrices, consecutively in YR 2 60% of Cohort 1 and 50% of Cohort 2 should see the benefits of using promoted GAPs, in Yr 3 75% of cohort 1 and 60% of cohort 2 should continue implementing 2 or more technologies and at the end of the programme, it is anticipated that 85% of cohort 1 and 75% of cohort 2 should be applying the technologies.These targets include HH also reached under the FFS where it is expected 50% of HH will implement CSA. Indicator to be measured based on 3 out of these factors: 1. Practice of Integrated Pest Management (IPM) 2. Inter-cropping with legumes, in maize fields. 3. Planting perennials and agroforestry species in crop fields. 4. Planting adaptive crop varieties (early maturing, drought tolerant.) 5. Conservation Agriculture (minimum tillage, mulching and use of herbicides). 6. Use improved storage facilities for the harvest. 7. Manure collection and production from livestock. 8. Use of disease resistant breeds under livestock. 9. Engaging in irrigation crop production. Output Indictor 1.2: Targets based on numbers of farmers reached through the FFS model to improve extension services. Output Indictor 1.3: Indicator will capture both number of programme participants disaggregated by sex and hectares under production in the targeted irrigation schemes receiving PROSPER support. Collecting area under production and dissagregating it by sex allows for consideration of intra-household gender nuances of ownership, access and distribution of resources. Output Indictors 1.4 The indicators should be revisited when the baseline is set to ensure they are ambitious yet achievable. The target is set at 50% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence more than half of the population in PROSPER areas -- both men and women influencing the MAD for women in the household. Output Indicator 1.5: The target is set at 40% of the population for this group based on the assumption that the revamped SBCC groups will reach and influence households in the PROSPER areas -- with more ground needing to be gained for young children's MAD. Output Indicator 1.6 These targets includes only SU beneficiaries. Milestone 1 is caculated based on 45% of SU (cohort 1), Milestone 2 ad 3 are 100% of SU (cohort 1 and cohort 2) while Milestone 4 is 55% of SU (cohort 2 only as cohort 1 subsidised inputs will phase out in Year 4)..
|  | Achieved | See tab |  | 78,253 (47,063F, 31,190M) individuals were trained in CSA practises | 37% (34,965hh - 12,587 FHH, 22,378 MHH) adopting CSA (6 or more practices), PROSPER 2020 Annual survey | Data not available - Annual Survey not undertaken due to ODA cuts | 74.6% adopted CSA (3 or more practices) | 89%
Source
WFP/FAO annual survey
| Output Indicator 1.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage farmers who report improvements in extension services received (by type of extension provider: public, community-based, private) | Planned | See tab | 49.5% of farmers receiving services | First cohort of FFS master training complete and FFS established in PROSPER areas Lead farmer training complete Private sector extension activities complete | 27000 | 47.87% | 51% | 90%
|  | Achieved | See tab |  | Completed | 30,240 The Annual Survey also found 49.5% of respondents reported receiving extension services. Of these, 64% reported improved extension services - which equates to a result of 32% when applied to whole population. So applying the 32% to the 94,500 farmers gives us 30,240 | Data not available - Annual Survey not undertaken due to ODA cuts | 89% Annual assessment survey findings, Dec 2022. As PROSPER has currently trained 2,404 community-based facilitators (CBFs) through farmers field schools, the outreach in terms of improved extension services has increased in the project locations. These CBFs are directly providing extension support to approximately 70,000 farmers | 92.8% With the provision of mobility support through bicycles and also provision of training materials to Community Based Facilitators (CBFs) in all project locations, the programme maximized the reach to follower farmers with extension services. FAO managed to train over 2,400 CBF who are supporting in the provision of extension services under the supervision of the 60 Master Trainers (MTs) also trained under the programme
|  | Source |  |  | Source
Partner's survey (WFP/FAO)
| Output Indicator 1.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Hectares of farm land under irrigation (disaggregated by size of scheme, type of technology) | Planned | See tab | 0 | Agreement with PumpAid in place Feasibility assessments and planning for irrigation schemes in identified areas complete | Irrigation activities underway for winter cropping season. Baseline and milestones established. | 303.4 | 102 | 117
|  | Achieved | See tab |  | Completed | Completed Baseline established at 12.6hectares | 379.94 | 52 | 205.81
|  | Source |  |  | Source
Programme Annual Survey
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 19000000 |  | 0 | 0 |  |  |  | 19000000 | 100
INPUTS (HR) | FCDO (FTEs)
3.5
IMPACT WEIGHTING (%) | Output indicator 2.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
10 | Number of households/individuals with access to financial services as a result of FCDO support (FCDO Global Indicator List) | Planned | See tab | 0 | 20250 | 20250 | 40500 | 20000 | 30700
|  | Achieved | See tab |  | 72,276 (21,663M, 50,613F) households | 72,276 (21,663M, 50,613F) households | 60670 | 25,867 (16,520F, 9,347M) | 31,135 (26,391F, 3,744M)
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 8500000 |  | 0 | 0 |  |  |  | 7500000 | 100
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 3 | Output Indicator 3.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumption | Comments on Indicators and Targets
Vulnerable households and communities in targeted areas have reduced exposure to drought and floods | Number of people supported by FCDO programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines | Planned Direct | See tab | 0 | 313240 | 313240 | 541930 | 541930 | 313429 | Cooperation with District Natural Resource teams, technical skills in catchment planning and irrigation scheme development are available, timely procurement of materials for implementation of works during appropriate seasons; institutions established by the programme for managing water and forest are functional and equitable. Humanitarian stakeholders willing to be coordinated; appropriate insitutitional arrangements can be established to enable rapid response. | Output 3.1 Indicator will track direct and indirect individuals receiving high and medium intensity support respectively. Targets for direct beneficiaries based on total number of individuals receiving direct support from PROSPER (123,166 HH * 4.4 individuals per HH). Year 1 targets based on Cohort 1 of 45% of SU/SO plus all HI in Year 1, adding Cohort 2 of 55% of SO/SU in Year 2 to reach 100% of SU/SO. Target maintained for four years. Indirect beneficiaries calculated based on population within the target PROSPER TA who will benefit from PROSPER activities and institutional capacity building at TA level but are not direct programme beneficaries. Data taken from NSO 2018 Census, including population totals and annual population growth rates. Output 3.2 Milestones calculated based on estimation of 200 ha per watershed, with 14 watersheds targeted within NGO programme - included forest areas and beneficiary fields (watershed delineation completed June 2019). INGO reaching a total of 2,800ha and UN 6,992 ha. Targets are based on the amount of land wherein restorative measures are planned based on resources allocated. Output 3.3 Target is expected to be 100% of the HH identified in need of assistance. Output 3.4 Target percentage expected to increase as more people are reached by shock responsive social protection. This indicator will be measured according to the use of government social protection systems where money is also channeled through government. This is only taking into consideration districts above 20% IPC and these targets are subject to be revised based on donor funding via government and the appropriateness of cash as a modality each year. This indicator covers the entire country, not just the four PROSPER districts because it is linked to the crisis modifier. Output 3.5 Milestones will be calculated based on the risk assesment and risk mapping to identify the population being supported by mitigation works
|  | Planned Indirect | See tab | 0 | 715961 | 715961 | 507303 | 527914 | 759852
|  | Achieved Direct | See tab |  | 355,039 direct (180,001F, 175,038M) | 355,039 direct (180,001F, 175,038M) | 435,960 (221,032F, 214,928M) | 305,833 (178,826F; 127,007M)7, | 305,833 (178,826F; 127,007M)
|  | Achieved Indirect | See tab |  | 516,648 indirect (261,941F, 254,707M) | 516,648 indirect (261,941F, 254,707M) | 647,320 (323,121F, 314,999M) | 759,852 (391,324F; 368,528M) | 759,852 (391,324F; 368,528M)
Source
Quarterly reports from implementing agencies
| Output Indicator 3.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Areas (ha) of degraded micro catchment/watershed rehabilitated/conserved | Planned | See tab | 0 | 4400 | 4400 | 3400 | 4792 | 12264
|  | Achieved | See tab |  | 5799 | 5799 | 14190 | 3011 | 7855
Source
Programme Data, delineation, hotspot mapping and follow up measurement (remote sensing and other tools)
| Output Indicator 3.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of people reached during the lean season response with cash transfers - Annual target | Planned | 150000 |  | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 96,295 - SP donors influenced to support VE - Response aligned to MVAC recommended modality | 500000 | 409239 | 409239
|  | Achieved | 134400 |  | 155,000 people reached | 155,000 people reached | 488340 | 168,246 (82,439M; 85,807F) | 409,239 reached
Source
MVAC
| Output Indicator 3.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need | Planned | See tab | 0 | 20% | 20% | 30% | 40% | 50%
|  | Achieved | See tab |  | 35.09% | 35.09% | 45.01% | 27% | 92%
Source
MVAC and UBR data
| Output Indicator 3.5 |  | Inception (06/19) | Basline (07/19) | Milesonte 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of people with access to flood evacuation centres during a flood occurrence | Planned | See tab |  |  |  |  | 2400 | 2400
|  | Achieved | See tab |  |  |  |  | 1995 | 1995
Source:
Impact Survey, District Reports
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
|  |  | 0 | 0 |  |  |  |  | 100%
INPUTS (HR) | FCDO (FTEs)
IMPACT WEIGHTING (%)
25
OUTPUT 4 | Output Indicator 4.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks. | Number of districts with integrated coordination, monitoring and social accountability systems for social protection/resilience and emergency interventions | Planned | See tab | 0 | 2 | 2 | 4 | 4 | 4 | Combined efforts of partners on district capacity strengthening will have measurable effects Coordination of PROSPER partners will enable coordination across all actors and empower districts to gain greater capacity for integrated coordination Combined efforts of BRACC partners on district capacity strengthening will have measurable effects Shock-responsive social protection will have demonstrable positive outcomes from the 2019 season that will encourage systems investment in subsequent years | Output 5.1 Qualitative survey of district stakeholders on the existence and quality of integrated coordination, monitoring systems and social accountability systems for a) social protection b) resilience programmes and c) emergency interventions. Output 5.2 The process will involve collection of baseline data against all 8 targets of the Sendai framework, setting up of data collection systems and systematic collection of data to track progress in implementing the Sendai framework for DRR. This work will be linked to MGDS and National resilience strategy. Currently 9 districts in Malawi meet this criteria, but none are the four PROSPER districts. Output 5.3 Targets set to achieve beyond 4 PROSPER for lean-season : Key shock responsive features include : 1) preparednessof the service provider, 2) developed targeting procedure 3) scalable data management systems 4) scalable grievances mechanisms 5) processes informing or triggering a scale-up 6) clarification of funding channels 7) a developed communication strategy for a scale-up 8) a developed M&E Framework
|  | Achieved | See tab |  | 2 | 2 | 4 | 6 | 4
Source
Partner reports; District Coordinator reports
| Output Indicator 4.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Number of Districts with functional Disaster Information Management System | Planned | See tab | 0 | - | 1 | 4 | 4 | 4
|  | Achieved | See tab |  | - | 1 | 4 | 4 | 4
Source
Reports submitted by the Government of Malawi to inform the accomplishment of Sendai Framework reporting
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
5 | Number of shock-responsive features of key social protection programmes put in place within the Malawi social protection programme (preparedness) | Planned | See tab | 1 | 2 | 2 | 4 | 5 | 6
|  | Achieved | See tab |  | 2 | 2 | 4 | 5 | 4
|  | Source | [7 empty] | RISK RATING
|  | MNSSP Reporting cycles, program reports, donors reports | [7 empty] | MEDIUM
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 3000000 |  | 0 | 0 |  |  |  | 3000000 | 100
INPUTS (HR) | FCDO (FTEs)
3
Analysis of register for peo-ple regarding number of days and number of volunteers in the micro-catchments; Documentation of completed activities by community wa-tershed committees and comparison with the imple-mentation plan (e.g. VAP).
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) | Other (£) |  |  | Total (£) | FCDO SHARE (%)
| 5000000 |  | Germany £7,158,160 | 0 | EU :£2,681,431 |  |  | 14839591 | 34
INPUTS (HR) | FCDO (FTEs)
3.5
OUTPUT 5 | Output Indicator 5.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions | Comments on Indicators and Targets
Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods | No of people with livelihood co-benefits from improved forest management | Planned | See tab | 0 | DCA agreed with USAID African Parks Baseline Assesment Report completed; and livelihoods projects in each park identified. | MCHF NR based value chains have been analysed and early stage innoavtors identified and selected | 5000 | 15000 | 96000 | Natural resource based entreprises can be identified and create sufficient incentives for improved forest management Co-management agreements can be agreed between private sector, communities and local authorities in targeted landscapes
|  | Achieved | See tab |  | Completed | Partially completed | 1802 | 29950 | 95078
Source
Quarterly reports from implementing agencies
| Output Indicator 5.2 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| No hectares of degraded landscapes under improved management | Planned | See tab | 0 | 0 | MCHF Target landscapes identify and delineated, restoration opportunites assessed | 0 | 3500 | 10000
|  | Achieved | See tab |  | 0 | Completed | Interim indicators completed | 9026 | 14720
Source
Quarterly reports from implementing agencies
| Output Indicator 5.3 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
| Tons of sustainable charcoal or alternative biomass energy produced | Planned | See tab | 0 | 0 | PEA on charcoal value chain completed | 0 | 0 | 4000
|  | Achieved | See tab |  | 0 | Partially completed | Interim indicators completed | 1500 | 536.80MT
Source
Quarterly reports from implementing agencies
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23)
20 | Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies | Planned | See tab | 0 | 0 | Finance and investment for FE and AE sectors mobilised through programme and non programme sources | 0 | $2million | $4million
|  | Achieved | See tab |  | 0 | Completed | Interim indicators completed | $2.756million | $5,459,201
|  | Source | [7 empty] | RISK RATING
|  | Quarterly reports from implementing agencies | [7 empty] | MEDIUM
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 5000000 |  | 0 | 0 |  |  |  | 5000000 | 100
INPUTS (HR) | FCDO (FTEs)
2.5
OUTPUT 6 | Output Indicator 6.1 |  | Inception (06/19) | Baseline (07/19) | Milestone 1 (03/20) | Milestone 2 (08/20) | Milestone 3 (08/21) | Milestone 4 (08/22) | Target (03/23) | Assumptions
More effective, coordinated and targeted, Government and donor investments | # of communications/evidence products generated by programme partners, including a publically accessible data/document store that can be handed over to GoM | Planned | 10 (monthly maize market reports, rapid analytics, policy brief) | 12 | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | 20 (monthly maize market reports, rapid analytics, policy brief) | Opportunities for TA are identified; There is enough political feedback and flexibility in contracting to enable the facility to be responsive to the most relevant opportunities.
|  | Achieved | 12 |  | 24 | 24 | 19 | 19 | 19
IMPACT WEIGHTING (%)
5 | Source | [8 empty] | RISK RATING
| IFPRI project reports | [8 empty] | HIGH
INPUTS (£) | FCDO (£) |  | Other (£) | Govt (£) |  |  |  | Total (£) | FCDO SHARE (%)
| 8000000 |  | 0 | 0 |  |  |  | 8000000 | 100
INPUTS (HR) | FCDO (FTEs)
3.5