## Annual Review Template

Title: Building Resilience and Adapting to Climate Change Programme (BRACC)
Programme Value £ (full life): £90.5 million		Review date: 22/02/2026
Programme Code : 300113	AMP start date: 18/07/2018	AMP end date: 31/10/2027

Summary of Programme Performance
Year	2019-20	2020-21	2020-21 Update	2021-22	2022-23	2024-25	2025-26
Overall Output Score	B	A	A	A	A	A	A
Overall programme risk rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300113/documents
DevTracker Link to results framework:	D0004472.xlsx

Acronyms	Definition
AA	Anticipatory Action
AMP	Aid Management Platform
BRACC	Building Resilience and Adapting to Climate Change Programme
CDF	Community Disaster Fund
CRCS	Climate Resilience Capacity Score
CS-EPWP	Climate Smart Enhanced Public Works Programme
DoDMA	Department of Disaster Management Affairs
DRMCs	Disaster Risk Management Committees
EOC	Emergency Operations Centre
EU	European Union
FAO	Food and Agriculture Organisation
FRA	Fiduciary Risk Assessment
GCMF	Global Commodity Management Facility
GoM	Government of Malawi
ICF	International Climate Finance
IFPRI	International Food Policy Research Institute
IPC	Integrated Food Security Phase Classification
JEFAP	Joint Emergency Food Assistance Programme
KPI	Key Performance Indicator
MDTF	Multi‑Donor Trust Fund
MCHF	Modern Cooking for Healthy Forests programme
NGO	Non‑Governmental Organisation
NLGFC	National Local Government Finance Committee
PFP	Programme‑Funded Post
PREPARE	WFP emergency preparedness and response
PROSPER	Promoting Sustainable Partnerships for Empowered Resilience
RCO	UN Resident Coordinator’s Office
SCTP	Social Cash Transfer Programme
UBR	Unified Beneficiary Registry
UN	United Nations
UNDP	United Nations Development Programme
UNICEF	United Nations Children Fund
USAID	United States Agency for Development
WFP	World Food Programme

A. SUMMARY AND OVERVIEW

Description of programme

The UK is investing up to £90.5 million over eight years (2018-2027) in the ‘Building Resilience and Adapting to Climate Change (BRACC) programme’. The long-term impact is to contribute to a reduction in extreme poverty and end the recurrent cycle of hunger and humanitarian assistance in Malawi. The outcome is strengthened resilience of an estimated 300,000 poor and vulnerable households (around 1.7million people) to withstand current and future weather and climate related shocks and stresses. The programme does this by developing scalable social safety net systems that respond more predictably and efficiently to weather and climate related shocks; improving livelihoods; and addressing environmental degradation. The programme has undergone major changes during the review period.

The programme has five main components. It supports (1) climate‑resilient livelihoods by helping vulnerable households cope with climate shocks through improving their: i.) access to weather information ii.) farming techniques iii.) management of natural resources, and iv.) diversifying their incomes. From 2021-2024, these activities were delivered through a UN consortium; in the past year, FCDO has funded an NGO consortium to work in targeted vulnerable districts. (2) A scalable safety‑net to respond to food insecurity, delivered through a standalone agreement with WFP. (3) Work on strengthening social protection systems began through an MoU with Germany and now continues through the World Bank’s Malawi Social Protection Multi‑Donor Trust Fund, mainly supporting social cash transfers and environmental public works. (4) Natural resource management efforts to protect forests and reduce charcoal-driven deforestation was previously implemented through African Parks (2019-2021) and the Modern Cooking for Healthy Forests programme (2021-2025): final work in this area is being finalised in 2025/26 through a separate agreement with Tetra Tech. (5) Finally, the programme has invested in evidence and policy influence, now supported through an Accountable Grant with IFPRI and a programme-funded post that helps the Government of Malawi prepare for and respond to shocks.

Summary supporting narrative for the overall score in this review

Malawi is increasingly vulnerable to climate related shocks. The operating environment has posed challenges with. delayed and uncertain funding decisions, staffing changes, and the 2026 election and political transition.
Despite these constraints, the team and delivery partners used the adaptive design of the programme to design pragmatic and cost-effective interventions. These were validated by formal beneficiary engagement exercises informing new activities and moderating existing ones (Annex 1). Most milestones have been achieved. However, given the early closure of Modern Cooking for Healthy Forest (MCHF) in January 2025, Output 3 has not been scored. The other two outputs scored an “A” while the last output scored a “B”. Together with progress at outcome level the programme scored an “A” overall.

Major lessons and recommendations for the year ahead

1. FCDO’s position is to move away from service delivery on cash transfers to encouraging greater host country ownership and the Government of Malawi (GoM), have to date indicated a willingness to fund four more districts. FCDO should continue to push for a proportionate increase in funding commitments. Given the new government’s limited fiscal space, FCDO help shape development partner positions on the appropriate pace for a self-financing trajectory.
2. Beneficiaries expressed preference for resilience building activities over food handouts and continuing to check whether the interventions are helpful. Self Help Africa should monitor the recent interventions in Phalombe, assessing where activities have worked and or need changing. A full evaluation will be undertaken at the end of the funding cycle.
3. FCDO should engage in early collaboration with partners and government stakeholders ahead of predictable seasonal weather patterns when considering crisis modifiers and agree the emergency kit contents and thresholds.
4. FCDO should work with Tetra Tech to produce a synthesis of what works in climate and energy programming, drawing on lessons around effectiveness, efficiency, coherence and equity. Tetra Tech should draft a short options paper that outlines evidence-based and programmatic choices for the next business case, consistent with FCDO’s evaluation strategy and wider climate finance guidance.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Background and Context change
FCDO’s resilience framework and wider global evidence highlight that resilience is a product of interlinked capacities to anticipate, absorb, and adapt to shocks and stresses. The programme interventions are therefore designed to: increase the adaptive, absorptive and anticipatory capacities of targeted households and communities, alongside work to contribute to transformative systems strengthening. The UK’s International Climate Finance (ICF) KPI 4 – Number of people with improved resilience – is also based on this.

As previous annual reviews explained, the programme changed significantly from 2021-2024 as budgets changed, and the economy and weather shocks worsened. A review of the theory of change in 2024 noted that while partners were able to meet their individual outputs and some outcomes, the programme fell short of meeting numerous overall outcomes due to intense weather shocks but also due to economic policy choices. This situation persisted in 2025: Malawi’s overall growth rate in the last three years has been 2 percentage points lower than the population growth rate; overall poverty and inequality have risen, annual inflation rose to 30+%; and consecutive[1] severe cyclones and dry spells have led to repeated poor agricultural seasons. In the last two years, domestic food production deficits prompted development partners including FCDO to import humanitarian food assistance.
[1] Including Cyclones Gombe (2022), Ana (2022), Freddy (2023) and dry spells associated with El Nino in 2024.

2025 programming changes
Continuation of resilience activities: In line with beneficiary engagement findings and global efforts to localise resilience efforts, FCDO supported a proposal to deliver more community resilience activities by the Malawi NGO Humanitarian Committee. This aligns directly with the programme’s overarching Theory of Change (TOC) by strengthening the adaptive, anticipatory, and absorptive capacities of vulnerable households. Through layered interventions[2] the component contributes to several ToC outputs (i.e. 3,4,5). Although activities only started late in the year (October), since they used existing initiatives and district structures, funded entities made quick progress and were able to deliver on schedule.
[2] This includes anticipatory action, community-managed disaster funds, enhanced early warning systems, multi‑purpose cash assistance, and protection-sensitive programming.

Natural resources: Although the Modern Cooking for Healthy Forests (MCHF) programme demonstrated strong progress and early evidence validating the ToC, particularly in FY22-24, the premature closure of the project following the USAID Stop Work Order in January 2025 prevented the full realisation and verification of the intended long-term outcomes.

The early outputs and intermediate outcomes suggested strong potential for impact, however, the project closure means that the final outcomes cannot be conclusively attributed or measured. Continued progress toward the TOC’s intended environmental and emissions-reduction goals will depend on the extent to which Government of Malawi institutions, private-sector actors and development partners sustain, scale, and integrate the interventions initiated under MCHF. FCDO supported some close-out activities for MCHF and is considering further modest support in this space through future programming.

Annex 1 provides details of further minor changes and their justification over the last year.
Figure 1 BRACC Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme’s contribution to the expected outcomes are measured against the five outcome level indicators. As noted in the 2024 annual review, nutritional outcomes were not met due to consecutive shocks and economy issues: they are reported through the Social Support to Resilience Livelihood Programme which FCDO contributes. In the year ahead, FCDO plans to continue supporting resilience related activities including TA support to the Government of Malawi and with partners at district level, reduce bilateral funding for humanitarian response. Support on clean energy and carbon finance will be provided through a new Business Case under development.

Impact Indicator	Milestone for this review	Progress
Percentage of the population in target districts living below the national poverty line	2.5% decrease	Waiting for Integrated Household Survey (IHS) data due June 2026. The last IHS survey was in 2019. The overall rise in Malawi’s poverty levels over recent years mean it is unlikely that this milestone will be met.
Lower incidence of food insecurity in targeted Traditional Authorities, compared to non-targeted ones. [3]	% change in PROSPER TA always < non-PROSPER TAs	Met expectations in 2024 but was subsequently dropped. This will no longer be reported in subsequent annual reviews because these activities were being funded under PROSPER which ended in 2024.
Outcome Indicator	Milestone for this review	Progress
Percentage of people whose resilience has been improved as a result of project support (ICF KPI4) (WFP)	90% of households	Did not meet expectations in 2024 but was dropped in 2025 because the current WFP projects did not report. However, the NGO consortium will be able to report against this indicator after conducting the rapid endline scheduled for March 2026.
Percentage of people of all genders that have used their increased capacities for resilience and adaptation to the effects of climate change (NGO consortium)	30% (midline) 60% (endline)	Exceeded expectation. / 43% (31% male households; 12% female households) of people of all genders have used their increased capacities for resilience and adaptation to the effects of climate change. / This has been attributed to prior capacity building support by implementing partners.
% Households classified as being marginally food secure (SSRLP)	68%	Likely did not met expectations- Due to rising food prices and impacts of El Nino in 2024, fewer people were classified as food secure. / 41%- reporting the same value as in 2024 because it is based on most recent surveys (Midline June 2024). Endline survey will provide final update which will be in 2027.
Proportion of Social Protection and humanitarian aid beneficiary households with an improved food consumption score (Percentage)[4]	60% (MDTF) / 95% (WFP)	Met Expectations / 65% (MDTF) for both Social Cash Transfers (SCTP) Public Works Programme CS-EPWP), exceeding expectations / NB: This value is based on 2024 Midline survey results. New data will be available in the 2027 endline survey / 82% (WFP) – below expectations. / The data was collected, on average, 29 days after the distributions. Given this delay, it is likely that household food stocks had already declined.
[3] This was previously referred to by its measurement: difference in difference comparison of targeted Traditional Authorities (TAs) and non-targeted TAs for the proportion of population being in Integrated Phase Classification Phase 3 (Crisis) or higher.
[4] The Food Consumption Score (FCS) is a composite indicator that measures household food security based on three dimensions: dietary diversity, food consumption frequency, and the relative nutritional value of different food groups. As such, the FCS serves as a proxy indicator of household food intake and caloric consumption

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The programme has continued to deliver improvements in resilience for crisis-hit communities. It will continue to its end date, as FCDO develops a new portfolio strategy for Malawi alongside this. FCDO will explore other options on this agenda, through CMPs or a new programme.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title		Vulnerable households and communities in targeted areas have reduced exposure and have great capacity to recover from floods and droughts
Output number:			1		Output Score:		A
Impact weighting (%):			90		Weighting revised since last AR?		Yes, (+35%)
	Indicator(s)			Milestone(s) for this review		Progress
	SHOCK RESPONSIVE ASSISTANCE, COVERAGE AND DELIVERY
	1.1 Number of people supported by FCDO programmes to cope with the effects of climate change (KPI1) - Annual target - as per ICF guidelines (contributed by WFP, and NGO Consortium)			334,104 (direct beneficiaries) / 43,300 (indirect beneficiaries) / Total: 377,404		Met expectations. / Direct[5] / 342,556 (170,929F; 171,627M), consisting of: / WFP / 71,579 (34,860F: 36,719M) people reached during the lean season with cash transfers / 33,526 (16,327F; 17,199M) people received cash for work / NGO Consortium / 127,800 (64,260F; 63,540M) people covered by early warning systems installed by the project, plus people accessing seasonal forecasts. / 57,474 (29,331F; 28,143M) people received cash assistance. / 51,727 (26,074F; 25,653M) people supported with climate‑smart technologies. / 450 (77F; 373M) artisan builders trained in resilient housing / Indirect beneficiaries[6]: / 43,300 (22,083F; 21,217M) / 40,500 people (20,655F; 19,845M) supported by Community Disaster Funds for Nsanje and Chikwawa. / 2,800 (1,428F; 1,372M) people using five solar‑powered irrigation schemes rehabilitated in Phalombe. / Total: 385,856 (193,012F; 192,884M)
	1.2 Number of people reached during the lean season response (LSR) with cash transfers - Annual target (from WFP and NGOs for FY2025)			100%		Met expectation- All 100% beneficiaries (129,053 people) / were given cash transfers. The target is in percentage because it is expected that WFP will reach 100% of the household identified in need of assistance that particular year. The figure is determined based on the needs following a disaster and according to the MVAC figures. This consists of: / WFP: 71,579 (34,860F: 36,719M) people reached in LSR in 24/25 in Blantyre by WFP within the first month of the emergency response (mid-September to mid-October 2024) and in February-March 2025. / NGO Consortium: 57,474 (29,331F; 28,143M) people were reached with cash assistance by the NGO consortium for 2 months from November and December 2025.
	1.3 Percentage of people affected who receive humanitarian assistance via government social protection channels in districts above 20% MVAC need			95%		Did not meet expectation / 62.4% of people affected received the humanitarian assistance via government social protection channels. / Harmonised tools and approaches were adopted, including joint resource mobilisation, standardised beneficiary targeting and verification, coordinated distribution planning, unified complaints and feedback mechanisms (CFM/GRM) and consistent reporting channels.
	1.4a Number of people benefiting from the cash-based interventions (Number of people) (World Bank)			1,000,000 (overall, not burden share)		Met expectation / 999,514 (544,464F; 455,050M) / NB: The number of beneficiaries for Social Cash Transfer Programme (SCTP) were revised down (from 1,371,914) to exclude households by KFW which were reported in 2024 annual review.
	1.4b Number of people using digitally enabled services during social cash transfer and public works programme (World Bank)			3,400,000		Did not meet expectation / 2,659,158 (1,299,369M; 1,359,789F). The Climate Smart-Enhanced Public Works Programme (CS-EPWP) has reached 26 out of 28 districts with e-payments and 17 out of 28 districts for SCTP. / Payments are currently being delivered through five payment service providers, and these are: TNM, Airtel, FDH, Standard Bank, and Kaku Pay. / Public works has not met the target due to lack of national IDs for beneficiaries (which affected enrolment), delays in know your customer exercise and low wages which affects the registration of beneficiaries in the programme.
	1.5 Number of refugees receiving unconditional cash assistance (PREPARE AND CURRENT WFP PROGRAMME)			57,000		Met expectation / 55,190 (28,656F; 26,534M) / WFP reached 55,190 refugees. This deviates from the original figure of 57,000 because some beneficiaries, especially those that did not have accounts opened during the distribution period did not show up to collect their entitlements.
	1.6 Number of people receiving food in-kind assistance (disaggregated by gender and disability) (WFP-El Nino Response)			465,000		Met expectations / 465,120 people (226,532F; 238,588M) / The El Niño-induced drought severely affected Malawi. In response, WFP, provided food assistance from September 2024 to May 2025, targeting the most vulnerable populations in Chikwawa and Balaka.
	1.7 Number of beneficiaries of productive inclusion programmes (World Bank) / This indicator captures people supported but who cannot be included in the overall resilience target 1.1 because not possible to attribute FCDO funding).			2,400,000		Met Expectation / 2,067,277 (988,132F; 1,079,145 M) / The reduction from the previous reporting period (2,270,920 in 2024) reflects the outcome of the retargeting exercise. The review showed that some households were enrolled in both SCTP and CS-EPWP, yet the programme requires that a household should belong to only one stream. When correcting the lists, most of those households chose to remain under SCTP because the transfers do not require providing labour. This reduced the number of households counted as CS-EPWP beneficiaries.
[5] Targets for direct beneficiaries are based on total number of individuals receiving direct support from NGO and WFP interventions. The gender disaggregation calculated using the gender ratios from NSO 2018 Census data (50.7%F / 49.3%M).
[6] Indirect numbers are calculated based on the population within the targeted NGO Traditional Authority (TA) who will benefit from the activities and institutional capacity building at TA level but are not direct programme beneficiaries

PREPAREDNESS, SYSTEMS STRENGTHENING AND RESILIENT LIVELIHOODS
1.8 Number of kits procured and prepositioned in number of sites-PREPARE ONLY	15,000	Met expectation / 15,000 kits procured / The lower procurement of kits was primarily due to the absence of a storm reaching the scale envisioned in the original proposal. This intentional decision was made due to a reassessment of anticipated needs for the 2024-25 cyclone season, following a cost-efficiency analysis of pre-positioning late in the cyclone season.
1.9 Number of people engaged in capacity strengthening activities- (PREPARE ONLY)	30	Exceeded expectation / 91-The first workshop included 35 participants (15 F, 20 M), and the second 56 participants (26 F, 30 M), / Two workshops were held, in addition to regular working group sessions with DoDMA, to strengthen emergency preparedness coordination.
1.10 Number of partners utilising storage services for prepositioning (PREPARE ONLY)	10	Not met expectation / 4- WFP made free-to-user common logistics services available to government and humanitarian partners to encourage prepositioning ahead of the rainy season. The target was not met because storms were not as bad as anticipated.
1.11 Percentage of Agricultural inputs provided in line with pre-defined performance criteria (NGO consortium)	85%	Did not meet expectation (but with justification) / 71.2% by end of December. The project provided agricultural input in November and delayed sweet potato vines distribution to December to suit sweet potato planting times as advised by Agricultural extension in respective planning areas, leading to a revision in the timing. Agricultural inputs were provided with pre-defined performance criteria.
1.12 Number of Community Disaster Funds (CDFs) established and fully operational (NGO consortium).	7	Met expectation. / 6 CDF established and fully operational in Nsanje and Chikwawa / All the 6 CDF in Nsanje and Chikwawa received 75% (approx. $3800) of their proposed funds, with the remaining 25% that will be transferred upon satisfactory progress. / Phalombe CDF will be operational at the end of January 2026.
1.13 Number of irrigation schemes rehabilitated or improved (NGO consortium).	4	Met expectation. / 5 solar-powered irrigation schemes rehabilitated in Phalombe. / Efforts to improve and/or rehabilitate irrigation schemes in Nsanje and Chikwawa irrigation are in progress as partners have identified consultants to do the work.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output captures a broad set of interventions supporting households and communities to better manage climate related shocks. Activities were delivered through WFP’s PREPARE project, the World Bank’s Social Protection Programme, and the NGO led consortium. Together, these interventions contributed to early warning, preparedness, humanitarian response and longer-term resilience strengthening.

Although no large-scale cyclone occurred during the review period[7] , the PREPARE project allowed WFP to test preparedness approaches during cyclones or floods. Activities included pre-positioning of supplies, capacity strengthening for emergency coordination and small-scale cash for work interventions.
[7] Cyclone Chido (December 2024) led to 46,000 displaced and the smaller Tropical Storms Jude (March 2025) affected up to 11,370 people but neither caused widespread damage.

The activities under the NGO consortium contributed to output 1.11-1.13. The project’s main interventions include supporting Community Disaster Funds for undertaking public works (a model established successfully by the Zurich Foundation), inputs for climate-smart agriculture, rehabilitation of irrigation schemes, and working with the meteorological office on downscaling of seasonal forecasts and improving prediction. Given the vulnerability of housing (given poor construction) the project also included training for local artisan builders on low-cost improvements to housing design. A crisis modifier was included to provide cash to targeted households in the event of disasters. Good progress has been made by the project in the year to date, although several findings were observed by partners and FCDO:

- On training of builders, economic constraints are limiting the uptake of Build Back Better Artisans as many households lack resources to invest in resilient housing this year.
- More detailed sustainability plans are needed for irrigations schemes, given vulnerability of their operations to flooding.
Under the Social Support for Resilient Livelihoods Programme (SSRLP), the Enhanced Public Works transitioned to a continuous implementation modality with notable improvements in asset quality and marginal improvements in the timeliness of wage payments. Despite its overall progress, the Social Cash Transfer Programme progress still faces delays in cash disbursement to beneficiaries, and some discrepancy in lists of beneficiaries held by the district councils and payment providers resulting in payroll errors. FCDO’s Fiduciary Risk Assessment of late 2025 provided assurance that the programme was rectifying these issues at a good rate.

Progress against this output has been good, and the overall score is “A”.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

- Output 1.6-1.8 will no longer be reported in the next annual review because the PREPARE project with WFP ended in July 2025.
- Output 1.11-1.13 have been added to the logical framework from the NGO consortium interventions.
- The impact weighting has been revised upwards to 90% because of the level of funding to the interventions under this output.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from last AR	Progress
Although SCTP is making steady progress, FCDO should monitor the challenges associated with targeting and systems integration that are being faced and ensure the WB and GoM adequately addresses these before the next review. FCDO to continuously assess the cost effectiveness and role of SCTP cash transfers versus other modalities as part of a cash-benchmarking exercise to inform the next business case (by July 2025).	Completed: The World Bank is leading the reforms in the cash transfer programme, including a comprehensive review of categorical targeting to ensure that the intended beneficiaries are accurately reached. It is also supporting efforts to strengthen Government ownership and increase domestic resource allocation for the programme. These reforms will guide the future design and implementation of social cash transfers in Malawi.

Lessons learned and recommendations for next year.

Recommendation #1: FCDO should engage in early collaboration with partners and government stakeholders when designing any future prepositioning projects in the new Business Case and agree the emergency kit contents and thresholds. Emergency kits were originally designed to meet households’ immediate needs for 5–7 days during large-scale emergencies, bridging the gap until broader response efforts commence. However, in smaller events such as Tropical Cyclone Jude, where only a one-off distribution occurs, the kit contents were not fully suited to the context and often duplicated items from other disbursements. Early engagement will help ensure that approaches and operational details are agreed upon, and that interventions effectively address community needs while promoting long-term ownership- By July 2026

Recommendation #2: The World Bank and National Local Government Finance Committee (NLGFC) should collaborate with district councils to resolve discrepancies in beneficiary numbers and ensure that beneficiary list has been harmonised across councils and service providers to allow for improved accuracy in lists and timely payouts- By March 2026

Recommendation #3: The World Bank and NLGFC should work with the district councils to improve the timeliness of benefit payments (the target is payment within two weeks) to Public Works and Social Cash Transfer Programme beneficiaries. FCDO should continue monitoring how the programme is resolving the bottlenecks to ensure timely disbursement to beneficiaries-On-going

Recommendation #4: Self Help Africa should test the feasibility and value for money of Build Back Better intervention before scaling up in Phalombe to ensure the approach is context‑appropriate and cost‑effective-On-going

Recommendation #5: FCDO should revise the targets for 2026 for both CS-EPWP and SCTP to reflect the outcomes of the retargeting exercise. -By March 2026.

Output Title	Increased capacity of national, sub-national and non-state actors to prepare for, plan, monitor and respond to shocks.
Output number:		2	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	Yes (+5%)

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of partners/LNGOs reporting improved knowledge in emergency management (NGO Consortium)	5	Not met expectations / 0 The trainings have been re-scheduled from November/ December to February 2026
2.2 Number of districts supported with training and engagement on revised AA, EOC and emergency response coordination SOPs to enhance their capacity for emergency response (WFP)	2	Exceeded expectations / 9 districts have supported with trainings (Mulanje, Chiradzulu, Balaka, Mwanza, Phalombe, Nsanje, Zomba, Mangochi and Machinga)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 2 focused on strengthening institutional capacity across government, NGOs and community structures to deliver services necessary for effective emergency response. The key activities included training on emergency preparedness, anticipatory action and emergency response coordination. In 2024, FCDO did not fund activities that supported this output with the partners hence this output was not scored in the last annual review. In 2025, FCDO resumed supporting the partners through this output.

Through WFP, the project supported training targeted at councils to downscale emergency coordination, establishing Standard Operating Procedures (SOPs) for Emergency Operations Centres at council level.

In February 2025, WFP also provided minor continued support on Search and Rescue, supporting a deployment of the UK’s International Search and Rescue team to train Malawian responders from the Marine Police and Defence forces through a residential course. Training included emergency planning theory and practice, live rescue, and other practical courses. This training was highly appreciated by the Government agencies and should improve capacity of responders from participating districts and command units. In the event of future trainings however, it will be important to ascertain participant readiness to undertake exercises (e.g. swimming proficiency) through pre-assessments. Strengthening the national search and rescue capability will reduce the reliance on external humanitarian response and allows the trained responders to contribute to faster, safer and more coordinated rescue operations, thereby saving lives in future emergencies.

Self Help Africa and consortium partners are expected to conduct trainings to local NGOs on improved knowledge in emergency management in February 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from last AR	Progress
Although PROSPER has come to an end, FCDO should continue monitoring how the Disaster Risk Information Management System is expanding and being used for how it considers working in this area in future.	Completed: The Disaster Risk Information Management System has been expanded to 6 districts and UNDP have been discussing with the World Bank to scale it up to all the districts through their climate and resilience programme
FCDO to continue engaging social protection actors like NLFGC to raise awareness about the call centre facility established at the Ministry of Gender and be able to use it and report cases.	In Progress: UNICEF has been proactive in raising awareness of the call centre to the partners through the social protection donor group meetings to ensure it is fully utilised by all actors. The call centre is part of the grievance redress mechanisms for social cash transfer.

Lessons learned and recommendations for next year.

Recommendation #1: Self Help Africa and WFP should support Government in the creation of a standardised monitoring framework to track how districts and NGOs apply the revised Anticipatory Action (AA), Emergency Operating Centre (EOC), and emergency coordination Standard Operating Procedure’s (SOPs) after trainings. This should include regular follow-up assessments, field monitoring visits, and simple performance checklists to measure improvements in coordination, response activation, and decision-making‑up assessments, field monitoring visits, and simple performance checklists to measure improvements in coordination, response activation, and decision‑making.

Output Title	Forest deforestation and degradation is reduced, and forest dependent communities in targeted areas have more sustainable livelihoods
Output number:		3	Output Score:	Not scored
Impact weighting (%):		0%	Weighting revised since last AR?	Yes (this output no longer being scored in 2025)

Briefly describe the output’s activities and provide supporting narrative for the score.

FCDO no longer co-funds this output and its indicators[8] because MCHF closed early following a USAID stop-work order issued to the programme in January 2025 (see Sections E [risk] and F [Programme management] for more detail. Indicators for the subsequent TetraTech close-out work were added to Output 4 and details on outputs from the Social Protection programme were added into Output 1.
[8] 3.1: # of people with livelihood co-benefits from improved forest management 3.2: # of hectares of degraded landscapes under improved management 3.3: Tons of sustainable charcoal or alternative biomass energy produced 3.4: Amount of private sector finance leveraged for alternative energy options and efficient cooking technologies 3.5: Tonnes of greenhouse gases reduced or avoided because of ICF 6

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from last AR	Progress
Pending a way forward on MCHF activities through 2025, FCDO to integrate final updates to MCHF results into the logframe.	Completed: The new indicator from Tetra tech on the finalisation of MCHF products and reports has been included in the logframe

Lessons learned and recommendations for the next year

Recommendation #1: FCDO should work with Tetra Tech to produce a brief options paper in this annual review period of what works in climate and energy programming, drawing on lessons around effectiveness, efficiency, coherence, and equity. Tetra Tech should draft a short options paper that outlines evidence‑based and programmatic choices for the next business case, consistent with FCDO’s evaluation strategy and wider climate finance guidance.

Output Title	More effective, coordinated and targeted, government and donor investments [in resilience]
Output number:		4	Output Score:	B
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 # of communications/evidence products generated by programme partners, including a publicly accessible data/document store that can be handed over to GoM	20 (monthly maize market reports, rapid analytics, policy brief) / (Cumulative)	Met expectation / 20 publications have been produced including 2 research papers, 2 policy briefs, 1 journal article, 3 blogs and 12 market reports. All are freely accessible at www.massp.ifpri.info.
4.2 # of disaster preparedness and response official releases the PFP influenced through technical advice	6	Not met expectations / 4. Consecutive PFPs provided advice on the i.) preparedness and disaster risk financing ii.) responses to tropical cyclone Jude; informing the proportionate release of humanitarian supplies; iii +iv.) conducting community voice exercises to collate feedback. Due to staffing gap, fewer products than expected were issued.
4.3 # of summaries and learning products and reports developed as part of close out activities for MCHF	4	Met expectation / 4 products that have been produced and delivered are: The cost of cooking report; a brief two-four-page summary of key findings from the report; Third Biennial Urban Cooking Survey Report and Third Biennial Urban Cooking Survey data.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output 4 is about using evidence and knowledge to influence policy and drive more effective donor and government investments in climate resilience, including inputs from the International Food Policy Research Institute (IFPRI) and activities of FCDO’s Programme Funded Post seconded to DODMA. This work has been delivered through:
(a) an Accountable Grant with IFPRI for research on activities on (i.) social safety nets (2018-2023); (ii.) strengthening agricultural markets and institutions (formerly) and strengthening food security in Malawi with a focus on the role of grain reserves and cross border trade (currently). A key aspect has also been on communications related activities to ensure the learning and evidence reaches a wider audience. (b) A programme funded post at the Government of Malawi’s Department of Disaster Management Affairs to increase the capacity of local authorities, communities and individuals to prepare and respond to shocks by supporting more effective, coordinated and targeted Government and Donor sectoral investments. (c) a contract with Tetra Tech which was signed in September 2025 to finalise key data and reports which were in progress prior to the termination of the MCHF contract with USAID. The contract is ending in March 2026.

The work package on strategic grain reserves by IFPRI has fallen behind schedule due to difficulties in accessing data from government agencies and programming the empirical model. In December 2025, IFPRI took the decision to abandon the empirical model and complete the report based on existing literature, historical information and a theoretical model. This will ensure that the report is delivered and appropriately disseminated before the end of the project in March 2026.

The Project Funded Post (PFP) has been seconded in the Department of Disaster Management Affairs (DoDMA) since early 2024 with the aim of supporting the Government of Malawi’s national and district staff to more effectively prepare and respond to shocks and coordinate internally and externally more effectively. The PFP is implementing a set of agreed objectives covering: support to strategic planning for the department; resource mobilisation with a focus on access to climate finance and improved efficacy of disaster risk financing; and improving coordination in preparation for and during a response, with a particular focus on inter-cluster coordination. Activities under these objectives are underway, examples include supporting DoDMA to develop a proposal for the Fund for Responding to Loss and Damage. However, as there was an 8-month gap between postings for PFPs and the indicator wasn’t adjusted, fewer outputs were produced against the target.

Tetra Tech has developed survey reports and a summary of knowledge products, including the Malawi Cost of Cooking Study, the Third Biennial Urban Cooking Survey, and the Malawi Regulatory and Enforcement Brief. The drafting of these reports began during the implementation phase of the MCHF project. FCDO has now engaged Tetra Tech to finalize and disseminate these reports to key stakeholders in the energy and carbon finance sectors.

This output has met expectations and is scored “B”.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A new indicator has been added on the finalisation of reports and surveys by Tetra Tech

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation from last AR	Progress
There has been staff turnover at IFPRI’s headquarters which has affected the timely submission and quality of the financial report. IFPRI should ensure high quality financial reports are internally reviewed and submitted to FCDO on time.	Completed: The quality of IFPRI’s financial reports has improved significantly. FCDO reviews each report and engages with IFPRI whenever revisions are necessary. IFPRI has consistently responded promptly and provided timely feedback
FCDO should include an indicator in the log frame on the PFP’s performance to better capture the range of technical and strategic support provided through this role. By July 2025	Completed: The PFP indicator has been added in the log frame, and this will be reported in this annual review

Lessons learned and recommendations for next year.

Recommendation #1: With IFPRI’s agreement ending in March 2026, FCDO to consider within this annual review period, the fit between IFPRI’s skillset and future governance/ climate governance needs. By February 2026.

Recommendation #2: FCDO should amend the indicator in the logframe to “# of disaster risk management (DRM) activities the PFP influenced through technical advice.” This could include input into policies and strategies; preparedness, resilience and response activities, including the development of proposals, guidance, improved coordination processes or official releases.

## VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

Economy

Partners continued to use comparative procurement that met the criteria for open and competitive processes, benchmarking and using global facilities when purchasing goods, materials or equipment. For example, for PREPARE and El Nino response project, WFP continued to prioritize local procurement for other commodities such as cowpeas and super cereal whenever feasible. WFP also leveraged the purchase of maize and CSB++ through its Global Commodity Management Facility (GCMF) in Tanzania. This facility allows WFP to pre-position food stocks before country offices receive contributions, operating on a first-come, first-served basis.

Due to the advance payment and strategically timed funding from FCDO, WFP was able to make savings of approximately 46 percent due to early purchase in the region rather than buying locally during peak lean season. This saving allowed WFP to procure significantly more maize for the same amount of funding and reach more beneficiaries. WFP was able to procure 3,113 MT, instead of 1,688.21 MT if procured locally later in the season. This resulted in an additional 29,280 households (131,760 individuals) reached – using the 50 kg ration per month per household.

For the NGO consortium, procurement of goods and services, including climate-resilient agricultural inputs and irrigation equipment, was done in a competitive process to ensure inputs are procured at the right price. Specifically, all goods and services were purchased after conducting market research to understand market conditions, suppliers, and pricing options. Competitive bidding processes were applied to ensure suppliers are selected through transparent and consistently applied criteria. Additionally, the use of locally sourced materials for CDF activities further promoted local enterprises and sustainability.

Efficiency

The early financial commitment from FCDO in responding early to the crisis facilitated strategic planning across the supply chain, enabling effective management of streamlined storage, downstream logistics, inventory and distribution processes. This enabled WFP to pool resources with other donors, optimising transport allocations and reducing per-unit costs. These efficiencies translated into tangible cost savings of 46% than the original amount and allowed WFP to procure more maize comparing to procuring the maize locally. This led to improved delivery timelines and demonstrated a high level of operational efficiency.

During discussions of budgets with the NGO consortium, significant efficiency savings were made by streamlining roles and responsibilities, including relying more on local staffing where appropriate. The NGO consortium has subsequently achieved project efficiency through regular review of output and work plans, supported by periodic programme level assessments and robust Monitoring & Evaluation (M&E) arrangements that enable adaptive management and timely correction. Furthermore, the programme builds on implementing organizations’ established presence in target areas and longstanding government and development partner relationships, enabling rapid start-up and effective delivery.

Effectiveness:

The project builds on proven, scalable models, such as the Zurich Climate Resilience Alliance’s (ZCRA) Community Disaster Fund (CDF) pilot, which have demonstrated strong community ownership and tangible results (e.g., dykes and drainage systems that reduce flood damage). The Community Disaster Fund model enhances efficiency by decentralizing decision making to community level, streamlining fund utilization, and reducing administrative bottlenecks. By enabling communities to prioritize, design, and implement their own solutions with light technical oversight, the model accelerates implementation, promotes ownership, and maximizes impact.
Regular site visits, monthly reporting, and real-time data collection through digital tools ensure that activities remain aligned with targets and adaptive to emerging risks. Additionally, collaboration with the government and wider sector’s actors, and a people-centered approach, ensures programme sustainability and scale.
FCDO and other partners in the Multi-Donor Trust Fund for Social Protection reviewed the 2025 programme’s annual budget and workplan, noting that the costs for Daily Subsistence Allowances (DSAs) and trainings were high. As a result, the overall budget was reduced by 4%, accompanied by a decrease in the number of trainings conducted and DSAs disbursed.

The use of cash assistance has enabled cost-effective and flexible support to affected households. According to the Post Distribution Monitoring (PDM) assessments, 99% of the respondents reported they were satisfied with the assistance provided and that it was provided on time, while integrating resilience interventions such as drought tolerant crops, early warning systems and capacity building, contributed to sustained impact beyond immediate relief.

Equity:

Self Help Africa and the partners have been using a participatory and data-driven approach to identify the most at risk households and communities. Pre-identification of communities was done through disaster risk baselines, community disaster plans and district level vulnerability mapping which enabled equitable resource allocation. Specific efforts were made to prioritise women-headed households, people with disabilities, elderly and ultra poor households in cash transfers, climate smart agriculture input distribution and irrigation support.

E: RISK

Overview of risk management

The overall BRACC risk rating for the programme remains ‘Moderate’ reflecting both the challenging operating environment and the programme’s ability to respond adaptively to emerging risks. The programme this year has continued to adapt to changes in the operating environment including the early closure of the USAID-contracted MCHF programme, fuel shortages and the 2025 elections. The programme team continues to actively manage the risks through regular engagement with implementing partners including the NGO consortium, the World Bank and WFP and monthly reviews of office/economy wide and programme-specific risks. Below is a summary of the relevant risk categories.

Risk trends

Strategy & Context risks: The risk appetite is within FCDO Malawi’s risk appetite of “receptive”. The programme aims to break humanitarian and environmental degradation cycles through resilience building and governance improvements but is also subject to overall shocks that Malawi faces which impact operations (e.g. fuel, inflation) and beneficiaries (droughts, floods) to which the programme needs to respond. Additionally, the macro-economic instability in the country has affected the agricultural productivity and programme delivery as mentioned in the background section.

Policy & Programme Delivery risks: BRACC’s appetite for policy and programme– “Receptive” – mirrors BHC Lilongwe’s appetite level. Programme delivery risks were factored into our partner selection through e.g. our due diligence with NGO Humanitarian Consortium, who also use a risk register that we review regularly. A major source of programme delivery risk this year stemmed from a stop-work order and subsequent closure of USAID and its partnerships in country. These stopped all activities under the Modern Cooking for Healthy Forests programme (which FCDO significantly funded), and also substantially affected the funding landscape for humanitarian response, including for WFP. We sought to mitigate the impacts of USAID’s closure by exploring alternative contracting modalities, but ultimately the project closed. Risks associated with loss of data were mitigated through discussions with USAID over handover of data and assets to the GoM, and FCDO provided additional funding to the project team to finalise products under development.

Financial & Fiduciary risks: The risk is within FCDO Malawi’s “cautious” risk appetite. During the reporting period, monitoring visits and beneficiary consultations have been central to identifying and addressing risks including the use of DSAs by the partners. During spot checks of the social protection programme, discrepancies were noted between beneficiary numbers recorded by district councils, service provider and central team, raising concerns about potential ghost beneficiaries and delays in payments. The World Bank has since taken corrective steps, including limiting the timeframe for completing the Know Your Customer processes and strengthening controls over beneficiary enrolment and cash out authorisation. FCDO commissioned an independent consultant to update the Fiduciary Risk Assessment in late 2025 to provide assurances about the systems and controls in the district councils and the partners which maintained the risk level at moderate/major. Partners have submitted annual audits and statements which provided assurances on how funds are being used. FCDO has also issued a fraud and safeguarding letter to all partners to bring awareness on fraud and cyber-crimes.

For funding previously disbursed to USAID for the Modern Cooking for Healthy Forests programme, FCDO has reclaimed outstanding funds from USAID that were not disbursed as a result of the project’s early termination, and we are waiting for final confirmation of the reimbursement.

Partners have been requesting for approvals from FCDO whenever they want to issue DSAs in accordance with the DSA guidelines. Additionally, DSA budget lines from the partners are reviewed by FCDO to ensure they follow the approved guidelines.

Reputational risks: This risk appetite is at cautious and remains within FCDO Malawi risk appetite.

Public Service Delivery & Operations: This risk appetite is at cautious and remains within FCDO Malawi risk appetite. In the past year, there were fuel shortages in the country, which disrupted programme implementation, monitoring and distribution of supplies by partners. To mitigate this, partners signed agreements with service stations in the districts where implementation is taking place to be prioritized and access fuel.

Safeguarding risks: This risk remains at Cautious. Given the programme’s focus on vulnerable populations including refugees and households receiving humanitarian support, robust safeguarding systems are essential. To mitigate this, all partners conduct mandatory awareness training for all staff including volunteers and downstream partners. Partners include Preventing Sexual Exploitation and Abuse (PSEA) in all trainings/onboarding sessions for contractors and cooperating partners. Beneficiary sensitisation initiatives are also undertaken. They also conduct periodic self and partner capacity assessments of safeguarding measures to ensure that the systems and measures for preventing sexual exploitation and abuse are effective and adjusted as necessary. An Enhanced Due Diligence Assessment was done with all partners, incorporating a comprehensive safeguarding section, with key findings under this pillar clearly articulated. Partners have confirmed their zero-tolerance stance against any form of exploitation and abuse for its staff, service providers, contractors and beneficiaries. The safeguarding letter was issued to raise awareness of Sexual Exploitation, Abuse and Harassment and to reinforce the use of the Reporting Concerns mechanism. WFP conducted an outcome survey that assessed protection concerns. Ninety-eight percent of households reported no safety issues, and nonexperience barriers to accessing WFP assistance or reported being treated disrespectfully. These results suggest that most respondents feel safe, face no access barriers, and are treated with dignity, reflecting a generally positive experience with WFP assistance.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Performance of partnerships

Programme delivery during the reporting period remained strong, with partners broadly meeting expected milestones and demonstrating responsiveness to emerging humanitarian and resilience needs. Management arrangements across implementing partners remained effective, enabling coordinated delivery despite challenging environment marked by climatic shocks and economic pressures.
Self Help Africa- The consortium led by Self Help Africa demonstrated strong programme management capacity. Governance structures were established early, and SHA provided consistent coordination and oversight across the NGO partners. Engagement with Government agencies was constructive, with entry level meetings completed and standard operating procedures agreed across partners. Reporting requirements were met, with timely submission of monthly progress reports, risk register and the budgets. The consortium continues to implement activities aligned with localisation objectives and is on track for completion by March 2026.

WFP – WFP delivered substantial humanitarian and resilience support in line with the agreement which was signed in 2025. This included the procurement and distribution of maize for food insecure households during the lean season, logistical preparedness for cyclone response, and nutritional treatment for beneficiaries experiencing moderate acute malnutrition. WFP maintained strong coordination with Government departments, UN agencies (including UNHCR), and district stakeholders, ensuring targeted and efficient service delivery. Their ability to rapidly mobilise regional maize procurement contributed to cost efficiencies and timely response.

World Bank (MDTF)- FCDO has made its second contribution to the MDTF in December 2025. The recent field monitoring report shows some significant progress in the implementation of enhanced public works but more awareness to the beneficiaries needs to be made in the implementation of choice model and also ensure that the district councils have the correct numbers of beneficiaries. The district councils need to ensure that cases are managed and resolved in good time to ensure beneficiaries receive their dues on time. World Bank have also been conducting quarterly implementation support mission to monitor progress and assess key risks to programme delivery.

IFPRI- IFPRI’s performance strengthened over the reporting period, particularly in financial management. Improvements in the quality and timeliness of financial reporting were noted, following early challenges linked to staff turnover at their headquarters. Research activities continued with a focus on food security, market systems, and policy influence. Although delays affected some analytical work, IFPRI took corrective action by adjusting methodologies to ensure deliverables remain on schedule for the agreement ending in March 2026.

USAID (for Modern Cooking for Healthy Forests) The agency’s abrupt funding pause in February 2025 and subsequent closure affected UK’s funding directly and indirectly. In response, BHC staff at technical and senior level engaged US counterparts to find a solution and ensure as smooth a transition as possible.

Tetra Tech- Through a short-term contract, Tetra Tech focused on completing technical outputs initiated under the MCHF programme. These included finalisation of survey reports, and development of knowledge products. Deliverables were completed on time and were disseminated to relevant Government and sector stakeholders through one-on-one interface. The contract remains on track for closure in February 2026.

Financial Performance for FY25/26

WFP – WFP executed its activities, including the procurement of emergency kits within the project period. Cost management was addressed through detailed project planning to minimize cost overruns and maximise cost efficiencies. Cooperating Partner costs were denominated in US dollars to mitigate the impact of price inflation. FCDO will conduct the financial spot check with the partners to verify how the partners have used the exchange rate gains and losses. The PREPARE project demonstrated the importance of flexibility in emergency funding. While the design was thorough and clearly defined budget lines, this level of prescription limited the ability to adapt quickly when needs shifted. FCDO however provided the approvals budget changes swiftly and timely, and WFP was able to deliver support for nutrition treatment and cash assistance to both refugees and vulnerable households.
Partners (IFPRI, WFP and World Bank) have submitted audit reports for the past year, and all the audits were unqualified. The financial reports for all the partners were scrutinised and provided the information that helped us make decisions on which budget lines they are underspending/overspending and requested clarifications.

Self Help Africa- Overall programme expenditure during the reporting period (October–December 2025) remains largely aligned with delivery progress (at 63% expenditure rate), with performance varying by output in line with implementation sequencing and external market conditions. Variances have been actively monitored and managed to protect delivery and provide value for money

The 2025/26 forecast was £9,000,000.00 and the current expenditure as of December 2025 is £8,073,323.97 representing 89% spend. Total programmes spend to date against the revised budget is shown in the table below.

Partner	Revised Budget (£)	Spend as of 31st December 2024 (cumulative, all years)	Status
Support to design of BC	57,074	57,074	Closed
Concern Worldwide (PROSPER)	13,983,205	13,983,205	Closed
UN (PROSPER)	25,479,955.79	25,479,955.79	Closed
UN PROSPER (CONSTRUCTION OF EVACUATION CENTRES)	1,142,630	1,142,630	Closed
GIZ (SPP)	2,691,842	2,691,842	Closed
IFPRI (1)	1,911,787	1,911,787	This agreement ended
IFPRI (2)	500,000	381,708.20	On-going till March 2026
African Parks	850,568	850,568	Closed
USAID (Modern Cooking)	5,250,000	5,250,000	Closed due USAID closure
LTS (BRACC Hub)	1,129,832	1,129,832	Closed
Lean Season Response	17,131,780	17,131,780	Closed
Emergency Preparedness and Response	652,907	652,907	Closed
Addressing Food Needs (PREPARE PROJECT/El Nino Response)	11,150,000	11,150,000	Closed
Climate Adaptation and Resilience for Communities through Malawi Humanitarian NGOs (Self Help Africa)	3,000,000	2,514,326	On-going till March 2026
Contract with Tetra Tech to finalise close out activities for MCHF	100,000	60,290	On-going till February 2026
Support to national level resilience and humanitarian coordination	645,000	554,534	On-going till October 2027
Support to Social Protection	4,823,420	1,962,162	On-going till December 2026
TOTAL	90,500,000	86,904,600

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

FCDO conducted quarterly field monitoring visits to the project’s sites to MDTF, WFP and NGO projects to assess risks, compliance and progress against targets. During these monitoring visits, FCDO engaged with beneficiaries to get their feedback through small group interactions to understand perspectives on performance and relevance of programme activities and used these to make recommendations to the partners. For the MDTF and NGO partners, bi-monthly and monthly meetings respectively were conducted where in depth discussion on programme progress, risks, safeguarding and fraud were discussed.

The NGO component had M&E sector working group meetings and technical field visits to backstop quality implementation. These technical visits included engagement with Disaster Risk Management Committee’s (DRMCs) to review the best beneficiary identification criteria and use of Joint Emergency Assistance Programme (JEFAP)/Unified Beneficiary Registry (UBR). The project employed a unified beneficiaries registration tool for easy tracking of adherence to identification criteria and database management. The field visits, registration forms and transparent complaint reporting system made verification of beneficiaries efficient, with some ineligible beneficiaries tracked and replaced with eligible ones.

Evidence and Learning

As indicated in Output 4, Tetra Tech have produced products which includes concise summaries, learning pieces, and key datasets and reports that were underway prior to the Stop Work Order. The resulting outputs are intended to benefit not only FCDO, but also the Government of Malawi, private sector partners, and other stakeholders in the forestry and energy sectors.

The NGO consortium has used participatory monitoring and evaluation, technical field visits, community consultations, district coordination meetings, and spot checks to capture and share lessons. Key lessons include the importance of adaptive planning in response to climate related shocks, the value of robust verification systems and unified beneficiary registration tools, and the benefits of participatory approaches that strengthen ownership and accountability. While the UBR and robust verification systems are beneficial, their effectiveness depends on how current and accurate the data is. When the UBR tool is regularly updated, it significantly reduces the time required for verification. In districts where the UBR data was outdated and required more time, additional verification steps were necessary, resulting in delays. To address this, the process had to be complemented with the JEFAP approach in Chikwawa and Nsanje, which helped to expedite the process, validate the data and minimize errors in UBR as it was outdated with some beneficiaries moving on or reallocating including death, at community level. This highlights the importance of continuous data updating and the need for flexible, complementary systems to ensure both speed and accuracy in targeting.

Gender, disability, and safeguarding considerations were integrated across activities to ensure equitable access and protection for vulnerable groups. Lessons for wider FCDO and development work include the need for strengthened coordination among partners, early guidance on risk management and flexibility, and anticipatory approaches for rapid response. Building on these insights, the programme aims to further embed adaptive learning mechanisms, structured reflection sessions, targeted knowledge sharing, and ongoing monitoring of inclusion and safeguarding outcomes.

The programme will continue to leverage existing partner monitoring and learning systems, as well as evaluation survey reports, to generate evidence and learning products that inform engagement with Government and other stakeholders and support policy influence. In addition, FCDO will draw on evaluation expertise from the central Centre of Expertise to strengthen oversight and assess programme impact.

Date of last narrative financial report	IFPRI- 21 November 2025 (for July-September 2025 Quarter) / WFP- September 2025 (for December 2024-June 2025) / MDTF- April 2025 (for period of up to March 2025) / Self Help Africa-4 February 2026 (for Oct-Dec Quarter)	Date of last audited annual statement	MDTF- 8 September 2025 (for period ending June 2025) / IFPRI- September 2025 (for period ending December 2024) / Self Help Africa- March 2025 (for period ending December 2024) NB: this component started in October 2025, and the audit will be available in March 2026 / WFP- May 2025 (for period ending December 2024)

Annex 1: Changes to programming in 2025/26 included:
Beneficiary engagement: In April/May 2025, the programme deployed a short-term Humanitarian Adviser, who conducted community sessions in Nsanje and Phalombe to hear their voices on how humanitarian response and resilience activities were working and should be improved. The major finding from these sessions highlighted community preferences for support that supported livelihood activities rather than handouts and picked up concerns with some of the targeting approaches being used.

Re-design of activities: building on these findings, in August 2025, FCDO sought a proposal from the NGO Humanitarian Committee members to implement a community-based humanitarian and resilience interventions leveraging established presence and ongoing interventions which are working well. The project is delivering an integrated resilience, preparedness and humanitarian interventions by working with local and international organisations through a consortium.

Lean season food needs and crisis modifiers: FCDO continued providing support to World Food Programme (WFP) to address most urgent food needs of vulnerable population during the 25/26 lean season. Anticipating large gaps in funds for refugee food needs (given the closure of USAID) and uncertainty over the lean season response given the September election and transition of power, FCDO decided to again provide early funding for both international purchase and distribution of food and for supporting refugee costs. The funding further allowed WFP to procure maize and nutrition supplies and distribute to people who were food insecure during the lean season.

Ongoing support to shock-responsive social protection. FCDO continued support on social protection in the reporting period and monitored closely the key risks that were identified in the fiduciary risk assessment in December 2024. FCDO joined other donor partners in the mission field spot checks as part of monitoring the risks and engaging with the beneficiaries. Close discussions with the World Bank were held to ensure that the identified risks were being addressed proactively. In December 2025, FCDO has made a second contribution to the Multi Donor Trust Fund (MDTF) after undergoing internal approvals and has updated the Fiduciary Risk Assessment (FRA).

Responsible exit from our forest and energy access project: The abrupt closure by USAID of our (predominantly FCDO-funded) vehicle used to support forest governance, cooking energy and carbon market activities. While programming contracting regulations prevented continued support to the main contractor, FCDO did support close out activities were able to finalise contracting to complete unfinished work.

Annex 2: 2025 Logframe Changes

Indicator level	Description/Justification
Impact Indicator 2: (Difference comparison of targeted TAs and non-targeted TAs on levels of food insecurity)	This will discontinue to be reported in FY 2025 because it was reported by WFP under PROSPER which ended in July 2024 and we no longer will have access to this data and are no longer using a targeted TA approach.
Outcome Indicator 1b: % of people of all genders that have used their increased capacities for resilience and adaptation to the effects of climate change (NGO Consortium)	Included the new outcome indicator from the NGO consortium work to align to the resilience indicators
Outcome Indicator 3: Proportion of Social Cash Transfer and Public Works Programme project beneficiary households with an improved food consumption score (Percentage) (World Bank)	Added “Public Works Programme” beneficiaries as part of reporting in addition to the social cash transfer. This is in line with what World Bank will be reporting on
Outcome Indicator 3: (% households classified as being marginally food secure or food secure)	This will continue to be reported by Social Support on Resilience and Livelihoods Programme (SSRLP) because they also use the same WFP methodology to collect the data
Output 1 (rephrasing the name of the output): / Vulnerable households and communities in targeted areas have reduced exposure and have great capacity to recover from floods and droughts (this includes cash transfer and Early Warning Systems (EWS)	Output name has been rephrased and added “have great capacity to recover from floods and droughts (this includes cash transfer and EWS)” to reflect the interventions being implemented in the programme. While the original output focused solely on reducing exposure to droughts and floods, the updated version recognises that programme activities go beyond risk reduction and also strengthen the capacity of vulnerable households and communities to recover from climate shocks.
Output Indicator 1.1: Number of people supported by FCDO programmes to cope with the effects of climate change (KPI1***) - Annual target - as per ICF guidelines (contributed by WFP and NGO)	Changed the target for 2025 from 4,950,607 to 4,371,972. This is due to USAID cut and also reflecting the support from the NGO's work which started in October 2025 This will compose of beneficiaries from SSRLP cash transfer (1,724,873) and public works (2,400,000); WFP-refugee support (57,000), cash for work (25,074); NGO's- crisis modifier (5000), cash transfers (160,025). / The target for 2026 has been changed too.
Output Indicator 1.2: Number of people reached during the lean season response with cash transfers - Annual target (from WFP and NGOs for FY2025)	Specified who is contributing to the output
Output Indicator 1.4b: Number of people using digitally enabled services during social cash transfer and public works programme (World Bank)	Indicator removed from Output 2 to output 1.4b in order to group the cash transfer indicators together.
Output Indicator 1.5: Number of refugees receiving unconditional cash assistance (PREPARE AND CURRENT WFP PROGRAMME)	Added new target for 2026 based on current project with WFP
Output Indicator 1.9: Percentage of timely in-kind transfers reaching beneficiaries per month	Removed indicator as it does not apply to the current WFP project
Output Indicator 1.11: Number of beneficiaries of productive inclusion programmes (World Bank)	Indicator removed from Output 3.8 to this output as part of the rephrasing of this new output and to streamline reporting / Revised target for 2026
Output Indicator 1.12-1.14 (NGO related indicators)	New indicators added from the NGO consortium work
Output Indicator 2.1: Number of partner LNGOs reporting improved knowledge in emergency management (NGO Consortium)	New indicator added from the NGO consortium work
Output Indicator 2.2: Number of districts supported with training and engagement on revised AA, EOC and emergency response coordination SOPs to enhance their capacity for emergency response (WFP Current Project)	New indicator added from the current work with WFP
Output Indicator 3.1-3.9 (MCHF related indicators)	All the outputs have been removed as they were being reported by MCHF which is not continuing
Output Indicator 4.3: # of summaries and learning products and reports developed as part of close out activities for MCHF	New indicator added from Tetra Tech’s activities