## Master Logframe
Master Logframe: Productivity for Prosperity - Aceli Africa, Manufacturing Africa and the Green Growth Fund | [8 empty] | Last Updated: July 2024
IMPACT | Impact Indicator 1 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31 | Total Cumulative | comments
Sustainable economic transformation in Tanzania through increased labour productivity and climate-resilience in job-creating sectors. | Number of new jobs and number of jobs with improved incomes as result of programme's activities (cumulative, unique people). | Planned: New Jobs (% women) | - | 6 (30%) | 21 (30%) | 36 (30%) | 298 (30%) | 874 (30%) | 2,171 (30%) | 3,732 (30%)
|  | Aceli Africa | 0 | 5.9375 | 20.9375 | 36.3281 | 55.7531 | 68.3531 | 68.3531 | 0 |  | GGF Aceli MA
|  | of which women | 0 | 1.7812 | 6.2812 | 10.8984 | 16.7259 | 20.5059 | 20.5059 | 0
|  | Manufacturing Africa |  |  |  |  | 242 | 806 | 1770 | 2732
|  | of which women |  |  |  |  | 72.6 | 241.8 | 531 | 819.6
|  | Green Growth Facility |  |  |  |  | 0 | 0 | 333 | 1000
|  | of which women |  |  |  |  | 0 | 0 | 100 | 300
|  | Planned: Jobs with Improved Incomes (% women) | - | 460 (30%) | 1,623 (30%) | 2,815 (30%) | 4,084 (30%) | 4,906 (30%) | 13,240 (30%) | 25,000 (30%)
|  | Aceli Africa | 0 | 460.1562 | 1622.6562 | 2815.4297 | 4083.6047 | 4906.2047 | 4906.2047 | 0
|  | of which women | 0 | 138.0469 | 486.7969 | 844.6289 | 1225.0814 | 1471.8614 | 1471.8614 | 0
Manufacturing Africa
of which women
|  | Green Growth Facility |  |  |  |  | 0 | 0 | 8333.3333 | 25000
|  | of which women |  |  |  |  | 0 | 0 | 2500 | 7500
|  | Achieved: New Jobs (% women) | - | 9 (33%) | - | 30 (29%) | 638 (13%) | - | - | -
|  | Aceli Africa | 0 | 9 | 0 | 29.6 | 58.2 | 0 | 0 | 0
|  | of which women | 0 | 3 | 0 | 8.525 | 17.46 | 0 | 0 | 0
|  | Manufacturing Africa |  |  |  |  | 0 | 0 | 0 | 0
|  | of which women |  |  |  |  | 0 | 0 | 0 | 0
|  | Green Growth Facility |  |  |  |  | 580 | 0 | 0 | 0
|  | of which women |  |  |  |  | 66 | 0 | 0 | 0
|  | Achieved: Jobs with Improved Incomes (% women) | - | 331 (56%) | - | 1,300 (32%) | 2,652 (31%) | - | - | -
|  | Aceli Africa | 0 | 331 | 0 | 1300 | 2646.2 | 0 | 0 | 0
|  | of which women | 0 | 186 | 0 | 414.8 | 819.875 | 0 | 0 | 0
Manufacturing Africa
of which women
|  | Green Growth Facility |  |  |  |  | 6 | 0 | 0 | 0
|  | of which women |  |  |  |  | 3 | 0 | 0 | 0
Source
Aceli Africa Salesforce M&E System; Green Growth Fund MEL System; Manufacturing Africa M&E Systems
| Impact Indicator 2 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| ICF KPI 4: Number of people whose climate resilience has been improved as a result of ICF (cumulative, unique people). [Aceli Only] | Planned (% women) | - | 1,380 (30%) | 4,635 (30%) | 5,362 (30%) | 7,137 (30%) | 8,289 (30%) | 8,289 (30%) | -
|  | Aceli Africa | 0 | 1380.4688 | 4635.4688 | 5361.7266 | 7137.1716 | 8288.8116 | 8288.8116 | 0 |  | Aceli GGF not contributing
|  | of which women | 0 | 414.1406 | 1390.6406 | 1608.518 | 2141.1515 | 2486.6435 | 2486.6435 | 0
|  | Manufacturing Africa |  | 0 | 0 | 0
|  | of which women |  | 0 | 0 | 0
|  | Green Growth Facility |  | 0 | 0 | 0
|  | of which women |  | 0 | 0 | 0
|  | Achieved (% women) | - | 1,613 (41%) | - | 6,313 (35%) | 12,417 (27%) | - | - | -
|  | Aceli Africa |  | 1613 | 0 | 6313 | 12416.5 | 0 | 0 | 0
|  | of which women |  | 660 | 0 | 2183 | 3333.5 | 0 | 0 | 0
Manufacturing Africa
of which women
Green Growth Fund
of which women
Source
Aceli Africa Lenders' data, Africert verfication visits with SMEs and sampled farmers; Green Growth Fund MEL System; Manufacturing Africa M&E Systems
| Impact Indicator 3 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Relative growth of agriprocessing, manufacturing and horticulture sectors vs agriculture (cumulative vs baseline). [MA Only] | Planned |  |  |  |  | 0 | 0.01 | 0.01 | 0 |  | MA
|  | Achieved |  |  |  |  | 2% | 0% | 0% | 0%
Source
Manufacturing Africa M&E Systems
OUTCOME | Outcome Indicator 1 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31 |  |  | Assumptions
A better business environment, increased investment (including climate and nature finance), improved business practices, and increased domestic and international trade. | Investment mobilised as a result of programme's activities (cumulative, includes: domestic direct investment, foreign direct investment, portfolio investment). (Public investments?) | Planned (2X Gender Challenge criteria) | - | $3,493,750 (30%) | $10,143,750 (30%) | $15,754,688 (50%) | £36,314,288 (29%) | £77,725,453 (18%) | £111,484,493 (1%) | £173,253,659 (1%) |  |  | Political feasibility: the assessment of political feasibility in the options appraisal is correct and remains steady. Domestic economic stability: Tanzania’s current broadly positive economic trajectory continues and there is not a major economic crisis. Global economic recovery: the global economic recovery will continue its current trend, and the market for Tanzanian exports (notably agriculture and tourism) will grow. Private sector capacity: there are sufficient SMEs in Tanzania that are capable of responding to technical assistance and absorbing investment. Effective delivery: the contracted supplier is able to establish an office in Tanzania and recruit staff with the require expertise to implement the programme. Climate impacts: the climate change impacts on agriculture production will not be so severe as to render large proportions of the sector unviable within 10 years.
|  | Aceli Africa | 0 | 3493750 | 10143750 | 15754687.5 | 20858148.75 | 26825508.75 |  | 0 |  | GGF, MA and Aceli
|  | of which meet the 2X Gender Challenge criteria | 0 | 1048125 | 3043125 | 7877343.75 | 10429074.375 | 13412754.375 |  | 0
|  | Manufacturing Africa |  |  |  |  | 14634146.3415 | 48780487.8049 | 107317073.1707 | 165853658.5366
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 0 | 0 | 1 | 0
|  | Green Growth Fund |  |  |  |  | 821992.7171 | 2119456.0491 | 4167419.5686 | 7400000 |  |  |  |  | 0.74
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 246597.8151 | 635836.8147 | 1250225.8706 | 2220000
|  | Achieved (2X Gender Challenge criteria) | - | £5,092,429 (96%) | - | £13,427,074 (68%) | £21,663,347 (60%) | - | - | -
|  | Aceli Africa |  | 5092429 | 0 | 13427073.6452 | 20834990.5018 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  | 4904429 | 0 | 9191789.22 | 12783120.1151 | 0 | 0 | 0
|  | Manufacturing Africa |  |  |  |  | 0 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 0 | 0 | 0 | 0
|  | Green Growth Fund |  |  |  |  | 828356 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 309320 | 0 | 0 | 0
Source
Aceli Africa Salesforce M&E System; Green Growth Fund MEL System; Manufacturing Africa M&E Systems
| Outcome Indicator 2 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| ICF KPI 12: Volume of private finance mobilised for climate change purpose as a result of ICF (cumulative). | Planned (2X Gender Challenge criteria) | - | $698,750 (30%) | $2,028,750 (30%) | $4,945,922 (65%) | £7,542,190 (48%) | £10,912,888 (47%) | £12,448,861 (45%) | £5,550,000 (30%)
|  | Aceli Africa | 0 | 698750 | 2028750 | 4945921.5625 | 6925695.8438 | 9323295.8438 | 9323295.8438 | 0 |  | Aceli GGF
|  | of which meet the 2X Gender Challenge criteria | 0 | 209625 | 608625 | 3214849.0156 | 3462847.9219 | 4661647.9219 | 4661647.9219 | 0
Manufacturing Africa
of which meet the 2X Gender Challenge criteria
|  | Green Growth Fund |  |  |  |  | 616494.5378 | 1589592.0368 | 3125564.6765 | 5550000
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 184948.3613 | 476877.611 | 937669.4029 | 1665000 |  |  |  | 1.2323
|  | Achieved (2X Gender Challenge criteria) | - | $2,133,212 (97%) | - | $6,435,201 (66%) | £9,294,097 (62%) | - | - | - |  |  |  | 0.62965
|  | Aceli Africa |  | 2133212 | 0 | 6435200.85 | 8659177.2283 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  | 2067212 | 0 | 4241398.43 | 5452237.4382 | 0 | 0 | 0
|  | Manufacturing Africa | [12 empty] | 12.5676
of which meet the 2X Gender Challenge criteria
|  | Green Growth Fund |  |  |  |  | 634920 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 309320 | 0 | 0 | 0
Source
Aceli Africa Salesforce M&E System, Lenders data; Green Growth Fund MEL System; Manufacturing Africa M&E Systems
| Outcome Indicator 3 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Increase in sales and international trade as a direct result of programme's activities (annual sales, as measured by value of new purchase orders). | Planned: Total Sales (2X Gender Challenge criteria) | - | $902,500 (30%) | $2,280,000 (30%) | - | £4,718,111 (65%) | £8,898,482 (60%) | £11,134,537 (54%) | £7,400,000 (30%) |  | Aceli , GGF
|  | Aceli Africa | 0 | 902500 | 2280000 | 3135000 | 4718110.5 | 7607496 | 7607496 | 0
|  | of which meet the 2X Gender Challenge criteria | 0 | 270750 | 684000 | 2037750 | 3066771.825 | 4944872.4 | 4944872.4 | 0
Manufacturing Africa
of which meet the 2X Gender Challenge criteria
|  | Green Growth Fund |  | 0 | 0 | #REF! | 0 | 1290986.4634 | 3527040.6098 | 7400000
|  | of which meet the 2X Gender Challenge criteria |  | 0 | 0 | #REF! | 0 | 387295.939 | 1058112.183 | 2220000
|  | Planned: International Trade (2X Gender Challenge criteria) | - | $451,250 (30%) | $1,140,000 (30%) | - | £3,187,913 (65%) | £4,449,241 (47%) | £5,567,268 (44%) | £3,700,000 (30%)
|  | Aceli Africa | 0 | 451250 | 1140000 | 1776500 | 3187912.5 | 3803748 | 3803748 | 0
|  | of which meet the 2X Gender Challenge criteria | 0 | 135375 | 342000 | 1154725 | 2072143.125 | 1901874 | 1901874 | 0
Manufacturing Africa
of which meet the 2X Gender Challenge criteria
|  | Green Growth Fund |  | 0 | 0 | #REF! | 0 | 645493.2317 | 1763520.3049 | 3700000
|  | of which meet the 2X Gender Challenge criteria |  | 0 | 0 | #REF! | 0 | 193647.9695 | 529056.0915 | 1110000
|  | Achieved: Total Sales (2X Gender Challenge criteria) | - | $782,119 (96%) | - | $3,356,532 (65%) | £6,385,791 (61%) | - | -
|  | Aceli Africa |  | 782119 | 0 | 3356532.134 | 5987439.9044 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  | 753179 | 0 | 2185775.334 | 3877631.2144 | 0 | 0
Manufacturing Africa
of which meet the 2X Gender Challenge criteria
|  | Green Growth Fund |  |  |  |  | 398350.88 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  |  |  |  | 0 | 0 | 0 | 0
|  | Achieved: International Trade (2X Gender Challenge criteria) |  | 556,718 (95%) | - | - | £2,499,960 (61%) | - | - | -
|  | Aceli Africa |  | 556718 | 0 | 1590348.4018 | 2483221.3604 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  | 530307 | 0 | 921471.8925 | 1529357.0877 | 0 | 0
Manufacturing Africa
of which meet the 2X Gender Challenge criteria
|  | Green Growth Fund |  |  |  | #REF! | 16738.8 | 0 | 0 | 0
|  | of which meet the 2X Gender Challenge criteria |  |  |  | #REF! | 0 | 0 | 0 | 0
Source
Aceli Africa Salesforce M&E System, Lenders data; Green Growth Fund MEL System; Manufacturing Africa M&E Systems
| Outcome Indicator 4 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of effective TA interventions that improve the business environment and/or market system. | Planned | 0 | 0 | 0 | 0 | 5 | 12 | 20 | 12 |  | MA, GGF, Aceli
|  | Aceli Africa | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Manufacturing Africa |  |  |  |  | 3 | 6 | 11 | 0
|  | Green Growth Fund |  |  |  |  | 2 | 5 | 8 | 12
|  | Achieved |  |  |  |  | 3
|  | Aceli Africa |  |  |  |  | 0 | 0 | 0 | 0
|  | Manufacturing Africa |  |  |  |  | 0 | 0 | 0 | 0
|  | Green Growth Fund |  |  |  |  | 3 | 0 | 0 | 0
Source
“Policy reform” entails a change to legislation, strategy, or approach recorded in a public pronouncement; OR substantial improvements made to the operations of a government institution (cumulative).
| Outcome Indicator 5 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Emissions reduced or avoided that have been supported by ICF TA (ICF TA KPI 5) - GGF Only | Planned |  |  |  | #REF! | 0 | 130843 | 357470 | 750000 |  | GGF
|  | Achieved |  |  |  | #REF! | 219 | 0 | 0 | 0
Source
GGF's indicator reference sheets.
| Outcome Indicator 6 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| ICF KPI 17: Hectares of land that have received sustainable land management practices as a result of ICF (cumulative) - GGF Only | Planned | 0 | 0 | 0 | #REF! | 0 | 117758.9004 | 185746.9004 |  |  | GGF
|  | Green Growth Fund |  | 0 | 0 | #REF! | 0 | 117758.9004 | 185746.9004
|  | Achieved |  |  |  |  | 345163
|  | Green Growth Fund |  |  |  | #REF! | 345163 | 0 | 0 | 0 | 0 | 0
Source
Aceli Africa Salesforce M&E System; Green Growth Fund MEL System; Manufacturing Africa M&E Systems
| Outcome Indicator 7 | [10 empty] | GGF only; check why Aceli isnt reporting (Alex)
| ICF KPI 15: Extent to which ICF intervention is likely to lead to transformational change - GGF Only | Planned |  | No target for Y1 | No target for Y2 |  | 0 | 0 | 1 | 3
|  | Achieved |  |  |  | No target for Y1 | 0 | 0 | 0 | 0
Source: GGF's indicator reference sheets.
| Outcome Indicator 8 | [10 empty] | GGF
| Number of supported business environment reforms that receive ‘high level hearing’ within the GoT and number of GGF-supported TA interventions that the GoT deploys and are operational (cumulative) - GGF ONLY | Planned | 0 |  |  | 0 | 2 | 5 | 8 | 10
|  | Achieved |  |  |  |  | 3 | 0 | 0 | 0
Source: GGF's indicator reference sheets. Note: “Policy reform” entails a change to legislation, strategy, or approach recorded in a public pronouncement; OR substantial improvements made to the operations of a government institution.
Output 1 | Output Indicator 1.1 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31 |  |  | Assumptions
Aceli Africa. Mobilising investment for job-creating domestic agri-business ($50k-$2m ticket size), through (1) financial risk-sharing and (2) technical assistance to businesses and local/regional financial institutions. | [Mobilisation Indicator] Develop and agree budget and workplan for Aceli Africa, agree Accountable Grant and mobilise in Tanzania. | Planned | C: Agree budget, logframe & workplan B: Complete enhanced due diligence; achieve MAG approval; achieve Prof11 approval A: Sign accountable grant within 6 months of BC approval A+: Sign accountable grant within 4 months of BC approval A++: Sign accountable grant within 2 months of BC approval |  | - | - | - | - |  |  |  |  | Support to investment promotion related activities and agencies will attracted increased FDI inflows. Relative productivity levels are much higher in P4P target sectors versus subsistence agriculture. GoT is willing and able to reform and remove barriers to investment. Actors are willing and able to partner with P4P to promote manufacturing FDI
|  | Achieved |  | A+ | - | - | - | -
| Sub-Weight | Source
| 0% | Aceli Africa Salesforce M&E System
| Output Indicator 1.2 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of businesses receiving technical assistance (cumulative). | Planned |  | 4 | 14 | 34 | 51 | 51 | 61 | 61 |  | Aceli
|  | of which meet the 2x Gender Challenge criteria |  | 1.2 | 4.2 | 11.9 | 17.85 | 17.85 | 21.35 | 21.35
|  | Achieved |  | 4 |  | 46 | 63
|  | of which meet the 2x Gender Challenge criteria |  | 0 |  | 18 | 26
| Sub-Weight | Source
| 20% | Aceli Africa Salesforce M&E System
| Output Indicator 1.3 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Percentage of SMEs satsified with TA programme | Planned |  |  |  | 0 | 70% | 0 | 70% |  |  | 0
|  | Achieved |  |  |  | 0 | 89% | 0
| Sub-Weight | Source
| 20% | Aceli Africa Salesforce M&E System
| Output Indicator 1.4 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of financial institutions actively lending in partnership with Aceli (cumulative). | Planned |  | 7 | 9 | 10 | 12 | 12 | 12 | 12 |  | Aceli
|  | Achieved |  | 7 |  |  | 11
| Sub-Weight | Source
| 20% | Aceli Africa Salesforce M&E System
| Output Indicator 1.5 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of financial institutions receiving technical assistance (cumulative). | Planned |  | 0 | 1 | 1 | 2 | 4 | 4 | 0 |  | Aceli
|  | Achieved |  | 0 |  |  | 2
| Sub-Weight | Source
| 20% | Aceli Africa Salesforce M&E System
| Output Indicator 1.6 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of loans approved as a result of Aceli's financial incentives (cumulative). | Planned |  | 23.75 | 60 | 101 | 240 | 312 | 312 | 312 |  | Aceli
|  | of which meet the 2x Gender Challenge criteria |  | 7.125 | 26 | 50.5 | 120 | 156 | 156 | 156
|  | Achieved |  | 26 |  | 111 | 264
|  | of which meet the 2x Gender Challenge criteria |  | 23 |  | 72 | 157
Weight | Sub-Weight | Source
35% | 20% | Aceli Africa Salesforce M&E System
£ Inputs | 7500000 | HR Inputs | Lead: Alex Mangowi (30%); Adviser: Priti Prajapati (10%); Programme Manager: Evans Rwamuhuru (25%); Oversight: Euan Davidson (5%)
Output 2 | Output Indicator 2.1 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31 |  |  | Assumptions
Manufacturing Africa. Business environment reform and Foreign Direct Investment (FDI) facilitation ($2m-$15m ticket size) through: (1) technical assistance to Government (2) and FDI transaction facilitation. | [Mobilisation Indicator] Develop and agree proposal, budget and workplan for Manufacturing Africa's expansion into Tanzania. | Planned | C: Discussions initiated with MA Team B: Proposal, budget and workplan received A: Proposal, budget and workplan agreed A+: Team mobilised and inception phase commenced A++: First draft inception report delivered |  | Logframe Indicators Agreed | - | - | - | - | - |  | MA | Support to investment promotion related activities and agencies will attracted increased FDI inflows. Relative productivity levels are much higher in P4P target sectors versus subsistence agriculture. GoT is willing and able to reform and remove barriers to investment. Actors are willing and able to partner with P4P to promote manufacturing FDI
|  | Achieved | - | A | - | - | - | - | - | -
| Sub-Weight | Source
0%
| Output Indicator 2.2 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of investment deals provided with high quality substantive support | Planned |  |  | TBC | 2 | 13 | 24 | 34 | 0 |  | MA
|  | of which meet the 2x Gender Challenge criteria |  |  | TBC | 2 | 13 | 24 | 34
|  | Achieved |  |  |  | 3 | 13 | 0 | 0 | 0
|  | of which meet the 2x Gender Challenge criteria |  |  |  | 3 | 13 | 0 | 0 | 0
| Weight | Source
15%
| Output Indicator 2.3 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of deals provided with high quality support which are potentially eligible for the second stage PBR payment if they reach deal close. | Planned |  |  | TBC | 1 | 6 | 12 | 17 | 0 |  | MA
|  | of which meet the 2x Gender Challenge criteria |  |  | TBC
|  | Achieved |  |  |  | 3 | 10 | 0 | 0 | 0
of which meet the 2x Gender Challenge criteria
| Weight | Source
20%
| Output Indicator 2.4 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of substantive technical assistance deliverables supporting government agencies / institutions approved and implemented to a high-quality standard. | Planned |  |  | TBC | 0 | 1 | 3 | 6 | 0 |  | MA
|  | Achieved |  |  | TBC |  | 1
| Weight | Source
15%
| Output Indicator 2.5 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of support programmes guided by market systems principles, designed and implemented by the contractor in targeted sectors which address key barriers to manufacturing activity, and which are delivered to a high standard. | Planned |  |  | TBC | 0 | 6 | 12 | 23 | 0 |  | MA
|  | of which meet the 2x Gender Challenge criteria |  |  | TBC
|  | Achieved |  |  |  | 2 | 3 | 0 | 0 | 0
of which meet the 2x Gender Challenge criteria
| Weight | Source
15%
| Output Indicator 2.6 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of third parties substantially engaged with, in a way judged to be effective to undertake new activity targeted at addressing key barriers to manufacturing activity. | Planned |  |  | TBC | 0 | 1 | 2 | 4 | 0 |  | MA
|  | of which meet the 2x Gender Challenge criteria |  |  | TBC
|  | Achieved |  |  |  | 0 | 3 | 0 | 0 | 0
of which meet the 2x Gender Challenge criteria
| Weight | Source
15%
| Output Indicator 2.7 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of support packages provided either to foreign investors to encourage them to increase demand from domestic enterprises, or to domestic enterprises themselves to enable them to meet such demand. | Planned |  |  | TBC | 0 | 2 | 4 | 6 |  |  | MA
|  | of which meet the 2x Gender Challenge criteria |  |  | TBC
|  | Achieved |  |  |  | 0 | 3 | 0 | 0 | 0
of which meet the 2x Gender Challenge criteria
| Weight | Source
20%
| Output Indicator 2.8 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of new buyers (global or domestic) introduced to FDI investors or manufacturers who could credibly meet the buyers' demands within a reasonable time frame (max 2 years). | Planned |  |  | TBC |  | No target this FY |  |  |  |  | MA
|  | of which meet the 2x Gender Challenge criteria |  |  | TBC |  | No target this FY
Achieved
of which meet the 2x Gender Challenge criteria
Weight | Sub-Weight | Source
30% | 0%
£ Inputs | 16500000 | HR Inputs | Lead: Priti Prajapati (50%); Adviser: Alex Mangowi (20%); Programme Manager: Evans Rwamuhuru (25%); Oversight: Euan Davidson (5%)
Output 3 | Output Indicator 3.1 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31 |  |  | Assumptions
Green Growth Fund. Improved climate policies, and stronger UK-Tanzania economic cooperation through demand-driven technical assistance. | [Mobilisation Indicator] Undertake procurement process to launch Green Growth Fund. | Planned | C: Agree route to market based on business planning commission. B: Complete first draft of Terms of Reference A: Market-ready ToR, responds to comments A+: Procurement launched A++: Supplier bids assessed |  | - | - | - | - | - | - |  |  | Support to investment promotion related activities and agencies will attracted increased FDI inflows. Relative productivity levels are much higher in P4P target sectors versus subsistence agriculture. GoT is willing and able to reform and remove barriers to investment. Actors are willing and able to partner with P4P to promote manufacturing FDI
|  | Achieved |  | A | - | - | - | - | - | -
| Sub-Weight | Source
| 0% | Green Growth Fund MEL System
| Output Indicator 3.2 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of Government policy reform, systems building, and capacity building initiatives that GGF undertakes with Government or other influential ecosystem actors, through an approved SOW. | Planned – total SoWs |  |  |  |  | 3 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have climate impact |  |  |  |  | 1 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have gender impact |  |  |  |  | 0 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved – total SoWs |  |  |  |  | 4
|  | Of which have climate impact |  |  |  |  | 1
|  | Of which have gender impact |  |  |  |  | 0
| Sub-Weight | Source
| 20% | Green Growth Fund MEL System
| Output Indicator 3.3 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of business innovations to support growth, investment readiness, and/or exports, that GGF supports through private or public actors, through an approved SOW | Planned – total SoWs |  |  |  |  | 4 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have climate impact |  |  |  |  | 1 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have gender impact |  |  |  |  | 1 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved – total SoWs |  |  |  |  | 4
|  | Of which have climate impact |  |  |  |  | 3
|  | Of which have gender impact |  |  |  |  | 2
| Sub-Weight | Source
| 20% | Green Growth Fund MEL System
| Output Indicator 3.4 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Number of supporting functions and services that GGF helps to develop to overcome constraints to market development, through an approved SOW | Planned – total SoWs |  |  |  |  | 2 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have climate impact |  |  |  |  | 0 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have gender impact |  |  |  |  | 0 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved – total SoWs |  |  |  |  | 3 | N/A | N/A | N/A
|  | Of which have climate impact |  |  |  |  | 0 | N/A | N/A | N/A
|  | Of which have gender impact |  |  |  |  | 2 | N/A | N/A | N/A
| Sub-Weight | Source
| 15% | Green Growth Fund MEL System
| Output Indicator 3.5 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Percentage of completed SOWs approved by FCDO without substantial revision. | Planned |  |  |  |  | 85% | Target set annually. | Target set annually. | Target set annually.
|  | Achieved |  |  |  |  | 100% | 0% | 0% | 0%
| Sub-Weight | Source
| 15% | For source data, see GGF's indicator reference sheets.
| Output Indicator 3.6 |  | Baseline (Jun-2021) | 44742 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Percentage of SoWs agreed approved in the preceding reporting year, submitted and approved by FCDO by the end of the review year. | Planned |  |  |  |  | 75% | Target set annually. | Target set annually. | Target set annually.
|  | Achieved |  |  |  |  | 70% | N/A | N/A | N/A
For source data and other measurement details, see GGF's indicator reference sheets.
15%
| Output Indicator 3.7 |  |  | 44742 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| GGF implements a system to track learning and how it informs programme management decision making. | Planned |  |  |  |  | System has been designed and put into practice in Y2 of the Programme. | Target set annually. | Target set annually. | Target set annually.
|  | Achieved |  |  |  |  | MEL system had been designed and put into place in Y2 | N/A | N/A | N/A
For source data and other measurement details, see GGF's indicator reference sheets.
Weight | Sub-Weight | Source
30% | 15%
£ Inputs | 11000000 | HR Inputs | Lead: Priti Prajapati (50%); Adviser: Alex Mangowi (10%); Adviser: Abdalla Shah (10%); Programme Manager: Evans Rwamuhuru(25%); Oversight: Euan Davidson (5%)
Output 4 | Output Indicator 4.1 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31 |  |  | Assumptions
Overseas Development Institute (ODI): Support to the Government of Tanzania on economic planning. | Technical assistance support provided to the Planning Commission on prioritization and economic transformation. | Planned |  |  | - |  | Technical assistance support provided to the Planning Commission on prioritisation and economic transformation | Target set annually. | Target set annually. | Target set annually.
|  | Achieved |  | #REF! | - |  | Prioritisation and economic transformation integrated into national planning through strategic engagement and sectoral analysis.
| Sub-Weight | Source
| 50% | Green Growth Fund MEL System
| Output Indicator 4.2 |  | Baseline (Jun-2021) | 2022-06-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 2026-03-30 | 2027-03-30 | 2027-12-31
| Technical assistance support to the design of Tanzania Development Vision 2050 | Planned |  |  |  |  | Technical assistance support to the design of Tanzania Development Vision 2050 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved |  | #REF! | - |  | Support finalisation of vision 2050 draft and groundwork laid for the long- and short-term planning frameworks
Weight | Sub-Weight | Source
5% | 50% | ODI MEL System
£ Inputs | 16500000 | HR Inputs | Lead: Priti Prajapati (50%); Adviser: Alex Mangowi (20%); Programme Manager: Evans Rwamuhuru (25%); Oversight: Euan Davidson (5%)
Total £ Inputs | 35000000 | Total HR Inputs | SRO: Priti Prajapati (60%); Adviser: Alex Mangowi (60%); Adviser: Abdalla Shah (30%); Adviser: Head of Climate Change (30%); Programme Manager/PRO: Evans Rwamuhuru (75%)
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. GGF are measuring new Jobs from FY26/27, 2. MA are only contributing to new jobs and not jobs with improved income 3. MA doesn’t have women’s target (although they will report. We need to agree that they set the targets)
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of jobs is reported cumulatively so shouldn’t be less than the year before.
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I’ve suggested using 30%
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both MA and GGF are not contributing while their budget is 70% ICF
Note on B57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Again, MA doesn’t have planned target for investment mobilized of which meet the 2x gender challenge
Note on B75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MA not contributing despite having a 70% ICF budget?
Note on B92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MA not contributing?
Note on B139: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GGF indicate to measure and report this at the end of the programme, Dec 2027? Is it?

## Aceli Africa
Aceli Africa
IMPACT | Impact Indicator 1 |  | Baseline (Nov-2021) | 2022-06-30 | Annual review notes | 2022-09-01 | Q3- Sept.2022- Comments | 2023-06-30 | June 2023-Comments | 2024-03-01 | March 2024 Comments | 2024-06-30 | 2025-03-01 | March 2025 Comments | 2026-03-30 | 2027-03-31 | Total Cumulative Unique | Attribution Assumption: 25% to Aceli Anticipate 10% growth in jobs and salaries New jobs = number of fulltime employees Improved incomes = number of SHF suppliers Assumptions: 10 FTE / SME 775 SHFs / SME Impact Indicator 2 is measuring SHFs linked to SMEs meeting C&E impact bonus. Our policy is that a majority of farmers are practicing climate smart agriculture (assuming 50%) as that is conditional on the SME qualifying for the impact bonus. NOTE: This means actuals are divided by 2
Sustainable economic transformation in Tanzania through increased labour productivity and climate-resilience in job-creating sectors. | Number of new jobs and number of jobs with improved incomes as result of Aceli's activities (cumulative). | Planned: New Jobs | 0 | 5.9375 |  |  |  | 20.9375 |  | 36.3281 |  | 48.4375 | 55.7531 |  | 68.3531 | 68.3531 | 0
|  | of which women | 0 | 1.7812 |  |  |  | 6.2812 |  | 10.8984 |  | 14.5312 | 16.7259 |  | 20.5059 | 20.5059 | 0
|  | Planned: Jobs with Improved Incomes | 0 | 460.1562 |  |  |  | 1622.6562 |  | 2815.4297 |  | 3753.9062 | 4083.6047 |  | 4906.2047 | 4906.2047 | 0
|  | of which women | 0 | 138.0469 |  |  |  | 486.7969 |  | 844.6289 |  | 1126.1719 | 1225.0814 |  | 1471.8614 | 1471.8614 | 0
|  | Achieved: New Jobs | 0 | 9.2 | Ahead of target: Aceli-supported SMEs have more employees than projected. However, this number varies greatly across each SME, therefore we do not propose to adjust the projections | 12.65 | On track. 62% to annual target. | 22.25 | Above target (105%) | 29.6 |  |  | 58.2 | Achieved 104%
|  | of which women | 0 | 2.725 | On target | 3.825 | on track. 67% to annual target. | 6.225 | Achieved (100%) | 8.525 |  |  | 17.46 | Achieved 100%
|  | Achieved: Jobs with Improved Incomes | 0 | 331.2 | Under target: Aceli-supported SMEs have less SHF suppliers than projected, and expect to improve as more SMEs are supported. However, this number varies greatly across each SME, therefore we do not propose to adjust the projections. | 447.85 | Under target. 28% to annual target. | 1125.475 | Achieved 70% of target. | 1300 |  |  | 2646.2 | Achieved 65%. We have noted a significant drop in the average number of smalholder farmers (SHF) served by an SME. Target had assumed 457 SHF per SME, on average, but we are seeing that on aveage an SME serves 400 SHF. This trend is supported by the trend towards much smaller loans as the portfolio tilts more to new borrowers who tend to be smaller SMEs
|  | of which women | 0 | 186.275 | On target | 219.775 | On track. 45% to annual target. | 368.3 | Achieved 76% of target. A relatively small number of women SHF (33%) and women fulltime employees (28%) during the period has kept this number below target. Overall women participation in Aceli portfolio is larger than observed here for P4P loans. | 414.8 |  |  | 819.875 | Achieved 67%. For a reason similar to that stated above - the portfolio is tilting more towards new borrowers who tend to be smaller SMEs with relatively smaller scale operations, hence serving fewer SMEs than it had been assumed when setting the target
Source: Lenders' data
| Impact Indicator 2 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| ICF KPI 4: Number of people whose climate resilience has been improved as a result of Aceli's (cumulative). | Planned | 0 | 1380.4688 |  |  |  | 4635.4688 |  | 5361.7266 |  | 7148.9688 | 7137.1716 |  | 8288.8116 | 8288.8116 | 0
|  | of which women | 0 | 414.1406 |  |  |  | 1390.6406 |  | 1608.518 |  | 2144.6906 | 2141.1515 |  | 2486.6435 | 2486.6435 | 0
|  | Achieved | 0 | 1612.5 | On target | 2397.5 | Ontrack. 52% to annual target. | 4244 | Achieved 92% of target. Efforts to promote C&E awareness among lenders are ongoing and over time encouraging improvements have been noticed. | 6313 | Achieved 95% | 174% | 12416.5 | Achieved 174% On average, SMEs meeting Climate and Environment (C&E) criteria serve more SHF than other SMEs. This is because value chains such as cashew, coffee (with coop membership,many smallholder farmers) tend to meet C&E criteria | 0 | 0 | 0
|  | of which women | 0 | 659.5 | On target | 679.5 | On track. 49% to annual target. | 1452 | Above target (104%). | 2183 | Achieved 109% |  | 3333.5 | Achieved 156%. For a reason similar to that stated above. This number represents number of Ssmallholder farmesr affiliated to SMEs receiving loans that meet the C&E criteria AND meet the 2x gender challenge criteria. It is estimated that 30% of these smallholder farmers are women. |  |  | 0
Source: Lenders' data, Africert verfication visits with SMEs and sampled farmers
OUTCOME | Outcome Indicator 1 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique | Assumptions
A better business environment, increased investment (including climate and nature finance), improved business practices, and increased domestic and international trade. | Investment mobilised as a result of Aceli's activities (cumulative, includes: domestic investment, domestic direct investment, foreign direct investment, foreign portfolio investment). | Planned | 0 | 3493750 |  |  |  | 10143750 |  | 15754687.5 |  | 21006250 | 28186687.5 |  | 36250687.5 | 36250687.5 | 0 | Export value chains: coffee, cocoa, cotton, cashews, tea,vanilla,cloves, rice, avocado Political feasibility: the assessment of political feasibility in the options appraisal is correct and remains steady. Domestic economic stability: Tanzania’s current broadly positive economic trajectory continues and there is not a major economic crisis. Global economic recovery: the global economic recovery will continue its current trend, and the market for Tanzanian exports (notably agriculture and tourism) will grow. Private sector capacity: there are sufficient SMEs in Tanzania that are capable of responding to technical assistance and absorbing investment. Effective delivery: the contracted supplier is able to establish an office in Tanzania and recruit staff with the require expertise to implement the programme. Climate impacts: the climate change impacts on agriculture production will not be so severe as to render large proportions of the sector unviable within 10 years.
|  | of which meet the 2X Gender Challenge criteria | 0 | 1048125 |  |  |  | 3043125 |  | 7877343.75 |  | 10503125 | 14093343.75 |  | 18125343.75 | 18125343.75 | 0
|  | Achieved | 0 | 5092429 | Ahead of target: avg loan size was slightly higher than projected. This is primarly due to two loans $1.9M totall accounting for 43% of investment amount. | 5776019.41 | Ontrack. 57% to annual target. | 10351544.65 | Above target (102%) | 13427073.6452 | Achieved 85% |  | 28155392.57 | Achieved 99%
|  | of which meet the 2X Gender Challenge criteria | 0 | 4904429 | Ahead of target: we initially projected that 30% of Aceli's portfolio would be gender inclusive (aligned with the 2X collaborative international standard). We have been pleased to see 88% of Aceli's P4P portfolio meets this criteria. Also, we have had few loans with outlier (significantly above average) loan amounts. Given such outlier observations, and limited data of only 26 loans so far, we are not inclined to change our target. | 5410429.41 | Ahead of target. We are seeing a larger number of gender inclusive loans than initially anticipated. However, these observations are from a limited data set of 37 loans so far. | 7020683.22 | Above target (104%). Leadership (management,ownership, and board participation) contributes 43%. Employment, products for women, and women suppliers contrinute 57% | 9191789.22 | Achieved 117% |  | 17274486.642 | Achieved 123%
Source: Lenders' data
| Outcome Indicator 2 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| ICF KPI 12: Volume of private finance mobilised for climate change purpose as a result of Aceli's (cumulative). | Planned | 0 | 698750 |  |  |  | 2028750 |  | 4945921.5625 |  | 5818731.25 | 9359048.4375 |  | 12599048.4375 | 12599048.4375 | 0
|  | of which meet the 2X Gender Challenge criteria | 0 | 209625 |  |  |  | 608625 |  | 3214849.0156 |  | 3782175.3125 | 4679524.2188 |  | 6299524.2188 | 6299524.2188 | 0
|  | Achieved | 0 | 2133212.42 | Ahead of target: while we are significantly above target, one loan (out of 6) accounts for 50% of this total number. Therefore, our target was not underestimated, we just received a larger than expected loan. | 2296612.42 | Above annual target. Note however, that 1 loan out of 9 is accounting for 50% of total volume of finance achieved. | 4646944.85 | Above target(229%). Note however, that 3 loans out of 23 are accounting for 55% of total volume of finance achieved. | 6435200.85 | Achieved 130% |  | 11701590.849 | Achieved 125%
|  | of which meet the 2X Gender Challenge criteria | 0 | 2067212.42 | Ahead of target: we initially projected that 30% of Aceli's portfolio would be gender inclusive (aligned with the 2X collaborative international standard). We have been pleased to see 88% of our P4P portfolio meets this criteria. This is explains the difference between planned and acheived. We are not inclined to change our targets yet as overtime the number of gender inclusive loans may decrease as a proportion to our total portfolio. | 2230612.42 | Ahead of target. We are seeing a larger number of gender inclusive loans than initially anticipated. However, these observations are from a limited data set of 37 loans so far. Also one loan with outlier loan amount accounts for 50% of the amount | 2649942.43 | Above target (435%). Note however, that 3 loans out of 14 are accounting for 73% of total volume of finance achieved. | 4241398.43 | Achieved 132% |  | 7367888.43 | Achieved 157%. We had expected that 50% of the SME portfolio will meet 2X criteria, actually 59%of SMEs in the portfolio met 2X citeria.
Source: Lenders' data
| Outcome Indicator 3 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| Increase in sales and international trade as a direct result of Aceli's activities (latest annual sales figure, as measured by value of new purchase orders). | Planned: Total Sales | 0 | 902500 |  |  |  | 2280000 |  | 3135000 |  | 4180000 | 6375825 |  | 10280400 | 10280400 | 0
|  | of which meet the 2X Gender Challenge criteria | 0 | 270750 |  |  |  | 684000 |  | 2037750 |  | 2717000 | 4144286.25 |  | 6682260 | 6682260 | 0
|  | Planned: International Trade | 0 | 451250 |  |  |  | 1140000 |  | 1776500 |  | 2090000 | 3187912.5 |  | 5140200 | 5140200 | 0
|  | of which meet the 2X Gender Challenge criteria | 0 | 135375 |  |  |  | 342000 |  | 1154725 |  | 1358500 | 2072143.125 |  | 2570100 | 2570100 | 0
|  | Achieved: Total Sales | 0 | 782119.153 | Under target: our actual is slightly below target we view because the businesses are a bit smaller than expected. Since we are only below target by 15%, we don't propose to adjust our projection. | 1160604.1595 | On track. 51% to annual target. | 2625455.1175 | Achieved 85% of target. This is contributed by some SMEs being smaller in size, as evidenced by relatively smaller approved loan amounts, on average, than anticipated | 3356532.134 | Achieved 107% |  | 8091135.006 | Achieved 127% |  |  | 16015845.57
|  | of which meet the 2X Gender Challenge criteria | 0 | 753178.598 | Ahead of target: we initially projected that 30% of Aceli's portfolio would be gender inclusive (aligned with the 2X collaborative international standard). We have been pleased to see 88% of our P4P portfolio meets this criteria. This is explains the difference between planned and acheived. We are not inclined to change our targets yet as overtime the number of gender inclusive loans may decrease as a proportion to our total portfolio. | 918392.7935 | Ahead of target. We are seeing a larger number of gender inclusive loans than initially anticipated. However, these observations are from a limited data set of 37 loans so far. | 1724142.096 | Above target (152%). Contributed by some loans to SMEs with relatively high enteprise revenue and meeting gender inclusion criteria | 2185775.334 | Achieved 107% |  | 5240042.1816 | Achieved 126% |  |  | 10821531.0031
|  | Achieved: International Trade | 0 | 556717.5165 | Ahead of target: we do not feel this target was underestimated and propose not to make any changes. | 847525.5425 | On track. 74% to annual target. | 1576973.215 | Above target (138%). A good number of SMEs in traditional export value chains such as coffee, cashew have been supported. Also SMEs in emerging export crops i.e., avocado and rice have been supported. | 1590348.4018 | Achieved 90% |  | 3355704.541 | Achieved 105% |  |  | 7927269.2168
|  | of which meet the 2X Gender Challenge criteria | 0 | 530306.9615 | Ahead of target: we initially projected that 30% of Aceli's portfolio would be gender inclusive (aligned with the 2X collaborative international standard). We have been pleased to see 88% of our P4P portfolio meets this criteria. This is explains the difference between planned and acheived. We are not inclined to change our targets yet as overtime the number of gender inclusive loans may decrease as a proportion to our total portfolio. | 638775.9515 | On track. We are seeing a larger number of gender inclusive loans than initially anticipated. However, these observations are from a limited data set of 37 loans so far. | 892524.0895 | Ahead of target (161%). Contributed by some loans to SMEs in export value chains with relatively high enteprise revenue and meeting gender inclusion criteria | 921471.8925 | Achieved 80% |  | 2066698.7672 | Achieved 99% |  |  | 5049777.6622
Source: Lenders' data
| Outcome Indicator 4 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| Number of business environment reforms supported with government agencies. (cumulative). | Planned | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 1 | 1 | 1
|  | Achieved | 0 | 0 | On target | 0 | In progress and on target. In addition to policy mapping report, we recently published a working paper on impact of central bank policies to Agri lending in East Africa. We are working with partners to influence implementation of policy reforms | 0 | In progress. Policy mapping report published. Also published a working paper on impact of central bank policies to Agri lending in East Africa. Formation of a working group with other partners/stakeholders to further our work on policy in progress |  | In progress. Formation of working group with other partners to develop road map for policy advocacy in progress. |  | 0 | In progress. Stakeholder work group session held in March. Drafting of policy briefs ongoing
Source: Aceli reporting
“Policy reform” entails a change to legislation, strategy, or approach recorded in a public pronouncement; OR substantial improvements made to the operations of a government institution.
Output 1 | Output Indicator 1.1 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique | Assumptions
Aceli Africa. Mobilising investment for job-creating domestic agri-business ($50k-$2m ticket size), through (1) financial risk-sharing and (2) technical assistance to businesses and local/regional financial institutions. | [Process indicator] Develop and agree budget and workplan for Aceli Africa, agree Accountable Grant and mobilise in Tanzania. | Planned | - | C: Agree budget, logframe & workplan B: Complete enhancede due dliigence; acheive MAG approval; achieve Prof11 approval A: Sign accountable grant within 8 months of BC approval A+: Sign accountable grant within 4 months of BC approval A++: Sign accountable grant within 2 months of BC approval |  |  |  | - |  |  |  | - |  |  | - | - | - | For the number of loans, we are counting the total number. It is not possible to attribute loans to Aceli (although we can attribute unique SMEs that recive loans).
|  | Achieved | - | A+ |  |  |  | - |  |  |  | - |  |  | - | - | -
| Sub-Weight | Source
20%
| Output Indicator 1.2 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| Number of businesses receiving technical assistance (cumulative) | Planned | 0 | 4 |  |  |  | 14 |  | 34 |  | 38 | 51 |  | 61 | 61 | 61
|  | of which meet the 2x Gender Challenge criteria | 0 | 1.2 |  |  |  | 4.2 |  | 11.9 |  | 13.3 | 17.85 |  | 21.35 | 21.35 | 0
|  | Achieved | 0 | 4 | On target | 13 | On track. 93% to annual target | 28 | Above target. Increase in SME uptake of TA following introduction of Kiswahili language for early stage SMEs, as well as increased uptake of TA for growth/established SMEs because of more business development service providers in 2023 (from two to four providers) | 46 | Achieved 135%. |  | 63 | Achieved 124%
|  | of which meet the 2x Gender Challenge criteria | 0 | 0 | Under target: we anticipate that SMEs meeting the gender inclusion criteria will increase in additional cohorts. Therefore, we do not propose to adjust our targets | 1 | On track. 25% to annual target | 8 | Above target (200%) | 18 | Achieved 150% |  | 26 | Achieved 146%
| Sub-Weight | Source: SMEs in TA Program, Aceli reporting
20%
| Output Indicator 1.3 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 | March 2024-Comments | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-01 | Total Cumulative Unique
| Percentage of SMEs satsified with TA programme | Planned | [10 empty] | 70% |  |  |  | 0
|  | Achieved | [10 empty] | 89% | Achieved 127%
| Sub-Weight | Source: SMEs in TA Program, Aceli reporting
20%
| Output Indicator 1.4 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| Number of financial institutions actively lending in partnership with Aceli (cumulative) | Planned | 0 | 7 |  |  |  | 9 |  | 10 |  | 11 | 12 |  | 12 | 12 | 0
|  | Achieved | 0 | 7 | On target: we expect to accredit and onboard 3 to 5 additional lenders by end of the year. Please note that over time some lenders may drop out of the Aceli program if they don't meet the lender mandatory requirements for loan registration | 7 | On target. We expect to accredit and onboard 2 to 3 lenders by Q2 next year | 9 | Achieved (100%). We are in process to onboard two more lenders |  |  |  | 11 | Achieved 92%
| Sub-Weight | Source: Aceli Reporting
20%
| Output Indicator 1.5 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| Number of financial instituions receiving technical assistance (cumulative) | Planned | 0 | 0 |  |  |  | 1 |  | 1 |  | 1 | 2 |  | 4 | 4 | 0
|  | Achieved | - | 0 | On target | 0 | Two financial institutions have been identified as potential beneficiaries. We are also recruting more service providers (consultant(s)) in addition to the one we have in order to increase capacity to deliver TA to financial institutions | 1 | Ongoing Technical Asistance (capacity building) to Tanzania Commercial Bank (TCB) |  |  |  | 2 | Achieved 100%
| Sub-Weight | Source: Aceli Reporting
20%
| Output Indicator 1.6 |  | Baseline (Nov-2021) | 2022-06-30 |  |  |  | 2023-06-30 |  | 2024-03-01 |  | 2024-06-30 | 2025-03-01 |  | 2026-03-30 | 2027-03-31 | Total Cumulative Unique
| Number of loans approved as a result of Aceli's financial incentives (cumulative) | Planned | 0 | 23.75 |  |  |  | 60 |  | 101 |  | 110 | 240 |  | 312 | 312 | 0
|  | of which meet the 2x Gender Challenge criteria | 0 | 7.125 |  |  |  | 18 |  | 50.5 |  | 55 | 120 |  | 156 | 156 | 0
|  | Achieved | 0 | 26 | On target | 37 | On track. 62% to annual target | 75 | Ahead of target (125%) | 111 | Achieved 110% |  | 264 | Achieved 110% | - |  | -
|  | of which meet the 2x Gender Challenge criteria | 0 | 23 | Ahead of target: we initially projected that 30% of Aceli's portfolio would be gender inclusive (aligned with the 2X collaborative international standard). We have been pleased to see 88% of our P4P portfolio meets this criteria. This is explains the difference between planned and acheived. We are not inclined to change our targets yet as overtime the number of gender inclusive loans may decrease as a proportion to our total portfolio. | 31 | Ahead of target. We are seeing a larger number of gender inclusive loans than initially anticipated. However, these observations are from a limited data set of 37 loans so far. | 49 | Ahead of target (272%). We have seen a large number of loans registered meeting gender inclusion criteria during the period due to active engagement and building awareness among lenders | 72 | Achieved 141% |  | 157 | Achieved 131%
Weight | Sub-Weight | Source: Lenders' data, Aceli Reporting
60% | 20%
£ Inputs | 7500000 | HR Inputs | Lead: Alex Mangowi (30%); Adviser: Priti Prajapati (10%); Programme Manager: Evans Rwamuhuru (25%); Oversight: Euan Davidson (5%)
Note on I31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: approved loan amount for C&E loans

## Manufacturing Africa
Programme name: | Manufacturing Africa
|  | Year |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | MA prog. - year ending | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
IMPACT | Impact Indicator 1A | [10 empty] | Assumptions
Significantly increase FDI flows to the manufacturing sector stimulating inclusive economic transformation that generates new jobs and increases in the value of production in economy | Number of direct employees investors supported by MA have committed to engage at financial close as a direct result of the investment supported by Manufacturing Africa. (cumulative, unique people) [Maps to master logframe Impact Indicators 1A & 1B] | Planned |  | 0 | 120.5902 | 402.5574 | 884.5246 | 1366.4918 |  |  | 1366.4918
|  | Achieved (total) |  |  | 0
|  | Source and measurement approach | Data provided by investors / companies supported by MA at point of financial close. MA M&E team check in with investor / company to verify that business plan submitted previously still holds true, or whether adjustments need to be made to committed number of direct jobs based on amount of capital raised or other internal / external factors.
| Impact Indicator 1B |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of direct and indirect jobs MA helped create (gender disaggregated) | Planned |  | 0 | 242 | 806 | 1770 | 2732 | 3506 | 5419 | 5419
|  | Achieved (total) |  |  | 0
Achieved (direct jobs for men)
Achieved (direct jobs for women):
Achieved (indirect jobs):
|  | Source and measurement approach | Data to be collected from investors / companies 18-24 months after financial close. Direct jobs data will be based on actual employee contracts in the last financial year, whereas indirect jobs will be modelled using MA's development impact model using companies' revenues and local spend on inputs/raw materials as an input.
| Impact Indicator 2 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Relative growth of manufacturing output in priority sectors of the programme compared to growth in manufacturing output in each MA focus country. [Maps to master logframe Impact Indicator 2] | Planned |  | 0% | 0% | 1% | 1% |  |  |  | N/A - not cumulative
|  | Achieved |  |  | 2%
|  | Source and measurement approach | Data used to compare output in MA priority sectors with overall manufacturing sector output in Tanzania will be collected from MA company data (where supporting new sectors), national statistical agencies and World Bank data.
OUTCOME | Outcome Indicator 1 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Increased foreign direct investment that leads to significant productivity spillovers in the host economy while strengthening local institutions to attract and retain FDI. | Additional foreign direct investment generated by Manufacturing Africa (£ Billion) - Definition as per "deal signing" in PBR document. | Planned |  | 0 | 0.014634 | 0.04878 | 0.10732 | 0.16585 |  |  | 0.16585 | Other factors do not undermine the positive impact on investment. Potential factors include (but are not limited to): - Political unrest - Conflict - Global economic slowdown - Unavailability of finance Investor perceptions change in line with actual reforms
|  | Achived (total) |  |  | 0
|  | Source and measurement approach | Data collected at point of financial close from signed term sheets or investor press releases and recorded in Salesforce. The level of FDI will again be checked 18-24 months after financial close (to the extent that is reasonably possible) to ensure that funds have been disbursed and spent. FDI targets will include working capital facilitated as well as investment facilitated, reflecting the Covid context. This will apply up to the year ending 2022. Consideration will be given to extending this to cover the year ending 2023 as well accounting for the duration of Covid. A view will be taken on this at the 2021 Annual Review. Results should be reported separately for relevant years both for working capital facilitated and for investment facilitated.
| Outcome Indicator 3 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of deals which meet performance targets relating to high economic transformation or high positive climate impact | Planned |  | 0 | 0 | 0 | 1 | 3 | 5 |  | 5
|  | Achieved |  |  | 0
|  | Source and measurement approach | PBR element scores either a)above 10 total PbR points or b) 3 or more points for positive climate impact during a final check of PbR scores 18-24 months after financial close. This final check will be completed by MA's M&E team who will collect written evidence from companies / investors to support this. Final PbR scores will be signed off by an FCDO advisor and recorded in Salesforce.
| Outcome Indicator 4 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of International Climate Finance (ICF) interventions in the programme (either technical assistance or transaction facilitation) which have evidence of transformational climate impact (i.e. scoring 3 or 4 against ICF KPI 15) | Planned |  | 0 | 1 | 2 | 3 |  |  |  | 3
|  | Achieved |  |  | 0
|  | Source and measurement approach | MA's M&E and Climate and Environment teams will prepare a submission of ICF impact KPIs on an annual basis, which will include evidence of transformational impact for key interventions (as per ICF guidance). This will be used to provide evidence for this logframe indicator.
Intermediate Outcome 1 | Intermediate Outcome Indicator 1 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Number of qualifying FDI investments generated and supported by Manufacturing Africa in target countries. | Number of deals brought to financial close. [Maps to master logframe Intermediate Outcome Indicator 1.1] | Planned |  | 0 | 1 | 3 | 6 | 9 |  |  | 9 | Significant number of manufacturing MNEs are looking to relocate productive capacity in new low cost locations. Potential investments can be used to leverage regulatory changes and aftercare support in partner countries.
|  | Achieved |  |  | 0
|  | Source and measurement approach | Data collected at point of financial close from signed term sheets or investor press releases and recorded in Salesforce.
| Intermediate Outcome Indicator 2.2 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of market development technical assistance interventions designed and implemented in targeted sectors, which businesses assess as having successfully addressed key barriers to investment originating from either the public or private sector (e.g. lack of local skills, weak logistics, lack of infrastructure etc)" | Planned |  | 0 | 3 | 6 | 11 |  |  |  | 11
|  | Achieved |  | 0 | 0
|  | Source and measurement approach | Evidence of feedback from market actors (e.g. investors, businesses, industry associations) which demonstrates that TA has addressed key barriers to investment.
Intermediate Outcome 2 | Intermediate Outcome Indicator 2.1 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Improved manufacturing business environment and strengthened Government capacity to deliver foreign investor related services in targeted countries | Number of investment/business environment policy reforms supported with government agencies/ institutions (“Policy reform” entails a change to legislation or a change in strategy or approach by a government institution recorded in a public pronouncement); OR substantial improvements made to the operations of such an institution (as reflected by feedback from a leader in that organisation or beneficiaries of its services) | Planned |  | 0 | 1 | 1 | 2 |  |  |  | 4 | Technical inputs are internalised within partner Governments and are used in policy/decision-making - Political imperatives do not supersede the use of evidence based decision-making in the majority of cases - Partner Governments trusts the advice coming from the facility and uses the expertise available
|  | Achieved (total) |  |  | 0
Achieved (policy reform)
Achieved (improved operations)
|  | Source and measurement approach | Evidence of feedback from government agencies and IPAs which demonstrates policy reform or operational improvements have been implemented.
| Intermediate Outcome Indicator 2.2 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of market development technical assistance interventions designed and implemented in targeted sectors, which businesses assess as having successfully addressed key barriers to investment originating from either the public or private sector (e.g. lack of local skills, weak logistics, lack of infrastructure etc)" | Planned |  | 0 | 3 | 6 | 11 |  |  |  | 11
|  | Achieved |  |  | 0
|  | Source and measurement approach | Evidence of feedback from market actors (e.g. investors, businesses, industry associations) which demonstrates that TA has addressed key barriers to investment.
Intermediate Outcome 3 | Intermediate Outcome Indicator 3 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Business linkages for African firms facilitated by Manufacturing Africa. | Number of domestic enterprises that have secured contracts as upstream market providers in the value chain as a result of Manufacturing Africa. [Maps to master logframe Intermediate Outcome Indicator 3.1] | Planned |  | 0 | 1 | 2 | 3 |  |  |  | 6 | Sufficient local capacity to be included in MNE supply chains. Domestic enterprises trust the advice and facilitation coming from MA and uses the expertise available. Domestic firms can access finance to increase capacity as needed to supply MNEs.
|  | Achieved |  |  | 0
|  | Source and measurement approach | Written evidence from companies and investors which demonstrates that they have contracted upstream domestic enterprises to provide inputs or services after financial close and establishment of manufacturing operations.
Output 1 | Output Indicator 1.1 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Manufacturing businesses and investors provided with targeted transaction facilitation support, e.g. on investor memo development, investor outreach, business case development, market assessment and due diligence | Number of investment leads provided with high quality substantive support - i.e. Those that which the firm agrees had a significant positive impact on their investment decision [Maps to master logframe Output Indicator 1.1 & 1.3] | Planned |  | 2 | 13 | 24 | 34 |  |  |  | 73 | MNEs are willing to engage with and receive support from Manufacturing Africa. Significant number of manufacturing MNEs are looking to relocate productive capacity in new low cost locations. Potential investments can be used to leverage regulatory changes and aftercare support in partner countries.
|  | Achieved |  | 3 | 13
|  | Source and measurement approach | Deals which are at "support completed" stage in Salesforce.
| Output Indicator 1.2 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of deals supported which qualify as "highly economically transformative". [Maps to master logframe Output Indicator 1.2] | Planned |  | 1 | 6 | 12 | 17 |  |  |  | 36
|  | Achieved |  | 3 | 10
|  | Source and measurement approach | Deals which are at "support completed" stage in Salesforce and which are expected to score 10 or more PbR points.
| Output Indicator 1.3 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of deals provided with substantive support which have been screened for Basic Compliance related to Gender, Economic and Social Inclusion (as evidenced by a completed GESI DD Form) . [Maps to master logframe Output Indicator 2.1 [2x Challenge] | Planned |  | 2 | 13 | 24 | 34 |  |  |  | 73
|  | Achieved |  | 3 | 13
|  | Source and measurement approach | Evidence of GESI DD forms completed for all deals supported.
Output 2 | Output Indicator 2 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Government agencies / institutions supported or influenced to improve policy and operations in response to problems impeding FDI (especially those holding back identified potential investments) – e.g. targeted at investment policies, local content strategies, special economic zones etc | Number of substantive technical assistance deliverables (i.e. entailing at least 10 days of support) supporting government agencies / institutions approved and implemented to a high-quality standard (as assessed by the FCDO advisor, drawing on recipient feedback). [Maps to master logframe Output Indicator 2.1] | Planned |  | 0 | 1 | 3 | 6 |  |  |  | 10 | Government requests support in areas that are relevant to the current/future investment programme Technical inputs are internalised within partner Governments and are used in policy/decision-making - Political imperatives do not supersede the use of evidence based decision-making in the majority of cases - Partner Governments trusts the advice coming from the facility and uses the expertise available - Government requests support in areas that are relevant to the current/future investment programme
|  | Achieved |  | 0 | 1
|  | Source and measurement approach | Final TA project deliverables approved by FCDO. Each standalone deliverable which entailed at least 10 days of support within a TA call down supporting a government institution will count towards the target here. For example, if under one call down MA supports an Investment Promotion Authority to develop pitch decks for two different sectors and redesign its aftercare process, this will count as 3 substantive deliverables.
Output 3 | Output Indicator 3.1 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Wider support (beyond just Government) to address problems impeding manufacturing FDI (especially those holding back identified potential investments or linked activity) – e.g. skills development, support for local input providers, lack of infrastructure etc | Number of support programmes (i.e. standalone projects entailing at least 10 days of support), guided by market systems principles, designed and implemented by the contractor in targeted sectors which address key barriers to manufacturing activity, and which are delivered to a high standard (as assessed by the FCDO advisor, drawing on recipient feedback). [Maps to master logframe Output Indicator 3.1] | Planned |  | 0 | 6 | 12 | 23 |  |  |  | 41 | Certain key issues impeding identified investors can be addressed within a reasonable time frame (c.2 years) Other FCDO programmes and development partners are open to collaboration and co-funding initiatives alongside MA.
|  | Achieved |  | 2 | 3
|  | Source and measurement approach | Final TA project deliverables approved by FCDO. Each standalone deliverable which entailed at least 10 days of support within a TA call down focused on market systems development will count towards the target here. For example, if under one call down MA implements an e-mobility pilot and convenes investors and provides capacity building to plastic recycling SMEs around standards, this will count as 2 substantive deliverables.
| Output Indicator 3.2 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final)
| Number of third parties (other FCDO programmes, other donors, charities, philanthropic organisations etc) substantially engaged with (i.e. at least 5 days time invested), in a way judged to be effective (as assessed by the FCDO advisor, drawing on recipient feedback) to undertake new activity targeted at addressing key barriers to manufacturing activity. [Maps to master logframe Output Indicator 3.2] | Planned |  | 0 | 1 | 2 | 4 |  |  |  | 7
|  | Achieved |  | 0 | 3
|  | Source and measurement approach | Evidence of MA working with partner programmes or organisations to address barriers to manufacturing.
Output 4 | Output Indicator 4.1 |  | Baseline | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | Target (Final) | Assumptions
Support to investors and manufacturers to strengthen upstream and downstream linkages | Number of support packages provided either to foreign investors to encourage them to increase demand from domestic enterprises, or to domestic enterprises themselves to enable them to meet such demand (entailing at least 5 days of support, and implemented to a high-quality standard as reviewed by the FCDO advisor, drawing on recipient feedback). [Maps to master logframe Output Indicator 4.1] | Planned |  | 0 | 2 | 4 | 6 |  |  |  | 12 | Sufficient local capacity to be included in MNE supply chains. Domestic enterprises trust the advice and facilitation coming from MA and uses the expertise available. Domestic firms can access finance to increase capacity as needed to supply MNEs.
|  | Achieved |  | 0 | 3
|  | Source and measurement approach | Evidence of TF work packages which help investors and businesses source from domestic enterprises as saved in Salesforce.
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why not report which meet 2x?

## ODI
Tanzania Productivity for Prosperity (P4P)
Project number 300116-401
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Sucessful formulation and delivery of TDV2050 | TDV2050 that includes policy considerations based on economic transformation priorities and increased knowledge of Tanzania's financial sector contribution. | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Commitment to finance economic transformation inititaives aimed at producing equitable development outcomes, creating jobs and reducing poverty by the Government of Tanzania | Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Ministry of Investment and Planning (MIP) and Planning Commission (PC) are equiped to draft TDV2050 | Increased technical knowledge and capacity of MIP and PC staff. | Planned
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Increased technical knowledge and capacity of TDV2050 drafters, planning comission and Permananet Secretaries and Deputy permanent Secretaries and LTPP | Planned
Achieved
Source
INPUTS (£) | FCDO (£) |  | Appeal income (£) | Other (£) | Total (£) | FCDO SHARE (%)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumption
Increased knowledge based on research to support the formulation of TDV20250 | Economic analysis on Economic Transformation | Planned |  | Draft research paper | Final research Paper
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Production of research paper on financing Financing Tanzania’s Development Vision 2050 | Planned |  | Draft research Paper | Final research paper
Achieved
Source
WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Deep dive paper | Planned |  | Draft Outline and draft paper | Final Deep dive paper
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  | Appeal income (£) | Other (£) | Total (£) | FCDO SHARE (%)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
TDV Support | signing MOU with the Ministry and Planning Commisson | Planned | 0 | Signed MOU
Achieved
Source
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Provision of technical assistance to Planning comission such as peer review and advisory support | Planned |  | On going
Achieved
Source
WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  | Appeal income (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Capacity Building | Capacity building workshops for TDV2050 drafters, planning comission staff and Permananet Secretaries and Deputy permanent Secretaries and LTPP | Planned | 0 | 14?12/2023 | 01/06/2024
Achieved
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Deep Dive Workshop | Planned | 0 | 2025-03-15
Achieved
Source
WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
INPUTS (£) | FCDO (£) |  | Appeal income (£) | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Green Growth Facility
UK-Tanzania Green Growth Fund
Result level | Indicator |  | Cumulative or annual | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
IMPACT | Impact Indicator 1
Sustainable economic transformation in Tanzania through increased labour productivity and climate-resilience in job-creating sectors. | Number of new jobs and number of jobs with improved incomes as result of the Facility's activities Disaggregated by results for (i) Gender, (ii) direct and indirect jobs, (iii) projection and actuals | Planned: new jobs | Cumulative | 0 | 0 | 0 | 0 | 333 | 1000
|  | of which women | Cumulative | 0 | 0 | 0 | 0 | 100 | 300
|  | Planned: jobs with improved incomes | Cumulative | 0 | 0 | 0 | 0 | 8333.3333 | 25000
|  | of which women | Cumulative | 0 | 0 | 0 | 0 | 2500 | 7500
|  | Achieved: new jobs | Cumulative |  | 0 | 580
|  | of which women | Cumulative |  | 0 | 66
|  | Achieved: jobs with improved incomes | Cumulative |  | 0 | 6
|  | of which women | Cumulative |  | 0 | 3
For source data and other measurement details, see GGF's indicator reference sheets.
OUTCOME | Outcome Indicator 1 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01 | Assumptions
A better business environment, increased investment (including climate and nature finance), improved business practices, and increased domestic and international trade. | Volume of investment mobilised Disaggregated by (i) Projections and actuals (further disaggregated by (a) investments that have secured an investor commitment, such as a term sheet and (b) investments disbursed), (ii) Direct and indirect investment (iii) 2X Challenge sales and non-2X Challenge firms | Total volume of investment – planned | Cumulative | 0 | 0 | 1110800.969 | 2864129.796 | 5631648.0657 | 10000000
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | 333240.2907 | 859238.9388 | 1689494.4197 | 3000000
|  | Total committed investment – planned | Cumulative | 0 | 0 | 1110800.969 | 2864129.796 | 5631648.0657 | 10000000
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | 333240.2907 | 859238.9388 | 1689494.4197 | 3000000
|  | Total disbursed investment – planned | Cumulative | 0 | 0 | N/A – this aggregation was created in Y2.
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | N/A – this aggregation was created in Y2.
|  | Total volume of investment – achieved | Cumulative |  | 0 | 1119400
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 418000
|  | Total committed investment – achieved | Cumulative |  | 0 | 701400
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 0
|  | Total disbursed investment – achieved | Cumulative |  | 0 | 418000
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 0
For source data and other measurement details, see GGF's indicator reference sheets.
| Outcome Indicator 2 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01 | Assumptions
| Volume of private investment mobilised for climate change purposes (i) Projections and actuals (further disaggregated by (a) investments that have secured an investor commitment, such as a term sheet and (b) investments disbursed), (ii) Direct and indirect investment, (iii) investment mobilised for 2X Challenge firms and non-2X Challenge firms | Total investment for climate – planned | Cumulative | 0 | 0 | 833100.7268 | 2148097.347 | 4223736.0493 | 7500000
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | 249930.218 | 644429.2041 | 1267120.8148 | 2250000
|  | Total committed investment for climate – planned | Cumulative | 0 | 0 | 833100.7268 | 2148097.347 | 4223736.0493 | 7500000
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | 249930.218 | 644429.2041 | 1267120.8148 | 2250000
|  | Total disbursed investment for climate – planned | Cumulative | 0 | 0 | N/A – this aggregation was created in Y2.
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | N/A – this aggregation was created in Y2.
|  | Total investment for climate – achieved | Cumulative |  | 0 | 858000
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 418000
|  | Total committed investment for climate – achieved | Cumulative |  | 0 | 0
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 0
|  | Total disbursed investment for climate – achieved | Cumulative |  | 0 | 418000
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 418000
For source data and other measurement details, see GGF's indicator reference sheets.
| Outcome Indicator 3 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Increase in firm revenues Disaggregated by (i) Direct and indirect sales (ii) 2X Challenge sales and non-2X Challenge sales, (iii) national and international sales | Planned – Total sales | Cumulative | 0 | 0 | 0 | 1744576.3019 | 4766271.0944 | 10000000
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | 0 | 523372.8906 | 1429881.3283 | 3000000 | 3000000
|  | Planned – International Trade | Cumulative | 0 | 0 | 0 | 872288.1509 | 2383135.5472 | 5000000
|  | of which meet the 2X Gender Challenge criteria | Cumulative | 0 | 0 | 0 | 261686.4453 | 714940.6642 | 1500000
|  | Achieved – Total sales | Cumulative |  | 0 | 538312 | 0
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 0 | 0
|  | Achieved – International Trade | Cumulative |  | 0 | 22620 | 0
|  | of which meet the 2X Gender Challenge criteria | Cumulative |  | 0 | 0 | 0
For source data and other measurement details, see GGF's indicator reference sheets.
| Outcome Indicator 4 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Number of politically informed, substantive business environment reforms progressed with government agencies Disaggregated by (i) Policy reform and Government systems-building activities, (ii) policy reform stage, as outlined in GGF’s policy reform tracker. | Planned – politically informed, substantive business environment reforms progressed with government agencies | Cumulative | 0 | 0 | 2 | 5 | 8 | 12
|  | Planned – of which reach 'high level response' (stage 3) | Cumulative | 0 | 0 | 2 | 5 | 8 | 10
|  | Planned – of which reach 'formal policy change' (stage 4) | Cumulative | 0 | 0 | 0 | 0 | 0 | 2
|  | Actual – politically informed, substantive business environment reforms progressed with government agencies | Cumulative | 0 | 0 | 3
|  | Actual – of which reach 'high level response' (stage 3) | Cumulative | 0 | 0 | 3
|  | Actual – of which reach 'formal policy change' (stage 4) | Cumulative | 0 | 0 | 0
For source data and other measurement details, see GGF's indicator reference sheets.
| Outcome Indicator 5 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Emissions reduced or avoided that have been supported by ICF TA (ICF TA KPI 5) FCDO’s ICF TA KPI 5 guidance note outlines the following types of disaggregation: (i) sector, (ii) type of TA, and (iii) actor that has delivered the emissions abatements. GGF will also (iv) disaggregate between actuals and projections. | Planned - total emissions reduced or avoided | Cumulative | 0 | 0 | 0 | 130843 | 357470 | 750000
|  | Achieved - total emissions reduced or avoided | Cumulative |  | 0 | 219
For source data and other measurement details, see GGF's indicator reference sheets.
| Outcome Indicator 6 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Hectares of land that have received sustainable land management practices FCDO’s ICF KPI 17 guidance note outlines the following types of disaggregation: (i) sustainable management theme: management, restoration or protection, (ii) sustainable management practice (SMP) group, (iii) ecosystem type, and (iv) results achieved and results projected | Planned - total hectares of land | Cumulative | 0 | 0 | 0 | 117758.9004 | 185746.9004 | #REF!
|  | Achieved - total hectares of land | Cumulative |  | 0 | 345163
For source data and other measurement details, see GGF's indicator reference sheets.
| Outcome Indicator 7 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Number of intervention areas with evidence that it is leading to transformational market systems changes | Planned | Cumulative | 0 | 0 | 0 | 0 | 1 | 3
|  | Achieved | Cumulative |  | 0
For source data and other measurement details, see GGF's indicator reference sheets.
OUTPUTS | Output Indicator 1 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01 | Assumptions
Improved climate policies, and stronger UK-Tanzania economic cooperation through demand-driven technical assistance. | Number of Government policy reform, systems building, and capacity building initiatives that GGF undertakes with Government or other influential ecosystem actors, through an approved SOW. | Planned – total SoWs | Annual | N/A | N/A – this output indicator was created in Y2. | 3 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have climate impact | Annual | N/A | N/A – this output indicator was created in Y2. | 1 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have gender impact | Annual | N/A | N/A – this output indicator was created in Y2. | 0 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved – total SoWs | Annual | N/A | N/A | 4
|  | Of which have climate impact | Annual | N/A | N/A | 1
|  | Of which have gender impact | Annual | N/A | N/A | 0
| Weight | For source data and other measurement details, see GGF's indicator reference sheets.
30%
| Output Indicator 2 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Number of business innovations to support growth, investment readiness, and/or exports, that GGF supports through private or public actors, through an approved SOW | Planned – total SoWs | Annual | N/A | N/A – this output indicator was created in Y2. | 4 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have climate impact | Annual | N/A | N/A – this output indicator was created in Y2. | 1 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have gender impact | Annual | N/A | N/A – this output indicator was created in Y2. | 1 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved – total SoWs | Annual | N/A | N/A | 4
|  | Of which have climate impact | Annual | N/A | N/A | 3
|  | Of which have gender impact | Annual | N/A | N/A | 2
| Weight | For source data and other measurement details, see GGF's indicator reference sheets.
30%
| Output Indicator 3 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Number of supporting functions and services that GGF helps to develop to overcome constraints to market development, through an approved SOW | Planned – total SoWs | Annual | N/A | N/A – this output indicator was created in Y2. | 2 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have climate impact | Annual | N/A | N/A – this output indicator was created in Y2. | 0 | Target set annually. | Target set annually. | Target set annually.
|  | Of which have gender impact | Annual | N/A | N/A – this output indicator was created in Y2. | 0 | Target set annually. | Target set annually. | Target set annually.
|  | Achieved – total SoWs | Annual | N/A | N/A | 3
|  | Of which have climate impact | Annual | N/A | N/A | 0
|  | Of which have gender impact | Annual | N/A | N/A | 2
| Output Indicator 4 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Percentage of completed SOWs approved by FCDO without substantial revision. Disaggregated by (i) Percentage without substantial revision by Outputs 1, 2 and 3 and (ii) percentage without substantial revision by workstream | Planned - Completed SoWs | Annual | 0 | N/A – this output indicator was created in Y2. | 85% | Target set annually. | Target set annually. | Target set annually.
|  | Of which contributes to Output 1 | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Of which contributes to Output 2 | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Of which contributes to Output 3 | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Of which is under TAF workstream | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Of which is under carbon markets workstream | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Of which contributes to investment markets workstream | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Of which contributes to high value crops workstream | Annual | 0 | N/A – this aggregation was created in Y2. | N/A – this aggregation was created in Y2. | Target set annually. | Target set annually. | Target set annually.
|  | Achieved - Completed SoWs | Annual |  | N/A | 100%
|  | Of which contributes to Output 1 | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which contributes to Output 2 | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which contributes to Output 3 | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which is under TAF workstream | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which is under carbon markets workstream | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which contributes to investment markets workstream | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which contributes to high value crops workstream | Annual |  | N/A – this aggregation was created in Y2. | 100%
For source data and other measurement details, see GGF's indicator reference sheets.
| Output Indicator 5 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| Percentage of SoWs agreed approved in the preceding reporting year, submitted and approved by FCDO by the end of the review year. Disaggregated by (i) Percentage completion by Outputs 1, 2 and 3 and (ii) percentage completion by workstream | Planned - Approved SoWs | Annual | 0 | N/A – this output indicator was created in Y2. | 75% | Target set annually. | Target set annually. | Target set annually.
|  | Of which contributes to Output 1 | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Of which contributes to Output 2 | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Of which contributes to Output 3 | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Of which is under TAF workstream | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Of which is under carbon markets workstream | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Of which contributes to investment markets workstream | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Of which contributes to high value crops workstream | Annual | 0 | N/A – this aggregation was created in Y2.
|  | Achieved - Approved SoWs | Annual |  | N/A | 70%
|  | Of which contributes to Output 1 | Annual |  | N/A – this aggregation was created in Y2. | 67%
|  | Of which contributes to Output 2 | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which contributes to Output 3 | Annual |  | N/A – this aggregation was created in Y2. | 0%
|  | Of which is under TAF workstream | Annual |  | N/A – this aggregation was created in Y2. | 75%
|  | Of which is under carbon markets workstream | Annual |  | N/A – this aggregation was created in Y2. | 100%
|  | Of which contributes to investment markets workstream | Annual |  | N/A – this aggregation was created in Y2. | 50%
|  | Of which contributes to high value crops workstream | Annual |  | N/A – this aggregation was created in Y2. | 100%
For source data and other measurement details, see GGF's indicator reference sheets.
| Output Indicator 6 |  |  | Baseline (Aug.-2023) | 2024-03-31 | 2025-03-31 | 2026-03-01 | 2027-03-01 | 2027-12-01
| GGF implements a system to track learning and how it informs programme management decision making. | Planned | Annual | 0 | N/A – this output indicator was created in Y2. | System has been designed and put into practice in Y2 of the Programme. | Target set annually. | Target set annually. | Target set annually.
|  | Achieved | Annual |  | N/A | MEL system had been designed and put into place in Y2 | N/A | N/A | N/A
For source data and other measurement details, see GGF's indicator reference sheets.