## Annual Review 2025
Title: Productivity for Prosperity (P4P)
Programme Value £ (full life): 35,000,000		Review date: August 2025
Programme Code: 300116	AMP start date: August 2021	AMP end date: December 2027

Summary of Programme Performance
Year	2022	2023	2024	2025	2026	2027
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Major	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300116/documents
DevTracker Link to results framework:

## A. SUMMARY AND OVERVIEW

Description of programme
Productivity for Prosperity (P4P) is the British High Commission in Tanzania’s (BHC’s) flagship sustainable prosperity programme. The programme supports the UK’s growth and climate objectives in Tanzania. P4P’s goal is to support sustainable economic transformation in Tanzania through increased productivity and climate-resilience in job-creating sectors. P4P achieves this through investment facilitation and business environment support. P4P aims to catalyse at least £100mn of investment in job creating and climate sectors, while supporting 10,000 jobs and raising incomes for 125,000 people. At least 75% of P4P spend is climate focused; the programme contributes to five International Climate Finance (ICF) Key Performance Indicators (KPIs), supporting the UK’s commitment to provide £11.6bn in climate finance by 2025.
[note] ICF KPI 4 (people whose climate resilience improved), ICF KPI 5 (emissions reduction or avoided/supported by ICF technical assistance), ICF KPI 12 (private finance mobilized for climate change purpose), ICF KPI 15 (extent to which ICF intervention is likely to lead to transformational changes), and ICF KPI 17 (area under sustainable land management practices)
P4P’s flexible design enables it to respond to emerging UK and Tanzanian climate and prosperity priorities. P4P has four workstreams, summarised as follows:
Aceli Africa (£7.5m). Aceli works with 11 financial institutions to provide financial incentives (loan guarantees/first loss cover and origination incentives) to increase investment in high-potential agribusinesses. Aceli’s financial incentives support loan sizes from £11k to £1.27m, targeting the critical “missing middle” in small and medium enterprise (SME) financing needed to drive economic diversification and job growth. Aceli provides impact bonuses for investment in businesses that support food security, women, youth employment, and the adoption of climate smart agriculture. To date, it has mobilised over £20.8 million in investment for Tanzanian businesses, with £12.8 million directed toward gender-inclusive SMEs. In addition to financial incentives, Aceli offers technical assistance at the pre- and post-investment stages. Aceli commenced P4P implementation in October 2021 earlier than other components and a 5-year timeframe was agreed initially with a view to considering extensions in line with the Business Case time frame based on performance and strategic alignment.

Manufacturing Africa (MA, £11m). MA is one of the UK’s Centres of Expertise and works with African governments and international companies to attract large-scale Foreign Direct Investment (FDI) into the manufacturing sector. MA targets investment sizes from £1.5m upwards. To date, across Africa, MA has raised £37 for every £1 spent (given a 12-month period to close) and has raised £2bn since 2019. MA is well-established in Kenya, Nigeria, Senegal, Rwanda, and Ethiopia. P4P jointly-funded the expansion of MA into Tanzania in August 2023. In Tanzania, MA is supporting 11 companies to be investment ready through the transaction facilitation workstream and providing technical assistance to the Ministry of Minerals on investment opportunities in value addition. MA contributes to the 1% target of annual growth of the sector in manufacturing in Tanzania, so far supporting the potential raising of £166m of FDI from supported deals in Tanzania by December 2027.

UK-Tanzania Green Growth Facility (GGF, £11-16m). The GGF provides rapid, flexible, demand-driven technical support – such as policy research or technical assistance to the Government, private sector, or other partners critical to unlock investments and jobs. The GGF also complements BHC external engagements, supporting the UK’s economic and climate diplomacy. The programme supports business environment reforms, aims to create 1000 new jobs and support 25,000 people with increased incomes, and mobilise over £7.4m in private investment. The GGF contract commenced in August 2023.

4.Support to the Government of Tanzania (GoT) on economic planning (ODI, £0.7m). ODI provides demand-driven Technical Assistance to the National Planning Commission. The assistance is supporting the design of the Tanzania Development Vision 2050 (TDV2050) with a focus on economic transformation and leveraging the role of the private sector in Tanzania’s inclusive growth. ODI work under P4P commenced in November 2023 and expected to end in March 2026.

In addition, P4P enables the BHC to deliver strong results against the Mutual Prosperity Partnership (MPP), signed between UK and Tanzanian Governments in April 2024 to deepen shared prosperity goals. P4P gets behind Government of Tanzania’s economic and poverty reduction goals, including Vision 2050 and key business environment reforms. The programme’s flexible design allows it to adapt to evolving political and economic dynamics, a crucial feature as Tanzania approaches its 2025 elections, and the FCDO navigates the new spending review.

Summary supporting narrative for the overall score in this review
P4P achieved an A rating, having met majority of its planned targets.
Key achievements this year include:
The programme’s contribution to the Mutual Prosperity Partnership has been widely recognised, including programme activities such as the Natural Extracts Industry and Horticulture Export Accelerator Programme which have been commended by the Tanzanian Minister for Investment and Planning. Several programme results (GGF’s carbon markets finance, MA’s critical minerals perspective) were also highlighted at the one-year MPP anniversary event as key achievements.
1. Aceli facilitated 264 loans to agricultural and climate focused SMEs, surpassing its target of 240. Notably, 157 of these loans met the 2X Challenge gender criteria. The growth trend of women owned SMEs as a percentage of all SMEs supported by Aceli has been 8% in 2022, 13% in 2023, and 25% in 2024. The agribusinesses supported have potential for increased lending support from financial institutions. The programme is supporting banks to lend to new value chains including cassava, and to new underserved geographies, such as Unguja and Mafia islands in Tanzania.
2. MA. In this review period MA grew its pipeline of companies significantly, 10 investment deals were approved for support, totalling a potential £52.4m in FDI. These opportunities span agri-processing (six deals), forestry (two), medical equipment (one), and chemicals (one) as well as Commercial Diligence Analysis (CDA) for a pioneering electric vehicles company. MA’s ground-breaking technical assistance to Government of Tanzania on Minerals Value Addition has received very positive feedback from senior Ministers and Government. The work provides the Government with the options it can pursue to create further value addition in critical minerals. The report was launched by the UK Minister for Africa and Tanzania Minister of Minerals in February 2019. The findings were later presented as a success story at the Mutual Prosperity Partnership one year anniversary event in Dodoma. BHC further disseminated the findings at a side event of the East Africa Trade and Investment Forum in May 2025. Finally, it was presented to the Chief Secretary and all Permanent Secretaries in July 2025.
3. GGF launched the Horticultural Export Accelerator Programme (HEAP) initiative. The initiative has facilitated Tanzanian SMEs to link to buyers in UK and Europe. As a result, Fruit Logistica has secured avocado orders to India via one the leading UK exporter, with an initial value of £270,000. Another Tanzania Horticultural Association member, a women-led enterprise, increased her vegetable exports from 15 to 25 tonnes thanks to market linkages. HEAP also brokered linkages for Tanzanian companies exporting cashew, tea/coffee, and herbs and spices to UK, EU and Middle East. Another significant GGF result was through Village Climate Solutions (VCSL), a Tanzanian carbon market developer. GGF also delivered strategically the technical assistance to Tanzania’s Fair Competition Commission (FCC), the Public Private Partnership Centre, and the Tax Ombudsman of Tanzania as well as work to support Zanzibar on clean energy (net metering) and sustainable tourism. These efforts are on track to support sustainable growth models, improve the business environment and unlock barriers to private investment.
4. ODI supported the development of Tanzania Development Vision 2050 (TDV2050) and the Long-Term Perspective Plan through strategic engagement with senior officials and delivery of deep dives on transport and financing. These informed national planning processes, prioritised transformative sectors, and laid the foundation for future BHC support to unlock inclusive, private sector driven economic growth. The UK was able to respond quickly to the opportunity to engage on Vision 2050 and offer continued support to this once in a generation planning process.

Major lessons and recommendations for the year ahead
Major lessons:
- Government buy-in and local partnerships. The Critical Minerals work demonstrated the need to ensure early buy-in from Government and a local stakeholder engagement plan built in from the start. Local partnerships matter for sustainable results.
- Ensure interventions are embedded within the local context; some project staff are posted overseas and bring excellent international and technical experience. However, an on the ground team members in Tanzania needs to be involved in every programme activity to ensure relationships are maintained, opportunities are not missed, and the activity is evolving in real time.
- Coordination is occurring but there are ongoing gaps and this could be deepened. meetings have improved information flow and referrals of companies and project ideas between partners. However, gaps remain between the presence and needs of the investors, the information investors have on investible companies in Tanzania. Gaps also exist for the companies supported, their investment size and the type of support offered by P4P partners in investment readiness.
- Many transformations and market systems changes are not yet being captured by the results reporting. For example, changes in financial institutions behaviour (sustained increases in lending to smallholder farmers), increasing access to climate finance in agriculture and carbon market; establishing pathways to scale for small businesses through working across P4P partners (through transfers between partners).
- Small bets and learning and adaptation: in the first two years the programme was identifying where it could deliver results and impact and many ‘small bets’ were taken. As the programme is at mid-point, it is a good time for partners to make decisions on where to focus. GGF learning and business environment trackers are useful tools in this regard.

Recommendations:
- Prioritise and consolidate. The BHC will need to review P4P’s focus in light of evolving strategic priorities. The programme will need to be prioritised to focus on the areas where the evidence is strongest, the Government demand is high, and where we can have the most demonstrable impact on results. Partners should report to FCDO on how they are progressing on prioritisation, consolidation and focus by September 2025. Improving results reporting on narrower transformations in the market systems or institutional behaviour should be better captured.
- General election. P4P will need to manage risks and respond to opportunities presented by the general election in October 2025. Whilst the election year environment may pose some challenges for private sector (delays for investment, taxation), the programme is well placed to seize new post-election relationships and policy announcements to improve investment and trade. All partners should report to FCDO on risks, impacts and opportunities before (August) and after the election (October-November 2025) within existing reporting mechanisms.
- Accelerate the Invest for Impact Tanzania initiative. To improve coordination and plug gaps, there’s an opportunity to further bring efforts of GGF, MA and Aceli under a new cross P4P initiative which links impact investors (BII, FMO and other private equity and venture capital funds) with companies based in Tanzania seeking investment. The design of Invest for Impact Tanzania (IIT) currently under scope by GGF should be accelerated in order to:
  1. Bring together the offer more coherently between GGF and MA support. MA and GGF both proposed to offer investment readiness. Bringing these offers together promotes greater coordination and cohesion of FCDO funding.
  2. Bridge the gap between investment-ready businesses and investors. GGF’s Invest for Impact proposal is designed to address this gap by offering targeted support that accelerates deal closures for growth-oriented Tanzanian companies supported by GGF and MA. Given its strategic alignment and potential for high impact, it is recommended that the Invest for Impact proposal be supported and accelerated.
  3. Embed flexibility. To better serve businesses seeking investment, it's important to incorporate flexibility into the support provided. Different investors require distinct financial models. Partners should tailor their support to accommodate varying investor requirements. One effective approach is to involve businesses in the design of their financial models. This builds internal capacity and ensures that if adjustments are needed to meet specific investor criteria, businesses are equipped to make those changes independently.

Monitor systemic change in financial institutions. P4P activities are designed to shift institutional behaviour (financial institutions) in favour of previously underserved businesses. Delivery partners should capture and report these behavioural shifts. For example, Aceli provides TA and financial incentives to financial institutions to stimulate lending to agribusinesses which is currently underserved due to a lack of available diverse financial products, asymmetric information and driving high collateral requirements. It also supports SMEs in becoming more bankable and meeting lending criteria. This dual approach is beginning to yield results, banks like Tanzania Commercial Bank are now actively developing agriculture-focused lending products. Such developments could be signalling a meaningful shift in lender behaviour, demonstrating that the programme is driving systemic change in the financial sector. Similarly, GGF’s Simbuka programme is designed to incentivise financial institutions to provide working capital and invoice financing to underserved businesses, GGF should put in place measures to collect data to monitor how the work is impacting choices and adoption by financial institutions.

- Continue to strengthen Government engagement to address ecosystem barriers. Partners should deepen their collaboration with the Government of Tanzania to address systemic barriers. This includes strategically leveraging BHC to advocate for targeted sector reforms that create a more enabling environment for private sector growth. For example, government agricultural boards have been cited as obstructive to industry development. Supporting sector stakeholders to advocate for reform in these bodies could unlock growth in agriculture. Additionally, persistent logistical constraints, particularly the limited availability of air freight for agricultural exports, could be addressed by encouraging government to incentivise airlines to transport Tanzania’s agricultural products, especially perishable goods.
- Strengthen clarity on additionality and business selection criteria. All delivery partners should be more explicit in demonstrating additionality, clearly showing that the outcomes achieved would not have occurred without programme support. This includes improving how results are reported. Additionally, partners should consider refining their business selection criteria to prioritise enterprises with stronger potential for profitability and long-term sustainability. Selecting businesses with a clear path to financial independence will help enhance the programme’s impact and ensure value for money.

In order to support the BHC’s communications priority around growth and climate, partners should on an ongoing and minimum two monthly basis report to the BHC on communications opportunities on programme results as well as continue to participate at the Mutual Prosperity Partnership events. BHC to link Programme partners communications leads with BHC Communication Lead to discuss the BHC growth and climate campaigns in September 2025.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
P4P aims to contribute to sustainable and inclusive economic transformation in Tanzania. This is achieved through:
- Strengthening the business environment and practices (through technical assistance to businesses and Government, and facilitation between Government, the private sector and civil society) [All Outputs] and
- Increasing investment and trade (through reducing investment risks for businesses and financial institutions and increasing incentives, research and facilitation), with a focus on climate and job producing sectors. [GGF, Aceli and MA]

The outcome and impact indicators have not changed over the last year. The Theory of Change was reviewed as part of this Annual Review, with some updates to the outputs to improve clarity. The review confirmed that the broad output-impact theory was still valid, and the programme is working in the right sectors to facilitate more productive, sustainable and inclusive growth. However, this high-level Theory of Change did not fully capture the positive narrower transformational changes which the programme is focusing on, and how these are being delivered across the partners. Examples include sustained increases in lending to smallholder farmers by national financial institutions; increasing access to climate finance in agriculture and carbon market; establishing pathways to scale for small businesses through working across P4P partners (through transfers between partners).
See the P4P Theory of Change as Annex 1 to this report

Recommendation. P4P team to set out P4P’s more detailed expected transformational changes, and how these are being achieved across P4P partners, to complement the high-level Theory of Change.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Progress against Impact and outcome level indicators
Outcome/Impact indicator	2025 Planned	2025 Achieved
Impact Indicator 1: Number of new jobs and number of jobs with improved incomes as result of programme's activities (cumulative, unique people).	Total planned New Jobs: 298 (of which 30% are women) / Aceli: 56 (of which 17 are women) / GGF: 0 / MA: 242 (of which 73 are women)	Total Achieved New Jobs: 638 (of which 13% are women) / Aceli: 58 (of which 17 are women) / GGF: 580 (of which 86 are women) / MA: 0
	Total planned Improved Income: 4,084 of which 30% are women / Aceli: 4,084 (of which 1225 are women) / GGF: 0 / MA: 0	Total Achieved Improved Income: 2,652 of which 31% are women / Aceli: 2,646 (of which 820 are women) / GGF: 6 (of which 3 are women) / MA: 0
Impact Indicator 2 [Aceli Only]: ICF KPI 4: Number of people whose climate resilience has been improved as a result of ICF (cumulative, unique people).	Planned: 7,137 of which 30% are women	Achieved: 12,417 of which 27% are women
Impact Indicator 3: Relative growth of manufacturing output in priority sectors of the programme compared to growth in manufacturing output in each MA focus country	Planned: 0	Achieved: 2%
Outcome Indicator 1: Investment mobilised as a result of programme's activities (cumulative, includes: domestic direct investment, foreign direct investment, portfolio investment) [disaggregated by private climate finance]	Total planned: £36m, 29% meeting 2x gender challenge / Aceli: £20.9m, 50% supporting women’s empowerment (meeting 2X challenge), £6.9m climate finance / GGF: £0.8m, 30% 2x challenge, £0.6m climate finance / MA: £15m	Total Achieved: £21.7m, 60% meeting 2x gender challenge / Aceli: £20.8m (61% meeting 2x challenge, £8.7m climate finance) / GGF: £0.8m, 37% meeting 2x challenge, £0.3m climate / MA: 0
Outcome Indicator 2: ICF KPI 12: Volume of private finance mobilised for climate change purpose as a result of ICF (cumulative). [Aceli & GGF]	Total planned: £7.5m (48% meeting 2X gender challenge) / Aceli: £6.9m, 50% supporting women’s empowerment (meeting 2X gender challenge) / GGF: £0.6m, 30% meeting 2x gender challenge	Total Achieved: £9.3m (62% meeting 2X gender challenge) / Aceli: £8.7m, 63% supporting women’s empowerment (meeting 2x gender challenge) / GGF: £0.6m, 49% meeting 2x gender challenge
Outcome Indicator 3: Increase in sales and trade as a direct result of programme's activities (annual sales, as measured by value of new purchase orders).	Planned Total sales: £4.7m, 65% meeting 2x gender challenge / Aceli: £4.7m Increase in sales, 65% meeting 2x gender challenge / GFF: 0	Achieved Total sales: £6.4m, 61% meeting 2x gender challenge / Aceli: £5.9m Increase in sales, 65% meeting 2x gender challenge / GGF: £0.40m Increase in sales
	Total planned International Trade: £3.2m, 65% meeting 2x gender challenge / Aceli: £3.2m increased in international trade, 65% meeting 2x gender challenge / GFF: 0	Total achieved International Trade: £2.5m, 61% meeting 2x gender challenge / Aceli: £2.48m increased in international trade, 61% meeting 2x gender challenge / GFF: £16k increased in international trade
Outcome Indicator 4: Number of effective TA interventions that improve the business environment and/or market system.	Total Planned: 5 / Aceli: Not applicable / GGF: 2 / MA: 3	Total Achieved: 3 / Aceli: Not applicable / GGF: 3 / MA: 0
Outcome Indicator 5: Emissions reduced or avoided that have been supported by ICF TA (ICF TA KPI 5) - GGF Only	Planned Emission reduced or avoided: 0	Achieved Emission reduced or avoided: 219 tonnes Co2 emissions
Outcome Indicator 6: ICF KPI 17: Hectares of land that have received sustainable land management practices as a result of ICF (cumulative) - GGF Only	Planned Hectares of land managed: 0	Achieved Hectares of land managed: 345,163 hectares, avoiding 219 tonnes Co2 emissions
Outcome Indicator 8: Number of supported business environment reforms that receive ‘high level hearing’ within the GoT and number of GGF-supported TA interventions that the GoT deploys and are operational (cumulative) - GGF Only	Planned Business Reforms: / 2 business reforms reaching high level discussion with Government	Achieved Business Reforms: 3 business reforms reaching high level discussion with Government, on sustainable tourism, tax ombudsman and FCC M&A regulations

Context. Overall, growth and macroeconomic stability remain strong in Tanzania, with the economy growing by 5.5% in 2024, mostly driven by gold exports, services and agriculture. IMF assess Tanzania’s economic outlook as favourable, although the upcoming election creates short-term uncertainty. Business environment reforms are continuing, but structural transformation and foreign investment are only increasing slowly, constrained by the relatively weak and complex business environment.

Jobs and incomes (impact indicator). The business case aimed to improve incomes of 125,000 people by 2027, including at least 3,000 new jobs. P4P is on track to in relation to new jobs but not on improving incomes. P4P partners are expecting to increase incomes for only 34,000 Tanzanians by 2027, with the relatively low figure at least partly due to difficulties in collecting this data accurately. Of the 630 jobs created to date, only 13% were women and this may be due to deep occupational norms in Tanzania.

Investment mobilised. The programme is making good progress towards investment targets and on track to mobilise more than £145m of private investment by the end of the programme, significantly higher than the £50m in the Business Case. Aceli and GGF are securing investments roughly in line with expectations. Manufacturing Africa has yet to close a deal but has a strong pipeline of 13 deals being supported (10 of which are highly economically transformative).

Business environment reforms. GGF has overachieved on business reforms. Aceli has started to contribute to this outcome. Manufacturing Africa is yet to use its valuable experience from company level support to identify sectoral barriers in manufacturing and the entry points to address them with Government to support the growth of the manufacturing sector.

Climate finance and resilience: P4P is generally achieving its climate outcomes. Aceli has exceeded expectations on its impact indicator to provide loans which support climate smart practices. GGF has been able to start reporting results related to carbon finance facilitation earlier than expected.

Gender and Inclusion. Delivery partners are reporting on and meeting 2x challenge targets. However, greater emphasis at the design of interventions about whether specific activities can improve gender inclusion and break occupational or discriminatory gender norms could enhance job inclusion results.
Recommendations:
- P4P partners to strengthen analysis of their full impact on incomes and jobs and report to BHC by October 2025.
- All partners to be more targeted and explicit about gender and inclusion interventions and results.
- Building on Manufacturing Africa’s success on the critical minerals work, the programme should consider how it can influence and build political momentum on the growth of manufacturing and industrialisation more broadly in Tanzania and sector specific unlocks. Preparation now ahead of the elections to seize opportunities after would be well timed.
- Now that the P4P programme is established, increase focus and reporting against broader transformational changes across P4P work, beyond individual investments and policy changes.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
P4P has made significant progress, is performing well, and remains central to delivering the BHC’s Country Business Plan and Mutual Prosperity Partnership. P4P is well equipped to deliver on its ambitious targets, including unlocking £100 million in investment and mobilising carbon finance.
Given its strategic relevance, strong alignment with government priorities, and consistent delivery, it is recommended that P4P continue.

## C. DETAILED OUTPUT SCORING
Output Title	Aceli Africa. Mobilising investment for job-creating domestic agri-business (£10.92k-£1.27m ticket size), through (1) financial risk-sharing and (2) technical assistance to businesses and local/regional financial institutions.
Output number:		1	Output Score:	A+: Moderately exceeded expectations
Impact weighting (%):		35%	Weighting revised since last AR.	Yes from 32%

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1.2 Number of businesses receiving technical assistance (cumulative).	51 businesses of which 18 are women-owned business	63 (124% achieved) businesses of which 26 are women-owned business.
Indicator 1.3 Number of financial institutions actively lending in partnership with Aceli (cumulative).	12	11 (92% achieved)
Indicator 1.4 Percentage of SMEs satisfied with TA programme	70%	88% (127% achievement)
Indicator 1.5 Number of financial institutions receiving technical assistance (cumulative).	2	2 (100% achieved)
Indicator 1.6 Number of loans approved as a result of Aceli's financial incentives (cumulative).	240 (120)	264 (110% achieved) loans approved of which 157 were for women-owned businesses.

The overall score for the output is A+, as Aceli’s performance exceeded expectations for the number of businesses and financial institutions receiving incentives and technical assistance, percentage of SMEs satisfied with its TA programme, and the number of loans approved.
This year, Aceli supported 63 SMEs, 51 of which met the 2x gender challenge criteria. Success was driven by enhanced outreach and strategic partnerships with a network of referral organisations. Aceli improved TA by adding a business adviser based in Tanzania to closely support growth stage SMEs and widening the use of Kiswahili-language to increase inclusion of early-stage SMEs. Capacity building was successfully delivered, with Tanzania Commercial Bank (TCB) to establish a dedicated agri-lending unit. Additionally, 9 lenders participated in Gender Lens Investing training. Out of the 264 loans Aceli supported, 74% were new borrowers, highlighting additionality.
[note] 2X Criteria is the global industry standard for assessing and structuring investments that provide women with leadership opportunities, quality employment, finance, enterprise support, and products and services that enhance economic participation and access
[note] Includes Farm to Market Alliance (FtMA), Agricultural Council of Tanzania (ACT), MEDA, SAGCOT, and TAHA.
Feedback from programme beneficiaries was overwhelmingly positive. Businesses were able to expand operations and meet growing demand, made possible by access to longer-term loans and increased loan amounts. One SME noted that they would not have qualified for a larger loan due to insufficient collateral. However, with Aceli’s backing, the bank was able to approve a larger loan, enabling the business to scale its operations. TCB provided evidence that through Aceli’s support, the bank was able to lend to new geographical areas, such as Kigoma, and to attract new customers for the bank’s other products.
[note] including a leather processing company, Animal Feed miller, and an agricultural logistics
Describe any changes to this output during the past year, and any planned changes as a result of this review. The output weightage was revised from 32% to 35% as this review was Aceli’s year 4 in the programme, contributing more broadly to the programme outcome and impact.

Progress on recommendations from the previous AR (if completed). See Annex 2
Lessons learned this year
- Aceli is still using modelled estimates to report results, it has however commissioned field research to monitor results on the ground. This learning should then be reflected in a revised modelling.
- Most of the loans meet the 2X criteria through employees and supplier’s indicator. Based on this, Aceli introduced additional incentives and adjusted qualifying criteria to focus lenders on the need to serve more women owned SMEs and we have seen a significant growth of loans in this segment in Tanzania, from 8% in 2022, 13% in 2023 and 25% in 2024. Comparatively, Women owned businesses continue to struggle to access finance, but lenders are increasingly motivated to serve them.

Recommendations for the Year Ahead
- Aceli to report on progress of financial sector transformation more systematically as an outcome level by September 2025.
- Aceli develop a revised model based on Tanzania survey data to measure jobs (given many of the results are modelled estimates) by September 2025.
- Aceli to enhance documentation of additionality and adherence to P4P criteria. While some supported companies had previously received loans from partner banks, the programme’s contribution often lies in enabling access to larger loan amounts that would not have been approved due to collateral constraints. These nuances, such as increased loan size or improved loan terms, should be systematically captured and reported to better reflect the programme’s value-add. Aceli needs to demonstrate how its banks are not using Aceli as a safety net for existing customers and those not in the target sectors for P4P (ongoing).
- Aceli to review indicator 4 to focus on SMEs reporting implementation of TA recommendations leading to measurable business improvements by September 2025.
- Aceli to establish its offer to the Invest for Impact and ensure regular referrals of companies to GGF and MA (ongoing).

Output Title	Manufacturing Africa. Foreign Direct Investment (FDI) facilitation (£1.46m-£11m ticket size) through FDI transaction facilitation.
Output number:		2	Output Score:	A: met expectations
Impact weighting (%):		30%	Weighting revised since last AR?	Yes, from 32%

Indicator(s)	Milestone(s) for this review	Progress
Indicator 2.2 Number of investment deals provided with high quality substantive support.	13	13 (100% achieved)
Indicator 2.3 Number of deals provided with high quality support which are potentially eligible for the second stage PbR payment if they reach deal close.	6	10 (167% achieved)
Indicator 2.4 Number of substantive technical assistance deliverables supporting government agencies/institutions approved and implemented to a high-quality standard.	1	1 (100% achieved)
Indicator 2.5 Number of support programmes guided by market systems principles, designed and implemented by the contractor in targeted sectors which address key barriers to manufacturing activity, and which are delivered to a high standard.	6	3 (50% achieved)
Indicator 2.6 Number of third parties substantially engaged with, in a way judged to be effective to undertake new activity targeted at addressing key barriers to manufacturing activity.	1	3 (300% achieved)
Indicator 2.7 Number of support packages provided either to foreign investors to encourage them to increase demand from domestic enterprises, or to domestic enterprises themselves to enable them to meet such demand.	2	3 (150% achieved)
[note] Number of substantive technical assistance deliverables (i.e. entailing at least 10 days of support) supporting government agencies / institutions approved and implemented to a high-quality standard (as assessed by the FCDO advisor, drawing on recipient feedback)

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for this output is A. On balance, MA performed well this year despite staffing gaps. MA expanded its pipeline thanks to outreach and referrals from P4P partners, the East Africa Venture Capital Association (EAVCA) and the MoU with the Confederation of Tanzania Industries (CTI). The partnership with CTI enabled MA to source new companies and the partnership provided 20 out of the total of 30 companies MA screened for support in the year MA achieved its annual target with 10 deals approved by the Support Approval Committee to receive high quality support; the highest number recorded in a year 1 across MA focus countries. The approved deals span agri-processing, forestry, medical equipment, and chemicals, and represent a potential investment value of £52.4m.
MA provided Commercial Diligence Support to an Electric Vehicle (EV) company which expressed satisfaction with the Technical Assistance received, noting it helped validate the case for local manufacturing of three-wheelers. MA’s experience from the Kenyan market provided useful insights, which the company is leveraging in discussions with two potential investors.
MA launched its first TA to the Ministry of Minerals, to develop perspectives on mineral value addition, building on the Government’s Critical and Strategic Minerals Strategy which seeks to boost the sector’s contribution to GDP up to 10% by 2025. In the report, 14 value addition opportunities were identified, with potential to generate up to £8bn annually, marking a significant shift from the current gold and raw minerals exports dominated sector. The report has been championed and launched by the Minister of Minerals, as well as by the Chief Secretary and all Permanent Secretaries. It aims to influence and mobilise the Government to attract more investment in the sector, creating tax revenues, growth of industrialisation in Tanzania, and create jobs in a sustainable way.
MA however missed output indicator 2.5 significantly and is not yet contributing to outcome targets (no deal has yet been closed, as it usually takes 18 to 24 months to close deals and see outcomes).

Describe any changes to this output during the past year, and any planned changes as a result of this review. The output weightage was revised from 32% to 30% to accommodate additional weight to Aceli and ODI.

Progress on recommendations from the previous AR (if completed). See Annex 2

Lessons Learned
- Recruitment challenges have affected the pace and quality of implementation, highlighting the importance of proactive recruitment planning and transition resourcing. An interim lead should have been put in place during the recruitment for the Country Director and more resource pulled to plug senior gaps. Exit interviews and lessons should feed into the consortium's recruitment and retention strategies.
- The success of technical assistance and more transformational sector unlocks requires a person on the ground making Government contacts, understanding the political economy, and knowing how to influence change in the sector.
- Feedback from beneficiaries underscore the need for more adaptable financial models. MA could build companies capacity so they can meet the diverse requirements of different investors.

Recommendations for the Year Ahead
- Strengthen recruitment and transition plans with immediate effect.
- Any TA in Tanzania needs to combine on the ground presence. For technical assistance to be successful in country, the consortium needs to collaborate with an effective Country Manager fronting this work in country and managing relationships actively, backed by McKinsey expertise. Any future TA proposals will need to address this.
- More could be done beyond transactions. Tackling sectoral or ecosystem barriers would directly respond to challenges raised by businesses. Using political economy analysis to identify where constraints to investment in manufacturing lie in Tanzania and identifying where MA is most likely to be able to influence change should be integrated into the next years workplan.
- Focus on deal closure. MA in Tanzania is yet to close a deal. More proactive investor engagement and collaboration with GGF on Invest for Impact in next year's workplan should help this.
- Strengthening prioritisation and reporting of gender and climate. Given 70% of MA funding in Tanzania is ICF, it is essential for MA to place stronger emphasis in consistently identifying, prioritising, and reporting on deals and pipelines that targets climate outcomes and gender equality (2x challenge). MA should not only mainstream gender and climate but have more intentional climate and gender prioritisation – including using the forthcoming Green Business Building Accelerator (an initiative which aims to target smaller and green manufacturers), to target and document climate and gender impact better. The team should also strengthen coordination between the technical and MEL teams.

Output Title	Green Growth Facility. Stronger UK-Tanzania economic and climate cooperation through demand-driven technical assistance to Government and Private Sector.
Output number:		3	Output Score:	A: Moderately exceed expectations
Impact weighting (%):		30%	Weighting revised since last AR?	Yes, from 32%

Indicator(s)	Milestone(s) for this review	Progress
Indicator 3.2 Number of Government policy reform, systems building, and capacity building initiatives that GGF undertakes with Government or other influential ecosystem actors, through an approved Statement of Works (SoW).	3	4 (133% achieved)
Indicator 3.3 Number of business innovations to support growth, investment readiness, and/or exports, that GGF supports through private or public actors, through an approved SoW	4	4 (100% achieved)
Indicator 3.4 Number of supporting functions and services that GGF helps to develop to overcome constraints to market development, through an approved SoW	2	3 (150% achieved)
Indicator 3.5 Percentage of completed SoWs approved by FCDO without substantial revision.	80%	100% (125% achieved)
Indicator 3.6 Percentage of SoW agreed and approved in the preceding reporting year, submitted and approved by FCDO by the end of the review year.	75%	70% (93 % achieved)
Indicator 3.7 GGF implements a system to track learning and how it informs programme management decision making.	System has been designed and put into practice in Y2 of the Programme.	MEL system had been designed and put into place in Y2

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall score for this output is A, highlighting GGF’s good performance. GGF exceeded targets on the number of government policy reforms, systems building, and capacity building initiatives delivered. GGF also exceeded the target number of functions and services it helped to develop to overcome constraints to market development, and the percentage of completed SoWs approved by FCDO without substantial revision.
GGF has delivered strong results on business environment reforms. Highlights include the development of the Sustainable Tourism Accreditation Roadmap, endorsed by the Zanzibar Ministry of Tourism, and support to the Zanzibar Ministry of Energy in approving a new net-metering pilot and regulations. GGF also facilitated the Public Private Partnerships (PPPC) Centre’s start-up phase and flexibly supported the continuity until handover to World Bank which was highly valued by the Executive Director of the PPP Centre. The findings from its Tax Ombudsman comparative study were very well received by the President’s Tax Commission, and also shared with Ministry of Finance, TRA, and parliamentary committees therefore well placed to shape the decision on the need for an independent tax ombudsman in line with international best practice. The Fair Competition Commission adopted many of GGF’s recommendations to improve M&A regulations, which should over time reduce time and costs in seeking approvals for both domestic and foreign investors.
In agriculture, in addition to the HEAP initiative mentioned in Section A, GGF has supported Tanzanian exporters in driving value addition and market access. Natural Extracts Industries (NEI) were supported to achieve Rainforest Alliance Certification and secured cocoa nib exports to EU and UK. GGF’s supported a tech-enabled inclusive agri-business, East African Foods to enter the Kenyan market, with sales results looking promising, reaching £16,000 in early sales and projecting £0.9 million by year-end.
On the Investment Climate workstream, GGF is supporting Simbuka, a fintech company providing digital solutions to financial institutions to unlock access to non-collateralised lending for SMEs. While the initiative in Tanzania is still in its pilot phase, close monitoring of deliverables will be essential. Key risks include limited SME adoption due to device access and digital literacy challenges, low trust in fintech solutions, limited bank participation, as some institutions may be too risk-averse or bureaucratic to adopt new technologies, and lack of clear Government buy in leading to potential regulatory hurdles that could affect implementation and scale.
GGF has played a catalytic role in advancing carbon finance. GGF support enabled Dark Earth Carbon to issue the region’s first industrial biochar credits, generating £6,997 in early revenue (attributing £1,960 – 25% – of the sales value to GGF support). GGF’s assessment and initial sales validate biochar’s market potential in Tanzania and advanced DEC’s transition from pilot operations to early-stage commercialisation and laid the foundations for scaling and raising investment.
Describe any changes to this output during the past year, and any planned changes as a result of this review. The output weightage was revised from 32% to 30% to accommodate additional weight to Aceli and ODI.
GGF should revise indicators 3.5 and 3.6 which refer to SOWs approved by FCDO to measure meaningful outputs rather than inputs and approvals. Even if a SoW is approved, it does not guarantee implementation, having them as a standalone output indicators risk overstating progress. It is important that the indicators that refer to ‘number of’ should not incentivise more activities, therefore other means of defining and capturing results needs to be taken into account; following this annual review there should clearly be an increased focus on narrowing down activities; targets will likely be lower and need to consider quality. Proposals for indicator 3.5 around quality of implementation and 3.6 timeliness of implementation: % of SoWs approved in 2023/4, which have been completed by March 2025’.

Progress on recommendations from the previous AR (if completed). See Annex 2

Lessons learned
- Gender has not always been integrated fully at design stage of interventions. The GGF team need to incorporate this during design phase and monitor during implementation.
- Ensuring beneficiary or Government buy in on projects is essential. Frontclear is an example where the evidence on Government buy-in could have been stronger. The projects that have been more successful have been getting behind existing institutions and momentum.

Recommendations for the year ahead
- Consolidate and focus within workstreams. GGF has a lot of small projects (potentially not helped by targets which include ‘number of interventions’) and each workstream should prioritise, focus and propose to BHC the 2-3 main activities where it can have most impact (September 2025). Some agility and flexibility should be built in and remain.
- To influence the adoption of Simbuka by banks, GGF should showcase success stories from Maisha Finance, and other countries to early adopters. This could help build confidence and reduce perceived risk. The team should identify the results and success metrics that should be on track by September, and if these are not reached, the GGF team should consider adaptation or transferring the funds to Invest for Impact.
- GGF’s planned support to FrontClear aimed to strengthen financial institutions’ capacity to implement Bank of Tanzania regulatory reforms and accelerate bank participation in their Tradeclear platform to access its guarantee facility. However, implementation has stalled due to unresolved contractual issues between GGF and FrontClear. It is recommended that GGF discontinue its engagement with Frontclear as soon as possible (July 2025).
- After the selection of a company to work on cold chain that did not lead to the desired results, GGF should give clear upfront evidence before developing SOWs on where they can have most impact and course correct as required. (August 2025).

Output Title	Overseas Development Institute (ODI): Support to the Government of Tanzania on economic planning.
Output number:		4	Output Score:	A: Met Expectations
Impact weighting (%):		5%	Weighting revised since last AR?	Yes, from 4%

Indicator(s)	Milestone(s) for this review	Progress
Indicator 4.1 Technical assistance support provided to the Planning Commission on prioritisation and economic transformation	Prioritisation and economic transformation integrated into national planning through strategic engagement and sectoral analysis.	Met expectations
Indicator 4.2 Technical assistance support to the design of Tanzania Development Vision 2050	Support finalisation of vision 2050 draft and groundwork laid for the long- and short-term planning frameworks	Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score. This component scores an A.
ODI, with support from BHC, played a central role in supporting the National Planning Commission (NPC) and President’s Office Planning and Investment in the development of TDV2050 and its planned operationalisation through the Long-Term Perspective Plan (LTPP). Key activities included:

Facilitation of a strategic dialogue with senior government and Permanent Secretaries (PSs), to embed prioritisation and economic transformation into national planning. A series of coordinated policy discussions brought together PSs from across ministries to reflect on Tanzania’s development trajectory and the institutional reforms required to deliver TDV2050. These sessions examined lessons from past planning cycles, aligned on sectoral priorities, and explored how to leverage private sector investment for inclusive growth. The Chief Secretary’s active involvement and endorsement reinforced the government’s commitment to strengthening delivery and accountability at the highest levels of the civil service.
Provision of technical assistance to the NPC included peer review and advisory support to TDV2050 drafters and reviewers. The project team supported the NPC to organise a TDV2050 workshop which took stock of progress on the drafting of the TDV2050, identified gaps, and planned actions to address these.

ODI delivered two strategic sectoral studies:
  1. Transport, Logistics and Mobility Deep Dive: This provided a comprehensive analysis of infrastructure gaps, investment needs, and policy bottlenecks across ports, rail, roads, aviation, and urban mobility. It demonstrated that a 10% annual increase in transport investment could raise GDP by over £97.6 billion by 2050, while a 50% improvement in efficiency could boost exports by 9%. The report highlighted strong linkages with agriculture, manufacturing, and trade (all P4P priorities), and recommended reforms in intermodal connectivity, digitalisation, ESG-aligned infrastructure, and spatial development initiatives.
  2. Financing Strategy for TDV2050: This outlined a roadmap to mobilise and allocate financial resources across priority sectors. It proposed innovative mechanisms such as blended finance, diaspora bonds, ESG-linked investments, and digital finance platforms.
These studies were directly integrated into the TDV2050 and LTPP drafts, strengthening the use of evidence, technical robustness, policy coherence and enhanced government ownerships. TDV2050 and its respective LTPP have been passed by the Parliament this June and launched in July; thus, strengthening NPC’s mandate to drive it and oversee progress. Government has been very positive about UK’s support and role, given UK were quick to respond and the only donor giving practical support during the important early stages of the Vision 2050 process.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output evolved in 2025. Initially focused on technical inputs to TDV2050, the scope expanded to include:
- Development of a financing strategy for TDV2050, with technical inputs and stakeholder consultations.
- Support to the LTPP and first Five-Year Development Plan (FYDP) under the new vision, including conceptualisation, background papers, and a series of strategic dialogues.
These changes reflect the NPC’s evolving needs and the growing importance of aligning financing with long-term development goals.

Progress on recommendations from the previous AR (if completed). N/A

Lessons learned this year
- Government ownership and trust are critical. ODI’s evidence-based, behind-the-scenes support has been effective in maintaining influence and responsiveness. ODI were also specifically requested by the Government of Tanzania due to this approach.
- BHC’s convening power was essential in enabling high-level engagement, particularly the PSs workshop, which catalysed cross-sectoral dialogue and commitment to prioritisation.
- Flexibility and adaptability are essential in navigating leadership transitions, including the passing of the NPC Executive Secretary and the planned 2025 national elections.
- Continuous engagement with both senior and technical level government officials ensured momentum and alignment with national priorities.

Recommendations for the year ahead:
- Deepen support to the FYDP process, including delivery of quality technical papers and a high-level strategic policy dialogue.
- Continue with coordination with other FCDO funded and non-FCDO partners to avoid duplication and maximise impact.
- The ongoing work under this output is critical to the next round of FCDO programming that will support TDV2050, the FYDPs and unlock additional gains in key transformative sectors.
  [note] Currently being designed and subject to approval

## D: VALUE FOR MONEY
The programme continues to deliver value for money across all five dimensions of FCDO’s Value for Money framework: Economy, Efficiency, Effectiveness, Cost-Effectiveness, and Equity. Across the components, results indicate that the programme is contributing towards transformative outcomes, inclusive growth, and sustainable economic impact.
Economy
Partners are leveraging cost-saving strategies, including use of shared platforms, local expertise, and lean delivery structures. For instance, MA has used consortium local resources and infrastructure such as shared office spaces, utilising expertise from MA programme team in other countries, and standardised templates and documents for delivery of TF support. These have contributed to reduced set-up and onboarding costs. Their average day rate remains within acceptable threshold, with administrative costs accounting for just 3.1% against the total Tanzania programme cost. GGF has reported a healthy 61% spend on direct programme costs in this review period, a significant improvement from 42% in previous review, with direct core spend (Core Inputs) expenditure down from 58% in Year 1 to 39% in this review period. This reflects GGF’s successful transition from inception to active delivery and a deliberate strategic focus on enhancing direct delivery. Aceli maintained administrative costs proportional and reasonable to scale and geographic scope of operations (admin vs programme ratio of 1:3) while enabling outreach to 105,000+ individuals.

Efficiency
The programme has converted inputs into outputs efficiently. MA completed all TF support within SAC-approved days and kept costs low through integration with consortium knowledge systems. Their use of standardised tools (reports, datasets, tools, benchmarking, etc), and experienced regional advisors allowed for efficient programme scale-up in Tanzania. GGF demonstrated strong output conversion from spend, with business partnerships and workstream investments already generating early returns. They have generated 130 new jobs while retaining 450 jobs, against a target of zero this review period, through bridge financing for the Village Forest REDD+ project which faced a funding shortfall. GGF has also supported the East African Food (EAF) to mobilise around £364,000 in private investment following the Go-to-Market strategy. Aceli have managed to deliver 264 loans through 11 lenders (financial institutions), with these loans mobilising £20.38 million in private capital, representing a 14x return on FCDO investment —evidence of scalable systems driving efficient service delivery.

Effectiveness
Programme investments are translating into tangible results, underscoring improved business practices and mobilisation of private capital in climate-smart, gender-inclusive enterprises. Aceli reached over 105,000 smallholder farmers through SME support creating 58 new jobs and facilitating loans to 74% first-time borrowers —highlighting strong reach and additionality, with repeat borrowers reporting a 26% revenue growth. GGF have exceeded year 2 projections for job creation (580 new jobs vs. target of 0) and new created market opportunities for high value crops following its support to EAF. MA have supported multiple TF deals complied with GESI minimum standards, creating nearly 2,000 job commitments across their portfolio.

Cost-Effectiveness
Across the programme, evidence of cost-effective delivery is strong. Aceli’s cost per loan facilitated compares favourably with market benchmarks when adjusted for programme reach and additionality. Leveraging high impact through modest financial input is evidenced by their 14x return on capital. GGF similarly demonstrated early results with minimal resources—achieving business growth through well-targeted TA and financial support mechanisms – pro-actively encouraging stakeholders to commit their own resources into programmes activities – GGF estimates a contribution of over £32,000 from stakeholders in form of consultancy services offered, honorarium, and meeting venues. GGF has played a key role in efforts to improving Tanzania's business environment through policy advocacy. For example, in collaboration with the FCC, through a small technical assistance report, GGF provided the FCC with the evidence to make the case on reforms to be in line with international best practice and over time this should reduce the cost and time related to approvals at the FCC for investors, a barrier to investment as cited by investors. In Zanzibar, GGF has supported the development of net metering regulations, and a pilot that several businesses are implementing which could support renewable energy adoption, provide reliable supply of electricity and lower the cost of electricity bills. Additionally, its partnership with TAHA through the HEAP project has strengthened a major market barrier: information and connectivity, by providing linkages between Tanzanian exporters and UK companies, supporting exports and broader targets under the UK-Tanzania Mutual Prosperity Partnership. Overall, the relative cost of these technical assistance pieces, usually under £150,000 per year, have potentially large potential pay offs to the value of millions of pounds in investments and exports. On MA, the largest potential cost effectiveness indicator would be the investment leveraged. The MA team will need to focus on deal closure this financial year to demonstrate this and BHC will ensure there will be an outcome target for MA to measure and report against.

Equity
Equity considerations remain central to programme delivery, with gender and social inclusion targets not only being met but exceeded in some indicators. All partners have embedded gender equity into programme design and delivery. GESI compliance screening is routine across all partners. Aceli’s loan portfolio includes 59% of loans to gender-inclusive SMEs and 45% to youth-inclusive SMEs. Disaggregated job creation data from GGF indicates 11.4% of created jobs were for women (66 out of 580) with efforts to realise more jobs for women in the coming review period, maintaining a gender-balanced team and delivery structure, with over 40% of project staff inputs delivered by women. MA has been providing deeper support on gender and inclusion, where appropriate, to companies – for example MA targeted GESI support to Project Asili.
Aceli have offered Gender Lens Investing (GLI) as a thematic capacity building to help lenders internalize and operationalize gender lens strategies in their institutions. Nine lenders participated the training, virtual and in person, on foundational concepts of GLI both. Four lenders were selected to receive further support to develop GLI strategy, goals and work plans.
While partners are meeting equity targets, this review recommends partners to quantify, and report, the additional cost of achieving equity outcomes for comprehensive VfM assessments under P4P programme.

Assessment of whether the programme continues to represent value for money
Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, P4P programme continues to deliver value for money with the programme showing to be relevant in the changing ODA context.

E: RISK
Overview of risk management
The P4P programme continues to operate within its overall risk appetite. Risk management is embedded across programme implementation. In addition to partners’ internal quarterly risk discussions and updating their risk matrices and delivery chain risk mapping, the programme holds quarterly risks discussions with its implementing partners. The structured systems allow the programme to identify, monitor, and mitigate risks.
While no risks were closed this review period, all existing risks continue to be monitored, and mitigation strategies are in place. Also, no risk that has materialised this period requiring escalation. However, the programme has identified and added two new risks on Policy and Programme Delivery following ODA budget reduction and programme partner’s staff turnover.
Below are the key risks that the programme is managing:
Major Residual Risks: Two major residual risks are managed which are
1. Changes in the political context with the general election (2025), and
2. Failure to influence policy or facilitate transactions due to an inability to access information to influence political settlement and vested interests.
Both risks are managed through political economy analysis (PEA), adaptive work planning, and high-level government engagement around the 2025 elections and re-building key relations.
Moderate & minor residual Risks. Under these two categories, the programme closely manages the risks below:
- Delivery risks because of ODA reduction. To manage this risk, the programme team is maintaining transparent and timely communication with suppliers. Going forward, when further clarity is available on ODA cuts, the programme will establish clear communication with partners outlining funding realities, and early discussions on possible changes to delivery arrangements and agreements such as reviewing contracts and service level agreements to align expectations and introduce exit or transitional clauses where necessary.
- Staff turnover in programme delivery partner teams. A more proactive approach will be employed to ensure partners maintain internal talent pipelines, conduct early handovers, have transition plans, maintain leadership oversight, ensure key contacts and documentation are stored and available for business continuity and, whenever possible, maintain their core programme teams.
- Fraud or misappropriation and diversion of funds by suppliers or their downstream partners or grant beneficiaries. Fiduciary risks are addressed through regular financial system reviews, and updated delivery chain maps.
- Safeguarding risk. BHC continues to engage with partners to ensure they are meeting FCDO safeguarding standards. Partners continues to report on safeguarding measures including staff training on safeguarding.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The programme continues to demonstrate strong and adaptive programme management across delivery, commercial, and financial performance, underpinned by structured coordination and proactive engagement with P4P partners.

Delivery and Commercial Performance
Regular programme governance mechanisms—including quarterly P4P coordination meetings, fortnightly technical catchups, financial review drop-ins, and quarterly M&E leads’ engagements—have significantly strengthened alignment and consistency in delivery, providing space for technical and regular feedback loop between BHC and implementing partners.
Notably, Palladium (GGF Component) Strategic Supplier Relationship Management (SSRM) has been progressively increased, reflecting improvements in delivery, quality of work, capability and capacity to deliver risk management, and supplier’s commitment to drive value and innovation across all workstreams. Similarly, McKinsey (Manufacturing Africa component) maintained momentum in programme delivery, achieving 100% Support Approval Committee (SAC) approvals and adhering to compliance requirements.
Aceli Africa have met key targets, including strong performance on job creation, investment mobilisation, and inclusion metrics. ODI have managed to meet planned targets for this review period, although their responsiveness to feedback and other requests from BHC could be improved. This has been reflected in ODI’s recent due diligence assessment. The MA CMP has achieved 11 of its 12 service KPIs during this review period and scored an A++, as they did in the previous review period, while GGF has achieved 7 of its 7 KPIs during this review period.
Staff transitions occurred within GGF and Manufacturing Africa, with key personnel exiting in late 2024 and early 2025. These changes highlight the need for robust transition and contingency planning. Programme partners are encouraged to maintain internal talent pipelines, conduct early handovers, maintain leadership oversight, and maintain core institutional knowledge to mitigate risks from turnover in critical roles.

Financial Performance
Overall, programme partners have demonstrated strong financial management practices. Forecasting and financial controls were generally prudent. Spending across all partners was within the 5% variance threshold and within the agreed Non-project Attributable Costs (NPAC) parameters. Budget flexibility was effectively employed by programme team without undermining programme outputs. On the profit margin, both GGF and Manufacturing Africa have operated within their agreed profit margin thresholds, demonstrating sound budget management, adhering to the contractual requirements.
[note] This measure doesn’t apply to Aceli and ODI as they are accountable grant (not for profit).

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
P4P’s M&E activities consist of:
- Aceli: Intensive external and internal monitoring of loans, lender behaviour, SME and farmer surveys, technical assistance impacts, third party verification of climate bonuses.
- Internal monitoring by Manufacturing Africa, including beneficiary surveys after each output, supplemented by BHC Tanzania and HQ assessments of progress.
- Green Growth Facility monitoring and evaluation conducted by a dedicated M&E consortium partner DevLearn. This year the monitoring and indicators system was further developed, including M&E plans for each intervention, final close out notes for four interventions (and planned for all closed interventions), a more flexible attribution model, a policy tracker to track progress with Government reforms, a SoW tracker and a learning and adaptation tracker.
- BHC-led quarterly coordination meetings with all partners, at least quarterly progress reports and meetings and field visits. MEL coordination meetings were also introduced this year.
This Annual Review was conducted by the P4P programme team and a Private Sector Development Adviser from BHC Sierra Leone as an independent reviewer, with inputs from cross cutting Advisers and quality assurance by the BHC Team Leader. The review was informed by a combination of desk review of programme partners’ annual implementation reports followed by meetings with a wide range of stakeholders. The stakeholder’s consultation and field visit confirmed the effectiveness of P4P in supporting SME in Tanzania, and it set an expectation that P4P could achieve even higher results if they support businesses in accessing finance alongside addressing the business environment necessary to attract more DFI and Investor to Tanzanian market (including for larger sized investments).

New Evidence and Learning
Aceli has a strong focus on learning and evidence and produces a learning report each year. Evidence over this year confirmed the positive impact Aceli is having on individual businesses and farmers, and the financial sector more generally. This year Aceli finalised an experimental study in Uganda to assess how incentives influence lender decision-making through randomization of potential loans. Preliminary findings suggest that the incentives contributed to a modest increase in the lender's agricultural portfolio but no significant difference in loan terms. A similar study is now being run in Zambia at the market level. Since the experiment in Zambia is conducted at the market level, its results will contribute to the broader evidence base on how Aceli incentives influence lender behaviour across the overall Aceli program, including in Tanzania. Therefore, Aceli will analyse and deploy learnings from the study in the Tanzanian context. Furthermore, in Tanzania, Aceli conducted an annual portfolio analysis across all partner lenders which showed around 30% growth in the number of small loans (£7.3k-£36.4k). In 2024, a survey of 30 SMEs who received bank financed loans in Tanzania showed that, following the loan, 83% improved their business operations, 64% increased revenues, and 40% increased the number of employees. Aceli is planning a larger survey of beneficiaries next year to collect stronger evidence on outcomes and the extent of increases to jobs, sales and trade. In 2024, Aceli also undertook an evaluation of the impact of TA in 4 countries (including Tanzania) which showed an increased interest in working capital loans, but not an increase in the number of loans applied for or approved. Participants confirmed that the TA improved financial stability, risk management and resilience to business shocks. A more intensive type of TA helped 2 women-led businesses (out of 6 supported) secure £51k worth of loans.
The GGF strengthened its quarterly strategic review process, including through the learning and adaptation tracker to more systematically identify, and act on successes and challenges. Actions included prioritising workstreams where the recipients were most responsive and improving consultant oversight.
Manufacturing Africa carries out a learning series across different geographies on a range of themes such as financial close, working in Special Economic Zones, working in smaller markets, and sectoral learning such as pharmaceuticals and agriculture. It has also now introduced more direct investor engagement for supported companies given this was initially an area that was identified as a gap.
Quarterly P4P MEL meetings were started this year to help coordinate and learn lessons. This includes sharing approaches to quantifying attribution, and MA’s model to estimate indirect jobs.
Date of last narrative financial report		Date of last audited annual statement

ANNEX 1: P4P Theory of Change

ANNEX 2: Follow up on recommendations from last year
ACELI
- Wider and deeper impact: Aceli has introduced additional incentive for institutions extending to underserved geographies, specifically Zanzibar and Mafia islands. On business environment, Aceli collaborated with the Tanzania Bankers’ Association (TBA) to host a workshop focused on achieving a deeper understanding and alignment across: loan classification and provisioning specific for agricultural lending, alternative collateral, movable collateral registry, and harmonisation of the leasing law with other laws. The insights gained from this workshop will contribute towards development of policy and advocacy briefs.
- Explore adding more direct measures of P4P impacts on jobs, incomes, resilience, sales, and trade: FCDO and Aceli held consultative sessions to examine the assumptions, methodology, and analysis of results measurement. Following that, Aceli added an additional output to measure the performance of the Technical Assistance to SMEs. Aceli is also tracking the percentage growth in SME sales from the overall Aceli intervention and in future SME surveys will include questions related to SME’s jobs created and /or sustained to complement modelled data on impact indicator. This recommendation will remain valid for the next reporting year.

Manufacturing Africa
Future transaction facilitation: MA has continued to build a pipeline of deals that align with P4P principles. Such deals include Project Asili (cashew), which qualifies for a 2X investment challenge, Project Usafiri (EV), and Project Pamba (cotton), which are potentially highly transformative.
[note] Deals which are at "support completed" stage in Salesforce and which are expected to score 10 or more Pay-by-Results (PbR) points
Consider the bigger picture: Beneficiaries have engaged MA to support policy measures in some sectors to make locally manufactured products competitive. To do that, MA has involved the BHC in supporting the fronting of the beneficiaries' requests to the relevant government authorities. However, the MA team can do more in coordinating such constraints as highlighted in the Outcome section recommendation.
Engagement with GoT: MA started the Mineral Value Addition TA to the Ministry of Minerals. Government engagement has been wide ranging and high level.
Political economy, additionality, and sustainability of the intervention: An external appraisal of PEA processes was conducted by The Policy Practice for the whole MA programme, following which MA heightened its screening of all deals for political exposure and risk, especially from PEP perspectives, and pulled some deals from the pipeline as a result. MA has continued to be diligent in deal sourcing, which has improved reputational risk awareness following feedback on a plastics proposal. MA deals have added argumentation on additionality, especially on expediting going to market, demonstrating the absence of corporate finance skills to produce investor-grade documents.
[note] The Policy Practice is a network of experienced development professionals who all take a political economy perspective to development Home | The Policy Practice
P4P and wider UK coordination: MA has received deals recommended by P4P partners such as Project Maua, a vanilla processing company referred to MA by GGF. MA continues to engage with GGF, including sharing deals that seek carbon credit trading support.
Dissemination of insights: The findings from the TA on Minerals Value Addition have been widely disseminated and strongly received by GoT and private sector. The findings have been presented at numerous forums. The MA website serves as a library for published insights.
Timeline of delivery: A time extension to the MA head contract is under consideration subject to budget by the FCDO Centrally Managed Programme team.

GREEN GROWTH FACILITY
FCDO priorities and balancing short and long term: Implemented in full. While three interventions have been terminated early, based on learning and adaptation, all other interventions have seen support phased over a period of 12 months or longer.
Balancing support to Government and private sector: Implemented in full, with a much greater balance of projects focused on government.
Economic and climate diplomacy: Implemented in full. GGF has been actively coordinating and supporting BHC’s wider economic diplomacy efforts, including the MPP.
Strengthened PEA for the portfolio: Implemented and ongoing. FCDO and GGF are considering a monthly discussion on political economy. GGF leads Political Economy Analysis discussions for the programme partners during the quarterly P4P Partners coordination meetings. GGF assesses political will and blockers prior to interventions.
Proposals to support individual businesses need to continue to have a clear link to the achievement of programme results, additionality, and support to the wider sector - spillover, replication (Implemented). Evidence of systemic and spillover effects has been (or will be) shared through Evaluation Notes on individual interventions with firms.
A transparent business environment and clarity around business risk and integrity is critical to 1) facilitating more trade and investment and 2) managing programme risk. Over the last year, GGF has struggled to find suitable entry points, or sufficient interest from Government agencies for such support to date, but the programme is still scoping through Invest for Impact to support corporate governance.
Carbon markets: The government has maintained its stance of not providing any meaningful guidance since the previous reporting year - engagement on key policy and regulatory issues has stalled. To re-energize activity in the carbon markets space, an effort is under consideration to provide technical assistance support at central government level to coordinate government agencies and catalyse market engagement.
Inclusion: GGF has performed strongly against its 2X logframe targets and will continue to do so based on interventions in value chains with high gender participation. GGF has also invested in considerable scoping to identify and propose strong gender projects and looks forward to getting approval to mobilise an appropriate intervention in Year 3.