## Annual Review Template

Title: Modern Energy Cooking Services (MECS) Programme - DevTracker link
Programme Value £ (full life): Up to £99m		Review date: October 2025
Programme Code: 300123	AMP start date: 7th Oct 2018	AMP end date: 31st Dec 2030

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Rating	A+	A+	A	A	A	A+	A+
Risk	Moderate	Moderate	Major	Major	Moderate	Moderate	Moderate

A. SUMMARY AND OVERVIEW

Programme Description

Modern Energy Cooking Services (MECS) is the flagship FCDO research and innovation programme accelerating the uptake of clean, modern energy cooking in developing countries, with a focus on Sub-Saharan Africa, and South and Southeast Asia — regions where reliance on polluting cooking fuels remains widespread, posing serious health and environmental risks.

MECS develops and disseminates policy-focused research that helps governments and other key stakeholders to integrate modern energy cooking into their strategies and planning (including gender responsive studies); it funds feasibility studies, early-stage pilots and demonstrators of innovative clean cooking technologies and business models; and it supports scaling of appliance manufacturing and distribution through venture-led R&D. It also co-funds global tracking tools and market-shaping initiatives such as the World Bank Clean Cooking Fund which aims to unlock public and private investment in the clean cooking sector.

MECS targets the 2.1 billion people (a quarter of the world’s population) who still rely on polluting fuels like firewood and charcoal for cooking. Women are disproportionately affected, as main cooks and fuel collectors in most developing countries. These practices contribute to 3.2m deaths annually, including 237,000 children under five. In Africa, women and children account for 60% of smoke-related fatalities — nearly 700,000 in 2019 (10% of the continent’s total mortality). Biomass use also drives forest degradation, biodiversity loss and ~2% of global CO₂ emissions.

MECS directly contributes to Sustainable Development Goal (SDG) 7 which calls for “affordable, reliable, sustainable and modern energy for all” by 2030, with a focus on SDG 7.1.2 on “clean cooking fuels and technology”. It also supports progress on nine other SDGs, including SDG 13 on “urgent action to combat climate change and its impacts”, and the Paris Agreement which seeks to limit the global temperature rise to 1.5°C above pre-industrial levels.

MECS is the lead UK programme for the ‘Modern Cooking’ Challenge under the up to £1bn Ayrton Fund, part of the £11.6bn International Climate Finance (ICF3) commitment (2021–2026). MECS features as a case study in the ICF Annual Report 2024 and the UK Net Zero Research and Innovation Delivery Plan 2022–2025. Its research is often cited in key publications; for example, the IPCC Climate Change Report 2022 and the IEA Universal Clean Cooking in Africa Report 2025.

Delivered by three Tier 1 partners — Loughborough University (LU), CLASP, and the World Bank’s ESMAP — MECS has funded a network to date of over 200 innovators, academics, entrepreneurs, and civil society partners delivering research and innovation activities across 37 countries.

In November 2025, the MECS business case was extended to December 2030 and the budget increased from £55m to £99m. CLASP was added as a Tier 1 partner, and a ministerial announcement was made at COP29. However, since the ODA budget reduction announced in February 2025, the FCDO has only been able to commit £64m of the total budget so far, and the MECS delivery plan and several logframe targets have been adjusted accordingly.
Narrative Summary for Annual Review Rating
MECS is rated an ‘A+’ this year, reflecting the programme’s strong performance in meeting and in some cases exceeding milestones during the annual review period (Sep 2024–Aug 2025). So far, MECS-supported innovations have improved clean energy access for 4.5 million people in developing countries (+700k since last year), preventing 2.5 million tonnes of CO₂ emissions (equivalent to removing 1.7 million UK cars from the road for one year). MECS has leveraged £435m in public and private investment (+£34m since last year), delivering £10 for every £1 of UK spend, and created 1,325 new green jobs (+522 jobs since last year). MECS has built a strong evidence base that has contributed to 16 developing countries announcing plans to expand modern energy cooking; 8 of which are now implementing major initiatives with support from the programme (with Sierra Leone added this year). MECS evidence has also directly influenced national policy adoption of electric cooking (eCooking) in Kenya, Uganda, Tanzania, India, Bhutan, and Nepal. Recent notable achievements by MECS partners include ATEC raising $15.5m to roll out 200,000 IoT cookstoves across South Asia; Indian Oil committing £65m to clean cooking scale-up, funding the initial deployment of 100,000 solar cookers in Madhya Pradesh, and securing Gates Foundation support; and Sierra Leone integrating eCooking into its forthcoming National Clean Cooking Strategy.

In 2025, the UK signed MoUs with Saudi Arabia and France which include collaboration on clean energy and specifically clean cooking initiatives. A new $3.5m eCooking pilot in Sierra Leone funded by Saudi Arabia and designed with MECS support is now underway. France recently joined the MECS-managed Global Electric Cooking Coalition (GeCCo), and Saudi Arabia is expected to do the same next year. Ongoing discussions with both countries aim to expand clean cooking efforts and collaboration in the coming years, building on the two MECS demonstrators in Tanzania and Uganda.

Key results and headline narrative on scoring per Output are as follows:

Output 1 - Foundational research and training (£24.7m) (A+):	MECS has developed and published 421 research reports (target 388) advancing clean cooking knowledge, viewed over 215,000 times (target 220,000). A notable publication this year was the Meeting the Clean Cooking Challenge in Africa developed by LU in collaboration with the Africa Energy Commission (AFREC), and the Brazil G20 Clean Cooking Roadmap developed with support from ESMAP. MECS supported 43 learning events (target 30) on topics such as carbon financing and appliance repair & maintenance, and MECS representatives spoke at several high-level events this past year including COP29, the SDG7 Forum, and G20. Furthermore, 6 countries (target 6) have adopted MECS planning tools for eCooking transitions, including Sierra Leone this year.
Output 2 - Technology accelerators and challenge calls / (£12.3m) (A):	All 7 planned innovation calls have been successfully delivered, including the new STARSS call launched in August 2024 to test eCooking feasibility on standalone and off-grid solar systems. Through these calls, MECS has driven R&D of 154 clean cooking innovations (target 135) and supported 88 projects (target 84). In addition, 7 case studies showcasing innovations with potential for market uptake were developed, including two in the past year: one focused on Uganda’s new eCooking tariff tool developed with MECS support (now informing utility-led scale-up) and another exploring bioethanol scalability in East Africa.
Output 3 - Venture building (£1.6m) (A)	This newly launched output, led by CLASP, has made strong early progress. Within three months of the FCDO funding agreement (July 2025), a five-year workplan was developed and early-stage clean cooking companies identified in high-opportunity markets for future MECS R&D support, aimed at improving investability and enabling scale-up. All activities are on track, and CLASP’s role as a Tier 1 partner is expected to strengthen the pathway from R&D to market scale-up for clean cooking innovations.
Output 4 – Market shaping (£13.1m) (A+):	11 World Bank Country Climate and Development Reports (CCDR) that include MECS evidence and analysis were published (target 6), including 6 in the past year – Uganda, Tanzania, Sierra Leone, Senegal, Togo, and Burundi. MECS also supported the design of 14 new clean cooking Results Based Financing (RBF) and Carbon/Climate Finance programmes (target 14), including one large World Bank investment project in Malawi in 2025. To date, MECS partners have provided evidence and expert advice to 33 developing countries in support of their clean cooking transitions. GeCCo held 4 meetings (target 3) and received 8 letters of intent (target 6) from countries welcoming its support – Laos, Somalia, Nigeria, Rwanda, Sierra Leone, Madagascar, Kenya and Burundi.
Output 5 - Leadership and coordination (£5.3m) (A):	To date, 3 MECS Advisory Group meetings and 3 Ayrton Modern Cooking Challenge Steering Group meetings have been convened as planned, to strengthen strategic direction and coordination across the sector. The Ayrton Challenge Plan was updated, and monthly MECS newsletters consistently published. An independent mid-term review, completed in December 2024, rated the MECS programme’s performance and value for money as “Very Good”.
Output 6 – Country Demonstrators (£7.15m) (A):	Demonstrators supported by Posts in Tanzania and Uganda are progressing well with strong support from British High Commissioners. Nationwide campaigns to raise awareness of eCooking reached 30m people across both countries (target 7m), and 721 technicians were trained in appliance repair and maintenance (target 500). In Tanzania, 2,727 households received appliances (target 3,000), though only 1 school (target 6) has been transitioned to eCooking so far (though 32 more are expected by next year). In Uganda, appliance distribution was delayed due to procurement challenges but is now advancing with a supplier identified.

Lessons and Recommendations
Lessons learned during this review period are detailed in the Output sections and will inform MECS’s approach going forward. Building effective partnerships takes time and persistence, illustrated by the African Development Bank’s transformation into a leading eCooking investor after sustained MECS engagement since 2019. The addition of CLASP as a Tier 1 partner seeks to strengthen the pathway from R&D to scale-up. Demand for robust data and modelling tools continues to grow, though measuring co-benefits like health and gender remains challenging. Transitioning schools to eCooking has proven more complex and costly than anticipated due to the need to upgrade electrical infrastructure highlighting the need for early, multi-stakeholder engagement. Diverse financing mechanisms and local capacity-building are essential for sustainable delivery.

Annex 1 confirms that all recommendations from the previous annual review have been progressed; some completed (e.g. updating the Ayrton Modern Cooking Challenge Plan, integrating gender and jobs KPIs), others ongoing (e.g. multi-fuel research, institutional/commercial cooking studies, and tackling appliance cost barriers). Recommendations for the year ahead are detailed in the Output sections and summarised below.
1. LU to develop systematic approach for introducing partners and potential users to R&D modelling tools by March 2026.
2. CLASP and LU to develop joint framework by April 2026 to transition R&D projects from LU’s tech accelerator to CLASP’s Venture Building support.
3. CLASP to establish a clear and transparent process for selecting eCooking ventures to receive MECS R&D support by December 2025, and to seek approval from the FCDO.
4. MECS to continue exploring a diverse range of financing mechanisms beyond carbon finance, such as on-bill financing with utilities and Mission 300 RBF facilities.
5. GeCCo to propose a new logframe KPI by March 2026 focused on measuring the depth and quality of engagement with partner countries (beyond letters of intent).
6. LU to lead stocktake of the Ayrton Modern Cooking Challenge by December 2025.
7. LU to conduct ‘lessons learned’ review of the Tanzania and Uganda demonstrators after the first phase completion in March 2026.
8. LU to work with Post to develop a 1-year extension to the Uganda Demonstrator and ramp up communication of outcomes.
9. FCDO to agree a set of H&S improvements with MECS partners by October 2025.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Following the MECS extension to December 2030, the Theory of Change below and logframe were updated to include a new Output (4) focused on Venture Building R&D, led by new Tier 1 partner, CLASP. A new outcome gender KPI was also agreed (KPI 7). Due to a reduction in the ODA budget, the list of MECS priority countries for 2025–2030 was revised from 18 to 11, with a focus on countries where there is strong potential to scale clean cooking innovations and attract co-funding partnerships. This includes Ghana, Kenya, Malawi, Tanzania, Rwanda, Uganda, Zambia, Bangladesh, India, Nepal, and Indonesia.
Progress against Outcomes

The outcome that MECS seeks to achieve is “A market ready range of technology and business model innovations that lead to improved choice of affordable and reliable modern energy cooking services for consumers”. MECS is making excellent progress towards this outcome, with most milestones exceeded to date. A summary of progress against Outcome KPIs is provided below:

1.1 Countries that actively implement policies, evidence, and programmes to increase access to MECS	Milestone: / 8	Result: / 8	Rating: / Met

Performance is on track with eight MECS-supported countries actively implementing policies and programmes to expand access to modern energy cooking. Since 2022, these countries have demonstrated growing political commitment and increasingly integrated MECS research and evidence into national planning. Annex 2 summarises progress in each country with key development over the past year including:
- Sierra Leone: eCooking is being integrated into the forthcoming National Clean Cooking Strategy being developed with MECS research support. A new $3.5m pilot project funded by Saudi Arabia’s Middle East Green Initiative (MGI) and developed with MECS input was launched, covering eCooking in schools, off-grid solar, and appliance repair and maintenance.
- Uganda: Finalisation of a National eCooking Strategy developed with MECS evidence, expected to be launched at the Renewable Energy Conference in October 2025. The £3.65m MECS Demonstrator is underway (see Output 6.2), alongside a $5.1m eCooking grant from the African Development Bank Group.
- Tanzania: Hosted a high-level delegation in London in July 2025 to explore pathways and financing for its National Clean Cooking Strategy developed with MECS research. The £3.5m MECS Demonstrator continues (see Output 6.1), and a $6m eCooking loan was included in the Submarine Cable to Zanzibar Project funded by the by the African Development Bank Group.
- Kenya: Advanced tariff reform through a joint experiment in 2024 in collaboration with MECS research support. In 2025, the African Development Bank began developing a new $4.4m eCooking Market Development Project, pending Board approval in Q4.
- India: Launched a tender for 100,000 clean cooking appliances with technical advice from MECS, and developed mandatory energy labelling for induction cooktops informed by international testing by the CLASP-led Global LEAP Awards (expected to be announced in early 2026). Several state governments are exploring eCooking to boost electricity demand, including an upcoming project in Kerala with support from the Global Green Growth Institute (GGGI).
- Nepal: Incorporated MECS evidence into its updated Nationally Determined Contribution by recognising black carbon harms, promoting carbon finance for clean cooking, raising its household eCooking target, and adding a new eCooking target for institutions and firms. The Government also endorsed MECS repair & maintenance training for future national programmes.
- Bhutan: Continued planning for a national eCooking rollout with support from UNESCAP and MECS evidence. Also, advanced its Article 6.2 carbon finance programme, securing verbal commitments from Singapore-based industries and banks. The project was added to Bhutan’s ‘positive list’ and announced at COP29.
- Rwanda: Developing a national clean cooking strategy as part of its broader energy and climate commitments using MECS produced evidence. Currently implementing the Energy Access and Quality Improvement Project supported by the World Bank ESMAP, which seeks to expand access to clean cooking to 500,000 households and leverage US$30 million in investment.
1.2 Countries that have announced plans to increase access to MECS (incl. policies, evidence and programmes)	Milestone: / 12	Result: / 16	Rating: / Exceeded

Performance is exceeding expectations, with 16 countries announcing plans to expand access to modern energy cooking services. In addition to the eight countries reported previously as actively implementing significant initiatives with MECS support, this group includes Nigeria, Lao PDR, Bangladesh, Cambodia, Ghana, Zambia, Malawi, and Burundi, which are on a strong trajectory towards implementation and expected to move to active, government-supported delivery soon. A summary of progress in each country is provided in Annex 3. Key developments over the past year include: Nigeria securing $300k from the Climate and Clean Air Coalition (CCAC) for national strategy work and proposing a £5m battery bank-based eCooking project; Lao PDR advancing a National eCooking Strategy and carbon finance readiness; Bangladesh and Cambodia scaling up private sector-led induction stove rollouts; Ghana and Zambia expanding IoT-enabled cookstove; and Malawi and Burundi progressing carbon finance arrangements and national planning.
2. International organisations that adopt MECS principles and indicators (as evidenced by key documents)	Milestone: / 12	Result: / 12	Rating: / Met

Performance is on track, with 12 international organisations now adopting MECS principles and indicators, including major actors such as IEA, IRENA, WFP and SEforALL, among others, who have integrated MECS approaches into their planning, reporting, and advocacy. For further details, see Annex 4. This year, two organisations supported by MECS joined the list: the Clean Cooking Association (CCA), which led the Clean Cooking and Climate Consortium (4C) to develop the CLEAR methodology for crediting emissions reductions from cookstove projects drawing heavily on MECS’s metered methodology and aiming to revive a self-certification route for improved cookstoves; and the G20 Brazil Presidency which developed a roadmap for clean cooking and committed to prioritising this topic through its G20 and COP30 presidencies.
3. People with improved clean energy access in developing countries	Milestone: / 4.5m	Result: / 4.5m	Rating: / Met

Performance is on track, with MECS-stimulated innovations reaching 4.5m people so far (including nearly 700k people in the past year) across Sub-Saharan Africa, South Asia, and Southeast Asia. Of these, 3.1m people benefitted from clean cooking technologies (mainly electric cookstoves) and 1.4m from access to clean electricity (mainly due to earlier MECS contributions to ESMAP, which were unpreferenced). Attribution is based on MECS funding share and estimated contribution to outcomes, supported by evidence from activities and partner reporting. A notable example this year is Nepal, where 600k people are now using induction cookstoves, with 20% (120k people) estimated as attributable to MECS. Since 2019, MECS has worked with local partners in Nepal to pilot initiatives and engage government and development stakeholders, contributing to the country’s national goal of 25% of households adopting eCooking by 2030. In Kenya, 4m people transitioned to eCooking due to effective MECS’s evidence, research, and policy engagement (with 30%, 1.2m estimated as attributable to MECS), which played a key role in supporting the Government to develop and implement a national eCooking strategy and raising overall uptake from 1% in 2019 to 6.4% in 2024.
4. Public and private sector funding mobilised into clean cooking and clean energy RD&D	Milestone: / £500m	Result: / £435m	Rating: / Not met

Performance appears to be behind due to a lag in ESMAP reporting and the absence of FCDO funding for the Clean Cooking Fund in 2023/24. As a result, ESMAP results (typically substantial but reported with a lag) are not included in this year’s annual review. These are expected to be included in the next annual review following a £2.65m FCDO contribution to the Clean Cooking Fund in 2024/25. Despite this, MECS-supported projects mobilised £435m in additional funding to date (£35m more than last year) achieving a leverage ratio of £10 for every £1 of UK investment. Public funding (£222m) came from agencies such as SIDA, the EU, USAID, and national governments (e.g. Kenya, Nepal), while private funding (£213m) included contributions from the Rockefeller Foundation, ATEC, and BURN. Of the total funding leveraged to date, 65% comes from ESMAP and 35% from Loughborough University projects. A key achievement this year is the £65m investment from Indian Oil (of which 50% is estimated as attributable to MECS’s support) to deploy the Surya Nutan solar cooker, beginning with an initial rollout to 100,000 off-grid homes in Madhya Pradesh. MECS and its local partner Finovista, played a pivotal role by shaping the project design, facilitating strategic corporate partnerships, and enabling access to carbon finance. This directly contributed to Indian Oil’s investment decision and was instrumental in securing a follow-on grant from the Bill & Melinda Gates Foundation for a pilot.
5. CO2 emissions reduced as a result of MECS stimulated innovations and research (t/CO2)	Milestone: / 650,000	Result: / 2.5m	Rating: / Exceeded

MECS estimates that its support for modern energy cooking innovations has led to the avoidance of 2.5m tonnes of CO₂ emissions to date, exceeding expectations. This is based on a new ICF-compatible methodology that uses a counterfactual of low electric cooking uptake without MECS support, and applies a conservative attribution by country, national emissions factors, and third-party verification through Gold Standard audits. This result highlights MECS’s significant contribution to climate mitigation through clean cooking transitions. To put it into perspective, reducing 2.5m tonnes of CO₂ is equivalent to removing 1.7m UK cars[1] from the road for one year, or the annual emissions of more than 460,000 people[2] in the UK. Given that the final logframe target of 1m tonnes of CO₂ emissions reduced by 2030 has already been surpassed, FCDO will increase it to a more realistic level of 6m tonnes.
[1] Average annual UK car emissions in 2024: 1,470,120 grams of CO2
[2] 2024 UK carbon dioxide net emissions were estimated at 371m tonnes (Mt) / or an estimated 5.4 per capita
6. Green jobs created in the clean cooking sector	Milestone: / 855	Result: / 1,325	Rating: / Exceeded

Performance exceeded expectations with MECS funding creating 1,325 new jobs across a diverse range of clean cooking organisations. These roles span multiple countries in Sub-Saharan Africa, South Asia, and Southeast Asia, and cover key functions such as management, production, distribution, monitoring, and evaluation. Examples include BURN in Uganda, TaTEDO in Tanzania, Geres in Myanmar, and Finovista in India. Of these, 619 jobs (47%) have been held by women. MECS-supported innovator Kachione in Malawi is a good example of how women can be empowered to work in the clean cooking sector. Since 2019, MECS has supported Kachione through a technology accelerator (TRIID) which led to the company securing domestic banking finance to expand its operations and currently providing 45 sustainable jobs for women through its local network of solar shops. Given that the final target of 1,300 jobs has already been surpassed, FCDO will increase it to 1,900 jobs.
7. Proportion of women in senior and middle management positions in the clean cooking sector	Milestone: / N/A	Result: 39.5%	Rating: N/A

This KPI was added to the MECS logframe in July 2025, so no milestone was set for this year. MECS has been developing a methodology to track gender representation in management roles across delivery partners. Data from 36 partners shows a combined workforce of 7,533, including 362 staff in middle and senior management; 143 of whom (39.5%) are women. This figure will serve as the baseline for future progress, with milestones introduced from 2026. It compares favourably to global benchmarks: UN Women (2023) reported 24% of managerial roles held by women, and IRENA (2019) found women made up 32% of the renewable energy workforce. As MECS partner composition may vary annually, figures could fluctuate. Future results may also align with broader sector efforts led by UN Women and IRENA.
Progress against Impact

The impact that MECS seeks to achieve is “Clean cooking and clean energy transition accelerated in developing countries in Sub-Saharan Africa, South and Southeast Asia and the Indo-Pacific” measured by progress against SDG7.1.2 as summarised below.

1. People without clean cooking access (SDG7.1.2)	Milestone: 1.8bn	Result: 2.1bn

According to the 2025 SDG7 Tracking Report, 2.1 billion people still relied on polluting fuels for cooking in 2023, primarily in Sub-Saharan Africa and South Asia. This figure remains unchanged from the previous year but marks a decline from 2.3 billion in 2021 and 2.7 billion in 2015. While global clean cooking access is improving, progress remains too slow to keep up with population growth, especially in Sub-Saharan Africa. Over the past five years, approximately 13 million people in the region have gained access to clean cooking each year. This is 20% more than the previous decade, driven largely by the uptake of LPG, with electric cooking accounting for around 1 million new users annually. However, due to widespread fuel and stove stacking (a practice where households continue using polluting fuels alongside cleaner alternatives), MECS estimates that up to 4 billion people may still be exposed to polluting fuels. If current trends persist, nearly 1.8 billion people will remain without clean cooking access by 2030, with 60% of them in Sub-Saharan Africa. Encouragingly, 70% of Africans without access now live in countries that have strengthened their clean cooking policy frameworks, with 40 new policies adopted since 2024. Yet clean cooking remains one of the most underfunded SDG targets, with an estimated $4 billion needed annually in Africa alone to achieve universal clean cooking access. Political momentum is building: $2.2 billion was pledged at the 2024 IEA Clean Cooking Summit in Paris, clean cooking featured prominently at COP29 in Azerbaijan, and 28 African Heads of State committed to advancing clean cooking at the Mission 300 Summit in 2025. While achieving SDG7.1.2 (universal clean cooking access) by 2030 is increasingly unlikely given the scale of need and investment shortfall, significant progress is still within reach. MECS continues to play a pivotal role in tackling the global clean cooking challenge and is well-positioned to help drive progress through innovation, evidence, and partnerships.

Justification of Programme Continuation (based on merit and wider portfolio context)

MECS is a flagship programme within the UK’s ICF portfolio, consistently delivering strong results on clean energy access, climate mitigation, and gender equity. MECS delivers 9–25 times its share of ICF results relative to its funding, highlighting its exceptional impact (see table below). It has met or exceeded milestones, shaped national policies, and driven market transformation in priority countries. Its innovations and partnerships are recognised as international best practice, and independent review rates its value for money as “Very Good” with cost per outcome outperforming global benchmarks. MECS fills a critical gap in the ICF portfolio by tackling the persistent and underfunded challenge of universal clean cooking access. Its unique blend of research, innovation, venture building R&D and market shaping complements other UK investments and positions the UK as a global leader in this space. With political momentum at an all-time high, and MECS embedded in major country partnerships and strategies, continued support will ensure the UK remains at the forefront of delivering scalable clean cooking solutions for millions still reliant on polluting fuels.

ICF results attributable to MECS:	ICF / portfolio / results / (Apr’11 to Mar’25)[3]	MECS results included in ICF portfolio results / (Aug’18 to Mar’25)	MECS share / of ICF results
People with improved clean energy access	89.2 million	4.5 million	5%
CO2 emissions reduced	145.8 million	2.5 million	1.7%
Public finance mobilised	£10.6 billion	£222 million	2%
Private finance mobilised	£10.5 billion	£213 million	2%
ICF/MECS spend linked to results reported	£18.4 billion	£40.3 million	0.2%
[3] UK International Climate Finance Results 2025

## C. DETAILED OUTPUT SCORING

Output 1 - Foundational research and training to develop data and capabilities on modern energy cooking services
Impact weighting (%):	40%	Rating:	A+ - Output moderately exceeded expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
MECS research published / (incl. number peer reviewed)	388	421	Exceeded
1.2 Online views of MECS publications	220,000	215,205	Met
1.3 MECS learning events and training	30	43	Exceeded
1.4 Countries using clean cooking planning tools and load modelling to support eCooking transition	6	6 / (Sierra Leone, Malawi, Rwanda, Kenya, Namibia, Tanzania)	Met

Performance Summary
This output is progressing strongly, with two milestones exceeded and the remainder on track, justifying the ‘A+’ rating. MECS surpassed its research publication and events targets, while targets for online views and countries using MECS clean cooking tools are on track. These achievements reflect MECS’ growing role in shaping national strategies and global dialogues on clean cooking.
1.1. MECS research: To date, MECS has developed and published 421 clean cooking reports (target 388), including 398 commissioned by Loughborough University and 23 by ESMAP, all peer-reviewed (i.e. independent review process by subject matter experts prior to publication, ensuring technical accuracy and quality). The reports span topics such as off-grid technologies, alternative fuels, financing, and business models across diverse regions. At least 20 reports focus primarily on gender, while all incorporate gender and social inclusion considerations and address the needs of women. Over the past year, 67 new reports were published (66 by LU, 1 by ESMAP). Highlights include:
- Brazil G20 Clean Cooking Roadmap: Commissioned by the Brazil G20 Presidency and developed by ESMAP in collaboration with IEA, SEforAll, and Loughborough University, the roadmap outlines strategic actions for accelerating global clean cooking access, offering a framework for G20 coordination, finance mobilisation, and integration of clean cooking into energy and climate agendas.
- Meeting the Clean Cooking Challenge in Africa: Jointly produced by the African Energy Commission (AFREC) and MECS, this report offers insights into regional initiatives and collaboration. It analyses barriers and opportunities for scaling clean cooking, and presents policy recommendations, financing models, and case studies to guide national strategies and global partnerships.
- Opportunities for Digital Monitoring of SDG Impacts Beyond Carbon Emission Reductions in Modern Cooking: This report explores how digital technologies can enable simple, cost-effective monitoring of a wide range of SDG impacts. It highlights the potential of digital tools to improve data accuracy and support decision-making in the clean cooking sector.
- MEPS and Safety Standards for eCooking Appliances in Tanzania: This report outlines the development of Minimum Energy Performance Standards (MEPS) and safety protocols for eCooking appliances, supporting safer and more efficient adoption of clean cooking technologies in Tanzania.
Two emerging areas for future MECS publications are schools and commercial settings. In schools, MECS demonstrators in Uganda and Tanzania, alongside interest from the Rockefeller Foundation, CIFF, Verst Carbon, WFP, and SEforAll, have built a strong portfolio. MECS has supported over 20 schools (Kenya, Guinea, Lesotho, Tanzania) in adopting cleaner fuels and technologies, and researched baseline needs, emissions, and costs. A library of baseline data is planned to support a regional Carbon Finance Programme, with IEA collaboration to assess wider market potential. In commercial settings, MECS is distinguishing domestic from business eCooking use. Building on the Shell Foundation and Odyssey’s RBF gender pilot (supported by the FCDO TEA platform), MECS has studied 2,000 women-led businesses using induction stoves in Kenya and Tanzania, with further research underway in Nepal to deepen understanding of commercial eCooking adoption.
Publications	Views
MECS publications page	18,036
Newsletters	841
Energies open access journal	112,057
ESMAP clean cooking reports	84,271
Total	215,205

1.2 Online views of MECS publications: MECS publications are estimated to have been viewed 215,205 times to date (target 220,000). This is a conservative estimate based on views of the MECS publications page, newsletters, special issues published on the 'Energies' open access journal, and downloads of ESMAP clean cooking reports. This year, downloads of the Brazil G20 Roadmap were not included, as the website is not managed by ESMAP. This level of interest underscores the growing recognition of clean cooking as a critical component of global energy access and development efforts, and MECS’ role as a leading source of knowledge and guidance in the sector, informing policymakers, practitioners, and stakeholders worldwide. As more countries and organisations seek to address the pressing challenge of providing clean and sustainable cooking options, the demand for MECS’ expertise and resources is expected to grow.
1.3 MECS learning events and training: Since tracking began in 2023, MECS has supported 43 events (target: 30), listed in Annex 5. These include technical trainings, research dissemination, and conference panels. Highlights from the past year include business modelling training for eCooking companies in Tanzania, school energy audits in Uganda, and a Climate Parliament gathering 35 MPs from Africa and Southeast Asia to discuss carbon finance, institutional cooking, and eCooking tariffs. Topics covered range from schools and PUE to data, user insights, and policy change.
1.4. Countries using clean cooking planning tools and load modelling: 6 countries (target 6) have used MECS tools to support eCooking transitions, including the ESMAP Clean Cooking Planning Tool (CCPT) designed to help energy planners, decision makers, program developers, and researchers visualise potential transition pathways to universal clean cooking access by 2030. Sierra Leone joined this group this year, using CCPT with the Presidential Initiative on Climate Change, Renewable Energy, and Food Security (PI-CREF) and the World Bank to identify a $4.7bn eCooking opportunity (key to its forthcoming National Strategy, also informed by MECS research). In 2025, MECS also developed two new modelling tools: the Virtual Knowledge Data Dashboard (VKDD) and the Transition Impact Modelling for eCooking (TIMeC). These user-friendly tools help validate modelling assumptions and uniquely account for stacking behaviour, which other models overlook.
Output Changes
Since next year’s milestones for KPI 1.1 and 1.3 are already met or nearly met, FCDO will work with partners to revise them to a more realistic level.

Lessons and Recommendations
The MECS programme continues to demonstrate the value of evidence-based approaches in advancing modern energy cooking services. The strong uptake of peer-reviewed research and modelling tools has enabled countries to quantify the benefits of eCooking and integrate it into national strategies, as seen in Sierra Leone. However, many international clean cooking dialogues still rely on anecdotal data and inconsistent cost comparisons, often overlooking long-term climate and health impacts. MECS’ contributions are helping to shift this narrative, but more work is needed to embed robust data into global investment and policy decisions.

Recommendation 1: LU to develop a systematic approach for introducing partners and potential users to modelling tools such as the new Virtual Knowledge Data Dashboard (VKDD) and the Transition Impact Modelling for eCooking (TIMeC) tool, by March 2026. Providing support during the initial learning phase will help build local capacity, improve data-driven decision-making, and ensure partners can effectively model and understand clean cooking data as the sector evolves.
Output 2 - Technology accelerators and challenge calls tackle key off-track technologies for clean cooking access
Impact weighting (%):	15%	Rating:	A - Output met expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
2.1 Innovation challenge calls	7	7	Met
2.2 Projects supported via challenge calls	84	88	Met
2.3 Innovations researched, developed and/or piloted (technologies and business models)	135	154	Exceeded
2.4 Case studies developed on technology and business innovations previously funded by MECS that show maturing and market uptake potential	7	7	Met

Performance Summary
This output is progressing strongly, with two of the four milestones exceeded and the remainder on track, justifying the ‘A’ rating. MECS has successfully delivered all planned challenge calls, surpassed targets for supported projects and innovations, and completed all scheduled case studies, demonstrating strong programme momentum and contributing to growing market engagement with clean cooking solutions.
2.1–2.3 Innovations: To date, MECS has launched seven innovation challenge calls as planned, awarding over £6.5m million to 88 projects (target 84) and supporting R&D of 154 clean cooking innovations (target 135) - slightly ahead of expectations. These include a range of technologies and business models such as DC electric pressure cookers, Pay-As-You-Go systems, biogas bottling, LPG traceability, ethanol stoves, and phase change materials (see Annex 6 for a summary of MECS calls). The latest call — Standalone or Rooftop Solar Systems Inclusion of eCooking (STARSS) — was launched in August 2024 to test the feasibility of eCooking on standalone and off-grid systems. It awarded £0.69m to 11 projects, including the deployment of solar-based eCooking systems in schools and churches across three countries ( Mozambique, Kenya, Uganda), installation of solar-powered e-cookstoves in Nigeria, Kenya, India and Uganda, mesh-grid powered solutions in rural Madagascar, and a results-based financing model trialled in Malawi that credits users for appliance use and related economic and environmental benefits. Findings from these projects will be published and inform future programme design, investments, and policy recommendations.
User of ATEC smart induction hob in Rwanda, scaled up with MECS support.
2.4 Case Studies: Seven case studies have been completed as planned, showcasing innovations with potential for market uptake. Five were developed in previous years (ATEC, Kachione, Bio LPG, Tefal EPC, and BURN), with two new additions this year. One case study due to be published soon highlights Umeme Ltd’s eCooking tariff pilot in Uganda, where smart meter data from 500 households showed that Electric Pressure Cookers were used an average of 27.2 times per month. Households aware of the tariff were more likely to view electric cooking as affordable, demonstrating that tariff awareness is an effective engagement tool. These findings are now informing utility-led eCooking scale-up efforts in Tanzania (via TANESCO) and Kenya (via KPLC). The second case study, developed with UNIDO and Koko Networks, explored the scalability of bioethanol (1, 2) in Kenya, Rwanda, and Tanzania. Kenya has made progress through commercial investment and tax incentives, while Tanzania continues to face regulatory and affordability barriers. Although large-scale bioethanol expansion is unlikely in the short term, many countries are considering it within broader multi-fuel strategies, making it important to keep research and evidence up to date.
Output Changes
No changes.

Lessons and Recommendations
The addition of CLASP as a Tier 1 MECS partner for Venture Building aims to strengthen the continuity of MECS support from early-stage R&D through to market readiness and scale-up. The innovation projects funded under the previous Sparking the Cooking Supply Chain (S2C) call were originally intended to progress into a third phase. However, ATEC secured significant investment through capital raises and carbon registration, making further grant funding unnecessary. The remaining companies were unable to demonstrate viable business models for scaling supply chains without continued external support (e.g. grants, carbon finance, or results-based funding). Under the new delivery model, LU/Gamos will focus on supporting early- to mid-stage innovations helping de-risk the development of their technologies and early trialling, with promising ventures ‘graduating’ to CLASP’s Venture Building R&D support which is designed to position them for participation in national-scale programmes such as the ESMAP Clean Cooking Fund and other large initiatives.
Work on the SC2 call has also highlighted the challenges of reaching remote areas, where customer acquisition costs are significantly higher; something many companies still overlook when designing their business models. Several COSMO projects have found that community-based appliance demonstrations are key to building customer trust in new technologies. Exploring ways to replicate this kind of engagement at scale could help improve uptake and reduce acquisition barriers in underserved regions.
Recommendation 2: CLASP and LU to develop a joint framework by April 2026 to transition high-potential projects from LU’s tech accelerator to CLASP’s Venture Building support. This should include criteria for graduation, regular progress reviews, and alignment with national programmes like the ESMAP Clean Cooking Fund, ensuring continuity from R&D to scale-up and preventing promising innovations from stalling due to funding or capacity gaps.
A woman in Uganda using electric cooking appliances outdoors, powered by a mini grid supported by a MECS pilot (CREEC).

Output 3 - Venture building R&D support to individual companies, studios and investors to increase manufacturing and distribution of clean cooking devices
Impact weighting (%):	10%	Rating:	A - Output met expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
3.1 Businesses supported with R&D to integrate or expand eCooking device production and sales	0	0	N/A
3.2 Businesses securing Series A funding, raising at least $250k in investment, or obtaining commercial loans or blended financing for eCooking expansion	0	0	N/A
3.3 Businesses that achieve positive Earnings Before Interest, Taxes, Depreciation, and Amortization (EBITDA) for at least two consecutive quarters	0	0	N/A

Performance Summary
This output was launched in June 2025, following the signing of a new funding agreement between FCDO and CLASP. As this annual review only covers the first three months of implementation (up to August 2025), no specific logframe milestones were set. The ‘A’ rating recognises the progress made during this inception period and that planned activities are on track.

Despite the short timeframe, foundational activities have begun. CLASP has agreed a five-year workplan with FCDO focused on targeted venture building support for at least three high-potential, early-stage clean cooking companies (with scope to expand if additional budget is allocated). These ventures will be selected through strategic consultations and prior collaboration experience. Each will receive tailored business-relevant R&D grants and complementary technical support from MECS for example to validate product-market fit, customer surveys, or to further pilot innovative approaches in new areas, helping businesses unlock investment and scale their eCooking product sales.
Electric boiler manufacturing facility in Kenya (Ecobora).

CLASP has also initiated exploratory work on potential joint venture opportunities, which could include investment by established players, product line expansion by appliance manufacturers, partnerships with local distributors, market entry support for regional manufacturers, and cross-sector collaborations with solar, agri-processing, and LPG actors. CLASP will engage capital providers such as Acumen, Shell Foundation, Persistent Energy, Manufacturing Africa, Trade Development Bank, and Equity Bank to shape investment criteria, de-risk opportunities, and mobilise blended finance for selected ventures.

Initial activities are focused on high-opportunity markets: Kenya, Malawi, Ghana, India, Indonesia, and Nepal, selected based on local presence, partnerships, early signs of market potential, and alignment with MECS goals.

Output Changes
None. This is a newly launched Output.

Lessons and Recommendations
Recommendation 3 – CLASP to establish a clear and transparent process for selecting eCooking ventures to receive MECS support, by December 2025. This should include a Steering Committee, defined selection criteria, and final approval from FCDO.
Output 4 - Market infrastructure supported to underpin clean cooking transition
Impact weighting (%):	20%	Rating:	A+ - Output moderately exceeded expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
4.1 New World Bank Country Climate and Development Reports (CCDR) developed with support from ESMAP that include a clean cooking analysis	6	11	Exceeded
4.2 New clean cooking Results Based Financing (RBF) or Carbon/Climate Finance initiatives developed and/or piloted with support from MECS	14	14	Met
4.3 Countries provided with MECS technical advice for clean cooking scale-up	LU: 15 / ESMAP: 30	LU: 16 / ESMAP: 30	Met
4.4 Energy-efficient eCooking appliances identified, tested, and recognised through Global LEAP Awards	0	0	N/A
4.5.1 Letters of intent (LoIs) from national representatives welcoming GeCCo support	6	8	Exceeded
4.5.2 GeCCo engagement group meetings held	3	4	Met

Performance Summary
This output is progressing strongly, with two milestones exceeded and the remainder on track, justifying the ‘A+’ rating. MECS has delivered robust R&D contributions that inform programme design, financing and policy – covering diagnostics, modelling and technical analysis to strengthen the enabling environment for clean cooking transitions.

4.1 New Country Climate and Development Reports (CCDR) developed with ESMAP support: CCDRs are World Bank country diagnostics that integrate climate and development priorities to guide impactful actions on emissions reduction, adaptation, and broader development goals. ESMAP supports the integration of clean cooking into these reports through research, analysis, and climate model data. So far 11 CCDRs (target 6) have been supported by the MECS programme: Kenya, DRC, Côte d’Ivoire, Liberia, Benin, and published this year, Uganda, Tanzania, Sierra Leone, Senegal, Togo, and Burundi, all featuring substantive clean cooking contributions.

4.2 New clean cooking Results Based Financing (RBF) instruments or Carbon and Climate Finance programmes developed and/or piloted with MECS support: To date, MECS research, evidence and technical support has influenced the design and development of 14 clean cooking finance instruments and programmes (target: 14). Loughborough University has supported 11, including the RBF mechanism for electric pressure cookers (funded by EnDev), Gold Standard’s metered methodology, and the SPARK+ Africa Fund, which raised over $40m to invest in clean cooking solutions. A new instrument added this year enables black carbon impact calculations as an extension to the MECS-developed Methodology for Metered & Measured Energy Cooking Devices (MMMECD). Additionally, MECS R&D contributions via the ESMAP Clean Cooking Fund have supported the design and development of two World Bank investment projects (including a new project in Malawi this year) which are now being directly supported by RBF contributions from the FCDO Pioneer Outcomes Fund programme:
- Accelerating Sustainable and Clean Energy Access Transformation Program (ASCENT) (P181328): $5bn programme to increase access to sustainable and clean energy in Eastern and Southern Africa, including by accelerating access to clean cooking. It includes a regional RBF Facility designed to accelerate the deployment of distributed renewable energy (DRE) and clean cooking solutions in underserved and unserved markets.
- Accelerating Sustainable and Clean Energy Access Transformation in Malawi (P502464): $250m programme supporting grid and off-grid electrification, which includes a dedicated clean cooking component. It targets households, schools, and health centres, addressing Malawi’s heavy reliance on biomass and associated health and environmental impacts. Findings from this initiative will inform future programme design and policy development.
4.3 Countries supported with clean cooking scale-up: through applied research and technical advice, 33 unique countries have been supported between Loughborough University and ESMAP to accelerate clean cooking adoption and innovation.
Loughborough University supported clean cooking scale-up in 16 countries[4] (target 15) across Sub-Saharan Africa and South Asia. In addition to the Tanzania and Uganda demonstrators, key contributions this year include technical inputs to Sierra Leone’s forthcoming National Strategy (ensuring inclusion of eCooking) and enabling a landmark Article 6.2 Carbon Purchase Agreement between Malawi and Switzerland, set to benefit 85k households and unlock $4m in carbon finance. In Nepal, where 54% of households rely on traditional biomass for cooking, MECS research and advocacy helped embed eCooking targets and recognition of black carbon’s harmful impacts in the country’s latest Nationally Determined Contribution. ESMAP supported 30 countries[5] (target: 30), with five countries added this year: Liberia, Burkina Faso, Honduras, Nigeria, and Colombia.
[4] Countries supported by LU: Bangladesh, Bhutan, Burundi, Cambodia, Ghana, India, Kenya, Lao PDR, Malawi, Nepal, Nigeria, Rwanda, Sierra Leone, Tanzania, Uganda and Zambia.
[5] Countries supported by ESMAP: Bangladesh, Burkina Faso, Burundi, China, Colombia, DRC, Ghana, Guatemala, Honduras, India, Kyrgyz Republic, Laos, Liberia, Malawi, Mauritania, Mozambique, Myanmar, Namibia, Nepal, Niger, Nigeria, Panama, Papua New Guinea, Rwanda, Sierra Leone, South Africa, Tanzania, Uganda, Yemen, Zambia.

4.4 Global Leap Awards: CLASP is preparing to launch the 2026 Global LEAP Awards competition, with clean cooking appliances to be tested in Ghana and Indonesia. This R&D initiative aims to stimulate market development by identifying, testing, and recognising high-performing eCooking appliances, while encouraging greater private sector engagement. Over the past three months, CLASP has initiated preparatory activities including engagement with product suppliers and manufacturers, identification of local testing partners in Ghana and Indonesia, updates to the competition’s administrative infrastructure, and implementation of risk mitigation measures. These efforts are intended to support strong participation and ensure effective delivery.

4.5 GeCCo letters of intent and Engagement Group Meetings: Letters of intent expressing interest in coalition support have been received from 8 countries to date (target: 6), including Laos, Somalia, Nigeria, and 5 new additions this year - Rwanda, Sierra Leone, Madagascar, Kenya, and Burundi. While submissions will remain open, the focus is shifting to tracking tangible collaboration with countries already engaged in GeCCo. Over the past 12 months, MECS convened 4 GeCCo engagement group meetings (target: 3), along with 7 country-specific sessions open to GeCCo members. The engagement group now includes 36 international organisations.

Output Changes
No changes.

Lessons and Recommendations
Recent experience highlights the growing importance of robust data modelling and technical analysis in supporting clean cooking transitions. Beyond carbon finance, partners increasingly seek guidance on complex issues like fuel stacking and practical tools to interpret clean cooking data. Digital data collection offers new monitoring opportunities, though measuring co-benefits (such as health and gender impacts) remains costly and complex. For GeCCo, the focus should now shift from securing new letters of intent to deepening engagement with committed countries, maximising the impact of technical support and collaboration.
Recommendation 4: MECS to continue exploring a diverse range of financing mechanisms beyond carbon finance, such as on-bill financing with utilities and Mission 300 RBF facilities, to help overcome the upfront costs of clean cooking appliances. Although carbon finance is attractive, relying solely on it could leave companies vulnerable to fluctuations in global carbon markets. Expanding partnerships with utilities and piloting alternative financing models will help drive sustainable growth in the sector.
Recommendation 5: GeCCo to propose a new logframe KPI by March 2026 (in addition to tracking meetings and letters of intent), focused on measuring the depth and quality of engagement with countries already committed to the programme. This KPI will help track progress beyond initial expressions of interest and ensure that technical support and collaboration are delivering meaningful outcomes.
Output 5 - Leadership and coordination on clean cooking and MECS M&E
Impact weighting (%):	5%	Rating:	A - Output met expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
5.1 Meetings convened for MECS Advisory Group	3	3	Met
5.2 Meetings convened for Leadership Group of Ayrton Fund Modern Cooking Challenge	3	3	Met
5.3 Ayrton Modern Cooking Challenge Plan drafted, updated annually, and shared with FCDO	2	2	Met
5.4 MECS newsletters published	24	24	Met
5.5 Independent reviews of the MECS programme	1	1	Met

Performance Summary
This output is on track, with all milestones met and an ‘A’ rating achieved. MECS has convened essential governance meetings, delivered strategic planning documents, strengthened coordination across the Ayrton Fund portfolio and wider clean cooking sector, and maintained consistent communications. An independent mid-term review of the programme was also completed.
5.1 MECS Advisory Group meetings: 3 meetings held to date as planned, with internal and key external stakeholders, including in Nov 2024 and Jun 2025. Discussions included the collaboration between LU, CLASP and ESMAP, the reduced ODA budget and implications for MECS, future MECS priorities, as well as key topics such as carbon finance, Article 6 and event planning.
5.2-3 Ayrton Fund Modern Cooking Challenge meetings and plan: A Steering Group for the Modern Cooking Challenge, comprising partners such as LEIA, ICLEI, Shell Foundation, GDC, Crowd Power, GGE-EA, M4D, ASPIRE, and BRILHO, was established to guide strategic direction of the Challenge and has met 3 times to date as planned, including twice in the past year. In Dec 2024, the group explored carbon finance and Article 6, while the May 2025 meeting focused on gender and emerging work in institutional and commercial cooking. The next meeting is scheduled for Nov 2025. The Challenge plan was also updated in 2025.
5.4 Newsletters: Monthly MECS newsletters have continued to be published, maintaining consistent communication with stakeholders and generating strong engagement, with over 5,000 views recorded over the past year.
5.5 Mid-term review: An independent mid-term review of the MECS programme was completed by ECO Limited in Dec 2024. Its recommendations, including around programme structure, budget allocation, and strategic partnerships have informed this annual review and the design of the second phase of the programme between 2025-2030. See final section (G) on Monitoring, Evidence and Learning, for an update on these recommendations.

Output Changes
No changes.

Lessons and Recommendations
In December 2024, the gender framework was presented and follow ups requested from several participants. There seems to be an opportunity to engage on the Aryton Modern Cooking group on wider issues of GEDSI which can be explored.

Recommendation 6: LU to lead and complete a stocktake of the Ayrton Fund Modern Cooking Challenge by December 2025, following the approach set out by the Carbon Trust, to review key actions, outcomes, and lessons learned and inform future HMG programmes and priorities.
Output 6.1 - Country demonstrators funded by FCDO Posts to scale-up clean cooking innovations in target countries: Tanzania
Impact weighting (%):	5%	Rating:	A - Output met expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
6.1.1 Households provided with affordable efficient electric cooking appliances	3,000	2,727	Met / (91% achieved)
6.1.2 People reached by nationwide government-stamped advertising campaign to increase awareness and demand for eCooking	3,000,000	>10,000,000	Exceeded
6.1.3 Technicians trained on repair and maintenance of electric cooking appliances	200	321	Exceeded
6.1.4 Schools supported to transition to clean cooking (via SEforAll and WFP)	6	1	Not met

Performance Summary
This Output, funded with £3.5m from the British High Commission in Tanzania, continues to demonstrate the viability of scaling eCooking nationally and has strong support from the British High Commissioner. Appliance distribution is progressing well, while the awareness campaign and technician training have already surpassed their final targets. Progress on school transitions has been slower, with one school converted so far, but significant scale-up is expected in the coming months. The output is rated ‘A’ due to strong progress overall; where delays exist, these are largely due to external factors, and all targets remain on track for completion by March 2026. The UK in Tanzania, through MECS, is now seen by the Uganda government as the go to partner on eCooking.
British High Commissioner to Tanzania, Marianna Young, participates in a MECS workshop in Dar es Salaam on 'Clean Cooking Transitions in Schools’.
6.1.1 Households Provided with eCooking appliances: MECS is collaborating with the Tanzania Electric Supply Company Limited (TANESCO) and 11 supply chain companies to stimulate the market for efficient eCooking appliances. To date, these companies have sold 2,727 appliances against a target of 3,000 and expect to double this figure in the next quarter. With MECS support, TANESCO launched a new staff payment scheme for eCookers, resulting in 1,000 EPCs sold in just one week. Inspired by this, the Uganda Ministry of Energy and the Rural Electrification Agency are now developing similar schemes. A TANESCO pilot for on-bill financing is also planned, which is expected to further accelerate uptake over the coming year. This activity experienced a brief delay due to internal management changes within TANESCO and contracting issues with suppliers. Meanwhile, the smaller companies, supported through working capital grants, are steadily building their market share and customer base.
6.1.2 Awareness Campaign: Fern Marketing has been contracted to deliver a nationwide campaign to increase awareness of eCooking across Tanzania. To date, the campaign has reached 10m people (against a final target of 6m expected by March 2026) through radio jingles, billboards, and two episodes of a six-part educational series. Additionally, 52 full-day demonstrations have been conducted across five regions, directly engaging 3,100 individuals.
6.1.3 Technician Training: FixChap has trained 321 technicians on the repair and maintenance of eCooking appliances (target 200). Notably, 22% of trainees are female, and the programme has already exceeded the target expected by March 2026 (of 400 technicians trained).
6.1.4 School Transition to Clean Cooking: SEforAll, in partnership with WFP, the Government of Tanzania, and with support from MECS, has transitioned Kibasila Primary School in Dar es Salaam to clean cooking and plans to support 32 additional schools by January 2026, including 20 attributable to MECS. Although the target was to reach at least 6 schools by now, progress has been slowed by infrastructure challenges, procurement delays, and rising costs. The launch of the first eCooking Model Kitchen at Kibasila is a key milestone, with the school now equipped with electric pressure cookers and upgraded kitchen infrastructure, serving over 350 students daily. This pilot lays the foundation for national scale-up and demonstrates the potential of clean cooking to improve health, education, and sustainability outcomes.
Output Changes
No changes.

Lessons and Recommendations
Delivering eCooking innovations at scale in Tanzania has taken longer than expected, mainly due to a limited number of local suppliers and the need to adapt products with overseas manufacturers. Early and regular engagement with government ministries has proven essential for overcoming regulatory and logistical hurdles.
Having an in-country liaison has been invaluable for maintaining momentum, ensuring cultural sensitivity, and keeping stakeholders engaged.
Upgrading school infrastructure for eCooking has proven more complex and costly than anticipated. The appliance itself is a small part of the transition, which often requires kitchen renovations, new meters, and grid upgrades. Projects involve multiple stakeholders, from ministries and regulators to utilities, banks, and schools with varied legal structures. MECS has faced a steep learning curve over the past year and is increasingly recognised as a key authority on school transitions.
Going forward, allocating more time at the outset for engaging all relevant ministries, parastatals, and local partners will help address challenges early and lay a stronger foundation for delivery.
Recommendation 7: LU to conduct a ‘lessons learned’ review after the completion of the first phase of the MECS Tanzania and Uganda demonstrators in March 2026 to capture practical insights on overcoming delivery challenges, inform the design of future demonstrators, and support more effective scale-up of clean cooking innovations in other countries.
Kibasila Primary School in Dar es Salaam, Tanzania, recently transitioned to clean cooking.
Output 6.2 - Country demonstrators funded by FCDO Posts to scale-up clean cooking innovations in target countries: Uganda
Impact weighting (%):	5%	Rating:	A - Output met expectation

Indicator	Milestone / (Sep’18 to Aug’25)	Achieved / (Sep’18 to Aug’25)	Rating
6.2.1 eCooking appliances supplied to households and schools through aggregators, local distributors and businesses	5,000	0	Not met
6.2.2 People reached by nationwide government-stamped advertising campaign to increase awareness and demand for eCooking	4,000,000	>20,000,000	Exceeded
6.2.3 Technicians trained on repair and maintenance of electric cooking appliances	300	400	Exceeded

Performance Summary
This Output, funded with £3.5m from the British High Commission in Uganda, continues to demonstrate the viability of scaling eCooking nationally and has strong support from the British High Commissioner. Despite delays in launching appliance distribution through a financial aggregator, the Output is rated ‘A’ as the nationwide awareness campaign and technician training have significantly exceeded their targets. Strong overachievement in these areas highlights effective delivery and positive impact, outweighing the temporary distribution setback. Performance was validated through a joint review by RED and the Country Post in October 2025. Following this, the Post has committed additional budget to extend this Demonstrator for one year, until March 2027.
British High Commissioner, Lisa Chesney, with Minister for Energy, Ruth Nankabirwa, during clean cooking demonstration event.
6.2.1 Households and Schools Provided with eCooking appliances: Progress has been made towards appliance distribution (including EPCs and induction hobs), though it hasn’t started. Procurement for a financial provider began in Nov 2024 but failed twice due to limited interest; the tender was revised and reissued. Progress has been slow as banks are risk-averse and developing a new financial product has been complex, but a supplier has been selected, and contracting is underway. The Fund is expected to become operational in Q3 2025/26, paving the way for distribution. Meanwhile, 100 schools and four delivery partners have been selected for an eCooking pilot, energy audits completed, and work expected to start in Q3.
6.2.2 Awareness Campaign: The nationwide awareness campaign for eCooking implemented by the National Renewable Energy Platform (NREP) has gained strong traction. To date, it has reached over 20m people through in-person events, radio shows, TV debates and adverts (print and social media), far exceeding the milestone of 4m and the final target of 9m people expected by March 2026. The campaign has focused on schools, religious institutions, and public and cultural spaces, and is being recognised as a successful model for behaviour change communication in Uganda.
6.2.3 Technician Training: The technician training programme is delivered by the Centre for Research in Energy and Energy Conservation (CREEC) and is progressing well, with 400 individuals trained so far (including 21% female), exceeding the milestone of 300. The programme is on track to meet the final target of 600 technicians trained by March 2026.

Output Changes
Technicians trained on appliance repair and maintenance in Uganda.

No changes.
Lessons and Recommendations
Scaling eCooking rapidly remains a challenge, but the Uganda demonstrator is emerging as a strong model. The Ministry of Energy and Mineral Development (MEMD) increasingly views it as a reference for future clean cooking programmes. The demonstrator has helped drive policy change, with MECS-supported evidence shaping Uganda’s clean cooking strategy, informing standards, tariffs, and subsidies, and contributing to Uganda’s Fourth National Development Plan targets. It has also influenced broader energy policy, including the Free Connections Policy, reinforcing MECS’s long-term role in government engagement.
While it is estimated that over 10,000 EPCs have already been sold, the lack of systematic sales reporting creates a data gap, making it difficult to verify uptake. This highlights the need for an aggregator to manage finance and provide centralised, reliable evidence of sector-wide progress.
User preferences show strong demand for larger EPCs (especially those over six litres) and for access through Savings and Credit Cooperative Organisations (SACCOs) and group financing models. Live demonstrations have been the most effective tool for shifting perceptions and building trust. Surprisingly, men are often the decision-makers in EPC purchases, motivated by economic benefits. Rural and low-income households require targeted subsidies to ensure equitable access.
To maximise the impact of technician training, refresher courses, toolkits, and stronger links to distributors are essential. At the same time, low awareness of biomass-related health risks suggests the health narrative remains an underused driver of demand.
To sustain and scale the impact of this eCooking demonstrator, future activities should integrate air quality and health data into campaigns to highlight the benefits of reduced indoor pollution. The nationally recognised awareness campaign should be maintained through partnerships with MEMD, development partners, and the private sector. Expanding access via SACCOs and savings groups will help address affordability, while empowering local champions (such as teachers, faith leaders, and technicians) will reinforce trust. Interventions should also extend to humanitarian settings, where biomass reliance is high. Ensuring product quality through stronger standards enforcement, introducing supply-side subsidies, and deepening technician support will strengthen consumer confidence. Finally, embedding tools and practices within the Clean Cooking Unit (CCU) will help institutionalise progress and support long-term scale-up.

Recommendation 8: LU to work with Post to develop a 1-year extension to the Uganda Demonstrator and ramp up communication of outcomes, including consolidation of funding lines, continued engagement with the CCU, and planning for visits to the Demonstrator in 2026 by the Minister for Development and potential scale-up funders, such as Saudi Arabia.
Uganda Minister for Energy, Ruth Nankabirwa, with community and religious leaders during MECS-supported clean cooking demonstration event.
## D: VALUE FOR MONEY (VfM)

The independent mid-term review of the MECS programme completed in December 2024, rated the programme’s overall Value for Money as Very Good. The programme demonstrates strong performance across the core VfM dimensions of economy, efficiency, effectiveness, cost-effectiveness and equity, with ratings and main findings summarised below:
VfM Dimension	Rating (LU)	Rating (ESMAP)
Economy	Excellent	Very Good
Efficiency	Excellent	Excellent
Effectiveness	Very Good	Very Good
Cost-Effectiveness	Very Good	Very Good
Equity	Good	Good
Overall	Very Good	Very Good

Economy: Operational costs at Loughborough University (LU) are rated Excellent at 9% of total spend, which is comparable to or better than similar international programmes such as EnDev and the FCDO Transforming Energy Access (TEA) platform. LU’s cost management is robust, with prudent procurement, competitive tendering, and the use of skilled in-country experts to maximise value. MECS has also demonstrated strong co-funding leverage, mobilising significant additional resources from both public and private sources. For ESMAP, economy is rated Very Good, but the review notes that cost tracking is less transparent due to the Clean Cooking Fund’s structure, making it harder to isolate MECS-specific spending.
Efficiency: Rated as Excellent. MECS consistently delivers outputs on time and within budget, with many outputs exceeding targets. The programme reinvests any savings to maximise delivery and impact. Standardised processes, regular quarterly and annual reporting, and adaptive management have enabled MECS to maintain high efficiency even during periods of budget cuts and external shocks such as the COVID-19 pandemic. Both LU and ESMAP benefit from established administrative and HR systems, which support efficient delivery.
Effectiveness: Rated Very Good. MECS has exceeded its targets for co-funding leverage, energy access, and green jobs. The programme’s research, policy influence, and partnerships have contributed to significant progress in clean cooking access and market development. MECS has also played a key role in shaping national policies and supporting international organisations to adopt clean cooking principles.
Cost-Effectiveness: Rated Very Good. MECS achieves cost per outcome levels that are below or comparable to international benchmarks for access to clean energy and CO₂ emissions avoided. For example, the cost per person with improved energy access is £10.51, outperforming the EnDev benchmark of £12.13. The cost per tonne of CO₂ avoided is £39.66, which is well below comparable programmes. Results demonstrate MECS is delivering significant impact for each pound invested by the UK.
Equity: Equity is rated as Good. MECS’s focus on eCooking benefits women and marginalised groups, and nearly half of green jobs created are held by women. However, the review notes that the poorest and those without electricity may be excluded from the programme’s benefits. While MECS has made progress on gender, further work is needed to fully integrate Gender and Social Inclusion (GESI) into the logframe and reporting, and to ensure that equity is systematically tracked and reported.
Areas for Strengthening: The mid-term review recommended further improvements in cost tracking (especially for ESMAP), more structured partner selection, and enhanced reporting on equity and GESI outcomes. MECS is taking steps to address these, including operationalising the Gender Framework, updating the logframe, and strengthening local partnerships (see M&E section for details).
E: RISK

FCDO’s risk appetite for the MECS programme is shown below.
Pillar	FCDO risk appetite
Strategy & Context	Receptive
Policy & Programme Delivery	Receptive
Financial & Fiduciary	Cautious
Safeguarding	Cautious
Reputational	Cautious

The overall risk rating for MECS is Moderate, with all risks currently assessed as being within appetite. Risk management across the programme is robust, supported by clear mitigation strategies and regular reviews. Each MECS project maintains a live risk register, which is periodically reviewed with project managers to ensure responsiveness to emerging risks. Some of the current risks associated with the delivery of MECS primarily relate to:
- Country stability: MECS operates primarily in stable environments, which helps to keep overall risk low. However, recent political disruptions in countries such as Nepal have led to some delays in programme delivery. The MECS management team remains in close contact with local partners in affected areas, actively monitoring developments and adapting workplans as needed to minimise disruption and ensure continuity.
- GeCCo: Working within the GeCCo coalition presents unique challenges due to its structure as a coalition rather than a single programme. Coordinating among multiple parties, each with ambitious goals and a small Secretariat, requires significant effort and flexibility. Nevertheless, this coalition model also creates valuable opportunities for MECS to leverage its influence and evidence base to broker new partnerships and initiatives—for example, ongoing discussions facilitated by MECS between the Governments of Saudi Arabia and Kenya to scale up modern energy access.
- Demonstrators: Timely implementation of country demonstrators remains a challenge, largely due to their scale and the pace required for delivery. Strong relationships with British High Commissions and lead government ministries have been instrumental in navigating these complexities and maintaining momentum. Lessons learned from current demonstrator projects are informing future staffing models, particularly to address the challenges of recruiting for short-term contracts and ensuring sufficient capacity for delivery.

The FCDO has worked with MECS partners to review their downstream Health & Safety (H&S) practices, and to assess overall risk and key mitigations. Overall, H&S risk for MECS is considered low and activities can broadly be categorised into three types – desk, lab, and field-based. H&S risks for desk-based activities are negligible. Lab based activities are always conducted with experienced partners, but there is scope to improve the recording of specific H&S risks in project preparation and reporting documentation. Field research is always conducted by experienced, local partners. All travel is risk-assessed and international travel is limited (travel to high risk/conflict zones is not permitted). Partners of lab and field-based activities are required to have appropriate insurance, document and report project risks, and ensure any cooking appliances used in project activities meet national or international safety standards. Participants receive safety briefings along with all the ethical requirements of informed consent. The review has found opportunities to strengthen the overall approach, such as requiring all partners to explicitly declare H&S risks and proposed mitigations from the outset as part of project proposals, and to report against these throughout implementation, including through risk registers. For activities considered higher risk (including, for example, venture building R&D which will support selected companies to develop and scale eCooking products), partners will also be required to have a documented H&S policy in place, which will be reviewed according to specific criteria.

Recommendation 9: FCDO to agree a set of H&S improvements to the MECS programme with partners by October 2025, ensuring that requirements remain proportionate to the level of risk involved in each activity.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

In November 2025, the MECS business case was extended to December 2030 and the budget increased from £55m to £99m, as announced at COP29. However, following the ODA budget reduction announced by the UK government in February 2025, a temporary pause was placed on signing new funding agreements while an FCDO-wide review and prioritisation exercise took place. As a result, funding agreements with MECS delivery partners for the extension period are currently at a lower budget level than originally anticipated, and the size of additional funding and results to be achieved is being consider as part of the current spending review process. The MECS ToC remains valid at this lower budget level and significant results can still be achieved cost effectively.

Of the total MECS business case budget envelope of up to £99m between 2018/19 and 2030/31 (comprising £79m for R&D and £20m for demonstration projects), £64m has been committed so far through funding agreements with Tier 1 partners (£57m for R&D and £7m for demonstration). The remaining £35m is currently uncertain, due to the reduction in the ODA budget, and will depend on FCDO budget availability and annual allocations in the coming years

Below is a summary of MECS budget commitments by Tier 1 partner and component. To date, most of the committed budget has been allocated to Loughborough University and its partners (81%), followed by CLASP (6%), ESMAP (13%), and ECO for the mid-term review (0.1%).

Funding	Year	L. University / (R&D)	CLASP / (R&D)	ESMAP / (R&D)	L. University demonstrators / (Tanzania & Uganda)	ECO (MECS mid-term review 2024)	Total
Spent	2018/19 – 2024/25	£30,096,358		£7,350,000	£2,781,771	£93,965	£40,322,095
Budget	2025/26	£4,500,000	£1,500,000	£1,000,000	£4,368,229	-	£11,368,229
	2026/27	£2,500,000	£1,000,000	-	-	-	£3,500,000
	2027/28	£2,500,000	£500,000	-	-	-	£3,000,000
	2028/29	£2,500,000	£500,000	-	-	-	£3,000,000
	2029/30	£2,500,000	£500,000	-	-	-	£3,000,000
	2030/31	-	-	-	-	-	-
Total		£44,596,358	£4,000,000	£8,350,000	£7,150,000	£93,965	£64,190,323

Performance and Key Developments (Sept 2024 – Aug 2025)
- MECS partners continued to meet expectations, submitting timely reports and invoices, providing accurate forecasts, and responding promptly to FCDO requests and corporate commissions.
- A plan for the MECS extension to December 2030 was agreed, including a smaller, more focused geographic scope and an updated logframe to reflect the Venture Building R&D work of new Tier 1 partner, CLASP.
- MECS partners reported results against ICF KPIs up to March 2025, with:
  - Nearly 700k people provided with clean cooking access (cumulative total: 4.5m).
  - £34m leveraged for clean energy and cooking R&D (cumulative total: £435m).
  - 2.5 million tonnes of CO₂ emissions avoided, reported for the first time using a newly developed ICF-compatible methodology.
  - All results were quality-assured by the ICF team, with no adjustments required.
- An independent mid-term review of MECS was conducted by ECO Limited between June and December 2024. The supplier performed well and delivered on the contract terms, with findings summarised in the next section.
- Loughborough University updated the Ayrton Fund Energy Portfolio Analytics (EPA) database, mapping the MECS delivery chain by country, technology, sector, and funding. This has been invaluable for FCDO, improving visibility and enabling timely responses to HMG briefings and commissions.
G: MONITORING, EVIDENCE AND LEARNING

The independent mid-term review of the MECS programme, assessed its performance very positively. The review highlighted MECS’s significant influence on the global clean cooking agenda, especially in advancing eCooking, and its ability to leverage substantial co-funding and partnerships across 37 countries. MECS was commended for its agility, technical credibility, and strong alignment with the Ayrton Fund and UK International Climate Finance (ICF) objectives. The review also praised MECS for exceeding targets on clean cooking access, co-funding, and green jobs, for its robust governance and quality assurance frameworks, and for its diverse teams (55% women, 45% from the Global South). MECS’s research and policy work were also noted as shaping international discourse and supporting policy change in multiple countries.

Key areas for improvement and actions taken so far:

Expand strategic partnerships and local voices: CLASP was added as a new Tier 1 partner to strengthen venture-building and private sector engagement. MECS will further improve localisation by seeking opportunities for local partners to shape strategy and delivery, and by considering the recommendations from the recently completed Ayrton Fund deep dive on localisation and equitable partnerships and how to apply these to MECS.

Shift to proactive, systemic management: One new professorial-level co-investigator has joined the MECS management team, and CLASP is adding additional programme management capacity. MECS will continue to review management structures to ensure resilience and proactive delivery.

Enhance communications and clarify partner roles: The MECS communications strategy and website are being updated to reflect the MECS2 extension, with a focus on clearer partner roles and improved accessibility for non-academic and private sector audiences. The search function has been improved. CLASP, ESMAP and LU have a standing monthly management meeting to discuss ongoing and forthcoming activities and events.

Increase gender and Global South representation: MECS will continue to seek opportunities to increase gender and Global South representation at major events and in programme leadership, including sponsoring partners to participate in global forums and expanding the “Voices of MECS” initiative.

Expand pilots and support for marginalised groups: While reduced budgets have limited new technology accelerators, MECS will prioritise pilots for marginalised groups if additional funding becomes available and will continue to support work in informal settlements and with vulnerable communities.

Strengthen focus and transparency on GESI: The MECS Gender Framework has been completed and an outcome-level gender KPI added to the logframe. Partners are exploring how best to operationalise this framework as part of the MECS2 extension.

Address delays in country demonstrators: Demonstrators in Tanzania and Uganda are now operational and delivering results. Discussions are ongoing with other country posts (e.g., Malawi, Indonesia) about future demonstrators.

Date of last narrative and financial report	L. University and CLASP MECS2 presentation, Aug 2025 (Internal) / ESMAP Annual Report 2024
Date of last audited annual statement	Loughborough University Financial Statements 2023/24 / World Bank Year-end Single Audit Report for June 2024

## Annex 1 – Summary of progress against 2024 annual review recommendations

No.	Recommendation	Update
1	Where countries are not ready to embrace a full transition to electric cooking, MECS partners should situate research findings within in a multi-fuel approach, working towards a partial or phased transition.	Ongoing. For example, this year MECS partners have worked with AFREC, CCAC and the G20 clean cooking advisory group on multi-fuel approaches.
2	MECS partners to increase research on institutional and commercial cooking.	Ongoing. Four studies on using eCooking in the pre-cooked food sector have been commissioned. MECS is working with Shell Foundation (under TEA) on a project with street food vendors. Research on institutional settings is also embedded into both ongoing demonstrators.
3	MECS partners to embed research in influential data and modelling collections such as by the IEA, IRENA, and SEforAll.	Ongoing. Development and launch of the Visualisation of Key Data and Decision Tool (VKDD) is intended to be used by modelers at the start of a project to check their assumptions and to include stacking behaviour.
4	Loughborough University to develop a plan for future innovation calls by April 2025, building on an analysis of past successes and challenges.	Paused. This action was put on hold when the reduction to ODA was announced in February 2025, with no more calls expected with the current budget envelope.
5	MECS partners to work with venture building organisations such as CLASP, Acumen, and E4I to explore approaches to unlock the capital needed to support venture building activities.	Completed. CLASP have been brought on board as a Tier 1 partner and will work on Venture Building activities.
6	MECS partners to explore a wide range of mechanisms that can overcome the upfront costs of cooking appliances.	Ongoing. Through STARSS projects, MECS partners are looking at how different technology configurations can support wider adoption of eCooking.
7	MECS partners to coordinate with the new £30m Results Based Finance contribution from FCDO ECED.	Ongoing. One day planning meeting held in June 2025 to design a programme of activity over the next 12 months.
8	Loughborough University to update Ayrton Modern Cooking Challenge Plan in January 2025, after Steering Group meeting in December 2024.	Completed and presented.
9	MECS partners to actively engage with the upcoming Ayrton Fund study on Localisation and Equitable Partnerships in Q1 2025.	Completed via interviews and feedback on the draft report.
10	FCDO and MECS partners to integrate gender KPIs into the logframe and Theory of Change, expand KPI on jobs created to also include jobs supported, and consider including a forest/nature Outcome-level KPI, by April 2025.	Completed. Gender and jobs KPIs created. Forest/nature KPI considered but deemed too complex to measure at this point. Work on FnRB in relation to carbon calculations might make this possible in the future.

## Annex 2 – Outcome KPI 1.1 Countries that actively implement policies, evidence, and programmes to increase access to modern energy cooking services (MECS)

Sierra Leone: In 2024, the President of Sierra Leone announced the government’s partnership with MECS and the development of a GeCCo Readiness Assessment for Sierra Leone during the IEA Clean Cooking Summit in Paris. eCooking was not originally included in the forthcoming Sierra Leone’s National Clean Cooking Strategy, reflecting the separation of cooking from energy access, and low national electrification (36%, mainly urban). Based on MECS evidence and collaboration with GeCCO, eCooking is now included, aligning with Sierra Leone’s electrification ambitions and paving the way for its inclusion in NDC 3.0 targets. eCooking is expected to account for 25% of the technology mix in urban areas by 2050. Since 2025, Saudi Arabia’s Middle East Green Initiative (MGI) is funding a $3.5m Scale and Support Programme, developed with GeCCO and MECS input, which covers eCooking in schools, off-grid solar, and appliance repair and maintenance.
Uganda: In 2021, informed by MECS evidence and research, the Uganda Energy Regulatory Authority (ERA) implemented a cooking tariff to allow households to use electricity for cooking at half the cost of regular kWh units. A MECS pilot with Uganda's main electricity distribution company (UMEME) started in late 2023 to collect data on usage and help the government adjust the tariff for maximum effectiveness. UMEME's ongoing work has supported local supply chains and markets by offering cooking appliances and collaborating with the regulator to understand the impact of the eCooking tariff. A broader assessment of the tariff and its impact is planned for 2025. In 2024, with MECS support, the Ministry of Energy and Mineral Development developed a National eCooking strategy, aiming to increase eCooking adoption from 1% to 18% by 2030 (this is due to be launched at the Renewable Energy Conference in October 2025). A 2-year £3.65m MECS Demonstrator funded by FCDO Uganda started in mid-2024, including joint action with the government and stakeholders on standards, supply chain, schools, institutional eCooking, repair and maintenance networks, and a national awareness campaign (more details are included under Output 6.2). In 2025, a new Biogas and Electric Cooking Project in Uganda funded by the African Development Bank Group was launched, with a $5.1m grant for eCooking.
Tanzania: In 2024, Tanzania actively engaged on the world stage regarding clean cooking. The President, Hon. Samia, co-chaired the IEA Clean Cooking in Africa Summit in Paris in May 2024 to raise awareness and funding for clean cooking as a policy priority and launched the Tanzania National Clean Cooking Strategy 2024-2034. This strategy aims to ensure that 80% of Tanzanians use clean cooking solutions by 2034. It is a balanced, multi-fuel strategy, including improved cookstoves (ICS), liquified natural gas (LNG), LPG, eCooking, biogas, and bioethanol. MECS reviewed drafts of the strategy twice, providing comments on integrated energy planning and eCooking feasibility and cost-effectiveness to the Ministry of Energy. In July 2025 the government sent a high-level delegation of 5 officials including the Treasury to London to undertake a deep dive into how to fund the strategy, 35 partner representatives were also present. This was supported by Children’s Investment Fund foundation (CIFF) and Afcen with MECS providing technical support. The result was greater clarity on the role of Schools in enabling the transition and deeper discussion of the fiscal space required. The strategy paved the way for the government to support eCooking actions, including enabling electric stoves to be paid for through TANESCO LUKU meters by June 2025, which has been enabled by a 2-year £3.5m MECS Demonstrator funded by FCDO Tanzania (see Output 6.1). The Demonstrator includes joint action with the government and stakeholders on standards, supply chain, schools, institutional eCooking, repair and maintenance networks, and a national awareness campaign. In December 2024, the Submarine Cable Zanzibar Project in Tanzania funded by the African Development Bank Group was launched, with a $6m loan for eCooking.
Kenya: In 2023, the Kenyan Energy and Petroleum Regulatory Authority (EPRA) announced a new domestic customer tariff, highlighting MECS research in their decision. In 2024, a joint tariff experiment by the government, the utility, MECS, and other stakeholders aimed to refine the tariff structure for 2026 to optimise eCooking uptake. The completion of actions funded by MECS and UK PACT, along with contributions from Germany, France, and the Green Climate Fund, led to the launch of a new National Clean Cooking Strategy 2024-2028, and a specific National eCooking Strategy. The Clean Cooking Strategy commits Kenya to a multi-fuel approach, emphasising ethanol, electricity, and biogas, while phasing out biomass and LPG. The Kenya eCooking strategy sets a target of 10% of the population using electricity as their primary cooking fuel by 2030, with further growth expected. Baseline surveys revealed that 6.4% of households now use eCooking as their primary or tertiary cooking fuel, from a baseline of 1% in 2019, which is partly attributable to effective MECS evidence and research. Further exploration of the differentiation between the SDG measure of ‘primary’ fuel and fuel stacking behaviour is planned for 2025 and beyond. A new eCooking Market Development Project is currently being developed in Kenya by AfDB, with $4.4m potentially allocated to it (pending Board approval in Q4 2025).
Rwanda: Rwanda’s Climate Action Plan, set out in its updated Nationally Determined Contribution, commits the country to reducing emissions by 38% by 2030 and reaching Net-Zero by 2050. One key measure in this plan is the dissemination of modern efficient cook stoves to 80% of the rural population and 50% of the urban population by 2030, achieving a sustainable balance between biomass supply and demand, and reducing firewood and fossil energy consumption for cooking. Over 80% of Rwandan households use wood for cooking, followed by charcoal, crop waste, gas, or biogas. The World Bank’s Energy Access and Quality Improvement Project in Rwanda, is the first Clean Cooking Fund project and the largest World Bank financed clean cooking project in Africa, seeking to expand access to clean cooking to 500,000 households across the country and leverage US$30 million in public and private sector investment. The project has established several rounds of its Results-Based Financing programme in Rwanda, enabling purveyors of higher-tier stoves and fuels to provide a supply chain of modern energy cooking services. Other notable projects in Rwanda include BURN Manufacturing, previously supported by MECS, who started a cooking pilot in Rwanda also funded by the Clean Cooking Fund and Electrocook who undertook a study documenting user behaviour in 2023.
India: In 2023, MECS activities with Energy Efficiency Services Limited (EESL) were launched and promoted by the India Ministry of Power in a press release, and these activities have continued to gain pace in 2025 with a tender for 100,000 units being launched in August 2025. Building on the Energy Transition Advisory Committee (ETAC) report: The Green Shift calling for 25% electric cooking adoption by 2030, the Government of India has reached out to MECS for support in developing a ‘carbon calculator’ as they move forward with developing the Indian Carbon Market (ICM). The objective of ICM is to decarbonize the Indian economy by pricing Green House Gas (GHG) emissions through trading of Carbon Credit Certificates. In 2024, MECS published a compendium of 17 policies recently implemented and supportive to eCooking, so that state-level authorities can identify how such national policies apply to them. The Bureau of Energy Efficiency (BEE) continues to implement its MECS-supported star rating for induction stoves to improve energy efficiency among consumer goods. In 2025, international testing by the CLASP-led Global LEAP Awards helped shape India’s new mandatory energy labelling policy for induction cooktops. From 2026, all induction cooktops sold in India must display an energy label, with standards for efficiency and safety set at levels comparable to the EU and China, which is expected to accelerate the adoption of clean, efficient cooking solutions. 2025 has also seen a growing interest from several State level governments in using eCooking to enhance electricity demand and improve revenues. For example, the state government of Kerela are now in active discussions with GGGI regarding a programme of work.
Nepal: In 2023, the Asian Development Bank (ADB) launched a call influenced by discussion with MECS, for a large eCooking pilot distribution project targeting 1,000 households in Nepal as part of the South Asia Subregional Economic Cooperation Power Transmission and Distribution System Strengthening Project. MECS engagement with the Government of Nepal before and during COP28 in Dubai, bore dividends during the formal launch of the MECS-led Global Electric Cooking Coalition (GeCCo) at the mainstage of COP, where Hon. Shakti Bahadur Basnet, Minister of Energy, Water Resources and Irrigation (MoEWRI) participated and provided strong backing for the coalition and acceleration of eCooking. The Government’s Alternative Energy Promotion Centre (AEPC) acknowledged the importance of MECS research on subsidies, repair and maintenance and called for findings to be incorporated in the national electric cookstoves standards in Nepal. The MECS training on repairs and maintenance (available in Nepali and English) has also been endorsed by AEPC, the Council For Technical Education and Vocational Training (CTEVT), and several other major organisations. AEPC intend to make the modules and manuals a key component of the aftersales service in their future interventions, such as the Green Climate Fund-supported eCooking project targeting 500,000 households, and the AEPC-UNDP Renewable Energy for Rural Livelihood (RERL) programme which seeks to integrate eCooking in micro-hydropower sites. In 2025, MECS research and advocacy have shaped Nepal’s latest Nationally Determined Contribution (NDC3), raising the eCooking target for households to 2.1m by 2035, informing a new eCooking target for institutions and firms, and the use of carbon finance for clean cooking promotion. For the first time, Nepal’s NDC3 also recognises the harms of black carbon (much of which is produced from traditional cooking). With 54% of households still using biomass, this shift is crucial for health and emissions, supporting Nepal’s goal of carbon neutrality by 2045.
Bhutan: In 2025, the Government of Bhutan continued to advance plans for a national eCooking rollout, building on a pilot supported by MECS and UNESCAP. As part of the pilot, MECS provided technical support and funding for over 700 IoT-enabled induction appliances, while UNESCAP offered oversight and international expertise. The government covered remaining costs, including user engagement. Following the pilot’s success, Bhutan is currently designing an Article 6.2 carbon finance programme with its Ministries of Environment and Energy and ATEC (private supplier, previously supported by MECS). Discussions with Singapore have led to verbal commitments for carbon finance and pre-finance from international banks. Baselines are complete, but the project depends on securing a high carbon price per credit (early indications are positive). Bhutan added the new project to its Article 6.2 ‘positive list’ in February 2025, though the connection fee is still pending. The goal is to achieve nationwide eCooking adoption by 2028, funded through carbon finance. Bhutan, which uses 100% renewable electricity, currently spends $13m annually importing LPG from India. The project was announced at COP29.

## Annex 3 – Outcome KPI 1.2 Countries that have announced plans to increase access to MECS (including policies, evidence and programmes)

Nigeria: MECS, via GeCCo, advised the Nigerian Alliance for Clean Cooking (NACC) and the National Council for Climate Change (NCCC) on content for an eCooking component in the upcoming National Clean Cooking Policy Implementation Plan. This content formed the basis of a funding request from Government of Nigeria to CCAC. Simultaneously, CCAC were advised on the content that would need to be included in the call for proposals for an eCooking component at national strategy level. The result was the allocation of $300k by the CCAC funding committee to complete the work. The successful consultant will be announced in Nigeria at AICEES conference in September. In collaboration with SEforALL, MECS has also been supporting the development of an innovative proposal to develop a battery bank-based approach to eCooking for productive use, to be submitted to FCDO Nigeria for potential funding. The aim of this project through SEforALL's Universal Energy Facility (UEF), is to incentivise outcomes and encourage private sector investment into the sector, with £5m from ECED's Climate Pull Facility.
Lao PDR: MECS is currently funding and supporting the development of a National eCooking Strategy in Laos PDR, expected to be launched in early 2026. SNV are the lead consultants, working in collaboration with the Department of Energy Efficiency and Promotion (DEEP) and the Ministry of Energy and Mines. UNESCAP are seeking to replicate their actions in Bhutan in Laos, having secured interest from the government to start the three-phase process of accessing Article 6.2 Carbon credits with IoT eCooking. Still on Phase 1, the Controlled Cooking Tests and Kitchen Performance Tests are being supported by MECS. The programme is also working with Energising Development (EnDev) in developing the TORs for a GeCCo Readiness Assessment and supporting the Laos government in developing a Letter of Intent for GeCCo membership.
Bangladesh: through local partners Practical Action and ATEC (supported by MECS through technology accelerators), continues to enable the private sector to roll out induction stoves under the voluntary carbon market. Reaching tens of thousands of users, there is a need for the government to be more aware of this opportunity that contributes to "a market ready range of technology and business model innovations that lead to improved choice of affordable and reliable modern energy cooking services for consumers”. In 2019, MECS supported the revision of the National Action Plan for Clean Cooking 2020-2030 (however, this doesn’t mention eCooking). Following a stakeholder validation workshop in December 2024, the key recommendation was that the revised national clean cooking plan should be incorporated into the Integrated Energy and Power Master Plan (IEPMP) 2023, to ensure alignment and coherence across national energy planning. The IEPMP was approved by the Power Division in 2023 and serves as a key policy framework. ATEC has raised USD $15.5m to expand its network in Bangladesh, Cambodia, Malawi and Nepal, and rollout up to 200,000 IoT (Internet of Things) electric cookstoves.
Cambodia: is host to the private sector initiative of ATEC that has reached thousands of households with induction stoves. ATEC were invited to present their work at the ECED Directors forum in May 2024 where their initiatives were well received. There is a need to create a more purposeful enabling environment within the government, and MECS will build on its earlier market work with IDE which involved studying low income and informal market access, working with the National Council for Sustainable Development and Ministry of Environment, and helping ATEC access Series A investment from SPARK+. ATEC raise of USD $15.5m to do 200,000 of ATEC’s IoT (Internet of Things) electric cookstoves over the next three years (see Bangladesh) includes Cambodia.
Ghana: MECS continues to accelerate the IoT technology of BURN through various activities. In 2023, BURN was awarded Energy Catalyst support from the Transforming Energy Access (TEA) platform to develop the pre-commercial roll out of 10,000 IoT induction stoves in Kenya, Tanzania, Ghana and Zambia. An assembly line has already been established in Ghana, and MECS worked with BURN on refining the Metered Methodology to access voluntary carbon credits for future commercialisation. Since project completion, BURN have started a new factory in Ghana and are selling nearly 3,000 units a month. Ghana has a framework in place for Article 6, and MECS will work towards application of Article 6.2 on carbon credits with Switzerland.
Zambia: MECS had been supporting the USAID Alternatives to Charcoal (A2C) project and contributing to a National Clean Cooking Strategy and Action Plan (CCSAP). A2C closed with the ending of USAID funding so the future of the strategy development was uncertain. In July 2025, MECS received a formal notification from the Permanent Secretary Eng Simwaba Ministry of Energy that they wanted to finish the CCASP and would ‘call on MECS expertise’. MECS has confirmed willingness to be involved. Zambia has released a Mission 300 National Energy Compact, in which they aim to increase access to clean cooking solutions from 8.9% to 40% by 2030, the GRZ will promote alternative fuels and clean cooking technologies. BURN has signed a landmark agreement with The Trade and Development Bank Group (TDB Group) to distribute 430,000 clean cooking appliances across Mozambique, DRC, and Zambia. The initiative will directly impact over 2.1 million people, prevent ~3 million tonnes of CO₂ emissions, and save households an estimated USD $80–100 million in fuel costs by 2030. Backed by TDB’s ASCENT Platform under Mission 300, the deal combines debt and results-based financing to scale BURN’s biomass and IoT-enabled induction cookstoves.
Malawi: Sustainable Energy for All (SEforALL) and the Government of Malawi hosted a stakeholder consultation focused on the roadmap developed from the Integrated Energy Planning (IEP) in 2024. It included presentations on MECS research and discussion on how to implement the IEP. The MECS lead local partner in Malawi – Kachione - met with the Minister of Energy in Malawi privately and presented their programme of work. Since then, the Minister has visited one of their locations and seems active in discussing how it may go to scale. Kachione has been identified by CLASP as a potential company for MECS to support through the new ‘Venture Building’ output. ATEC raise of USD $15.5m to do 200,000 of ATEC’s IoT (Internet of Things) electric cookstoves over the next three years (see Bangladesh) includes Malawi. ATEC have also been able to access and Article 6.2 carbon finance arrangement between Malawi and Switzerland. This project should enable 85,000 households to transition to ATEC equipment over the next few years. Each HH is likely to save on average $500 over the 6 years compared to their current monthly cooking fuel expenditure.
Burundi: Attendance at COP29 led to interest from Burundi and their Mission 300 roll out of electricity access using eCooking as an anchor demand to improve the net returns on the investments, and inclusion of the project in the Burundi Nationally Determined Contribution (NDC). With follow up, during 2025, MECS has worked with the Article 6 Group, Weza Power (Utility) and the Govt of Burundi as part of their Mission 300 planning to embed eCooking as a demand within the improved access to electricity. They launched a TOR for 5,000 eCooking appliances after MECS technical support. A letter of Intent was sent to GeCCo in Jun 2025. A MECS Readiness Assessment is underway to support integrated energy planning inclusive of eCooking.
Early-stage actions that might lead to announcements in future years
Mozambique: BURN with the support of MECS are discussing a pilot in Mozambique and seeking to access funds from the BRILHO programme, an FCDO Mozambique-funded Ayrton Demonstrator programme. Mozambique is also part of the BURN TDB Group deal cited above in the Zambia section.
Democratic Republic of Congo: The activities with USAID have ended, but Gridworks through their Moyi Power utility in DRC aim to supply solar-powered electricity to households and businesses via metro grids in up to 100 cities in northern DRC, initially with three pilot cities with a current combined population of 700,000. Stimulation of demand for electricity is a critical requirement and eCooking is one of the key approaches. MECS has supported with analysis of cooking loads. A similar initiative has now started in Burundi led by Anzana Electric Group, with MECS providing technical advice. DRC is also part of the BURN TDB Group deal cited above in the Zambia section.
Fiji: In collaboration with SEforALL, UNESCAP, ESMAP and MECS, the ADB propose to support the Government of Fiji's objective of implementing clean cooking solutions in institutional settings. ADB plans to implement eCooking solutions in a university dormitory in Fiji as a prelude to a wider eCooking programme.
## Annex 4 – Outcome KPI 2. International organisations that adopt MECS principles and indicators (as evidenced by their key documents including MECS principles, tracking and reporting arrangements)

African Energy Commission (AFREC): A significant amount of effort has gone into drafting a major new publication on clean cooking in Africa titled “Sustainable Scaling: Meeting the Clean Cooking Challenge in Africa”. The report was developed by MECS and AFREC to support the design of the African Union (AU)’s African Clean Cooking programme called for by the African Ministers responsible for Transport and Energy. The intent is to help establish a baseline and track progress on clean cooking in the continent; disseminate information on the status of clean cooking across Africa; support the development of a properly informed and targeted continental clean cooking strategy; and the establishment of an AU-led Africa Clean Cooking Facility to provide technical and financial support to AU Member States in their nationally determined transition efforts. The report was formally launched in 2024 by the AU in the Africa Pavilion during COP29.
G20 Brazil Presidency MECS (working through ESMAP and LU) supported in development of the roadmap for clean cooking. At the IEA led Summit for Clean Cooking in Africa, Brazil committed to building on this momentum through its G20 and Conference of the Parties (COP) 30 presidencies, prioritising clean cooking for the G20’s Energy Transition Sherpa Track. During the third meeting of the Energy Transition Working Group, the G20 presidency requested the support of the IEA, Sustainable Energy for All (SEforALL), and World Bank’s Energy Sector Management Assistance Program (WB-ESMAP) in preparing recommendations and co-organizing events related to the clean cooking challenge.), and World Bank’s Energy Sector Management Assistance Program (WB-ESMAP) in preparing recommendations and co-organizing events related to the clean cooking challenge.
Sustainable Energy for All (SEforALL): In early 2022, announced an Integrated Energy Planning Tool (IPET) and published its first analysis for Nigeria that covers both electricity and cooking in the same models. In June 2022, the organisation presented to the G20 Energy Transition Working Group a clear call for integration of clean cooking into policy planning. IEPTs in Nigeria, Rwanda, Madagascar and Malawi have all revealed strong potential for the adoption of eCooking and SEforALL continue to be a strong advocate.
Global Electric Cooking Coalition (GeCCo): Launched at COP28 in Dubai, this initiative is expected to lead to more international organisations adopting MECS principles and indicators in the coming years. Launched by MECS, the Global Energy Alliance for People and Planet (GEAPP), SEforAll and EnDev, GeCCo seeks to catalyse the transition to eCooking for at least 10% of the populations in over 10 countries by 2030. It will do this by uniting diverse stakeholders to establish the in-country conditions for a transformative shift in cooking practices, and by championing eCooking as a sustainable and modern alternative – with MECS acting as the knowledge partner and as its Secretariat for at least the first year. Beyond the core organisations, the GeCCo engagement group now numbers 36 international organisations and the country governments engaged with GeCCo numbers 8.
Energising Development (EnDev): Have embraced a strong and mostly exclusive focus on eCooking in their clean cooking programming. This marks an important and MECS-informed shift for this major actor on the clean cooking, which historically focussed on improved firewood and charcoal stoves. Another GeCCo anchor partner, MECS began working closely with EnDev in 2019 and produced a series of important market development reports in 2020. Their Global Electric Cooking Accelerator (GeCA) is an innovative channel for supporting the scaling of eCooking adoption which surpassed midline targets. They launched six new pilots through the Innovation Window and expanded work on carbon market mechanisms, supporting sustainable business models while unlocking new financing avenues.
Gold Standard: which operates the Voluntary Carbon Standard, continues to implement the metered methodology for verification of carbon savings through digital technology. This has been a strong influence on the carbon offset industry, as other methods have come under question and have been exposed as subject to abuse. The MECS-funded methodology for metered & measured energy cooking devices (MMMECD) issued in 2021 has been vital to the future possibilities for carbon finance. Phase 1 work on Black Carbon has been launched, which utilises the MMMECD to calculate the black carbon savings.
Verra: which operates in the Voluntary Carbon Standard market, has last year produced a new draft “Methodology for Improved Cookstoves and Other Distributed Thermal Energy Generation Units” which allows for a very similar Digital Measurement, Reporting, and Verification (DMRV) approach to that of Gold Standard. The metered methodology introduced by MECS is becoming the standard by which other methods are judged. The previous self-certified method which has been widely criticised in both academic literature and the international press. The increased confidence in the accuracy of the method means prices can be as high as $40/tonne compared to the current value of $4 to $8/tonne for non-metered projects.
Clean Cooking Association (CCA) led the Clean Cooking and Climate Consortium (4C) to undertake a sector-wide effort to develop a new methodology for crediting emissions reductions from cookstove projects. The Comprehensive Lowered Emissions Assessment and Reporting (CLEAR) Methodology for Cooking Energy Transitions. UNFCCC released the CLEAR methodology for public comment in June. MECS has been an integral member of the working committee, and CLEAR leans heavily on the MMMECD, but also seeks to revive a self-certification route for improved cookstoves.
Solar-Electric Cooking Partnership (SOLCO): MECS supported the development of SOLCO launched at the Africa Climate Summit in 2023. SOLCO is a platform led by Last Mile Climate that seeks to transition 250,000 households in refugee-hosting countries in Africa to solar-electric cooking by 2027, and leverage at least $100 million in financing. SOLCO representative in Rwanda is situated within the EnDev team office one day a week to support close alignment with GeCCo-SOLCO in country activities.
World Food Programme (WFP): in 2022 published the Clean and Modern Energy for Cooking - A Path to Food Security and Sustainable Development report, highlighting different cooking techniques and identifying how WFP and partners can promote the use of energy-efficient stoves to support families to boost their food security and increasingly transition to greener and energy-efficient cooking systems. In 2024, WFP linked MECS to the School Meals Coalition, and authored section 2.2 of their white paper on School Meals and Food Systems: Rethinking the Consequences for Climate, Environment, Biodiversity, and Food Sovereignty. WFP is currently working with MECS on the schools workstream under the Tanzania demonstrator, as well as on 11 additional studies, led by WFP country offices looking at eCooking in schools.
International Energy Agency (IEA): MECS language and data continues to inform IEA outputs, including the most recent IEA Universal Clean Cooking in Africa Report 2025. . MECS was invited to attend the IEA’s Clean Cooking Summit in Africa in Paris in May 2024. In the run up to the Summit, MECS provided detailed drafting input to the set of ‘Chair’s summaries’ that were developed as the key outcomes of the event. The IEA’s key background report A Vision for Clean Cooking Access for All 2023 also included reference to MECS research, and the IEA are currently discussing with MECS how to better include its research and evidence into their data analysis and modelling.
International Renewable Energy Agency (IRENA): published a major report in 2023 with a significant analysis of the possibilities of eCooking - Renewables-Based Electric Cooking: Climate Commitments and Finance. A broader analysis picking up on non-electric renewable possibilities was also published - Advancing Renewables-Based Clean Cooking Solutions: Key Messages and Outcomes. The 2023 MECS research paper The Emergence of Large-Scale Bioethanol Utilities: Accelerating Energy Transitions for Cooking published in the Energies journal is cited by IRENA in their policy influencing documents and was also picked up by UNIDO.
## Annex 5 – Summary of MECS learning events and training (Output KPI 1.3)

Loughborough University

Country	Event/training title	Key participants	Month/Year	Short description
Tanzania	Article 6 Readiness workshop	National Carbon Monitoring Centre, Tanzania	August 2025	Information, exercise and discussion on the use of Article 6 mechanism
UK	Tanzania Clean Cooking Strategy Retreat	Multiple Stakeholders including: The Tanzanian Ministry of Energy, Ministry of Finance, TANESCO, AfCEN, CIFF, MECS, BURN, Lightrock	August 2025	Hosted by the Government of Tanzania, the African Climate and Energy Nexus (AfCEN), and the Children’s Investment Fund Foundation, the Retreat brough together government and non-government stakeholder to focus on strategies and the pathway to achieve Tanzania’s clean cooking goal of 80% access by 2034
Global	The Research Consortium for School Health and Nutrition webinar 'Introducing the New Planetary Health Communities of Practice’	A diverse group from around the world.	June 2025	MECS Kenya joined a diverse panel within the Research Consortium for School Health and Nutrition, “Introducing the New Planetary Health Communities of Practice.” He delivered a presentation on “Advancing Clean Cooking in Schools: Learnings from the Kenyan Experience” and Its Integration with School Feeding Programmes and Nutrition.
SSA	eCooking on mini-grids webinar series	40 – 60 attendees per session.	June-July 2025	3-part Webinar series on eCooking in off-grid settings, covering eCooking, mini-grid contexts, and financing.
Tanzania	Co-Creation Workshop on Data-Driven Utility Management for Demand Response in Dar es Salam	Utilities & regulators from Tanzania, Kenya, Uganda, Malawi & Ethiopia	May 2025	Presentation: Overview of utility-enabled eCooking & summary of country-level market assessments. / Co-creation session: designing pilot projects to address systemic barriers to scaling utility-enabled eCooking in each country. See Trip Report and Story of Change below for further details.
User insights	Working with CCA User insight team on prep of a report	CCA and participants using multi fuel stacking	May 2025	Gathering qualitative data on household use and insights into multi fuel stacking, in cooperation with CCA for industry insight.
India	eCooking exhibition	Government agencies, Academia and private companies	April 2025	The Clean cooking technology showcase at NCEEITET 2025 on 22nd-23rd April at the 10th National Conference & Exhibition at GCEC Chalk Bhawan, Jammu.
Kenya	PUE research survey training and orientation.	Burn Mftg & enumerators/researchers	March 2025	Training for 6-10 enumerators to visit 60 business in Kenya and Tanzania to conduct a survey to shed light on cooking practices, fuels and other details.
Multiple	MP awareness raising on eCooking	35 MPs from Africa and southeast Asia	February 2025	Climate parliament as described above – 2-day conference to raise awareness across the issues of: carbon financing, institutional cooking, eCooking tariffs, SOLCO, cooking demo
Nepal	AEPC International Clean Energy Day Summit 2025	Government of Nepal, wide range of the key energy and clean cooking sector actors in Nepal	February 2025	Range of activities, including Practical Action Consulting (PAC) and People, Energy & Environment Development Association (PEEDA) showcasing the impact of their MECS funded research towards scaling electric cooking in Nepal.
Multiple	MECS Gender Framework	Global – web resources	January 2025	Three short videos for MECS Gender Framework Guidance Resources
Uganda	Energy and Kitchen Audits for Schools in Uganda at Hotel JFrigh, Makere, Kampala.	Circodu & enumerators/researchers	January 2025	Training for ~30 enumerators and researchers who would visit 180 schools across Uganda to gather data into school energy and cooking practices to inform better decision-making for deployment of eCooking equipment in school.
Global	Institutional COP (x2)	GPA, UNITAR, WFP, UNEP, SE4All	November 2024	Community of Practice for institutional cooking
Tanzania	1 day training on business modelling for eCooking supply chain	Small scale businesses in Tanzania	November 2024	Training on sustainable business models for eCooking supply chain, virtual and in person (Dar es Salaam)
United Kingdom	Africa Summit: Resilience and Adaptability for Climate Change - Lessons from Sub-Sahara Africa (SSA)	IAS Visiting Fellows, Academics, Policymakers, Researchers, Students, Public Sector Leaders.	October 2024	The discussion examined SSA’s innovative approaches to climate challenges and explored opportunities for supporting the UK’s net-zero targets through sustainable, cross-continental collaboration.
Kenya	The 2024 Clean Cooking Week	Diverse stakeholders from across the country, drawn from government, private sector, development organizations, and research.	October 2024	Clean Cooking Week 2024, hosted by CCAK and the Ministry of Energy and Petroleum in Kajiado County, marked the launch of three key national strategies to accelerate Kenya’s transition to clean cooking solutions. The event provided a platform for stakeholders to display various clean and modern cooking solutions, emphasizing the importance of sustainable energy transitions.
SAARC Region (e.g. Bangladesh, Bhutan, India, Maldives, Nepal,	Webinar on “Modern Clean Cooking in South Asia” (SAARC Secretariat)	SAARC Secretariat representatives; National energy ministry officials; Clean cooking and energy access NGOs; MECS partners; Academia and research institutes	October 2024	MECS presented on scaling solutions in South Asia, key opportunities and challenges, together with an overview of the MECS programme and its holistic approach to address policy, social and economic aspects.
Kenya	Repair and Maintenance of eCooking Appliances Training	Over 18 eCooking champions and Last Mile Entrepreneurs	September 2024	Inaugural training on repair and maintenance of electric pressure cookers (EPC), at the Kisumu eCooking Hub, supported by MECS and EnDev, the training aimed to enhance local capacity in EPC maintenance.
Uganda	Technician training	30 technicians (9 women)	July 2024	In-person EPC repair training course, developed and delivered by CREEC under the Umeme pilot project. 343 Expressions of Interest were received.
Nepal	Training in EPC repair and sales	44 members from Women's Awareness Centre Nepal (WACN)	June 2024	WACN together with a local vocational training institute trained the members on the repair of a range of common eCooking appliances (EPCs, induction stoves, infra-red stoves, rice cookers, kettles, water heaters, and mixers)
India	Training of Trainer (ToT) Programme on Clean Cookstove Sales	Clean cook stoves stakeholders from 20 different organisations- including manufacturers, consultants, supply chain platforms, etc	June 2024	Training of Trainer (ToT) Programme on Clean Cookstove Sales and Maintenance Executive, aligned with the National Skill Qualification Framework (NSQF).
Nepal	Voluntary Carbon Market (VCM) Network Meeting	VCM Network members (19)	June 2024	Discussion on the need for amended carbon market regulations in Nepal based on the analysis of proposed Climate Change Authority Act and Nepal's CDM experience in developing clean cooking activities.
Global	In Person and Online Training: Sparking the Change: Clean Cooking at the Coeur of Energy Access & Clean Transition	The forum is joined by all World Bank staff from the Energy and Extractives Global Practices as well as external audiences by invitation.	May 2024	This event session at the EEX Forum focused on incorporating clean cooking into energy access planning at national, regional, and global levels. The discussion covered strategies, National Determined Contributions (NDCs) goals, and subsidy policies, exploring ways to unlock the socio-economic transformative impact of the energy transition. MECS’ session focused on why it is imperative to incorporate cooking into the electricity regulatory and policy framework and how this integration can be achieved.
Global	Webinar: Technical challenges of Digital Monitoring, Reporting and Verification (dMRV) in Modern Energy Cooking	Carbon credit project developers (187)	March 2024	To explain the technical needs and available resources related to the Gold Standard Methodology for Metered and Measured Energy Cooking Devices and similar standards.
Global	Webinar: Meeting the challenges of accessing carbon finance for modern energy cooking projects	Carbon credit project developers (295)	March 2024	To explain the issues that developers of modern energy cooking projects should be aware of when seeking carbon finance through the voluntary carbon market.
Kenya	Piloting Electric Pressure Cookers in Kalobeyei Integrated Settlement	Six participants from the eCooking Community of Practice, representing government, NGOs, academia, research institutions, entrepreneurs, financial institutions, development partners, and private sector players in the clean cooking and electricity sectors.	November 2023	Marion Ambani and Maryanne Wanjiru from SNV presented findings and lessons from the PEPCI-K project. They discussed how these insights could influence the expansion of eCooking initiatives in the Kakuma and Kalobeyei integrated settlement. Some MECS in-country partners from India also attended this event.
Global	Webinar: World Cooking Index: A Global Analysis of Cooking Around the World	Health and nutrition professionals, development academics (152)	November 2023	Presented findings from Cookpad analysis and paper on links between choice of cooking fuels and wellbeing.
India	Training and Demonstrations of eCooking Technologies	130 representatives of Panchyats of Kerala who were a part of Navekeralam Initiative	October 2023	Training and demonstration organised in Kerala under the Net Zero Initiative. Live demonstrations of eCooking technologies were, conducted along with a technology showcase.
Global	Recipe for Success: Acumen report, key findings and conclusions	Cooking entrepreneurs, development finance institutions, and institutional funders (105)	October 2023	Following the publication of “Recipe for Success: Lessons from Acumen’s Cookstove Investments”, the panel discussed the challenges faced by cooking companies and the factors that enabled companies to sell a quality product at an affordable price. It also described some of the requirements that funders may have in making investments.
Nepal	Training in EPC and Induction Stove repair	Four local repair technicians in Mahankal Rural Municipality.	September 2023	PEEDA together with a local vocational training institute trained the technicians on how to repair the main issues affecting EPCs and induction stoves (the main issues were identified by the repair inventory developed by PEEDA earlier in the study).
Global	What happens when your cooker no longer works: a dive into the afterlife of domestic electric items	Clean cooking community (105)	August 2023	During the Webinar, consultants at CLASP, Doko Recyclers, Rural Senses, and Qualiquant, presented findings based on their reports on repair and end of life (EoL) of electric cooking devices and domestic appliances.
Global	Moving the Needle on Clean Cooking: The Future of Carbon Finance	Carbon credit project developers (184)	May 2023	Following MECS’ publication of the Role of Voluntary Carbon Markets in Clean Cooking this webinar presented the findings of the report. It was followed by a panel discussion where representatives of several leading groups, representing diverse perspectives including project development, carbon certification and research, offered their views on recent developments.

ESMAP

Title	Event type	Date	Host Organisation	ESMAP Role
G20 - Brazil G20 Presidency’s Clean Cooking Roadmap	External Event	November 22-23, 2025	Brazil G20 Presidency	Speaker
Energy Now SDG 7 Action Forum in New York - The Global Clean Cooking Roadmap: Advances and Challenges	External Event	September 24-25, 2025	UN-Energy	Speaker
COP 29 - AFREC’s Meeting the Clean Cooking Challenge in Africa	External Event	November 11-22, 2024	UNFCCC	Speaker
Asia Clean Energy Forum (ACEF) 2024: Deep-dive Workshop on Asia Clean Energy Forum Electrifying Cooking - Innovative Approaches and Business Models for Asia and the Pacific	External Event	June 5, 2024	Asian Development Bank	Speaker
G20 Energy Transition Working Group (ETWG): side event on “Advancing Just and Inclusive Energy Transitions”	External Event	May 27, 2024	G20 ETWG	Speaker
G20 Energy Transition Working Group (ETWG): High-level dialogue “Principles for just and inclusive energy transitions”	External Event	May 27, 2024	G20 ETWG	Speaker
EEX Forum 2024: Sparking the Change: Clean Cooking at the Coeur of Energy Access & Clean Transition[6]	Internal Event	May 21, 2024	World Bank/ESMAP	Host
IEA Summit on Clean Cooking in Africa	External Event	May 14, 2024	IEA, CCA, Tanzania	Speaker
Spring Meeting Knowledge Café: Clean Cooking at the heart of energy access	Internal Event	April 18, 2024	World Bank/ESMAP	Host
Transforming Energy Access Forum 2024 - MECS workshop: “Modern Cooking: integrating and Innovating”	External Event	March 14, 2024	MECS, World Bank/ESMAP	Co-host
The International Vienna Energy and Climate Forum (IVECF): Catalyzing Sustainable Development Goals through Clean Cooking Solutions	External Event	November 2-3, 2023	UNIDO, the Austrian Government and the International Institute for Applied Systems Analysis	Speaker
UNGA 78 – SDG Mobilization Day Side Event: “Opportunities & Challenges for Implementing a Global Roadmap for a Just and Inclusive Clean Cooking Energy Transition”	External Event	September 17, 2023	World Bank/ESMAP, WHO, UN Energy	Co-host
[6] This event was also reported by Loughborough University, so it has not been counted towards the result of KPI 1.3.

## Annex 6 – MECS Innovation Calls

Status	Challenge call	Objective	Launch year	Funding awarded	Projects supported	Innovations stimulated
Live	Standalone or Rooftop Solar Systems Inclusion of eCooking / (STARSS)	To explore the current possibilities for eCooking on standalone and off-grid systems (e.g. heat batteries, solar home systems).	2024	£689,600	11 projects	eCooking Systems for institutions (schools and churches), mesh-grid powered e-cooking solutions testing a results-based financing system that credits customers with cooker use.
Live	Sparking the Cooking Supply Chain (S2C)	To strengthen sustainable supply chains for electric cooking appliances.	2022	£2,701,817	18 projects across 2 phases	End to end supply chain, increasing affordability with local financial institutions, customer awareness and onboarding
Live	Cooking Support on Mini-Grids (COSMO)	To strengthen the utilisation of mini-grids for eCooking (targeted at mini-grid developers specifically, who were about to implement or adapt a grid).	2022	£786,983	11 projects across 2 phases	Sustainable electric cooking, micro hydro power, domestic and commercial customers, solar-home-systems, smart meters with automated energy management, EPCs, solar hybrid mini-grid, mini grids
Closed	Energy For Access – Enabling Technologies Call (LEIA 2)	To develop enabling technologies for products and services in weak grid and off-grid areas.	2020	£229,516	6 projects (4 were terminated due to funding cuts)	Hybrid AC/DC EPC, ‘earn & grow’ solar cooking business model, AC cooker on DC mesh grid networks.
Closed	Low Energy Inclusive Appliances (LEIA 1)	To accelerate the affordability, availability, efficiency and performance of eCooking appliances.	2019	£700,299	6 projects	EPCs on mini grids, solar based eCooking, PAYGO systems, Solar pressure cookers.
Closed	Technology Research for International Development (TRIID)	To fund early-stage research projects in support of innovative ideas or concepts that facilitate a transition to modern energy cooking services.	2019	£605,086	22 projects	DC EPCs, LPG tag and trace, recycled batteries, salt batteries, PAYGO for eCooking appliances.
Closed	Electric Cooking Outreach (ECO)	To look at the potential for scaling up the outreach of electric cooking through community scale pilot studies and market assessments.	2019	£782,792	14 projects	Community scale pilots of EPCs and market assessments.