## Logframe
Logframe updated: October 2025
PROJECT TITLE | Modern energy cooking services (MECS)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Clean cooking and clean energy transition accelerated in developing countries in Sub-Saharan Africa, South and Southeast Asia and the Indo-Pacific | People without clean cooking access (SDG7.1.2) | Planned | 2.4 billion (2020) | 2.3 billion (2021) | 2 billion (2022) | 1.8 billion (2023) | 1.5 billion (2024) | 1.4 billion (2025) | 1.3 billion (2026) | 1.1 billion (2027) | 900,000 (2028)
|  | Achieved | 2.4 billion (2020) | 2.3 billion (2021) | 2.1 billion (2022) | 2.1 billion (2023)
| Note: there is a 2-year lag in SDG7 reporting. | Source
SDG 7.1 Global Tracking Framework reports/MTF reports, Global Alliance for Clean Cookstoves Annual Reports
OUTCOME | Outcome Indicator 1.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumptions
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
A market ready range of technology and business model innovations that lead to improved choice of affordable and reliable modern energy cooking services for consumers | Countries that actively implement policies, evidence and programmes to increase access to modern energy cooking services (MECS) (cumulative) | Planned | 2 | 3 | 6 | 8 | 9 | 10 | 12 | 13 | 13 | An increasing number of countries wants to and continues to engage with modern energy cooking and implement policies and programmes in addition to or instead of those focused on LPG (KPI 1.1) .
|  | Achieved | 2 (India, Uganda) | 4 (India, Uganda, Tanzania, Kenya) | 7 (India, Uganda, Tanzania, Kenya, Nepal, Bhutan, Rwanda) | 8 (India, Uganda, Tanzania, Kenya, Nepal, Bhutan, Rwanda, Sierra Leone)
|  | Source | [9 empty] | *Announced plans can be by government, sizeable NGO programme or sizeable private sector initative (KPI 1.2).
MECS progress reports, evidenced by country plans (Government, Donor or Large NGO)
| Outcome Indicator 1.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | International organisations are willing to incorporate MECS research and evidence into their high level principles and indicators (KPI 2).
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Countries that have announced plans to increase access to MECS (including policies, evidence and programmes)' (cumulative) | Planned | 2 | 5 | 6 | 12 | 14 | 16 | 18 | 20 | 20 | The ESMAP indicator wording is Number of people provided with access to clean cooking - so will include tier 3 and 4 stoves (KPI 3).
|  | Achieved | 2 (India, Uganda) | 7 (India, Uganda, Tanzania, Kenya, Nepal, Bangladesh, Cambodia) | 13 (India, Uganda, Tanzania, Kenya, Nepal, Bhutan, Rwanda, Bangladesh, Cambodia, Ghana, Zambia, Malawi, Sierra Leone) | 16 (India, Uganda, Tanzania, Kenya, Nepal, Bhutan, Rwanda, Sierra Leone, Bangladesh, Cambodia, Ghana, Zambia, Malawi, Nigeria, Lao PDR, Burundi)
|  | Source | [9 empty] | The programme is able to continue mobilising public and private sector funds (KPI4)
MECS progress reports, evidenced by country plans (Government, Donor or Large NGO)
| Outcome Indicator 2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Basis of the calculations for CO2 emissions reduced (KPI 5):
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| International organisations that adopt MECS principles and indicators (as evidenced by their key documents including MECS principles, tracking and reporting arrangements) (cumulative) | Planned | 0 | 2 | 4 | 12 | 13 | 14 | 15 | 16 | 16 | • That allows calculation of a baseline emission factor for each fuel, using standard data for fuels
|  | Achieved | 1 (IEA) | 4 (IEA, SEforAll, IPCC, WFP) | 10 (AFREC, SEforALL, GeCCo, EnDev, Gold Standard, Verra, SOLCO, WfP, IEA, IRENA) | 12 (CCAC, G20,AFREC, SEforALL, GeCCo, EnDev, Gold Standard, Verra, SOLCO, WfP, IEA, IRENA) | [5 empty] | • Assumed electricity use of each eCook type in actual use cooking
|  | Source | [9 empty] | • That allows calculation of eCook emission factor for each eCook type, using standard national power system emission factors
|  | SDG 7.1 Global Tracking Framework reports/MTF reports, document review and stakeholder consultations | [9 empty] | • The baseline shares are used to allow representation of two types used on average by households
| Outcome Indicator 3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | • Those shares are combined with the emission factors to give emissions per household for baseline
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030) | • Only one eCook type per entry…if a project has multiple eCook types, enter as separate rows
| People with improved clean energy access in developing countries due to more efficient cookstoves and clean electricity (cumulative) | Planned | 2158676 | 2426868 | 3500000 | 4500000 | 5500000 | 5750000 | 6000000 | 6250000 | 6500000 | • The energy ratios are used to calculate how much baseline fuel use is avoided by eCooking
|  | Achieved (LU) | 636487 | 703294 | 1994975 | 2966998 | [5 empty] | • And finally the avoided baseline emissions – the eCook emissions give the emissions reduction
|  | Achieved (LU - Tanzania demo) | - | - | - | 200
|  | Achieved (LU - Uganda demo) | - | - | - | - | [5 empty] | Proportion of women in senior and middle management positions will have to be based on partner projects initially with a view to seeing if the figures can be found within larger data sets over time (KPI7).
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | 1723574 | 1787574 | 1787574 | 1787574
|  | Achieved (total) | 2360061 | 2490868 | 3782549 | 4754773 | - | - | - | - | -
Source
MECS annual results returns (following ICF methodology)
| Outcome Indicator 4.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Public sector funding mobilised into clean cooking and clean energy RD&D (cumulative) | Planned | 139550306 | 187904079 | 200000000 | 270000000 | 400000000 | 425000000 | 450000000 | 475000000 | 500000000
|  | Achieved (LU) | 45799555 | 47358756 | 56037089 | 66300748
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | 93750752 | 140545323 | 156208503 | 156208503
|  | Achieved | 139550306 | 187904079 | 212245592 | 222509251 | £- | £- | £- | £- | £-
Source
MECS annual results returns (following ICF methodology)
| Outcome Indicator 4.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Private sector funding mobilised into clean cooking and clean energy RD&D (cumulative) | Planned | 101835374 | 129121679 | 160000000 | 230000000 | 270000000 | 290000000 | 310000000 | 330000000 | 350000000
|  | Achieved (LU) | 25004528 | 26859000 | 61030446 | 86226446
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | 76830846 | 102262679 | 126390356 | 126390356
|  | Achieved | 101835374 | 129121679 | 187420802 | 212616802 | £- | £- | £- | £- | £-
Source
MECS annual results returns (following ICF methodology)
| Outcome Indicator 5 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| CO2 emissions reduced as a result of MECS stimulated innovations and research ((t/CO2) (cumulative) | Planned | - | - | - | 650000 | 3500000 | 4500000 | 5500000 | 6000000 | 6000000
|  | Achieved (LU) | - | - | - | 2536192
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | - | - | - | -
|  | Achieved | £- | £- | £- | 2536192 | £- | £- | £- | £- | £-
Source
MECS annual results returns (following ICF methodology)
| Outcome Indicator 6 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Green jobs created and supported in the clean cooking sector (direct only) (cumulative) | Planned (LU) | 373 | 752 | 800 | 850 | 1400 | 1500 | 1600 | 1700 | 1800
|  | Planned (CLASP) | - | - | - | - | 5 | 15 | 25 | 50 | 100
|  | Planned (Total) | 373 | 752 | 800 | 850 | 1405 | 1515 | 1625 | 1750 | 1900
|  | Achieved (LU) - Male | - | 235 | 248 | 547
|  | Achived (LU) - Female | - | 342 | 395 | 619
|  | Achived (LU) - Unknown | 373 | 175 | 160 | 159
|  | Achieved (CLASP) - Male | - | - | - | -
|  | Achieved (CLASP) - Female | - | - | - | -
|  | Achieved (CLASP) - Unknown | - | - | - | -
|  | Achieved (Total) | 373 | 752 | 803 | 1325 | - | - | - | - | -
Source
MECS annual results returns
| Outcome Indicator 7 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Proportion of women in senior and midde management positions in the clean cooking sector (cumulative) | Planned | - | - | - | - | 42% | 44% | 46% | 48% | 50%
|  | Achieved | - | - | - | 39.5%
Source
MECS annual results returns
INPUTS (£) | FCDO (£)
Up to £99m, with £64m committed by FCDO by September 2025
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumptions
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Foundational research and training to develop data and capabilities on modern energy cooking services | MECS research published (incl. number peer reviewed) (cumulative) | Planned (LU) | 213 | 283 | 330 | 360 | 410 | 450 | 480 | 500 | 507 | Research outputs require further streamlining or financial support to adapt to specific country contexts; policies and environments. Research outputs may be written products as in traditional published papers or working papers, but may also include webinars or presentations at key events as long as these are recorded and available post event. By researching business and institutional use, vulnerable people such as children (e.g. at schools) and the displaced, will be enabled to transition. By researching the drivers and barriers further in a changing global context, the knowledge contributes to evidence based decision making. The use of the new tools will encourage the use of modern energy for clean cooking not just perpetuating the use of biomass.
|  | Planned (CLASP) | - | - | - | - | 2 | 3 | 4 | 5 | 6
|  | Planned (ESMAP) | 15 | 20 | 23 | 28 | 30 | 32 | 34 | 36 | 37
|  | Planned (total) | 228 | 303 | 353 | 388 | 442 | 485 | 518 | 541 | 550
|  | Achieved (LU) | 213 | 283 | 332 | 398
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | 15 | 20 | 22 | 23
|  | Achieved (total) | 228 (all peer-reviewed) | 303 (all peer-reviewed) | 354 (all peer-reviewed) | 421 (all peer-reviewed)
MECS website, MECS research output tracker, ESMAP website
| Output Indicator 1.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Online views of MECS publications (including views of MECS website publications page, newsletters, and special issues published on the 'Energies' open access journal, views of relevant publications on CLASP website and newsletters, and reach thereof on social pages, and also downloads of ESMAP clean cooking research reports) (cumulative) | Planned (LU) | 24338 | 30000 | 70000 | 120000 | 150000 | 180000 | 210000 | 240000 | 250000
|  | Planned (CLASP) | - | - | - | - | 10000 | 30000 | 50000 | 70000 | 90000
|  | Planned (ESMAP) | 31000 | 55000 | 80000 | 100000 | 120000 | 140000 | 160000 | 180000 | 200000
|  | Planned (total) | 55338 | 85000 | 150000 | 220000 | 280000 | 350000 | 420000 | 490000 | 540000
|  | Achieved (LU) | MECS page: 3,328 | MECS page: 8,689 | MECS page:12,196 | MECS page:18,036
|  |  | Newsletters: 510 | Newsletters: 650 | Newsletters: 755 | Newsletters: 841
|  |  | Energies: 24,338 | Energies: 53,615 | Energies: 84,646 | Energies: 112,057
|  |  | Total: 28,176 | Total: 62,954 | Total: 97,597 | Total: 130,934
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | 30700 | 54696 | 75255 | 84271
|  | Achieved (total) | 58876 | 117650 | 172852 | 215205
MECS website, Newsletter, 'Energies' open access journal, ESMAP website
| Output Indicator 1.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| MECS learning events and training (cumulative) | Planned | - | - | 15 | 30 | 65 | 85 | 105 | 125 | 140
|  | Achieved (LU) | - | - | 14 | 32
|  | Achieved (ESMAP) | - | - | 8 | 11
|  | Achieved (CLASP) |  | - | - | -
|  | Achieved (total) | - | - | 22 | 43 | - | - | - | - | -
MECS research programme progress reports and publications
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
40% | Countries using clean cooking planning tools and load modelling to support eCooking transition (cumulative) | Planned | 0 | 2 | 3 | 6 | 7 | 8 | 9 | 11 | 12
|  | Achieved | 0 | 1 (Rwanda) | 5 (Rwanda, Malawi, Kenya, Namibia, Tanzania) | 6 (Sierra Leone, Rwanda, Malawi, Kenya, Namibia, Tanzania)
RISK RATING
|  | MECS research programme progress reports and publications | [9 empty] | Minor
INPUTS (£) | FCDO (£)
MECS1 (£14.7m), MECS2 (£10m) = £24.7m
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumption
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Technology accelerators tackle key off-track technologies for clean cooking access | MECS innovation challenge calls (cumulative) | Planned | 4 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | That the global trend which is lowering the cost of renewable energy (particularly Solar PV) and energy storage continues. That no major incidence, economic shock or shortages disrupt the global learning rate for the above technologies. Candidate maturing technologies and business models include PAYG enabled energy efficient eCooking appliances, more transparent verification of carbon and results based payments, carbon credits reaching the consumer to mitigate fuels costs, localised manufacture of eCooking appliances, Direct Current systems capable of off-grid cooking, energy efficient appliances being used on mini grids, and raised consumer awareness through digital media. That some of the technical innovations do not reach viable system price points. That global changes in alternative fuel prices and/or system components/inputs make proposed MECS approaches and designs unaffordable.
|  |  |  | (with winners contracted) | (support to existing calls) | (support to existing calls)
|  | Achieved | 6 | 6 | 7 | 7
|  |  | (S2C, COSMO, LEIA1, LEIA2, TRIID, ECO) | (no new calls, but second phase of S2C and COSMO) | (+STARSS, and second phase of S2C and COSMO) | (+STARSS, and second phase of S2C and COSMO)
Source
MECS research programme progress reports and publications
| Output Indicator 2.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Projects supported via challenge calls (cumulative) | Planned | 51 | 69 | 76 | 84 | 95 | 95 | 95 | 95 | 95
|  | Achieved | 51 | 69 | 76 | 88
Source
MECS research program progress report and publications
| Output Indicator 2.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| MECS innovations researched, developed and/or piloted (technologies and business models) (cumulative) | Planned | 70 | 101 | 112 | 135 | 154 | 154 | 154 | 154 | 154
|  | Achieved | 70 | 101 | 128 | 154
Source
MECS research program progress report and publications
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
15% | Case studies developed on technology and business innovations previously funded by MECS that show promise of maturing and market uptake (cumulative) | Planned | 0 | 3 | 3 | 7 | 9 | 15 | 20 | 25 | 25
|  |  |  | (case studies on MECS innovations that show promise of maturing) | (case studies on MECS innovations that show promise of maturing)
|  | Achieved | 0 | 3 | 5 | 7
|  | Source | [9 empty] | RISK RATING
|  | MECS research program progress report and publications | [9 empty] | Moderate
FCDO (£)
MECS1 (£10m), MECS2 (£2.3m) = £12.3m
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumptions
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Venture building R&D support to individual companies, studios and investors to increase manufacture and distribution of clean cooking devices | Businesses supported with R&D to integrate or expanding eCooking device production and sales (cumulative) | Planned | - | - | - | - | 2 | 3 | 3 | 3 | 3 | That the venture studio model for eCooking continues to gain traction as an effective approach for scaling early-stage businesses. That no major economic disruptions, policy changes, or market shocks significantly alter the investment landscape for eCooking ventures. Candidate business models include PAYG-enabled eCooking appliances, carbon-financed eCooking solutions, local assembly and distribution of energy-efficient appliances, integration of eCooking with mini-grids, and direct consumer incentives to drive adoption. That some ventures will not reach commercialization due to challenges in business viability, market demand, or investment readiness.
|  | Achieved (UK businesses) | - | - | -
|  | Achieved (International businesses) | - | - | -
Achieved (Local businesses)
|  | Achieved | - | - | - | - | - | - | - | - | -
Source
Business registration records, production data, partnership agreements, product catalogs, and company self-reports verified through site visits.
| Output Indicator 3.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Businesses securing Series A funding, raising at least $250,000 in external investment, or obtaining commercial loans or blended financing specifically for eCooking expansion (cumulative) | Planned | - | - | - | - | - | 1 | 2 | 2 | 2
|  | Achieved (UK businesses) | - | - | -
Achieved (International businesses)
|  | Achieved (Local businesses) | - | - | -
|  | Achieved | - | - | - | - | - | - | - | - | -
Source
Venture funding announcements, investment agreements, loan approvals, blended financing arrangements, financial disclosures
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
10% | Businesses that achieve positive Earnings Before Interest, Taxes, Depreciation, and Amortization (EBITDA) for at least two consecutive quarters | Planned | - | - | - | - | - | - | 1 | 1 | 1
|  | Achieved (UK businesses) | - | - | -
Achieved (International businesses)
|  | Achieved (Local businesses) | - | - | -
|  | Achieved | - | - | - | - | - | - | - | - | -
|  | Source | [9 empty] | RISK RATING
|  | Audited financial statements, financial reports from venture partners, self-reported data verified through due diligence | [9 empty] | Moderate
INPUTS (£) | FCDO (£)
MECS2 (£1.6m)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumption
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Market shaping to enable uptake of clean cooking solutions | Number of new World Bank Country Climate and Development Reports (CCDR) developed with support from ESMAP that include a clean cooking analysis | Planned | - | - | 3 | 6 | 9 | 11 | 13 | 15 | 17 | On providing countries and programmes with technical advice - the assumption is that countries and programmes running RBF and other carbon finance projects continue to reach out to MECS and ask for technical advice. On GECCO - that the Secretariat is formed and able to maintain momentum across the coalition, particularly if new initiatives arise which may be launched and split attention. Global LEAP - Manufacturers and distributors are willing and able to participate in the Global LEAP Awards, and the competition results will be taken up by program funders, governments, and implementers to inform procurement, performance eligibility criteria, and investment decisions.
|  | Achieved | - | - | 5 | 11
Source
ESMAP progress updates
| Output Indicator 4.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| New clean cooking Results Based Financing (RBF) instruments or Carbon and Climate Finance programmes developed and/or piloted with support from MECS (e.g. design, TA, funding) (including World Bank instruments and programmes) (cumulative) | Planned (LU) | 1 | 2 | 8 | 11 | 12 | 13 | 14 | 15 | 15
|  | Planned (CLASP) | - | - | - | - | 2 | 3 | 4 | 5 | 5
|  | Planned (ESMAP) | - | - | - | 3 | 5 | 7 | 9 | 10 | 11
|  | Planned (total) | 1 | 2 | 8 | 14 | 19 | 23 | 27 | 30 | 31
|  | Achieved (LU) | 1 | 6 | 11 | 11
|  | Achieved (CLASP) | - | - | - | -
|  | Achieved (ESMAP) | - | - | 2 | 3
|  | Achieved (total) | 1 | 6 | 13 | 14 | - | - | - | - | -
Source
MECS research programme progress reports and publications, ESMAP progress updates
| Output Indicator 4.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Countries provided with MECS technical advice for clean cooking scale-up (cumulative) | Planned (LU) | 7 | 11 | 13 | 15 | 17 | 19 | 21 | 23 | 23
|  | Achieved (LU) | 7: 7; 11: 11; 13: 13; 15: 16
| Note: results are reported and assessed individually for each partner, as some countries might be the same. | Planned (CLASP) | - | - | - | - | 2 | 4 | 6 | 7 | 8
Achieved(CLASP) | bar: 7 to 15
|  | Planned (ESMAP) | 15 | 23 | 25 | 30 | 33 | 36 | 38 | 39 | 40
|  | Achieved (ESMAP) | 7: 24; 11: 23; 13: 25; 15: 30
Source
MECS research programme progress reports and publications
| Output Indicator 4.4 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Number of energy-efficient eCooking appliances identified, tested, and recognised through the Global LEAP Awards (cumulative) | Planned | - | - | - | - | 10 | 15 | 20 | 25 | 25
Achieved | bar: 7 to 15
Source
Global LEAP Awards competition records, product testing reports, and certification documents.
| Output Indicator 4.5.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| GeCCo letters of intent (LoIs) received from national representatives confirming they welcome GeCCo support (cumulative) | Planned | - | - | 3 | 6 | 8 | 10 | 12 | 14 | 14
|  | Achieved | 7: -; 11: -; 13: 3; 15: 8 (Nigeria, Laos, Somalia, Sierra Leone, Rwanda, Kenya, Madagascar, Burundi)
Source
Letters of intent
IMPACT WEIGHTING (%) | Output Indicator 4.5.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
20% | GeCCo engagement group meetings held (per year) | Planned | - | - | 3 | 3 | 3 | 3 | 3 | 3 | 1
|  | Achieved | 7: -; 11: -; 13: 2; 15: 4
|  | Source | [9 empty] | RISK RATING
|  | Meeting notes and records of meetings | [9 empty] | Moderate
FCDO (£)
MECS1 (£9m), MECS2 (£4.1m) = £13.1m
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumptions
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Leadership and coordination on clean cooking and MECS M&E | Meetings convened for MECS Advisory Group (every 6 months / 2 per year) (cumulative) | Planned | - | - | 1 | 3 | 5 | 7 | 9 | 11 | 13 | Communication strategies and messaging are joined up and speak with one voice. Programme is able to access high level stakeholder meetings, SDG forums and decision boards. Communication products utilise all effective media sources.
|  | Achieved | 7: -; 11: -; 13: 1; 15: 3
Source
Meeting minutes and MECS progress report
| Output Indicator 5.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Meetings convened for Leadership Group of Ayrton Fund Modern Cooking Challenge (every 6 months / 2 per year) (cumulative) | Planned | - | - | 1 | 3 | 5 | 7 | 9 | 11 | 13
|  | Achieved | 7: -; 11: -; 13: 1; 15: 3
Source
Meeting minutes and MECS progress report
| Output Indicator 5.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Ayrton Modern Cooking Challenge Plan drafted, updated annually and shared with FCDO (once a year) (cumulative) | Planned | - | - | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Achieved | 7: -; 11: -; 13: 1; 15: 2
Source
Ayrton Challenge Plan
| Output Indicator 5.4 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| MECS monthly newsletters published (cumulative) | Planned | - | - | 12 | 24 | 36 | 48 | 60 | 72 | 84
|  | Achieved | 7: -; 11: -; 13: 12; 15: 24
Source
Ayrton Challenge Plan
IMPACT WEIGHTING (%) | Output Indicator 5.5 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (Aug 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
5% | Number of external FCDO reviews conducted of the MECS programme (cumulative) | Planned | - | - | 1 | 1 | 1 | 1 | 1 | 1 | 2
Achieved | bar: 7 to 15
|  | Source | [9 empty] | RISK RATING
|  | MECS research programme progress reports | [9 empty] | Minor
INPUTS (£) | FCDO (£)
MECS1 (£3.7m), MECS2 (£1.5m), Mid-term Review (£0.1m) = £5.3m
OUTPUT 6.1 | Output Indicator 6.1.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumption
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Country demonstrators funded by FCDO Posts to scale-up clean cooking innovations in target countries: | Households provided with affordable efficient electric cooking appliances (cumulative) | Planned | 7: -; 11: -; 13: -; 15: 3000; 17: 8000 | Contracting and procurement processes means a majority of contracts/agreements should be signed in September 2024. Activities will begin from that point. On TANESCO, the assumption is that they are able to receive the appliances in sufficient quantity and without long transport/customs delays to start selling early in the programme. On the number of technicians, the assumption is that this number of technicians can be identified and encouraged to complete the training. On SEforAll the assumption is that activities in the schools will happen in phases, with learning from year 1 supporting activities in year 2.
Tanzania |  | Achieved | 7: -; 11: -; 13: -; 15: 2,727
Source
(additional KPIs in next tab)
| Output Indicator 6.1.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| People reached by nationwide government-stamped advertising campaign to increase awareness and demand for eCooking (cumulative) | Planned | 7: -; 11: -; 13: -; 15: 3000000; 17: 6000000
|  | Achieved | 7: -; 11: -; 13: -; 15: 10000000
Source
MECS progress reports and evidence
| Output Indicator 6.1.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| Technicians trained on repair and maintenance of electric cooking appliances (cumulative) | Planned | 7: -; 11: -; 13: -; 15: 200; 17: 300
|  | Achieved | 7: -; 11: -; 13: -; 15: 321
Source
MECS progress reports and evidence
IMPACT WEIGHTING (%) | Output Indicator 6.1.4 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
5% | Schools supported to transition to clean cooking (via SEforAll and WFP) (cumulative) | Planned | 7: -; 11: -; 13: -; 15: 6; 17: 20
Achieved | bar: 7 to 15
|  | Source | [9 empty] | RISK RATING
|  | MECS progress reports and evidence | [9 empty] | Moderate
FCDO (£)
MECS1 (£3.5m)
OUTPUT 6.2 | Output Indicator 6.2.1 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12 | Assumption
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
Country demonstrators funded by FCDO Posts to scale-up clean cooking innovations in target countries: | eCooking appliances supplied to households and schools through aggregators, local distributors and businesses (cumulative) | Planned | - | - | - | 5000 | 10000 | N/A | N/A | N/A | N/A | Contracting and procurement processes means a majority of contracts/agreements should be signed from September- November 2024. Activities will begin from that point. On SEforAll the assumption is that activities in the schools will happen in phases, with learning from year 1 supporting activities in year 2. On the awareness raising campaign, that NREP (who are entirely responsible for this activity) are able to meet the demands of the workplan, working to a high quality, at speed and scale. On the number of technicians, the assumption is that this number of technicians can be identified and encouraged to complete the training.
Uganda |  | Achieved | - | - | - | 0 |  | N/A | N/A | N/A | N/A
Source
(additional KPIs in next tab) |  | MECS progress reports and evidence
| Output Indicator 6.2.2 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
| People reached by nationwide government-stamped advertising campaign to increase awareness and demand for eCooking (cumulative) | Planned | - | - | - | 4000000 | 9000000 | N/A | N/A | N/A | N/A
|  | Achieved | - | - | - | 20040746 |  | N/A | N/A | N/A | N/A
Source
MECS progress reports and evidence
IMPACT WEIGHTING (%) | Output Indicator 6.2.3 |  | Baseline | Milestone Y5 | Milestone Y6 | Milestone Y7 | Target Y8 | Target Y9 | Target Y10 | Target Y11 | Target Y12
|  |  | (up to Aug 2022) | (Aug 2023) | (Aug 2024) | (Aug 2025) | (March 2026) | (Aug 2027) | (Aug 2028) | (Aug 2029) | (March 2030)
5% | Technicians trained on repair and maintenance of electric cooking appliances (cumulative) | Planned | - | - | - | 300 | 600 | N/A | N/A | N/A | N/A
|  | Achieved | - | - | - | 400 |  | N/A | N/A | N/A | N/A
|  | Source | [9 empty] | RISK RATING
|  | MECS progress reports and evidence | [9 empty] | Moderate
MECS1 (£3.65m)