## Annual Review Template

Title: Sustainable Manufacturing and Environmental Pollution Programme
Programme Value £ (full life): 24.65 million		Review date: July 2025
Programme Code: [AMP ID#] 300124	AMP start date: 21 August 2019	AMP end date: 30 November 2026

Summary of Programme Performance
Year	1	2	3	4	5	6	7
Overall Output Score	A	A	A	A	A+	A	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/31255160.odt
DevTracker Link to Results Framework:	https://iati.fcdo.gov.uk/iati_documents/56330982.xlsx

## A: SUMMARY AND OVERVIEW
The Sustainable Manufacturing and Environmental Pollution (SMEP) Programme, established in 2018, aims to address human health risks associated with a variety of environmental pollutant pathways linked to manufacturing and industrial processes in developing countries. It does this through three core components: (1) research to support practical solutions with a high chance of uptake and impact (market and policy at various levels); (2) developing and testing innovative solutions and (3) identifying and developing suitable supporting (and scalable) business models and policies to adopt the innovative technology-based solution.
The Programme encompasses five portfolios of grant projects covering the Plastics, Organic Waste & Water, Used Lead Acid Batteries, Textiles and Tanneries sectors. These were identified as high contributors to manufacturing pollution through initial scoping studies. To support implementation of the Programme’s Strategic Framework, the Thematic Areas of Water and Oceans (through land-to-sea pollution pathways), and the Circular Bio-economy have been defined as cross-cutting, strategically focused lenses. These areas and the Framework serve to organise and prioritise ongoing and planned activities, helping to sharpen the Programme’s focus and maximise impact across its established workstreams.
The Programme is geographically spread across Sub-Saharan Africa (SSA) and South Asia (SA) – with existing grant projects based in Ghana, Kenya, Ethiopia, Nigeria, South Africa, Uganda, Nepal, Bangladesh, and Pakistan. The Programme is implemented in partnership with the United Nations Trade and Development (UNCTAD) and administered by the Programme Management Agent (PMA). Competitively selected, the PMA comprises a consortium between Pegasys and SouthSouthNorth (SSN). UNCTAD and the PMA work in close coordination across the three programme components and five portfolios of grant projects to help leverage knowledge and learnings from projects to inform local, national and international policy processes.
Summary supporting narrative for the overall score in this review
The programme is scored at A+ for FY2024-25, recognising that a significant majority of milestones have been exceeded for the year in review. The two key thematic areas circular bioeconomy, and water and oceans, have enabled targeted and impactful interventions. UNCTAD have leveraged SMEP projects and learning as case studies in various national and international policy processes. SMEP has also been recognised in the Foreign Secretary’s Kew Garden’s Lecture, noting the positive potential impact of the biodegradable fishing nets on the marine environment. The few shortfalls in milestone achievement are expected to be met in the final year, with various activities underway to support their attainment.

Figure 1: A summary of key achievements for the SMEP Programme during the year under review. The SMEP business maturity matrix levels are in Annex 1, and GESI levels are in Annex 2.
Major lessons and recommendations for the year ahead
Key lessons learned, in order of priority:
- The SMEP Strategic Framework, produced in 2024, has been expanded on to capture Thematic Areas which span across portfolios and sector strategic pathways. This has been useful to frame established workstreams’ prioritisation and continued UNCTAD-PMA alignment.
- Cross-grantee workshops improve collaboration on delivery priorities and project cross-pollination, further catalysing environmental and social benefits. These strengthen SMEP’s role in solution generation and value addition, including better alignment of policy barriers and recommendations under the thematic areas.
- Monitoring, Evaluation, Reporting and Learning (MERL) The MERL process has been refined to good effect, taking lessons from the previous annual review and prior quarterly reporting cycles. The refined system has supported better data analysis, accuracy of reporting and feeds into adaptive management and decision-making.
- The Gender Equality and Social Inclusion (GESI) Framework has been updated and supports SMEP and its grantees in practically embedding GESI considerations throughout the project lifecycle. At the core of this framework are two interlinked components: beneficiary mapping and GESI mainstreaming levels. Together, these provide a methodology for identifying who benefits from project activities and how meaningfully GESI principles are being integrated across different stages and stakeholder groups. This has enabled the programme to more effectively monitor progress, promote accountability and more inclusive practices.
Recommendations for FY 2025-26, in order of priority:
- Continue to prioritise efforts and funding according to the Strategic Framework (PMA, UNCTAD and FCDO throughout SMEP Programme), generating research that is useful and relevant. This includes the systematic application of the framework and its tools, such as the Maturity Matrix (Annex 1) and Portfolio Roadmaps, to identify priority actions for grantees to achieve portfolio and programme level medium- to long-term objectives.
- Further review and update logframe outcome and output indicators (PMA, UNCTAD and FCDO by end of Q2 FY2025-26). This should include reviewing relevant future milestones so that the programme maintains ambition in its remaining lifetime.
- Maintain grantee engagement on GESI mainstreaming, safeguarding and beneficiary reporting through learning workshops (PMA, throughout FY25/26). The PMA will proactively work with grantees to share approaches on inclusion through hosting GESI workshops.
- Revisit, refine and begin actioning exit strategy (PMA, UNCTAD and FCDO, by September 2025). Given SMEP is in its final stage of delivery, close out actions are underway for some projects completing in 2025 and the exit plan will be kept updated to ensure it is fit for purpose. The PMA needs to plan in a timely manner for effective programme close-out.
- Continue to leverage SMEP’s networks and platforms to demonstrate and communicate solution viability (PMA, UNCTAD, throughout FY 2025/26). Different strategies to promote results are already underway and the PMA will continue to oversee the expansion and effective delivery of these projects within the SMEP timeline[1]. Additionally, the PMA will continue to identify opportunities to promote learnings from projects that have already come to an end[2].
  [1] High priority projects include Pakistan Leather Sustainability, Leathertrace, Green Tannery Initiatives, Textiles Wastewater Management, SAFECONOMY, Textile Waste Traceability and Banatex-EA, as well as the Waste to Insect Protein and Fertiliser project and Wastewater treatment in Nairobi.
  [2] Flipflopi Project.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
The Theory of Change (ToC) asserts that environmental and human health challenges associated with manufacturing and plastic pollution can be addressed through technology-based and circular solutions, and associated policy changes. By doing this, SMEP aims to generate knowledge and technical advice for partner governments; create a business case for public and private investment for adoption and replication of solutions, and promote an enabling environment for scaling, which will ultimately lead to reduced manufacturing pollution and associated human health impacts.
The ToC has not been updated from the original business case. There have been selected changes to some logframe indicators at the impact and outcome level to add clarity. Outcome-level adjustment has been to better reflect SMEP’s key channels of influence, and the realities of attribution given the many contributing factors and long decision-making timelines. They also account for the pilot nature of projects and enable clearer tracking of progress in solution, market, and business model maturity. An impact level indicator has been refined to Potential future environmental pollution abatement and associated health benefits by scaled SMEP solutions demonstrated, including through quantification in DALYs. This enhanced pollution emphasis better reflects the pollution abatement directly anchored in each project’s interventions and helps the focus of relevant health and environmental benefit analysis.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The Programme is on track to achieve expected outcomes. All but one outcome indicator (A.1) milestone have been exceeded for the year under review. Outcome A.1 has several activities underway across various decision-making pathways to achieve its milestone in the year ahead. In line with SMEP’s Strategic Framework, the Programme is prioritising interventions and technical assistance along strategic pathways that directly address key challenges and increase the likelihood of achieving tangible outcomes that help shift manufacturing processes towards less harmful environmental and health impacts. As part of this approach, Water and Oceans and Circular Bio-economy are key cross-cutting thematic areas that SMEP is contributing to.
Outcome A: Partner governments have the necessary tools, technical advice, and knowledge to address the problems identified.
Outcome indicator	Milestone (cumulative)	Progress
A.1: Number of decisions relating to policy, regulation or standards, primarily in SMEP target countries informed and/or influenced by SMEP Programme.	8	Underachieved* / Cumulative: 5 / FY 2024-25: 3 / *In addition to the reported count for this FY, significant progress is currently underway for various decision-making pathways, where SMEP is a meaningful player, but is not quite yet sufficient for attribution. So not yet counted until further progress made.
A.2: Number of partner government and agency led initiatives in SMEP target countries tackling pollution from manufacturing, which have been directly informed or influenced by SMEP evidence.	3	Exceeded / Cumulative: 5 / FY 2024-25: 2
Outcome B: Increased production efficiency and profitability of selected manufacturing processes creates the business case for adoption and replication of technological solutions and improved manufacturing processes.
B.1: Testing of technology-based solutions developed by SMEP programme across target countries provides evidence of reduced levels of environmental pollution including plastics, environmental degradation and associated health impacts.	6	Exceeded / Cumulative: sustained pollution reduction in 8 SMEP projects. / FY 2024-25: 8 out of 19 projects (42%) have demonstrated sustained pollution reduction either through pollution repurposing, substitution or treatment.
B.2: Expanding evidence of feasible greenhouse gas (GHG) reduction co-benefits in piloted solutions in SMEP priority sectors.	Additional 40% reduction in GHG emissions is achieved from year previous.	Exceeded / 91% greater reduction than the previous year. / (Cumulatively overall average of 71% reduction in GHG emissions is reported, when compared to initial baseline/no-activity scenario.)
B.3: Percentage (%) of solutions demonstrating pollution mitigation that have also shown potential for long-term sustainability beyond SMEP by progressing at least 1 aggregate level on the maturity matrix across: / Solution viability / Market viability / Business model viability	25% of solutions	Exceeded / 61% of all solutions have progressed at least 1 level from baseline.
Outcome C: Businesses are motivated and enabled to improve manufacturing practices and processes through a mix of incentives, technology-based solutions and business models.
C.1: Number of businesses in SMEP target countries, which adopt solutions or evidence developed by SMEP programme and/or which decide to form partnerships with SMEP and/or local governments to tackle the issue of pollution from manufacturing.	7	Exceeded / Cumulative: 11 / FY2024-25: 8

Notable examples of how SMEP is delivering against the Programme’s outcomes:
- Evidence generated by SMEP is playing a leading role in promoting non-plastic substitutes, alternatives, circular design, and trade transparency in the International Negotiating Committee (INC) on Plastics global process that is developing an Internationally Legally Binding Instrument (ILBI) to address plastic pollution. Without SMEP’s involvement, certain provisions within the ILBI would likely not have been included (for example provisions related to trade transparency and traceability of plastics and substitutes; and related to circular product and packaging design).
- Led by Kenya National Cleaner Production Centre (KNCPC), the Wastewater Treatment in Nairobi project’s pilot is promoting awareness for industry on the benefits of resource efficiency and cleaner production (RECP) and water treatment technologies. The pilot is developing financing models and providing research of technical solutions, laying the foundation for potential scaling. Importantly, the pilot has had engagement from the Nairobi Rivers Commission (NRC) and Ministry of Industry, Trade and Investment, enhancing prospects of subsequent application. The project has advanced women’s empowerment by encouraging each participating industry to nominate at least one woman for RECP trainings, resulting in near gender parity among participants. Further, a code of conduct and reporting platform were developed with partners to address employment, sexual harassment, and health and safety risks.
- The Textile Wastewater Management project pilot facility, with Fakir Knitwear, Bangladesh, showcases how advanced wastewater treatment technologies like ultrafiltration and reverse osmosis can significantly cut greenhouse gas (GHG) emissions, water use, and chemical dependency in Bangladesh’s textile sector. Over seven years, the technology used in the Textile Wastewater Management project is estimated to enable 50% water reuse, save 756,000 m³ of groundwater and avoid 78,583 tCO2e emissions. As the textile sector contributes over 12% of Bangladesh’s national GHG emissions and 8.2% of electricity use, scaling such solutions can drive widespread decarbonisation and boost sectoral competitiveness (see also UNCTAD policy brief: From Waste to value: upcycling agricultural residues for sustainable textiles).
- Carbon credits are also playing an increasingly important role for SMEP pilot projects. For example, under the organic waste and water portfolio, two grantees have secured routes for carbon sales and will be generating revenues from this source in FY2025-26; and at least three of the SMEP-funded traceability interventions are including carbon footprint digital tracking in the value proposition (tanneries, textile and plastics recycling sectors).
- The Mananasi Fibre project has proven the technical and business viability of converting pineapple leaf waste into natural textile fibre through acquisition by Del Monte, thus showing strong market validation and scaling support. The project has attracted requests for expanding the decortication technology involved to other waste types and regions, such as Ivory Coast. Cross-grantee learnings (with Uganda-based Banatex-EA project) are facilitating further solutions for scalability, such as more efficient processes and improving spinnability of the fibres. Broader scaling potential of the banana fibre-based venture (Banatex-EA) is illustrated by the project garnering interest from Walmart Innovation Team at the 2025 Walmart Innovation Summit. Both projects have adopted GESI responsive and transformative approaches in their implementation. Mananasi Fibre promotes equitable employment practices, while the Banatex-EA supports local communities in generating income through targeted interventions.
- The FRESHPPACT Hub – a collaborative model for business, academia and industry consortia to identify and pilot solutions to improve and embed sustainability in fresh food produce sector – has attracted interest from key partners and the Barclays Foundation has confirmed willingness to fund the Hub beyond SMEP (The value of the support will depend on the nature and scale of the challenge funds implemented). In addition to maintaining the overall model post SMEP for longer run work and further impact, pilots under FRESHPPACT are already delivering. For example, Coco360 is converting coconut waste into agricultural products like mulch and will be scaling through securing £100,000 in follow-on funding from the Waitrose Foundation to scale operations and expand trials. And the Kelpi biodegradable packaging pilot is currently raising both grant and commercial capital to advance product development and achieve critical food-grade certifications.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The programme should continue. The outcome evidence above shows that the technologies/solutions being developed/piloted through the SMEP Programme are (1) generating promising reductions in environmental waste and associated GHG emissions, (2) demonstrating the ability to attract investment and scale through building viable business cases, (3) demonstrating GESI responsive or transformative levels of mainstreaming across different beneficiary groups, and (4) are providing evidence case studies of actual operational on-the-ground experience which are concretely informing various national and international policy processes, through the SMEP-UNCTAD partnership. Finally, SMEP is the only explicitly environmental pollution-focused programme within the FCDO’s Research and Evidence portfolio and is contributing to International Climate Finance indicators in reducing GHG emissions.
## C. DETAILED OUTPUT SCORING

Output Title	Improved knowledge and understanding of the environmental and health impacts of, and solutions for, pollution from manufacturing, including plastics.
Output number:		1	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
Number of peer reviewed research papers submitted and accepted concerning the environmental and health impacts of, and solutions for, pollution from manufacturing, including plastics.	25	Exceeded / Cumulative: 27 / FY 2024-25: 8
i) Number of research outputs aimed at advancing our understanding of the environmental and health impacts of, and solutions for, pollution from manufacturing.	32	Exceeded / Cumulative: 38[3] / FY 2024-25: 12
1.2ii) Number of research outputs that address the Gender, Equality and Social Inclusion implications of environmental health impacts of, and solutions for, pollution from manufacturing.	7	Not yet achieved / Cumulative: 5 / FY 2024-25: 3
Number of policy briefings or reports providing a synthesis of academic evidence and results aimed at policymakers, regulatory agencies and planners.	5	Substantially exceeded / Cumulative: 10 / FY 2024-25: 7
[3] A counting error in the FY2023-24 Annual Review under-reported against this indicator, leading to an FY2023-24 cumulative count of 25 when should have been 26. This has been corrected in this annual review.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output’s milestones have been exceeded, except 1.2ii which is slightly under achieved. However, SMEP is on track to meet the target, with activities already underway to support meeting the only currently off-track milestone. SMEP continues to generate robust, evidence-based solutions for addressing plastic and manufacturing pollution, contributing meaningfully to informed decision-making.
Aligned with its underpinning Research for Development (R4D) mandate, SMEP advanced empirical evidence in FY2024–25 to support policy briefs and reports aimed at influencing policy and regulatory decisions across its core Thematic Areas. Key examples include:
- SMEP developed several peer-reviewed papers (8), research outputs (12), including with a GESI angle (3), and policy briefs (7) to inform ongoing efforts to promote non-plastic substitutes in the INC instrument; East Africa Community’s (EAC) Single Use Plastic (SUP) Bill and World Trade Organization’s (WTO) Dialogue on Plastics Pollution (DPP). The UNCTAD-led Leaving the shore: Marine-based substitutes and alternatives to plastics report outlines the opportunities and risks associated with scaling up seaweed production, drawing out the implications for women and youth.
- The Mananasi Fibre project detailed the benefits to soil of Biochar enriched compost produced from pineapple waste, through increasing the soil organic carbon content.
- Policy recommendations for Bangladesh policy actors were developed to improve battery quality and safety for the ubiquitous three-wheeler vehicles in widespread use.
Following the end of the financial year under review, representatives of the UNCTAD team and relevant grant project participated in the World Circular Economy Forum, which drove the generation of two policy briefs: From Waste to Value: Upcycling Agricultural Residues for Sustainable Textiles and Beyond the Technical Loop: Driving the Circular Bioeconomy through Global Policy Coherence. These, and their outcomes, will be reported in next year’s annual report.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Reflecting the positive progress of the programme to date, output level milestones were revised during FY24/25. Further review is planned this year of relevant milestones to maintain an appropriate level of stretch within targets.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
2023-24 Report recommendation	Progress update
It is recommended that the promotion of more research synthetisation into policy brief and report formats is done with grantees and UNCTAD to get Output 1.3 on track. There are already several studies that are underway, with others planned for commencement in FY2024-25. There is confidence that these will generate several policy briefs to complement the other dissemination pathways mentioned above. The ULAB project will present a draft policy brief by the end of June 2024, which will inform the follow up round of consultation with policymakers.	The programme successfully addressed these recommendations and has exceeded the financial year’s milestone. / Studies which had begun in the year prior, were finalised for the year under review, bringing valuable research into the strategic pathways – including the ULAB project’s policy brief.
It is recommended that the GESI focal person per grant project works closely with grantees, especially those in the recently completed procurements for organic waste and water, tanneries, and textiles that integrated GESI from the outset, to ensure sufficient attention is retained to get Output 1.2.ii on track.	The PMA’s GESI focal point has been working closely with each grantee’s focal point, as well as enhancing the monitoring systems to document and track relevant interventions. However, this remains an area for further work in order to meet programme GESI ambition.

Lessons learned: For grantee knowledge generation (outputs) to support wider beneficial influence and impact, often the PMA or UNCTAD is required to proactively facilitate dissemination to the correct audiences.
Recommendations for the year ahead:
- Output 1.2 and 1.3 have exceeded milestones – a logframe review should be done by end of Q2 FY2025-26.
- Apply findings from GESI framework and reporting to improve GESI wherever possible on the programme and deliver output 1.2 ii

Output Title	Identification and development, in conjunction with key stakeholders, of policy and regulatory models that can promote and facilitate the adoption of technology-based solutions to address the pollution caused by manufacturing sector and plastics.
Output number:		2	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
2.1) Number of new policy and regulatory models or standards identified.	20	Exceeded / Cumulative: 26 / FY 2024-25: 9
2.2) Number of new policy and regulatory models or standards developed.	9	Under-achieved[4] / Cumulative: 7 / FY 2024-25: 4
2.3) Number of new policies; regulatory or standards related models that are tested and verified for effectiveness and capacity to achieve results in real-life scenario.	9	Exceeded / Cumulative: 11 / FY 2024-25: 5
2.4) Programme scoping and outreach including development of partnerships with private sector and civil society necessary for achieving the programme targets: relating to policy, regulatory or standards; as well as uptake (industry engagements).	19 formal agreements/partnerships55 events	Substantially Exceeded / Cumulative: 39 partnerships, 74 events / FY2024-25: 27 partnerships, 28 events
[4] Another 7 are on track currently for the FY 25-26.

Briefly describe the output’s activities and provide supporting narrative for the score.
The majority of this output’s milestones have been exceeded. Output 2.2 is under-achieved due to a time lag from identifying a policy to developing one. While SMEP only reports on policy models which are fully developed, several are currently under development. Notable examples of progress for this year include activities seeking to improve the enabling environment and promoting solution adoption for scaling:
Developed a policy model to promote gravity water filters, offering safe drinking water without relying on single-use plastics or large infrastructure in low-resource settings.
- At Kenya’s National Environmental Management Authority’s (NEMA) request, and with Environmental Coalition on Standards (ECOS) support, UNCTAD developed a policy model promoting biodegradable and compostable plastic alternatives in packaging and agriculture highlighting crop residue opportunities which was also followed-up with a workshop on implementation strategies.
- UNCTAD commissioned a study on second-hand clothing markets in Uganda and Tanzania in response to Uganda’s proposed ban on second-hand clothing imports and EU textile waste concerns. This was also set in the context of the textile recycling pilot in Uganda and complemented similar market analysis work by UNEP in other countries, thereby enabling a level of regional analysis and overview. Presented at COP29 (UNCTAD-UNEP event), the study proposes regulating imports and upcycling tailoring waste instead of outright bans.
- UNCTAD developed a policy model for alternative fibres, drawing on SMEP banana and pineapple fibre projects, to support rural value addition and job creation in developing countries.
Key events to note:
- The SAFECONOMY project, delivered an industry event workshop and expo stand at the Pakistan Water and Energy Expo which allowed industry player engagement with the project’s wastewater treatment solution.
- UNCTAD’s trade related dashboard tool, produced under SMEP, was presented at the Trade Tools for Climate Action event, which included discussions on a global framework for reducing GHG emissions arising from plastics, hosted by the Centre on Inclusive Trade and Development (CITD).
Key partnerships to note:
- UNCTAD is supporting a collaboration between Used lead acid batteries (ULAB) solutions project in Bangladesh and TradeLabs at the Graduate Institute, Geneva, to analyse, through a range of scenarios, ways in which the Bangladeshi Government can incentivise formal recycling of ULABs. Until this is possible in Bangladesh, additional mitigation may include facilitation of exports to specialised recycling locations outside of Bangladesh. This is to reduce harmful, informal and inefficient recycling practices currently prevalent in Bangladesh. This is a study examining a concept, not an endorsement of any specific actions..
- In partnership with the World Bank’s ProBlue Programme, SMEP’s Biodegradable Fishing Gear Project and UNCTAD worked together to include a case study in the World Bank’s Abandoned, Lost, and Otherwise Discarded Fishing Gear (ALDFG) report – offering relevant empirical evidence to the UN INC international treaty negotiation process.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Reflecting the positive progress of the programme to date, output level milestones were revised during FY24/25. Further review is planned this year of relevant milestones to maintain an appropriate level of stretch within targets.
Progress on recommendations from the previous AR (if completed)
2023-24 Report recommendation	Progress update
Explore participation in more events like the International Solid Waste Association (ISWA) World Congress in Cape Town, 12 September 2024: such events present potential avenues for impact in SMEP’s outcome areas related to policy impact and solution adoption, as well as knowledge production. Resulting from research coming out of ULAB project in Bangladesh a conference paper was submitted by Curtin University and UNCTAD, and has been approved for participation at The ISWA World Congress [this] coming year. There is potential to showcase the outcomes of the Circular Economy projects in Kenya at such events in future.	SMEP attended the ISWA Waste to Wealth event, and others relevant industry events, some key examples include: / UNCTAD presented research done by UNCTAD and WasteAid UK into the second-hand textiles industry in East Africa at the SMART annual convention on recycling (Dubai). The impact should be a more informed global conversation around the sector and eventually better-informed policy. / The Mananasi Fibres Project participated in events, presenting their SMEP Project: / Africa Waste is Wealth Series (AWWS II), Nairobi. The interview is included in the conference report. UNCTAD also moderated a panel discussion focused on strategies for driving sustainable organic pollution control strategies though trade. / Marine-based Products and Services (MAPS) Expo Geneva / International day of zero waste hosted by British High Commission in Nairobi / UNCTAD disseminated SMEP findings at a report launch for ‘Mozambique’s Second-Hand Clothing Market: The Opportunities and Challenges’. UNCTAD’s findings compliment this research and are helping to add to a growing evidence base that is being used by UNEP to develop global criteria for textiles waste – adding much needed data to a critical area of required policy change. / UNCTAD made presentation at the ‘Plastics Recycling Conference’ in Washington DC, as part of the Textiles Session: Exporters/Processors – Global Perspectives on Second-hand Clothing. The conference briought together top executives and decision-makers from plastics processors, converters, global brands, resin manufacturers, government agencies, trade groups and other key sector categories.

Lessons learned: Once policy models are identified, there can be a significant lag time before operational detail of model/s is developed. This slows progress against the relevant indicator as only policy models which are fully developed are recorded as progress, not those still under development. Strategic relationships (events and partnerships) assist in leveraging SMEP evidence to inform decision making at various levels, as well with the scaling of solutions –through exposure to relevant industry players.
Recommendations for the year ahead: Output 2.4 has exceeded milestones. Further review is planned this year of relevant milestones to maintain an appropriate level of stretch within targets.

Output Title	Development of technology-based solutions and supporting business models to reduce the environmental impact and enhance the gender and social equity of selected manufacturing processes including the plastics value chain.
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress / (cumulative)
3.1) Number of new technology-based solutions identified (hypothesised) across all target countries to address key sustainability and pollution issues related to selected manufacturing processes in SMEP target countries.	45	Exceeded / Cumulative: 50 / FY2024-25: 11 / Breakdown / Cumulative: 8 novel; 42 new to context / FY 2024-25: 2 novel, 9 new to context
3.2) Number of new technology-based solutions developed or adjusted, across all target countries to address key sustainability and pollution issues, in SMEP target countries.	32	Substantially Exceeded / Cumulative: 42 / FY2024-25: 13 / Breakdown / Cumulative: 10 novel, 32 new to context / FY 2024-25: 4 novel, 9 new to context
3.3) Number of successful pilot projects and/or field testing of technology-based solutions developed by SMEP programme across all target countries, providing documented proof of technical and commercial viability.	16	Substantially Exceeded / Cumulative: 23 / FY 2024-25: 9 / Breakdown / Cumulative: 10 novel, 13 new to context / FY2024-25: 3 novel, 6 new to context
3.4) Number of grants with objectives to improve GESI as part of the technology or business model being developed.	11	Substantially Exceeded / Cumulative: 19 / FY 2024-25: 12

Briefly describe the output’s activities and provide supporting narrative for the score.
This output’s milestones have been exceeded and is on track to meet end-of-programme targets. During FY 2024-25, the final set of grantees, in the Tanneries industrial sector, entered delivery. This output addresses challenges within the value chain to enable pollution mitigation through innovations in technology and traceability, policy reform, and supporting industry to comply with changing standards and certifications.
Examples from SMEP-funded projects during the year under review include:
- Led by innovator Panta Rei, the Textile Wastewater Management project, aims to determine how circular water usage can be achieved within a garment factory’s overall resource envelope. The project is demonstrating a solution at a Bangladesh-based textile manufacturer. The newly formed National Alliance for Water Reuse and Recycling is using this demonstration as a case study showcasing market and economic viability of shifting towards circular solutions in textile manufacturing.
- The Pakistan Leather Sustainability project, led by the WWF-Pakistan, is developing and testing an e-traceability system for the tanneries sector. The international Leather Working Group has shown eagerness to collaborate, which kicked off with webinar planning in Q4 2024-25, to ensure alignment of standards. This demonstrates the meaningful role of SMEP-funded solutions in supporting compliance to regulations and standards.
- The Wastewater treatment in Nairobi project, led by KNCPC, has set up a demonstration site for membrane technology water treatment, supporting efforts to develop scaling models for wider uptake of technology-based solutions by addressing barriers to access to finance. Mechanisms for improved effluent treatment at source support the goals of the Nairobi River Commission and Kenyan Ministry of Industry, Trade and Investment to address pollution from industrial sources in the basin.
- The Waste-to-Insect Protein and Fertiliser project incorporated flexible working hours for mothers with babies under six months old to enable them to participate in formal employment. Mananasi Fibre has hired and trained a woman with a disability in their weaving team giving her an income, and there are three other persons with disabilities employed across SMEP in the Green Tannery Initiative and Plastics2Ghar projects.
Further information on the GESI approach being applied in SMEP projects and respective technology-based solutions and business models is presented in Annex 2.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Reflecting the positive progress of the programme to date, output level milestones were revised during FY24/25. Further review is planned this year to maintain an appropriate level of stretch.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
2023-24 Report recommendation	Progress update
It is recommended that the GESI focal person per grant project works closely with grantees, especially those in the recently completed procurements for organic waste and water, tanneries, and textiles that integrated GESI from the outset, to ensure sufficient attention is retained to get Output 3.4 on track. A further review of logframe milestones in relation to the programme extension is underway and will be completed by end of Q2 FY2024-25.	The SMEP PMA introduced a revised GESI framework that provides an actionable approach to promoting inclusive practices, alongside workshops to strengthen GESI activities. The framework allows for a more robust reporting approach that collects a range of disaggregated beneficiary data, while also providing qualitative insights to show the changes from activities undertaken. This framework encourages grantees to report and count transformative activities that contribute towards meaningful reforms across the three thematic areas: project team, direct beneficiaries or indirect beneficiaries of solutions tested. SMEP grantees are encouraged to use this framing to assess the changes triggered by their inclusive actions and to monitor how these changes influence their immediate and extended operating environments. Examples of strengthened GESI activities: / Taka Taka Solutions and Mananasi Fibre have implemented flexible working hours for lactating mothers with babies under 6 months, providing slightly longer lunch breaks to support exclusive breastfeeding for up to 6 months. These arrangements allow mothers to participate in formal employment and promote healthy conditions for both mothers and their babies. / Busitema University trained the project team on financial literacy and sexual and gender-based violence. / These engagements with grantees have encouraged stronger GESI mainstreaming in project delivery, promoting the active identification of social and gendered challenges and the continued integration of inclusive approaches into project design and implementation. The framework can be found here. Cases of good project practice (such as the above examples) are shared across shared across SMEP programme through published stories, posts and learning workshops.

Lessons learned:
Many innovative ways to incorporate GESI into projects through technology end users; and/or team considerations. These approaches offer potential for replication.
Recommendations for the year ahead:
- Continue to leverage the Programme’s networks and platforms to demonstrate solution viability, as per the Panta Rei example (PMA, UNCTAD, throughout FY 2025/26).
- Milestones exceeded for 3.2; 3.3 and 3.4. A logframe milestone review should be done by end of Q2 FY2025-26.
- Maintain grantee engagement on GESI mainstreaming and beneficiary reporting through learning workshops (PMA, throughout FY25/26).

Output Title	Establishment of new circular processes that reduce environmental damage and industrial waste from manufacturing and plastics value chain and establish new sources of wealth and growth.
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
4.1) Number of new circular processes identified, aimed at reducing waste and pollution from selected manufacturing production processes and value chains in target countries.	22	Exceeded Cumulative: 27 / FY 24-25: 12
4.2) Number of new circular processes developed and established, aimed at reducing waste and pollution from selected manufacturing production processes and value chains in target countries.	15	Exceeded Cumulative: 19 / FY 24-25: 5
4.3) Number of successful pilot projects and/or field testing of new circular processes, providing proof of technical and commercial viability.	6	Exceeded Cumulative: 11 / FY 24-25: 7

Briefly describe the output’s activities and provide supporting narrative for the score.
This output’s milestones have all been exceeded. This output complements output 3, with a focus on circular processes rather than purely technology solutions. This includes re-design to minimise waste and maximise resource efficiency across entire value chains. Often these are low-barrier, context-sensitive interventions that can be more rapidly implemented and adapted to local conditions (compared to introduction of new technology). Both approaches are relevant, depending on the context.
Some examples of the circular-process solutions being funded by SMEP include:
- The Green Tannery Initiative project is replacing hazardous chemicals with enzymes for unhairing; and demonstrating/developing advanced waste management technologies for producing value added products from tannery solid wastes.
- The Waste-to-Insect Protein and Fertiliser project has demonstrated the success of their circular model: composting, biochar, and black soldier fly (BSF) processing using organic content of municipal waste. Interest in scaling opportunities (see outcome B and C) have highlighted the model’s regional relevance.
- The Mananasi Fibre project is using biochar to filter out wastewater from the pineapple decortication process so that the water can be reused at the project site, alongside reducing toxic discharge into the environment.
- The Waste-to-Biogas project is using fish offal blended with water hyacinth as feedstock for a biogas digester, testing the technical and economic feasibility of this alongside the environmental impact.
- The Waste-to-Biochar project has identified, developed and installed pyrolysis in its operations: organic waste from the food and beverage sector is being diverted to produce biochar which will be blended with organic waste for regenerative farming practices.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Reflecting the positive progress of the programme to date, output level milestones were revised during FY24/25. Further review is planned this year of relevant milestones to maintain an appropriate level of stretch within targets.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
2023-24 Report recommendation	Progress update
Continued SMEP cross-pollination of projects through grantee introductions and engagements, to create potential circular linkages or promote shared lessons about the integration of circularity into business practices.	Substantial progress was made in supporting cross-fertilisation within and across SMEP sectors through grantee introductions and engagements: / During the FY 2024-25 UNCTAD planned the facilitation of grantee learning at the World Circular Economy Forum (WCEF) which took place in May 2025. / Learning workshops were hosted between grantees to share learnings on water treatment technologies and processes. / Introductions between SMEP-funded projects for bilateral lesson-sharing engagements have been facilitated by the PMA.

Lessons learned:
- As noted under Output 3, the role of in-situ operational pilot projects in informing decision making and demonstrating a business case is key to bringing research into practice.
- GESI can be incorporated into projects in unconventional ways that can offer potential for replication: for example the Waste-to-Biochar project is piloting cement with biochar to reduce costs of pre-fabricated toilets increasing access for low-income households – as an indirect result of SMEP funding.
Recommendations for the year ahead:
- Continue to leverage the Programme’s networks and platforms in the arena of circular economy to demonstrate solution viability.
- 4.1 and 4.3 have exceeded milestones and a logframe review should be done by end of Q2FY 2025-26.

Output Title	Co-design/development of toolkits to be used by policy makers and planners.
Output number:		5	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review (cumulative)	Progress
5.1) Number of policymaking and/or regulatory agencies/bodies engaged in scoping of needs, as well as co-design and co-production process.	55	Slightly under-achieved / Cumulative: 52 / FY 24-25: 8
5.2) Number of toolkits developed and tested through pilot projects and or field-testing.	12	Achieved / Cumulative: 12 / FY 24-25:5
5.3) Number of policymaking and/or regulatory bodies providing a positive assessment/review of toolkits developed and adopting early versions for further development.	15	Exceeded / Cumulative: 25 / FY 24-25: 11

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall the output has been met. Engaging policymakers and developing/testing toolkits are key elements in SMEP’s pathway to success and, overall, satisfactory progress has been made during the year under review, including the production of toolkits for use in decision making and establishment of solution models.
Engaging policymaking and/or regulatory agencies in scoping of needs and co-design/co-production ensures that the design of SMEP-supported innovations is grounded in local policy realities, regulatory needs, and market conditions. Some key examples from the year under review include:
- UNCTAD co-organised a workshop with ECOS, the International Organization for Standardization (ISO) and the Africa Legal Network (ALN) on biodegradable and compostable standards. UNCTAD’s study analysing existing and potential standards was used as the basis of a workshop with national stakeholders from Kenya, Ghana and Nigeria to foster enhanced collaboration on plastic-related standards and policies. The workshop convened National Standards Bodies (NSBs), Environmental Regulators and other key stakeholders, providing a platform for in-depth discussions and coordination. An important output of this workshop was to provide guidance to the eventual East Africa Community Single Use Plastic draft Bill.
- The Flipflopi Toolkit was co-designed with policymakers in East and West Africa. There was a high level of interest, particularly in how to reduce the public burden of plastic waste and enabling plastic recyclers to thrive in resource-constrained environments.
Developing and testing toolkits through pilot projects or field-testing translates research and piloted innovations into practical, evidence-based tools that have been tested in real contexts. Some examples include:
- In alignment to the WTO DPP and INC processes, UNCTAD has created a new database tool for policy makers which represents trade in non-plastic substitutes, helping users of UNCTAD’s Data Hub to better understand current trade dynamics of non-plastic substitutes. This allows them to plan for increases in trade of these, potentially related to decreases in trade of plastics (article link).
- UNCTAD developed a data tool for identifying the role of services in the prevention and mitigation of plastic pollution.The Flipflopi Toolkit is a practical and adaptable resource for any organisation looking to make community-based plastic waste management work in challenging environments.
The Programme’s feedback for evidence-based tools has been positive – largely through invitations to present toolkits and research at relevant industry events and panels; as well as reference to SMEP tools in formal papers. For example, the UNCTAD publication "Beyond Plastics: A Review of Trade-related Policy Measures on Non-plastic Substitutes" as part of the SMEP Programme was featured on Devdiscourse, a media platform for development stakeholders with significant reach and of good reputation among international development partners. This demonstrates the usefulness of the work the Programme is developing.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Reflecting the positive progress of the programme to date, output level milestones were revised during FY24/25. Further review is planned this year of relevant milestones to maintain an appropriate level of stretch within targets..
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
2023-24 Report recommendation	Progress update
None	N/A

Recommendations for the year ahead: 5.3 has exceeded milestones. A logframe review should be done by Q2 FY 2025-26 milestone.

## D. VALUE FOR MONEY
Key cost drivers and performance
Key cost drivers for the PMA and UNCTAD have remained staff time in delivering the Programme, notably programme management costs associated with strategic and technical oversight and managing annual budget allocations which require flexibility and a phased approach to procuring and managing downstream grants. Value for money has been maintained through the FCDO framework contract with PMA (which has fixed fee rates that were developed through the framework competition processes) as well as in-kind contributions from UNCTAD (staff time and conferences). Textiles and Tanneries Calls have been completed, with all selected grantees onboard enabling full delivery of the programme.
Assessment of whether the programme continues to represent value for money
SMEP continues to represent good value for money, particularly as it is now at a mature stage and delivering well against outputs and outcomes (as noted in above sections) within its agreed budget.
Table 2 below provides an overview of VfM performance to date and in the past financial year.
Table 2. VfM Performance
Economy – minimising input cost
% of grant funding going to delivery vs. overheads	Out of £5,461,832 in grant expenditure this FY, £405,606 (7%) was spent on overheads and £5,056,225 (93%) was spent on delivery. / Grant projects in the Plastics Pollution portfolio have the highest overhead costs, composing 17% of overall funding whereas other portfolios range between 2% and 4%. This is due to the portfolio having more UK-based universities as grantees, which tend to have higher overhead costs.
Co-contributions to UNCTAD activities	Co-contributions leveraged for UNCTAD-led activities amounted to USD 121,600.00. This is additional to UNCTAD’s £362,327 in-kind contributions to SMEP for staff time, facilities and infrastructure.
Efficiency – conversion of inputs to outputs
Ratio of management costs to programme costs	With the PMA costs totalling £513,406 out of an overall £6,420,921 in programme expenditure, management costs represent 8% of the budget.
Effectiveness – conversion of outputs into outcomes
Progress towards outcomes	Of the 25 grant projects that were active this FY: / Five projects have had solutions scale. / Eight projects have demonstrated sustained pollution abatement; and / All projects in the Plastics Pollution, Organic Waste & Water as well as the Tanneries portfolios have had at least one piloted solution progress at least one level against the maturity matrix. / Some projects where the early evidence proved less promising or research partner was not able to fully deliver despite support, have been closed early, with option to reallocate savings from these projects to fund more successful projects.
Equity – degree to which results of intervention are equally distributed
% of beneficiaries who are women, youth and persons with disability (PWD)	The SMEP GESI framework has been revised to provide a more coherent and actionable approach to promoting inclusive innovation across the manufacturing sectors. Together, these components provide a methodology for identifying who benefits from project activities and how meaningfully GESI principles are being integrated across different stages and stakeholder groups. Several examples of how GESI has been strengthened on projects are noted under output 3 above. / The following information is based on the data submitted by SMEP grantees at the end of FY2024-25 Q4: / 39% of 605 people directly employed on SMEP grant projects are women / 56% of direct employees are youth aged between 18 and 35. / Four persons with disabilities (PWD) are currently employed through the programme. / 36% of policy influencers reached are women by UNCTAD events. (The aim is for 50% female presenters/panellists, representing local voices where possible)

E: RISK
Overview of risk management
The SMEP Programme’s overall risk rating of “moderate” remains unchanged and risks have stayed within the Programme’s risk-appetite. High-level context-related risks included extreme weather events, climate change, natural disasters and political instability. In the reporting year, SMEP budgets were not directly affected by these risks, but delivery was slightly delayed for some projects operating in Bangladesh (Table 3). Most grant-funded projects were not impacted by the global cut in USAID projects and, where their co-financing was, delivery has not been impacted. There are operational risks given the nature of some of the interventions within the portfolio, specific issues can and do arise during actual implementation. The operational SMEP risk management system is relevant, picking up emerging risks and issues which are discussed and mitigated, with escalation in PMA and FCDO where necessary. Active learning as well as mitigation is undertaken regarding any risks that do materialise. For example, SMEP has begun a process of strengthening grantee safeguarding risk assessments and mitigations this year with a focus on occupational health and safety; including with enhanced incorporation into Key Performance Indicators. This will continue into the next reporting period including training for grantees.
Table 3. FY2024-25 Programme Risk Overview
Risk	Mitigating Action
Strategy and context: The Bangladesh government was overturned in January 2024. While an interim administration is in place, political uncertainty remains high due to disagreements over election timelines and proposed reforms. This poses a contextual delivery risk for SMEP grantees – delays in obtaining permits and approvals, disruption to field activities, and unpredictability in regulatory or policy environments.	The PMA is monitoring the political and security context on an ongoing basis. Additionally, close coordination is maintained between the projects’ leads and the respective Portfolio Manager. This includes the close monitoring of currency gains or losses and adapting activities where applicable.
Delivery: There remains some risk that not all projects will complete piloting by the end of FY2025-26 as planned due to unforeseen issues and delays	The PMA continues optimal use of technical sector experts, Independent Technical Advisory Panel (ITAP) and UNCTAD technical assistance. Effective planning, coordination and prioritisation between UNCTAD, PMA, FCDO and grantees is ongoing. / Select grantees from the Tanneries and Textiles calls have been granted no-cost extensions for an additional three months into June 2026, giving the Programme until November 2026 to close-out. This is in line with the earlier agreed contract extension for PMA to November 2026.
Safeguarding including sexual exploitation and harassment: Due to the nature of some of the sectors that SMEP is targeting, there is exposure to potential safeguarding issues, that are inherent to the sectors, like occupational health and safety, unfair labour practises, child labour, modern day slavery. Health or safeguarding incidents could also occur during travel to SMEP related events or site visits. Several of these risks could cause Reputational damage to the organisations involved in SMEP programme as well as serious harm to individuals. / Environmental Safeguarding Risks	Stringent due diligence checks applied to the projects that potentially have this exposure during the grant application processes, contracting and implementation. Site visits and guidance provided where needs identified. Pro-active insurance enforcement on all official travel. / PMA have updated the risk assessments and guidance to grantees including more focus on identifying and ensuring appropriate management of occupational health and safety risks. This is being supplemented by support from The Ethical Trading Initiative (ETI) including trainings and guidance materials in the coming months. / The purpose of SMEP is to mitigate environmental risk but specific controls are in place to ensure the innovations that SMEP supports do not increase environmental risk.
Financial and Fiduciary: delayed and / or poor-quality financial reporting leads to inaccurate budgeting and decision making.	The PMA actively engages grantees throughout implementation, including hosting trainings on SMEP’s financial requirements. Where required, additional bespoke trainings are provided, and some grantees use monthly rather than quarterly financial reporting.
Sustainability: Projects funded by SMEP are not able to continue after SMEP funding	Mitigation includes refining and actioning the exit plan and encouraging co-financing and partnerships between various stakeholders across the value chain. The PMA is actively tracking where grantees have potential opportunities for scaling, including where they already have committed funding from non-SMEP partners. SMEP grantee outputs will be readily accessible for an additional two years beyond the lifetime of the programme via the website and LinkedIn page, extending the probability of uptake and scaling. They will also be available through The UK Government Research for Development (R4D) website.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Delivery and partnership considerations: UNCTAD and the PMA continue to work in partnership across all delivery areas. Collaboration includes coordination on the overall Programme strategy, progress towards outcomes as well as on events, grantee site visits and asset checks. The PMA maintains an up-to-date asset register (updated quarterly) which has been validated through site visits to Ghana, Kenya, Pakistan and Uganda this year. As the Programme enters its last 15 months, planning for a responsible close-out of the grants and programme will be a priority in the year ahead. Timely confirmation of the FY2024-25 and FY2025-26 annual budgets from FCDO to PMA and PMA to grantees has been helpful in enabling delivery and is important for the final months of implementation in FY2026-27.
Financial and commercial performance: The PMA has performed well (consistently scoring “good” or “approaching target”) against its quarterly key performance indicators which relate to Financial Management; Programme Milestones and Grant Performance. Invoicing by the PMA and UNCTAD has been timely and accurate with updates made to the delivery chain map accordingly. Table 4 below provides a breakdown of the funds disbursed to the PMA for FY2024-25.
Table 4. SMEP PMA Drawdown from FCDO to Date
Category	Programme to FY2024-25	Year to date (FY2024-25)
PMA Personnel and Expenses	£ 2,095,332	£ 513,406
Grant Fund	£ 14,371,643	£ 5,907,515
Total	£ 16,466,975	£ 6,420,921

UNCTAD is funded through a bilateral MoU with FCDO for SMEP of up to £2,600,000. £600,000 funding was disbursed to UNCTAD during this reporting period including: £20,000 for Technical Studies and Tools; £480,000 for research into Policy-impact Activities; £45,000 for Communications and £55,000 for monitoring and event logistics. UNCTAD committed an additional £362,327 in-kind for staff time, facilities and infrastructure.
Compliance: The PMA continues to demonstrate compliance with the Supply Partner Code and the Gender Equity Duty for ODA programmes. Specific updates for the period FY2024-25 on Financial Management, Gender Equality and Social Inclusion (GESI) and Safeguarding are provided below.
- Financial Management: SMEP grantees are required to supplement the PMA with quarterly financial reports on expenditure, including transaction listings. Additional spot checks are carried out quarterly and backed up by the PMA on site visits. All grantees have signed annual declarations on tax compliance and conflict of interest.
- GESI: The PMA has updated the programme GESI Framework to enable both the programme and grantees to monitor progress, promote accountability and track mainstreaming across funded projects and in relation to their project teams as well as direct and indirect beneficiaries of the solutions being tested.
- Safeguarding: SMEP’s project-level safeguarding approach has been updated to include enhanced risk assessments (ETI UK were on-boarded at the close of FY 2024-25 to support this) and guidance to grantees during implementation.
G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation: The FCDO SMEP Programme team completed this annual review based on reporting from PMA and UNCTAD. The PMA provides quarterly narrative (including risk) and financial reporting to FCDO, and this is followed up with a meeting each quarter. UNCTAD provides bi-annual reporting to FCDO (with follow-up meetings) linked to payments. In addition, PMA, UNCTAD and FCDO convene through management and steering committee meetings as needed to plan project visits for the reporting year, co-ordinating of workplans between UNCTAD and PMA and to make Grant Call decisions. The PMA continues to monitor grantee progress through quarterly reports, technical and financial, grantee quarterly progress meetings and site visits. In this reporting period, FCDO staff joined visits to the Organic Waste & Water Portfolio grantees in Kenya. Separately, the PMA and UNCTAD have visited grantees in Ghana, Uganda, South Africa and Pakistan. With regards to outcome level reporting, the following tools are utilised and fed into the Strategic Framework:
- Portfolio roadmaps: Portfolio roadmaps continue to be an effective mechanism to track regulatory initiatives and stakeholder engagement under Outcome A. Impact pathways are routinely updated by the PMA, in conjunction with UNCTAD.
- Pollution abatement data: Grantees report pollution abatement data into the quarterly environmental pollution forms.
- Green House Gas (GHG) emission data: Data is collated from grantees by specialists contracted to draft the Programme’s bi-annual ICF reports.
- Outcome Monitoring Tool: An Outcome Monitoring Tool was launched in the second half of this reporting period to strengthen outcome-level tracking across the grant portfolio. This tool functions to systematically capture the progress of grantee solutions against the Maturity Matrix across solution viability (pilot progress and pollution abatement), market viability (standards and regulations) and business model viability (Outcome B.3). It also captures the grantee solutions’ potential for scaling and adoption (Outcome C.1).
Evidence: The M&E System has been further strengthened through the automation of all data analysis with PowerBI – all SMEP monitoring tools have been linked to the platform. SMEP has also developed a new form for collecting grantee data on beneficiaries reached and GESI mainstreaming. This was rolled out in FY2024-25 Q3 and updated in Q4, enabling the Programme to better understand and report on co-benefits. Following a monitoring visit and follow-up, the Steering Committee decided to responsibly terminate early one grantee’s contract because it emerged during initial project work that the main rationale, which aimed to address a significant textile waste problem in Uganda, could not be validated. The unused project grant funds are being reallocated to other better value for money SMEP intervention. UNCTAD will still draw on the work that was successfully completed under the project in its wider ongoing textile engagement with key international and local stakeholders.
Learning: In March 2025, the PMA convened a trilateral learning workshop in Cape Town, attended by FCDO and UNCTAD representatives. The workshop provided a platform for presenting progress across Portfolio Roadmaps, GESI-related achievements and key lessons emerging from the grant portfolio. Two overarching thematic areas were crystallised during the discussions, reflecting common challenges and innovation potential across sectors: Water and Oceans and the Circular Bio-economy (as outlined in the overview section). These themes will inform strategic direction, learning priorities and potential allocation of remaining grant funding for the final phase of SMEP’s implementation. The workshop also reinforced the importance of cross-portfolio dialogue in surfacing shared solutions and transferable approaches.

Date of last narrative financial report	09.05.25	Date of last audited annual statement	29.02.24

ANNEX 1 SMEP Business Maturity Matrix

Annex 2: overview of key GESI achievements for FY2024-25 based on the new GESI framework.