Climate Compatible Growth Research programme
Management Review (FINAL Draft)
Authors: Simon Trace, Fernanda Carneiro, Craig Bardsley
April 2025
About Oxford Policy Management
Our vision is for fair public policy that benefits both people and the planet. Our purpose is to improve lives through sustainable policy change in low- and middle-income countries.
Through our global network of offices, we work in partnership with national stakeholders and decision makers to research, design, implement and evaluate impactful public policy. We work in all areas of economic and social policy and governance, including health, finance, education, climate change and public sector management. We have cross-cutting expertise in our dedicated teams of monitoring and evaluation, political economy analysis, statistics, and research methods specialists. We draw on our local and international sector experts to provide the very best evidence-based support.

# Preface
This assessment is being carried out by OPM, the project manager is Simon Trace. The remaining team members are Fernanda Carneiro and Craig Bardsley. For further information contact Simon Trace at simon.trace@opml.co.uk
Executive summary
Purpose and extent of review
The purpose of this exercise was to review the management of the Climate Compatible Growth applied research programme. The exercise aimed to follow up and comment on progress on management-related recommendations made in the Phase 1 evaluation of the CCG programme completed in 2023, to reflect on the direction of travel of recently updated programme management and administrative systems and processes, and to consider any potential issues emerging since the evaluation was completed.
The review was carried out over February and March 2025 and involved a one day workshop with CCG’s Programme Management Unit (PMU) and representatives of Loughborough University’s (LU’s) Research and Innovation Office (RIO), 11 individual interviews with 13 CCG and LU staff, a review of documentation and follow-up email exchanges.
We were unable to complete two interviews because of travel commitments or illness on behalf of the interviewees but other than that experienced no obstacles to completing this assignment. We received good cooperation from all CCG and LU staff involved.
Overall finding
Our overall finding from this review was that the strategic, management and administrative support to the programme has improved significantly since the phase 1 evaluation. The staffing up of the PMU, particularly in the last six months, is universally welcomed across the CCG staff interviewed. Work around projectisation and monitoring and evaluation have progressed significantly since the Phase 1 evaluation was concluded in May 2024, with the former now a well-embedded practice. These improvements in management and administrative processes, combined with other actions such as the work on a new research strategy by the new Research Director, has led to a better sense of programmatic coherence across the workstreams as a result.
Specific findings
We found that CCG’s efforts to projectise its work were proceeding reasonably well. A basic spreadsheet system for reporting progress against objectives was in place and working. Further support seems to be needed for a minority of workstreams to improve their ability to identify objectives and report progress at a level of detail and usefulness consistent the remaining workstreams. Care also needs to be taken with the introduction of the new ClickUp software that aims to replace the current spreadsheet-based system, to avoid duplication of information requests and minimise any additional effort required from the workstreams as the main data providers.
Some consortium partners continue to miss quarterly invoicing deadlines. Our analysis of the past four quarters of invoicing showed Imperial College was the worst performer, submitting invoices significantly late in three out of the four quarters reviewed. However, across the consortium as a whole there is no real distinguishable pattern across that 12-month period, with only four of the nine partners consistently submitting invoices on time. Also, the situation doesn’t seem to be heading in a particular direction – although quarter 2 reporting was a significant improvement over quarter 1 for this year, quarter 3 represented a deterioration on quarter 2 again. CCG has recently reached agreement with FCDO that two invoices can be sent each quarter, the first being within the planned quarterly timeframe and the second to cover any remaining consortium partner invoices which have been submitted late. We are not clear if this action has been sufficient to mitigate the problem late invoicing has been causing FCDO and so make no recommendations We do note in the text that further options for consideration could be shifting consortium partners who are regularly late with invoice submission on to monthly invoicing, or requiring them to allocate some of their grant to further administrative support in their institution to speed processes up.
We reviewed the time taken to complete contracts under most recent FRF and SPF calls and found that the average time to completion was reasonable. As far as formalising relationships with international partners (MDBs, international organisations etc) is concerned, most of the MOUs required by the International Partnerships workstream are in place and, as they don’t involve funding, will not need to be annually renewed. One issue did arise last year with ICTP, a UNESCO subsidiary, where the organisation in question insisted on using a form of MoU / letter of contribution when LU would normally use a contract (as funding was involved). This took some time to resolve with LU, but a subsequent renewal of the same agreement this year was relatively smooth and quick.
We reviewed the function of the STEER centre at Loughborough University, under which CCG (and the MECS programme) sit. We found that grouping programmes together under STEER doesn’t produce any economies of scale in terms of cost savings through the sharing of resources. But it does have significant advantages in making operating what are non-standard projects (for a Higher Education Institute) easier within the LU environs.
In reviewing the Operational Intelligence Framework unit (OIF) we found that the work it originally did around conceptualising how CCG’s activities could be projectized in order to better track progress against objectives, has been further developed and mainstreamed into annual planning and monthly reporting processes under the PMU. OIF now focuses on quality assurance processes both for output and outcome KPI data and support for flexible funding calls. Institutionally it sits within the wider PMU function and reports to the Head of Programme Portfolio.
With respect to the staffing of the PMU we note that historically, budget restrictions and decisions in such circumstances to prioritise research activities over management have meant that staffing levels within the PMU have been a real limitation in the past. We also note that the level of support provided to CCG from staff paid for by CCG but sitting in the RIO has not always lived up to expectations and that from April 2025 CCG will no longer provide additional funding for these positions but expect the RIO to fund them from its overhead recovery from CCG. The RIO has committed to doing this and CCG has now added a new grants manager to strengthen the PMU. The programme has only had a full complement of staff (with respect to what was envisaged under the original £38m budget) over the last 6 months, but this has already had a significant positive impact on the PMU’s ability to implement processes at speed. Given that CCG’s budget has now increased to 94.6, £94.6m (of which around £91m is marked for an accountable grant with LU) and annual turnover this year is double that of prior years’ however, there are still additional posts within the PMU that need to be filled to ensure its capacity is aligned with the current scale of the programme.
Budget cycle risk remains a central concern for the PMU and consortium partners. It creates a significant additional administrative burden and continues to cause problems for the recruitment and retention of staff at consortium partners. We identify three interrelated problems: FCDO’s inability in recent years, as a result of uncertainties across Government, to be able to confirm budgets for consortium partners for more than 12 months at a time; FCDO’s often late confirmation of the budget for the coming fiscal year; and further delays with CCG consortium partners completing the necessary tasks before annual letters of variation to consortium partners’ contracts can be finalised. We set out some possible courses of action to reduce the impact but recognise that some of these (for example the confirmation of multi-year budgets), may be unrealistic in the current uncertain environment with cuts to the UK aid budget.
With respect to CCG’s monitoring and evaluation, our review confirms that there is a functioning MEL system in place, but there are some further improvements that could be made. We suggest that the Operational Intelligence Framework unit currently responsible for MEL would benefit from an additional post to provide more capacity to reflect on what works, what is not working and why, to better support programme improvement. We suggest that further documentation is required to formalise and detail the individual MEL indicators, how and by whom their data is to be collected, how the data is analysed and progress assessed, how data is safely stored, and how (and by whom) any regular processes such as data cleaning and removal of duplications is to be carried out and logged. We recommend that quarterly MEL data is used to reflect on actions / course corrections needed going forward and that the result of these discussion is documented. Finally, we suggest CCG should consider developing more dynamic tools or ways to display the outputs from the MEL system (such as dashboards) to support greater engagement on and discussion of results.
[note] CCG’s M&E reporting system is still in the process of finalization and subject to FCDO’s final approval.
On risk management we recognise that CCG has an Enhanced Risk Management Strategy (ERMS) which details the process for recording, monitoring, and escalating risks. We suggest the risk register could be improved by creating a compound risk rating (a combination of likelihood and impact) and introducing, as a comparator, an assessment of risk appetite for each risk. We identify that risk capture at workstream level needs reviewing to set an expectation of level of detail required, given some workstreams’ identification of potential risks seems quite shallow while one workstream’s analysis is over elaborate. We also note that the programme-level risk register could be consolidated (to remove duplicates or risks that are no longer relevant). Finally, we note that the programme-level risk register contains only generic risk descriptions and that there is no evidence in it to demonstrate that senior management are actively managing current specific risks. We suggest some specific risks that we would have expected to see on the programme level register in this respect.
While the CCG Value for Money (VFM) framework was used in the FY 24/25 FCDO Annual Review, the framework remains in draft form and subject to FCDO approval. It is also the subject of some contention. Having reviewed the existing draft and discussed with the PMU we raise two main issues. Firstly, we detect a watering down of the original definition of some VFM standards which we believe puts them at odds with generic definitions of excellent, good, adequate, or poor performance. We suggest CCG should reconsider the standards being set for each criterion in the light of the generic description of ‘excellent’, ‘good’, ‘adequate’ and ‘poor’ we provide in Table 2 of this document. Secondly, we note that the economy criterion of the VFM framework seems to create particular implementation difficulties for the programme. We believe this is caused, at least in part, by CCG trying to use this element of the framework as an expenses / procurement policy rather than the retrospective evaluative framework for assessing the VFM arising from the consortium applying their own expenses and procurement policies in practice. We suggest an approach to resolving this issue.
Finally, with respect to management and governance we note that CCG recognises the current arrangements for an external advisory group are not providing value and are currently under review. We suggest that the purpose of the external advisor role needs to be more tightly defined and set out four possible options. We would further suggest that given the scale and complexity of CCG, external advisors, if used, be allocated to individual workstreams, with regular task-based touch points scheduled, to allow them to develop some depth of knowledge of an area of CCG operation and to be in a better position to provide whatever function is required of the role type eventually decided upon.
A full set of recommendations from this review can be found in section 6 of this report.
Table of contents

List of tables and boxes

List of abbreviations
AGA	Annual Grant Agreement
CCG	Climate Compatible Growth research programme
ESMAP	Energy Sector Management Assistance Programme, World Bank
FIA	FIA Foundation - Federation Internationale de l'Automobile
FCDO	Foreign, Commonwealth and Development Office
FRF	Flexible Research Fund
FY	Fiscal Year
KTH	KTH Royan Institution of Technology, Stockholm
LU	Loughborough University
MECS	Modern Energy Cooking Services research programme
MEL	Monitoring, Evaluation and Learning
OIF	Operational Intelligence Framework unit
OPM	Oxford Policy Management
PMU	Programme Management Unit
RIO	Research and Innovation Office of Loughborough University
SPF	Southern Partners’ Fund
STEER	Centre for Sustainable Transitions: Energy, Environment and Resilience
UNFCC	United Nations Framework Convention on Climate Change
VFM	Value for Money
WS	Workstream

# Introduction
## Purpose of review
The purpose of this exercise was to review the management of the Climate Compatible Growth applied research programme. The exercise aimed to:
- Provide an opportunity to follow-up and comment on progress on management-related recommendations made in the Phase 1 evaluation of the CCG programme completed in 2023
- Reflect on the direction of travel of recently refreshed (or under development) programme management and administrative systems and processes
- Consider additional questions not covered in the evaluation or related to potential issues emerging since the evaluation was completed.
The review covered questions under five areas as follows:
1. Programme management and contracting
2. Staffing and resourcing
3. Monitoring, evaluation, and learning
4. Decision making and governance
5. The Operational Intelligence Framework
The full terms of reference are provided in Annex A
## Methodology and approach
This was a short review exercise running across February and March 2025. Early on in the process a day-long workshop was held at Loughborough University with the CCG Director and Deputy Director, staff of the CCG Project Management Unit (PMU), the STEER Centre representative, and support staff from Loughborough University’s Research and Innovation Office (RIO). FCDO were in attendance remotely. This workshop allowed for an initial wide-ranging conversation covering the review questions. This workshop was followed up with a series of 11 individual interviews with 13 CCG and Loughborough University staff. Those present in the workshop or interviewed after it are listed in Annex B of this document. In addition to the workshop and interviews the team reviewed a number of relevant documents (see Section 6 Bibliography for further details) and had further email exchanges with CCG and FCDO staff.
Summary notes from all interviews and from the workshop were provided back to those involved for review and correction. To ensure confidentiality, where appropriate, interviewees were provided the option of identifying any areas of their response they considered particularly sensitive so that the review team could ensure they would not be attributed (directly or bey deduction) in this report.
## Limitations
We were unable to complete two interviews because of travel commitments or illness on behalf of the interviewees. Other than that there were no obstacles to completing this assignment. The Review Team received good cooperation from all CCG and Loughborough University staff involved.
## Structure of report
The remainder of this report consists of four sections as follows:
- Section 2 deals with programme management and contracting
- Section 3 covers staffing and resourcing
- Section 4 reviews current efforts on monitoring, evaluation, and learning
- Section 5 covers decision-making and governance issues
- Section 6 brings together all of the recommendations made in sections 2-5 for ease of reference.
Each of the above sections is divided into subsections dealing with specific review questions from the Terms of Reference for this exercise. The review questions under consideration are listed in italics at the start of each sub section. Recommendations or possible further actions are listed at the end of each subsection.
# Programme management and contracting
2.1	The roles of STEER, the CCG PMU, and Loughborough University’s RIO
2.1.1	STEER
The Centre for Sustainable Transitions: Energy, Environment and Resilience (STEER) is not an entity in its own right but a Loughborough University Senate-approved research collective. It brings together a group of externally funded research programmes around a common theme, that currently includes CCG and MECS (funded by FCDO) and work funded by the Ayrton Fund, UK PACT, the EU, and the UN. CCG and MECS are the largest of these elements.
STEER sits within Loughborough University (LU)’s Department of Geography and Environment which in turn sits within the School of Social Science and Humanities. It was created in 2022 and so post-dates the formation of CCG and MECS. It aligns with LU’s strategy which includes a focus on climate change, net zero and energy.
Judy Billington is the only (non-academic) resource under STEER. Her role is to support knowledge sharing and the exchange of good practice across the research programmes under STEER, to ensure policies are applied consistently across the STEER programmes, and to represent and act as a voice for the STEER programmes to Loughborough University.
2.1.2	RIO and CCG MPU
The Research and Innovation Office (RIO) is a part of LU’s formal structure and a main point of interaction between the institutions of the University and STEER and its research programmes. RIO supports the non-teaching aspects of LU’s operations. That includes pre-award support to academics to develop proposals, contracting, finance management reporting and ensuring funders’ policies are followed, research culture and ethics, a research excellence framework, impact, and commercialisation and IPR.
Within the context of the CCG, RIO’s contracts team has responsibility on behalf of the LU for risk assessment of contracts, any necessary negotiations of a legal nature, and final sign off on behalf of LU. The CCG PMU has responsibility for the process of originating projects (through internal or external calls or other means), negotiating the technical aspects of all contracts and getting them to a stage whether RIO can then review any legal aspects. CCG PMU also has responsibility for managing all non-contractual risks including project risk and due diligence risks.
RIO has three members of staff dedicated to supporting STEER. Two of these support the financial side (both pre-award and post-contract award payments, with the latter including financial reporting for LU, and consolidation of financial reporting for FDCO). The third member of staff supports the contractual side. The CCG PMU is responsible for ensuring consortium partners produce financial reports on time and provides oversight of, and management of, overall budgets, co-ordinating invoicing to FCDO based on consolidated figures from partners. It is also responsible for providing oversight to OIF and the implementation of the projectisation process, the Value for Money framework and the MEL system that supports progress reporting against the logframe KPIs.
2.2	Programme management
Review question: How is CCG’s attempt to projectise the research portfolio developing?
2.2.1	Current situation
CCG has now projectized its work to the extent that there are deliverables identified for every element of every workstream and as well for individual projects under Agile, SPF, FRF and RRF funding mechanisms. Deliverables for each workstream (WS) are based on what is planned to be achieved in the current fiscal year (FY), while deliverables for projects under the flexible funding arrangements relate to the contract periods for those projects. CCG is unable to track progress against budgets at the activity or project level as time sheets are not kept and it is not possible to disaggregate researcher time across projects. For projects under flexible funds however spend against budget is also considered and, for the programme as a whole, the PMU is able to manage budget at the consortium partner department level.
Progress is tracked on the CCG WS Projectisation spreadsheet, which has a separate tab for each WS and also separate tabs for each of the flexible funding mechanisms. Deliverables are listed in detail. Completion status is tracked in terms of % complete for each output (<50%, 50-75%, 75-95%, 100%). Where delays are occurring new estimates of completion dates are provided and there is space for supporting information / explanations to be provided.
Currently the PMU has monthly meetings with each workstream to update the excel template and also the associated risk register. This process is manual and administratively burdensome for the PMU at the moment but there is a move to introduce a software project management tool ‘ClickUp’ that should allow workstream leads to update information themselves as well as also attach important outputs and other key evidence as it is produced. A part time PhD student has been employed to support the workstream leads operationalise ClickUp, which will allow it to be piloted this spring. Full roll out and training will take some time to complete as a process however and it is not expected to be fully functional for CCG until FY 26/27.
There are to be some changes in the CCG structure shortly, with for example a revision to the workstream structure for the programme extension period. ClickUp will be developed to align with this revised structure. ClickUp will also eventually allow resource allocation to be considered (in terms of at least ensuring no one is allocated more than 100% of their time on work and being able to spot resources that are underutilised). There is no intention to track actual spend at the project level however and this will continue to be tracked at the overall consortium partner level.
There is still some work to do to better support planning and tracking of progress on work that spans across multiple workstreams and where key dependencies exist. An example would be work planned on a number of publications around Data to Deal for the next G7 meeting, where progress is dependent on different workstreams completing tasks in a certain order.
2.2.2	Commentary
A review of the latest version of the CCG WS Projectisation 2024_25 Vs 2 Jan 25.xls spreadsheet largely aligned with the PMU’s assessment of progress above. All of the workstreams tabs, together with Agile, FRF and SPF project tabs, had been completed. Work appeared to have been broken down in each case into activities with specified deliverables and start and completion dates. Completion status (%) was provided for all activities / projects. The main variation found between workstreams was the provision or lack of provision of supporting information on progress challenges or reasons for delay, if relevant. Workstreams 2, 3, 4, 5 5a and 7a, together with the FRF all did provide reasonable levels of information on this, while workstreams 1, 5b, 5c, and Agile and SPF projects provided little or no information in this respect. WS 1 seems to have particularly struggled, with generic activities rather than deliverables for all of its country programmes, no information on progress challenges and then a series of additional activities with also no information on completion status.
Interviews with workstream leads on this issue were largely positive. Whilst there was some recognition that identifying outputs and timescales does not always come naturally to academic researchers, 80% of the interviewees suggested the projectisation process was useful as a reporting tool. Comments included:
“…reports are now much shorter, and project information is captured a lot more clearly and easy to reference.”
“Participating in monthly projectisation meetings has worked very well. The frameworks used to collect the information are good. No one like to spend time on administrative exercises, but we all see the necessity of it. It was frustrating when there wasn’t a consistent approach but that has settled down.”
“For workstream 2 projectisation fits as a process. There are clear ‘product lines’ and outputs.
“Spreadsheet approach somewhat effective, allowing project leaders to keep up to date on progress and identify anything impeding delivery.”
“Projectisation will be helpful. It should allow the senior management to identify for example where work is going slow and where underspends are likely md- year and thus reallocate funds to ensure their best use.”
In line with our review of the latest projectisation reporting spreadsheet above, the Country Partnerships workstream (WS1) was the only workstream where feedback provided to the review team included strong reservations on projectisation. Whist the workstream lead agreed with the importance of projectisation individuals within the team who have to implement it felt otherwise:
“this is not suited for purpose and should only be required for the research partners within the consortium. We do not work in terms of projects, but rather the core of the CP workstreams work is to build an ecosystem of partnerships and collaborations and deliver on the country strategy. To say that our work fits into a project is missing the fundamental element of our team which is to be 'adaptive' and 'responsive' that is, to move within the needs of the country. This requires deep stakeholder engagement, and we should feel we have the flexibility to be able to shift to the arising needs and priorities within the country that also aligned to CCG's outcomes and impact….. there is also a great deal of overlap with Qualtrics which causes timewasting extra work ”.
While a degree of flexibility and adaptation will undoubtedly be needed in any planning and reporting system for the country programmes, this will also be needed for the core research programmes, many of which have successfully identified deliverables that would describe the planned intentions for the programme for the 12 months in question. Our experience of reviewing the Laos and Kenya country programmes in detail during phase 1 of the evaluation would suggest it should be possible to identify a series of planned outputs for the year ahead (capacity building objectives, expected outputs from Special Interest Group projects, events, new project proposals to seek funding for, new relationships to establish etc). It may be that WS 1 requires additional assistance to identify the outputs it is already committed to delivering in the year in question that it would be useful to monitor, as well as ways of describing in general terms what might be expected to emerge from the application of response and adaptive approaches during the year (this could be as simple as a deliverable that was phrased along the lines of: ‘as a result of demand led approach during the year we expect to have developed at least x new relationships, funding proposals, or other initiatives as yet unforeseen’).
The use of ClickUp came up only a few times in interviews. In the majority of the cases the sentiment was cautiously optimistic:
“Move to ClickUp could be good if it is a bit more structured and less error prone…. [than the spreadsheet approach] …and easier for FCDO to extract information from.”
“The Click up system seems to work pretty well.”
“With the introduction of ClickUp one concern has been to avoid duplication. During the first iteration of Click Up it was treated as an interesting management tool that CCG should try to fit its management information into. In the current second phase there is a more determined effort to align the ClickUp architecture with the projectisation reporting sheet to make things work in a streamlined manner.”
In one case however there was a concern expressed that CCG might be moving to a system that wouldn’t be used often enough by the data inputters to develop the familiarisation needed to make it an efficient tool to use:
“Although the current spreadsheet-based reporting would be phased out if ClickUp is widely adopted there are still some additional time costs associated with adopting ClickUp. It is a different tool which requires familiarisation. If it was being used every day this would not be such a problem, but given ClickUp is likely to be only used once a quarter for reporting, there could be problems with people not becoming really used to using the system and having to spend time every quarter ‘relearning’ how to use the software to input data”.
2.2.3	Recommendations
CCG should continue with its current efforts to further embed its projectisation process. The move to ClickUp should continue but with careful review as rolled out to ensure the adoption workstreams, as the data inputters, is as easy as possible and that CCG’s systems as a whole only require data to be inputted once.
CCG should consider providing additional support and guidance to workstreams 1, 5b, 5c, and to holders of Agile and SPF projects to bring the quality of their projectisation reporting up to that of the other workstreams.
2.3	CCG reporting to FCDO
Review question: How can CCG be more effective at providing timely programme management information, including payment requests and financial forecasting information? What is the cause of current delays to payment requests and financial forecasting and how can this be mitigated? Do downstream suppliers allocate sufficient contracting and project management resources in support of the central team?
2.3.1	Current situation
The CCG reporting year runs from April to March. Progress on outputs and outcomes are provided through three quarterly reports and a more extensive annual report, submitted less than two months after the completion of the quarter or year. Invoices are submitted quarterly and accompanied by a financial report compiled by LU’s RIO. Responsibility for payments and financial reporting is held by a dedicated staff member within RIO. The CCG PMU is responsible for ensuring consortium partners produce financial reports on time, provide oversight, and manage overall budgets.
According to the PMU, there have been few issues with quarterly or annual progress reports, but some with financial reporting. While quarterly progress reporting had been delayed in the past, this has been timely during 2024-25. One issue related to progress reporting has been the timeliness of the annual report, which CCG has struggled to provide in advance of the annual review process. This year the annual review has been rescheduled to June, which should hopefully alleviate this issue.
Financial reporting to FCDO is dependent on timely receipt of financial reports from consortium partners, which has been an on-going issue. Table 1 provides an analysis of when consortium partner invoices were due and when they were actually received for the last four completed quarters at the time of producing this report. The largest delays were caused by UCL and Imperial Colleges in the last quarter of year 4 (2 months) and Imperial and Oxford in quarter 1 of the current year (3 months). Imperial is the worst performer over the 12-month period reviewed, submitting invoices significantly late in three out of the four quarters. However, beyond this there is no real distinguishable pattern across the 12-month period as a whole, with only four of the nine partners consistently submitting invoices on time. Also, the situation doesn’t seem to be heading in a particular direction – although quarter 2 reporting was a significant improvement over quarter 1 for this year, quarter 3 represented a deterioration on quarter 2 again.
Table 1: Analysis of partner invoice due dates and actual invoice dates for last four quarters.

CCG has taken steps to address these issues. It has been agreed with FCDO that two quarterly invoices can be sent, the first being within the planned quarterly timeframe and the second to cover any remaining consortium partner invoices which have been submitted late. CCG has also instigated quarterly consortium partner meetings to discuss any delays and over / under spends and has issued standard financial reporting packs for partners to use to improve consistency of reporting, although as noted above this does not yet seem to have resulted in a definite trend towards more consistent timely invoice submission.
2.3.2	Recommendation
If the above initiatives are not yet sufficient to meet FCDO and / or CCG Management’s need for timely financial reporting, then we would recommend consideration of one or both of the following options:
Require consortium partners that regularly exceed invoice due dates by significant margins to invoice monthly rather than quarterly, to reduce the level of uncertainty around actual spend.
and / or
Require those consortium partners to use a portion of their assigned grant to cover the cost of additional finance and administrative support in their institutions to enable faster processing and more timely submission.

2.4	Contracting partners
Review questions:
Does Loughborough University allocate sufficient resources to provide effective contracting for CCG, including on behalf of the Flexible Research and Southern Researchers Funds and the new Engagement Fund?
What are the implications for responsive/agile research (including FRF, SRF and Engagement Fund) given all CCG consortium research must be contracted through Loughborough University?
What challenges does CCG face in contracting institutions based in the Global South? Does CCG have adequate approaches and systems in place to mitigate these challenges?
2.4.1	Current situation
Contracting partners in the global south will often produce complications, not least because such organisations may not be familiar with actions required to meet all the requirements of standard due diligence processes (for example having adequate levels of indemnity insurance). Resolving these issues may take time. However, for the most recent round of the FRF call, the time between funding decision and finalisation of contracts averaged between two and three months, which is not an unreasonable length of time. For the most recent SPF call, project revisions were finalised within two months in all cases, though some projects appear to have been delayed but up to an additional 4 months, though it is not clear whether this was related to logistical or contractual issues.
Feedback from interviewees suggests that some challenges with international contracting are likely inevitable. Workstream leads have asserted that lessons are being learned in this process and steady improvements in the contracting process are being realised.
More specific challenges have arisen in signing MOUs with some international organisations. Most of these do not involve funding and we understand from Vivien Foster that most the anticipated agreements need for the International Partnerships workstream are now in place. There was a specific problem with an agreement with ICTP, a subsidiary of UNESCO, where CCG is funding a staff placement. ICTP insisted on a form of MOU / letter of contribution where LU would have normally required a formal and enforceable contract because funding was involved. Approving this required engagement with the LU Finance Director to accept what was for LU, a non-standard agreement. The letter of contribution under this particular MoU will require annual renewal because of FCDO budget cycle issues but has been renewed recently with only minor delays. The current view of the RIO is that the experience gained from these instances will allow for future contracting to proceed more smoothly, as evidenced by a much shorter processing time for the ICTP extension mentioned above.
2.4.2	Recommendation
No recommendation
2.5	Added value of STEER
Review question: Does CCG benefit from scale associated with being housed in STEER alongside MECS? Are there shared administrative functions that allow greater value for money?
2.5.1	Current situation
Grouping programmes together under STEER doesn’t really produce any economies of scale in terms of cost savings through the sharing of resources. But it does have significant advantages in making operating what are non-standard projects (for a Higher Education Institute) easier within the LU environs. For example:
- CCG was able to adopt safeguarding and due diligence procedures developed under MECS and already agreed with FCDO, rather than have to develop its own from scratch. Also CCG has identified that the ‘break clause’ wording used in FCDO’s contract with LU for MECS causes fewer issues with LU than the wording used in the contract for CCG and is now in the process of negotiating a change in the CCG contract to make the most of this learning.
- Grouping programmes together under STEER provides weight to a voice to argue for adaptation of LU policies and procedures to cope with ‘non-standard’ projects that don’t fit easily in to university procedures. The fact that LU has adapted processes, sometimes quite quickly and at short notice, to accommodate STEER programmes is evidence that this approach has worked and that it is beneficial to the operation of individual STEER programmes.
While the advantages that STEER brings are real, it is recognised that LU still has a way to go to move towards a ‘research as a business’ approach that would allow it to move quickly to take advantage of  new opportunities to build a portfolio of work in this area. This would require changes across the board from employment and contracting procedures through to risk appetite. There is some movement towards a more business approach in the university, but the pace of change is characterised by the CCG team as ‘slow-burn.’
A positive to note is that LU wants to host programmes such as CCG and that the experience of working with CCG and other STEER programmes is seen very much as part of a learning process for the University on how to do this. It is also noted that the RIO team go out of their way to provide fast and constructive support to STEER and to do their best to make the current system supportive of the STEER programmes’ needs.
2.5.2	Recommendation
No recommendation.
2.6	Operational Intelligence Framework
Review question: What is the role of the OIF, how has this evolved and how is the OIF expected to this develop in future? Are the functions of the OIF likely to be absorbed by mainstream management processes, and if so, how will this be formalised?
2.6.1	Current situation
Now that William Blyth has moved on from the OIF to other operational activities within CCG, OIF is now essentially a single person – Ligia Zagato, with Peter Rooney from the PMU providing some additional support and acting as a stand-in for Ligia when she is away from post (although the organisational chart in the latest version of the CCG Project Manual shows an additional OIF position “to be confirmed”). William wore both a CCG and a FCDO hat and while in post this meant the OIF, to an extent, looked in both directions. With the departure of William and the strengthening of the PMU with the arrival of Romana Rauf, the OIF now seems to be more fully embedded in CCG’s mainstream management, with Ligia now reporting directly to Romana rather than to the CCG Director or Partnership Director as in the past.
A major function of OIF is the quality assurance of reporting on logframe outputs and outcomes and the compilation of that material for quarterly reporting to FCDO. Each CCG partner collects data on outputs monthly directly through the online Qualtrics platform (a survey maker solution used in business and academia). After each workstream uploads their outputs to the Qualtrics platform, the PMU (senior and junior staff members) conducts two rounds of internal review. After this is completed final quality assurance checks are done by OIF include reviewing the results held in the platform, checking for duplicates, and cross-checking the evidence included against the information entered to avoid claims of outputs that are not connected to CCG (e.g. if a publication included does not include any acknowledgement to CCG). Data on outcomes is now collected quarterly rather than at the end of the year as before, which helps avoid an end of year rush for data. Outcomes are not reported through Qualtrics. There is a protocol in place to help define outcome indicators, their requirements, and the necessary internal processes to verify results and a methodology for triangulation, with OIF taking on selective deep dives as part of a verification process. OIF presents progress on outputs and outcomes twice yearly to the CCG team in its General Meetings. OIF’s taking on of quality assurance of outcome and output reporting has taken some pressure off the PMU in terms of MEL, although they still have a significant workload in reviewing key documents and reports and drafting the quarterly progress reports to FCDO. More information about the MEL system is available in section 4 of this report.
OIF takes on some additional ad hoc tasks related to reporting. For example, FCDO said it wanted to track overall citations from CCG and so OIF is now working with KTH to see if they can develop a bot to automate some of the existing work with Google scholar to make that easier to do.
With respect to flexible funding calls (Agile, FRF, SPF and Engagement Fund) OIF’s role is similar to that it has always been. Before calls go out OIF reviews them from a thematic viewpoint to ensure the calls make sense from a CCG perspective. After the call closes OIF and the assessment board reviews and scores proposals, OIF conducts a quality control exercise to ensure the scoring process was done correctly and properly documented. At the point of final selection OIF checks to make sure the overall balance of approved proposals makes sense (for example the panel will select the best scoring projects, but CCG may also need to consider things like geographical spread etc). The PMU (specifically Peter Rooney) then does the on-going oversight process in terms of formally checking grantees are making progress against objectives (in addition to any oversight provided by the relevant workstream lead). More broadly OIF continuously monitors the calls process to identify where things could be improved in future calls.
The work OIF originally did around conceptualising how CCG’s activities could be projectized in order to better track progress against objectives has been further developed and mainstreamed into annual planning and monthly reporting processes under the PMU.
Overall, as noted above, OIF now focuses on quality assurance processes both for output and outcome KPI data and for flexible funding calls. Institutionally it sits within the wider PMU function and reports to the Head of Programme Portfolio.
2.6.2	Recommendation
No specific recommendations. We raise the possible need for additional staff resource to support OIF’s MEL responsibilities in section 4.
# Staffing and resourcing
3.1	PMU staffing
Review question: Is the PMU appropriately staffed/resourced? Are there capacity bottlenecks in the programme management or administrative structures and how might these be mitigated? How might CCG more formally/effectively monitor and forecast programme/project management and administrative burden? How can this inform mitigation?
3.1.1	Current situation
There is an underlying base load of work for PMU that is foreseeable and can be planned for, including monthly check-ins with workstreams, the data collection, review and report writing requirements of the quarterly and annual report production, and implementing the response to recommendations from the previous year’s annual review (and, currently, the phase 1 evaluation). There are additional semi-foreseeable peak loads around contracting of any new FRF, SPF, Engagement Fund or agile fund arrangements (the timing of which may be dependent on the time it takes to complete proposal reviews, due diligence etc) and annual re-contracting of staff and consortium partners (the timing of which is dependent on when FCDO can confirm a figure for the annual budget), all of which has to be carried out in collaboration with Loughborough University’s RIO. Finaly, according to PMU, there are ad hoc demands, mostly from FCDO and usually in the form of requests for specific data and analysis that is not part of normal reporting, often with short deadlines, in response to an internal FCDO demand for information.
Both PMU and RIO confirmed that the additional administrative burden of having to re-contract all staff, all consortium partners, and any flexible funding contract that extends over two fiscal years because of the FCDO budget cycle constraint discussed in 3.2 below is significant and we would conclude that it should not be underestimated.
CCG was funding two positions within RIO – a finance position and a contracts support position. According to our discussions with RIO there are advantages for CCG in having support capacity embedded in RIO rather than all support being in its own PMU. This should be particularly true in terms of managing the peaks and troughs of workload associated with CCG calls for proposals under the SPF, FRF, Agile and other call arrangements. RIO has a staff of around 100, which means they should be able to be called on to help with spikes in workload. In practice however, the PMU reports that these RIO positions were not ring fenced for STEER and that CCG work requirements were in competition with demands from other areas of LU. CCG therefore renegotiated the arrangement with the previous Head of RIO. As a result, CCG will withdraw that funding from April 2025 onwards and RIO will cover the costs of those two positions (which it should be able to do from the overhead changes it gets from CCG covering the costs of the deputy programme director of CCG and two research assistants). PMU has now added a grants manager to its own staffing. RIO confirmed in an interview that it intended to maintain its two support positions in line with the revised agreement and that the overhead it could reclaim from the CCG agreement with FCDO should be sufficient to cover costs. This new arrangement is still bedding in and one of the RIO posts has to be re-recruited (as the former post-holder moved to take up the PMU grants manager position), so it is early to say whether it is working as intended or not.
Based on the discussions held at the Loughborough University workshop it would appear that the main PMU / RIO capacity constraint comes when there are conflicting demands occasioned by multiple scheduled and unscheduled activities coinciding. Examples would be when a large number of grant releases are scheduled at the same time as a quarterly report or clash with an unexpected demand for information from FCDO. In the current year (FY24/25) this sort of delay occurred with the FRF process because of lack of staff resources within the PMU. Recruitment took place in the summer and the process was only able to move forward after that (meaning funding is only now being released in February / March for this year’s FRF work, which in turn pushes up against the annual re-contracting process occasioned by the budget cycle constraints).
Historically, budget restrictions, and decisions in such circumstances to prioritise research activities over management, have meant that staffing levels within the PMU have been a real limitation in the past. The programme has only had a full complement of staff (with respect to what was envisaged under the original £38m budget) over the last 6 months. This has already had a significant impact on the PMU’s ability to implement processes at speed. Interviews with workstream leads. The CCG Deputy Director confirmed that the arrival of the Operations Director Romana and the establishment of the PMU had made a significant difference to CCG’s ability to manage administrative and managerial workloads and that the summer recruitments had improved things further. Given that the CCG budget passing through LU has now increased to around £91m and annual turnover this year is double that of prior years, there are still additional posts within the PMU that need to be filled to ensure its capacity is aligned with the current scale of the programme. There have been some delays in confirming the CCG budget for the next FY which have in turn delayed recruitment to fill these posts, meaning the PMU is still having to act without a full complement of staff, recognising that it is in a much better position than 6 months ago.
We note also in section 4.1.1 below that an additional PMU staff member to supplement OIF’s capacity on monitoring, evaluation and learning would be highly desirable.
3.1.2	Recommendation:
Given the above we would recommend that CCG does proceed with recruitment of the remaining unfilled posts in the current staffing plan in order to be adequately resourced, together with the support from RIO, to manage peak workloads and to be able to ensure the monitoring, evaluation and learning function is fully supported
3.2	Budget cycle risk
Review question: How does the perception of budget cycle risk, and the necessity of break-clause implementation in contracts, impact on contracting and project management? How could this be better managed?
3.2.1	Issue:
This is still perceived as a significant risk by the vast majority of workstream leads and PMU staff interviewed. There appears to be three elements to the issue:
FCDO’s inability in recent years, as a result of uncertainties across Government, to be able to confirm budgets for consortium partners for more than 12 months at a time. This creates uncertainties for the consortium universities (see below) but also some practical problems. For example, some universities will not take on PhD students (used on CCG as researchers by some partners) without 3 years’ funding being secured. Employment contracts for most non-permanent staff working on CCG will be linked to guaranteed funds and in these circumstances can only be issued for 1 year at a time (and often less because of (3) below). This then has the additional disadvantage of making recruiting researchers more difficult in the first place, as they may prefer to go for positions that offer a least a couple of years of security.
Limiting funding assurance to 12 months also creates additional administrative work as consortium partners’ contracts and the vast majority of CCG staff contracts across the consortium, and any flexible funding contracts (FRF, SRF agile etc) that span more than one fiscal year, all have to be reissued each year for a further 12 months, creating a bulge of otherwise unnecessary contract work at the start of each fiscal year.
FCDO’s often late confirmation of the budget for the coming fiscal year. In the current budget cycle, an indicator of the minimum budget figure for CCG for FY25/26 was provided by FCDO on 24th November 2024 and communicated to consortium partners as their respective minimum budgets for FY 25/26 in December 2024. FCDO then confirmed a final budget figure for FY 25/26 for CCG on 12th February 2025. The difference between the two figures was around £1.2m or 10% of the annual budget, so not insignificant in planning terms.
Consortium partners have different levels of risk appetite and so may make decisions at different points in the budget cycle concerning the following fiscal year. Based on interviews it appears that some partners might take sufficient comfort from the November minimum FCDO budget figure to at least renew existing non-permanent staff contracts. Others appear to only renew those staff contracts once the CCG budget for the coming year is confirmed by FCDO (24th February 2025 in this year’s example). According to the PMU most will wait until their contract variation letter is signed by both parties before committing to any new staff required for projects for the year (delaying the start of recruitment).
This process can cause significant stress to staff – the PMU staff based at Loughborough University were all issued contract termination notices just before Christmas 2024, as were staff at some partner institutions, based on the absence of a confirmed budget for FY 25/26 from FCDO and in line with those Universities’ policy to provide 3 months’ notice to anyone having their employment contract terminated. Although these contracts were subsequently reinstated, one partner reported the loss of two team members who applied for other jobs because of the insecurity surrounding the CCG posts.
Further delays with CCG consortium partners completing the necessary tasks before letters of amendment to consortium partners’ contracts can be finalised. The unsigned FCDO amended grant agreement was provided to CCG on the 24th of February this year and is currently with Loughborough University for review and signing, after which it will be returned to FCDO for counter signature. The PMU estimates this will take until the end of March or early April to complete (five – six weeks). Loughborough University maintains it cannot issue any grant payments to partners before the variation of contract agreement has been signed by all nine consortium partners, which is in turn dependent on all consortium partners confirming their annual budgets and outputs for the new fiscal year. This usually causes further delays, as some partners take a lot longer that others to complete these tasks. The PMU is anticipating it taking more than 4 weeks this year.
Given the above, grant funding may not be available to partners until mid-May at the earliest. This has the largest potential impact on the two partners who are paid in advance (as much of their funding is passed through to Southern partners who cannot pre-finance CCG’s work). Last year, as an exception, CCG persuaded LU to issue an advance payment to CGE (but not Climate Parliament) in advance of the remaining consortium partners signing their annual letters of variation. Last year however CGE still had to pre-finance its work for 2 – 3 months before Loughborough University then agreed to release funds in advance of releasing to other partners. This will become increasingly challenging for CGE as the programme grows, as CGE doesn’t have the cash flow to cover a larger funding gap itself.
We understand that CCG has been working with FCDO to remove an annual break clause in its AGA agreement and to align the wording of the agreement with a similar clause in the MECS agreement, that does not have a break clause but does have a 3-month notice period should cuts in FCDO agreed budgets be required. This is expected to be sufficient for Loughborough University to continue staff contracts beyond fiscal year ends in future years, although that will only be tested in practice towards the end of FY 25/26. Email exchanges with the PMU suggest that this change may not be sufficient to provide assurance to the more risk-averse consortium partners, who will then still wait for formal confirmation of annual budgets before extending the contracts of non-permanent staff reliant on CCG funding.
In the absence of a confirmed multi-year budget, we understand that consortium partner annual contracting and re-contracting of FRF, SPF and other grants that cross fiscal years will still be necessary.
3.2.2	Possible courses of action:
In descending order of impact, actions that would mitigate or partially mitigate this risk would be:
1. FCDO provide multi-year confirmed budget figures. This would fully mitigate the risk, but in the current circumstances of UK Government imposed development assistance budget cuts may be difficult to be achieve.
2. FCDO provide earlier confirmation of the budget figure for the following fiscal year. Confirming the budget figure before December each year should provide adequate time for CCG consortium partners to finalise plans and budgets in advance of the new fiscal year starting. Confirming a budget figure at least 3 months in advance of the fiscal year should also avoid the issue of staff termination notices being issued.
3. FCDO and CCG confirm agreement of proposed change in the wording of the AGA, with the replacement of the break clause with a requirement for FCDO to provide 3 months’ notice of funding reductions. This would reduce the staffing risk, at least for Loughborough, but would not resolve all issues.
4. FCDO and CCG reduce the time it takes to sign the amended grant agreement; the current estimated five to six weeks seems like a very extended timescale to complete what should be a straight forward amendment with no changes to terms and conditions beyond confirmation of the budget figure for the year.
5. CCG consortium members to do more to planning on the basis of the minimum budget figure provided in December, perhaps with scenarios to cover a 5 or 10% uplift if it occurs when the final figure is issued in February, to avoid delays caused by consortium partners being late in submitting their budgets and planned outputs for the new fiscal year.
# Monitoring, evaluation and learning
4.1	MEL Strategy
Review Question: With reference to CCG’s developing MEL strategy: What is CCG’s programme-wide approach to Monitoring, Evaluation and Learning, how can MEL be institutionalised within the programme, and is continual MEL appropriately incentivised/resourced?
4.1.1	Current situation
The Monitoring and Evaluation Framework states its purpose to be to support accountability, foster continuous learning and improve programme effectiveness. It aims to do so by ensuring the achievement of six objectives: i) planning biannual targets, ii) continuous monitoring to inform changes, iii) monitoring progress and performance towards achieving outputs and outcomes, iv) analysing and reporting, v) evaluating and vi) promoting continuous learning. The approach, as stated, is pragmatic and focused on agreed logframe indicators, using their targets as parameters for reflection.
Under monitoring, the current logframe indicators are seen by CCG as good enough to measure significant progress at a programme level. CCG management confirms that logframe, and associated targets are annually updated in collaboration with the (OIF) unit, “a process that involves deep reflection on programme performance”. Data flows continuously from workstreams to a centralised data repository (supported by the survey software Qualtrics and reviewed on a monthly basis), and data is then quality assured centrally with outcome indicators requiring further checks before being incorporated in reporting. Biannual targets help to monitor progress in preparation for annual reports. In addition, feedback from participants in capacity building support activities are captured in event reports. Quarterly and annual reporting helps compile results and should support adaptive management and there are quarterly workshops with CCG Management and FCDO to review programme targets and progress to ensure continued alignment with strategic objectives. With the projectisation process, monthly meetings help track the workstream's progress, with results captured in an Excel sheet, which is planned to be replaced by ClickUp in the current year.
[note] Response from CCG management to first draft of this report
[note] ibid
Evaluation is done externally to test assumptions and understand the programme results at the impact level. The Country Partnership strategies support specific contextual insights. Learnings and recommendations are seen as means to support programme adaptation. The programme sets a continuous cycle with biannual reviews planned so that reflections on the programme results can be discussed in light of the milestones committed to, providing justification and a plan to solve issues encountered. While the programme has taken seriously external recommendations from recent independent evaluation, documenting a formal response showing how plans and approaches have changed as a result, reflections and responses to the findings of the monitoring system are not currently recorded at latest general meeting.
4.1.2	Ways in which to institutionalise and ensure continual MEL is appropriately incentivised and resourced
This review confirmed that there is an operational MEL system in place that fulfils most of its functions. It may be strengthened by ensuring key documents are adequately finalised and through a participatory process, creating opportunities for feedback loops to provide insightful results analysis. This may ensure greater commitment to using the results and analysis more continuously. In order to provide specific recommendations on how MEL work can be appropriately resourced, incentivised and institutionalised, the CCG MEL system was reviewed against the following dimensions: 1) Resources and Capacity, 2) Strategies, frameworks and Plans, 3) Data Collection and quality reviews 4) Analysis and use.
#### Resources and capacity:
The evidence reviewed indicates that the MEL team may require further formal support or greater capacity. Essentially, OIF has only one person to exercise all the required tasks under MEL, which include verifying results, quality-checking them, analysing, reporting, and supporting learning. In practice, more than 1000 records of outputs were entered in the last financial year, requiring efforts to verify these results, manage the database and proceed with quality checks, which is time-consuming. It may be ambitious to expect that one member of staff would be able to quality assure more than one thousand data entries in detail together with other competing priorities. Good practice also shows that more than one person in the M&E team should be trained and able to retrieve data in the databases and proceed with the analysis when required. Outcome-level results, in particular, require significant time for verification. In addition, key strategic documents require continuous updates. Currently, to respond to the usual demand and requirements, the MEL team counts on the support of an intern who joins temporarily to support the first round of verification of the results reported. Following the document review and the interview with OIF, it is clear that there is a need to formalise this extra support received for data quality checks as a permanent role within the M&E team so that it does not lack the capacity to deliver on the other parts of its functions.
#### Strategies, frameworks, and Plans:
The M&E strategy, which is currently under review, should be developed in more detail to ensure greater clarity and to keep an institutional memory. For example, it does not capture how the M&E function is delivered within the team (showing individual’s roles and responsibilities), nor how the CCG team contributes to the M&E system, the roles of the individuals responsible, what is expected from them, how data flows and how it is kept or used for analysis. Having a detailed plan will also ensure that the recently introduced GESI indicators have adequate plans for reporting. Given that CCG is a long-term programme, and indicators may, and have already, changed along the way, it is important to keep a written document that details how the M&E function is delivered, how each indicator is to be reported, criteria for the analysis, data sources, individuals responsible, and other key information so that the team is clear on how it is assessed, and the plans cover all indicators as well as the processes involved.
#### Data Collection and Quality Reviews:
Data collection at a programme level is seen as a smooth process. Using Qualtrics ensures an efficient and consistent way to collect data from the different programme parts. Documents available for review have not, however, covered how historical data is stored and do not provide details on the quality assurance processes in place, although as noted above, there is evidence that these processes are being implemented. While quality assurance checks are being carried out, the frequency and the depth of these checks are not well recorded. In order for MEL to be adequately institutionalised it is important to keep a written record that identifies the datasets and evidence that are kept through the system, ensuring they are located in a safe space, explaining the processes carried out, including a log that confirms when these processes have been undertaken, by whom, and their results.
In addition, this review identified a challenge for capturing outcome-level results related to public goods such as learning materials and modelling summer schools. While the programme is very attentive to not overclaiming results, it currently does not have processes supporting identifying new outcomes when the results are more indirect. The CCG programme could benefit from introducing more feedback loops with support recipients in those instances. Even short surveys on an annual basis can be an opportunity for the stakeholders to share their perceptions about the use of knowledge gained, as well as help identify blockers or possible incentives or opportunities for the outputs to be implemented. In this context, the WS2 has identified a way to track outcomes related to modelling trainees by developing and making use of an alumni network, which seems to be a useful route that the programme can replicate. Key information collected through these channels can be useful for the programme not only to identify possible new outcomes but also to adapt in response to challenges and opportunities identified through these networks.
#### Analysis and use:
Learning is considered a priority for improving programme effectiveness, which is one of the purposes of the M&E Framework. However, some challenges exist to ensuring that monitoring data is being used. Currently, no workstream lead interviewed was able to recall an occasion in which they have used monitoring data to inform their decision. While there are opportunities for reviewing results (on a monthly basis at the workstream level and biannually at a programme level), as noted above, there appears to be no written record of the results of these reflections at a programme-level, showing how the programme adapted in response. In the substantial annual report produced by CCG the situation is similar, with results presented and not followed by any reflection on whether or not they have achieved their targets and or the action to be taken in response. While keeping a written record of these reflections is a good practice, the challenge here is also on how to use these spaces so to enable useful discussions. We recommend that the programme reflect on how MEL data can be collected, analysed, and displayed to support decision-making in these occasions. It looks like the projectisation process is already going in the right direction. Here we suggest some areas for further investigation within the team:
- Reflections on performance are not adequately/directly dealt with or noted in instances where this would be expected. For example, the general meeting report of 2024, and the CCG annual report 23-24 currently do not address reasons for under or over performance of indicators and do not capture any action or needs for adaptation in response (although this is addressed to an extent in FCDO’s annual review). We would suggest more active use of MEL quarterly data to facilitate reflection on actions to address issues such as underperformance or course changes required during the year and for the results of these discussions to be recorded. Some of the lessons may be used by different workstreams, countries, or programmes, and keeping a record of them will help institutionalise knowledge produced internally and may even support improving the setting up of future targets.
- Internal reporting can also benefit from more dynamic tools or ways to display the results to support greater engagement, such as dashboards. More thinking about how it would look would be needed. Ideally, the participation of the workstream leads to defining how a more iterative reporting could look and how they could benefit from it. It could be a positive way to move forward with this suggestion. However, we understand there may also be costs and resource implications to be considered.
4.1.3	Recommendations
We conclude that OIF would benefit from an additional post so that the team has enough capacity to operationalise the different components, including learning to support reflection on what works, what is not working and why, to better support programme improvement.
A more detailed written document should be produced to clarify how each MEL indicator is to be reported, the criteria for the analysis, data sources, individual responsible, and other key information so that the team is clear on how each indicator is assessed, and institutional memory is preserved.
To ensure MEL data security and retrievability there should be a written record that identifies what datasets and evidence are collected and stored, informing their location, and any regular processes that need to be carried out (e.g. cleaning and removing duplicates) are kept through the system, ensuring they are located in a safe space. This should be accompanied by a log that confirms when these processes have been undertaken, by whom, and their results
CCG should consider introducing more feedback loops with programme counterparts or targeted recipients of the work delivered to capture new outcome-level results obtained, especially in the area of use of public goods provided by CCG. Short surveys implemented through the recently established modelling alumnae channels, for example, could provide an excellent opportunity for external stakeholders to share information on not only possible outcomes achieved but also help identifying blockers or incentives that could enable future uptake.
CCG should more actively use MEL quarterly data to facilitate not just discussion on what has been achieved to date, but as an opportunity to reflect on and agree actions required to address issues such as underperformance or course changes or reallocation of budget to ensure full utilisation and avoid underspend over the year ahead. These discussions should be recorded in a report for future reference and review of progress on actions agreed. The mid-year general meeting would be a particularly useful time to do this.
CCG should also consider developing more dynamic tools or ways to display the outputs from the MEL system (such as dashboards) to support greater engagement on and discussion of results during those review instances.
4.2	Monitoring of risk
Review question: Does CCG have an effective internal process for recording, monitoring, and escalating risks?
4.2.1	Current situation
CCG has an Enhanced Risk Management Strategy (ERMS) which details the process for recording, monitoring and escalating risks. It aims to describe how the strategy is to be implemented amid staffing constraints, highlighting the roles of key personnel, and includes the quarterly risk review processes involving WS leads and management team. This document is in a draft format, and we would suggest finalizing it, while ensuring greater consistency on the risks managed across the workstreams’ risk registers, and ensuring the reviews planned are effectively taking place on a continuous basis.
For identifying risks: CCG has a system for identifying and managing risks that involves regular reviews every three months. Key people evaluate risks determining their likelihood and potential impact. New risks are to be logged immediately, and updates shared with the leadership team, with urgent risks reported sooner. If more resources are needed to address a risk, there is a process for acquiring more funds.
For monitoring and reporting risks: There is a risk register at a programme level which is reviewed on a quarterly basis and that combines the risk registers at the workstream level. The risk register is in a standard Excel format capturing key information required (type of risk with their description, likelihood and impact of the inherent risk, mitigation actions, residual risk, risk manager and owner). In addition to these reviews, risk managers are asked to promptly notify the CCG Program Office about any risks requiring escalation.
Interviews with workstream leads suggested that risk registers were indeed in place at the workstream level and reviewed and reported on quarterly. One interviewee mentioned that regular bi-monthly meetings with the management team that included reviews of their risk register were no longer happening (but that the register still existed). However, when reviewing the risk registers we noted that the date of the latest reviews vary significantly between the different workstreams, which may indicate the need for a more standardized approach to be applied across the different parts of the programme.
4.2.2	Recommendations
The analysis of levels of risk in the programme and individual workstream risk registers could be improved to bring it into line with best practice. Two changes we would suggest would be to include additional columns to show what the combination of the likelihood and impact score risk is for both inherent and residual risks, and then also, for residual risk to also have a column that shows FCDO / CCG’s agreed consolidated risk appetite (likelihood and impact combined) for each risk. The traffic light system used is not sufficient alone to do this as it does not allow for the fact that risk appetite could and should be different for different types of risk. A research and innovation programme would be expected, by its nature, to have some areas where it is prepared to take higher risks in order to innovate, but this is not obvious in the register at the moment.
 While the programme level risk register seems very comprehensive (or possibly over detailed - see below), the risks captured at the workstream level vary significantly in their level of depth, even across workstreams that would be expected to have similar risk profiles. For example, in the risk framework shared with us workstreams 3a, 5a and 5b only recorded 3 risks each, while workstream 5c recorded 46. A more uniform depth of analysis across workstreams with similar likely risk profiles would be desirable.
[note] The risk register shared was undated but likely to be December 2024 given the latest ‘review date’ recorded in all the registers
The programme level risk framework could be consolidated further. There is duplication within the risks listed (fraud is referenced at least four times and could be consolidated into a single risk) and there are also risks that may no longer relevant and could be dropped (e.g. COVID resurgence).
Finally, the programme level risk framework is notable in that it only contains generic risks. There is nothing that is a specific and live risk that suggests the senior management team is actively identifying and managing current risks that are an issue at a programmatic level. From this review alone, for example, if the sample risk register we were shown was indeed December 2024 then live risks that might justifiably been on the register to actively manage would have included the lack of a final confirmed budget figure for FY25/26 (which had resulted in some CCG staff receiving termination notices), continued staffing gaps in the PMU leading to challenges at peak contracting workloads, and problems with Loughborough University allocating sufficient time from RIO staff time. Normally a programme level risk matrix would also include risks from lower down in the organisation that were significant enough to merit the attention of the senior management team, at least until they were mitigated to the extent that they could then be managed by, in this case, the relevant workstream where they would otherwise sit. It seems unlikely that in a programme the size of CCG there are no specific live risks of this nature that need active management at senior management team level
4.3	Monitoring of VfM
Review question: To what extent has CCG been able to adapt and contextualise a Value for Money framework that is useful for both programme management and reporting?
4.3.1	Application of framework to date
An updated version of the VFM framework developed during the Phase 1 evaluation was applied and reported on in the FCDO Annual Review for FY 24/25. The programme was unable to provide evidence on the balanced portfolio element of the efficiency criterion as CCG was awarded additional budget during the year but did not adjust the ‘balanced portfolio’ benchmarks to account for this (an adjustment that CCG and FCDO have committed to make if in-year budget adjustments occur again in the future). The programme was however able to assess efficiency in delivery, which is the other efficiency criterion in the framework. Other than this, the framework seems to have been applied successfully in that evidence-based VFM scores were arrived at for economy, efficiency, effectiveness, and equity, although no effort was made to combine these into an overall VFM score for the year.
While the application of the VFM framework in the last annual review is encouraging, the framework document appears to be contentious within CCG and is still in draft form, with discussions around it on-going more than a year since it was first drafted. During the workshop held for this review at Loughborough University the sense was that the PMU recognised having a way of reporting on VFM was important for FCDO’s oversight of the programme, but that the original framework was ‘not fit for purpose, nor that much use to management’.
4.3.2	Changes to original proposed standards
Having had the above discussion with the PMU and having reviewed the current draft of the framework we would suggest that it might be helpful to review what the purpose of this sort of VFM framework is. The framework is evaluative and is designed to be retrospectively applied, typically on an annual basis, to assess actual VFM achieved against a predetermined set of criteria and standards of what, in this case, FCDO and CCG agree represents poor, adequate, good, or excellent performance. Looking at the current draft of the framework we would suggest it is worth considering again what the generic description of those fours levels of performance would look like. The description generally used by OPM (and used in this case while working with CCG to develop the original draft) is shown in Table 2.
Table 2: Generic standards of performance
Excellent	Good	Adequate	Poor
Exceeding reasonable expectations given the context / Room for incremental improvements	Meeting reasonable expectations given the context / Scope for some improvements	Fulfilling minimum requirements / Significant improvements required	Not fulfilling minimum requirements / Urgent improvements required

In the current version of the framework, it appears that some of the original standards agreed have been lowered to the extent that they would no longer appear to really align with the above descriptions. For example:
- Under ‘efficiency’ the standard for assessing whether a project’s delivery its intended outputs, meets an ‘excellent’ performance standard is now that “All project deliverables nearly (>90%) achieved”, whereas the original standard was that the output targets would have to be exceeded. We would suggest that delivering 10% under the planned objectives of a project aligns better with a standard of meeting reasonable expectations given the context (i.e. good) rather than exceeding reasonable expectation (excellent).
- Likewise where the high, medium and low logframe output targets were originally used to establish excellent, good and adequate standards of performance these standards have in some cases also been lowered – for example the performance standards for equity now only require CCG to achieve 75% of its high target to be considered excellent, 75% of its medium target to be considered good and so on.
Beyond the above, the equity standard also appears to have been significantly weakened with the removal of the reference to differing possible levels of commitment across CCG workstreams to incorporating issues of equity as the subject of research. Here standards of performance have been replaced with a broad, but we would argue non-specific and difficult to measure, commitment: “CCG encourages the acknowledgment of its GESI strategy and will monitor and report the implementation of it across the consortium.”
4.3.3	Challenges with standards for ‘economy’
There appears to be particular stumbling blocks for the PMU with the economy element of the VFM framework. During the Loughborough workshop the PMU’s expressed view was that “…the LU IT systems for raising requests and approvals are not aligned with the VfM framework, so LU has to manually review and check compliance to VfM thresholds before requests are entered in the LU system in the pre phase (approvers would only consider LU thresholds, not FCDO VfM ones) …”
We recognise that the PMU has limited control over economy for CCG. Individual consortium partners follow their own salary scales for example, which limits CCG’s ability to determine fee rates. Individual consortium partners also follow their own policies around hotels, travel, and expenses. These can be quite different, with the result, for example, that staff from different partners attending the same event in a country may have to stay in different qualities of hotels.
We would suggest one of the reasons why there are difficulties with the economy area of the VFM framework is that CCG management is trying to treat it as an expenses / procurement policy, which is not what it was designed to be. The intention was for the framework to retrospectively measure the VFM achieved from exercising such policies in practice (or in the case of CCG, the VFM achieved from the consortium members all exercising their own expenses and procurement policies).
Given the PMU has limited or no control over consortium partners’ execution of their own expenses, salary and procurement policies, the standards set in the VFM framework would better focus on what, over a year, considering all the different consortium members expenses and procurement policies, would be a good level of performance, say for the average cost achieved for a flight from Europe to Africa or the average cost of hotels achieved in a particular country. Excellent would then be coming in a certain percentage below that average while adequate would be exceeding that ‘good ’figure by a certain percentage. At the moment some thresholds seem to be set at the maximum possible, so as to allow for all possibilities for a single instance. A benchmark of £3,998 for a return from flight from Europe to Africa is a good example where, with advanced planning, you would expect the average costs of flights from Europe to Africa over a year to be a lot less than this. Likewise inserting caveats into standards to allow for all situations (e.g. “Exceptions will apply for pre-authorised strategic events (e.g. COP, Summer Schools, G20), when accommodation and flight costs may exceed benchmarks; three quotes will be provided as evidence of high costs”) again seems to be an attempt to cover all possible bases (an expenses policy) rather than an attempt to set a bench mark that, on average over a year, would be a good (or excellent or adequate or poor) level of VFM performance for that type of expense.
[note] Table 1 of the current VFM framework draft
If the approach suggested above were adopted, management could then look at the VFM achieved against these standards overall in any year but also consider VFM achieved at the individual consortium partner level. The latter might then allow for some discussion on how best to utilise consortium partners with higher salary scales and more generous expenses policies, in order to ensure reasonable overall VFM is achieved.
4.3.4	Recommendations
Across the current version of the VFM framework as a whole CCG should reconsider the standards being set for each criterion in the light of the generic description of ‘excellent’, ‘good’, ‘adequate’ and ‘poor’ provided in Table 2 to ensure they are sufficiently ambitious to meet these definitions.
For the economy criteria, CCG should avoid trying to use the VFM framework as an expenses / procurement policy and instead seek to identify, for each criterion, what average performance across the consortium over a year would merit ‘good’ performance and then relative to that what excellent, adequate and poor would look like.
CCG and FCDO should seek to finalise this framework as speedily as possible, given it has been in draft form now for well over a year.
# Decision making and governance
5.1	Senior management support to programmes
Review question: Are improvements being made in support from senior management to CCG academics adequate? Particularly in relation to:
  - how individual workstreams fit within and add value to CCG’s overarching goals and outcomes;
  - what changes are proposed to improve this (including consulting with CCG academics and integrating their views when changes are made);
  - how important decisions are made and how has the recently implemented ‘enhanced annual consortium review’ contributed to that process.
5.1.1	Current situation
The response from interviews of workstream leads was largely very positive in respect to most of the above questions, as the following quotes from interviews with four different workstream leads illustrates:
“The Loughborough team has expanded and this has made a big difference, as it is a very big programme. The strengthening of operational support has been quite effective. The structures to support communication across the programme are ok, and working relationships are generally good. Strategically, research is given appropriate latitude to set our research strategy with feedback and input from the broader directorate and FCDO. Those processes work quite well. There are multiple rounds of review so the result reflects the whole programme. Processes ensure that different parts of the programme are engaged with each other.”
“There has been a huge improvement in the overall management of CCG over the past 18 months, made possible by better staffing levels at the centre. More can be done but the direction of travel is very encouraging.ne it is possible for the workstream to at least respond to those ideas and also to anticipate and plan for change.”
“This has improved quite a lot. The structure of CCG has become more clear. Previously there were gaps between the directorate and delivery, but these have been filled. The monthly meetings are very good. Roles and responsibilities are more specific”
“There is now a lot more support for the workstreams and the work stream leads than there was in the past. [X] has a half hour meeting with Romana and Peri every week on administrative and budget issues and has regular 1:1’s with Mark. Mark also checks in with the workstream team every couple of weeks. In addition, there is also a monthly meeting with senior management to review progress on deliverables etc.”
One other workstream lead felt the difference was not so much in the increased management capacity at the centre but the actions of the new Research Director:
“There is not so much interaction with or support from Jairo or Romana, although there isn’t much of a felt need for more support from those quarters either. ….. The most unifying effort currently underway is Adam Hawkes’ efforts to create a new research strategy. This has helped KTH and the workstream feel a lot more part of the CCG programme, highlighting the relationship of its work to that of other CCG teams and showing what collaboration could be possible.”
[note] CCG consortium partners KTH Royal Institute of Technology, Stockholm
While there were no suggestions that support had deteriorated, one other workstream lead felt that increased capacity at the centre had not managed to resolve the key issue of budget cycle risk:
“The additional resourcing has not delivered improvements to the [consortium] contracting process, which is the main area of concern. Addressing this would be the most helpful thing they could do for programme PIs.”
We were unable to get a good sense from interviews of the impact of the enhanced annual consortium review carried out this year. Some workstream leads were not much aware of the process and those that were aware seemed unsure of its value or impact:
“The Enhanced Annual Consortium review was presented at the General Meeting. It is not clear that this will deliver something valuable.”
With this exception however, our conclusion is that strategic, management and administrative support to workstream leads has improved significantly since the phase 1 evaluation and that, combined with other actions such as the work on a new research strategy by the new Research Director, there is a better sense of programmatic coherence as a result.
5.1.2	Recommendations
We make no further recommendations in this area.
5.2	Functioning of Advisory Group
[note] In response to the first draft of this report we have been informed that the CCG Director Mark Howells had a detailed engagement with the External Advisory Gorup during the February 2025 General Meeting where their roles and value add were discussed in detail, The review team was unaware of this activity during the review period. We understand that a report from this discussion is in the process of preparation. While that report may thus supersede our analysis in section 5.2, we leave it in place as a record of our understanding at the time and our recommendations in that context.
Review question: Is the Advisory Group an effective means of providing expert external advice and direction? How could the AG improve?
5.2.1	Current situation
From discussions with the CCG Deputy Director and email exchanges with FCDO we understand that the External Advisors group meets as part of the bi-annual CCG general meetings and also communicates occasionally by email. They were also involved in reviewing the content of the last FRF call for expressions of interest. We further understand that the consensus, at least within CCG, is that the programme has not “used them to their full potential to date.”
The current ToR for the external advisors is included in full in Annex C. Key responsibilities are list as:
- Identify, propose and (where possible to do so), support opportunities to deliver the Outcomes and Impacts of the programme.
- Identify areas where the programme would benefit from working more or less and to improve the broader impact and coherence of its activities in alignment with its overall objectives.
- Provide specialist insights, best practice, and up-to date sector knowledge on specialist areas of expertise.
Members are expected to engage with the programme at a senior level through:
- Attendance of two annual meetings per year which will be in a hybrid format. In-person attendance is preferred if possible.
  [note] CCG Management, in response to the first draft of this report, clarifies that practice differs somewhat from the Advisors TOR and that External Advisors group meets as part of the bi-annual CCG general meetings (the External Advisory Group are invited to attend one of the two CCG General meetings, not both).
- Review of both the programme Annual Report and the Quarterly Report produced before the mid-year meeting in preparation for, or after the above meetings to ensure they are up-to-speed with current delivery status.
- Participation in ad-hoc virtual meetings/consultations of a frequency no more than once per quarter in relation to programme development and delivery activity, such as to provide expert insight and recommendations.
- Attend (at discretion) workshops/meetings that the CCG management may decide to host on an ad-hoc basis aligned with major climate-compatible growth-focused events.
Box 1 lists the External Advisors Group membership and it is clear that, combined, they have extensive knowledge of the sector and undoubtedly a lot of useful networks and contacts.
Box 1: CCG External Advisors Group membership
Kandeh Yumkella: Chief Executive Officer of Sustainable Energy for All / Professor Xi Liang: Professor of Sustainable Transition in Construction and Infrastructure, UCL / Sheila Watson: Deputy director of FIA foundation / Maruxa Cardema: Secretary General, SLOCAT Partnership / Geoffrey Morgan: Senior infrastructure sustainability, resilience, and inclusion specialist, from UNOPS / Professor Kevin Urama: Acting Chief Economist for Economic Governance and Knowledge Management ADB / Gabriela Elizondo Azuela: Practice Manager Global Energy Programs, ESMAP, The World Bank / Youba Sokona: Special Advisor for Sustainable Development at the South Centre. / Fatima Denton: Director of the Institute for Natural Resources in Africa at the United Nations University, Ghana / Simon Sharp: Director of Economics for the UNFCCC Climate Champions, and a Senior Fellow at the World Resources Institute / Ambuj Sagar: Professor of Policy Studies at the Indian Institute of Technology Delhi / Izabella Mônica Vieira Teixeira, Co-Chair of the International Resource Panel

They are all also clearly occupying senior positions in institutions that make it likely they would have limited availability to dedicate significant time to CCG. This is a common issue with advisory groups of this nature, along with how such advisors can usefully engage when their contact with a large and very complex programme is limited to two or three touch points per year. In this respect, the expectation in the current ToR that each advisor would familiarise themselves with the current delivery status of the entire CCG programme once every 6 months in order to be able to contribute to a General Meeting would seem to be ambitious.
We understand that at the last general meeting in February 2025 there was some discussion on this matter, with suggestions that individual advisors might work with different CCG units or help connect CCG country programmes with relevant people in national government. We understand however that no decisions have been taken as yet and that what might go in a potential revised ToR is still under discussion.
We would suggest that it would be more practical for external advisors to be associated with a particular workstream in order that they might more easily develop an understanding of an element of CCG’s purpose, strategy, progress, and challenges.
Clarity of the purpose of the role advisors are filling is important. We would suggest there are a number of roles an external advisor could play at a workstream level, for example:
1. Technical expertise: Provision of advice to a workstream lead on the current state of knowledge in a field relevant to the workstreams research area. The advisor would need to be recognised and respected by the workstream lead as a leading expert in their field and add additional insight to the workstream team.
2. Stakeholder knowledge: Provision of advice to a workstream lead around stakeholders’ needs – the likely customer for the research product / service and what will be required in practice for research results to lead to impact. The advisor would in this case need to be familiar with and able to represent the views, needs, and the practical and political economy challenges that will need to be addressed for uptake to be achieved.
3. Quality assurance: Provision of a 2nd opinion to CCG senior management. In this guise, the external advisor acts more as quality assurance for CCG management, becoming familiar with and providing a second independent opinion on the work of a particular workstream.
4. Ambassadorial role: An external advisor who has good familiarity with a workstream may play an ambassadorial role promoting awareness of CCG or its research products in a network that CCG has limited access to, thus widening its potential impact.
In all cases the advisor would need to be recognised and respected by the workstream lead and senior management as a leading expert in their field and have the capabilities to advise (as oppose to direct) and, in the case of (4) above, be willing to use their networks to help senior management or workstream leads navigate routes to impact. Roles (1), (2) and (3) are quite distinct and attempting to combine one or more of them in a single person may well create conflicts of interest and thus could be counter-productive. Role (4) could be combined with any of roles (1), (2) or (3) however.
Advisors allocated to specific workstreams could be used to review strategies, funding calls and the resulting proposals, papers, and research outputs and so on, to have more frequent touch points to stay up to date with and deepen understanding of a particular aspect of CCG. Under such arrangements it could be interesting to have an annual meeting of advisors with CCG senior management and FCDO to share advisor experience of engaging with workstreams and their understanding from their workstream’s point of view, of what is working well across CCG and where there are challenges.
5.2.2	Recommendations
We understand that the role of the external advisors’ group is currently being reassessed by FDCO and CCG. As part of this process we would recommend that further clarity be provided on the purpose of the role and would suggest the four role-types we have set out above would be a good starting point for such a discussion. We would further suggest that given the scale and complexity of CCG, external advisors, if used, be allocated to individual workstreams, with regular task-based touch points scheduled. This should allow them to develop some depth of knowledge of a specific area of CCG operation and be in a better position to provide whatever function is required of the role type eventually decided upon.
# Recommendations
For ease of reference the following brings together the recommendation made in the preceding section of this report. We have allocated a high / medium / low level of importance to each recommendation based on our own assessment of their relative likely impact on operations in terms of improving efficiency or reducing risk.
6.1	Programme management and contracting
#### Programme management
  1. CCG should continue with its current efforts to further embed its projectisation process. The move to ClickUp should continue but with careful review as rolled out to ensure the adoption workstreams, as the data inputters, is as easy as possible and that CCG’s systems as a whole only require data to be inputted once. [MEDIUM]
  2. CCG should consider providing additional support and guidance to workstreams 1, 5b, 5c, and to holders of Agile and SPF projects to bring the quality of their projectisation reporting up to that of the other workstreams. [HIGH]
6.2	Staffing and resourcing
#### PMU staffing
  1. CCG should proceed with recruitment of the remaining unfilled posts in the current staffing plan in order to be adequately resourced to be able to ensure the monitoring, evaluation and learning function in OIF is fully supported and that general progress on reducing bottlenecks with administrative and contracting processes, in conjunction with RIO, continues. [HIGH]
#### Budget cycle risk
  1. We suggest a range of actions, in descending order of impact, which would mitigate or partially mitigate the current budget cycle risk [HIGH]:
1. FCDO provide multi-year confirmed budget figures. This would fully mitigate the risk, but in the current circumstances of UK Government imposed development assistance budget cuts may be difficult to be achieve.
2. FCDO provide earlier confirmation of the budget figure for the following fiscal year. Confirming the budget figure in December each year should provide adequate time for CCG consortium partners to finalise plans and budgets in advance of the new fiscal year starting. Confirming a budget figure at least 3 months in advance of the fiscal year should also avoid the issue of staff termination notices being issued.
3. FCDO and CCG confirm agreement of proposed change in the wording of the AGA, with the replacement of the break clause with a requirement for FCDO to provide 3 months’ notice of funding reductions. This would reduce the staffing risk, at least for Loughborough, but would not resolve all issues.
4. FCDO and CCG reduce the time it takes to sign the amended grant agreement; the current estimated five to six weeks seems like a very extended timescale to complete what should be a straight forward amendment with no changes to terms and conditions beyond confirmation of the budget figure for the year.
5. CCG consortium members to do more to planning on the basis of the minimum budget figure provided in December, perhaps with scenarios to cover a 5 or 10% uplift if it occurs when the final figure is issued in February, to avoid delays caused by consortium partners being late in submitting their budgets and planned outputs for the new fiscal year.
6.3	Monitoring, evaluation and learning
#### MEL system
  1. A more detailed written document should be produced that details how each MEL indicator is to be reported, the criteria for the analysis, data sources, individual responsible, and other key information so that the team is clear on how each indicator is assessed. [HIGH]
  2. To ensure MEL data security and retrievability there should be a written record that identifies what datasets and evidence are collected, where they are stored, and any regular processes that need to be carried out (e.g. cleaning and removing duplicates) are kept through the system, ensuring they are located in a safe space. This should be accompanied by a log that confirms when these processes have been undertaken, by whom, and their results. [MEDIUM]
  3. CCG should consider introducing more feedback loops with programme counterparts or targeted recipients of the work delivered to capture new outcome-level results obtained, especially in the area of use of public goods provided by CCG.
  4. CCG should more actively use MEL quarterly data to facilitate not just discussion on what has been achieved to date, but as an opportunity to reflect on and agree actions required to address issues such as underperformance or course changes or reallocation of budget to ensure full utilisation and avoid underspend over the year ahead. These discussions should be recorded in a report for future reference and review of progress on actions agreed. The mid-year general meeting would be a particularly useful time to do this.
  5. CCG should also consider developing more dynamic tools or ways to display the outputs from the MEL system (such as dashboards) to support greater engagement on and discussion of results. [LOW]
#### Monitoring of risk
  1. The programme and workstream risk registers should include additional columns a consolidated risk based on the combination of the likelihood and impact. This should be compared to FCDO / CCG’s agreed consolidated risk appetite for each risk. [HIGH]
  2. Workstreams should be supported to provide a more uniform depth of risk analysis in their registers. Workstreams 3a, 5a and 5b should be encouraged to provide more depth in their analysis which workstream 5c needs to provide a much more concise analysis of the most important risks. [HIGH]
  3. The programme level risk framework should be consolidated further by removing duplicates and risks that are no longer relevant. It also needs to include the specific risks the senior management team is actively managing down at the current time and not just, as is the case at the moment, just a set of generic risks and generic responses. [HIGH]
#### Monitoring of VFM
  1. Across the current version of the VFM framework as a whole CCG should reconsider the standards being set for each criterion in the light of the generic description of ‘excellent’, ‘good’, ‘adequate’ and ‘poor’ provided in Table 2 to ensure they are sufficiently ambitious to meet these definitions. [MEDIUM]
  2. For the economy criteria, CCG should avoid trying to use the VFM framework as an expenses / procurement policy and instead seek to identify, for each criterion, what average performance over a year would merit ‘good’ performance and then relative to that what excellent, adequate and poor would look like. [MEDIUM]
  3. CCG and FCDO should seek to finalise this framework as speedily as possible, given it has been in draft form now for well over a year. [HIGH]
6.4	Decision making and governance issues.
#### Functioning of advisory group
[note] We noted earlier that further discussions took place between the CCG Director and the advisory group during the course of this review. The review team were not able to see the report emerging from those discussions within the time frame of the review. We acknowledge therefore that the continued relevance of the above recommendation may be dependent on the results of those discussion.
  1. Further clarity could be provided on the purpose of the advisory group member role. Given the scale and complexity of CCG, external advisors, if used, should be allocated to individual workstreams, with regular task-based touch points scheduled, to allow them to develop some depth of knowledge of an area of CCG operation and be in a better position to provide whatever function is required of the role type eventually decided upon. [LOW]

Bibliography
#### Progress reporting
- CCG Annual Report 23 24 Final to FCDO (and annexes)
- FY5 Q2 CCG Quarterly Report to FCDO 14Nov24 (and annexes)
- FY5 – CCG WS Projectisation 2024_25 Vs 2Jan2025
- OIF Report FY5- Q3.ppt
- CCG Outcomes Summary 2022-2023
- Example of Outcomes Reporting: Uganda Energy Transition Plan
- Justification statement for achievement of CCG OI.1 Uganda Energy Transition Plan
- Signed endorsement letter from Ministry of Energy & Mineral Development Uganda for description of CCG’s contribution to the preparation of Uganda’s Energy Transition Plan
- Outcomes list.xls

#### FRF SRF Engagement fund docs
- Draft Engagement Fund Procedure Vs0 1jan25
- SPF Process Update Vs 15Jan 24
#### Manuals / TORs / Procedures
- CCG VFM Framework Draft 15-01-25 (work in progress)
- Draft CCG Enhanced Risk Management Strategy addressing FCDO comments (Jan14)
- Monitoring Evaluation Framework for CCG
- OIF TOR 2024
- CCG Project Manual
- LogFrame Methodology for measuring CCG’s Output and Outcome Indicators
- Reporting an Outcome – Guiding Note Operational Intelligence Framework
#### Other
- General Meeting 2024 Sept Days 1-2 Summary
- CCG Management Response Final 1Feb25 (to the Phase 1 evaluation report of May 2024)
- Climate-Compatible Growth (CCG) Programme Terms of Reference for the Role of External Advisor
- Logframe FY 24-25
- CCG – The power of research and partnership, Mapping our journey April 2021-March 2024

1. Terms of reference
  1. Purpose:
The purpose of this exercise is to review the management of the Climate Compatible Growth applied research programme. The exercise will:
Provide an opportunity to follow-up and comment on progress on management-related recommendations made in the Phase 1 evaluation of the CCG programme completed in 2023
Reflect on the direction of travel of recently refreshed (or under development) programme management and administrative systems and processes
Consider additional questions not covered in the evaluation or related to potential issues emerging since the evaluation was completed.
  1. Review questions:
The review is expected to cover the questions outlined under the following five areas:
    1. Programme Management and contracting
How can CCG be more effective at providing timely programme management information, including payment requests and financial forecasting information? What is the cause of current delays to payment requests and financial forecasting and how can this be mitigated? Do downstream suppliers allocate sufficient contracting and project management resources in support of the central team?
Does Loughborough University allocate sufficient resources to provide effective contracting for CCG, including on behalf of the Flexible Research and Southern Researchers Funds and the new Engagement Fund?
What are the implications for responsive/agile research (including that funded through the Flexible Research Fund, the Southern Researchers Fund, and the Engagement Fund) given all CCG consortium research must be contracted through Loughborough University?
Does CCG benefit from scale associated with being housed in STEER alongside MECS? Are there shared administrative functions that allow greater value for money?
How is CCG’s attempts to projectise the research portfolio (to aid tracking timeliness and outputs) developing?
What challenges does CCG face in contracting institutions based in the Global South? Does CCG have adequate approaches and systems in place to mitigate these challenges?
How does the perception of budget cycle risk, and the necessity of break-clause implementation in contracts, impact on contracting and project management? How could this be better managed?
    1. Staffing and Resourcing
Is the PMU appropriately staffed/resourced? Are there capacity bottlenecks in the programme management or administrative structures and how might these be mitigated?
How might CCG more formally/effectively monitor and forecast programme/project management and administrative burden? How can this inform mitigation?
    1. Monitoring, Evaluation and Learning
With reference to CCG’s developing MEL strategy: What is CCG’s programme-wide approach to Monitoring, Evaluation and Learning, how can MEL be institutionalised within the programme, and is continual MEL appropriately incentivised/resourced?
Does CCG have an effective internal process for recording, monitoring, and escalating risks?
To what extent has CCG been able to adapt and contextualise a Value for Money framework that is useful for both programme management and reporting?
    1. Decision Making and Governance
Are improvements being made in support from senior management to CCG academics adequate? Particularly in relation to:
how individual workstreams fit within and add value to CCG’s overarching goals and outcomes;
what changes are proposed to improve this (including consulting with CCG academics and integrating their views when changes are made);
how important decisions are made and how has the recently implemented ‘enhanced annual consortium review’ contributed to that process.
Is the Advisory Group an effective means of providing expert external advice and direction? How could the AG improve?
    1. Operational Intelligence Framework
What is the role of the OIF, how has this evolved, and how is the OIF expected to develop in future? Are the functions of the OIF likely to be absorbed by mainstream management processes, and if so, how will this be formalised?

  1. Approach
The review will involve (mostly remote) interviews with CCG and FCDO personnel and review of relevant documentation. Where appropriate the review will take note of and build on the findings from the Phase 1 evaluation of the CCG programme carried out in 2023 to avoid duplication of work already done.
The exercise may involve a day long workshop / meeting in person at Loughborough University with CCG PMU staff and FCDO.
Allowance should be made for production of a first draft and, after review by FCDO, a second final draft report. The report should be summarised in a set of PowerPoint slides and time allowed for a workshop with FCDO and CCG management to present the review’s findings.

  1. Proposed timing
A kick-off meeting is expected to take place with CCG and FCDO at the beginning of December 2024.
The bulk of the activity in terms of interviews and requests for documentation is expected to occur during January and February 2025.
A draft report will be produced by mid-March 2025.

  1. Expected outputs
The outputs from the review will be:
A report that includes an Executive summary that can also be used as a stand-alone document.
A slide pack summarising the report, to be presented at a workshop for FCDO and CCG management.
1. List of interviewees
  1. Loughborough University workshop attendees
FCDO:
Dawn Wood,
Alfie Alsop

CCG:
Mark Howells,
Jairo Quiros-Tortos,
Romana Rauf,
Peri Williams

Loughborough University Research and Innovation Office:
Charles Shannon,
Lizi Wheater,
Denise Smith

Loughborough University Procurement:
Anna Ellis

STEER:
Judy Billington

  1. 1:1 interviews:
Lara Allen (CCG Country Programmes Lead)
Vivien Foster (WS2 Lead)
Adam Hawkes (Research Director, CCG)
Jennifer Johnson (Director of Research and Innovation, Loughborough University) with Charles Shannon (Head of Research and Innovation Operations, Loughborough University)
Alex Money (Workstream 5c lead)
Ramona Rauf with Peri Williams (CCG PMU)
Jairo Quiros-Tortos (CCG Deputy Director)
Will Usher (WS71 Lead)
Rudolf Yeganyan (… Lead)
Ligia Zagato (CCG OIF)

External Advisors TOR
 Climate-Compatible Growth (CCG) Programme
Terms of Reference for the Role of External Advisor
Introduction
The Climate Compatible Growth Programme (CCG) is a £38m, five-year action-oriented research programme, launched in January 2021. It is the FCDO’s first research programme to take a holistic approach to addressing climate-compatible and inclusive growth in low and lower-middle income countries.
CCG aims to accelerate the roll-out of improved infrastructure that reduces GHG emissions and increases inclusive economic growth in developing countries. It does this by:
- Improving the evidence base on what works;
- Developing open-source tools and data; and,
- Promoting uptake of this evidence / tools /data into improved policy and investment decision-making.
CCG’s research is strongly aligned with priorities set out in the UK Government’s International Development Strategy (published May 2022). It provided strategically significant support during COP26, including pivotal support to the Energy Transition Council and Green Grids Initiative, and continues to be involved in these initiatives.
CCG is currently focused on grid-scale energy and transport systems, with the potential to expand to other sectors in the future.
 The programme is delivered by a core consortium of seven universities (Loughborough, Imperial, UCL, Oxford, Cambridge, KTH in Sweden, the Open University), alongside MDB research funded directly by the FCDO via the World Bank and Asian Development Bank. It works through two main modalities: (1) research partnerships with countries, international organisations, and initiatives; (2) academic-led core research.
CCG contributes to International Climate Finance (ICF) goals and is one of the key delivery platforms for the £1billion UK Ayrton Fund for clean energy innovation in 2021-2026.
External Advisors
The FCDO and CCG’s Programme Directorate recognise the ongoing need for external expertise to support the delivery of a quality programme. We are seeking to establish a formal Advisory Group which encompasses a broad range of perspectives from different geographies, backgrounds, sectors, and demographics.

Role of External Advisor
The overarching role of the External Advisor will be to support the quality assurance function of the programme. This will be done through review of the programme’s activities, outputs, outcomes, and impacts, contextualised through the Advisor’s own specialist knowledge and sector experience. This will allow them to:
- Identify, propose and (where possible to do so), support opportunities to deliver the Outcomes and Impacts of the programme.
- Identify areas where the programme would benefit from working more or less and to improve the broader impact and coherence of its activities in alignment with its overall objectives.
- Provide specialist insights, best practice, and up-to date sector knowledge on specialist areas of expertise.
Tenure is not limited, and is anticipated to last as long as the programme lasts (until March 2026) by mutual agreement.
#### Responsibilities
External Advisor Responsibilities
External Advisors will be expected to engage with the programme at a senior level in the following ways:
- Attendance of two annual meetings per year which will be in a hybrid format. In-person attendance is preferred if possible.
- Review both the programme Annual Report and the Quarterly Report produced before the mid-year meeting in preparation for, or after the above meetings to ensure they are up-to-speed with current delivery status.
- Be willing to participate in ad-hoc virtual meetings/consultations of a frequency no more than once per quarter in relation to programme development and delivery activity, such as to provide expert insight and recommendations.
- Attend (at discretion) workshops/meetings that the CCG management may decide to host on an ad-hoc basis aligned with major climate-compatible growth-focused events.
CCG Programme Directorate (PD) Responsibilities
To support the functionality of the External Advisors, the CCG PD commits to the following:
- Provide adequate notification of events and documentation to External Advisors to allow them to comfortably accommodate within their schedules and review any pre-meeting material prior to attendance.
- Either pre-purchase or fully reimburse all reasonable costs associated with the fulfilment of the requested responsibilities of the External Advisor (e.g. travel, accommodation, and food).
- Be responsive to External Advisor requests and questions in relation to the delivery of the programme or agreed upon actions.