# The Climate Compatible Growth Programme.
# Learning brief on the challenges of managing and co-ordinating a large and complex research programme
## Introduction
The Climate Compatible Growth research programme (CCG) is a five-year FCDO ODA-funded programme that launched in January 2021. CCG has recently been extended to 2030 with a total budget of £95m. It aims to provide robust evidence to help low- and middle-income countries (LMICs) take an integrated approach across sectors to future-proof their deployment of infrastructure capital and to create national development strategies that put them on a trajectory to clean, inclusive and sustainable growth. It does this by improving the evidence base on what works, developing open-source tools and data, and promoting uptake of this evidence / tools / data into improved policy and investment decision-making.
CCG is led and delivered by a core University Partnership, made up of University College London, the Universities of Oxford and Cambridge, Imperial College London, Loughborough University, the Open University and KTH Royal Institute of Technology in Sweden, together with the University of Cambridge-affiliated Centre for Global Equality and the Climate Parliament. Strathclyde University was added to the consortium after the evaluation was completed. The academics within the CCG partnership combine technological, economic, behavioural, political, and financial skills and expertise.
A recent mid-term evaluation of the CCG programme found CCG had made substantive progress, but also identified challenges in managing and coordinating such a large and complex research programme. This learning brief sets out some of the lessons emerging from those challenges.

## CCG working modalities and organisational structure
CCG works through two main modalities: (1) applied research partnerships with LMIC institutions, international organisations and initiatives focussed largely on promoting the application of improved tools and data to real-life problems; and (2) academic-led core research, guided by those partnerships, but focussed more on pushing the boundaries of academic research. The organisational structure of CCG involves collaborative work across multiple partner institutions, but can be thought of in terms of five components:
[note] It should be noted that components 2 and 3 also involve elements of research.
1.	Programmed Research: CCG’s portfolio of academic and applied research across 5 thematic areas, both to advance CCG’s goal to push the frontier of academic knowledge on climate-compatible growth in LMICs and to inform and support activities under components 2 and 3 below.
2.	International Partnerships: CCG’s activity with international partners such as development banks or the Green Grids Initiative (GGI) to embed CCG products in their policies and practice, contributing to the outcomes of their partnerships with LMICs.
3.	National Partnerships: CCG’s activities with national partners in specific country programmes to pursue the outcome of working with LMIC government to embed CCG data, tools and knowledge products and activities in policies and procedures.
4.	Capacity strengthening: encompassing training materials, data sets and other products made available through CCG’s on-line Open Learn platform, but also encompassing training and capacity strengthening activities carried out under the components described above.
5.	Management: administration, contract management, strategic direction and governance.
CCG’s structure is complex. The three main components (the programme research workstreams and the international and national partnership workstreams) reflect the three outcomes CCG is designed to deliver and facilitate work to that end. The core university partnership is structured and financed to encourage collaboration across institutions in the belief that will facilitate valuable research outputs that would otherwise not be possible. The evaluation found that CCG functions, by and large, well from the perspective of its external stakeholders. As such the structure, although complex, can be considered appropriate for the intended outcomes.
## Lessons emerging from management challenges
While the structure may be appropriate for the intended outcomes, the scale and complexity of the programme does come with challenges. Five lessons arising from the challenges observed by the evaluation are summarised below.
Programme strategies may be built in part from the bottom up, but also need to provide overarching guidance on resource allocation priorities. The CCG goal of supporting LMICs to future-proof their deployment of infrastructure capital and secure a trajectory to clean, inclusive and sustainable growth is a very wide canvas to operate on. Decisions need to be made on what constitutes a useful balance of research in terms of focus, for example across different infrastructure sectors (energy vs transport vs other infrastructure), or different impacts (e.g. the impact of infrastructure choices on climate vs equitable growth goals). Likewise, decisions are required on the types of research to invest in (for example modelling vs other forms of research).
Currently the above investment decisions are guided by the strategies developed for each individual workstream (which are reviewed annually). In essence the overall balances between options are derived from a bottom-up summation of those strategies. The evaluation found this resulted in clear areas of emphasis. For example modelling approaches account for around 75% of all Programmed Research commitments to the end of year 4, with 25% allocated to other forms of research. Transport research was allocated 15% of funding with most of the remaining 85% being focused on energy infrastructure. These current balances between choices such as energy vs other infrastructure and climate vs equitable growth impacts reflect the evolution of the programme. In the early years, against a backdrop of ODA budget cuts and uncertainty, the FCDO were content to let the allocation of resources across approaches and sectors be led via the bottom-up development of research strategies, which in turn were shaped by the makeup of CCG’s academic consortium (largely energy modelling experts). However, in recent years the FCDO’s budget allocation to CCG has stabilised, enabling the CCG university consortium to bring in new staff and institutions. Alongside this the FCDO has provided greater guidance on approach and sectoral foci, for example requiring a greater proportional focus on transport, critical minerals and the cross-cutting themes of gender equality and social inclusion and political economy.
There is still room however for FCDO, in dialogue with the CCG consortium, to consider more explicit guidance on what they see as an appropriate overarching allocation across research approaches and sectors. This in turn would enable more coherent strategic guidance from CCG’s leadership to the academics within the consortium .

If programmes are serious about engaging with and supporting Southern research capabilities, the budgets for doing so need to be protected in times of crisis. The reallocation of the UK Overseas Development Assistance budget following COVID led to significant reductions in the budget available for CCG in its early years, forcing the programme to make choices around budget allocations, including the balance between funding delivery through the core university partnership and the provision of funds to engage LMIC academia. During this period the CCG research consortium, in consultation with FCDO, prioritised continuing to fund the Programmed Research through the core university consortium members. This decision reduced the resources available for the Southern Partners’ Fund (SPF), with only £782,000 allocated in the first 4 years of CCG compared to an original 5 year planned budget of £1.9 million. This shortfall in funding affected the extent to which Southern researchers and other stakeholders have been involved in projects and activities, impacting the fund’s effectiveness in supporting country-led work and bringing equity into the relationships with local partners.

The trade-off between breadth of geographic footprint and depth of investment in individual countries needs to be carefully weighed for implications on programmatic impact and partnership building. CCG has had some early success with its national partnerships, building strong networks of partners in countries such as Kenya, Laos and Zambia, making significant contributions to building national planning capabilities as well as co-creating research with national institutions. The level of demand for CCG’s services in its countries of operation (in particular its modelling capability strengthening support) is high and there are also many opportunities for collaboration with national institutions on research using grants from CCG’s Southern Partner Fund (SPF) and Flexible Research Fund (FRF) vehicles. Furthermore, CCG has ambitions around developing high quality data and analytical capabilities outside of government to support national planning. The Kenya CCG country strategy, for example, aims to create “An inclusive and integrated network of Kenyan-owned analytical units and institutions that are recognised by the Government for unbiased, verifiable and reproducible policy-facing data and analysis”. There are thus tensions between a desire to achieve significant impacts in CCG’s existing countries of operation (and the level of investment required to do this) and any desire to further expand its geographic footprint.
[note] See CCG evaluation learning brief on inclusive and effective national partnerships
At the time of the evaluation CCG had established national programmes in six countries, with plans to extend this to eight. It is not clear that CCG will be able to match the levels of support, inputs, and outcomes in its initial national programmes such as Kenya across other countries as its portfolio expands. Funds to co-create research with national institutions are already stretched, for example, and the programme may encounter diminishing returns as a result as additional investments are made in new countries using this model. CCG is also developing a concept of ‘Affiliate Countries’ where its approach is to some degree replicated by other international organisations, with much lower levels of investment and support from CCG. This may eventually prove a more effective way of CCG expanding its geographic footprint further.

Where individual projects involve multiple partners and funding routes, managing value for money can be challenging and requires a clear picture of what ‘good’ performance looks like. One area where CCG’s complexity manifests challenges is in financial management. Loughborough University (LU) is the grant holder for the CCG university consortium and has the due diligence responsibilities associated with that role. Although LU is able to operate high levels of control on contracts let to external institutions under CCG’s SPF and FRF funding mechanisms, its management oversight of the bulk of CCG funds, which pass through the core consortium partners, is less straightforward. As Figure 1 shows, workstreams, and individual pieces of work within them, are often reliant on contributions from multiple consortium partners, each drawing on their own budget allocations from CCG.
Figure 1: CCG Financial flows (£) based on consolidated figures for year 2 & 3 expenditure + year 4 budget

At the time of the evaluation CCG lacked a clear mechanism for reviewing allocative efficiency – whether the current allocation of funding across the consortium partners was optimal in terms of the value derived. Funds that pass through the consortium partners are provided as annual allocations aligned with annual plans, but disbursed without any specific link to work progress or outputs produced. At the time this evaluation exercise was being carried out a ‘projectisation process’ was underway in an attempt to exert more management control on CCG research work by packaging it up into discrete activities with identifiable outputs, timelines, and possibly budget allocations. At the time of finalising this report CCG had proposed, and FCDO accepted, that the level of effort required to allocate researchers’ time to specific ‘projects’ to derive budgets was disproportionate to the benefit and that idea had been dropped. We understand the FY23/24 FCDO annual review of CCG has recommended that an annual Consortium Review process instigated in FY23/24 be further enhanced to include, amongst other things, a comparison of outputs versus budget for each Workstream with accompanying explanation for variations between Workstreams. This, when fully implemented, may allow CCG management to make a more informed allocation of resources across workstreams that takes account of progress against the outputs and goals in each workstream’s strategic plan.
Strategic and operation management of complex research programmes needs to be resourced adequately. As Figure 1 suggests, a core consortium of nine institutions collaborating in different combinations on at least 13 different workstreams is likely to throw up management challenges. CCG has a relatively light management structure and the most senior management team members split their time between CCG management oversight, being actively engaged in CCG research themselves, and, with the exception of the programme director who is full-time on CCG, other work at their own institutions. The evaluation found further effort is needed to ensure that individual workstreams are provided adequate feedback on their work, that their efforts are managed to ensure the sum of CCG’s individual parts is optimised, and that there is a good understanding across all the consortium partners of the progress CCG is making against its strategic goals and the basis for the central decisions that are made to keep it on track. At the time of the evaluation CCG was recruiting to further strengthen its management team to address some of these issues.
## Conclusions
The evaluation found that the CCG programme is making substantive progress against its Theory of Change and Log Frame milestones. Nevertheless, a programme of this scale and complexity faces both strategic and operational management challenges, notably around how to develop, communicate and use a vision of what ‘good’ overall performance would look like to guide resource allocation, manage value for money, and communicate and drive progress internally.