## Climate Compatible Growth: Annual Review, July 2025

Title: Climate-Compatible Growth
Programme Value £ (full life): £94.7m		Review date: 23/07/2025
Programme Code: 300125	AMP start date: 02/02/2021	AMP end date: 31/03/2030

Summary of Programme Performance
Year	FY 21/22	FY 22/23	FY 23/24	FY 24/25
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300125/summary
DevTracker Link to results framework:	DevTracker Project GB-GOV-1-300125 Documents (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW

Description of programme

The Climate Compatible Growth (CCG) programme brings together a consortium of top UK and international researchers to carry out research and produce evidence in support of policymakers in making long-term low-carbon investment decisions that lead to inclusive economic growth. CCG is primarily an energy systems programme, with an established component on transport de-carbonisation and a growing focus on critical minerals. CCG’s offer is broad but at its core is a set of world-class, open-source energy and transport decarbonisation modelling tools and a developing set of critical minerals analysis tools designed to support policy and investment decision-making. These are coupled with training programmes that empower developing country stakeholders to carry out their own analysis and thus develop their own energy and low-carbon transport systems planning and, in the future, critical minerals investment strategies. These tools represent best practice in carrying out the analysis required to turn green infrastructure targets into investment plans and mobilise green finance for infrastructure at scale. CCG’s offer is increasingly framed through the Data-to-Deal framework, which translates high quality data and modelling efforts into evidence-based policy development and well-substantiated investment plans and strategies for enhanced access to climate finance.

In March 2024 Ministers approved a Business Case Addendum for CCG, extending the programme by five years to March 2030 with a corresponding budget increase of £57m of ODA, taking the programme’s total budget to £94.7m ODA. Ministers also approved £2.2m of non-ODA for CCG, which primarily is programmed for use in a Critical Minerals workstream, and is subject to annual non-ODA allocation processes within the Research and Evidence Directorate.

CCG currently has deep engagements with six partner countries, in which it works closely with FCDO Posts. These are Kenya, Zambia, Ghana, Laos PDR, Vietnam, and India. Two additional partnerships are in their initial stages, in Nepal and Malawi. These new partnerships are currently paused, pending the confirmation of future year budgets. CCG scales its offer through partnerships with international organisations that utilise its tools and approaches with a broader range of countries and through its own lighter-touch engagements with ‘Affiliate Countries,’ including South Africa and Sierra Leone. CCG is one of the main platforms for the £1 billion Ayrton Fund for clean energy innovation between 2021-2026, currently serving as the lead FCDO funded programme on Energy Systems, Critical Minerals, and Clean Transport challenges.

The majority of CCG’s activities are delivered by a core University Partnership: Loughborough University, University College London, Oxford, Cambridge, Imperial and Strathclyde Universities, the Open University, and KTH Royal Institute of Technology in Sweden together with the University of Cambridge-affiliated Centre for Global Equality and the Climate Parliament. In addition, CCG has a direct funding relationship with the Asian Development Bank (ADB) to support development of the ADB’s transport decarbonisation policy and drawing on the CCG developed data-to-deal framework.
CCG is modelling the impact of potential budget reductions in future financial years, as a result of the UK Government’s reduction of the UK ODA budget. Any reductions will necessitate a recalibration of the level of ambition of the programme, which will then be reflected in logframe targets. The programme’s theory of change is not currently expected to change.
[note] The UK Government announced the reduction of the ODA budget to 0.3% of Gross National Income (GNI) in February 2025.

Summary supporting narrative for the overall score in this review

This review covers the period 1st April 2024 – 31st March 2025. The review, overall, gives CCG an A for achievement against outputs, having scored an A for two output areas, and a B for the remaining output area. Four of the five outcome indicators have exceeded their high targets, with one outcome indicator meeting its low target, indicating strong progress in ensuring uptake of CCG’s knowledge products and analysis. CCG’s core consortium, country partnerships and international partnerships have all contributed to the generation of new, relevant, and demand-informed knowledge products, and the uptake of these products by decision-makers and stakeholders in partner governments.

Examples of achievement against recorded outcome indicators include:

- OI1: Contribution to Kenya’s Least Cost Power Development Plan (2024-2043), where CCG is formally acknowledged for its role in supporting plan development.
- OI2: CCG-curated OSeMOSYS open-source energy modelling tool embedded in energy planning processes in the Ministry of Energy in Sierra Leone, as a result of collaboration with CCG
- OI3: CCG analysis integrated into the World Bank’s engagement on transport planning in Southern Africa – the analysis, part of Oxford University’s suite of climate risk assessment tools, was featured in a key regional report and in country-level engagements.
- OI4: Embedding of “Geospatial Data, Best Practices for Collection and Management” course into curriculum in the National Economics University in Vietnam, and translated into Vietnamese, driven by CCG Vietnam coordinator Dr Huan.
- OI5: CCG’s most cited publication at time of reporting is Giarola et al. (2022) “MUSE: An open-source agent-based integrated assessment modelling framework”. Energy Strategy Reviews
In its fifth year, CCG is seeing the benefits its long-term approach to partnership and capacity-building, with collaborations initiated in previous years now achieving outcomes. CCG is now framing of much of its activities under the data-to-deal (D2D) framework – a seven step process which defines the science/analysis and policy interface, from high-level climate ambition all the way to well-evidenced investment planning, with the objective of supporting greater levels of access to finance.

CCG has also made excellent progress in the development of a Gender, Equality and Social Inclusion (GESI) strategy, articulating the programme’s ambitions in ensuring genuine mainstreaming of GESI considerations in its research. The finalisation of the Strategy has taken some time, but GESI activities (both mainstreaming and focused) have been underway for some years. This has yielded important results, including the development of a first-of-its kind framework for integrating GESI into energy and transport modelling and CCG contributing to Zambia’s new “Gender Impact Assessments for energy infrastructure projects in Zambia’s power sector” (an Outcome for this year). This Strategy will be fully implemented (including monitoring and evaluation) in FY 2025/2026. Alongside this, good progress has been made in the development of a Political Economy Unit (PEU) within the programme, supporting politically aware and contextually relevant core research, in addition to the political economy-informed approaches utilised through the country partnerships.

Progress against previous Annual Review Recommendations

CCG has made broadly good progress against the recommendations made in the previous annual review. Most recommendations have been responded to in full, and outstanding or continued actions remain a regular item of discussion between FCDO and CCG. Progress against previous recommendations is summarised below:

Recommendation from 2024/2025 Review	Response
1. Management and delivery of Southern Partners Fund (SPF) and Flexible Research Fund (FRF): (The SPF funds the participation of Southern researchers in projects led by CCG's core research consortium while the FRF procures research outside the consortium through open calls with a requirement that at least 40% of funding will be directed to Southern researchers.) CCG to: consider whether the budget allocated to the SPF and FRF is appropriate to achieve the programme’s goals and provide FCDO with a proposal; and develop proposal for a more efficient approach to management of the SPF and FRF by mid-October 2024.	Following extensive consultation, the SPF and FRF revised process documents were presented to the Directorate in December 24 and February 25 respectively and final revisions following the CCG-FCDO Q3 workshop comments.
2. Critical mineral expertise within Advisory Group: CCG to bring in an AG member with expertise and networks on Critical Minerals by October 2024.	Izabella Mônica Vieira Teixeira has accepted Advisory Group membership (critical minerals expert). Official appointment of new Advisory Group member was confirmed in December 24.
3. CCG's Internal M&E function: CCG to develop a brief M&E strategy, covering Programmed Research, Country Partnerships, International Partnerships, and cross-cutting functions by end of September 2024.	A draft M&E document (work-in-progress) was shared with FCDO for comments initially in Nov 24, and following feedback comments anticipated to be finalised in May 2025 (after input from the Management Review report).
4. Appointment of new Research Director: Following the departure of Prof Jim Watson at the end of March 2024, CCG to appoint a new Research Director with a strong track record of research excellence in the field and international recognition, profile, and networks at the earliest possible opportunity. The new Research Director should be appointed by the latest at the end of September 2024.	Adam Hawkes was appointed as new Research Director in October 2024, following nomination and interview due process (the second nominee having withdrawn candidacy), in consultation with FCDO.
5. Revision of CCG Directive Strategies for the extension: To ensure that CCG’s directive strategies (National, International, and Programmed-Research) remain aligned with the extended program timeframe, CCG will develop a revision plan by June 2024. This will set out how the revised strategies will: align with the CCG LogFrame and Theory of Change out to 2030; ensure there are clear and measurable objectives within the strategies to assess their effectiveness and value for money; and set out how the strategies will allow for potential changes in workplans and partners whilst maintaining CCG’s accountability to the FCDO and other key stakeholders.	CCG Plan was presented at the Oxford Q1 FCDO-CCG workshop and accepted by FCDO
6. Further to confirmation of the project extension to March 2030, all Research Strategies to be fully revised for the extension. Revisions should involve close consultation with Country and International Partnerships, to facilitate closer integration between Research and Partnerships, and take into account findings of horizon scanning activities carried out during FY24/25 for those Workstreams for which this is relevant. As this is a major revision the Strategies should be externally peer-reviewed. Finalisation of the Strategies, including incorporation of comments from external peer review and FCDO, by April 2025.	The Programmed Research document continues to be revised through extensive consultation process since November 2024 and ongoing to date. The next step is for the PR document to be independently reviewed by external experts.
7. CCG to develop an approach to long-term engagement of Global South researchers with CCG workstreams as appropriate, to function alongside the SPF. While the SPF plays an important role in enabling Global South researchers to engage on CCG projects with academics within the consortium, the need to compete for SPF funding and the relatively short term of the projects it funds means it cannot support strategic, longer-term engagements between workstreams and Global South researchers. CCG to provide FCDO with a strategy by October 2024 and to implement the new strategy from FY25/26 onwards.	The draft document was submitted to FCDO on 6 March 2025, awaiting FCDO comments to finalise.

There remain a small number of items that need further iteration and finalisation, including:

- The Annual Consortium Review (ACR) needs to be finalised and implemented in full, contributing to and synchronised with annual reporting cycles. This is a critical piece of assurance, now overdue, required by FCDO for accountability of core consortium members. The ACR supports the FCDO in oversight over CCG but is also intended to provide CCG’s management with insight into the performance of different groups within the consortium, and empower them to take corrective action as and when necessary.
- The Value for Money Framework, which is currently in an advance draft format, has been agreed and measured for the purposes of this annual review. The framework has advanced significantly since the last annual review but requires some further adjustment before being considered final. Further discussion is provided in the Value for Money section of this review.
- The Monitoring and Evaluation (M&E) strategy is expected to be finalised shortly after the annual review, using inputs from the OPM authored Management Review to refine and finalise.
- Further engagement between FCDO and CCG is required on the methodology for measuring CCG’s contributions to green infrastructure investments, to ensure this methodology is mutually agreed upon and implemented. This will also be a useful tool in the measurement of end-of-programme cost effectiveness.
Phase 1 of CCG’s independent evaluation was completed in May 2024, with the finalisation of a report including key findings and practical recommendations. The evaluation stated, in summary:

“CCG is making substantive progress against its ToC and log frame. In its more advanced national programmes such as Kenya, Zambia and Laos, it is positioning itself well to eventually achieve its intended outcomes of embedding CCG research products and tools into national planning processes… this evaluation’s analysis of CCG’s peer reviewed journal output to date found that it is adding material that is pushing the boundaries of academic thinking”

The evaluation offered a number of practical recommendations to maximise CCG’s impact through improvement (or improved articulation) of research focus, partner engagement, management, research commissioning, capacity building efforts and Gender, Equity and Social Inclusion (GESI) considerations. Following finalisation of OPM’s evaluation report, CCG produced a document in response, reflecting on recommendations and detailing how these would be addressed. The management response has been accepted by FCDO, with corresponding actions continuing to be monitored – some of these are paused pending confirmation of future year budgets, and many have steered the generation of strategic documents and workplans. An update to the management response has been provided as part of this year’s annual reporting.

Major lessons and recommendations for the year ahead

Over the course of this review, and in consultation with CCG’s leadership, the following recommendations are made, to be progressed in the coming period and reported against in the following annual review:

1. Finalise and implement in full the Value for Money Framework.
2. Finalise and implement in full the Annual Consortium Review (ACR), synchronised with annual reporting cycles.
3. In considering the approach to budget reductions, protect CCG’s ability to engage with researchers and institutions from LMICs (proportionate to the scale of budget reductions), whether through the Southern Partners Fund, Flexible Research Fund, Engagement Fund or otherwise (including through co-funding opportunities).
4. Continue to develop the co-funding strategy, and model, articulating CCG’s offer and achievement of outcomes (including reporting on levels of investment attributably influenced) to current and potential funders. Keep FCDO informed of high-potential (or confirmed) co-funding partners.
5. Develop and implement a formal conflict of interest policy, to be mainstreamed into CCG contractual engagements at earliest opportunity, following the finalisation of the policy.
6. Respond to recommendations made in the Management Review carried out by OPM
7. Develop a process for proactive prioritisation of CCG’s research and uptake activities and agree this with the FCDO, by end of October 2025, ahead of potential budget reductions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

As set out in the FY22/23 Annual Review, CCG’s Theory of Change (ToC) was revised in early 2023 in a process led by the consultants carrying out the independent evaluation, with input from senior representatives from the programme and from FCDO. The ToC remains unchanged since then and is provided on the following page. A narrative accompanying the ToC diagram has since been developed and is available at Annex A. In short, CCG provides developing economies and international organisations with the necessary evidence, data, and tools to inform policy interventions and investments, so that these may most effectively contribute to equitable low-carbon economic development in low- and lower-middle income countries.

The outcome and impact statements are unchanged from the 2023/24 annual review, and remain as follows:

Outcome: Participating countries, regions, and organisations are using CCG knowledge products and activities to set energy, transport, and other policy, planning, and programming with stronger or more realisable climate compatible growth ambition.

Impact: Improved climate compatible growth for developing countries in Africa, Asia and other regions through breakthrough increases in the level of investment – or reorganisation of spend patterns – in infrastructure, services, and policy. These accelerate economic growth and decelerate GHG-emissions per unit of growth.

The agreed indicators for Impact and Outcome monitoring remain unchanged from the previous annual review. Impact indicators are not monitored or reported on an annual basis. Achievement against outcome indicators is discussed in the following section.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

CCG has made good progress against agreed outcome targets in this reporting period, summarised in the below table. Outcomes 1, 2, 3, and 5 met or exceeded the high target for the period, with outcome 4 meeting the low target. All targets and achievements are cumulative.

Outcome Indicator	Indicator Description	Target for 2024/25	Achievement in 2024/25
OI.1 CCG knowledge products used for decision-making	# of instances of CCG products and activities used by countries and international organisations for policy or investment decision-making.	9/11/13	13 (8 new) / High target met
OI.2 Nationally embedded processes	# of instances in which countries have embedded CCG knowledge products into their institutional planning and policy development processes	6/8/10	11 (7 new) / High target exceeded
OI.3 Internationally embedded processes	# of instances in which international organisations (IGOs, IFIs) revise their engagement processes based on CCG products and activities	10/11/12	14 (6 new) / High target exceeded
OI.4 Use of CCG knowledge products in educational institutions	# of instances of uptake of CCG knowledge products in teaching and research within a university or degree issuing research institute	8/10/12	8 (one new) / Low target met
OI.5 Academic influence	# of publications, datasets, and software repositories with more than 15 citations.	20/23/26	29 (14 new) / High target exceeded

Details of each instance of outcome achievement are provided in Annex B.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

CCG is currently the UK’s apex offer to developing economies on energy systems, and one of a small number of interventions that engages on transport systems decarbonisation and critical minerals. The programme’s activities and theory of change align with UK Ministerial priorities on green and inclusive growth, and on continued UK leadership of clean energy roll-out. It plays an important role in meeting the UK’s commitment to international climate finance targets, as well as operating as a key programme under both the £1bn Ayrton fund and the Green Cities, Infrastructure and Energy Center of Expertise (GCIE COE). In its fifth year CCG is a mature programme with established, but continually improving administrative/management systems and processes, and hosts a consortium of world leading academics on energy systems, transport decarbonisation and critical minerals.

The programme has scored an A against its logframe targets and is meeting or exceeding outcome targets. Given this, and its strategic importance within the FCDO’s research portfolio and wider UK offer, the programme should continue.

## C. DETAILED OUTPUT SCORING

Output Title	PARTNERSHIPS: National & regional partnerships build and maintained to co-create research agendas, build capacity, and drive evidence uptake
Output number:		1	Output Score:	A
Impact weighting (%):		45	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 - Building and Maintaining communities, fora, processes etc	# of active regional or international communities that CCG is providing input to annually (cumulative) / Low/Medium/High Target: 12/14/18	Achieved: 14 (4 new) / Medium target met
1.2 – Partner-country special interest groups	# of proposed special-interest-groups & initiatives with annual workplans in countries that support CCG country-programming (cumulative) / Low/Medium/High Target: 20/24/30	Achieved: 27 (11 new) / Medium target met
1.3 – Uptake and engagement activities	# of knowledge management, research uptake and communications-engagement activities (cumulative) / Low/Medium/High Target: 700/750/800	Achieved: 711 (212 new) / Low target met
1.4 – Capacity Building	percentage of participants at capacity building events who would recommend the event to peers. / Low/Medium/High Target: 85%/90%/95%	Achieved: 98.4% / High target exceeded
1.5 – Co-creation events	# co-creation events that result in joint outputs with partners (cumulative) / Low/Medium/High Target: 125/135/145	Achieved: 141 (36 new) / Medium target met
1.6 – Development of teaching materials	# online learning units developed (or significantly revised) for uptake in government, IO, NGO or university knowledge Management or teaching activities (cumulative) / Low/Medium/High Target: 600/620/640	Achieved: 663 (113 new) / High target exceeded

Briefly describe the output’s activities and provide supporting narrative for the score.

This output area measures progress in CCG’s partnership activities, including Country Partnerships and International Partnerships, with the aim of ensuring that CCG knowledge products are informed by demand and context, and ensuring that that CCG evidence has in-built routes to uptake. All indicators for this output at least exceeded the low target, with high targets exceeded in two instances. As a result, Output Area 1 scores an A for this review. The below section covers Country Partnerships first, followed by International Partnerships.

Country Partnerships

CCG has established Country Partnerships in six countries; Ghana, Kenya, Zambia, Lao PDR, Vietnam, and India, and two additional nascent partnerships, in Nepal and Malawi. Country Partnership activities are guided by strategies co-created by CCG and Country Networks, and are informed by demand from government and academic engagement, and facilitated through engagement with FCDO posts.

The ways in which CCG country partnerships engage with FCDO posts (i.e. British High Commissions and Embassies) varies by country, according to the level of demand and the ways of working at post. CCG Country partnerships work with country programmes (as with collaboration on a workshop with the Green Cities and Infrastructure Programme (GCIP) in Accra, Ghana), respond directly to FCDO Post requests (in the case of Vietnam where a request was made to support Vietnam’s Ministry of Finance incorporate geospatial planning in Vietnam’s 2045 national strategy), working with multilaterals and FCDO posts (as was the case in Zambia where CCG collaborated with the World Bank, through discussions with the FCDO staff in Lusaka, in support of Zambia’s Country Climate and Development Report (CCDR) for Zambia’s energy sector).

Through this annual review, FCDO posts were requested to reflect on CCG’s engagement with them and their agenda. British Embassy Hanoi commented on the strength of CCG’s engagement with in-country partners and the appreciation of CCG’s support in response to direct requests, as well as the improved alignment and coordination with other UK initiatives (such as the Just Energy Transition Partnership – JETP, and the Green Cities Infrastructure Programme – GCIP). Continued pro-active engagement is required to ensure a clear and coordinated UK offer in partner countries.

As indicative, non-exhaustive highlights from three of the country partnerships (many of which are contributing to outcomes as per Annex B):

Kenya: CCG partnered with the Ministry of Energy and Petroleum to accelerate the Kenya National Energy Policy 2025–34 draft, promoting inclusive stakeholder engagement and integrating Gender, Equality, Disability, and Social Inclusion (GEDSI)-related policies for the first time. The CCG Kenya Network provided support for the delivery of the implementation of the Kenya Energy Transition and Investment Plan. This project was completed with series of well-received outputs: a Robust Decision-Making workshop; a comprehensive energy policy map; a GEDSI vulnerability analysis; and an engagement and communications plan.

Zambia: CCG has supported the development of a National Finance Strategy for the country’s Integrated Resource Plan (IRP). The Finance Strategy aims to unlock funding for Zambia’s electricity infrastructure and ensure the successful implementation of the IRP. CCG has collaborated with the Ministry of Energy and CIG Zambia to co-create a Whole Energy System Model, embedding the CCG curated OSeMOSYS tool, in service of implementation of the IRP. CCG has delivered a series of training and co-creation workshops in collaboration with the Zambian Government, on continued use of these tools. CCG support has also led to the establishment of the ‘Sustainable Urban Mobility Advisory Committee’ (SUMAC) which was set up in collaboration with the Zambia Institute for Policy Analysis and Research and is being co-led by the Zambian Ministry of Transport. SUMAC aims to support Lusaka in improving policy and implementation for public transport, enhancing cycling and walking infrastructure, reducing traffic congestion, promoting road safety, and fostering an inclusive and accessible urban transport system.
[note] Co-created with the Government of Zambia’s Ministry of Energy and the FCDO-funded programme CIG-Zambia. The IRP is a strategic document that outlines the power sector investments required to support increased industrial and economic development, also addressing sustainability, climate change, environmental protections, job creation and gender and social inclusion. Summary report available here.
[note] Counted as an outcome as per Annex B, as the SUMAC has become a platform that the Ministry of Transport now utilises as a means to engage with stakeholders through, as part of engagement on new and existing policy.

Vietnam: CCG contributed to the National Action Plan on Circular Economy through a collaboration between Country Partnerships, CCG Sector Interactions, the National Economics University and the Ministry of Natural Resources and Environment. Further achievements include embedding a CCG OpenLearn Geographic Information System (GIS) best practice course, which has been integrated into the Geospatial Data, Best Practices for Collection and Management Masters course at the National Economics University.

International Partnerships

International partnerships have made strong progress on outputs over the year, including through a growing workstream on implementation of the data-to-deal framework, detailed in Box 1. Highlights include:

- Major analytical work on transport decarbonisation pathways in partnership with the Asian Development Bank (ADB)
- Support for the recruitment of an Energy Transition Expert (also to serve as a liaison with CCG) within the African Development Bank. The recruited expert will be embedded in AfDB’s Sustainable Energy Fund for Africa (SEFA), and will play a critical role in facilitating research collaboration between SEFA and CCG while having direct supervisory responsibilities for AfDB/SEFA clean energy projects.
- Signing of grant agreements with the 2050 Pathways Platform and the French Development Agency (AFD), which will leverage co-funding to support Data-to-Deal country engagements in Botswana, Ghana, and Uganda
- Support to the launch of the African Institute for Sustainable Energy and Systems Analysis (AISESA), a pan-African academic network that aims to serve as a platform for African energy, climate and sustainable development scholars, and support evidence based decision making across the region.
- The co-convening of a data-to-deal workshop (titled ‘Advancing Capacity-Building and Financial Mobilization for the Energy Transition‘) in Paris with the IEA in December 2024. The workshop was attended by sector experts and public and private finance institutions to explore practical strategies to transition from decarbonisation planning to investment.
  Box 1: Data to Deal

  The Data to Deal (D2D) framework is a seven-step formalisation of the activity pipeline from high-level climate ambition to implementable investment plans. The pipeline emerged through the study of successes achieved by Costa Rica in securing funding for its climate transition.

  The seven steps of the D2D pipeline are:

  1. Politics: Garnering high-level support for decarbonisation and inclusive growth.
  2. Preparation: Establishing the foundations of institutional capacity.
  3. Vision: Aligning climate change objectives with broader development goals.
  4. Modelling: Conducting deliberative quantification of scenarios.
  5. Consultation: Engaging inclusively across stakeholder groups.
  6. Operationalisation: Enhancing the policy and regulatory framework.
  7. Finance: Developing investment plans and financing strategies
  D2D is not a prescriptive workflow, rather a framework of options to support national governments and stakeholders to enhance their core functions and capabilities. CCG has a suite of existing tools, and engagement modalities, that address each of these steps.

  CCG is convening expert working groups, with membership from relevant international organisations, to steer CCG (and broader) engagement on each step.

  In development and refinement of the D2D framework, CCG has built a broad coalition of international partners, including the Agence Française de Développement (AFD), Green Grids Initiative (GGI), 2050 Pathways Platform, Sustainable Energy for All (SE4ALL), the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) the Global Green Growth Institute (GGGI), the World Bank, the International Renewable Energy Agency (IRENA), the International Energy Agency (IEA), the World Resources Institute (WRI), and the Inter-American Development Bank (IDB), African Development Bank, the Glasgow Finance Alliance for Net Zero (GFANZ) among others. These partners are valuable stakeholders in the continued development and uptake of D2D products.

  A detailed articulation of the D2D framework is available here.

  Case studies are also available for Costa Rica, Chile, Dominican Republic and Uruguay.

The International Partnerships team also oversees capacity building efforts and events, including three face-to-face Energy Modelling Platform (EMP) events that took place within the reporting period, hosted in Ghana, Italy and Argentina – the latter of which was co-hosted with the University of Costa Rica, and co-funded by the World Bank and 2050 Pathways Platform. Over 200 participants took part in these training events, representing 46 different countries. A substantial number of participants were sponsored to participate through partners such as the World Bank and Sustainable Energy for All. Total co-funding for these events, in this reporting period, is estimated at £200,000. Separate, on-demand, training events were also delivered in India, Sierra Leone, Zambia, and South Africa.

CCG Hosted funds for commissioning demand-led research

In service of building and nurturing research partnerships, CCG hosts a number of ‘funds’ that serve as mechanisms for the commissioning of demand-led and responsive research. These funds include:

- The Flexible Research Fund (FRF). The FRF is CCG’s mechanism for open calls for proposals, and aims to increase the diversity of researchers and institutions engaged in CCG, by mandating that a minimum of 40% of project budgets are allocated to researchers or institutions from Low- and Lower-Middle income countries.
- The Southern Partners Fund (SPF). The SPF funds projects carried out by research teams in partner countries, responding to demonstrated demand and facilitating enhanced collaboration between CCG consortium members and institutions in partner countries.
- The Engagement Fund (EF). The EF aims to contribute to partner-led initiatives, such as the Transport Data Commons Initiative, where a small volume of funding has the opportunity to significantly advance outcomes in line with CCG’s theory of change.
- The Agile Fund – a flexible resource that allows CCG researchers to work on specific projects in service of CCG outputs.
An agreed budget was set for the SPF and FRF for the March 2025 - March 2030 period to allow for continuity and long-term planning. However, given UK ODA budget uncertainties, the FRF contracting process was paused in Q4 of FY 2024/2025. CCG’s directorate had approved 11 new projects, but the decision to pause further contracting was made after only 5 of these had been contracted.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to this output have been made during the past year. The logframe targets will be mutually agreed early in the coming period, calibrated against prior achievement, level of ambition, and available resources.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

From the previous annual review:

Country Partnerships and Affiliate Countries Sustainability Strategies: There is a risk that outcomes achieved in CCG Partner Countries and Affiliate Countries will erode once the programme leaves. By March 2025 CCG to have developed a strategy setting out how it will ensure long-term sustainability of these partnerships.

The plan for mitigating this risk was presented in a joint workshop in Q1 of the financial year, and was accepted by FCDO. CCG country partnerships consider long-term sustainability in each of their country partnership strategies.

A key lesson, for the coming period, is the importance of flexible and responsive funding mechanisms (as described above) for the integration of LMIC partner researchers and institutions. Pending budget clarity, it will be important to understand how CCG can best leverage funds for this purpose, whether through the FRF and SPF or through other mechanisms. These mechanisms are particularly important given CCG’s focus on co-creation, and demand-led applied research.

Additionally, following this annual review, it will be important for deeper consideration of CCG’s country partnerships’ ability to develop the science-policy interface in partner countries – supporting, through political-economy informed engagement, the relationship and information exchange between technical experts and policymakers. This will feature in discussions on CCG’s partnerships, and in consideration of the best-fit modalities for knowledge-product uptake.

In discussions on budget prioritisation, and when considering the continuation of funding mechanisms such as the Southern Partners Fund and the Flexible Research Fund, it will be important to safeguard CCG’s ability to respond to research needs emerging from country partnerships, whether through existing or new modalities, or a combination.

Output Title	RESEARCH: Additions of evidence, insight, frameworks, methods, data, tools, and their applications (collectively these shall be referred to as ‘knowledge products’).
Output number:		2	Output Score:	A
Impact weighting (%):		45	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 – Evidence Published (externally peer reviewed)	# of externally peer-reviewed knowledge products (such as journal papers, books, book chapters etc.) / Low/Medium/High Target: 105/114/123 / 2.1a: with 40% female authorship / Target: 25%/45%/55% / 2.1b: with 40% LMIC authorship / Target: 30%/40%/50% / 2.1c: with female authors first listed / Target: 15%/20%/25% / 2.1d: with LMIC authors first listed / Target: 10%/15%/25%	Achieved: 108 – Low target met (40 new) / 2.1a – 57.5% - High target exceeded (23 of 40) / 2.1b – 20% - target not met (8 of 40) / 2.1c – 57.5% - High target exceeded (23 of 40) / 2.1d – 5% - target not met (2 of 40)
2.2 – Evidence published (not externally peer-reviewed)	# of internally reviewed knowledge products published / Low/Medium/High Target: 270/290/310 / 2.2a: with 40% female authorship / Target: 25%/45%/55% / 2.2b: with 40% LMIC authorship / Target: 15%/25%/35% / 2.2c: with female authors first listed / Target: 15%/20%/25% / 2.2d: with LMIC authors first listed / Target: 10%/15%/25%	Achieved: 338 – High target exceeded (162 new) / 2.2a – 45.6% - Medium target met (74 of 162) / 2.2b – 64.2% - High target significantly exceeded (104 of 162) / 2.2c – 38.89% - High target exceeded (63 of 162) / 2.2d – 58% - High target significantly exceeded (94 of 162)
2.3 – Open-source tools, data, and software	# instances open-sourcing and hosting of (i) principles, (ii) frameworks, (iii) standards, (iv) methods, (v) workflows (vi) software & (vii) datasets / Low/Medium/High Target: 410/430/450	Achieved: 446 – Medium target exceeded (53 new)
2.4 – Review Articles	# of review articles published as pre-prints. / Low/Medium/High Target: 2/3/4	Achieved: 2 – Low target met (1 new)

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Area 2 measures CCG’s research and knowledge product outputs, including externally peer-reviewed and internally reviewed research publications, datasets, tools, and software. For the first time this round of reporting includes sub-indicators reflecting the lead authorship by female researchers and by researchers based in low- and lower-middle income countries, in addition to broader contributions by female authors and researchers from low- and lower-middle income countries (which has been measured in previous years). Six indicators met or exceeded the high target, two met or exceeded the medium target, two met or exceeded the low target, and two targets were not met. Overall, the output area scores an A.

The authorship of peer-reviewed papers by LMIC researchers (Indicators 2.1b, 2.1d) failed to meet agreed targets, although does show an improvement on the previous reporting period. However, involvement of LMIC researchers in internally reviewed documents has exceeded targets.
[note] In FY 2023/24 indicator 2.1b scored 9.7% with three papers substantively contributed to by LMIC authors

The causes for lower than expected engagement of LMIC researchers as lead-authors in peer-reviewed CCG publications need to be considered, whether this is a result of academic incentives within the core CCG consortium, or a shortcoming in CCG’s approach to inter-regional research collaboration and empowerment of country partners. An initial review of the sources of internally reviewed and externally peer-reviewed papers with substantive contributions (i.e. meeting indicators 2.1b or 2.1d) from LMIC authors indicates:
- Internally reviewed documents are largely generated by attendees to the EMP training workshops, supplemented by documents produced through Country Partners, Southern Partners Fund and Flexible Research Fund projects
- Sources of externally peer-reviewed papers with substantive LMIC authorship are more mixed – of the eight recorded instances, three are results of engagements with the Kenya country partner network, two are publications as a result of research deliverables from student theses, one is a result of attendance an EMP training event, one a result of an SPF project on critical minerals, and one a result of CCG programmed research.
In the previous annual review it was suggested that CCG support ‘mini-sabbaticals’ and continue engagement with researchers and EMP participants to help them convert the relatively high proportion of internal reports authored by LMIC researchers into externally peer-reviewed publications thereby contributing to Indicators 2.1b and 2.1d. Additionally, CCG offers ‘Scholar Bootcamps’, intensive capacity building activities with specific end-products (including peer-reviewed publications) in mind. The extent to which these activities can facilitate further participation of LMIC researchers in production of peer-reviewed articles should be considered further. It is likely, however, that in the coming year there will be improvement in LMIC authorship of peer-reviewed articles, given the pending launch of a special issue of a journal, intentionally and explicitly providing a platform to graduates of CCG’s EMP capacity building courses.

The proportion of contributions from female authors has increased from the previous reporting period, and has exceeded the medium target in one instance and exceeded the high target in three instances. Given that the energy and transport sectors are historically male-dominated, and even more so in LMICs, the level of female authorship in CCG knowledge products is a positive and notable indication of CCG’s intentional inclusion of female researchers. The targets for engagement should be reviewed to ensure they remain realistic and ambitious, but no further action is required.
[note] Scores from the previous reporting period: 2.1a – 48%, 2.2a – 39%

Examples of externally peer-reviewed and internally reviewed knowledge products with a high potential for impact, published in FY 2024/25, include:

Externally peer-reviewed: “Inconsistent measurement calls into question progress on electrification in sub-Saharan Africa”, Hirmer, S., Tomei, J., Yang, P. et al.

  - The paper, published in Nature, highlights significant uncertainties in electricity access statistics, which may result in systemic overestimation of electricity access rates in sub-Saharan Africa, therefore understating the need for finance and policy action to ensure last-mile delivery. The paper calls for a re-evaluation of definitions of electricity access, and the methodologies used to calculate access rates.

Externally peer-reviewed: “Value addition for who? Challenges to local participation in downstream critical mineral ventures in Zambia”, Cervantes Barron, K. et al

  - The paper critically assesses the potential for localised value addition, and the challenges faced to increased value addition, in critical minerals extraction industries in Zambia. It highlights three key challenges; i) dominance of foreign-owned entities in the upstream extractives sector, ii) an unfavourable landscape for local company participation, and iii) A lack of enabling environment for value addition activities. Recommendations are made to address these challenges, and for areas of policy reform and further research.

Internally reviewed: “Climate Finance Principles to Unlock Green Grids Financing”, Fuselli, L., Blyth, W., Brazier, R., Gullberg, M., Stewart, M., & Foster, V.

  - The Green Grids Initiative’s Climate Finance Principles aim to accelerate investments in grid infrastructure - an essential step for global decarbonisation. With over 3,000 GW of renewable projects awaiting grid connections, inadequate grid capacity hinders both energy security and progress toward net-zero goals. Developed in collaboration with finance and infrastructure experts, these 10 principles guide climate investors in identifying impactful grid projects.

Internally reviewed: “CLEWs Model for India: Coal Retirement vs Forest Cover for Lowering Emissions”, Gupta, M.

  - This paper is a result of the author’s attendance to the EMP Global workshop. The report provides a comprehensive analysis, utilising CLEWS, of two major policy interventions for CO2 reduction in India; Coal power-plant retirement, and forest cover increase. The analysis provides strong evidence for the prioritisation of coal power-plant retirement as a more effective strategy for reducing emissions.
The full list of externally peer-reviewed publications is available in Annex C.
Over the reporting period CCG has published 53 new open-source datasets, tools, software, and software repositories, taking the cumulative total to 446. These open-source datasets and tools are key elements of CCG’s training offer and are freely available for access and use by researchers, students, and practitioners. These products have been downloaded tens of thousands of times and form part of capacity building programmes within the International Energy Agency (IEA), International Atomic Energy Agency (IAEA), the World Bank’s ‘Energy Management Assistance Programme’ (ESMAP) and other organisations.

One new review article has been published this reporting period, taking the cumulative total to two. The published review paper is a systematic literature review regarding current and potential future uses for OSeMOSYS. This target is intended to incentivise CCG to produce review and synthesis papers as a means of more holistically reflecting the state of knowledge, and CCG advances to the state of knowledge. The relatively low number of review papers published by CCG reflects the relatively low proportion of review papers in the academic fields CCG works within, and the relative lack of incentives for researchers to develop and publish these documents. The logframe indicator and targets should be reviewed in the coming period to ensure that targets are ambitious but realistic, and that CCG is most effectively contributing in this space, whether through synthesis/review documents or otherwise.
[note] “Uncovering the Applications, Developments, and Future Research Directions of the Open-Source Energy Modelling System (OSeMOSYS): A Systematic Literature Review”, Plazas-Niño, F., Tan, N., Foster, V., Howells, M., & Quirós-Tortós, J. (2024)

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No major changes have been made to this output. Four additional sub-indicators have been introduced, tracking the contribution of female first- authors and first-authors from LMICs for externally peer reviewed and internally reviewed publications/knowledge outputs. These measures are additional to previous indicators measuring the percentage of papers with at least 40% of named authors being female or from LMICS respectively.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against previous recommendations is summarised earlier in this review.

As a result of this annual review, we recommend that CCG conducts a critical assessment of indicators 2.1b and 2.1d (regarding the authorship of peer-reviewed papers by LMIC researchers). Given the low scores achieved for LMIC author contributions to externally peer-reviewed publications, the underlying reasons for this should be surfaced, measures proposed to address this relative under-representation (including existing measures such as the mini-sabbaticals, and scholar boot-camps), and logframe targets calibrated to reflect ambitious but achievable goals. The engagement with country partner networks in the authorship of peer-reviewed papers should be considered, including the relatively high representation of the Kenya country network in peer-reviewed outputs should be reflected on. This assessment and agreement of logframe targets, should be completed by the end of October 2025.
[note] The only represented country network, making up three of the eight recorded instances of indicator 2.1b

The results of this assessment will also be relevant for CCG’s approach to long-term engagement of Global South Researchers, which will need to be reviewed, and potentially revised, in light of pending budget confirmations. Engagement of LMIC researchers and institutions is also relevant in discussions around the FRF and SPF funding mechanisms, and should be considered appropriately in discussions on the continuation and/or modification of these funds.

Output Title	MANAGEMENT AND DELIVERY: Joined up analysis, workplans and partnership
Output number:		3	Output Score:	B
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 – x-workstream sprints	# of cross-Workstream Sprints that include an element of how the research would contribute to CCG's route to impact. / Low/Medium/High Target: 7/8/10	Achieved: 8 – Medium Target met (2 new)
3.2 – Policy and programming engagement across HMG	# of instances of CCG engaging with other HMG programmes or policy teams (within the FCDO or other government departments) to deliver jointly developed research outputs or where CCG’s engagement substantively influences policy making or programme design. / Low/Medium/High Target: 12/14/19	Achieved: 13 – low target met (3 new)

Briefly describe the output’s activities and provide supporting narrative for the score.

CCG conducts cross-workstream sprints (a short-duration intensive period of collaboration) to facilitate collaboration between researchers working on separate workstreams. Two cross-workstream sprints were carried out in the reporting period, focusing on development of CCG’s Gender, Equity and Social Inclusion (GESI) strategy and on Critical Minerals in Africa. The GESI sprint has resulted in a finalised version of CCG’s GESI Strategy, discussed elsewhere. The Critical Minerals sprint involved two projects; one on a geospatial analysis of increased critical mineral processing across 14 countries in Southern Africa, and the other on a deep dive on local participation in the mining sector in Zambia, building on an early Southern Partner Fund supported study. Related to the second sprint, CCG also hosted a well-attended and well received event with Chatham House in 2024, titled ‘Beyond extraction: Value addition for Africa’s critical minerals’ which led to publication of an event brief: Critical-Minerals-_20241220.pdf
[note] Angola, Botswana, Burundi, DRC, Kenya, Madagascar, Malawi, Mozambique, Namibia, Uganda, South Africa, Tanzania, Zambia, and Zimbabwe

Indicator 3.2 reflects CCG’s intent to respond to engage with FCDO country offices and other UK Government departments as a means to support uptake of CCG evidence and knowledge products, and to contribute to UK efforts in international climate action. Three instances of such engagement have been recorded in this reporting period:

Engagement with the Department of Energy Security and Net Zero (DESNZ) in the further development of the Green Grids Initiative (GGI). Since September 2024 CCG has worked closely with DESNZ to promote grid planning, including co-producing a policy brief with the GGI team for COP29. CCG has coordinated the design and delivery of the Electricity Transition Playbook, supported stakeholder mapping, and convened country-level engagement strategies. CCG has played a leadership role in the newly spun-out GGI management structure, bring a focus on practical implementation, resulting in renewed political traction and country uptake, including workshops in Argentina, Bangkok, New York. CCG’s strategic input has directly shaped the direction and programming of GGI under UK international climate leadership.

Engagement with the British High Commission in Accra, Ghana. In September 2024, CCG met with stakeholders from the Ministry of Finance in Accra. This initial engagement, coordinated with the BHC Accra team, resulted in a clear request from national stakeholders for further technical and financial support. In December 2024, CCG secured a grant agreement with the 2050 Pathways Platform, with co-funding earmarked for collaboration with the Ministry of Environment, Science, Technology and Innovation (MESTI). This enabled the launch of a joint work programme focused on modelling long-term climate pathways and enhancing institutional capacity — directly supporting HMG’s objectives on international Long-Term Strategy support and UK-Ghana climate cooperation.

Engagement with the British Embassy Buenos Aires, Argentina. In February 2025, during the Energy Modelling Platform for Latin America and the Caribbean (EMP-LAC) held in Buenos Aires, CCG collaborated with the British Embassy in Argentina to convene a high-level meeting with senior government officials from several Latin American countries. The Embassy’s support was instrumental in securing participation from Argentina’s stakeholders, and in positioning the UK as a strategic partner on long-term energy planning and modelling.
CCG has made good progress in this output area. Increased levels of cross-UK Government engagement could be facilitated through clear and pro-active articulation of CCG’s potential offer (including different approaches taken by country partnerships, discussed in Section A of this review) to other departments, programmes, and country offices. This should be pursued in the coming period in partnership with FCDO team. Indicator targets will be reviewed and agreed jointly between CCG and FCDO.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No major changes have been made to this output in the review period. Targets for the coming period will need to be calibrated and agreed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

No recommendations specific to this output area were made in the previous review, nor are any made specifically as part of this review.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

The core of CCG’s spending profile is through long-term programmed research projects, delivered through its consortium of partners. Additionally, a number of responsive research commissioning elements (including the Flexible Research Fund and the Southern Partners Fund) allow for catalytic and demand-led project implementation, bringing in researchers from outside the consortium. A proportion of CCG’s spend supports collaboration with international organisations in the interest of achieving clear outcomes. Given CCG’s largely internal allocation of resources within the consortium (as per mutually agreed strategies), the programme management has worked to develop a value for money framework to evaluate and drive value for money across partners.

VfM performance compared to the original VfM proposition in the business case

As part of the CCG Independent Evaluation in FY 23/24, the Evaluators worked with CCG to develop a structured VfM framework with a set of indicators against each of the five Es of FCDO’s Value for Money Framework: economy, efficiency, effectiveness and equity (including gender equality and disability) and overall cost-effectiveness. Overall cost-effectiveness will be measured at the end of the programme only. Since the previous annual review and in consultation with FCDO, CCG has iterated its VfM framework to align better with CCG’s cost drivers and research commissioning modalities, with efforts made to benchmark specific metrics.
A key difficulty has been the reconciliation of the economy criteria with different downstream partner institution procurement policies (e.g. different Higher Education Institutions will have different policies on salary scales, travel and accommodation allowances), and arguably the treatment of the VFM framework as an overriding procurement policy. There may be value in separating these elements into separate documents. A key recommendation from this annual review is to finalise and agree the value for money framework.
CCG have reported against the current iteration of the framework for the sake of this annual review. The results are as follows:

While the current iteration of this framework enables a degree of evaluation, we recommend the following considerations for pending finalization:
- The Equity metric should make fuller use of suggested measures contained within CCG’s GESI strategy.
- The Economy metric should separate out elements of procurement-policy setting and consider these in a separate document, if necessary
- Agreement should be reached on the process around delegated approval and reporting of exceptions/edge cases.
- Future revisions to logframe indicator targets should reflect that achievement against these will have VFM scoring implications

Assessment of whether the programme continues to represent value for money

CCG continues to represent good value for money, as evidenced by the scoring against its VfM framework, as well as its achievement against ambitious outcome and output targets. CCG represents the UK’s primary offer for applied research on energy systems, as well as the energy-transport nexus and on critical minerals. As set out elsewhere in this review, CCG’s work is strongly aligned with FCDO and UK Government priority objectives.

E: RISK

Overview of risk management

In response to recommendations made in the 2023 Annual review, CCG developed an enhanced risk management strategy (ERMS), given that the volume of CCG activities and the complexity of their management was increasing, requiring more proactive risk management. The ERMS was finalised in November 2023, and has been revised within the current reporting period, in consultation with FCDO counterparts. The framework extends beyond risk related to key members of staff and now includes strategic and process related risks. In parallel, the risk register has been updated to align with CCG’s risk mitigation strategy, and to reflect changes to the risk profile.

The CCG risk framework has been updated with revisions to identified risks, mitigating actions and a review of the inherent risk assessment for each risk type. Some of these updates reflect CCG’s improved approach to risk management, including how the Code of Conduct is applied to new partner organisations, how the Due Diligence process is managed, and how the restructured Programmed Research can better mitigate risks associated with the commissioning of research. In this updated version, risks associated with specific workstreams only include those not otherwise covered in the risk framework to provide a more concise representation of risks and mitigations across CCG’s programming.

Programme risk appetites are set out below, all risks are within appetite. The programme has an overall risk rating of ‘Moderate.’

Strategy and Context: Moderate The principal ongoing risks related to operating within environments that may be unstable, for example potential disruption caused by governments or key policy makers changing in partner countries and/or project activities being disrupted by natural or climate-change related disasters. To date, however, these risks have not manifested and they remain moderate as they would affect only part of the project’s operations at a given time.

Financial and Fiduciary: Moderate Reductions in the FCDO’s research budget represent a major risk to CCG’s ability to continue to fund research and partnerships at the intended scale. This risk is being managed through close engagement between CCG and FCDO and mitigated through advanced notification of budget scenarios – allowing for proactive planning.

Policy and Programme Delivery: Minor CCG is a well-established programme with improved reporting and management processes. Insufficient senior management capacity has been a risk in previous years but is now being addressed through recent recruitments (including a Deputy Director and Senior Programme Manager). Insufficient capacity of Southern research partners is also a risk, and this has resulted in a higher time commitment from programme academics than expected in some cases. This is being managed through established quality assurance processes.

Public Service Delivery and Operations: Moderate CCG is delivered principally by a consortium of universities. The original rationale for selecting this model is set out in the Appraisal Case of the Business Case and has developed over time, particularly as CCG’s Country and International Partnerships have matured. However the consortium model reduces the level of competition within CCG’s delivery, and budget reductions are likely to result in the termination of the Flexible Research Fund (the main element of the programme for which competition is required for research funding), given that substantial overhead and administrative costs associated with the FRF are hard to justify.

Risks associated with the lack of competition within the programme are managed in two main ways:

- Independent external evaluation of the programme’s delivery and performance is provided by the Independent Evaluation (Phase 2 to commence in autumn 2025).
- Each year CCG is required to carry out an Annual Consortium Review (ACR) which assesses consortium member performance against both the Logframe and research strategy (further discussion of the ACR is presented in the following section).
Safeguarding: Minor CCG promotes an organisational culture that prioritises safeguarding. Loughborough University carries out due diligence check on CCG’s consortium members that includes a review of each organisation’s safeguarding policies. Where these are not judged adequate on their own, the individuals working on CCG are required to complete the safeguarding training developed by CCG prior to contracts being approved.

Reputational: Minor CCG has a rigorous approach to curating and quality assuring its data and tools, principally developed by the academics within the consortium before CCG was established and further enhanced as CCG’s visibility and scale increases. The risk of CCG models or data being publicly discredited is the only significant risk here, the majority of CCG research activities and topics pose little or no reputational risk.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The programme has a lean administrative team, although this has received much needed supplementation with the recruitment of the new Senior Programme Manager this year. While the administrative team has been supplemented, care must be taken to ensure that administrative and management burden is appropriately balanced between the Loughborough University based management and administrative team, and consortium members, the recent management review considers this in more detail. The CCG programme team benefits from the pooled expertise of all ten consortium partners, meaning that the programme has world-class academic expertise at its disposal, allowing for flexible and efficient deployment as required by programme activities. Where the necessary expertise cannot be sourced from within the programme, CCG continues to recruit external consultants to fill this gap. This has enabled CCG to respond to the changing demands of the programme quickly and efficiently, including responding to FCDO requests from both the centre and Posts.

CCG is required to conduct an Annual Consortium Review (ACR), where the performance of each of CCG’s units (teams/departments within HEI’s and other institutions) is evaluated through monitoring of their budget allocations and their level of contribution to CCG’s logframe outputs. This is an opportunity for CCG’s leadership to critically assess unit performance and, where necessary, take corrective action in cases of under-performance, and an important piece of assurance for FCDO.

Taken alone, the quantitative analysis produced through the ACR (i.e. comparison of budget allocation vs outputs produced) is a slightly blunt tool and so necessitates an accompanying narrative reflection on the broader contributions of units, including coordination functions, strategy development, partner engagement, sustained efforts and long-term initiatives. The existing methodology also requires discrete attribution of outputs to single units, where in fact many outputs are a result of cross-unit collaboration. CCG are iteratively improving the methodology for data collection and analysis, to maximise the value of the review. A key lesson from the previous ACR (covering 2023/2024) was the need for detailed output logging at the unit level, to enhance the precision of future assessments.

At present, the ACR process is out of synchronisation with annual reporting cycles, and the FY 2024/2025 is overdue. CCG have been requested to complete the FY 2024/2025 ACR as a priority, and to ensure that future annual reports are finalised alongside the ACR, using ACR results as inputs. By synchronising with annual reporting, it is hoped that the results and lessons of the ACR will be institutionalised and factor into CCG’s programme and performance management processes to a greater extent.

CCG’s PMU provides quarterly and annual reporting to FCDO, compiling achievements, progress, and issues arising from each programme component and workstream. The content and timeliness of reporting has improved over this reporting period, and the PMU has engaged constructively with FCDO requests and commissions for information, which often come at short notice and with tight timelines. CCG’s continued strengthening of management systems and reporting processes will reduce the time burden associated with responding to these requests in future.

The programme was allocated a budget of £13.2m for financial year 2024/2025, including £500,000 contribution to the Asian Development Bank for continued collaboration on transport decarbonization, and £162,000 to the African Development Bank’s SEFA programme for the recruitment of an Energy Transition Expert (who will also function as a liaison to the broader CCG programme). Separately, £709,000 has been allocated for non-ODA funding for continued work on Critical Minerals research (i.e. not from CCG’s business case), in addition to core ODA-funded work on Critical Minerals. In the 2025/2026 Financial Year, this non-ODA work will be funded from the CCG business case as per the business case amendment of May 2024.

As set out in the partner Contract Agreements, in this reporting period, the main project partners provided the Programme Office with quarterly finance reports and an invoice. The reports include: Statement of Expenditure, Activity Report and Budget Forecast for the following quarter. The Programme Office continues to experience delays with submission of quarterly financial reports and invoices from a relatively small number of the CCG University Partnership’s members, which has impacted on the broader programme’s ability to invoice FCDO on a timely basis. Further mitigation of this will be discussed following this annual review.

The CCG programme office operates within Loughborough University’s procurement systems and uses its supplier pool wherever possible, to minimise administrative spend and obtain good rates for travel and other expenditure. The University has a procurement procedure with multi-layer purchase approval processes, including the School Operations Manager and procurement/finance staff. Each of the programme’s partner institutions operates within its own institutional procurement frameworks, but all are (and will continue to be) reflected in CCG’s value for money framework.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Phase 1 of CCG’s independent evaluation was completed in May 2024, the conclusions and recommendations of which continue to be actioned as reported earlier in this review, as per the management response agreed with FCDO. A management review of CCG has been completed in April 2025, the recommendations of which will be responded to and/or actioned following this review.

CCG has developed a new Monitoring, Evaluation and Learning (MEL) framework, as per the recommendation set out in the independent evaluation. The MEL framework will be finalised in parallel with the actioning of management review recommendations, to incorporate any further guidance on this area.

In February 2025, the CCG PRO visited Laos PDR for a week to attend CCG’s annual country partnership workshop and spend time with the British Embassy Vientiane to ensure that all appropriate productive linkages with CCG’s work were being made. The workshop demonstrated excellent engagement from Laotian researchers and government stakeholders and was very well organised. Uptake of CCG’s offer by the Government of Laos could be stronger and CCG are acting upon this. Separately, the FCDO lead adviser attended the annual country partnership workshop in Kenya. Strong outcomes have been reported in Kenya, however the workshop did not sufficiently reflect the strength of engagement with Kenyan Government stakeholders – possibly due to staff turnover within the country partnerships team. A steer was given to provide a greater degree of support and guidance to the network, to ensure continued engagement and uptake of CCG knowledge products in Kenya.

Learning

CCG benefits from both internal and external learning. Externally, the independent evaluations provide a valuable and constructive independent perspective on CCG’s systems, processes, and achievements. Internally, CCG hosts twice-yearly general meetings with consortium members and FCDO, as well as smaller quarterly management meetings with FCDO – these meetings allow for open exchange on emerging issues, concerns and lessons learned. CCG’s Annual Consortium Review also serves as an opportunity to understand levels of performance and achievement across the consortium.

Date of last narrative financial report	July 2025	Date of last audited annual statement	November 2024

Annex A: CCG Theory of Change
# Introduction
Description of the Programme
The Climate Compatible Growth (CCG) programme aims to accelerate the rollout of improved infrastructure in developing countries to simultaneously reduce GHG emissions and increase economic growth. It conducts research and provides evidence and decision-support tools to help Low- and Middle- Income Countries decide how best to respond to the low-carbon transitions in energy, transport, industry, and other economic growth sectors. The majority of CCG’s activities are delivered by a core University Partnership, led by Loughborough University, and made up of University College London, Oxford, Cambridge, Strathclyde and Imperial Universities, the Open University, and KTH Royal Institute of Technology in Sweden together with the University of Cambridge-affiliated Centre for Global Equality and the Climate Parliament. Together with leading national and international organisations the partnership uses technological, economic, behavioural, political, and financial evidence to help countries deliver their low-carbon pro-poor growth agendas.

CCG Theory of Change
CCG’s Theory of Change sets the strategic direction for the programme. It defines the relationship between the issues that the programme is designed to tackle and the ultimate impact or real-world benefits that the programme is intended to have. This relationship is expressed in terms of the direct activities and outputs that the programme undertakes and the indirect outcomes and impacts it produces. These relationships are based on clearly identified assumptions which can be tested during the course of the programme.
The activities and outputs that the programme produces (such as research, knowledge creation, publishing of reports and training materials, developing national research partnerships, etc.) are within CCG’s ‘sphere of control.’
The programme’s outcomes are the changes in behaviour needed to effect change in the world. The CCG programme will have different levels of influence on different stakeholders, reflecting the range of other factors at play that are outside of CCG’s control. ‘Intermediate outcomes’ involve specific instances of behaviour change amongst partners that the programme works with. These are within CCG’s ‘sphere of direct influence.’ ‘Outcomes’ reflect longer-term systemic behaviour change amongst project partners and a wider set of stakeholders. These are within CCG’s ‘sphere of indirect influence.’
Impact is the ultimate goal or change in the world to which the programme aims to contribute. There are very many factors that determine this impact, so it is hard to attribute causality to the programme. Nevertheless, defining a quantifiable impact helps provide overall direction to the programme’s activities. The impact is within CCG’s ‘sphere of interest.’
The Theory of Change diagram (include in section B above) sets out these relationships visually. The narrative section provides further detail of each step, and the underlying assumptions.
Theory of Change narrative
## Problem statement
Low- and Middle-Income Countries’ (LMICs) inclusive growth ambitions to meet key sustainable development goals (SDGs) are hampered, in part, by insufficient and unsustainable investment in climate compatible markets and infrastructure.,, This arises partly from a lack of coherent policies, strategies, planning, regulations, and market systems, amongst regional, national, and sub-national governments and their development partners., Furthermore, knowledge and power asymmetries exist between national planners, policymakers & local-researchers on the one hand and development partners on the other. This can translate into a lack of widespread local ownership of national growth plans which restricts countries’ ability to plan for and negotiate investments appropriate to their needs.
[note] CDC, ODI 2016 “What are the links between power, economic growth and job creation?”. Development Impact Evaluation, Evidence Review.
[note] Bacon, R. and Kojima, M. 2016. Energy, Economic Growth and Poverty Reduction. World Bank, 2016 (PDF) Energy, Economic Growth, and Poverty Reduction: A Literature Review (researchgate.net)
[note] ODI 2019 Tracking G20 coal subsidies, available at: https://www.odi.org/publications/11355-g20-coal-subsidies-tracking-government-support-fading-industry
[note] Climate Policy Initiative. https://www.climatepolicyinitiative.org/gca-africa-adaptation-finance/barriers/regulatory-and-policy-barriers/
[note] Victor, D.G., Geels, F.W. and Sharpe, S., 2019 Accelerating the Low Carbon Transition: The Case for Stronger, More Targeted and Coordinated International Action, http://www.energy-transitions.org/sites/default/files/Accelerating-The-Transitions_Report.pdf
[note] Vivien Foster and Anshul Rana, 2020. Rethinking Power Sector Reform in the Developing World. World Bank, Washington DC. https://openknowledge.worldbank.org/bitstream/handle/10986/32335/9781464814426.pdf?sequence=10&isAllowed=y
There are multiple causes underpinning this challenge.
[note] Mulugetta, Y., Sokona, Y., Trotter, P.A. et al. Africa needs context-relevant evidence to shape its clean energy future. Nat Energy 7, 1015–1022 (2022). https://doi.org/10.1038/s41560-022-01152-0
- Support from development partners may lack coherence and capacity-strengthening, resulting in limited agency of LMIC analysts and decision makers. This includes, for example, the use of proprietary models and approaches that leave national governments with ‘black box’ solutions that limit their ability to make informed and adaptable decisions that can be adjusted as economic situations and needs change.
- This is exacerbated by an absence of a strong evidence-base for climate compatible growth policies that national planners can draw on, including a lack of accessible and appropriate open-data and open-source tools. There is also limited capability for local researchers and policymakers to use such tools and approaches to create and sustain a locally appropriate evidence base.
- Out-of-date processes that confine planning, operations and business models to sectoral silos miss the broader economic and cross-sectoral impacts and potential opportunities presented by the need to respond to climate change.
- Political economy factors have an important bearing on how decisions are made and which actors have the power to make them. These need to be considered when assessing how outcomes could be improved.
These underlying issues contribute to elevated levels of perceived risk, unfavourable investment conditions, challenges accessing international concessional climate finance, and a lack of investable projects that support climate compatible growth.
[note] World Bank 2019. Rebuilding Investor Confidence in Times of Uncertainty. https://openknowledge.worldbank.org/server/api/core/bitstreams/736358db-40d6-5ad3-8571-45c89ee8a697/content
## CCG’s approach to addressing these problems
The CCG programme is built on two key principles: the need for national ownership of strategic planning processes, and the importance of evidence-based policy making. CCG’s approach is to support an ecosystem of capacity, knowledge-products and partnerships. This enables agency of decision-makers in LMICs to develop nationally-owned appropriate growth strategies and pathways that can mobilise the required resources.
We believe that when delivered by nationally-owned processes, the facts regarding the suitability and alignment of climate compatible solutions with a country’s development interests will speak for themselves. This allows the programme to focus on creating evidence and empowering local decision-makers rather than lobbying for particular outcomes. This has two advantages. Firstly, relationships built on trust allow CCG to operate as ‘honest-brokers’ and ‘enabling-partners’ that help de-politicise decision-making to reduce risks and improve financial flows. Secondly, this helps deliver outcomes and impacts that can be nationally self-sustained in the longer-term beyond the lifetime of the programme.
A key example of how this is operationalised is ‘Data-to-Deal' (D2D), a process where a country carries out analysis, stakeholder consultation, cross-Ministry engagement; engagement with development partners and International Financial Institutions (IFIs). The aim is to strengthen the pipeline between evidence-based research, long-term strategy development, policy decision-making, and development of finance-ready infrastructure investment proposals.
## CCG Activities and outputs
To address the underlying issues outlined above, the CCG programme invests in the formation of national and international research-partnerships, programmed-research, and capacity building activities as described below.
CCG national partnerships
CCG’s national partnerships inform and demonstrate CCG’s route to impact by collaborating deeply in specific countries with key researchers, influencers, and decision-makers to co-create and apply CCG knowledge products. CCG currently has six national partnership countries: Lao PDR, Viet Nam, India, Kenya, Zambia and Ghana. There is an ambition to expand to more countries in the future.
National partnerships are a key part of CCG’s research uptake strategy. At a national level, this starts with trust-building scoping exercises and the selection of an in-country coordinator, generally at a research institution. This coordinator leads development of a country strategy in collaboration with CCG and key national stakeholders to identify research priorities for the country. This country strategy ensures CCG’s national activities are coherent with the whole CCG programme, aligned with country ambitions, and consider the political structures that enable decision making. Research activities are then organised through Special Interest Groups (SIGs) which are national collaborations focussed on different themes that work towards the country strategy. These comprise local expertise, stakeholders, and government. These collaborations lead to bi-directional capacity building, typically with: (1) tools and methods from CCG; (2) information and context from the SIG; and (3) through co-created knowledge product development and application. CCG also collaborates closely with FCDO Posts in each country.
SIGs engage with researchers and government officials that will use the research outputs from the programme. As they develop, SIGs are intended to be used as a mechanism to channel emerging evidence into policy and investment decision-making, including possibly adopting new decision support tools and models. CCG conducts Political Economy Analysis (PEA) in the countries in which it has established national partnerships with the aim of understanding the factors influencing national planning and how potential challenges to evidence-based decision making might be overcome. At the national level, a general goal is to support nationally owned growth planning processes that are coherent, cross-sectoral and climate compatible, and to increase the efficacy of information flows and agency. This is intended to enable more effective and faster access to national budget and concessionary finance.
CCG international partnerships
CCG also works internationally to broaden the reach of the programme beyond the national partnerships. It does this firstly by engaging directly with a wider cross-section of national academics and policymakers, and secondly by working indirectly through international organizations to amplify the diffusion of CCG products to a wider set of countries. For example, the International Energy Agency is using a set of such CCG products to support its Data-2-Deal capacity building efforts in ten countries in Africa.
CCG’s international partnerships are varied in nature and purpose. A portfolio of 15 partnership activities has been developed to date, organized along four business lines.
1. Technical Tools: CCG is developing a suite of freely available datasets and open-source modelling tools which provide the technical foundations for deeper engagement on climate compatible planning and resource mobilization. At present, these include Starter Data Kits for energy and transport, as well as a suite of modelling tools (including OSeMOSYS, CLEWS, FlexTool, NISMOD, OnSSET, FinPlan, MAED, MUSE) in collaboration with the wider OpTIMUS community.
  [note] Open source software is software for which the original source code is made freely available and may be redistributed and modified. It allows for faster uptake by national and university analysts as licence fees are removed. It increases trust as all parts of the code can be interrogated.
2. Professional Development: Building on the foundation of these technical tools, CCG provides a capacity building programme that trains academics and policymakers in the global south to implement modern planning techniques. This is based on a sustainable model of training trainers in partnership with local academic institutions. To date, this has been undertaken through a growing programme of regional and global “summer schools”, underpinned by a curriculum of self-administered training modules housed in the Open University’s Open Learn Collection.
3. Applied Research: This involves the development and uptake of CCG knowledge products with international organisations and researchers. For example, a global version of OSeMOSYS was developed and is being used to support analysis of planning and finance of cross-border transmission lines under the Green Grids Initiative.
4. Policy Engagement: This activity aims to amplify CCG’s reach and impact by using CCG knowledge products to engage with and inform key international policy processes. This includes policy briefings for major international climate events (such as COPs), as well as technical and secretariat support for a variety of international initiatives including the Green Grids Initiative, Energy Transition Council, and the Strategic Planning Round Table.
Research uptake is integral to the design of these activities. For example, summer school participants (typically government analysts or academics) are expected to produce and present the beginnings of applied research work that could have relevance and application in their own national situations. Where successful these may also culminate in the production of academic papers, generally led by Southern Authors (e.g. Special Issue of a leading journal on: Energy Systems Modelling for Planning in Africa and Small Island Countries).
Research (NB – this section does not yet reflect the updated programmed research priorities or structure, which are pending finalisation)
CCG’s ‘programmed’ research currently includes three main workstreams as set out below. These are informed by research strategies that are revised annually and are to be made available on the CCG website.
- System Design addresses core energy and transport system planning challenges at local, national, regional, and global scale by supporting development and co-creation of data, tools, models, processes, pipelines and frameworks that can support investment and policy decision-making in LMICs and their development partners.
- Sector Interactions explores the relationships between infrastructure, materials and resource development with the SDGs and national development priorities. It develops insights, tools, and processes to inform a multi-sector whole-systems approach to transitioning to climate compatible growth. This includes infrastructure resilience, integrated resources (land, energy, and water) and material supply chains, including the critical minerals that underpin energy and transport sector decarbonisation.
- Economics and Policy researches the economic implications of climate, political-economy and policy analysis and investment pipelines. This work examines: the opportunities and barriers to climate compatible growth; decision-making contexts and policy; and pathways to mobilise finance for investment that supports just transitions in CCG partner countries and other LMICs.
The bulk of this programmed research is carried out by the core team of UK universities plus KTH in Sweden. The focus may change over time as the agenda responds to demand. Specific activities in that research are often co-created or match demands of the country or international organisation that is being engaged with.
In addition to this programmed research, various flexibility mechanisms are built into CCG to ensure the programme can respond dynamically to research needs identified by programme partners and to fund a wider range of research inputs particularly from Southern researchers. These mechanisms include:
- Urgent asks (less than three months) that are not in the programmed research will be responded to via CCG’s “Responsive Unit” formed with CCG and external researchers and consultants.
- For asks aligned with CCG’s objectives, for which CCG has capacity, 20% of all CCG researcher time is on call to deliver what are termed Agile Outputs.
- A Flexible Research Fund (FRF) enables research to be procured from outside the core institutions in the University Partnership. This aids the responsiveness of the programme to demand from partners. It also diversifies the group of researchers and institutions involved in CCG and facilitates greater participation of researchers from LMICs.
- A Southern Partner Fund (SPF) ensures that Southern researchers are engaged in research and partnership activities with the dual aim of improving the quality and relevance of the research while building the research skills and capabilities of individual Southern researchers.
Outputs include a range of knowledge products including tools, models, frameworks, published papers and articles made available as global public goods through various mechanisms including a learning platform. The aim is to: (1) directly push the frontiers of knowledge on climate-compatible growth in LMICs; and (2) influence the research agenda and practice of the wider research community (beyond CCG’s own programming).
Research uptake is often carried out via the partnership activities outlined above. In addition, CCG aims to influence the international academic research agenda with respect to climate compatible growth planning. This is implemented via the conventional academic avenues of journal articles, conference papers and other publications. Due to the positioning of the partners, outputs are often solicited for presentation at high-level international events with international organisations. These include for example at the COP, G20 and others. Further, outputs include regular Nature-journal (or similarly prestigious) publications which allows for high-profile and extensive reach.
Capacity strengthening and building
At national level, CCG’s approach is to support the development of a national ‘ecosystem,’ involving a relationship of trust and mutual benefit between government planning units and national research institutions. The goal is for government units to be able draw upon national research institutions to provide them with high-quality, evidence-based analysis to feed into their policy development, investment planning and international climate reporting that helps build investor confidence. National research institutions can in turn gain credibility and greater access to resources by engaging in research with real-world impacts, leading to a virtuous circle of increasing research quality. The relationship can be strengthened and sustained by producing a stream of graduates to resource government planning units.
To achieve this, CCG capacity strengthening activities are designed to increase the ability of counterparts to co-create, adopt, and apply CCG’s knowledge products through access to training on the use of decision support tools and models. In CCG partner countries capacity strengthening activities include workshops open to planners, government analysts and researchers as well as support to communities of practice via Special Interest Groups (SIGs). This support is complemented by access to CCG’s Open Learn collection which provides free online access to a broad range of CCG training and the opportunity to apply for CCG “Summer Schools”.

CCG also reaches a wider range of LMICs by working with the technical assistance activities of international partner organisations (including development partners, finance institutions and multilateral development banks). The aim is to encourage use of common tools, frameworks, and policy approaches to foster more effective international support for coherent cross-sectoral climate compatible growth planning and Data-2-Deal pipelines at a national level.
        CCG is developing a ‘Platform’ that makes CCG knowledge products readily accessible for application by the CCG partnerships as well as providing an evidence base to inform further research activities. Examples include CCG Starter-data-kits, teaching kits, Open Learn Collection and tools being absorbed into university curricula and used in government processes and knowledge management activities. The CCG Platform has two audiences: those internal to the consortium and producing research outputs, and external stakeholders who use the outputs and may further develop those resources.
Outcomes from CCG’s capacity building work are expected to be:
- Enhanced research capabilities of individual Southern researchers
- Awareness of alternative policy options amongst national institutions leading to improved policies and processes
- Enhanced capabilities of LMIC planners, researchers, policy makers and investment decision-makers to incorporate evidence using appropriate decision support tools
- Improved agency of Southern partners to set national energy, transport and other policy and investment priorities when mobilising finance with external partners.

## Intended outcomes
The CCG programme is intended to deliver three broad outcomes:
- As a result of research uptake activity in-country, the governments and national institutions participating in national partnerships with CCG choose to embed knowledge products and activities derived from the CCG programme. This leads to national institutions having increased agency to set energy, transport and other policies, planning, and programming with stronger or more realisable climate compatible growth ambition, and paves the way for the mobilisation of finance.
- As a result of research uptake activity with international institutions to raise awareness of CCG programme research outputs, MDBs and other IOs embed CCG products and processes in their institutions and, as a result, change their engagement with LMICs to more effectively support climate compatible growth planning.
- As a result of making CCG programme research outputs available as global public goods, the broad international academic research agenda is influenced to focus more on key CCG research areas. LMIC researcher institutions’ capacity to engage in that research agenda is strengthened as a result of individual Southern researchers’ capabilities being increased through their engagement on CCG programme research projects.

Intermediate outcomes that would indicate that the CCG programme is on its way to achieving these outcomes include the following:
Amongst international organisations:
- Instances of international financial institutions and development partners using CCG products and processes.
- Instances of engagement practice between international organisations and LMICs being revised as a result of CCG products use.
In terms of advancing academic research:
- Researchers cite CCG knowledge products.
- Evidence of national research capability being increased and exercised.
And in terms of national impacts:
- National governments find CCG knowledge products and activities useful.
- Individual instances of national institutions strengthened through enhanced individual capabilities and improved polices and processes.
- Ad hoc instances of national governments choosing to use CCG knowledge products and activities to set energy, transport and other policies, planning, and programming with stronger or more realisable climate compatible growth ambition and investment potential.

## Intended impact
The intended impact to which CCG aims to contribute is improved climate compatible growth for developing countries in Africa, Asia, and other regions through re-organisation of spend patterns or increases in the level of investment in infrastructure, services and policy by both international financial institutions and national governments. These in turn should accelerate inclusive economic growth and decelerate greenhouse gas emissions per unit of growth.
## Assumptions underlying the Theory of Change
The following summarises the assumptions underlying the Theory of Change
Problem statement
- The overarching problem identified is a substantial contributor to national growth plans being incompatible with future climate related constraints and opportunities.
- The analysis of the causes of the overarching problem is correct and is not missing key causes.
From problem statement to activities
The iterative process of working with national and international partners in identifying research themes and co-creating research outputs ensures that the activities commissioned adequately address the causes identified in the problem statement.
From activities to outputs to intermediate outcomes
Research
- The research funded by the CCG programme is able to produce outputs (decision support tools, system configurations, business models, an enhanced evidence base, etc) that are relevant to issues faced by LMICs.
  [note] Relevance here would be defined as the resulting tools, policy approaches, evidence etc either being relevant to a specific context the research is co-produced in, or that the outputs have wider applicability and are transferrable across multiple contexts.
- The CCG programme is able to co-create research results and ‘agency-build’ with respect to developing and self-sustaining a knowledge base in a way that builds trust and is found useful and accessible by the programme’s key target audiences of planners and policy makers.
- The research commissioned will be of sufficient academic rigour that making results available as global public goods will lead to it being cited in academic literature and influencing future research agendas.
Research uptake
- The CCG core group of universities has the capacity and capability to effectively engage with existing (or create new) international and national partnerships that, in turn, accept the need for reform or policy change and have the authority and ability to engage in it.
- Engagement by the CCG programme at national level will enable identification and mitigation of barriers to evidence-based decision making that might otherwise thwart the adoption of appropriate tools, policies and processes by planners and decision makers.
- The CCG programme is also able to identify and mitigate selected knowledge-product and engagement issues in MDBs, IFIs and development partners that might prevent the application of appropriate tools, policies, and processes in the execution of international financial support.
Capacity building
- Capacity- and agency-building activities with individuals are focussed on those who have the potential to be change agents (i.e. they have the authority to engage in reform or policy change, accept the need for change) and that the capacity building activity will close any gaps in their ability to engage.
- Capacity- and agency-building with universities and planning units in-country, and supporting links between academic institutions and government, contributes significantly to a supportive environment for the above individuals to be effective as change agents.

From intermediate outcomes to outcomes
- Ad hoc instances of national or international institutions developing / adapting / using / trying out the tools, policies and processes developed by CCG will lead those institutions to understand their value and to formally embed them in their relevant policies and practice.
- Citing of CCG research in the wider academic literature indicates it is advancing the boundaries of knowledge in this general area of research.

From outcomes to impact
- The adoption of appropriate programme tools, policies and processes by national and international institutions will be sufficient to help improve coherent and inclusive decision-making on policies and strategies, planning, design of regulations and market systems and inclusion of climate-related factors by regional, national, and sub-national governments and their development partners.
- This, in turn, will lead to improved climate compatible growth for developing countries in Africa, Asia and other regions through breakthrough increases in the level of investment – or re-organisation of spend patterns – in infrastructure, services and policy.
Annex B – CCG Outcome Achievements for FY 2024/2025

OI.1 measures the number of instances of CCG products and activities used by countries and international organisations for policy or investment decision-making.
In the reporting period of FY24–25, eight instances were achieved this year (ten including non-LMIC) of OI.1:
Contribution to Kenya’s Least Cost Power Development Plan (2024–2043)
Contribution to Rwanda’s Least Cost Power Development Plan
Contribution to the National Green Hydrogen and Ammonia Roadmap in Lao PDR
Gender Impact Assessments for Energy Infrastructure Projects (ZMGIA) in Zambia
Technical support for Zambia’s Climate-Compatible Constituency Development Fund
Support for Kenya’s National Electric Cooking Strategy
Support to Kenya’s National Electric Cooking Strategy through open-source energy modelling
TEAM–Kenya model applied to the National Electric Mobility Policy
Contribution to the Second Nationally Determined Contribution (NDC) in Ecuador – Not counted
Choma district scenarios for long-term development planning in Zambia – Not counted

Contribution to Kenya’s Least Cost Power Development Plan (2024–2043)
CCG is formally acknowledged (on page 33) of Kenya’s Least Cost Power Development Plan (LCPDP) 2024–2043 for its pivotal role in supporting the plan’s development. CCG provided technical expertise and capacity-building to the Ministry of Energy and Petroleum, contributing to a more robust, evidence-based planning process. Its support was instrumental in integrating clean energy strategies focused on improving grid reliability and affordability. Additionally, the collaboration ensured that long-term sustainability considerations were embedded in the plan, aligning Kenya’s power sector development with national goals for economic growth and climate resilience.

Contribution to the National Green Hydrogen and Ammonia Roadmap in Lao PDR
In March 2025, the Ministry of Energy and Mines of Lao PDR officially signed off on the National Green Hydrogen and Ammonia Roadmap, with CCG’s contributions acknowledged (pages 6 and 57–63). CCG-supported, OSeMOSYS-trained modelers from various Lao ministries provided critical analytical inputs, reinforcing the roadmap’s technical foundation. An open-source OSeMOSYS model of the Lao power sector was used to estimate surplus electricity under exploratory scenarios (see section 3.5 of the roadmap). CCG also played a central role in the technical working group, helping to embed robust energy system modelling into national planning. This outcome reflects CCG’s sustained engagement in Lao PDR, supporting evidence-based policy and the alignment of national strategies with sustainable hydrogen and ammonia development pathways.

Contribution to Rwanda’s Least Cost Power Development Plan (LCPDP)
The Rwanda Energy Group (REG/EDCL) has issued a letter confirming CCG’s contribution to the development of Rwanda’s Least Cost Power Development Plan (LCPDP). CCG’s support included training on OSeMOSYS and FlexTool, which strengthened energy demand and supply analysis and enabled the integration of robust modelling frameworks into national planning. The LCPDP now embeds OSeMOSYS-generated reference energy systems, ensuring data-driven updates and long-term cost-effective decision-making. Additionally, modelling scenarios developed through CCG-supported EMP-G training were applied in MESSAGE and incorporated into the plan, further validating their practical use. By supporting the elaboration of Rwanda’s LCPDP, CCG has enhanced institutional capacity for strategic energy planning, aligning national policies with sustainability and affordability goals.

Gender Impact Assessments for Energy Infrastructure Projects (ZMGIA) in Zambia
CCG has provided strong support for the development of Gender Impact Assessments for energy infrastructure projects in Zambia’s power sector (ZMGIA). The Ministry of Energy has formally acknowledged this contribution in an official letter, recognizing CCG’s role in providing technical expertise, capacity building, and policy engagement to shape guidelines that integrate gender considerations into project design and implementation. By strengthening decision-making processes, this work contributes to more inclusive and equitable energy infrastructure development, reinforcing Zambia’s commitment to gender-responsive policies in the sector.

Support to Kenya’s National Electric Cooking Strategy through open-source energy modelling
Kenya’s first National Electric Cooking Strategy (KNeCS), launched in 2024 by the Ministry of Energy and Petroleum (MoEP), was underpinned by modelling work supported by the Climate Compatible Growth (CCG) programme. The modelling was led by the Nuvoni Centre for Innovation Research and used open-source tools including OSeMOSYS, with contributions from CCG. The strategy aims to transition 10% of Kenyan households to electric cooking by 2028 and was developed through a technical working group co-chaired by MoEP and Modern Energy Cooking Services (MECS), with active participation from CCG. The modelling informed scenario development, grid impact analysis, and infrastructure investment planning. CCG is acknowledged in the final strategy document (pages v and 76). Furthermore, the resulting electricity demand projections are now being officially used by the Least Cost Power Development Plan (LCPDP) team in Kenya’s national energy planning process.

Support for Vietnam’s National Plan on Circular Economy
 The Ministry of Natural Resources and Environment of Vietnam (MONRE) has issued letters confirming the contribution of CCG to the development of Vietnam’s National Action Plan on Circular Economy by 2035, which was promulgated by the Prime Minister on January 23, 2025. CCG support facilitated technical expertise and policy discussions, contributing to the identification of strategic priorities, goals, and implementation pathways for advancing circular economy principles. The contribution stemmed from a CCG Southern Partnership Fund project involving the Institute of Strategy and Policy on Natural Resources and Environment (ISPONRE) and the National Economics University (NEU) in Vietnam where circular economy indicators were estimated for Vietnam's packaging sector. The National Action Plan aligns with Vietnam’s Law on Environmental Protection 2020 and sets a comprehensive roadmap for circular economy adoption across multiple sectors. MONRE acknowledges CCG’s role in fostering constructive exchanges with key stakeholders, reinforcing the government’s efforts to embed circular economy practices into national policies and governance structures.

TEAM–Kenya Model Applied to National Electric Mobility Policy
The government of Kenya’s E-Mobility Taskforce, established by the Cabinet Secretary for Roads and Transport, used the TEAM-Kenya model, developed with support from the Climate Compatible Growth (CCG) programme, to inform the development of the country’s National Electric Mobility Policy. The model played a central role in evaluating the financial and macroeconomic impacts of electric vehicle (EV) adoption, identifying investment opportunities across the EV value chain, and assessing fiscal scenarios. Insights from the model were used to shape policy recommendations on infrastructure, local manufacturing, and incentive structures.

Technical Support for Zambia’s Climate-Compatible Constituency Development Fund
CCG played a pivotal role in shaping national policy in Zambia through its report Mobilising Investment for Climate-Compatible Growth through Zambia’s Constituency Development Fund (CDF). Developed in collaboration with Lloyds Financials and based on extensive field research conducted in early 2023, the report outlines how the CDF—originally intended to promote decentralised development—can be leveraged to attract external investment by integrating climate-compatible principles. It highlights practical recommendations across governance, process optimisation, monitoring and evaluation, and local economic development. Notably, Recommendation 1.5 called for embedding climate adaptation and mitigation into community project planning under the CDF. This recommendation was directly reflected in a Ministerial Directive issued by the Ministry of Local Government and Rural Development on 24th April 2024, which prioritises adaptation-based activities within the CDF framework. A formal endorsement letter from the Director of the Local Government Programme at Lloyds Financials confirms that the CCG report was reviewed by the Minister’s advisors and significantly influenced the directive. The letter further notes that the report has shaped the Ministry’s strategic thinking, particularly as Zambia seeks to align local funding mechanisms with the priorities of external funders and international climate finance institutions.

Contribution to the Second Nationally Determined Contribution (NDC) of Barbados – Not counted
At the SEforALL Global Forum in March 2025, it was independently reported by the United Nations Sustainable Development Solutions Network (SDSN) that the Government of Barbados has been working with SEforALL to develop the Energy Transition and Investment Plan using a suite of open-source energy system modelling tools, including OnSSET, OSeMOSYS and FlexTool, which are co-curated and co-developed by CCG. These tools have been applied to inform the country’s clean energy planning and were showcased as part of Barbados’ efforts to update its NDC under the Paris Agreement, due later in 2025. The SDSN article recognises that these CCG-supported tools and associated training are helping countries identify low-regret investment pathways and modernise infrastructure plans around clean energy-based systems.

Choma District Scenarios for Long-Term Development Planning – Not counted
Co-developed by ZIPAR and the Climate Compatible Growth (CCG) programme, the Choma District Scenarios for 2045 have been officially adopted and are now being used by the Choma Municipal Council to strengthen the implementation of the District Integrated Development Plan (IDP) 2021–2031. Validated through a stakeholder workshop and launched in February 2025, the scenarios are recognised by the Council as a practical tool for guiding local policy decisions and enhancing climate resilience.
OI.2 Nationally embedded processes
OI.2 measures the number of instances in which countries have embedded CCG knowledge products into their institutional planning and policy development processes.
In the reporting period of FY24–25, seven instances were achieved this year (x including non-LMIC) of OI.2:
Climate, Land, Energy, and Water systems (CLEWs) model used in training to support integrated planning in Kenya
Enhancing energy planning and financial modelling for sustainable nuclear energy deployment in Nigeria
Establishment of Zambia’s Energy Planning Centre
Institutional capacity strengthening of the Kenya Power and Lighting Company (KPLC)
Institutional embedding of CCG knowledge products in Rwanda’s energy planning
OSeMOSYS embedded in energy planning processes in the Ministry of Energy in Sierra Leone
Providing advisory support to the Sustainable Urban Mobility Committee in Zambia
Climate, Land, Energy, and Water systems (CLEWs) Model Used in Training to Support Integrated Planning in Kenya
CLEWs modelling framework is now embedded in training initiatives aimed at strengthening the capacity of government institutions for integrated planning in Kenya. In collaboration with academic institutions such as Taita Taveta University and Kenyatta University, CCG has helped deliver structured training programmes for public officials at both county and national levels. These sessions are equipping civil servants and technical staff with the skills to apply CLEWs in planning processes that span multiple sectors, including energy, water, land use, and climate adaptation. At the subnational level, training at Taita Taveta University has been aligned with the County Integrated Development Plan (CIDP), while ongoing sessions at Kenyatta University are reaching broader departments, including the Ministry of Energy and Petroleum, with responsibilities in infrastructure and energy. These efforts reflect a growing institutional commitment to using CLEWs as a core planning tool and illustrate how CCG’s work is contributing to more informed, systems-based decision-making across Kenya’s public sector.

Enhancing Energy Planning and Financial Modelling for Sustainable Nuclear Energy Deployment in Nigeria
CCG’s long-term engagement through capacity-building efforts contributed to improved energy planning and financial review processes within Kenya Power and Lighting Company (KPLC), under the Ministry of Energy. This support influenced cost reductions in Power Purchase Agreements (PPAs), strengthened regional energy exchange agreements with Uganda and Tanzania, and helped secure World Bank funding for the GREEN project. The expertise gained is now embedded in KPLC’s Infrastructure Division, shaping major national energy projects like KOSAP and Last-Mile Connectivity.

Establishment of Zambia’s Energy Planning Centre
CCG collaborated with the Ministry of Energy and Cities and Infrastructure for Growth Zambia (CIGZambia) to co-create a Whole Energy System Model (WESM) using the open-source OSeMOSYS tool, embedding it within the Ministry’s Energy Planning Centre to support implementation of the Integrated Resource Plan. Since April 2023, CCG has delivered a series of training and co-creation workshops involving planners from key institutions such as ZESCO, UNZA, and various ministries, building national modelling capacity. The WESM, now formally owned by the Ministry under a Memorandum of Understanding, includes key sectors like transport and cooking, and has been soft-linked with Antares modelling tools, further enhancing integrated energy planning capabilities across government.

Institutional capacity strengthening of the Kenya Power and Lighting Company (KPLC)
CCG supported capacity development in Kenya through the 2023 EMP-A and ICTP training, particularly in tools like MAED and Finplan. Following the training, a participant from Kenya Power and Lighting Company (KPLC) applied the acquired modelling expertise to national and regional energy initiatives. This included contributing to the review and renegotiation of Power Purchase Agreements (PPAs), enabling cost optimisation and tariff alignment. The tools also informed scenario-building for projects presented to the National Treasury and supported funding applications such as the World Bank GREEN project. The participant has since taken on a broader role within KPLC’s Infrastructure Division, working on major energy initiatives including KOSAP and the Last-Mile Connectivity Programme. CCG’s training impact further extends to innovative feasibility-stage projects like the Naivasha Industrial Park, which has been recognised for international presentation.

Institutional embedding of CCG knowledge products in Rwanda’s energy planning
CCG has successfully contributed to the institutional embedding of CCG knowledge products within Rwanda’s national energy planning processes. Specifically, the OSeMOSYS model, introduced through CCG’s EMP-G 2023 and Joint Summer School on Modelling Tools for Sustainable Development, has been integrated into Rwanda’s Least Cost Power Development Plan (LCPDP). The model has been used to develop reference energy systems and scenario analyses, informing long-term energy planning and investment decisions. The continued application of CCG-supported methodologies, including the replication of OSeMOSYS outputs in MESSAGE, ensures that Rwanda’s LCPDP updates are systematically grounded in robust analytical frameworks, leading to sustained improvements in national energy planning. Additionally, the training enhanced the ability of national stakeholders to interpret and communicate modeling insights, embedding CCG methodologies into policy discussions for long-term decision-making. Beyond energy planning, the integration of geospatial data analysis into the National Electrification Plan (NEP) and the National Integrated Clean Cooking Plan (NICCP) highlights the cross-sectoral impact of CCG-supported capacity-building efforts, reinforcing permanent institutional capacity for evidence-based policy formulation. These developments demonstrate the regular and ongoing use of CCG knowledge products within Rwanda’s national planning framework, ensuring that CCG’s impact will continue to shape Rwanda’s energy policies and investments well into the future.

OSeMOSYS Embedded in Energy Planning Processes in the Ministry of Energy in Sierra Leone
The Planning Unit of Sierra Leone’s Ministry of Energy has integrated the OSeMOSYS energy system modelling tool into its internal planning processes, with technical support from the CCG. Through this collaboration, the Ministry has strengthened its modelling capacity and developed seven strategic scenarios to assess long-term power sector options. The tool is currently being used to inform planning decisions, including infrastructure assessments for the Bumbuna and Yiben hydropower projects, and is expected to support ongoing evidence-based decision-making.

Providing advisory support to the Sustainable Urban Mobility Committee in Zambia
As part of the Engagement Fund, CCG has collaborated with the Zambia Institute for Policy Analysis and Research (ZIPAR) to establish the Sustainable Urban Mobility Advisory Committee (SUMAC). SUMAC is a policy-facing working group, chaired by the Ministry of Transport and ZIPAR, which aims to convene stakeholders from across academia, the private sector, and the government, to deliver evidence-based policy recommendations for reducing emissions within the transport sector in Zambia. The SUMAC has convened three times over the past 6 months, and the Ministry of Transport and ZIPAR have co-chaired these events. Based on its success, the Ministry of Transport has formally endorsed the SUMAC and recognises it as a key platform for decisions makers. Eng Emmanuel Sampa, Director of the Department of Transport at the Ministry of Transport formally endorsed the SUMAC in his speech at the Zambia CCG Annual Workshop in March 2025. This is an outcome because the SUMAC has become a platform that is relied upon by the Ministry of Transport for their stakeholder engagement activities around new and existing policies.
OI.3 Internationally embedded processes
OI.3 measures the number of instances in which international organisations (IGOs, IFIs) revise their engagement processes based on CCG products and activities.
In the reporting period of FY24–25, the consortium achieved six instances of OI.3:
Analysis Integrated into World Bank’s Engagement on Southern Africa Transport Planning
COP29 Legislators' Green Energy Pledge for Africa
Driving legislative action on Climate Finance through the UNIDO–Climate Parliament Partnership
Launch of the African Institute of Sustainable Energy and Systems Analysis (AISESA) as a platform for Africa’s energy transition and sustainable development
Integration of CCG knowledge tools by SEforALL into institutional processes for energy transition in LMICs
Supporting the launch of a new Steering Committee for OnStove open-source modelling tool
Analysis Integrated into World Bank’s Engagement on Southern Africa Transport Planning
In FY2024/25, the World Bank used CCG-supported analysis to shape its internal approach to transport and logistics planning in Southern and Eastern Africa. The analysis, part of Oxford University’s suite of climate risk assessment tools, focused on hazard exposure and climate vulnerability in regional transport networks, was incorporated into Chapter 4 of the Bank’s report "Resilient Transport and Logistics for Southern Africa", and served as the foundation for engagement with several country teams. According to World Bank staff, the work was used as a prototype for the type of climate-related analysis now prioritised in the region and also helped inform ongoing updates planned for the HDM-4 model. While the originally planned interactive map was not published, the underlying CCG input has been retained as part of the Bank’s evolving toolkit for climate-compatible transport engagement with LMICs.

Supporting COP29 Legislators' Green Energy Pledge for Africa
Legislators representing 32 nations (including Ghana, Kenya, Malawi and Zambia) committed to supporting the COP29 Green Energy Zones and Corridors Pledge to accelerate investment into transformative renewable energy infrastructure projects and to deploy their political influence to help create the infrastructure required to fulfil the landmark pledge. The 'Legislators' Pledge' was a result of the Istanbul Green Zones Investment Dialogue convened by the Climate Parliament and UNIDO, and a process through FY23/24, supported by CCG, to develop the Green Zones concept and strategy which will be deployed in 15 sub-Saharan African countries over the next two years. Green Zones provide a tangible way for legislators to use their position and influence to help create the conditions for attracting public and private green investment into their countries. Climate Parliament's partners in UNIDO held the pen on the COP29 pledge.

Launching the African Institute of Sustainable Energy and Systems Analysis (AISESA) as a Platform for Africa’s Energy Transition and Sustainable Development
CCG supported the establishment of the African Institute of Sustainable Energy and Systems Analysis (AISESA) as a collaborative platform to drive Africa’s energy transition and sustainable development. After two years of strategic planning and engagement, AISESA was formally launched in October 2024 during a meeting in Cape Town, where its governance structure, thematic work clusters, and long-term vision were defined. This African-led and African-owned initiative brings together stakeholders to co-create pathways for clean energy, effective implementation strategies, access to finance and technology, policy development, and institutional capacity building. AISESA now serves as a Pan-African platform for clean energy transitions, engaging over 50 universities and institutions to drive policy, finance, and capacity-building efforts.

Driving legislative Action on Climate Finance through the UNIDO–Climate Parliament Partnership
CCG’s support has been instrumental in enabling the UNIDO–Climate Parliament partnership, particularly through the Parliamentarians for Climate Finance (PCF) project. With funding from CCG, Climate Parliament has engaged legislators across Africa and South Asia on green grids, green zones, and climate finance, laying the groundwork for UNIDO’s strengthened collaboration with parliamentarians in the Global South. Through the PCF project, the partnership is institutionalising a collaborative model that brings together legislators, financiers, and technical experts to catalyse investment in renewable energy, low-carbon industries, and climate-resilient infrastructure. A structured platform has been established to integrate policy dialogue, capacity building, and strategic project identification in 15 African countries. Key contributions include capacity-building workshops that equip legislators with tools to shape effective climate finance policies, Green Investment Dialogues that promote innovative mechanisms like Green Zones to attract sustainable investment, and the development of project pipelines and strategic frameworks to advance scalable climate-resilient infrastructure investments.

SEforALL Integrating CCG Knowledge Tools into Institutional Processes for Energy Transition in LMICs
At the SEforALL Global Forum in March 2025, SDSN reported that SEforALL is now deploying a suite of open-source energy planning tools—including OnSSET, OSeMOSYS, and FlexTool, co-curated and co-developed by CCG—as part of its standard approach to supporting countries in the development of Energy Transition and Investment Plans (ETIPs). These tools are being used by SEforALL to work with countries such as Barbados, Ghana, Kenya, Nigeria, and Sierra Leone, helping inform national energy strategies and NDC updates. The SDSN article highlights the integration of these tools within SEforALL’s broader institutional model, including efforts to link geospatial tools with quantitative modelling pathways. This represents, thus, a revision of SEforALL’s engagement processes with LMICs based on the adoption of CCG knowledge products and methodologies.

Support for Launching the Steering Committee of the OnStove Open-Source Modelling Tool
CCG supported the establishment of a new Steering Committee for the OnStove open-source modelling tool, formally launched during the Energy Modelling Platform – Global (EMP-G) at ICTP Trieste. OnStove, a companion tool to OnSSET, supports planning for clean cooking access and plays a vital role in advancing SDG 7.1. With this governance structure now in place, OnStove has entered a new phase of coordinated development, bringing together partners such as KTH, SEforALL, the World Bank, MECS, WRI, and Duke University. The Steering Committee facilitates collaboration on methodological improvements, training materials, and usability enhancements, ensuring the tool remains responsive to evolving policy and technical needs. This milestone reflects CCG’s commitment to building strong institutional foundations for open-source tools that empower countries to plan for inclusive and sustainable energy transitions.
OI.4 Use of CCG knowledge products in educational institutions:
OI.4 measures the use of CCG knowledge products in educational institutions, indicating the number of instances where CCG knowledge products are used in teaching and research within universities or research institutes that award degrees.
In the reporting period of FY24–25, the consortium achieved one instance of OI.4 (two
including non-LMIC):
Embedding of Geospatial Data, Best Practices for Collection and Management course into Geographic Information Systems (GIS) course at the National Economics University in Vietnam
Institutional Embedding of CCG Knowledge Products in Research at the University of Cape Town, South Africa
Institutional Uptake of OSeMOSYS in MSc Curriculum at Addis Ababa University

Embedding of Geospatial Data, Best Practices for Collection and Management course into Geographic Information Systems (GIS) course at the National Economics University in Vietnam
The Geospatial Data, Best Practices for Collection and Management course has officially been embedded into the National Economics University and has been delivered twice over the past year at part of the Geographic Information Systems (GIS) course for students at NEU. After attending the EMP-Global last year in Trieste, Dr Huan (CCG Coordinator) was inspired to apply the course material to his teaching. He worked with CCG, ICTP and KARTORA to embed the course. This is an outcome become it demonstrates that CCG teaching material has been embedded for the long term into an academic institution in a Partner Country (Vietnam). The training material has been translated into Vietnamese, so it now can be taught in both English and Vietnamese.

Institutional Embedding of CCG Knowledge Products in Research at the University of Cape Town
The University of Cape Town (UCT), through its Energy Systems Research Group (ESRG), has demonstrated sustained and embedded use of CCG knowledge products—particularly the open-source OSeMOSYS modelling tool—in its institutional research practices. This includes a PhD research proposal applying OSeMOSYS to energy planning in the DRC mining sector and five peer-reviewed publications that either co-create or build upon CCG-supported tools and methods. This consistent application of CCG products in formal academic research, independent of one-off events, meets the requirements of OI.4 for embedded research uptake. The outcome reflects long-term integration of CCG methodologies into UCT’s institutional research capacity.

Institutional Uptake of OSeMOSYS in MSc Curriculum at Addis Ababa University
Addis Ababa University has implemented the CCG tool OSeMOSYS as part of the “MSc. Curriculum in Renewable Energy Engineering,” specifically in the “Modelling and Optimization of RE System” course. This course has been taught for more than one instance, as confirmed by the course curator. The course was implemented by Fitsum Salehu, an EMP-A 23 participant who attended the OSeMOSYS course. After learning the skills in OSeMOSYS, Fitsum implemented the course on his own, with some support from a separate project that they were working with (RE-INTEGRATE).

OI.5 Academic Influence
OI.5 measures of publications, datasets, and software repositories (to which CCG has contributed) with more than 15 citations.
In the reporting period of FY24–25, the consortium achieved fourteen OI. 5:
- Giarola et al. (2022) MUSE: An open-source agent-based integrated assessment modelling framework. Energy Strategy Reviews (26 citations)
- Mazzone et al. (2023) Indigenous cosmologies of energy for a sustainable energy future. Nature Energy (25 citations)
- Isihak et al. (2022) Evolution of GIS-based rural electrification planning models and an application of OnSSET in Nigeria. Renewable and Sustainable Energy Transition (24 citations)
- Vardon et al. (2023) From COVID-19 to green recovery with natural capital accounting. Ambio (23 citations)
- Yang et al. (2023) The global mismatch between equitable carbon dioxide removal liability and capacity (22 citations)
- Hersaputri et al. (2024) Reducing Fossil Fuel Dependence and Exploring Just Energy Transition Pathways in Indonesia Using OSeMOSYS (Open-Source Energy Modelling System) (21 citations)
- Plazas-Niño et al. (2023) Informing sustainable energy policy in developing countries: An assessment of decarbonization pathways in Colombia using open energy system optimization modelling. Energy Strategy Reviews (21 citations)
- Yang et al. (2023) Computational decision-support tools for urban design to improve resilience against COVID-19 and other infectious diseases: A systematic review. Progress in Planning (18 citations)
- Gardume et al. (2021) A scenario analysis of potential long-term impacts of COVID-19 on the Tunisian electricity sector
- Chan et al. (2022) Bank climate actions and their implications for the coal power sector. Energy Strategy Reviews (17 citations)
- Trotter et al. (2022) How climate policies can translate to tangible change: Evidence from eleven low- and lower-middle-income countries. Journal of Cleaner Production (17 citations)
- Hirmer et al. (2022) GESI-related: The power of language: Exploring values, empowerment dynamics, and communication strategies for gender-inclusive energy service design in rural Uganda (16 citations)
- Plazas-Niño et al. (2024) Open energy system modelling for low-emission hydrogen roadmap planning: The case of Colombia. Energy Strategy Reviews (16 citations)
- Cannone, C. et al (2023) Addressing Challenges in Long-Term Strategic Energy Planning in LMICs: Learning Pathways in an Energy Planning Ecosystem (15 citations)

Annex C – Externally peer-reviewed papers published in FY 2024/25

Title	Country or Countries	Theme	URL
A Critical Analysis of Morocco’s Green Hydrogen Roadmap: A Modelling Approach to Assess Country Readiness from the Energy Trilemma Perspective	Morocco	Energy	https://www.mdpi.com/2225-1154/12/5/61
How can emerging economies meet development and climate goals in the transport-energy system? Modelling co-developed scenarios in Kenya using a socio-technical approach	Kenya	Economic Growth, Energy, Transport, Inclusion (GESI)	https://doi.org/10.1016/j.esr.2024.101396
Long -Term Energy System Modelling for a Clean Energy Transition in Egypt's Energy Sector	Egypt	Energy	https://www.mdpi.com/1996-1073/17/10/2397
Long-Term Energy System Modelling for a Clean Energy Transition and Improved Energy Security in Botswana’s Energy Sector Using the Open-Source Energy Modelling System	Botswana	Energy	https://www.mdpi.com/2225-1154/12/6/88
Long-Term Forecasting: A MAED Application for Sierra Leone’s Electricity Demand (2023–2050)	Sierra Leone	Energy	https://www.mdpi.com/1996-1073/17/12/2878
Navigating complexity: Integrating political realities into energy system modelling for effective policy in Sub-Saharan Africa (Accepted manuscript - available online)	All	Energy, Whole Systems / Multi Sector	https://iopscience.iop.org/article/10.1088/2516-1083/ad5cbf
Open energy system modelling for low-emission hydrogen roadmap planning: The case of Colombia	Colombia	Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S2211467X24001081
Quantifying climate risks to infrastructure systems: A comparative review of developments across infrastructure sectors	All	Resilience, Energy, Transport, Whole Systems / Multi Sector, Inclusion (GESI)	https://doi.org/10.1371/journal.pclm.0000331
Techno-economic data and assumptions for open energy modelling of decarbonisation pathways in the Philippines	Philippines	Energy	https://www.sciencedirect.com/science/article/pii/S2352340924004281?via%3Dihub
The economics of coal phaseouts: auctions as a novel policy instrument for the energy transition	Germany	Energy	https://www.tandfonline.com/doi/full/10.1080/14693062.2024.2358114
The global and national energy systems techno-economic (GNESTE) database: Cost and performance data for electricity generation and storage technologies	All	Energy	https://www.sciencedirect.com/science/article/pii/S235234092400636X
A dataset for energy demand and supply modelling in Sierra Leone	Sierra Leone	Energy	https://www.sciencedirect.com/science/article/pii/S2352340924006826
Using open-source tools to project bulk and critical material demand and assess implications for low-carbon energy and transport systems: Introducing Mat-dp model tools	All countries	Resilience, Energy, Transport, Whole Systems / Multi Sector, Environment	https://www.sciencedirect.com/science/article/pii/S0921344924003975?via%3Dihub
How does energy modelling influence policymaking? Insights from low- and middle-income countries	All countries	Energy	https://www.sciencedirect.com/science/article/pii/S1364032124004520?via%3Dihub
clicSAND for OSeMOSYS: A User-Friendly Interface Using Open-Source Optimisation Software for Energy System Modelling Analysis	All countries	Energy	https://www.mdpi.com/1996-1073/17/16/3923
Macroeconomic impacts of African transport transitions: on the case of electric two-wheelers in Kenya	Kenya	Transport	https://www.sciencedirect.com/science/article/pii/S2950196224000085
GIS-based method for assessing the viability of solar-powered irrigation	Kenya	Economic Growth, Resilience, Energy, Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S0306261924018440?via%3Dihub
Inconsistent measurement calls into question progress on electrification in sub-Saharan Africa	All countries	Energy	https://www.nature.com/articles/s41560-024-01609-4#citeas
The map behind the roadmap—Introducing a geospatial energy model for utility-scale solar and wind power buildout in Kenya	Kenya	Economic Growth, Energy	https://www.cell.com/cell-reports-sustainability/fulltext/S2949-7906(24)00354-9
Value addition for who? Challenges to local participation in downstream critical mineral ventures in Zambia	Zambia	Energy, Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S2214790X24001503?via%3Dihub
A 10-Point Plan to Scale up Renewable Energy in the Global South	All	Energy	https://www.tandfonline.com/doi/full/10.1080/14693062.2024.2418948
Transport starter data kit: Historical passenger and freight transport data for selected countries in Africa, Asia, and South America	All	Energy, Transport	https://www.sciencedirect.com/science/article/pii/S2352340924009466
Climate Change Adaptation, Social Resilience, and Perceived Values Data from Turkana, Machakos and Narok Counties, Kenya	Kenya	Resilience, Energy, Inclusion (GESI)	https://www.sciencedirect.com/science/article/pii/S2352340924009405
Data governance and open science in energy planning: A case study of the Kenyan ecosystem	Kenya	Energy, Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S2214629624004122
Long-term Energy System Modelling for a Clean Energy Transition in Egypt’s Energy Sector	Egypt	Energy, Economic Growth, Whole System/Multi Sector	https://www.mdpi.com/1996-1073/17/10/2397
Integrated Long‐Term Expansion Planning and Short‐Term Operation Assessment in Brazil Considering Utility‐Scale Storage	Brazil	Energy, Economic Growth, Whole System/Multi Sector	https://onlinelibrary.wiley.com/doi/full/10.1002/est2.70056
Comparing long-term power sector pathways in Viet Nam: A simple cost-optimization approach with OSeMOSYS	Viet Nam	Power	https://www.mdpi.com/1996-1073/17/23/6158
An open and lite technoeconomic dataset and assumptions for open energy, emissions and mitigation modelling in the Republic of South Africa	South Africa	Energy	https://www.sciencedirect.com/science/article/pii/S2352340924009612
Climate Change Mitigation Policies for Developing Countries	All	Economic Growth, Energy, Environment	https://www.journals.uchicago.edu/doi/epdf/10.1086/732475
Exploring interlinkages in land, energy, and water in cooking and agriculture sectors: A case study in Kenya	Kenya	Energy, Whole Systems / Multi Sector, Environment	https://www.sciencedirect.com/science/article/pii/S2772427125000075
Exploring resilient alternatives in community energy systems planning to address parameter and structural hybrid uncertainties	All	Resilience, Energy, Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S2210670725000393
GeoH2 model: Geospatial cost optimization of green hydrogen production including storage and transportation	All	Whole Systems / Multi Sector, Energy	https://www.sciencedirect.com/science/article/pii/S2215016124001146
Global datasets of geospatial-AI-resolved energy consumers including climate-driven energy demands, geographical and socioeconomic realities for a transition reset	All	Energy	https://www.nature.com/articles/s41597-024-04277-x
Green hydrogen futures in LMICs: opportunities for fertiliser and steel production in Kenya	Kenya	Economic Growth, Energy, Whole Systems / Multi Sector, Environment	https://www.sciencedirect.com/science/article/pii/S2589004225005590?via%3Dihub
Renewable hydrogen trade in a global decarbonised energy system	All	Energy, Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S0360319924056714?via%3Dihub
Servitization for the energy transition: The case of enabling cooling-as-a-service (CaaS)	All	Economic Growth, Energy, Whole Systems / Multi Sector	https://www.sciencedirect.com/science/article/pii/S0959652624036394#abs0015
Shedding light on vulnerability: Intersectional energy planning for development	Kenya	Resilience, Energy, Inclusion (GESI)	https://www.sciencedirect.com/science/article/pii/S1364032124009250?via%3Dihub
The global implications of a Russian gas pivot to Asia	All	Energy, Whole Systems / Multi Sector	https://www.nature.com/articles/s41467-024-55697-7
The Philippines’ Energy Transition: Assessing Emerging Technology Options Using OSeMOSYS (Open-Source Energy Modelling System)	Philippines	Whole Systems / Multi Sector, Energy	https://www.mdpi.com/2225-1154/13/1/14
Which context matters for capturing energy needs? A multi-level analysis	Zambia, Uganda	Energy, Whole Systems / Multi Sector, Inclusion (GESI)	https://www.sciencedirect.com/science/article/pii/S1364032124006725#ack0010