## Annual Review Template

Title: Climate Adaptation and Resilience (CLARE)
Programme Value £ (full life): £102.5m (£14.5m (Phase 1 + additional £ 88m)		Review date: Sep 2025
Programme Code : 300126	AMP start date: 1st June 2019	AMP end date: 31 March 2027

Summary of Programme Performance
Year	19/20	20/21	21/22	22/23	23/24	24/25
Overall Output Score	A	A	A+	A+	A	A+
Risk Rating	Mod	Mod	Mod	Mod	Mod	Mod

DevTracker Link to Business Case:	DevTracker Project GB-GOV-1-300126 (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Project GB-GOV-1-300126 (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW

Description of programme
CLARE is a £110m+ framework research programme on Climate Adaptation and Resilience, announced at COP26. CLARE is bridging critical gaps between science and action by championing Southern leadership of research. It supports partner governments, communities, and the private sector to use evidence and innovation to drive effective solutions to the climate challenge, whilst building capacity of both those carrying out the research and those using the resulting evidence. CLARE is mostly (about 90%) funded by FCDO, and co-funded and run by Canada’s International Development Research Centre (IDRC).
CLARE is FCDO’s flagship programme on climate adaptation research, consolidating and building on a range of critical activities from predecessor programmes, as well as emerging priorities. Through long-term commitments and partnerships worldwide, delivering needs-driven, action-focused research, CLARE links up short- and long-term issues, enabling long-term, sustainable, and equitable economic and social development in a changing climate whilst supporting early action to reduce impacts of climate variability, providing a better understanding of the risks associated with climate.

Figure 1: Overview of the structure and timeline of the CLARE programme

Figure 2: Overview of the structure and timeline of the CLARE programme
CLARE includes three core pillars: ‘Research’, commissioning new, substantive, action-oriented research as well as providing the cross-programme infrastructure, jointly run and co-funded by the UK and by Canada’s International Development Research Centre; ‘Services’ providing timely weather and climate services to inform investments and actions by FCDO, UK government and wider stakeholders in partnership with the UK Met Office and others; and ‘Partnerships’, supporting strategic alliances on climate science and adaptation such as the Adaptation Research Alliance (ARA) and Climate Risks and Early Warning Systems (CREWS).
The three Pillars are supported by its ‘infrastructure’, including a Research 4 Impact (R4I) Hub, led by SouthSouthNorth (SSN), that supports projects to achieve impacts on the ground; a Capacity Strengthening (CS) Hub, in collaboration with the African Centre for Technology Studies and PlanAdapt; a Knowledge Management (KM) Platform, which supports both internal communication between project teams and external comms and branding; and the Monitoring, Evaluating and Learning (MEL) framework. Four Working Groups around R4I, Capacity Strengthening, MEL and Gender, Equality and Inclusion are supporting learning and exchange across project teams to enhance the impacts and capacity across these four dimensions.
The focus of this year’s Annual Review is on the progress that the programme has made on achieving its outcomes around influencing policies and creating solutions that are adopted, and on achieving strengthened capacity of the individuals directly involved in CLARE. It also continued to report on its outputs around collaborative, equitable and cross-sectoral, diverse partnerships; on strengthening capacity across the research to action chain; on new and improved science published. The research projects have continued to be assessed against the quality of the research as well as of the engagement to date in developing tools and technologies, which this year have also been reported as an output. Finally, this Annual Review continued to report on existing knowledge brokered to additional stakeholders, broadening the impact of existing evidence whilst new evidence is being developed.
Summary supporting narrative for the overall score in this review
- The programme scores an A+ with output milestones mostly exceeded. The programme is also evidencing progress toward outcomes, nearly meeting outcome 1 milestones and comfortably meeting outcome 2 milestones. The project is therefore rated Amber/Green in terms of its likelihood to achieve its outcomes, and this review has considered what changes may be needed to further support outcome delivery. CLARE research produced through the programme has already achieved important outcomes that resulted in real impact on the ground in terms of climate adaptation solutions adopted and policy supported that increase resilience. In particular, CLARE has influenced 20 government plans, policies or strategies to better integrate adaptation or improve climate resilient pathways (against a milestone of 24); and supported 17 climate adaptation solutions (tools, data, technologies, models and approaches) (against a milestone of 20) that were adopted by 60 organisations, institutions and communities (against a milestone of 31). Examples of policy impact include informing the draft of the third Nationally Determined Contribution (NDC) of Rwanda, (not yet approved but expected to be by end of calendar year), the Disaster Risk Reduction and Climate Change Programme of Action for the KwaZulu-Natal (KZN) province in South Africa, home of 12.5m people, and the draft of Nepal’s National Labour Migration Policy, which now recognises impacts from climate change to labour migration and migrants. The programme is also informing the planning for the upcoming Farkwa Dam in Tanzania, to ensure that leads to a sustainable use of water. Examples of solutions adopted on the ground include using a localised, impact-based forecasting system to identify weak points in the embankments potentially affected by Cyclone Remal, mobilise the local community to successfully reinforce them and significantly reducing the potential damage for around 200 households. The programme also produced an AI Flood Inundation Prediction Model that is now being used by a government Flood Task Force in South Sudan, to help them take action ahead of flooding.
- CLARE also achieved significant outcomes related to capacity strengthening, having met the relevant milestones around strengthening the agency of researchers and other actors involved in developing research for climate adaptation action. The vast majority of surveyed individuals directly involved in CLARE-supported project teams indicated that CLARE-supported activities had contributed to their capacity to conduct or apply climate adaptation research. The majority of researchers surveyed reported strengthened capacity to work in transdisciplinary research and capacity strengthening settings, improved ability to consider and address the concerns of diverse groups and differential vulnerability; and felt more equipped to design and conduct research in ways that position it for use and influence. Examples of capacity strengthening outcomes include training 24 community hydrologists in Dodoma, so that they have now mapped and collected data on borehole locations and levels, which are now being used to agree a sustainable water use regime for the capital of Tanzania, whose population is projected to grow at least 3-fold by mid-century. CLARE’s R4I Opportunities Fund facilitated the Central Bank of Uganda (BoU)’s access to climate risk data to conduct financial risk analyses, by connecting the Bank with local scientists, enabling the Bank to incorporate climate risks into its policy and decision making.
- CLARE has also delivered expected output milestones, by continuing to create and foster partnerships of diverse cross-sectoral actors and carrying out extensive capacity strengthening activities dedicated to climate adaptation action. The programme now counts 35 active research partnerships spanning 171 organisations in 44 countries (over 75% in Asia and Africa), carrying out research benefiting 36 countries. Additional 36 partnerships were established from previous ARA microgrants. Examples of new projects include URBAN TRACS, which brings together marginalised urban residents and local authorities in Sierra Leone and Kenya to enhance climate in informal settlements; CoHeRe, which uses cultural heritage as an entry point to bring together diverse groups across disciplines and coastal communities in Benin to support inclusive adaptation planning; ICRA, which is exploring how intersectional climate risk assessments can inform adaptation strategies in Nepal and South Africa. CLARE is also supporting the URBAN project through the Adaptation Research Alliance, using co-creation labs to identify climate resilient solutions addressing governance and finance barriers in 5 cities in Myanmar, Kenya, India and Philippines. The programme has also held 188 dissemination events involving over 16,000 participants in 51 countries. These included high-profile policy forums such as the UNDRR Africa Regional Platform and COP29; a national conference on migration, climate change, and societal change in Bhutan; the Eastern Africa Dialogue Platform on Anticipatory Action in Kenya, which resulted in a Declaration to scale up anticipatory action in the region; as well as grassroots activities like community theatre performances in Madagascar to raise awareness of early warning systems, which have attracted over 250 attendees and bolstered proactive preparedness.  In addition, over 200 capacity strengthening activities were delivered, involving almost 11,500 participants in 45 countries since September 2023. Examples include comprehensive training for community hydrologists in Tanzania, empowering women in Bangladesh through disaster risk reduction and gender justice workshops, and technical sessions for knowledge brokers in West Africa to develop early action protocols for flood response. The training provided a stress test of emergency response, with observed increased coordination across actors, and improved understanding of youth and communities on how to act swiftly when early warnings are issued.
  - In terms of public profile and FCDO Post engagement, CLARE partners contributed to high-level regional and international events such as the UNDRR Africa Regional Platform, the Global Meeting of the Anticipation Action Hub, and COP29. Where relevant, FCDO Posts and Ministerial teams provided representation during these events, including for example the British High Commissioner in Zambia providing the high-level opening of the annual CLARE conference, alongside the Zambian Minister for Green Economy and Environment and the Mayor of Lusaka; the UK Ambassador to ASEAN delivering inspiring remarks at the CLARE-ASEAN launch event in Jakarta; and the UK climate champion for the India and Indian Ocean Region delivering remarks at the CLARE in Asia workshop in Nepal.  Other notable engagements from Post included the DHM support for the G20 DRR Ministerial Meeting in Brazil; showcasing CLARE projects at the Brunei Mid-Year Conference and Exhibition; and supporting the Minister of Development's announcement of CLARE ASEAN at COP29, as well as her visit to South Sudan, which highlighted the impacts of flooding and the UK's support, including through the CLARE INFLOW project, in response to the humanitarian crisis.
  - The Adaptation Research Alliance has focused on transitioning the Secretariat to a different host organisation, implementing its governance process and setting up some organisational procedures that were still outstanding. This has limited the capability of the Secretariat to fundraise, which in turn has limited the outputs and outcomes that the Alliance was able to achieve, whilst its dependence on FCDO has continued. Despites these issues, the Alliance has continued to grow, albeit more slowly than previous years, and now counts 279 members, 66% from the Global South, and was able to achieve notable results. These included facilitating co-creation processes informing Gates Foundation programming and producing policy briefs through its regional leads that are expected to shape global dialogues on the Global Goal on Adaptation (GGA) and the New Collective Quantified Goal on climate finance (NCQG). ARA Member Insights were also shared with the Working Group II Technical Support Unit and are expected to inform aspects of the IPCC’s AR7 scoping process.
  - The partnership with the Met Office has continued to provide a wide range of dedicated support and services to FCDO and partners over the past year. Key climate information to FCDO and HMG stakeholders have continued to be provided through the Climate Outlooks, which were further tailored for global FCDO staff and further training provided, and the Climate Risk Reports, with a series of regional reports published covering the Asia region. The International Natural Hazard Forward Look service continues to provide weekly and monthly reports on global risks. Both the Outlooks and INHFL transitioned to the Science for Emergencies Centre of Expertise Programme in April this year. Met Office secondees and placements have made significant contributions, providing key scientific briefings to FCDO’s Chief Scientific Adviser and policy teams, informing FCDO’s policies and strategies, and providing timely information to FCDO Posts to help operational teams respond to upcoming weather events and climate variability, and programming teams to better incorporate climate risks into FCDO programming.
  - A mid-programme evaluation was carried out this year, focusing on CLARE’s capacity to achieve early outcomes, to be fit-for-purpose and to strengthen capacity of the individuals directly involved in CLARE. It confirms that CLARE is already contributing to meaningful early outcomes and is well placed to continue to do so, particularly in terms of influencing governmental actions and mobilising communities to take action to improve resilience. This is because of both the outcomes already achieved, and of the set-up of projects, benefiting from transdisciplinary teams that directly engage diverse stakeholders; dedicated efforts to establish constructive relationships with key stakeholders early on; and involving communities and governments in research co-design. The evaluation also found that the programme continues to be fit-for-purpose as it combines an evidence-informed programme design, alignment with good practice and socialised principles such as the Adaptation Research for Impact (R4I) principles, and the support infrastructure combining Programme Officers, Hubs, Working Groups, and platforms for ongoing sharing. Furthermore, the programme continues to build on its USP around enabling Southern leadership, which is also seen as a strength and much appreciated feature of the programme. Flexibility is regarded by supported teams as a strength of CLARE due to both the programme team at IDRC and FCDO’s willingness to adapt support, for example through supporting strategic partnerships or appropriate budget reallocations in response to evolving local contexts, as well as creating adaptive funding opportunities via the Hubs and project supplements, where needed. As mentioned above, the evaluation also found that CLARE is contributing to strengthening capacities of the range of actors involved in research teams, including early career researchers and practitioners. Whilst the overall findings of the evaluation have been positive, the process has identified some important areas where more could be done, in particular around achieving equitable partnership, focusing on a wider range of diversity issues and with regards to the timeline of the projects, as summarised in the next section.
Major lessons and recommendations for the year ahead
Many recommendations from last year’s Annual Review have been addressed:
- The team have carried out an extensive assessment of models for delivering the Research portfolio – including assessing models where the portfolio is delivered by a larger number of Tier 1 partners, with IDRC managing fewer, larger contracts whilst retaining direct management only of the riskiest contracts. The CLARE-ASEAN sub-programme has been implemented to test this model. However, the implementation of this model, expected for the next phase of CLARE, is being re-thought and will have to be reduced in scope due to the reduction in ODA budget.
- The role and structure of the R4I Hub have been reviewed, considering a model that better meets existing demand whilst providing better consistency across the programme. This model would involve the R4I Hub managing the relationship across working groups, as well as closer collaboration between the R4I and CS Hub, coupled with covering the central communication role and potentially MEL function across the programme. The implementation of this model is currently paused due to the uncertainty related to the ODA budget.
- FCDO has reduced the level of engagement that its advisers have with individual projects, relative to IDRC officers, in order to focus on more strategic aspect of the programme. This has been successful to date but, as expected, has highlighted the need for Tier 1 partners to bringing in more technical capabilities.
An important recommendation from the previous Annual Review that is still outstanding is around the sustainability of the ARA, thus repeated here with increased emphasis on its urgency:
Whilst a transition to a new Host Organisation for the ARA Secretariat has happened, including recruiting a new Head of Secretariat and electing new Steering Board members and co-chairs, the ARA continues to be mostly dependent on FCDO for funding. FCDO will reconsider funding in the future, including ceasing funding the ARA should the Secretariat be unsuccessful in bringing in any substantial additional funding by March 2026.
Issues emerging from this AR include:
- Whilst there has been substantive progress in the implementation of the research projects, and some of the outcomes have started to emerge, project teams have not reported on outcomes consistently. Whilst this can be due, for some projects, to deprioritising achieving outcomes compared to the academic results; for most projects probed, this appeared to be due to not capturing and reporting impacts sufficiently or to their full extent, as outcomes start emerging once a project is probed in more details. However, this lack of reporting has created uncertainty on whether projects are on track to achieve their potential in terms of impacts. Whilst projects are required to produce impact pathways within R4I Plans, which are then discussed with the R4I Hub to identify where support is more needed, this has been, in some cases, a separate process than the outcome identification and reporting, creating both inconsistencies and uncertainty to whether the R4I Plans are helpful to support projects achieving tangible outcomes.
- Whilst the logframe includes assessing sustainability of partnerships, and projects are required at proposal stage to outline the sustainability of their outcomes, at present there is no reported evidence on whether the changes in policies and capacity and the new tools produced would be viable and sustainable in the longer term.
- IDRC is steering projects and advising the programme successfully in focusing on research for impact, equitable partnerships and gender equality. However, transdisciplinary, complex projects require a wide set of technical expertise that can surpass that available in any one individual or organisation. As such, the CLARE team could draw in additional expertise to better steer projects, situating them in the broader context of strategic content-based outcomes with regards to climate adaptation.
- Whilst praising the Southern Leadership and equitable partnership within projects and across the programme, the external evaluation has also noted some ongoing challenges to ensure equal participation, including English remaining a dominant language, limited representation of and support for persons with disabilities within teams, stakeholders and beneficiaries, and perceptions that facilitators are predominantly white.
- The external evaluation also found issues in relation to the (short) duration of the projects, as this is not conducive to the co-creation, partnership building and capacity strengthening processes that are necessary to achieve action-oriented research. This was anticipated and it is consistent with the original design of CLARE being a 10-year programme.
- The uncertainty in time and budget for a follow-on phase of CLARE has delayed, and will require re-thinking, some of the transitions recommended during the previous Annual Review, in particular with regards to increasing the number of Tier 1 partners, as well as the new role of the R4I Hub. The uncertainty around CLARE3 also impacts on the ability to communicate no-cost extensions to projects, which in many cases would be very helpful to allow projects to achieve and harvest their full impacts, as highlighted by the external evaluation.
To address these, it is recommended:
1. It is fundamental that CLARE research delivers real outcomes and impacts by shaping policies, providing tools, building capacity and ultimately increasing people’s resilience and leading to transformational change. Whilst outcomes are starting to emerge, more should be done to support and encourage project teams to focus on, and report progress towards, these outcomes. It is recommended that, starting this year:
  1. Reporting mechanisms to IDRC need to fully integrate the CLARE MEL and logframe, with a clear assessment (and subsequent release of payments) of the progress that projects are making to achieve their intended impact.
  2. IDRC to ensure its Programme Officers understand the expectations of the CLARE MEL and ensure they are followed and reported against.
  3. IDRC and SSN must ensure that there is a stronger link between the impact pathways identified by projects, through the R4I Plans, and the MEL and Reporting processes.
2. The CLARE Executive Committee noted the importance of the sustainability of project’s outcomes. To assess and support the sustainability of outcomes it is recommended that:
  1. a detailed assessment is carried out by the end of 2025, with Programme Officers and the R4I Hub, probing the sustainability of each of the outcomes envisaged by projects.
  2. an overall assessment of outcome sustainability is included in the next phase of the evaluation.
3. By the end of 2025, the FCDO programme team, in collaboration with IDRC, should assess the range of capability and capacity needed to ensure projects, outputs and comms products have sufficient technical oversight, and agree a solution to secure the additional technical expertise needed. This could be achieved through expanding the IDRC team, by drawing further expertise from the R4I Hub or brought in from different partners.
4. The FCDO programme team will continue to monitor the assessment of equitable partnerships provided by partners and will seek assurance from Tier 1 partners (including IDRC). FCDO will also work with Tier 1 partners to ensure that disability issues will be better integrated into the GESI strategies, as far as possible within current projects (including better highlighting the positive strengths), and more structurally in the next phase of CLARE. FCDO will also work with partners to ensure that representation and facilitation will be more diverse. In particular, it is recommended that this is done by reviewing lessons from past experience including from CDKN and the REACH programme and identify actions by the end of 2025.
5. The FCDO programme team completes the design work of the follow-on phase of CLARE, in collaboration with IDRC, taking into account current budgetary uncertainty and potential constraints, whilst continuing to strive to implement the recommendations from last year – in particular around the development of the new R4I Hub, the diversification of partners and rationalisation of the portfolio around regional Hubs. The CLARE Executive Committee has also identified the need for capturing lessons from the current phase – both of successes and failures, as well as how the programme has shown adaptability and the value of it – and that they are used to both inform the next phase and further FCDO programming.
6. The landscape assessment of adaptation programming carried out by the R4I Hub has identified – and confirmed - CLARE’s USPs are its cross-sectoral nature, systemic approach, focus on transformational changes and embedding capacity and equity. A key enabler has been its ability to work and share evidence/lessons across multiple countries, with the Threads enabling the more substantive cross-cutting evidence to emerge, and the summary pieces produced by the R4I Hub enabling bringing together and disseminating cross-project findings. It is recommended that these continue to be sustained and possibly expanded in the next phase of the programme, and that in general the future phase of CLARE focuses on the programme USPs.
7. Following from the analysis around current programme risks (see section D), it is also recommended that FCDO refresh its understanding of IDRC’s controls with regards to the categories of safeguarding and fiduciary risks, as part of a due diligence refresh due next year.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

According to its Theory of Change (Annex 1), CLARE will achieve impact by ensuring that poor and marginalised communities in the Global South are more resilient to weather, climate change and related natural hazards in the near and longer term, through cross-sectoral networks and partnerships, strengthening along whole value chain from research to action, and through new knowledge for transformational change as well as tools, data and technologies for decision makers and practitioners.

The programme is going to deliver expected impacts in terms of increasing people’s resilience to climate change and supporting transformational changes in adaptive capacity through its outcomes, which are about increasing the adoption of actionable, socially inclusive climate adaptation solutions supporting the most vulnerable (Outcome 1) and strengthening agency of local governments, research bodies, practitioners and key stakeholders to do and use gender equitable and socially inclusive research for climate adaptation action (Outcome 2).

The programme works across three interlinked thematic areas, which also represent different timescales, covering the long-term, sustainable, and equitable economic and social development in a changing climate, early action to reduce impacts of climate variability and providing a better understanding of the risks associated with climate. For example, the research projects underpinning the ‘understanding risk’ theme not only aim to improve understanding of climate-related risks in countries such as Mozambique, Malawi, Madagascar, and South Africa, but also aim to use this information to inform both early warning systems and adaptation initiatives in the same countries.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Whilst it is too early for the programme to report on impacts, CLARE is on track to deliver its expected outcomes, although it is falling slightly behind on achieving its milestones. In all cases, research is progressing and likely to achieve its intended impacts, but in some cases, it is too early to be able to reach full adoption on the ground, either of a tool or of evidence being used in a policy.
The year ahead will focus in ensuring that the outcomes are fully met, as well as the impacts – by implementing the recommendations identified in this Annual Review.
Outcome 1 is underpinned by four milestones for this year, of which two have been partially met, one exceeded and one met. The programme has partially met its milestones around increasing the adoption of climate adaptation solutions supporting the most vulnerable, having influenced 20 government plans, policies or strategies to better integrate adaptation or improve climate resilient pathways (out of its milestone of 24); and supported 17 (out of 20) climate adaptation solutions (tools, data, technologies, models and approaches) that were adopted by 70 (against a milestone of 31) organisations, institutions and communities. The programme has also met its milestone by delivering 7 impact stories. Whilst overall the programme has satisfactorily achieved its expectations for this year, having partially met or met these milestones, and the external evaluation found evidence that the programme is on track to achieve its expected outcomes in terms of influencing governments and community action on the ground, this outcome continues to be closely monitored to ensure that it is fully achieved. This year, project teams have not reported consistently against this outcome, whilst this might be due, for some projects, to deprioritising achieving outcomes compared to the academic results; for most projects, this is due to not capturing and reporting outcomes sufficiently or to their full extent – as outcomes emerge once projects are probed in more details.
Examples of policy impact include:
- Evidence on economic impact from climate shocks, coping mechanisms, cost of solutions and differential vulnerabilities produced by ECONOGENESIS informed the draft of the third Nationally Determined Contribution (NDC) of Rwanda, and was used in particular to write the Loss and Damage Chapter.
- INACCT worked with the eThekwini Municipal Institute of Learning and South Africa’s Department of Co-operative Governance and Traditional Affairs to develop a programme of action and tools for municipal and traditional authorities to scale community-led solutions for inclusive flooding early warning and evacuation. The framework developed by INACCT was incorporated into CoGTA’s work for KwaZulu-Natal province, home of 12.5m people. This work draws on empirical evidence that demonstrate the remarkable ingenuity of low-cost solutions for disaster management, integrating scientific and local knowledge to scale them through targeted funding, institutional support and political will. through targeted funding, institutional support and political will.
- SUCCESS provided evidence to a government task force in Nepal on how climate change and labour-related migration are linked, and how this can be addressed in Nepal’s National Labour Migration Policy. The draft National Labour Migration Policy, currently before Cabinet for approval, now includes text that recognises impacts from climate change at different labour migration stages and potential actions, drawing on priorities identified through SUCCESS research, such as providing health support in the context of heat waves and flood risks, and supporting investment of remittances in climate resilient sectors.
- The evidence from REPRESA on the benefits of impact-based forecasting has resulted in an official endorsement from the UN Early Warnings for All (Ew4All) initiative, an global collaboration led by the WMO, UNDRR, ITU and IFRC, which in turn has led to impact-based forecasting now being incorporated into EW4All priorities.[1]
  [1] The Early Warnings for All (EW4All) initiative aims to ensure universal protection from hazardous hydrometeorological, climatological and related environmental events through life-saving multi-hazard early warning systems, anticipatory action and resilience efforts by the end of 2027, as called for by the United Nations Secretary-General António Guterres in 2022. ”
Examples of solutions adopted on the ground include:
- The Community Hydrology Training curriculum developed under CLARITY is being incorporated into the curriculum of the Farmer Water Schools, a province-wide initiative under the Karnataka state government in India, that also exists in other States in India (thus with a high potential of further uptake).[2] This is expected to create a cadre of volunteer community hydrologists who can support their communities to manage their water, for example by advising for example on the sustainable amount of water that can be extracted, on crop choices or soil management. There are very tangible possibilities of scaling these solutions, for example by engaging the community hydrologists with panchayats, Water User Cooperative Societies, other water schemes by the Government as the World Bank supported Modernization of Command Area Development scheme
  [2] Similar initiatives to the farmer water schools from other States (Provinces) of India include: - The Watershed Committees under the Jalyukt Shivar AbhiyaanIn Maharashtra - The Farmer Field Schools via Rythu Bharosa Kendras - The Water and Land Management Institute (WALMI), a State training institute which offers training to farmers under the Gujarat Irrigation Management Society in Gujarat
- SURF-IT used the localised, impact-based forecasting system that the project has developed, along with hydrological data provided by the Bangladesh Water Development Board, to predict potential embankment breach points in advance of Cyclone Remal. These predictions identified weak points in the embankments that, if left unaddressed, could have resulted in substantial losses to lives and property. The project team then mobilised the local community to successfully reinforce two of the identified weak points, preventing breaches and significantly reducing the potential damage for around 200 households.
- The AI Flood Inundation Prediction Model developed by INFLOW is being used by a national Flood Task Force and Technical Working Group in South Sudan, that include representatives from the Ministry of Water Resources and Irrigation and other officials, and it is helping them predict flooding and improve preparedness of vulnerable communities.
Outcome 2 is underpinned by two milestones, both of which have been met. The programme is on track to meet its outcome around strengthening the agency of both researchers and stakeholders to do and use research for climate adaptation action, with the vast majority of surveyed individuals directly involved in CLARE-supported project teams indicating that CLARE-supported activities had contributed to their capacity to conduct or apply climate adaptation research;[3] and 4 'case stories' demonstrating strengthened agency of local governments, research bodies, practitioners and key stakeholders to do and use research for climate adaptation action.
[3] Based on 124 (approx. 21% of the number of individuals involved on CLARE and subscribed on CLARE internal collaboration platform) surveyed individuals who were directly involved in CLARE-supported project teams, conducted by CLARE programme external evaluators), 89% of female and 91% of male respondents indicated that CLARE-supported activities had contributed to their capacity to conduct or apply climate adaptation research. Among those who responded to the survey, the vast majority live in the regions where CLARE works (61% in Africa and 27% in South Asia/Asia-Pacific), just over half identified as women, and most had minimal (47%) or some (36% experience in Climate Adaptation before joining a CLARE team. Most consider themselves academics (52%), while 35% identify as practitioners.
In particular:
- CLARE’s capacity strengthening efforts are reaching a diverse set of researchers[4] as well as increasing their capacity to achieve impacts on the ground that tackle adaptation in an equitable way. Ninety per cent (89% of females and 91% of males) of surveyed individuals directly engaged in CLARE-supported research teams agreed that CLARE-supported activities contributed to their capacities to conduct or apply climate adaptation research. In terms of particular areas of growth, the majority (65%) of researchers surveyed reported strengthened capacity to work in transdisciplinary settings; 61% reported improved ability to consider and address the concerns of diverse groups and differential vulnerability; and 52% felt more equipped to design and conduct research in ways that position it for use and influence.
  [4] To note: researchers is here used as synonym of individuals directly involved in CLARE, acknowledging that not all of them are researchers, as CLARE teams are made of researchers and practitioners.
- In Dodoma, the capital of Tanzania, CLARITY project has trained 24 community hydrologists, so that they have now mapped and collected data on borehole locations and levels, which now are being used by community-based water supply organisations and the Wami Ruvu Water Basin Board to agree a sustainable regime for extracting water. This is necessary for a city whose people and economic activity depend on borehole water, including to accommodate its projected growth from about 1m people now to a few million by mid-century. (Read more in the detailed case story in CLARE website)
- CLARE’s R4I Opportunities Fund facilitated the Central Bank of Uganda (BoU)’s access to climate risk data to conduct financial risk analyses, by connecting the Bank with local scientists. As a result, the BoU can better incorporate climate risks into its policy and decision making, and to implement its climate change risk policy. (Read more in the case story in CLARE website)
- RURBANISE has brought together scientists, architects, engineers, and NGOs, and helped seven informal communities in the Philippines to produce evidence and pilot solutions to understand and address the specific climate risks that affect them. This includes for example mapping key hazard-prone areas (e.g. areas prone to flooding) and exploring the potential for locally deployed environmental sensors to provide early warning. (Read more in the case story in CLARE website)
The programme is also on track to deliver its Theory of Change (ToC) as it is successfully implementing the approaches below. These approaches are a key part of the ToC as they ensure that the outputs will translate into the intended outcomes and impacts. These are:

- Transdisciplinary & systems approaches: CLARE has successfully created a portfolio of research projects that involve a breadth of disciplines and types of organisations and actors (including academic, policy, practitioner, NGO, humanitarian, etc.) and work across sectors and time scales. Furthermore, CLARE Threads working group has identified and is progressing on "linking short- and long-term actions to avoid maladaptation", on "how lived experiences influence climate adaptation actions" and on “climate-resilient development in the context of urban resilience”, the latter with the potential to feed into the IPCC Special Report on Cities and Climate Change. The outputs from these threads will be cross-project findings on these areas, thus evidence that goes beyond the context of the project thus can be applied more generally. This work supports the Theory of Change’s assumption that cross-programme collaboration and multi-level knowledge management and synthesis will lead to greater collective impact than a series of individual research projects alone.
- Southern ownership and capacity: The Research pillar has supported the establishment of a diverse and extensive network of 26 research partnerships including 135 organisations in 44 countries, 75% of which in Africa (69) and Asia (29), including a wide range of organisations, from research institutions in a range of disciplines, to NGOs, local government, Meteorological Agencies and from the private sector. Beyond project selection, CLARE is actively encouraging Southern leadership through creating collaborative spaces through its Working Groups as well as learning exchanges, and by actively encouraging projects to adopt internal ‘codes of conduct’ that focus on equitable partnership.
- Demand-responsiveness, co-design & co-development with users and engaging across the research to action value chain: Key requirements for all the research supported by CLARE is the application of the ARA Research for Impact Principles, meaning that all the selected proposals are needs-driven and that the research will be co-created with users / beneficiaries. Projects seek to identify adaptation solutions that are both evidence-based and co-created with users. For example, many projects such as CLARITY and REPRESA are doing so through lab-type approaches, i.e. inclusive spaces where stakeholders, practitioners and researchers come together to co-design and test ideas, co-produce knowledge and co-evaluate solutions. The Research for Impact (R4I) Hub also helps CLARE projects to set up the research so that it achieves impact on the ground, providing training as well as peer-learning opportunities, support, capture and leverage the collective findings as well as short summary pieces, and is running a demand-driven service to use knowledge from CLARE and predecessor programmes to answer demand from policy makers or other stakeholders..
- Gender equality and social inclusion. CLARE Research emphasised gender equality and inclusion considerations throughout the call and project selection process, ensuring a portfolio that engages intersectional members of marginalised communities in co-design and implementation. All 35 projects funded under the research pillar are at minimum GESI-integrated and GESI-sensitive. Six projects are GESI-specific, and four projects were designated as GESI-transformative. A GESI collaborative fund, managed in partnership with the Capacity Strengthening Hub, is supporting projects on masculinities, disability inclusion, and GEI-focused panels at events including a "Debates for a Changing World" conference held in the UK in June 2025. In addition, three capacity strengthening projects (Accelerating women’s leadership in climate action (AWARD), Enhancing local capacities in socially inclusive resilience in Asia (SIRA) and Innovative Facilitation for Resilience) are providing fellowships to 200 early to mid-career leaders, including over 100 women climate scientists and researchers.
- Cross-programme learning & collaboration: CLARE is designed to support collaboration and co-creation across all its activities. The four Working Groups established around Research-for-Impact (R4I), Capacity Strengthening, Monitoring and Evaluation (M&E), and Gender, Equality and Inclusion (GESI) now comprise hundreds of members from all of the CLARE projects and pillars.[5] In May 2025, the first in-person CLARExchange brought together more than 180 members of the CLARE global community in Lusaka, Zambia, advancing collaboration on key cross-cutting issues of CLARE work.
  [5] The four groups total 420 members, which however include the FCDO and IDRC project staff and count multiple times those members who are part of more than one group.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

- The CLARE programme continues to deliver high potential for impact and Value for Money. The research portfolio underway, its initial impacts on both adaptation actions and capacity of both those developing the research and those using the resulting evidence, the flexibility and cross-programme support from the programme’s infrastructure (Hubs, Knowledge Management Platform, Opportunity Fund) demonstrate its value and potential for transformational action and high-quality research and innovation. CLARE also continues to support and nurture key strategic Partnerships, including with the Adaptation Research Alliance that has continued on its journey in promoting and enabling co-creation of inclusive adaptation solutions; and by initiating a new strategic partnership with UNEP.
- The interest and support from partners and stakeholders in country, and the support from Posts are a strong demonstration of the programme’s merit to continue. The programme has seen strong engagement from research users and stakeholders from the very outset of the research and knowledge brokering work. High-level policy engagement is already evident in numerous projects – for example, CLARE partners substantively contributed to the UNDRR Africa Regional Platform, the Global Meeting of the Anticipation Action Hub, What Works Climate Solutions Summit in Berlin and COP29, including the negotiation decision text of the new collective quantified goal on climate finance (NCQG). This year showed continued to demand for CLARE opportunities, including over 300 organisations applying for the 20 slots offered by CO-CAT, 75 proposals received for four awards under ASEAN, and 508 applicants for 47 fellowships available under Accelerating African Women’s Leadership in Climate Action. CLARE’s sustained engagement with, and support from, diplomatic Posts has been demonstrated by the participation in local programme and project activities by the British High Commissioner in Zambia, the UK Ambassador to ASEAN, the UK climate champion for the India and Indian Ocean Region, and various policy and technical level staff from Posts in Indonesia, Nepal, Zambia, South Africa, Ghana and the Philippines.
- Evidence continues to mount confirming the increasingly urgent need for substantial and widescale action on climate change. The sixth IPCC assessment report (2022) confirmed that climate change impacts are experienced now, and they will increase. Evidence in that report showed that greenhouse gas emissions from human activities had unequivocally warmed the planet by 1.1°C already, causing widespread adverse impacts and related losses and damages to nature and people. The impacts already experienced are more widespread and severe than previous IPCC assessments, with adverse impacts intensifying with every increment of warming.[6] With recent years, newer evidence (WMO 2025) shows that global average warming has exceeded +1.3°C over preindustrial levels and there is 70% likelihood that global temperatures will exceed +1.5°C in 2025-2029.[7]
  [6] Sixth Assessment Report — IPCC
  [7] WMO (2025) State of global climate and Global annual to decadal climate update
- Research is needed to develop demand-led, evidence-based and context-specific solutions that also tackle underlying poverty, vulnerability, financial, governance, institutional and policy constraints. The evidence also continues to show that it is imperative to build resilience in the long term, also through sustainable, socio-economic development. Climate change impacts and socio-economic vulnerability go hand in hand: people in highly vulnerable areas are 15 times more likely to die in floods, droughts and storms;[8] and it is estimated that climate change will push 100m people into poverty by 2030 and 720m by 2050.[9] The IPCC AR6 noted that in the near-term (2021-2040) climate risks depend more strongly on changes in vulnerability and exposure than on differences in emissions scenarios'. Thus, reductions in vulnerability and exposure are paramount and it is therefore vital to tackle financial, governance, institutional and policy constraints. AR6 also highlighted that ‘the feasibility and effectiveness of options increases with integrated, multi-sectoral solutions that cut across systems and address social inequities'.[10]
  [8] Sixth Assessment Report — IPCC
  [9] openknowledge.worldbank.org/server/api/core/bitstreams/aa3a35e0-2a20-5d9c-8872-191c6b72a9b9/content
  [10] Sixth Assessment Report — IPCC
- Despite the urgency and need, adaptation research is considerably underfunded and only a tiny fraction flows to the poorest countries that are most in need of actionable evidence and strengthened research capacity. For instance, only 3.8% of climate-related research funding globally from 1990–2019 was devoted to the entire continent of Africa, of which 78% went to EU and North American institutions (IPCC AR6). Many countries lack both the institutional and the scientific capacity to identify and implement evidence-based, effective adaptation solutions. Research such as that supported by CLARE, linking up short-and long-term issues, is aimed at tackling this, and the high volume of good quality, Southern-led responses to the first CLARE research call demonstrates that the programme is well positioned to address this tangible need.
- Climate science, adaptation and resilience, and the importance of cultivating genuine partnerships and of ‘localisation’ are consistently identified as a top priority for FCDO as well as of the new UK government with climate remaining one of the government priorities. CLARE also supports other priorities, including supporting Fragile and Conflict Affected States (FCAS) and Women and Girls. It also directly contributes to the $100 billion target towards climate finance to which the UK is committed as well as the commitment to spend £11.6bn on International Climate Finance by 2025. Equitable research partnerships between the UK and international actors also provide the additional benefit of building and deepening lasting relationships and scientific collaboration between the UK and developing nations. The approach strengthens research capacity, whilst benefiting policies, decision-makers, scientists and practitioners, fostering wider innovation in these countries. As CLARE is RED’s principal programme on climate adaptation, resilience and disaster risk, its role in the context of FCDO’s wider portfolio remains fully justified.
## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Note that all counts are cumulative from the beginning of CLARE unless otherwise sated
Output Title	Collaborative partnerships of diverse cross-sectoral actors dedicated to gender-equitable and socially inclusive climate adaptation action are created and/or strengthened
Output number:		1		Output Score:	A+
Impact weighting (%):		20%		Weighting revised since last AR?	Yes

Indicator(s)			Milestone(s) for this review		Progress
1.1.1 Number of inter-disciplinary action-orientated research partnerships that CLARE has provided with direct financial support (cumulative)			Research: 31 / Services: / Partnerships: 36 / Total: 67		Mostly exceeded / Research: 35 / Services: / Partnerships: 36 / Total: 71
1.1.2 Number of organisations that are part of CLARE-supported action-orientated research partnerships			Research: 137 / Services: 15 / Partnerships: 286 / Total: 438		Exceeded / Research: 171 / Services: 15 / Partnerships: 286 / Total: 472
1.1.3 Number and percentage of CLARE supported research partnerships that / i) represent diverse research teams / ii) include transdisciplinary teams/focus / (new partnerships assessed this year; last year’s partnerships counted based on last year’s assessment)			Research: 80% of teams demonstrate at least moderate diversity (heterogeneous across at least 1 key GEI identifier) / At least 80% of teams are transdisciplinary (include individuals and/or organisations that represent different types of disciplines). / Services: n/a / Partnerships: 80%		Exceeded / Research: 100% / Services: n/a / Partnerships: 100%
1.1.4 Number of engagement and outreach events organised or co-organised by CLARE-supported partnerships for the purpose of sharing and encouraging use of evidence by key stakeholders.			Research: 100 / Services: 4 / Partnerships: 126		Substantially exceeded / Research: 188 / Services: 4 / Partnerships: 126

Briefly describe the output’s activities and provide supporting narrative for the score.

CLARE has exceeded all output indicators for partnership creation and strengthening. Across the research pillar, the programme now supports 35 partnerships, involving 171 organisations across 44 countries, with a strong focus on Asia and Africa (75%). All teams demonstrate moderate to high diversity and a transdisciplinary approach, ensuring a wide range of perspectives and expertise. New partnerships have expanded CLARE’s reach into urban resilience, health systems, and nature-based solutions, reflecting the programme’s transdisciplinary focus and commitment to inclusive, action-oriented research. In addition to the 171 organisations, and the Met Office’s relationship, partnerships this year have included British Geological Survey, Public Health England, DEFRA’s Animal and Plant Health Agency, ODI, Save the Children, and the Start Network Community of Practice, further strengthening the diversity and reach of CLARE-supported action-oriented research partnerships.

Over the past year, 188 engagement and outreach events were held, reaching over 16,000 participants, including high-level policy regional and international events as well as community-based activities. Notable examples include the UNDRR Africa Regional Platform, the Global Meeting of the Anticipation Action Hub, COP29, but also the National Conference on Migration, Climate Change and Societal Change in Bhutan, as well as community theatre performances in Madagascar to raise awareness of early warning systems.  Additionally, sessions led by PASSAGE project at the Eastern Africa Dialogue Platform in Kenya contributed to a Declaration to scale up anticipatory action across the region, which will inform future anticipatory action strategies across East Africa. The Met Office contributed to 4 engagement and outreach events this year, reaching a wide range of stakeholders from FCDO staff to humanitarian and policy partners. The ARA expanded to 279 member organisations (66% from the Global South) and delivered impactful co-creation spaces, toolkits, and policy briefs, strengthening diverse, cross-sectoral partnerships. The Alliance also organised over 110 engagement and outreach events (webinars, policy workshops, regional advocacy sessions), increasing the dissemination of evidence to key stakeholders and raising the profile of action-oriented research.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The weightings for all output scores were changed to 20% to reflect that all the outputs have the same importance this year (a shift from last year where there was a stronger emphasis on building partnerships and capacity over the research outputs). Whilst monitoring the equitability of each partnership will continue to be important, it is anticipated that the number of partners will not substantially change next year, thus the weight of this indicator might be revised to be lower.

Output Title	Capacity strengthening of researchers, knowledge brokers, policy makers and practitioners for gender transformative and socially inclusive climate adaptation research and action is provided
Output number:		2		Output Score:		A+
Impact weighting (%):		20%		Weighting revised since last AR?		Yes

Indicator(s)			Milestone(s) for this review		Progress
2.1.1 Number of capacity strengthening activities conducted through CLARE programme			Research: 150 / Services 2 / Partnerships: 81 / Total: 233		Exceeded / Research: 216 / Services: 2 / Partnerships: 78 / Total: 286
2.1.2 Number of attendees participating in capacity strengthening opportunities offered by CLARE programme			Research: 5000 / Services: 12 Partnerships: 2085		Substantially exceeded / Research: 11,157 / Services: 12 / Partnerships: 2,100
2.1.3 Number of countries in which CLARE-funded capacity strengthening participants are based			Research: 32 / Services: N/A Partnerships: 30		Exceeded / Research: 45 / Services: 7 / Partnerships: 8 / Unique number of countries: 45

Briefly describe the output’s activities and provide supporting narrative for the score.
CLARE delivered 216 capacity strengthening activities, reaching over 11,000 participants (45% female, 32% male, 23% unknown) in 45 countries, 83% of whom are based in the Global South. Last year’s activities targeted a wide range of stakeholders, including students, researchers, practitioners, policymakers, and community members, with a strong emphasis on gender and social inclusion. In Tanzania, CLARITY project trained 24 community hydrologists in Dodoma, who have mapped and collected data on borehole locations and levels, enabling community-based water supply organisations and the Wami Ruvu Water Basin Board to make informed decisions on sustainable water extraction practices. In Bangladesh, the capacity strengthening initiatives have empowered women to take active roles in disaster risk reduction, ensuring that gender perspectives are integrated into local disaster preparedness and response strategies. The technical workshops in West Africa have facilitated the development of early action protocols for flood response, promoting cross-border collaboration and alignment across humanitarian, academic, and government institutions. Met Office delivered training for international meteorologists, humanitarian partners, and internal staff, as well as co-learning sessions with NGOs and regional networks. The ARA conducted 5 targeted activities, engaging 51 participants from four countries and rolled out a new Gender Equality and Social Inclusion strategy and toolkit. These activities have contributed to building transdisciplinary collaboration and enhancing the ability of local actors to design and implement effective adaptation solutions.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output was missed during the previous AR, thus the milestone was set conservatively. However, this milestone was exceeded this year, suggesting that a middle ground should be adopted when setting next years’ milestone.
Output Title	New and improved science that supports socially inclusive climate adaptation action is produced
Output number:		3	Output Score:		A+
Impact weighting (%):		20%	Weighting revised since last AR?		Yes

Indicator(s)			Milestone(s) for this review	Progress
3.1.1 Cumulative Number of research publications, working papers and grey literature produced resulting from CLARE programme funded research activities (of which peer reviewed).			Research: 85 / Services: 49 / Partnerships: 28 / Total: 162	Exceeded / Research: 107 (32 peer-reviewed) / Services: 49 (2 peer-reviewed) / Partnerships: 63 (1 peer-reviewed) / Total: 219 (35 peer-reviewed)
3.1.2 Cumulative Number of climate adaptation solutions (tools, data, technologies, models, approaches) created or significantly improved through CLARE supported research activities.			Research: 50 / Services: 2 Partnerships: 7 / Total: 59	Met / Research: 51 / Services: 3 / Partnerships: 6 / Total: 60
3.1.3 The average quality rating of projects and activities on gender equality and social inclusion.			Research: 5.5 / Services: N/A Partnerships: N/A	Exceeded / Research: 5.9 / Services: N/A / Partnerships: N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

CLARE-supported research has produced a growing body of peer-reviewed and grey literature, with notable contributions from women and Global South (local) researchers. Research for Impact Hub produced the first CLARE programme working paper, "Research for impact approaches in CLARE: bridging science and action," and thematic briefs on building climate-resilient cities, addressing flood risk, and innovation for water security. Several innovative adaptation solutions have been developed or improved, including AI-based forecasting tools, gender-responsive methodologies, and participatory water management models. Notable examples include:
- BIMA's GIS-based framework, 3Map: Enhances drought monitoring and response through localised, data-driven decision-making.
- CLARITY's ladder-based approach to lake restoration: Reduces groundwater overexploitation and involves local communities in water conservation efforts.
- ECONOGENESIS's Adaptation Gap Database: Informs global climate finance negotiations and supports the Global Stocktake.
- INACCT's flood forecasting model: Provides cost-effective, accurate flood predictions for municipal disaster management.
- INFLOW's flood inundation prediction model: Integrates satellite data and advanced simulations to support anticipatory action in South Sudan.
- WOSFER's online platform for women farmers: Offers weather information and agricultural advisories to enhance climate resilience for women smallholder farmers.
- SURF-IT's localised forecasting system: Combines AI and community knowledge to improve tidal surge and cyclone preparedness in coastal Bangladesh.
- REPRESA's training pack for forecasters: Enhances skills in climate projection and flood forecasting, with potential for regional scaling.
- REBUMAA's Early Action Protocols: Co-created with stakeholders in Benin, Nigeria, and Togo to improve flood response and resilience.
The average GEI rating has increased, and Programme Officers note a growing focus on inclusion across the portfolio, along with deep intersectional considerations across new projects such as Tuwe Pamoja, iCRA and Urban TRACS. Met Office has significantly improved the Climate Outlook product, developed new climate profiles for four countries, and advanced the INHFL system with a new platform. ARA contributed 41 research publications and grey literature outputs, focusing on ensuring science is contextually relevant and action-oriented.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The progress on this output exceeded expectations in terms of publications, whilst being met last year, which is an important progress reflecting the maturity of the programme. The development of tools met the expectations,
Output Title	Tools and technologies for decision-makers that supports socially inclusive climate adaptation action are co-developed and tested
Output number:		4	Output Score:		A+
Impact weighting (%):		20%	Weighting revised since last AR?		Yes

Indicator(s)			Milestone(s) for this review	Progress
4.1.1 Testing Climate adaptation solutions (tools, data, technologies, models, approaches): / i) Number of organisations (institutional stakeholders) involved in co-developing and testing the tools			Research: 100 / Services: 2 / Partnerships: 267	Exceeded / Research: 169 / Services: 2 / Partnerships: 267
4.1.1 Testing Climate adaptation solutions (tools, data, technologies, models, approaches): / ii) Number of people involved in co-developing and testing the tools			Research: 1200 / Services: 50 / Partnerships: 438	Substantially exceeded / Research: 5099 / Services: 50 / Partnerships: 438
4.1.2 The Average Positioning for Use Scores for CLARE-supported research and activities, which includes: / i) RQ+ 4.1 User Engagement Score assessing the degree to which the research project built meaningful, two-way connections with intended knowledge users. / ii) RQ+4.2 Openness and Actionability Score assessing deliberate intent to ensure research results are useful for knowledge users.			Research: 5.5 / Services: N/A / Partnerships: N/A / Total:5.5	Exceeded / Research: 6,4 / Services: N/A / Partnerships: N/A / Total: 6.4
4.1.3 Percentage of female and male users involved in testing climate adaptation solutions that report high satisfaction with the usefulness of the solution tested.			Research: 50% / Services: N/A / Partnerships: N/A / Total:50%	Not reported this year / Research: N/A / Services: N/A / Partnerships: N/A / Total: N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

CLARE projects have actively engaged a diverse range of organisations and communities in co-developing and testing climate adaptation solutions, involving governmental bodies, intergovernmental organisations, met agencies, practitioner groups, and private sector entities. This collaborative approach has fostered connections with intended knowledge users, supporting the likelihood that research results are actionable and accessible. User engagement and openness scores are high, indicating good co-creation and accessibility. High user engagement scores also reflect the projects' focus on building relationships and co-creation processes, which are already yielding positive outcomes. (Early evidence shows that these efforts are leading to real-world adoption and policy influence). The increase in openness and accessibility scores indicates that projects are progressing well and better able to demonstrate the actionability of their research. The high number of individuals involved in testing the solutions compounds the outcome reported above on adoption, the latter also providing a proxy for users’ satisfaction despite this information not being collated this year. Overall, CLARE’s collaborative and inclusive approach to developing and testing climate adaptation solutions has resulted in high engagement, openness, and satisfaction among users, contributing significantly to the programme’s success in advancing climate resilience. ARA also successfully created co-creation spaces in Urban Resilience, LDC Universities, Smallholder Agriculture, and Nature-Based Solutions, involving numerous organisations in the development and testing of climate adaptation solutions. These activities produced impactful outputs such as the SECURe toolkit, which is now implemented in the URBAN project, and several policy briefs, advancing the Climate and Health agenda and engaging with funders like the Rockefeller Foundation and Wellcome Trust.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
This year, CLARE decided not to collect data on indicator 4.1.3 in order to manage demands placed on project teams and focus on solutions developed and adapted. We recommend revising this indicator, also taking into account the need to avoid respondent fatigue of those participating in the co-development of solutions. Moving forward, CLARE can sharpen the method used to assess satisfaction in a manner that can be quality assessed at programme level, especially as evidence of uptake of solutions (materializing through programme outcomes) indicates a level of satisfaction. at programme level, especially as evidence of uptake of solutions (materializing through programme outcomes) indicates a level of satisfaction.
Output Title	New and existing knowledge is brokered and disseminated to additional key stakeholders including decision-makers, practitioners, researchers and local communities (beyond those stakeholders targeted within the scope of the research projects).
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
5.1.1 Number of knowledge brokering services delivered by the CLARE Programme to stakeholders (beyond those targeted within research projects)	Research: 2 / Services: N/A / Partnerships: N/A / Total:2	Met / Research: 2 / Services: N/A / Partnerships: N/A / Total:2
5.1.2 Number of organisations that receive knowledge brokering services delivered by the CLARE Programme	Research: 2 / Services: N/A / Partnerships: N/A / Total:2	Met / Research: 2 / Services: N/A / Partnerships: N/A / Total:2
5.1.3 Percentage of organisations receiving knowledge brokering services delivered by the CLARE programme reporting high satisfaction	Research: 75% / Services: N/A / Partnerships: N/A / Total:75%	Exceeded / Research: 100% / Services: N/A / Partnerships: N/A / Total:100%

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme has met its output in brokering and disseminating new and existing knowledge to a wide array of stakeholders, including decision-makers, practitioners, researchers, and local communities, beyond those directly involved in the research projects. This year, the programme successfully delivered two knowledge brokering services, responding to the demand from various organisations such as the Bank of Uganda, which sought to leverage climate data and scientific networks to implement its climate change risk policy. The R4I Hub facilitated tailored expertise sessions and workshops, engaging professionals from Uganda’s climate and financial sectors, which resulted in immediate outcomes as evidenced by the strengthened capacity of the Central Bank of Uganda to incorporate climate risks into its policy and decision-making processes. Additionally, the programme has initiated four new opportunities in Kenya, Nepal, Bangladesh, and India, aimed at extending the use and impact of research through innovative activities aligned with local needs. The satisfaction rate among organisations receiving these services were 100%. This commitment to knowledge brokering is further demonstrated by the opening of the R4I Opportunities Fund to CLARE projects, enabling them to undertake additional activities that enhance the use and impact of their research. These activities have broadened the reach of CLARE's knowledge dissemination efforts and ensured that the research outputs are positioned for practical application and influence.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output was missed last year because it took longer than expected to initiate, scope and deliver the knowledge brokering requests. The milestones for this year were therefore kept very conservative.

## D: VALUE FOR MONEY (1 page)

The main cost drivers have remained consistent with those expected in the business case.
- The largest cost driver relates to the research & capacity strengthening project activities – with vast majority covering research staff salaries and associated research costs. A small proportion was allocated to travel and subsistence costs.
- Other cost drivers include
  - IDRC Project Management Costs (7% of the value of the MoU with IDRC)
  - Remuneration for FCDO programme funded staff who provide technical input and ensure CLARE is visible and coordinated with local policy and programming,
  - Research for impact support services (4.5% of the total Phase 2 value)
  - Monitoring and evaluation (0.5% of the total Phase 2 value).
  - Open access publication costs, in line with our principles of being open and transparent.
- Performance against business case indicators remains broadly on track as noted in sections.

Assessment of whether the programme continues to represent value for money

CLARE continues to represent value for money for taxpayer. The table below sets out an analysis on the programme’s approach against the four ‘E’s.

Value for Money Category	Examples of Evidence
Economy (inputs, i.e. spending less). Using the lowest cost use of goods and services within a project and ensuring and that input unit costs are benchmarked against market norms	The programme achieves economies in the following ways: / Research projects were selected through a highly competitive selection process to ensure funding goes to strong and relevant proposals. So far, CLARE supports 35 partnerships with 171 organisations in 44 countries, through a more coordinated and integrated approach, offering an economy of scale within a constrained budget. / Budgets for all projects were closely scrutinised as part of the project appraisal, diligence and contracting, with some negotiation of budgets resulting in cost reductions. This includes ensuring travel and subsistence costs are proportionate to activities in the budget (something that will be monitored as part of project reporting as well) and comply with IDRC day rates and expenses policies, which are consistent with FCDO’s. / The increased participation of southern-led, local research organisations strengthens the quality and contextual relevance of the research. Also, the increased participation of southern led local research organisations reduces travel costs and carbon footprint compared with predecessor programmes. / The partnership with IDRC is economical and value-adding, with IDRC providing 15% co-financing of the research component, and leveraging IDRC’s established competitive research call processes and research protocols for ensuring research quality throughout delivery. / IDRC project management costs are currently 7% - which is in line with amount and proportion (10%) agreed at programme outset / IDRC sub-contracts comply with IDRC agreed rates and expenses policies. The digital design was phased including, user needs analysis and concept, test site, full build to ensure fit for purpose. The design uses existing, open-source tools rather than reinvesting, and the design and costs were reviewed by IDRC and FCDO digital approval teams. / Technical experts are carefully selected and use approved IDRC rates. / IDRC Management and administrative fees are charged at rates agreed with FCDO. / FCDO negotiated reduced long-term rates with the UK Met Office for delivery of the Climate Risk Reports, and FCDO engage closely in risk report development to avoid cost-overruns.
Efficiency (i.e. spending well). This refers to ensuring the quality and quantity of inputs are appropriate to achieve the envisaged outputs and that inputs are managed in an efficient way during project delivery	CLARE was designed as one integrated programme instead of several separate initiatives to more efficiently bring different partnerships, organisations and support mechanisms together: / The platform programme enabled single support services on Research for Impact (R4I), Capacity Strengthening, MEL and Gender, Equality and Inclusion to be set up to support across a large number of research projects – providing a cheaper, more efficient delivery model than setting these up across multiple separate programmes, and better facilitating cross-learning. / Single cross-CLARE events (such as CLARExchange) enable different sectors such as climate scientists, cross-sectoral, and humanitarian actors to connect and share learning in one place. This wouldn’t typically happen under siloed programmes. / The competitive research call selection process prioritised projects with strong research to impact pathways, bringing research end users into projects from the outset. This ensures the research work is relevant, focused on delivering useful outputs that have tangible pathways for adoption. / The MEL platform enables efficient reporting and disaggregation – this is enabling earlier assessment of project progress from outputs through to outcome/impact. / The R4I hub is supporting projects to ensure these R4I pathways are prioritised and effective. This is enhancing the efficiency of ensuring that evidence is used in practice thus enabling reaching the achieve planned number of beneficiaries. This has also helped IDRC and FCDO identify early if research for impact plans are offtrack and enable early course correction. / All CLARE projects are transdisciplinary, engaging research users such as policymakers, civil society, and local communities throughout the research process, not just at the end. Projects intentionally align with local and regional priorities by encouraging actors from different societal sectors, including government and community groups, to play an active role. This supports co-production and co-creation, which are essential for building adaptive capacity and ensuring research leads to real world impact. CLARE builds on IDRC’s strong foundation in this area, demonstrating that investing in transdisciplinary approaches is an effective way to support long-term, user-driven adaptation solutions. Currently, 100% of CLARE-funded teams include a transdisciplinary focus. / The programme’s research services delivered by the Met Office, with Met Office secondees embedded in FCDO research team to ensure the services are relevant and useful to inform programme development and humanitarian response planning.
Effectiveness (i.e. spending wisely). Demonstrating that the chosen outputs are the most effective way to achieve the outcome	The CLARE Phase 2 Research Portfolio achieves the scope envisioned by the business case. All projects are endorsed by end users at the outset representing real and immediate adaptation needs. The portfolio covers a diverse range of climate risks and adaptation needs, where there are climate science and adaptation knowledge gaps. / The projects selected deliver research and adaptation action across 35 countries, while providing knowledge and tools on issues that represent much wider needs. Therefore, the scope for wider application of the knowledge generated is significant. The projects were selected based their focus on the poorest and the most vulnerable groups, and the strength of the research for impact (action) pathways, to ensure the programme is best positioned to improve the ability of at least 5million people to cope with climate change. / Robust processes are in place to maximise potential to achieve stated outcomes with IDRC Programme Officers closely managing projects to ensure they are on track in terms of research protocols, outputs and outcomes. CLARE logframe indicators (including annual KPI15 assessments) track the effectiveness of each research project reviewing research quality parameters, adaptation tools developed, engagement of relevant end users in testing those tools, evidence of policy change and adoption of tools, and resulting number of beneficiaries. / CLARE focuses on outputs most likely to lead to meaningful, long-term outcomes especially informing national policies, supporting local preparedness, improving risk assessment, and reducing climate risks. Projects produce knowledge and actionable adaptation solutions developed collaboratively with end users. This results in the uptake and use of new policies, approaches, and tools that increase the resilience of vulnerable communities. Early outcomes are demonstrating the effectiveness of this approach with 20 policies informed by CLARE research, and over 17 climate decision making tools developed by CLARE and adopted into use. / The role of the R4I Hub in ensuring the uptake and in supporting threads that generate evidence emerging across projects, increase the effectiveness of the programme by ensuring that research translate into action on the ground, and by ensuring that the evidence generated is more than of the sum of evidence generated by individual projects. / A key element of CLARE’s approach to driving transformational change is CLARE’s that capacity strengthening for researchers including early career researchers' policymakers, practitioners, and community members is integrated into how research projects are delivered. With over 200 activities reaching more than 11,000 participants across 45 countries, with surveyed participants reporting increased capacity, CLARE is building practical skills and knowledge to support socially inclusive climate adaptation. By strengthening capacities across diverse actors especially Southern actors, CLARE ensures that research is not only generated but actively mobilised and used to inform adaptation strategies and decision-making processes. This effort is key to effectiveness as well as sustainability.
Equity / This considers how the needs of poor and marginalised groups are incorporated	The CLARE portfolio prioritises Southern leadership, situating members of marginalised communities as decision-makers and powerholders and engaging them from the outset in co-design and implementation. CLARE ensures genuine, equitable partnerships with a broad range of southern-based partners and sub-grantees, both research and non-research, including research organisations, universities, the private sector, non-governmental organisations, women`s rights organisations, LBGTQI+ groups, disability rights groups, and youth groups, amongst others. / CLARE Research emphasised gender equality and social inclusion considerations throughout the research call and project selection process, responding to findings and lessons from CLARE transition phase. / CLARE output indicators confirm CLARE’s focus on gender equality and social inclusion. All 35 projects funded under the research pillar are at least GESI-integrated, with six GESI-specific. All projects are also at a minimum GESI sensitive, with 24 designated as responsive and four as transformative (representing increasing levels of ambition). / CLARE output indicators also confirm that its research portfolio focus on equitable research partnerships that include co/leadership of southern institutions and researchers with two-thirds (70%) of CLARE partner research intuitions from Africa and Asia. 61% of CLARE researchers surveyed this year reported improved ability to consider and address the concerns of diverse groups and differential vulnerability / A cross-programme working group, representing all projects, came together in Rwanda in September 2024 to reinforce practical steps to champion equality and inclusion in CLARE. Participants identified opportunities to work together on intersectionality, disability inclusion and masculinities. CLARE supported content and southern participation at the "Debates for a Changing World" workshop held in the UK in June 2025, which has catalysed a proposed special issue on marginalised communities and intersectionality for Climate and Development journal. / The Adaptation Research Alliance, with funding from CLARE, has also recently finalised its overarching GESI strategy, which will require an implementation drive from the new secretariat. Aside from the formal implementation of GESI across all activities, the secretariat will put GESI into decision making and engagement, for example the Steering Board and selection of suppliers has specific gender requirements in order to ensure that women and marginalised groups are represented.

Assessment of whether the programme continues to represent value for money

The programme continues to deliver high potential in terms of achieving Value for Money. The research portfolio underway, its initial impacts on both adaptation actions and capacity of both those developing the research and those using the resulting evidence, demonstrates its value and potential for transformational action alongside the high-quality research and innovation outputs being produced. The work delivered by the Met Office continues to empower FCDO to respond to pressing and increasing demand for climate evidence from Embassies, Consulates, central policy departments and regional offices to support development policy and programming. While continuity of Adaptation Research Alliance will depend on ARA securing co-funding this year, within CLARE the ARA has exceeded expectations in promoting and enabling co-creation of inclusive adaptation solutions.

## E: RISK

Overview of risk management

The current overall risk rating for CLARE programme is Moderate, though this is being kept under review, especially given current economic contexts. A comprehensive risk register is in place and has been updated throughout the year to reflect the changes in the context of the programme, on the operating environment, and the findings from monitoring visits and quarterly discussions. This risk register is kept updated and used for tracking, managing, and reporting on risks in the next reporting period and through the programme life cycle. This is a high ambition programme; risks are manageable by working with established partners with proven track records and by allocating adequate FCDO people resource to manage the programme. Our mitigation efforts are designed to ensure coordination across partners and a coherent MEL strategy will include effective engagement and use of an in-house MEL adviser and external MEL supplier role.
This programme has a receptive appetite to risk because of its nature of being research programme. Most of the potentially major risks are managed to a moderate risk level whilst accepting that few of the activities carry a moderate-to-major degree of residual risk, due to operating in fragile contexts and producing pioneering climate and adaptation research. No risks have been identified outside of the programme or department’s risk appetites.
The main risks are summarised below by Risk Category together with their mitigating actions:
Strategy and context risk are considered moderate to minor. The only risk identified in this category is around the programme working across 36 developing countries, including fragile states. This poses risks due to the complexity of the political economy, hindering the ability of partners to successfully operate in a country. These risks could affect research and data collection activities; controlled research environment (e.g., replicability of findings); or the ability of researchers to interact with governments, thus undermining uptake and impact pathways. At programme level, this risk is managed through the geographical diversity, and by assessing the number of countries at risk vs the total number, to ensure that overall the portfolio can produce meaningful results. Besides this, all projects are assessed on their political situation and stability, with plans for research findings to be used even if the research need to stop abruptly, and prioritising the safeguarding of staff and stakeholders.
Policy and programme delivery risks are now moderate or minor. The main delivery risks are related to 1. the ability of the programme to secure and maintain funding and 2. The ability of the programme to deliver meaningful adaptation action that has an impact on the ground. The first risk continue to be ‘moderate’ as the programme team is continuing to ensure that the programme is branded, disseminated and achieve impact that demonstrate its value, that it’s able to manage a level of funding variability and that is responding to current priorities. The second risk is mitigated by the programme’s design, ensuring that its approaches around co-creation, equity and inclusion, transdisciplinarity and systemicity are implemented through secure robust, actionable outcomes – and this implementation is supported by the MEL framework and working groups.
Safeguarding risks are present in the contexts in which projects are working, with residual risks assessed as moderate with further mitigating actions underway and planned. FCDO have a cautious appetite for safeguarding risk seeking to mitigate these risks as far as possible, and the team ensures that all partners are aware of these expectations and have robust policies which are implemented to prevent harm to partner staff or research participants and local communities. . IDRC attended the RED safeguarding partner learning session in 2025. Fortnightly check-ins with IDRC, include safeguarding risk as standing agenda item. FCDO will be refreshing its understanding of IDRC’s controls as part of a due diligence refresh due next year.
Financial and Fiduciary risks have been mitigated to a moderate residual risk. The main risk in this category is due to the reduction of ODA spend and, more generally, to the changes in the global economic situation that could result in further re-prioritisations. Besides continuing to make the case for funding, as outlined above, from a financial perspective this risk has been managed by ensuring flexibility in the portfolio, transparent dialogue with partners to review project expenditure across the portfolio lifetime. IDRC has shown an excellent flexibility to bring forward or delay activities (particularly strategic opportunities fund or support services) in accordance with budget allocated each year, and in working closely with FCDO to assess the impact of potential budget variations and options to minimise impact on the delivery of the outcomes, which has also been made possible by the ability of IDRC to accurately forecast spending patterns and foresee opportunities. Local Research and Community Based Organisation’s institutional policies and procedures can vary widely, with capability assessed as part of Tier 1 partner’s pre-project due diligence. FCDO and IDRC are reviewing learning from these assessments to enable local participation by building capacity and minimising risk.
The Operational risk has now been increased from minor to moderate. This is because of the current gaps in FCDO programme staff, which has not been possible to fulfil due to the current recruitment freeze. Understaffing on programme management leads to inefficiencies, with the lead adviser cover gaps on programme management with less time to drive the technical research quality.
Reputational risks have been mitigated to moderate or minor residual risk. The main ongoing reputational risk remains around the budget uncertainty and predictability, which is beyond the programme control and has been managed by ensuring transparency and dialogue with partners, as well as through managing the impacts on delivery as outlined above. The other reputational risk is classed as minor, and it relates to the ARA not being financially sustainable. While the ARA has delivered significant past results in enabling action-orientated adaptation research, there has been limited success in securing co-funding, therefore the FCDO will leave funding the Alliance if the Secretariat does not become financially independent by March 2026.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues.
Overall, implementation of the programme is progressing satisfactorily, with programme management activities discussed in detail regularly at quarterly meetings. CLARE is co-funded by IDRC, and the partnership is performing well at all levels, and there are regular meetings at operational as well as strategic levels.
Update on quality of financial management
For the IDRC projects, financial management in CLARE is largely handled by IDRC’s Grant Administration Division and by the IDRC CLARE team. The quality and assuredness of financial management is assessed as being very good with excellent attention to detail and a significant capability to engage in depth with individual consortia partners when necessary. The financial reports that FCDO receives from IDRC are transparent and easily read and understood. FCDO and IDRC have regular discussions on forecasting and spending. Any changes in forecasts and spend totals are discussed months in advance which gives FCDO enough time to make any adjustments if necessary. IDRC has made important progress in profiling FCDO’s role in the programme in comms material and external communications, as well as involving FCDO representatives in key meetings with partners. This has resulted in FCDO’s role, both its strategic footprint and as the main donor, being increasingly recognised externally, thus better portraying the partnership.
For the FCDO managed projects, financial management by the partners (list below) is assessed as good or very good. As previously noted, implementation partners have strong track records and working relationships with Research and Evidence Division.
The below table provides a brief summary of partners performances:
Project	Partner(s)	Assessment
Adaptation Research Alliance	SouthSouthNorth	Very Good – good quarterly financial and narrative reports produced. Team is responsive, have initiated steps to increase donor funding base, recruitment is ongoing, and underspend being monitored and actions taken.
Met Office Partnership (Outlooks, Risk Reports, International Natural Hazard Forward Look, Secondments)	UK Met Office	Good- invoices received regularly and costs pricing and forecasts are being produced on time.
Climate Change Local Adaptation Pathways programme (CLAPs)	University of Exeter	Good – good quarterly financial and narrative reports produced on time. The team are responsive and initiating steps to increase donor funding base for the future.
Sustainable Transition Exploration in Water and Agricultural programme (STEWARD)	University College London	Good – good quarterly financial and narrative reports produced though engagement could be improved.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation
CLARE has continued to leverage the online M&E system, which works well for roll-up of output-level indicators but does require a time investment of research teams for data entry, and has proven more challenging for outcomes. Outcome cases will evolve over time and likely require ongoing conversation with Programme Officers to understand progress and influence, whereas system limitations mean entries cannot be updated on an ongoing basis. The CLARE team will explore how to better integrate the online system with technical reporting to ensure that POs have a view of all results, and how they are being reported against CLARE log frame. As in previous years, some indicators (e.g. # publications, # partnerships, research quality assessments) are collected internally through existing systems without additional data entry requirements for project teams. IDRC programme staff also conduct regular monitoring check-ins with project grantees, with technical and financial reports to be submitted at established intervals depending on the timeframe of projects as well as the risk rating of each of the lead institutions.
This year the programme also commissioned a phased evaluation of the CLARE program, focusing mainly on its research pillar. The intended uses of the evaluation will be to understand the strengths and weaknesses of the program’s approaches to inform adaptative programme management, assess the (expected and unexpected) results, outcomes and positioning for impact of the programme alongside it’s theory of change, and to support identification and refinement of future programming approaches and/or areas of investment that could build on, strengthen, or complement the current CLARE portfolio and its results The first phase of the evaluation (which commenced in January 2025) is wrapping up, with some of the findings informing this annual review. Additional evaluation questions are being drawn, also from the finding of this review, and will be addressed in mid-2026 and end 2026, coinciding with the next Annual Review and the end of the current phase of CLARE.
Evidence
Given the increasing maturity of the CLARE Research portfolio, this was the first year that CLARE reported on all outputs and outcomes in the programme log frame. While the programme did not set a milestone for the indicator on number of beneficiaries, projects have reported data, which is being reviewed for submission to ICF ahead of their annual reporting deadline (while recognizing that as per project estimates, larger numbers are expected to materialize later in the program).
Reporting on the capacity strengthening outcome indicator, as well as some of the outcome cases, were informed by the first phase of the CLARE programme evaluation, which included a survey on capacity strengthening issued to all those directly involved in CLARE, and an outcome harvest for four sampled projects. The evaluation also includes findings related to relevance and fit-for-purpose of the programme. Based on emerging findings, recommendations are in the process of being co-created with evaluation users with the aim of informing how CLARE proceeds to 2027 and any potential future programming.
Learning
The CLARE working groups have matured and continued to play a key role in supporting program-level learning on common approaches that underpin CLARE’s Theory of Change. The R4I Hub has continued to implement their learning agenda, and the CS Hub is putting forward a learning agenda on capacity strengthening. The GEI working group continues to support learning on how to address GEI. On M&E in particular, the M&E working group continues to be a key forum for understanding and contributing to CLARE M&E requirements and supporting use of M&E data. The group, along with CLARE programme POs, will need to continue to enhance a focus on monitoring and sharing outcomes of project work in the final years of the programme. Select volunteers from this working group have also engaged in the CLARE programme evaluation process as secondary intended users.
CLARExchange activities continued to support and socialize program-level and cross-project learning, notably including the first program-wide in-person event at CLARExchange 2025 in Lusaka to catalyse and identify areas of potentially influential possible cross-project collaboration and interest. This included the first in-person discussions of the three CLARE “Threads”, space for projects to lead conversations on areas they wish to explore in collaboration with other projects, and discussions about transformational change and what this means for CLARE. Proposals for CLARExchange activities in 2026 are currently in discussion based on lessons from 2025 events and input from key stakeholders.

Partner Names	Date of last narrative financial report	Date of last audited annual statement
IDRC	17 June 2025	09 July 2024
SouthSouthNorth	01 Jul 2025	01 September 2025
Exeter University	09 Apr 2025	31 July 2024
University College London	17 Feb 2025	31 Jul 2024
Met Office Outlooks	05 Aug 2025	17 Jul 2025
Met Office Secondees and placements	05 Aug 2025	17 Jul 2025