## Annual Review Template

Title: ASEAN CATALYTIC GREEN FINANCE FACILITY (ACGF)
Programme Value £ (full life): £110 mn		Review date: 26 April 2025
Programme Code: [AMP ID#] / 300128	AMP start date: 26 April 2022	AMP end date: 31 March 2029

Summary of Programme Performance
Year	2023	2024	2025	2026
Overall Output Score	A	A+	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0000978.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004339.xlsx

## A. SUMMARY AND OVERVIEW

Description of programme

The ASEAN Catalytic Green Finance Facility (ACGF) is a partnership platform set up by ADB, as a ‘green window’ under the ASEAN Infrastructure Fund, to develop and finance green infrastructure projects in ODA-eligible countries in the ASEAN region. The UK’s contribution to ACGF, through this programme, aims to catalyse growth and investment in infrastructure in Southeast Asia that is greener than it would otherwise be – helping to reduce emissions, build resilience to climate change and protect biodiversity – while also reducing poverty. The UK will achieve this by deploying concessional finance and technical assistance – through the ACGF UK Trust Fund established within Asian Development Bank (ADB) – to incentivise greater public and private infrastructure investment to reduce emissions, increase resilience and boost growth.

This is a regionally managed Growth and Investment Partnership programme. It forms part of the UK’s strengthened and joined-up investment and economic development offer, through which Growth and Investment Partnerships seek a step change in clean and reliable infrastructure services – to support clean, inclusive and resilient growth. Consistent with the UK’s Indo-Pacific Strategy it is leading to more international investment in infrastructure and economic development characterised by high standards, transparency and reliability. The programme carries out activities in the “Bronze markets” of Thailand, Philippines, Vietnam, Indonesia and is forging partnerships with the important “Silver Markets” of Singapore and Korea.

ACGF’s technical assistance supports governments to identify and prepare both sovereign and commercially viable green infrastructure projects while the ACGF loans are utilised to cover upfront capital investment costs. This two-pronged approach ‘de-risks’ green infrastructure projects, making them more attractive to private capital investors. The programme contributes to UK COP26 commitments, the UK’s ICF targets and delivers against UK growth mission. The programme is delivering against ICF outcomes 1 & 12.

The ACGF is managed by the ADB and comprises multiple trust funds and parallel co-financing agreements with partners. The UK is one of eight partners in the ACGF, through the ACGF UK Trust Fund.

Summary supporting narrative for the overall score in this review

The ACGF remains a visible and major flagship programme in the Southeast Asia region, providing good visibility for the UK. Our partnership through this programme forms part of the UK Plan of Action with ASEAN and helps the region achieve its climate and economic goals.
The UK’s participation, alongside other donors, is helping to transform the financial architecture for green infrastructure finance in the region. Consistent with the UK’s Growth Mission, the programme is unlocking opportunities for the UK to move into finance and infrastructure markets in ASEAN, particularly around project consultancy where the UK has expertise.
Over the year, strong backward linkages to the UK were created. FCDO helped organize and participated in a side event at the ASEAN Energy Ministerial on the ASEAN Power Grid jointly with British High Commission (BHC) Singapore. The UK-led Green Grids Initiative have set out the UK offer to ASEAN including UK regulatory and financing expertise. The British High Commissioner to Singapore provided opening remarks to a clinic on greening data centres. The programme is a good example of how bilateral aid through a multilateral organisation can provide UK visibility.
The Green, Social, Sustainable Bonds programme (GSS+) is deepening capital markets in South-East Asia and provides opportunities for UK financing. UK support in greening the region’s capital markets is a highlight. The initiative assists governments, cities, and state-owned enterprises to develop and launch signature thematic bond issuances with a high demonstration effect. The initiative – co-funded by the ACGF UK Trust Fund and the Green Climate Fund – is highly catalytic, with c.$250k of UK funds supporting close to $1bn of issuances: During the year, three bond issuances with shared UK support were completed.
In late 2024, a second GSS+ study tour brought Southeast Asian officials to London for specialized training conducted by UK-based Climate Bonds Initiative. A dialogue was held with UK based organisations, including the UK’s Debt Management Office, Transport for London, London School of Economics, Climate Bonds Initiative, and London based investors.
In March 2025, the ASEAN Infrastructure Fund (AIF) Board of Directors endorsed the 2025-2028 Action Plan to transform the AIF into a larger and more regionally focused fund. This plan aims to significantly enhance AIF’s financial capacity and impact in the coming years by increasing its lending capacity, attracting additional capital, and enhancing its value to borrowers through improved price competitiveness and more product offerings.
ACGF has achieved an overall score of ‘A’ in this Annual Review – meaning that the programme’s ‘Outputs have met expectations’. The programme has made good progress in all outputs – two projects with expected UK cofinancing have progressed and are waiting for ADB Board approval this year. These are the:
1. Energy Transition Sector Development Program Subprogram 2 in Cambodia, with $12 million proposed cofinancing.
2. Baguio Resilient City Tourism Project in the Philippines, with $10 million proposed cofinancing.
All approved capital projects were screened against the UK criteria for use of concessional finance. UK Missions were involved in the approval process in all cases and are engaged locally on project development. FCDO Indonesia participated virtually in the ground-breaking ceremony for the North Java flood and coastal protection project.
Technical Assistance funds were allocated to activities including sector-specific initiatives, such as ASEAN Power Grid (APG), as well as cross-cutting support to the ASEAN Taxonomy for Sustainable Finance and Thailand’s national taxonomy (developing taxonomy components for waste management), which provide a common language and an overarching regulatory framework for sustainable finance, guiding both regulators and project developers. UK-ACGF TA supported an innovative finance clinic on Green Data Centres, which resulted in the development of 7 project ideas. The UK-ACGF also provided seed funding for the Nature Solutions Finance Hub, enabling ADB to launch a new channel of support for financing nature-based solutions.

In 2024, an international gender consultant was engaged to review the ACGF Gender Equality and Social Inclusion Action Plan (GESIAP), developed in 2021, to ensure that it incorporates ACGF requirements as well as those of ACGF partners. ADB’s gender mainstreaming policy, including categorization of projects, and corporate results framework are being updated and were made effective in early 2025. The ACGF GESIAP review is also ensuring alignment with the revised ADB gender categorization to ensure data compatibility and efficiency. The review will be finalized during the first quarter of the next financial year.

Major lessons and recommendations for the year ahead

There are two major lessons from the past year. The first is that the programme demonstrates an effective model for how UK’s support can be catalytic in mobilizing and deploying financing for innovative projects, by working in close partnership with delivery partners. Through the ACGF UK Trust Fund, the UK has committed GBP 107m of funding within a partnership platform that has attracted $2bn in pledges from the eight ACGF partners (three trust fund donors – of which the UK is one – and five mostly European Development Finance Institutions) and ADB. As the largest provider of the most concessional finance (zero interest loans) within the ACGF platform, the support from the UK is catalytic by effectively incentivising project designs with high ambitions on climate, resilience and innovation. Under the MoU signed with the ADB for the programme, the UK’s investment funds are to be deployed as concessional investment loans alongside – or ‘blended with’ – financing by ADB (as well as other Development Finance Institutions and at times also with AIF funds).

Thus far the UK has provided its approval (“no-objection”) for cofinancing of four projects – of which one has subsequently been approved by the ADB board, and the others are pending board approval. These are all first-of-a-kind projects with scope for influencing future pipeline of ADB’s lending in Southeast Asia (see narrative under Output 1).

The second lesson is that the decision to second a senior FCDO adviser into the team, with a mandate to work within the Green Finance Hub on strategic priorities, has generated additional UK partnership opportunities in areas of high ministerial priority. The role of the UK secondee is to support delivery of core ACGF activities as well as strategic initiatives. The lesson is that embedding this person within the team and being mostly ‘ADB-facing’ (so they are a key part of the team) while also carving out time to pursue linkage with the UK, has been effective.

During the reporting year, the UK secondee spearheaded, in partnership with the ADB Energy Sector Group, the development of a new initiative of support for the ASEAN Power Grid – including leading meetings with ASEAN Secretariat and the ASEAN Centre for Energy. By working closely with UK experts (FCDO, DESNZ, National Grid), the secondee was able to identify areas of common interest and create platforms to present the UK offer on energy transition. The secondee remains closely involved in this initiative, which has led to an emerging partnership between ADB and the UK-led Green Grids Initiative.

Recommendations Annual Review 2025	Summary
FCDO team to review the output and outcome targets that have already been met with a view to increasing ambition in collaboration with the ADB. September 2025.	Given rapid progress and evolving thinking of how the ACGF programme does capacity building (e.g. towards more frequent, but smaller and more tailored engagements), end-of programme outputs targets for Output 3 are already met. The programme team and ADB should therefore review these targets as part of the annual logframe review. / As part of the upcoming Mid-Term Review, the programme team should review the programme outcomes indicators, including the end-of-programme targets and approaches to attribution. This review should develop an end-of-programme target for Outcome indicator 2.
Further explore synergies across UK-supported trust funds, to maximize value for money for UK delivery through ADB.	FCDO intends to place an additional secondee to the ADB to enable the delivery of UK climate trust funds. This will increase the opportunities for coordination across the portfolio.
Broaden the engagement between ADB and the UK on the ASEAN Power Grid, including by leveraging the ACGF platform to mobilize technical assistance and project readiness support for APG projects.	UK Mission to ASEAN and Indo-Pacific Regional Department will continue to coordinate UK offer on APG.
Consider bringing forward the Mid-Term Review scheduled for 2026 to consider options for reconfiguring the UK-ACGF Trust Fund to align with UK fiscal conditions.	An amendment to the trust fund arrangements may be required to ensure the programme meets future UK priorities and remains within ODA availability.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The theory of change for the programme remains valid.[1] The intended impact is resilient low-carbon growth and development pathways in ASEAN. The ACGF UK programme outcomes include: (1) Projected GHG emissions reductions because of green infrastructure projects, (2) Projected increased resilience of populations through investment in green infrastructure, and (3) Additional finance mobilized.
[1] The theory of change was amended in line with the recommendations from the Annual Review in 2023 – aligning the three outputs with the programme log frame. There have been no material changes to the theory of change since the business case.

These outcomes will be achieved through three outputs: 1) the UK providing loans for de-risking infrastructure projects; 2) development of replicable and innovative green finance models and structures; and 3) building policy, knowledge and capacity on green finance. The bulk of the UK funding goes to de-risking loans for infrastructure investment. However, the other two output pathways are important means to achieve the project outcomes and impacts. The technical assistance is focused on trialing new ways to finance infrastructure projects with a view to being replicated more widely. The wider policy work – for example national strategies and green taxonomies – can change policy for a whole nation with large associated benefits.

The UK secondee, embedded in the ADB team managing the ACGF, supports this work by ensuring close alignment, on a week-by-week basis to identify opportunities for joint activities and partnerships as they emerge. The programme team’s experience is that this has been helpful in driving efficiency and hence value for money.

To date, the UK has provided its approval (i.e. ‘no-objection’) to allow concessional lending to 4 green infrastructure projects in ASEAN countries, to help address the viability gap that prevents investment in new, clean infrastructure projects. Two of these four were confirmed for funding in 2024, through no-objection provided by the UK for ACGF UK Trust Fund cofinancing. The date of ADB Board consideration is pending for both projects.

In addition, the UK funded a readiness assessment tool for ASEAN Power Grid interconnection projects, an innovative finance clinic on Green Data Centres and a Green Buildings Market Study in Thailand, seed funding for the Nature Solutions Finance Hub[2] and support to the ASEAN Green, Social, Sustainable, and Other Labelled (GSS+) Bonds Initiative.[3]
[2] Nature Solutions Finance Hub for Climate and the Environment, available here. News release available here.
[3] The Green, Social, Sustainable and Other Labeled (GSS+) Bonds Initiative for Southeast Asia, available here.

Across all these areas, there are many touch points between the work led by ADB, and the UK’s bilateral programming and ministerial priorities. The team in ADB managing the ACGF UK Trust Fund places a strong emphasis on UK content and visibility across its activities – but also look beyond this and aim to establish concrete partnerships that can allow the UK’s work (directly or through multilaterals) to be more catalytic and impactful.

In December 2023, the UK agreed to contribute $10m from the ACGF towards a $250m ADB loan to deliver a Flood Management and Coastal Protection project in North Java, Indonesia.[4] Since the last Annual Review, this project is now in implementation and will reduce flood risk in the northern coastal area of Java Island and strengthen the local community socio-economic resilience, thereby contributing towards against outcomes 2 and 3 of the programme. $3.7m of UK’s contribution to this project has been disbursed.
[4] Indonesia: Flood Management in North Java Project, available here. News release available here.

Although the ACGF UK programme is not designed to be an adaptive programme, adjustments will continue to be made when needed, in response to the needs of government stakeholders who are borrowing from ADB to undertake green infrastructure projects.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme has made progress in delivering towards expected outcomes and impacts. In the two years of implementation, four projects were approved by FCDO (in consultation with posts) for funding, i.e. FCDO providing ‘no-objection’ for co-financing (see Output 1),[5] and seven project concepts were developed with UK TA (see Output 2). The four no-objected projects account for $42m (or ~30% of the ACGF UK Trust Fund investment envelope).
[5] The ACGF UK Trust Fund was established and became operational in March 2023.

FCDO approves the use of its capital to blend with other sources of finance on a project-by-project basis and has the right to object if the project does not meet the UK criteria for approval. At the time of writing, one project where FCDO provided no-objection has been approved by the ADB board and progressed to implementation. Three other projects approved by FCDO (i.e. where FCDO provided no-objection) are pending ADB Board approval (two of which have expected board approval in 2025).

Further details of projects not yet ADB Board approved have been shared with FCDO as part of the no objection process but will not be published until ADB Board has approved. Table 1 sets out the expected contributions of the approved project to the outcomes, and Table 2 compares final programme targets with progress to date (considering Board-approved as well as the no-objected projects in the pipeline). Without final ADB Board approval we do not have certainty the projects will move to implementation and so the projected results against the indicators remain indicative. Overall, the four projects provide:

- For outcome indicator 1, the ADB Board-approved North Java Flood Management project was exempted from the GHG emissions reduction criteria. Approval of the Cambodia project (expected in 2025) would imply c.20% progress towards achieving the outcome. The tables show how the KPI as designed (where the entire CO2e reduction of the project is counted) is highly sensitive to large-scale energy transition projects, e.g. the ADB board approval of AICET[6] would mean that overall target for this indicator will have been met.
  [6] Indonesia: Accelerating Indonesia’s Clean Energy Transition Program (Phase 1), available here.
- For outcome indicator 2, the ADB board-approved North Java Flood Management project is expected to benefit 485,000 indirect beneficiaries (no direct beneficiaries considered given nature of the project). The programme does not have an end-of-program target for this indicator.
- For outcome indicator 3, the one ADB Board-approved project does not contribute to this indicator. If the three projects that have had FCDO ‘no objection’, but are not yet ADB Board-approved, were to go ahead, the first $42m from the ACGF UK Trust Fund would be associated with more than $1 billion in potential private or commercial financing.[7] However, these results are highly sensitive to a single, large project (Indonesia AICET).
  [7] Numbers based on modelling by the ADB project teams.

Table 1: Contributions to Outcome indicators of Board-approved projects
	Outcome indicator 1 - Climate mitigation (GHG emission reductions	Outcome indicator 2 – Climate resilience (beneficiaries with reduced vulnerability)	Outcome indicator 3 - Private finance mobilisation (potential mobilization of private, institutional and commercial finance)
Approved for financing by ADB (UK funds committed)
Indonesia Flood Management in North Java Project	Nil	485,000 (indirect beneficiaries)	N/A. Project is non-revenue generating and was approved according to the exceptions of the ACGF criteria for projects in rural areas.[8]
[8] The ACGF criteria allow for an exemption from this criterion for projects in rural areas, where bankability and commercial returns are insufficient to attract external capital, but are still deemed a priority by government.

Table 2: Progress towards Outcome targets for Board-approved as well as other no-objected projects
	Final program target	Progress towards target - Board approved projects	Progress towards target - all no-objected projects
Outcome indicator 1	500,000 tCO2e/year	Nil	31,152 tCO2e/year
Outcome indicator 2	No target set	485,000 (indirect beneficiaries)	226,000 direct beneficiaries and 485,000 indirect beneficiaries
Outcome indicator 3	1:1 (i.e. GBP 100m of private finance associated with our £100 million of co-finance)	Nil	1:0.95 (up to $40.2 m potential PIC mobilized, against $42m allocated through no-objection from the ACGF UK TF)

Considering all four projects that have been approved by FCDO through ‘no objection’, the programme is making progress towards all three outcome level targets. Considering only the one ADB board-approved project, progress is being made only on outcome indicator 2 (as outcome indicators 1 and 3 do not apply to this project).

Beyond the projects supported by the programme, the theory of change expresses how the programme will contribute to the outcomes and overall impact of a ‘resilient and low-carbon development pathway for ASEAN’. This includes through the technical assistance and partnership brokering enabled by the GBP 7 million Technical Assistance facility and the secondee embedded in the Southeast Asia Green Finance Hub (or SGFH -- the ADB team managing the ACGF).

The co-location within the SGFH of the ACGF team, as well as a network of 10+ climate advisers (outposted to countries in Southeast Asia), has provided direct opportunities for the UK programme to influence the dialogue and upstream country partnership and programming. For example, working closely with ADB Country Directors and Sector Group project teams, these country climate advisers reviewed the 2025-2027 pipeline projects to identified ways in which climate resilience and low-carbon development could be enhanced in each project. This exercise has facilitated connections between Sector Group teams and ACGF project and fund management teams, to seed discussions on potential ACGF technical assistance and co-financing.

With the ACGF UK Trust Fund becoming established and known within ADB and with government and private sector stakeholders, the pipeline of possible co-financing projects for the ACGF UK Trust Fund for the coming years of the programme is strong.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Evidence of progress to date, and a review of the theory of change, suggests the programme should continue. Since establishment in 2023, the ACGF UK Trust Fund has demonstrated its ability to originate innovative and high-impact projects, to influence the ADB, and to deliver secondary benefits and visibility for the UK. The programme makes an important contribution to the Indo-Pacific Business Plan, and the UK-ASEAN Plan of Action in which it is a referenced deliverable.

The programme has originated projects that are innovative and where UK funds can be catalytic in delivering the desired outcomes and impact. For example, the Indonesia AICET is the first results-based lending initiative under the JETP, taking a performance-based approach to incentivise the utility PLN to shift from coal to renewables. The Cambodia ETSDP SP2 is the country’s first policy-based loan to integrate private sector financing for energy efficiency, integrating policy support with private-sector led lending to SMEs for energy efficiency investments. As part of the no-objection process, ADB (supported by the secondee) organized briefing meetings with the High Commission/Embassy in each country where projects have been proposed, to ensure alignment of the project with regional UK strategic priorities.

The programme also develops technical and financing partnerships between ADB, the UK and others around the challenge of decarbonization, resilience and finance mobilization in SEA. One example is the role of the ACGF UK Trust Fund in supporting delivery of the UK’s bilateral ASEAN programs, e.g. by enabling British Embassy Jakarta to co-finance the Indonesia JETP project (AICET). Another example is the partnerships on green bonds between central banks and security commissions in ASEAN and UK financial sector including the Climate Bonds Initiative. Catalytic TA from the UK has led to landmark green and sustainability bond transactions, including the first ever local currency blue bond in Thailand, and Asia’s first sovereign sustainability-linked bond (together raising ~$1 billion).

One example with strong potential to support the UK growth agenda is the ASEAN Power Grid, where UK support through the ACGF includes technical assistance toward designing APG financing framework, and capacity building for utilities. UK support includes developing processes to identify and finance preparation studies needed to progress projects through to financing, which will create opportunities for UK expertise.[9] There are linkages with the project-level work, e.g. the AICET program in Indonesia would directly contribute to the APG by strengthening the domestic Indonesian grid (which is part of ASEAN’s vision of the APG).
[9] UK firms well-placed to benefit, by virtue of their existing experience on transmission infrastructure in Southeast Asia, include Arup, Mott MacDonald, Atkins, WSP Global, Buro Happold and Jacobs Engineering.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Provision of loans for de-risking green infrastructure projects
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.a UK financing approved for projects with potential green impacts (target: GBP 100 million) / This monitors the strengthening of the pipeline and tracks how much money is being committed by the UK towards infrastructure projects.	£20m / (cumulative)	Met. UK financing approved for projects with a cumulative value of $42m / ADB board-approved projects: / Indonesia: Flood Management in North Java Project. No-objection in 2023, board approved in 2024. $10 million. / No-objection projects: / Indonesia: Accelerating Indonesia’s Clean Energy Transition (AICET) Program, Phase 1. No-objection in 2023, expected approval 2025. $10 million. / Cambodia: Energy Transition Sector Development Program (ETSDP), Subprogram 2. No-objection in 2024, expected approval 2025. $12 million. / Philippines: Baguio Resilient City Tourism Project. No-objection in 2024, expected approval 2026. $10 million.
1.b Share of UK financing to projects classified as ‘priority green[10]’	45% / (average to date)	Met. / 52% of total UK funds committed or allocated to projects have been classified as priority green: $10 million committed to the Indonesia: Flood Management in North Java Project, and $12 million allocated to Cambodia: ETSDP, Subprogram 2 (two of four projects).
1.c Share of UK-supported projects approved that directly advance gender equality and social inclusion (target: 80%)	80% / (average to date)	Exceeded. / 100% i.e. all four projects on no-objection basis to date are classified as Effective Gender Mainstreaming, ADBs second highest classification, and meet the gender equality and social inclusion targets
1.d Total leverage ratio – including sovereign lending by ADB/others and PIC (final target: 1:6)	1:6 / (average to date)	Exceeded. / Approved project ratio: 1:25 / Pipeline (no-objected) projects ratio: 1:73
[10] Priority green projects are those that (a) meet the minimum threshold of 60% climate finance, (b) achieve global best practice performance thresholds and (c) have an additional environmental co-benefit. As opposed to “green” projects which are classified as having 60% climate finance only.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme met expectations on Output 1. By end-March 2025, $42m of co-financing had been allocated through the UK no-objection process to four projects. The additionality of FCDO’s money has been assessed in all cases.

In the case of Philippines tourism water and sanitation project, the project would not be financially viable without the additional concessionality provided by the UK, which would finance a lowering of the average cost of capital for civil works in the first years. The financial revenue from service charges is insufficient to cover the cost of the investment in the initial phases of the programme, despite the programme having significant economic and social benefits to justify the subsidy.

For Cambodia energy efficiency, the UK is providing seed capital for SME loans which is only available from bilateral donors.

In the case of Indonesia, as the UK provides a small contribution to a larger loan, our financial additionality is targeted on a specific performance indicator relating to the pace of renewable investment and our concessional finance reduces the relative costs of renewable investment. As a JETP partner to Indonesia the UK has a strong interest in financially supporting this major results-based loan.

Aside from the board-approved Indonesia Flood Management project, the no-objected projects are:

1. Indonesia: Accelerating Indonesia’s Clean Energy Transition (AICET) Program, Phase 1. $10 million. Target ADB approval 2025.
2. Philippines: Baguio Resilient City Tourism Project. Potential approval 2026. $10 million. Potential ADB approval in 2026.
3. Cambodia: Energy Transition Sector Development Program (ETSDP), Subprogram 2. Expected approval 2025. $12 million. Target ADB approval 2025.
All projects were fully assessed against ACGF criteria for deploying FCDO co-finance. The team engaged with the respective Embassies to present the projects to ensure alignment with UK priorities.

The Accelerating Indonesia’s Clean Energy Transition Program – Phase 1 is the first results-based lending (RBL) initiative under JETP, linking funding to measurable clean energy outcomes. It is the first JETP project to blend financing from multiple partners including ADB, and the UK-FCDO Trust Fund. This performance-based approach directly incentivizes PLN to shift from coal to renewables, setting a precedent for future JETP phases.[11]
[11] More details can be found here.

The Baguio Resilient City Tourism Project is the first ADB-supported initiative integrating climate-resilient sanitation with tourism sector development in the Philippines. The project will increase wastewater treatment capacity, addressing a critical gap. It also introduces a climate-resilient regional sanitation plan, improved flood protection for treatment plants, and a private sector-led skills training network to strengthen MSMEs. This holistic approach ensures environmental sustainability while enhancing Baguio’s tourism resilience.[12]
[12] More details can be found here.

The Energy Transition Sector Development Program (ETSDP) Subprogram 2 is Cambodia’s first policy-based lending program for clean energy that integrates private-sector financing for energy efficiency. It will establish an Energy Efficiency Revolving Fund (EERF) to provide concessional loans to SMEs, addressing the key barrier of limited access to finance for energy efficiency investments. The program also strengthens regulations for energy efficiency, including building codes and minimum energy performance standards.[13]
[13] More details can be found here.

The program is on track to meet end-of-programme targets.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The project is delivering against the results framework as negotiated and agreed with the ADB. There were no changes to this output during the year, and no changes are planned because of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations specific to Output 1 in the previous annual review.

During the year, the programme experienced delays on some projects progressing towards ADB board approval, due to delays with borrowing governments’ approval processes. In response, FCDO initiated a discussion with ADB about how to improve the flexibility of the programme. The result was the adoption of promissory notes as a mechanism for FCDO to deploy CDEL in a way that would capitalize the ACGF UK Trust Funds. The use of promissory notes will enable ADB to have more certainty with respect to funding availability. The ADB report that this has been helpful in building pipeline, by making the ACGF UK Trust Fund offer more certain and hence attractive to partner governments.

Output Title	Development of replicable and innovative green finance models and structures
Output number:		2	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.a Early-stage projects identified and documented in concept notes (target: 12 projects)	6 / (cumulative)	Met. / Seven early-stage projects were identified and documented in concept notes (see below).
2.b Finance ready late-stage projects identified and included in ACGF pipeline (target: 5 projects)	2 / (cumulative)	Met. / Two finance-ready late-stage projects were identified and included in ACGF pipeline (see below).
2.c. Green and sustainability bonds issued with UK support (target: 2 bonds)	0 / (cumulative)	Exceeded. / Three green and sustainability bonds were issued with UK support (see below).

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme met expectations on Output 2, with notable progress on identifying early-stage projects, supporting GSS+ bonds issuances and providing capacity building for Southeast Asian government officials. Under Output 2.a, seven early-stage concepts were developed:

1. Responsible forestry project in Lao PDR.
2. e-mobility initiative in Thailand.
3. e-mobility initiative in Viet Nam.
4. Blue economy project in Indonesia.
5. Blue economy project in the Philippines.
6. ASEAN Power Grid Financing Facility. Support with conceptual design, program management, and project pipeline tool.
7. Support to the Nature Solutions Finance Hub (NSFH), for preparation of an initial business plan, to identify the first pilot projects and evaluate these for potential support.
Under Output 2.b, two finance-ready late-stage project designs were developed with support from ACGF UK Trust Fund TA:

1. Lao PDR: Sustainable Agrifood Systems Project.[14] UK-funded TA supported late-stage structuring of the project, in preparation for presentation to the ADB Board for expected approval in 2025. The project will improve access to financial services for farmers and enterprises through participating financial institutions (PFIs) and development of small-scale climate resilient value chain infrastructure. This project will be cofinanced by the UK-funded Communities Resilience Partnership Programme (CRPP) trust fund.
  [14] Lao People's Democratic Republic Sustainable Agrifood Systems Sector Project, available here.
2. Indonesia: Flood Management in North Java Project. The project is cofinanced by the UK. In addition, TA was provided for the implementation of the nature-based infrastructure component.

On Output 2.c, the programme exceeded expectations. The Green, Social, Sustainable Bonds programme (GSS+) originated opportunities to mobilize green financing for landmark bond issuances in South-East Asia. The initiative – co-funded by the ACGF UK Trust Fund and the Green Climate Fund – is highly catalytic, with c.$250k of UK funds supporting close to $1bn of issuances: During the year, three bond issuances with UK financial support were completed:

1. Export-Import Bank of Thailand issued the first THB-denominated blue bond in Thailand, raising $87.5 million. The bond proceeds will support healthy oceans and blue economy projects in the priority sectors such as hotels and marine tourism, fishing and aquaculture, and waste management.
2. Public Debt Management Office (PDMO) of Thailand issued Asia's first sovereign sustainability-linked bond, raising $880 million. The PDMO intends to use the funds for support for e-mobility to reduce GHG emissions. Bond investors have agreed KPIs relating to reduction of GHG emissions and increased numbers of zero-emission vehicles (when KPI targets are met, this will lead to a coupon reduction).
3. Provincial Electricity Authority of Thailand issued a sustainability bond, raising $28.6 million. The borrower plans to use the funds for submarine cable extensions to support energy resilience on remote islands with the objective of increasing capacity and security for island systems.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The project is delivering against the results framework as negotiated and agreed with the ADB. There were no changes to this output during the year, and no changes are planned because of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

There were no recommendations specific to Output 2 in the previous annual review.

One lesson learned during the year is that deepening the engagement between the ACGF UK trust fund and other UK-supported ADB trust funds is effective at creating new opportunities for collaboration, thereby maximising value for money of UK investments. During 2024, the ACGF partnerships manager formalized a process for convening the teams managing the different UK-supported trust funds within ADB. This work has identified new collaboration opportunities that are currently being explored, for example:

- Co-financing of CRPP of the Lao PDR project (Sustainable Agrifood Systems Project) designed with ACGF UK Trust Fund support.
- Proposed co-financing of Urban Resilience Trust Fund (URTF) with ACGF trust fund partner Green Climate Fund on a project on green and resilient affordable housing in Indonesia (in design).

Another lesson is that the ACGF can be an effective platform for mobilizing joint UK-ADB engagements for influencing ASEAN stakeholders. For example, at the ASEAN Energy Ministerial in September 2024, ADB (through the UK secondee) organized a side-event on the ASEAN Power Grid jointly with BHC Singapore and the UK-led Green Grids Initiative, setting out the UK offer to ASEAN including UK regulatory and financing expertise.

Recommendations for next year:

- Further explore synergies across UK-supported trust funds, to maximize value for money for UK delivery through ADB.
- Broaden the engagement between ADB and the UK on the ASEAN Power Grid, including by leveraging the ACGF platform to mobilize technical assistance and project readiness support for APG projects.

Output Title	Building policy, knowledge and capacity on green finance
Output number:		3	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.a National policies, strategies and / or plans on green financing and green recovery developed (final target: 2 strategies)	1 / (cumulative)	Met. / Two national policies, strategies and/or plans on green financing were being developed during the reporting period.
3.b International investor roundtables held (final target: 2 roundtables)	1 / (cumulative)	Exceeded. / Two investor round tables have been held since the start of the programme.
3.c. ASEAN officials and finance stakeholders (men and women) trained in innovative finance through 6 Champions program (final target: 40 officials/stakeholders)	20 / (cumulative)	Exceeded. / 89 (65 men and 24 women) ASEAN officials and finance stakeholders have been trained.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme met expectations on this output. For Output 3.a, two national policies/strategies/plans have been developed:

- Thailand Taxonomy – Waste Management: In July 2024, consultants presented a first draft of the Thailand Taxonomy for Waste Management. Followed by a series of focus group and targeted stakeholder meetings, the draft was published for public consultation in October 2024. The final version is expected to be completed by July 2025.
- ASEAN Taxonomy for Sustainable Finance: In December 2024, a consultant was engaged to support preparation of Version 4 of the taxonomy, to be developed over the course of 2025.

For Output 3.b, two investor round tables have now been held. The first one was organized as part of the November 2023 London Municipal Bonds Study Tour to attend the Climate Bonds Initiative conference and meet stakeholders from City of London. A second investor roundtable in London was held in October 2024 with representatives from development partners, the private sector, and the UK government. The roundtable discussion focused on transition finance and taxonomy, highlighting the importance of both localized versions and interoperability. This event has generated concrete project opportunities to support bond issuances, including the first sub-sovereign bond Indonesia, and sovereign sustainable bond in Cambodia.

For Output 3.c, two events contributed to these results during the reporting period:

- Study Tour to London as part of the GSS+ Bonds Initiative for 12 government officials (9 men, 3 women) from 5 ASEAN countries. Meetings focused on municipal bond solutions for climate resilient cities in Southeast Asia, and on how municipal bond markets can mobilize green capital more rapidly and at scale.
- ACGF Innovative Finance Clinic: Green Data Centres, with 18 government officials (15 men, 3 women), resulting in 7 project ideas being explored. Given that all end-of-programme targets have been set for this output, the programme team should consider how the programme can establish meaningful targets to incentivise performance.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no changes to the output during the year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Three recommendations pertinent to this output were set out in the last annual review:
Recommendation from previous annual review	Status
Output indicator 3c has exceeded the programme target. Over the course of the year, we should establish a new higher target with the ACGF team.	Discussions ongoing. All end-of-programme targets have now been met for this Output. While no support to additional policies or strategies is foreseen, the programme team and the ADB team should discuss how to address this issue, e.g. consider a review of targets for 3b and 3c as part of the annual logframe review.
Develop qualitative indicator milestones for a new indicator (3d) to enable a more robust assessment of the level of awareness and engagement with the programme within the FCDO network.	Met. Following discussions between the programme team and ADB, it was agreed that rather than adding an additional indicator, that ADB would report on key engagements as part of the annual progress report which is now happening.
Over the next year finalise the UK-ACGF Trust Fund communications strategy to ensure knowledge generated by this programme is disseminated through the external and internal FCDO channels.	Met. During the year the ADB team developed a process for sharing information on upcoming events, allowing FCDO to provide early identification of UK priority engagements. FCDO will ask for the Trust fund manager to take the lead on developing the Comms strategy.

The experience of organizing the second bonds study tour during the reporting period shows that lessons from the first such event have been internalized. Issues around planning and logistics (e.g. securing visas for delegates to travel to the UK) were addressed and led to a more effective and smooth execution of the second bonds study tour to the UK in 2024. The repeat engagement of the same institutions/stakeholders is also proving to be an effective way in generating opportunities for collaboration (as evidenced by project opportunities generated from the second study tour).

By the end of the reporting period, final targets for all three indicators under the output have been met or exceeded, mainly due to support to a somewhat broader scope of activities than initially foreseen, especially for 3.b and 3.c. Initially the investor roundtables were foreseen to focus on project finance mobilization, above all for non-sovereign project origination, but was broadened to also include capital markets and potential bond issuers. Similarly, the ACGF has adopted a more flexible approach to training than initially foreseen, including in the case of UK funding study tours in addition to the Innovative Finance Clinics. While no support to additional policies or strategies have been identified, support for roundtables and training is expected to continue. For the indicators and their targets to remain relevant, the program should consider revising 3.b and 3c final targets, e.g. as part of the annual logframe review.

Recommendations for next year:

- ADB could report on when these ‘criteria for sustainable finance’ are adopted and used by project developers and investors linked to ADB-financed projects, this will represent an important contribution to programme outcomes.
- Given that all end-of-programme targets have been met for this output, the programme team together with ADB could review how the programme can establish meaningful targets to incentivise performance.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance compared to the original VfM proposition in the business case

The key cost drivers identified in the business case were.
Administration costs
Construction and material costs
Salaries
Accommodation costs (Manila)
Travel

The ADB Trust fund fees remain the same as those set out in the business case. A Trust fund co-ordinator has been recruited over the course of the last year, in line with the business case and MoU. Salaries and FCDO platform costs for the programme funded seconded expert in Manila remain in-line with expectations.

One project has commenced construction. We have seen no reporting on significant inflation pressures affecting construction and material costs of the project over the past year. The ACGF operating environment remains good as reflected in a strong pipeline of infrastructure projects. Most ASEAN countries remain able to take on infrastructure loans. Where a country is constrained, the programme has switched to technical assistance grants rather than loans.

VfM Indicators

In the business case we proposed to monitor the project value for money at the fund level using the indicators set out below. The purpose of the cost effectiveness indicator was to ensure where mitigation was the primary purpose of the project, the emission reductions generated are at reasonable cost, recognising that ACGF has multiple objectives beyond mitigation. Increasing the number of ‘bankable’ projects and crowding in finance from multiple sources are core to a blended finance facility such as this. It is right therefore the UK should seek to monitor these elements as part of its VFM analysis.

To date only one project – INO Flood Management and Coastal Protection in North Java – has been approved by the ADB Board. Over the past (FCDO fiscal year) year, the UK has committed new money to one project in Cambodia (November 2024) increasing to four the number of projects the UK has committed capital to.

Value for money area	Level	Indicator	Project	Current value
Cost effectiveness	Project	£/tonne CO2e mitigated; cost per t/CO2e, $/MWh generated	INO Flood Management and Coastal Protection in North Java Project / Indonesia (no-objected) / Philippines (no-objected) / Cambodia (no-objected)	1. N/A / 2. TBC on ADB board approval / 3. TBC on ADB board approval / 4. TBC on ADB board approval
Bankability	Project	A “before” and “after” calculation of the debt service coverage ratio (DSCR). For the ACGF these need to be 1.05 or above (<1 in the absence of the ACGF loan).	INO Flood Management and Coastal Protection in North Java Project / Indonesia (no-objected) / Philippines (no-objected) / Cambodia (no-objected)	1.N/A an exception clause was applied.[15] / 2. TBC on ADB board approval / 3. TBC on ADB board approval / 4. TBC on ADB board approval
Leverage	Fund / project	Ratio of ACGF UK Trust Fund loans: co-financing from other sources, disaggregated	INO Flood Management and Coastal Protection in North Java Project / Indonesia (no-objected) / Philippines (no-objected) / Cambodia / (no-objected)	1. 1:32 / 2. TBC on ADB board approval / 3. TBC on ADB board approval / 4. TBC on ADB board approval
[15] For example, for the board-approved Indonesia Flood Management programme, the project is assessed as bankable, but since the project is non-revenue-generating, ratio tests were not used (per guidelines which apply exceptions in such cases). Economic viability is demonstrated since the economic IRR (10.23%) exceeds the social discount threshold rate required by ADB. This is conservative as it does not factor in avoided damage costs (e.g., for commercial, industrial, municipal and institutional structures, roads, and other infrastructures).

To simplify monitoring arrangements, the FCDO programme team agreed to replace a Climate and Development Impact Grid with two targets (below) to ensure there were incentives to do projects with high climate and social impact.

Indicator	Target	Value
Share of UK financing to projects classified as ‘priority green’* / * For a project to be classified as priority green, at least 80% of the project cost should be categorized as climate finance.	45%	Indonesia North Java Flood Management Project. Priority green (100% climate finance). / Indonesia (no-objected). TBD. / Philippines (no-objected). TBD / Cambodia (no-objected). TBD.
Share of UK-supported projects approved that directly advance gender equality and social inclusion.	80%	INO Flood Management and Coastal Protection in North Java Project. Directly advances gender and inclusion. / Indonesia (no-objected). TBD. / Philippines (no-objected). TBD. / Cambodia (no-objected). TBD.

Transformative change in region
The objective of this programme is to achieve transformational change (systemic change, and scaling) in finance for infrastructure in the ASEAN region. Evidence that the ASEAN Catalytic Green Finance Facility is having a transformative impact has been collected over the year.

As reported last year, in October 2023, the AIF Board approved the repositioning of the ASEAN Infrastructure Fund (AIF) as a green fund. When it was established in 2011, the AIF was not set up as a green fund, but as a response to the infrastructure gap. The decision by the AIF Board in 2023 is attributable to the success and catalytic effect of the ACGF and its partners in its first years of operations.

The ACGF has demonstrated how concessional finance can be available from the international community for innovative and green infrastructure. Any infrastructure not aligned with a green taxonomy, would struggle to attract international co-finance.

In March 2025, the AIF Board of Directors endorsed the 2025-2028 Action Plan to transform the AIF into a larger and more regionally focused fund.

The Action Plan sets forth important changes aimed at scaling up and extending the reach of the AIF as an ASEAN-owned green finance platform. Malaysia is Chair of ASEAN in 2025 and has included AIF reform in the ASEAN agenda this year. The UK’s participation, alongside other donors, is helping to generate increased support for green infrastructure finance in the region.

Secondary benefits to the UK of the programme

The UK tracks the impact of the programme on the UK using the following indicators. This programme is assessed as having a high impact on UK-ASEAN dialogue and UK visibility on green infrastructure, growth and investment in the region.

1.Strengthened UK-ASEAN government dialogue on green infrastructure growth and investment (impact level)	Quality of UK-ASEAN dialogue on green growth and infrastructure investment (qualitative)	High impact. / Qualitative FCDO internal assessment.
2. UK investor opportunities and UK expertise drawn upon (output level)	Amount of UK sourced finance raised (cumulative)	Not applicable
	Number and value of bonds listed on London stock exchange (cumulative)	Not applicable
	Amount of UK participation in consultation services	Good.

The programme has had a significant impact on the quality UK-ASEAN dialogue around green infrastructure investment. The UK participates in the Annual ACGF Partners meeting each year. It provides updates to the UK-ASEAN Joint Co-operation Committee on its partnership through this facility. The UK has significant engagement in ACGF activities in 2024 (see table 3 below).

Table 3: UK engagement in ACGF activities

Activity type	Activity	Date	Participation
Innovative Finance Clinic[16]	Green and Resilient Buildings, Hanoi	September 2023	Recognized as co-funder. Logos displayed.
Innovative Finance Clinic	Green Data Centres	October 2024	UK High Commissioner to Singapore Nikesh Mehta delivered opening remarks.
Project cofinancing	Indonesia Flood Management in North Java	October 2024	Recognised as financier in press releases.
Knowledge and Capacity Building	Municipal Bonds study tour and Roundtable	October 2024	Co-organized activity. Recognized as cofounder. Ben Mellor, Director, Indo-Pacific, and Andrew Masters attended the private sector roundtable.
Engagement	24th ASEAN Energy Business Forum	October 2024	UK FCDO officials attended.
Engagement with ASEAN	AIF Board and ACGF Group Partners Meeting	November 2024	FCDO recognised as ACGF partner. UK officials attended.
Engagement with ASEAN	ASEAN-organized fora related to ASEAN Power Grid	Q3 2024-Q1 2025	FCDO recognized as ACGF partner.
[16] Green and Resilient Buildings in ASEAN Cities, available here.

A municipal bonds study tour for Southeast Asian government officials to the City of London was held in 2024 resulted in a high-quality dialogue with UK based organisations and government counterparts, including the UK’s Debt Management Office, Transport for London, London School of Economics, Climate Bonds Initiative, and London based investors.

To date there has been many opportunities to use the media to publicise UK partnership in the region through the programme. Our media links are listed below.

UK-ACGF Media Links
Partners Pledge $665 Million to Support Green Recovery in ASEAN | Asian Development Bank (adb.org) / Truss announces major investment in clean infrastructure in Asia - GOV.UK (www.gov.uk) / https://twitter.com/ADB_HQ/status/1544607276069261314 / https://twitter.com/SarahTiffinUK/status/1722239468101661155 / https://www.adb.org/news/adb-strengthens-flood-management-indonesia-250-million-loan / https://twitter.com/ACGF_Facility/status/1722313596166676719 / https://twitter.com/ClimateBonds/status/1722217793163346287 / https://www.adb.org/news/adb-strengthens-flood-management-indonesia-250-million-loan / UK announces agreement to strengthen ties with Southeast Asia and scale-up security and development links – GOV.UK (www.gov.uk)

VfM performance compared to the original VfM proposition in the business case

In line with the business case assessment, the evidence to date confirms the ADB is an efficient intermediary for dealing with large scale investment, particularly in relation to facilitating large scale sovereign lending to ASEAN member states. ADB overheads and management charges for the trust fund remain reasonable for the delivery of programmes of this scale and complexity. ADB has demonstrated its ability to mobilise other sources of finance to scale ACGF operations, by working closely with ASEAN and the finance ministers track through the AIF. The ADB is in discussions with multiple partners who are seeking to join the ACGF.

FCDO should continue to monitor the value for money of concessional finance for new renewable energy given the falling costs of this sector and the degree to which investments are attached to significant private sector mobilisation or market innovation. Common to all blended finance projects, the focus should be on the additional impact achieved to warrant the additional concessional finance.

Assessment of whether the programme continues to represent value for money

There is sufficient evidence for the programme to continue. It represents good value for money. This programme forms part of FCDO’s Indo-Pacific Business Plan. It delivers against International Climate Fund indicators and the UK-ASEAN work plan.

E: RISK

The team carries out an assessment of the programme risks every quarter. This involves an IPRD team discussion as well as an assessment exercise with the ADB programme team. ADB provides information to FCDO on a quarterly basis for this purpose. Accordingly, the risk register and risk appetite for the programme is updated. Since the beginning of this programme the overall risk has remained at Moderate. All the risks are within appetite.
Key risks identified are the absence of quality, investment ready sustainable infrastructure projects which meet UK requirements; slow end to end procurement for capital projects by borrowers, which could lead to slow delivery and could delay programme spend due to slow disbursements. Insufficient and uncertainty of ODA can also cause delays. These risks are well mitigated by working closely with ADB to expedite completion of administrative requirements for necessary approvals so that timely transfer of funds can be done. Specific performance indicators on borrower’s procurement capacity is included in ADBs project due diligence, and FCDO have been added this to the programme performance framework (to be monitored through ADB Annual Procurement reports). Procurement timelines are closely monitored and the stages that the borrowers are at, as per the proposed workplan, are discussed during quarterly discussion. ADB also provides a quarterly update of pipeline projects.

ADB has sound and comprehensive mechanisms in place to supervise and monitor implementation, including procurement support for borrowers for capital projects. Projects are led by sector experts in ADB’s Sectors Group, with support from appropriate specialist teams across the bank, such as legal, procurement, financial controllers, and safeguards. ACGF staff work closely with project team leaders to ensure that cofinancing is deployed appropriately. For all cofinanced projects, policies concerning anticorruption measures, governance, anti-money laundering, counter terrorist financing, procurement, non-consulting and consulting services, disbursement, and financial management apply, which mitigate associated risks.
At project level too, arrangements for financial accounting and reporting, disbursement procedures and auditing requirements are developed and will be included in the project administration manual for each sub-project. Standard ADB policies and procedures on assessing and addressing climate risks associated with projects are also applied.
In line with ADB relevant policies, the ADB Climate Risk Management Framework will be applied to all projects for identifying climate change risks in the early stages of project development, followed by evaluating technical and economic aspects of adaptation options and incorporating adaptation measures in the design of projects at risk. During implementation, monitoring and reporting of risk level and climate-proofing measures will be carried out.
ADB continues to maintain a record of borrower or grant recipients and/or the executing agencies supported by the ACGF-UK (the downstream partners), as identified in the relevant loan or TA agreement.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The UK-ACGF is managed by ADB’s Southeast Asia Department through its Green Finance Hub (SGFH) under the direction of the ACGF Fund Manager. The ACGF team allocates funds to projects and TA on a rolling basis in line with the governance structures set out in the MoU and as further specified in the Establishment Paper and Implementation Guidelines. The team also periodically reviews allocated resources to ensure effective deployment. For example, where funds are allocated to projects and where approval or commitment of such projects is at risk, SGFH will review the allocation in consultation with relevant teams and ADB country offices in view of reallocation to other projects in the pipeline. No such reallocations have yet taken place.

FCDO is a core member of the ACGF Partners Group, participating in the semi-annual Group Partner Meetings in June 2024 (virtually) with the ACGF administration team, and in November 2024 (Bangkok, Thailand) with the AIF Board of Directors, at which the SRO participated in person. The November 2024 meeting also included sessions on ACGF's 2025 knowledge and collaboration priorities; APG collaboration; and an update on the setup, operationalization, and partner engagement of the Nature Solutions Finance Hub.

The first UK-ACGF Steering Meeting was held in London in October 2024, attended by key members of IPRD and ADB teams. During the meeting, FCDO emphasized its commitment to a diverse portfolio of ACGF project and TA activities, with a particular focus on the Philippines and Thailand. FCDO also expressed its intention to continue fostering economic diplomacy and growth within the Indo-Pacific region, with particular interest in regional connectivity, digital development, and energy.

In 2024, the ACGF and FCDO teams continued to coordinate and foster strong links between the work of the ACGF and UK embassies and stakeholders in the region. This involves raising awareness of ACGF activities through external communication as well as direct engagement—when UK funding is involved—e.g. through meetings with UK embassies and stakeholders during ACGF scoping missions as well as through speaking opportunities.

The ACGF team ensures regular monthly engagements with FCDO and relevant stakeholders, as well as weekly internal meetings to review progress.

One of the top priorities in 2024 has been the implementation of the programme and approving investment projects. Funding for two investment projects have been transferred to ADB.
ADB submits its audited financial statements once a year as agreed in the MoU. And annual programme reports are shared with FCDO and other funding partners in the end of February every year.

During 2024, SGFH recruited additional staff and consultants to implement ACGF, bringing to 26 the number of personnel who are substantially dedicated to the program. Currently, 7 personnel support project origination, structuring, and cofinancing; 5 supporting knowledge and capacity building activities; and 9 supporting funds and partnerships, in the latter case including the handling day-to-day management of UK-ACGF resources and coordination with FCDO, among other duties. Within the funds and partnership team, positions newly recruited in 2024 included (i) an Operations Officer, with responsibility for managing procurement for TA activities including project support, events and knowledge products; (ii) a Financing Partnerships Officer, with responsibility for fiduciary administration of TA funds and the ACGF trust funds more broadly, including the UK-ACGF; and (iii) a Trust Fund Coordinator, with responsibility for supporting the oversight of the UK-ACGF, the European Union-ACGF trust fund and the Green Climate Fund ACGF program.

Augmenting the dedicated ACGF team is a range of functional specialists across ADB departments, at headquarters and in the field, with responsibility for project delivery, technical inputs, compliance, legal, and back-office functions.
Commercial performance

This project has only one implementing partner, the ADB. We have not entered any commercial contracts in the reported year of the programme.

Financial Performance

In FY 2024-25, £3.4 m RDEL and £ 9.6 m CDEL was disbursed to the UK- ACGF Trust Fund. Spend till date for the programme is £31.1m (28%) of total £110m of approved budget in first 3 financial years (2022-23,2023-24 and 2024-25). The programme has 4 years left until its end date of 31st March 2029 and £79m remaining budget to spend. This means £20m average spend in a year.

The UK is facing a period of profound change, with conflicts overseas undermining security and prosperity at home. Despite a difficult fiscal context in the UK, the UK remains committed to playing a significant role in international development. Tackling climate change is a top priority for this government and the UK remains committed to International Climate Finance. An amendment to the trust fund arrangements may be required to ensure the programme meets future UK priorities and remains with ODA availability. This may include adjusting the balance of technical assistance (current ceiling is £7 million) and blended capital (current ceiling £100 million) as well as adjusting the length of the programme.

Disbursements to partners are being tracked to ensure full utilization of FCDO’s funds and that there are no huge uncommitted balances. Of the $10m UK-ACGF funds allocated to the North Java Flood Management project, $3.7m had been disbursed.

RDEL 2024-25	CDEL 2024-25	Total Contribution Paid 2024-25
£ 3.4 m	£ 9.6m	£13 m

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

FCDO and the ADB have an annual trust fund Steering Meeting which is the main decision-making process for the programme. In addition, to this formal event, there is close and regular communication and working between FCDO and the ADB. The working relationship remains excellent. Regular catchups between ADB and FCDO teams have continued since the inception of the programme. These were held at different level of the management structure including on thematic basis for example quarterly catchups for assessment of programme risks and mitigation plans as well as separate meetings to discuss any changes required in Outputs, indicators or milestones in the Results Framework. At the programme management level, meetings are now held every month which includes Comms colleagues (both FCDO and ADB) as well. The ADB team are also invited to the ACGF weekly meetings in which Finance related discussions may also be held on specific matters (such as on Promissory Notes) and FCDO Finance colleagues are then included. With respect to the other ACGF Financing partners, the SRO and FCDO secondee participate in person at the ACGF Financing partners and Partners groups meeting or other events as possible. This ensures that FCDO inputs to planning of the programme continues and programming decisions can be informed. The ACGF team includes a consultant who leads on ACGF results monitoring and reporting to partners. In addition, all projects approved for financing adhere to ADB processes for progress monitoring and reporting.

Like the previous year, ACGF’s Annual Review process has included an external member (Development lead Southeast Asia Department), outside of the programme team but from within FCDO. The review team also included a Monitoring and Evaluation Adviser and Social Development Adviser. This was a desk based review using all project documentation and the ADB written UK-ACGF Trust Fund – Annual Report 2024.

For continuous learning and to support informed allocation decisions, a systematic and objective monitoring of both projects and TA activities is done. Monitoring is carried out jointly by user units (following standard ADB processes) and the ACGF team (through its review of biannual activity updates received from project teams). Activity updates include details on implementation progress, contributions to indicators and targets, and an account of unexpected results or challenges faced during the reporting period, if any. A dedicated team of experts oversees all monitoring and reporting to ensure quality and timelines and conducts regular analyses to inform learning and decision-making. In 2024, the Green Finance Hub (SGFH) established an internal data platform to support ACGF monitoring, and in 2025, regular learning sessions on reporting will be provided to SGFH staff and user units.

A mid-term review of the UK-ACGF is scheduled for 2026, to allow for a more thorough analysis of the portfolio of cofinanced projects, the outcomes of deployed TA funds, and alignment with UK-ACGF outcome targets.

Date of last narrative financial report	30 September 2024	Date of last audited annual statement	Expected in June 2025 as per ADB’s Financial reporting cycle