## Annual Review REMIT Programme

Title: Revenue Mobilisation, Investment and Trade Programme (REMIT)
Programme Value £ (full life): £39 million		Review date: November 2025
Programme Code: 300134	AMP start date: 11 November 2019	AMP end date: 30 March 2028

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025	2026	2027
Overall Output Score	Major	Major	Major	Major	Major	Major
Risk Rating	A	A	A	A	A	A+

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300134/documents
DevTracker Link to results framework:	https://iati.gov.uk/iati_documents/61128605.xlsx

A. SUMMARY AND OVERVIEW

Description of Programme
The Revenue Mobilisation, Investment and Trade Programme (REMIT) is a £39 million technical assistance (TA) programme supporting Pakistan to implement macroeconomic reforms and improve conditions for high and sustained growth, job creation and poverty reduction. The programme is supporting Pakistan to:
- Strengthen tax revenue mobilisation, including by increasing the number of taxpayers.
- Address investment environment challenges faced by local and UK businesses.
- Facilitate trade and drive competitiveness by reducing the barriers to trade to reduce Pakistan’s trade deficit.
- Modernise how macroeconomic policy is made and implemented, helping avoid future economic crises.

The programme is being delivered by:
- A commercial supplier, Adam Smith International (ASI), with a budget of £23 million, supporting reforms on revenue mobilisation, investment climate, trade competitiveness and macroeconomic management.
- The World Bank through the multi donor trust fund, the World Bank Trust Fund (WBTF) Pak @100 with a budget of £8 million, supporting revenue mobilisation, investment climate, macroeconomic management, and trade, reforms.
- Partner Across Government (PAGs): His Majesty’s Revenue and Customs (HMRC), Cabinet Office’s Government Communication Services International (GCSI) providing support to Government of Pakistan on revenue mobilisation reforms, and strategic communications.

Economic growth in partner countries is a priority for the UK Government and REMIT is fully with this agenda. It has the potential to strengthen the foundations for a stronger economic partnership between the UK and Pakistan.

Pakistan is currently at a pivotal moment, with a rare opportunity to pursue both economic stabilisation and growth. From being on the verge of default in May 2023, over the last 30 months, Pakistan’s authorities have demonstrated commitment to delivering results through policy measures to achieve macroeconomic stability and implement the IMF programmes. In addition, the authorities have introduced long-term strategies such as URAAN Pakistan and the Prime Minister’s Economic Transformation Agenda and Implementation Plan.

Building on this momentum, REMIT has become a high-profile and highly transformational programme, with frequent direct engagement of the Prime Minister (PM) and Finance Minister (FM) since after the election in February 2024. Notable high-profile events in the past year include Baroness Chapman launching the ‘regimeter’ with the PM in December 2025, British High Commissioner’s presence at the launch of the PM’s New Energy Vehicle Policy in August 2025, and the British High Commissioner chairing the REMIT Steering Committee meetings alongside the FM over the past year, all organised and funded through REMIT. Many senior and mid-level government officials (e.g. secretaries of relevant ministries such as MOC, BOI, FBR) have stated in REMIT Working Group Meetings that they highly appreciate the targeted high quality technical assistance (TA) provided by the programme (especially the ASI component) and BHC.

This context underscores the continued need for tailored technical assistance to help the Government of Pakistan advance its reform agenda. REMIT is well positioned to respond, offering flexibility to meet evolving priorities. Its adaptive design and strong delivery momentum make it an effective initiative. The programme has already supported key reforms, including FBR’s strategic plan, import tariff reforms, regulatory modernisations, the establishment of Invest Pakistan, and sectoral roadmaps for nine critical growth sectors.

Summary supporting narrative for the overall score in this review

The programme’s performance over the last year has been scored as an A+ overall. REMIT has demonstrated remarkable success in contributing towards strategic reforms for enabling economic growth in Pakistan. It is seen as the UK’s ‘flagship’ initiative in Pakistan and has strengthened the British High Commission’s senior diplomatic engagements. The programme has provided a strong and trusted platform, where the programme’s outputs have been shaped through effective partnerships with international financial institutions such as the IMF and key bilateral partners. The regular meetings of the Steering Committee (SC) co-chaired by the finance minister and the British High Commissioner shows strong ownership by the Government and the direct access to the BHC to inform critical policy decisions. The set-up of working groups under the Steering Committee further ensures operational-level ownership and collaborative delivery.

The last 12 months was highly significant for the REMIT programme. A major reform window opened two years ago in Pakistan and the REMIT programme, especially the component implemented by Adam Smith International (ASI), responded effectively to this reform window to deliver structural economic reforms. It used the flexibility built into the programme to quickly scale up the activities to respond to the government’s requests and use opportunities to drive change. The pace at which programme has worked and the flexibility it has demonstrated has been widely recognised by top government officials as being a key reason why they found it useful and impactful.

The programme worked at three levels: informing Pakistan’s high-level economic strategy through analysis and advice; providing extensive analytical and policy support on key legislative and policy reforms; and directly delivering digital transformation and organisational reforms at various government entities. At the implementation level, the programme supported the implementation of policies and organisational restructuring by working directly with key government entities. Over the last 12 months, some key results achieved by the REMIT programme were:

Revenue mobilisation:
- Nationwide rollout of the Compliance Risk Management system (CRM), which categorised taxpayers by risk, supported audit selection, and enabled PKR 1.2 billion (£ 31.72 million) in recoveries with PKR 34 billion (£ 89.87 million) under proceedings. CRM dashboards and five new national tax manuals standardised practices were adopted.
- An AI-powered Digital Eye system was deployed in 27 cement plants with 99.7% accuracy, reduced under-declaration.
- Digital upgrades, including an AI chatbot, are expected to cut 250,000 in-person visits for tax-payments annually.
Investment climate:
- Business environment strengthened through 541 regulatory reform proposals yielding PKR 422 billion in projected annual savings (over £1 billion pa), 465 Cabinet approved reforms, nationwide licence mapping
- Passage of the Asaan Karobar Act, 2025.
- Launch of the National Investment Facilitation Strategy.
- Support to Pakistan’s New Energy Vehicles and National Industrial Policies.
Trade reforms:
- Approval of the National Tariff Policy, which will see Pakistan being from among the most protected markets in South Asia to among the most open-to-trade by the end of the five-year implementation period.
- Restructuring of the PKR 50 billion (£ 13.12 million) Export Development Fund,
- Development of three export-sector studies.
- Rollout of SME e-learning modules for women entrepreneurs.
Macroeconomic governance:
- Leading economist Prof Stefan Dercon supported the Pakistan government to develop a new economic strategy - a five-year framework focused on export-led growth.
- A new Domestic Debt Analytical Tool was developed, helping raise the average time maturity of Pakistan’s debt to over four years.
- Five fiscal studies identifying PKR 384.8 billion in potential expenditure savings
institutionalisation of Climate, Gender & Disaster Budget Tagging across 40+ federal entities
While it is not possible to establish a direct causal link between these improved outcomes and programme activities, there is strong evidence to suggest they are closely associated. Moreover, many of the above achievements are providing the institutional foundations to reach the programme’s desired outcomes and impact in an effective and structural manner. There has been consistent annual growth in the taxpayer base, rising from a baseline of 860,000 to 4.75 million registered users by 2024/25, supported by improved enforcement, voluntary compliance, and strategic plans for the Federal Board of Revenue alongside digital initiatives and institutional strengthening. Exports have shown modest growth from US$25.3 billion to US$26.5 billion, though diversification remains unchanged; however, REMIT-supported trade reforms such as approval of the National Tariff Policy, restructuring of the PKR 50 billion Export Development Fund, and development of export-sector studies have laid the groundwork for future gains. New outcomes introduced over the past year include business friendliness and investment, with the B-READY index set to be tracked to capture both de facto and de jure reforms, alongside cumulative investments influenced by REMIT interventions. Fiscal devolution and PSDP alignment have improved slightly, with provincial expenditure share moving from 51% to around 50% and PSDP alignment increasing from 73% to 75%, while debt average time to maturity has improved from 3.6 years to 3.8 years. Key institutional reforms, including the establishment of the Debt Management Office and Medium-Term Fiscal Policy Unit, have been completed, providing a foundation for future macro-fiscal stability. These associations likely stem from the alignment of programme interventions with broader policy reforms, capacity-building measures, compliance campaigns, and the enabling environment created for trade and investment during the programme’s active implementation period.

While REMIT’s main focus remains on strengthening Pakistan’s fiscal, trade, and investment outcomes, this year the programme also placed greater emphasis on secondary benefits for the UK—such as enhanced bilateral ties, improved market access, and new opportunities for UK businesses. This is reflected in studies that identified barriers and trade potential, policy reforms like tariff liberalisation and the Strategic Trade Policy Framework (STPF) that promote openness and competitiveness, and the entry of UK firms like Wise, which is facilitating digital payments and deepening UK–Pakistan tech collaboration. Collectively, these efforts are making Pakistan’s business environment more attractive for international and UK investment, while supporting shared growth and innovation.

Major lessons and recommendations for the year ahead

- Flexibility in programme design and delivery has been crucial for economic reforms. Consultants’ regular check in with the FCDO TQA leads, availabiltiy and use of tools such as the responsive policy function, and platforms for the government to request for specific support have all helped deliver economic reforms, respond to changes in circumstance and maintain momentum. Opportunities for reform and economic shocks would have been difficult to foresee at the time the programme was designed, but in-built flexibility has been a key tool for success. Business cases, funding allocation, contractual arrangements with suppliers and project work plans for follow-on programming need to retain adequate flexibility to adapt and respond to emerging situations.
- The development and rollout of digital systems in key government departments and agencies have emerged as a major pillar of the programme, cutting across all four outputs. These digital systems help address information asymmetry and agency problems in government, which arise because senior management do not have the data to monitor the activities and performance. The ASI project team has developed the expertise to locally develop high quality software systems at low cost and deploy it at pace.
- Organisational restructuring and management reforms of various government entities has emerged as a further major area of support, where the Pakistan government has demand. Many government entities have outdated organisational structures and management processes, limiting their effectiveness.
- Support to arms-length government agencies with financial and operational autonomy has been especially effective. These institutions have proven to be capable of developing the management processes and human resources required to effectively implement policies and deliver high quality public services. One such mechanism is transforming government agencies into publicly owned non-profit companies that are established under section 42 of the Companies Act. The Pakistan Single Window is a good example of how this can work well.
- The context and political will is currently conducive to major economic reforms, but political economy remains critical. As is common globally, there are winners and losers and supporters and opponents of various reform initiatives among the key stakeholders. As such it is important for the programme continues to assess this and look for opportunities for continuous improvement in the quality of political economy analysis, and incorporation into recommendations.
- The role of the commercial partner ASI, especially component leads, is crucial because they build trusted relationships with senior policymakers in government and combine a strategic approach with attention to detail. The ability of the leads to build close relationships with major stakeholders and navigate political and bureaucratic complexity is crucial to deliver reforms.
- Over the last year the scope of the REMIT programme has substantially broadened, largely reflecting an impactful and positive response to increased demand, but with a couple of indications of possible overstretch. Demand from the government for support has grown across a broad range of topics and entities. This reflects the urgency of reforms from the government as well as the reputation that REMIT has developed for delivering impactful work at pace. While broadening of REMIT’s workplan is judged to be positive overall, in two instances activities were delivered with insufficient technical quality (initial draft of industrial strategy, and ASI support on National Fiscal Pact). This suggests a need for some additional prioritisation and quality assurance.
- The problem of frequent rotation of officials in key government institutions (e.g. FBR) remains a major challenge for policy continuity, reform implementation and development of expertise.
- The fly-in, fly-out model of support provided by UK Government institutions such as HMRC and GCSI is not well suited to delivering transformational change. This is especially the case where capacity and capability within the Pakistan government is limited, requiring long-term handholding support for implementation. Knowledge of how Pakistan’s administrative service works, as well as the ability to respond quickly, are limited for UK Government institutions.
- The funding to the World Bank Trust Fund enables the World Bank to provide technical assistance to the Government which it otherwise could not provide through its lending operations. The World Bank’s technical assistance could become more effective if it can make use of the insider knowledge of ASI consultants who work more closely with government officials, or if it replicated some of the ways of working of the ASI team.
Coordination is critical to effective delivery. Given the key role played by the REMIT programme on Pakistan’s economic reforms, FCDO should continue to have frequent engagement with the World Bank, IMF and ADB to ensure coherence, avoid duplication and share information.
Recommendations for the year ahead
- FCDO should more frequently provide, or at least review, technical quality assurance (‘TQA’) of empirical and policy analysis delivered to government by the commercial supplier ASI. This is especially the case for econometric analysis used for projections, forecasts, assessment of potential impact of policy changes, and policy recommendations. In the process of giving approval for TORs, FCDO should indicate points in the delivery process at which FCDO will either undertake TQA, or review TQA undertaken within ASI. ASI should ensure delivery timelines include sufficient time for this TQA/ TQA review. [to be led by REMIT SRO and technical leads ongoing for duration of programme].
- As it enters its final year, the programme should gradually narrow its scope to and work on a smaller number of prioritised activities. This is essential to ensure that the programme can consistently deliver high quality and impactful outputs, while also maximising impact by focusing on initiatives with the highest potential. FCDO should develop clearer guidelines on priorities and initiate a stronger governance structure (e.g. a lengthier sign-off processes for TOR approvals) through which requests for support from government entities are more thoroughly assessed and approved based on consistency with the guidelines provided. This process should ensure coherence and coordination of policy related work within the REMIT programme. [to be led by REMIT SRO by March 2026].
- Support through Partners across Government should be discontinued. For a given investment of FCDO human and financial resource, ASI and WB initiatives are judged to be higher impact than those of HMRC and GCSI because the former are based and operate in country making them engage, deliver and respond more consistently to the Pakistan system. Unless there is very strong demand from GoP that cannot be met in any other way, it is recommended to discontinue these components. [already agreed by REMIT SRO].
- Programme activities and interventions that directly work with or support the private sector are better suited for the upcoming JETPAK programme. Any such activities, such as support to SMEDA, should either be phased out or overseen by the JETPAK SRO to provide learning for this planned initiative. [REMIT SRO to discuss with JETPAK SRO by February 2026].
- FCDO should further enhance mechanisms to ensure that the policy advice and analysis provided by various components of the REMIT programme are coherent and coordinated with key development partners (e.g. IMF, World Bank). Coordination meetings are held for each programme pillar every 6-8 weeks. These should continue and should more consciously be used to identify opportunities for mutual technical quality assurance. [led by REMIT SRO and technical leads over the course of programme].
- ASI should develop a set of guidelines and process manuals which capture lessons learned from developing and implementing digital systems, organisational restructuring and strengthening management systems in government. These will be shared with relevant government departments and archived within the FCDO to ensure retention and dissemination of learning.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change including any changes to outcome and impact indicators from the original business case.

Figure 1: Summary of REMIT programme Theory of Change

Impact Indicators
1. Pakistan strengthens its ability to self-finance its national development. Indicator 1: Tax / GDP
2. Pakistan increases the role of exports in driving its future growth. Indicator 2: Exports / GDP
3. Pakistan makes its financing needs increasingly affordable. Indicator 3: Gross financing needs as percentage of GDP (debt service)
4. Pakistan boosts its productive capacity. Indicator 4: Gross capital formation (i.e. investment)
Outcome Indicators

1. 1a. Revenue (PKR Billion); 1b. Number of active taxpayers.
2. 2a. Amount of Exports (goods plus services) in US$ Billion; 2b. Diversification into New Products
3. 3a. percentage share of provincial expenditures in national expenditures net of federal debt servicing; 3b. percentage of PSDP allocated to federal subjects aligned with the constitution assignment; 3c. Domentic Debt Average Maturity Time (ATM, years)
4. 4a. B-Ready Scores (average weighted equally); 4b. Cumulative new investments contributed to by REMIT interventions ( £ million)

Outputs
Supporting Pakistan with technical assistance on specific reforms spanning institutional stengthening and implementation of strategic plans in the areas of:
1. Tax, 2. Exports, 3. macro-governance and 4.Business environment.
Outcome
Pakistan makes progress on key structural reforms
Impact
Pakistan implements an economic reform agenda that improves the economic outlook in an equitable manner

The expected impact of the programme is ‘Pakistan implements an economic reform agenda that improves the economic outlook in an equitable manner’. The expected outcome of the programme is ‘Pakistan making progress on key structural reforms’.

The theory of change is based on the premise that Pakistan’s long-term economic progress requires structural reforms to break the recurring “boom and bust” cycle of volatile growth. The programme addresses four core weaknesses in the economy: low tax revenue, inconsistent macroeconomic management, low investment, and weak, undiversified exports.

The programme ToC assumes that providing politically smart technical assistance (TA) will help the Government of Pakistan (GoP) deliver reforms and drive structural change. The TA is delivered across four main interconnected policy pillars, designed to address the underlying causes of economic instability:
1. Tax Revenue Mobilisation: Supporting reforms in tax administration and policy aimed at strengthening revenue collection and increasing the number of taxpayers to help raise the country’s tax-to-GDP ratio
2. Conducive Environment for Trade: Facilitating trade and driving competitiveness by reducing trade barriers and expanding exports
3. Business Environment: Addressing investment climate challenges faced by businesses (including UK businesses) to support regulatory modernisation
4. Improved Macroeconomic Governance and Operations: Improvements in macroeconomic policy is made and implemented to help avoid future economic crises

Changes to Outcome Indicators
Incorporating feedback from the previous annual review, the outcome framework now expands from two broad outcome indicators to four measurable outcome indicators and broadening scope to include trade, fiscal coordination, and investment climate. Below is a summary of the changes observed in the log frame.

Outcome Indicator 1: Shift from growth in tax filers to revenue (PKR) and active taxpayers, creating a stronger link to enforcement and voluntary compliance.

Outcome Indicator 2: Moves from qualitative equity to exports value (US$) and diversification, introducing explicit trade performance measures.

Outcome Indicator 3: Newly added outcome on business friendliness (B-Ready) and cumulative investments, focusing on investment conversion.

Outcome Indicator 4: Newly added outcome on vertical fiscal balance, PSDP alignment, and Domestic Debt ATM, reflecting macro-fiscal coordination.
By successfully delivering assistance in these areas, the programme expects to achieve its intermediate result: "Pakistan making progress on key structural reforms". This is measured through indicators such as the increase in the number of high-value taxpayers, improvement in constraints facing businesses, and reduction in trade tariffs or goods clearance time. Progress in meeting conditionalities set by International Financial Institutions (IFIs) also signals success at the outcome level; contribute to macroeconomic stability and sustained high growth, creating jobs and reducing poverty in an equitable manner. The main mechanism involves flexible deployment of technical experts through a mix of instruments, including long-term embedded experts, short-term missions for international experts.

UK Secondary Benefits
While the programme’s primary focus is on strengthening Pakistan’s fiscal, trade, and investment outcomes, this year it also more explicitly looked at secondary benefits for the UK through enhanced bilateral economic ties, improved market access, and opportunities for UK businesses to engage in a more competitive and transparent environment. This can be observed through the studies that have been conducted, the policies that are being developed, and the engagements that have been facilitated with UK companies.

Studies: The Foreign Firm Issues Study and Trade Potential Study together analyse how to strengthen Pakistan’s investment climate and trade competitiveness while deepening UK–Pakistan economic ties. By identifying and addressing barriers faced by international firms, Pakistan creates a more transparent and business-friendly environment that attracts foreign investment, including from UK companies. Simultaneously, the trade potential analysis informs reforms and identifies new opportunities for UK businesses; these studies were done during the UK-Pakistan Trade Dialogue with DBT engagement ensuring alignment with the DBT Trade and Industrial Strategies.

Policies: Pakistan’s tariff liberalisation policy, the Strategic Trade Policy Framework (STPF) together mark a decisive shift towards openness, competitiveness, and export-led growth. For Pakistan, these reforms unlock efficiency, attract foreign investment, and strengthen resilience against external shocks. For the UK, they open new opportunities for bilateral trade, supply chain integration, and green investment, while reinforcing shared commitments to open markets and sustainable growth.

Opportunities for the UK: WISE, a UK fin tech company has been engaging with the State Bank of Pakistan to enter and facilitate faster, low-cost cross-border transactions. For Pakistan, this means unlocking remittances, attracting foreign investment, and improving ease of doing business. For the UK, WISE’s expansion deepens commercial ties, enhances the global footprint of a UK-listed fintech, and creates opportunities for UK tech collaboration in emerging markets. This aligns with the broader outcomes of the Pakistan Tech Delegation’s engagement at London Tech Week 2025, which marked a new era of investor-focused tech diplomacy by connecting Pakistan’s digital ecosystem with UK capital and expertise.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track to contribute to its expected Outcome of "Pakistan making progress on key structural reforms" and its ultimate impact of "Pakistan implements an economic reform agenda that improves the economic outlook in an equitable manner". Over the last year, Pakistan has enjoyed credit rating upgrades from all major rating agencies, remains on track with its IMF-supported EFF and RSF programmes, and the heads of country offices of the IMF, World Bank and ADB have all publicly commented that Pakistan is making excellent progress on structural reforms.

Below are outcome indicators that showcase the trend since the programme began.

Revenue and Active Taxpayers: There has been consistent annual growth in the taxpayer base (an increase of 860,000 in the baseline to 4.75 million registered users in 2024/25), reflecting improved enforcement and voluntary compliance. Strategic plans for the Federal Board of Revenue have been drafted, digital initiatives and taxpayer facilitation measures are being rolled out, and institutional capacity is being strengthened for the coming year.

Exports and Diversification: While exports have shown modest growth (US$25.3 billion from baseline toward US$26.5 billion (2024/25), the diversification of export products remains unchanged. REMIT-supported policies (e.g. Tariff liberalisation and the upcoming STPF) have laid the groundwork for these indicators to improve.

Business Friendliness (B-Ready) & Investments: These are new outcomes as the focus over the past year has been on regulatory reforms and institutional strengthening. The B-READY index will now be tracked over the coming year (whereby de facto in addition to de jure changes are realised) along with cumulative new investments contributed to by REMIT interventions.

Intergovernmental Fiscal Balance & Debt ATM: Fiscal devolution and PSDP alignment have improved slightly (provincial expenditure share and PSDP alignment moved from 51% baseline to ~50% in 2024/25 and from 73% to 75% in 2024/25 respectively), while debt to maturity has dipped has improved (3.6 years in baseline to 3.8 years in 2025). Key institutional reforms—such as the establishment of the Debt Management Office (DMO) and Medium-Term Fiscal Policy Unit (MFPU)—have been completed, providing a foundation for future macro-fiscal stability.

It is important to note that Pakistan faced an economic crisis in 2023 (being close to default) and the type of reforms required by the IMF and being implemented through REMIT are structural where results are expected to yield over the medium to long term. Moreover, it is not straightforward to attribute REMIT’s above outputs to the achieved trends; but there is confidence that REMIT’s TA has inputted into the adoption and institutionalisation of difficult policies. Key examples include:

- High level economic policy advice for the National Economic Transformation Plan 2024-29 and implementation plan.
- Better Business Environment: Supported the passage of the Asaan Karobar (Business Made Easy) Act, 2025, creating a permanent legal basis for regulatory simplification.
- Tax Compliance: Rolled out the Compliance Risk Management (CRM) system and the “Digital Eye” manufacturing production monitoring system.

Work plan for 2025/2026:
In the coming year, REMIT will step up support for revenue mobilisation by helping FBR implement its transformation plan—focusing on digitalisation, compliance risk management, and voluntary compliance. The programme will also operationalise the Tax Policy Office, coordinate closely with international partners, and prioritise capacity building, training, and harmonisation of tax policies, all underpinned by expanded data integration and digital platforms.

On the investment climate front, REMIT will focus on implementing the PRMI roadmap and further developing the Asaan Karobar Act. The institutionalisation of regulatory impact evaluation and compliance audit processes will continue, alongside the rollout of the B-Ready Index in Sindh. The programme will also support the phasing out of Special Economic Zones in line with IMF requirements and strengthen investment facilitation mechanisms.

Trade competitiveness will be addressed through ongoing tariff rationalisation, particularly in the auto and steel sectors, and the restructuring of the National Tariff Commission. REMIT will support the finalisation and rollout of the Strategic Trade Policy Framework, digitisation of the Directorate General of Trade Organisations, and export facilitation schemes.

In macroeconomic governance, the programme will develop and roll out domestic debt management tools, supporting both the Debt Management Office and the Medium-Term Fiscal Policy Unit. Budget tagging for climate and social expenditures will be consolidated, and REMIT will assist with fiscal coordination, including support for the National Finance Commission and provincial budget processes.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
There is strong justification, based on the current performance and the ongoing reform initiatives of the Pakistan government along with the VfM analysis, for the programme to continue with adequate resources. The programme directly contributes to country business plan goal of contributing to economic growth both in Pakistan and the UK by undertaking critical economic reforms to stabilise the Pakistan economy and encourage increased trade and investment, including with the UK.

Over the last year, the REMIT programme has demonstrated that it can adapt and scale-up its activities rapidly to use technical assistance to deliver systemic reforms, making a strong contribution to achieving its expected outcomes over the last year. This was driven by its success in using the reform window that has opened to implement structural economic reform through legislative, policy and organisational reform. Seen as the UK’s ‘flagship’ initiative in Pakistan, it has also strengthened the British High Commission’s senior diplomatic engagements. This has helped ensure strong ownership by the Government to drive through the required reforms, including through the Steering Committee which is chaired by the Finance Minister and British High Commissioner.

## C. DETAILED OUTPUT SCORING

Output Title	Enhanced Tax Revenue Mobilisation
Output number:		01	Output Score:	A+
Impact weighting (%):		45%	Weighting revised since last AR.	No.

Indicator(s)	Milestone(s) for this review	Progress
Output 1.1 / Sub-output 1: / Taxpayers are segmented into high, medium, low risk categories enabling appropriate compliance actions. / Indicator: % of non-compliant taxpayers in IRIS categorised appropriately	10% of non-compliant taxpayers in IRIS categorised appropriately	Exceeded. 100% of non-compliant taxpayers in IRIS have been categorised as high, medium, or low risk. The CRM Code for all corporate and non-corporate taxpayers was developed and shared with FBR. Risk scoring was completed and initial CRM training delivered nationwide.
Output 1.2 / Sub-output 2: System (e.g. CRM) generates insights and foresights for tax collectors to increase compliance / Indicator 1: % of Tax Collectors having access to CRM Data Insights	Online access available to 200 Tax Collectors in Large Tax Offices (LTOs)	Exceeded. Online access available to 728 Tax Collectors in LTOs. Dashboard and Intelligence Scans configured and rolled out. Digital Eye deployment/system testing completed on 26 out of 27 cement factories.
Output 1.3 / Sub-output 3: Recommended policy and procedure amendments adopted and consistently deployed across the country / Indicator 1: Number of policy recommendations made / Indicator 2: Quantified analyses show revenue implications / benefits of policy / procedure change	Four policy recommendations shared (on revenue mobilisation, tax equity, climate/ environment supportive policy)	Exceeded. Seven Policy Recommendations shared with FBR. Draft procedural manuals developed and shared (Sales Tax Audit, Refund Processing etc). The Data Governance Policy was notified and is under implementation.

Output 1.4 / Sub-output 4: FBR's service delivery channels revamped in accordance with 18F Standards. / Indicator 1: Number of Services or Delivery Channels revamped in accordance with 18F Standards / Indicator 2: Case study on equity implications of delivery channels revamping - user experience, disaggregated to inform GESI	Four Services of Tax Filing Portal	Met. Eight IRIS services were redesigned and rolled out, including IT Return for Salaried Person, Wealth Statement, and others. The AI Chatbot underwent UAT and VAPT, with the Beta Version launched on the FBR website.
Output 1.5 / Sub-output 5: Communications capacity of relevant agencies to understand audiences, messages and behaviours adds value to effective economic reform campaigns / Indicator 1: Number of organisations engaged in capacity building programme / Indicator 2: % participants stating intention (upon completion of training) of implementing approach using OASIS framework OR GoP partners capability level on GCSI maturity scale / Indicator 3: Qualitative analysis of post-training behaviour	Five organisations engaged / 80% of participants committing to using the OASIS framework upon training completion OR GoP partners capability level is emerging on GCSI maturity scale / Qualitative analysis of post-training behaviour	Met: 27 participants from five Government of Pakistan organisations (FBR, IPO, MOF, TDAP, SBP) engaged in the cross-government Campaigning Training Programme. / Over 80% committed to using the OASIS framework or reached ‘emerging’ on the GCSI maturity scale. / Post-training, agencies applied campaign planning tools; TDAP, SBP, and FBR integrated best practices, demonstrating sustained behavioural change.
Output 1.6 / Sub-output 6: Improve inter-provincial and provincial-federal fiscal policy coordination, including around domestic revenue / Indicator 1: Number of round tables / Indicator 2: Single portal available (for GST) that enable taxpayers across the federation to file returns and pay via one platform, reducing tax compliance burden. / Indicator 3: Designing land/property tax reform plans (involving all provincial property taxes) for improved revenue mobilization / Indicator 4: Using behavioural experiments for improved tax compliance in FBR and KP. / Indicator 5: Improving production monitoring system at FBR	Three fiscal roundtables in FY25. Four tax roundtables in FY25. / Single Portal successfully rolled out to all provinces in at least two sectors / Design reform roadmaps for property taxation for all provinces / Design and implement behavioural experiments for tax compliance at least in KP. / Action plan to improve production monitoring system at FBR	Partially Met: Three fiscal and four tax roundtables are on track for FY25. / The single sales tax portal is live nationwide for telecom, with expansion to a second sector targeted this year (not met) / Property tax reform roadmaps are being developed for all provinces. / Behavioural experiments for tax compliance have been designed and implemented with FBR and KP. / The FBR Track and Trace review is informing the production monitoring action plan.
Output 1.7 / Sub-output 7: FBR carries out its tax transformation and strengthens its tax administration processes	MOU signed off to support reforms in line with strategic priorities. / Log Frames developed. Delivery plans agreed for all workstreams. / FBR make available relevant resourcing and single point of contact for participation in capacity building support.	Met: MOU in place as planned / FBR has published strategic plans for Inland Revenue and Customs, outlining its modernization roadmap. Key delivery plans and compliance work have been agreed with HMRC support, while capacity building continues through training and technical assistance / FBR is ensuring relevant resourcing and a single point of contact, as evidenced by recent programme visits and collaborative activities.

Briefly describe the output’s activities and provide supporting narrative for the score.

Digital Transformation of FBR
The digitalisation projects for FBR are one of the standout outputs of the programme. The systems are aimed at increasing the availability of key information to FBR management address agency problems and information asymmetry, which are crucial obstacles to revenue collection. In addition, short tenures and rapid rotation of staff within FBR remains a challenge for policy continuity, reform implementation and the development of subject matter expertise among staff.

Key Digital Initiatives
Several digital initiatives were rolled out at pace, with strong support from Pakistan’s Prime Minister and FBR Chairman:
- Compliance Risk Management (CRM) System: Automates audit selection based on risk parameters, reducing discretion and improving audit efficiency. Successfully deployed, categorising taxpayers into low, medium, and high-risk segments.
- Digital Eye System: Uses cameras to monitor industrial production (cement and sugar) to prevent underreporting. Rolled out to 26 of 27 cement factories and now expanding to sugar mills.
- Enhanced Taxpayer Services: Eight services on the online portal were redesigned (exceeding the milestone of four). Launch of an AI chatbot and upgraded portals is expected to cut 250,000 in-person visits annually.
- HR Management System: Currently under development to strengthen internal capacity.

Sustainability and Governance
The ASI-REMIT team and FBR have prioritised sustainability, including maintenance and upgrades. FBR staff have adequate capability to operate these systems, supported by Pakistan Revenue Automation (PRAL), which will manage them. Government stakeholders noted PRAL may require organisational restructuring to enhance its effectiveness.

Data Governance Framework
ASI-REMIT developed a data governance framework, leading to the creation of a Data Governance Office within FBR. Two dedicated positions—the Chief Data Governance Officer and Chief Data Acquisition and Integration Officer—have been established, underscoring the importance of appointing specialists to manage growing digital data volumes.

Policy Recommendations
ASI submitted seven policy recommendations to FBR based on econometric modelling to address slow tax revenue growth. These evidence-based proposals aim to strengthen reform design and implementation.

World Bank Support
The World Bank facilitated federal-provincial coordination through roundtables, enabling the rollout of a single GST portal for the telecom sector—a key step towards harmonising sales tax on services. It also supported a review of tax reform proposals, advancing evidence-based budgeting, and assessed fiscal costs of state-owned enterprises. Additionally, detailed microeconomic analysis informed a new electricity subsidy targeting approach.

HMRC Engagement
HMRC provided peer-to-peer support on international tax compliance, transfer pricing, and data analysis. While appreciated for its global perspective, short-term consultant visits proved less effective than sustained engagement. Funding constraints mean HMRC support will end at the close of the current financial year.

Describe any changes to this output during the past year, and any planned changes because of this review.

The Outputs 1.1–1.3 now emphasise measurable results (risk-based taxpayer categorisation, CRM insights access, and policy adoption), with extended targets to 2027 and a major outcome shift towards digital transformation (AI tools, data governance) and institutional sustainability

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Sr.	Recommendation	Progress
1.	There is currently a window of opportunity to support FBR make substantial progress on tax. It has set an ambitious target of increasing domestic resource mobilisation by 40% and is going through an FBR transformation plan. To support this, there is strong demand for TA from development partners, particularly fast, responsive TA at which ASI excels. Strong political economy and influencing skills from FCDO-P and ASI were crucial for getting tax work back on track after a brief use due to new government’s lack of buy-in. The workstream is now back on track with renewed traction reflected by FBR Chairman’s ask for support on implementation of FBR’s transformation plan at much faster speed. FCDO-P should respond quickly to these asks in line with FCDO’s internal controls and compliance standards (Programme SRO, Tax lead by March 2025).	Completed: The FBR Transformation Plan is being implemented, with ASI providing technical assistance. The CRM system has been deployed nationwide, and the FBR Chairman has requested accelerated support. The programme is responding promptly, and technical assistance is aligned with FCDO standards.
2.	HMRC are reconsidering its offer to FBR based on some concerns over the effectiveness, cost-effectiveness and sustainability of its technical assistance and are consequently considering whether to continue offering it in Pakistan. It has now made an offer to extend their support for one more year. In contrast, FBR were positive about HMRC support and there is demand for HMRC to continue and expand their provision of TA. FCDO should engage with HMRC to identify indicators of effectiveness, cost-effectiveness and sustainability that HMRC should monitor, these should be incorporated into the VFM framework, and government should be informed that adequate performance on these in future will be necessary for HMRC support to continue. (Programme SRO, by March 2025)	Completed: HMRC technical assistance continues, with ongoing collaboration and demand from FBR. Value for money and sustainability are emphasised, and local adaptation is highlighted.
3.	Staff rotation poses a risk to the programme. It is recommended that FCDO and implementing partners seek to influence government to agree that officials who are selected for training commit to remaining in post for a certain number of years; and for each key intervention a commitment is made for 2-3 specified people important for delivery to remain in post until the intervention is complete (e.g. development of chatbots). GoP seemed open to such commitments. (HMRC programme Manager, WBTF TTL, ASI TL. by June 2025)	Completed: Staff rotation and leadership changes are recognised as risks. The programme has delivered training and capacity building to mitigate continuity risks, and key interventions have been supported by dedicated personnel.
4.	Communications. Strong communications will be crucial for FBR and MoF to meet their objectives and should play an important role in the revised theory of change. It is recommended that an assessment be done of FBR’s and MoF’s needs and demands for communication TA and on the capability and VFM of GCSI and ASI to meet these potentially scaled-up needs and in-country requirements. (Investment Climate Lead and partner’s Lead (GCSI and ASI), by June 2025).	Completed: Communications needs have been assessed, and strategic communications support was provided to FBR and MoF.

Recommendations for year ahead

- Monitor usage and performance of digital systems delivered by the project. [ASI consultants to do by June 2026]
- Assess the capability of PRAL to manage the digital systems developed by REMIT. Develop detailed plans for the sustainability (maintenance, upgrades, budgeting etc) of the digital systems. [ASI consultants to do by June 2026]
- Assess the usefulness and feasibility of supporting the reorganisation of PRAL to improve its management systems and capability to manage digital systems of FBR. [ASI consultants to do by June 2026]

Output Title	Pakistan establishes a more conducive environment for trade by implementing trade policy and facilitation reforms aimed at improving trade competitiveness, productivity and diversification
Output number:		02	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR.	No.

Indicator(s)	Milestone(s) for this review		Progress
Output 2.1 / Sub-output 1: Institutions including e.g. EDF, PSW adopt and implement capability-enhancing measures / Indicator 1: Analyses / case studies trace the implications of measures in terms organisational performance including gender and equity		One institution supported	Exceeded: Three institutions (EDF, PSW, DGTO) were supported. Technical assistance included restructuring EDF, digital transformation of PSW and DGTO, and case studies were conducted to assess organisational performance and gender/equity implications.
Output 2.2 / Sub-output 2: / Key product level recommendations for improved market access & competitiveness approved / Indicator 1: Analyses/ case studies carried out to understand the implications of the implementation’s recommendations / measures in terms of market access, competitiveness, gender & equity		Two Product Level Recommendations developed	Exceeded: Three export diversification studies developed (agri-food, non-food manufacturing, and minerals), providing evidence-based inputs for Pakistan’s new export strategy and identifying high-potential products and markets. In addition, REMIT supported the development of STPF & National Tariff Policy (ETAIP)
Output 2.3 / Sub-output 3: Women-owned SMEs have better capacity for exports. / Indicator 1: sustainable training module in use		Online module developed for Trade Development Authority Pakistan 200 Women leaders of SMEs trained	Met: 200 women leaders have been trained. In addition, the Online module developed will ensure sustainability of the imparted knowledge
Output 2.4 / Sub-output 6: / Fiscal space created through strengthened capacity in National Tariff Commission and Ministry of Commerce / Indicator 1: Exporters benefit from migration to the Export facilitation Scheme and access to credit finance facility		75% of firms under previous facilitation schemes moved to Export Facilitation Scheme / Total number of exporters benefitting from the Export Facilitation Scheme increases by 15 percent from baseline number of total firms under EFS and all discontinued schemes in 2023/2025 / Share of total exporters using export finance scheme increased by 25% compared to baseline share of exporters using export finance scheme	Exceeded: The Export Facilitation Scheme was successfully rolled out, with a significant proportion of firms migrated from previous schemes. / The number of exporters benefitting from EFS increased, exceeding the 15% growth target. / The share of exporters using export finance facilities rose by more than 25% compared to baseline. These achievements contributed to improved access to export finance and enhanced fiscal space for exporters. / In addition, strengthened capacity in NTC and MoC led to initiation of a major reform to import tariffs.

Briefly describe the output’s activities and provide supporting narrative for the score.

This pillar achieved an A+ because the programme delivered substantial and high-impact results across all three dimensions of trade facilitation: policy reform, digitalisation, and organisational development. ASI provided comprehensive technical support to the Prime Minister’s Office and Ministry of Commerce for the National Tariff Policy 2025–2030, which was approved in June 2025. This policy marks a major shift from using tariffs primarily for revenue generation to a more strategic approach focused on industrial development and export competitiveness, representing a significant structural reform. A standout achievement was the development of the Airport Community System (ACS) for Pakistan Single Window (PSW). Once implemented in 2026, ACS will make cargo processing paperless at all airports and reduce handling costs by 20 to 25 percent. Despite procurement challenges, ASI successfully pivoted to an alternative approach by engaging international consultants, ensuring system development remains on track for completion by December 2025. In terms of organisational development,

ASI supported PSW in building capacity to deliver digital transformation in the public sector and contracted it to implement reforms at the Directorate General of Trade Organisations (DGTO), demonstrating a significant step in strengthening local institutional capability. ASI also helped restructure the Export Development Fund (EDF) into a Section 42 non-profit company, endorsed by the commerce minister. This reform increased EDF’s annual budget from PKR 3–4 billion to PKR 25 billion and granted operational autonomy, enabling recruitment of specialist staff.

The programme exceeded expectations on two sub-indicators, supporting three institutions (EDF, PSW, DGTO) and delivering three export diversification studies, while meeting the target for women’s SME training and online module development. The Export Facilitation Scheme was also successfully rolled out, with a significant proportion of firms migrated and notable increases in both the number of exporters benefitting and the share using export finance facilities. While some activities, such as export diversification studies and private sector training, had limited impact relative to cost, the overall achievements, particularly in policy reform and digitalisation, were transformative and fully justify the top score.

Describe any changes to this output during the past year, and any planned changes because of this review.
The output evolved from policy frameworks and reducing non-tariff measures to an institutionally anchored approach, strengthening capability in EDF, PSW, and DGTO (Output 2.1). Gender inclusion and SME capacity-building were expanded through online modules (Output 2.3), and tracking of exporter migration to the Export Facilitation Scheme was introduced (Output 2.4). Planned changes include deeper integration of digital tools and enhanced monitoring of institutional reforms.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Sr.	Recommendation	Progress
1.	Adaptive programming: As mentioned above, the workstream has been affected by shifting priorities of the recipients and other unanticipated setbacks beyond the control of the REMIT team. The programme remained opportunistic and adaptive. While continuing to stay adaptive, FCDO-P should ensure that such risks are considered in the identification of workstreams and their prioritisation going forward. The team should redefine its deliverables in consultation with GoP for entire remaining life of the programme and define clear milestones for these deliverables to stay focused, avoiding further changes in the delivery plan. (REMIT Trade lead, by September 2025).	Completed: The programme has adapted to shifting priorities, redefining deliverables and milestones in consultation with the Government of Pakistan. Risks are considered in workstream identification and prioritisation.
2.	Sustainability of training and entrepreneurial skills development: ASI has developed and handed over an online training module to FBR enabling women traders to access it through official website. This will help support sustainability and scale up of institutional reforms. Team should consider replicating this model in all other areas where trainings are being imparted and explore linkages to broader reform initiatives. (REMIT component leads and Delivery Partners, by July 2025)	Completed: Online training modules for women traders have been developed and handed over to TDAP, supporting sustainability and scale-up. Replication in other areas is under consideration.

• Accelerate implementation of the Airport Community System (ACS) for PSW and ensure interoperability with other trade facilitation platforms. [ASI consultants to do by June 2026]
• Operationalise the National Tariff Policy and Strategic Trade Policy Framework (STPF), including monitoring tariff rationalisation and integrating export diversification studies into actionable measures. [REMIT Trade Lead to do by September 2026]
• Quantify how many have migrated over from previous schemes to EFS [ASI consultants to do by June 2026] and expand uptake of the EFS to support diversification into high-potential sectors [ASI consultants to do by December 2026].

Output Title	Improved macroeconomic governance and operations
Output number:		03	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR.	No.

Indicator(s)	Milestone(s) for this review	Progress
Output 3.1 / Sub-output 01: Implemented reforms improve the efficiency and transparency of Public Expenditure and debt management / Indicator 1: Number of Analytic Reports shared on debt, subsidy and social protection expenditure.	Four analytical reports / One qualitative analysis / Data analytic tool (prototype) for domestic debt management developed	Met: Four Analytical Reports prepared (covering Federal Subsidy, BISP, PSDP, HEC expenditures, Federal Revenue & Expenditure). / Qualitative Assessment of debt management carried out, and prototype shared and presented in October 2025. Wireframes and BRD were approved
Indicator 2: Qualitative Analyses of the impact of recommendations used / adopted	One qualitative Analyses of the impact of recommendations used / adopted	Qualitative Analysis on Debt Analysis completed
Output 3.2 / Sub-output 02: Data led economic management optimised including policy priorities on climate, gender equity and social policy / Indicator 01: Number of data driven recommendations made / Indicator 02: Qualitative analyses of recommendations used in economic management decisions	Two data driven recommendations made / Five qualitative analyses of recommendations used in economic management decisions	Met: Five Data driven recommendations prepared and shared with MOF (PAMG, CGBT, BISP, HEC, PSDP). / Recommendations of 2 analysis being actioned – PAMG piloted in two federal entities; CGBT initiated in four provinces and two regions
Output 3.3 / Sub-output 03: Data analysis and evidence inform intergovernmental policy coordination efforts / Indicator 01: Number of intergovernmental consultations held that are informed by data and analyses / Indicators 02: Qualitative analyses / Case Studies of actions initiated / benefits of intergovernmental policy coordination efforts	Two intergovernmental consultations held / Two qualitative analyses	Met: / More than three intergovernmental consultations were held. CGBT consultations held in all 6 regions of Pakistan. / Two analyses / studies completed: a case study on the National Fiscal Pact; and a qualitative analysis on the benefits of intergovernmental policy coordination efforts
Output 3.4 / Sub-output 04: Productive sector subsidy reforms / Indicator 01: number of sectors for which a detailed subsidy reform roadmap has been produced	One sector for which a detailed subsidy reform roadmap has been produced	Partially achieved. / Analysis and modelling to inform reforms on power subsidies: ReMIT supported detailed microeconomic analysis and simulations to inform the design of a new deprivation-based electricity subsidy targeting approach

Briefly describe the output’s activities and provide supporting narrative for the score.
The programme successfully delivered key outputs during the year, including analytical reports, technical assistance for the National Fiscal Pact, and the development of a domestic debt management tool. Notably, government uptake of recommendations was strongest where these aligned with external agency requirements, particularly IMF conditionalities. REMIT’s support under this component was both structured and demand-driven, responding flexibly to government requests and providing high-quality technical assistance. The programme’s analytical work anchored expenditure management reforms within the National Fiscal Pact, offering pathways for federal-provincial expenditure sharing.

In addition to these outputs, two qualitative analyses were prepared on Climate, Gender & Disaster Budget Tagging and Public Assets Management Guidelines, further strengthening the programme’s contribution to inclusive and resilient fiscal governance.

The World Bank delivered a consolidated analysis on SOE fiscal costs and subsidies. The AR milestone refers to “four analytical reports” (Federal Subsidy, BISP, PSDP, HEC, Revenue & Expenditure).

These initiatives have contributed to strong macroeconomic governance by the Government of Pakistan over the past 12 months. The programme has supported adherence to IMF requirements and improved macroeconomic outcomes, such as achieving Pakistan’s primary fiscal and current account surpluses, increasing the average time to maturity of debt to over four years, and improving external credit ratings. However, macroeconomic governance remains one of Pakistan’s most significant economic challenges, shaped by complex political economy and technical constraints. This means that despite these efforts, in some cases translation of technical outputs into sustained policy change was only partially realised. This includes high ongoing federal expenditure in areas of devolved responsibility (BISP, HEC). Coordination challenges among implementing partners and across government entities hampered smooth delivery, limiting opportunities for greater progress on these complex political challenges.

In other cases, it is questionable whether delivery of these outputs will translate into enduring improvements in long-term macroeconomic governance, in line with the programme’s impact-level ambition. For example, the federal government continues to make significant budget allocations to the Development Budget (PSDP), and execution of this spending is only held back by budget constraints imposed externally by the IMF. In the context of Pakistan having had more IMF programmes than any other country, this raises critical questions about the sustainability of recent macroeconomic gains beyond the IMF EFF period ending in 2028.

Describe any changes to this output during the past year, and any planned changes because of this review.

The output transitioned from operationalising fiscal and debt management frameworks and energy reforms to a structured, results-linked approach across sub-outputs. Key changes include piloting a domestic debt management analytical tool (Output 3.1), institutionalising climate and gender budget tagging (Output 3.2), and embedding data-informed intergovernmental consultations (Output 3.3). Sectoral subsidy reform roadmaps were introduced (Output 3.4). Planned changes focus on extending milestones to 2027, accelerating uptake of recommendations, and deepening integration of climate and gender considerations into fiscal management.

Progress on recommendations from the previous AR

Sr.	Recommendation	Progress
1.	Budget tagging. There are substantial potential benefits from budget tagging such as availability of disaggregated expenditure and allocations data to make informed policy decisions, and substantial interest from different parts of government to use it. The programme team should plan to maximize benefits from the tagging exercise by directing tagged budget lines towards climate and gender development goals. For example, increased investment in disasters can reduce need for future recurrent expenditures.	In progress: Climate and gender budget tagging has been institutionalised across federal and provincial entities. Tagged budget lines are being directed towards climate and gender development goals.
2.	Managing expectations on green taxonomy implementation. While the State Bank of Pakistan has made good progress on developing a draft green taxonomy for Pakistan with World Bank support, substantial work remains to be done on revising and vetting the draft and stakeholder consultation. To support this process, FCDO should help manage GoP expectations through the Steering Committee about the time required for completion and implementation of the policy	In progress: The State Bank of Pakistan has notified Pakistan Green Taxonomy, that was developed with World Bank support. Further work and stakeholder consultation are ongoing, with expectations being managed regarding the implementation timeline.

Lessons learned this year and recommendations for the year ahead
Debt sustainability is one the biggest challenges that Pakistan faces. However, debt management responsibility is spread across at least three government entities which severely affects strategic and operational coherence.

There continues to be challenges regarding the coherence and coordination of policy advice within and among REMIT’s implementing partners. Advice by ASI’s experts to the top of the Pakistan government is not always well coordinated with the policy advice delivered to the ministries. Coherence and coordination with the World Bank remain a challenge. Improved information sharing and coordination with the World Bank, IMF, ADB and the Government of Pakistan would bring substantial benefits to improved macroeconomic governance in Pakistan.

Recommendations for the year ahead
- ASI should stop supporting Government of Pakistan on the National Finance Commission. The lead for ASI’s macroeconomic governance pillar has been appointed as a non-statutory member for Khyber Pakhtunkhwa (KP) in the currently active 11th National Finance Commission (NFC), so cannot support for conflict-of-interest reasons. It is judged that there is no suitable qualified technical resource to cover this work area, and World Bank are better placed to support. [REMIT SRO to finalise ASAP].
- The sequencing and implementation of macroeconomic reforms will benefit from a high-level coordination committee comprising of top GoP officials and representatives from the IMF, World Bank, ADB, FCDO and ASI. [REMIT Macro Lead and ASI consultants to do by March 2026].
- The programme should work with the IMF and the World Bank to propose the overhaul of the Pakistan debt management architecture and offer hand-on support for a well-resourced and empowered debt management agency. [FCDO Macro lead to do by March 2026].
- The programme should work on consolidating its support on macroeconomic governance and may pick up new areas based on strategic prioritization and the feasibility of being delivered within the programme life cycle. [FCDO Macro lead to do by March 2026].
Output Title	Business Environment Improved
Output number:		04	Output Score:	A+
Impact weighting (%):		15%	Weighting revised since last AR.	No.

Indicator(s)	Milestone(s) for this review	Progress
Output 4.1 / Sub-output 1: Established systemic approach (adapted from Regulatory Guillotine™[1]) assess, identifies, presents and implements critical regulatory reforms / Indicator 1: Number of reforms approved by Board of Investment (BoI) and submitted to Cabinet Committee on Regulatory Reforms (CCORR) for ratification / Indicator 2: Estimated financial impact of reforms approved by BOI and submitted to CCORR for ratification	150 Reforms approved by BOI and submitted to CCORR for ratification / Estimated impact of reforms approved by BOI and submitted to CCORR for ratification - PKR 100 billion, as per Regulatory Impact Assessment (RIA) methodology	Exceeded: 541 reforms have been submitted to CCoRR for approval and implementation. 465 reforms ratified for implementation. AK Act was passed by the lower house and the Senate / Exceeded: Estimated impact of reforms submitted to the CCoRR is more than PKR 423 billion annually (over £1 billion).
Output 4.2 / Sub-output 2: Institutions better support the conversion of investments and inclusion of MSMEs / Indicator 1: Economic policies (e.g. WEP, NIP & NEVP) contributing to economic growth and investment submitted to Cabinet for approval and supported in implementation / Indicator 2: Institutions responsible for economic growth and investment capacitated through structural and legal changes	At least two economic policies (e.g. WEP, NIP & NEVP) contributing to economic growth and investment submitted to Cabinet for approval	Met: Three national economic policies were submitted to the Federal Cabinet: The New Energy Vehicles Policy (NEVP), the National Industrial Policy (NIP), and the Women Entrepreneurship Policy (WEP). They are at various stages of approval and implementation. / Met: Institutional strengthening and legal reforms were also advanced.
[1] ‘The Regulatory Guillotine model’ is a methodology developed by Jacobs, Cordova & Associates who are implementing it through REMIT. It helps governments streamline regulatory frameworks by first counting all existing regulations and then rapidly reviewing them against clear, evidence-based criteria. Any regulation that cannot be justified as legal, necessary, and aligned with market economy principles is eliminated. This method has been implemented in over a dozen countries, resulting in the removal or simplification of tens of thousands of regulations and significant reductions in business costs.

Indicator(s)	Milestone(s) for this review	Progress
Output 4.3 / Sub-output 3: Sector Frameworks implemented to attract investments / Indicator 1: Number of investment frameworks submitted to government / Indicator 2: %age of actions taken on supporting implementation	Three Sector Investment Frameworks completed and submitted to government / 30% supported for implementation with 10% of reforms being major reforms	Met: Four sector investment frameworks (agriculture, IT, minerals, and livestock) were completed and submitted to the government. / Exceeded: Approximately 86% of regulatory reform actions have been ratified for implementation by the Cabinet Committee on Regulatory Reforms (CCoRR). This reflects a high rate of progress in supporting implementation of approved reforms. / In addition, some strategic initiatives were undertaken (London Tech Week attendance, studies for WISE market entry)
Output 4.4 / Sub-output 5: Targeted survey to build evidence for SME policy reform advocacy / Indicator 1: Pro-SME reforms recommended reforms included in the FY26 budget	Targeted survey to build evidence for SME policy reform advocacy.	Met: Targeted surveys were conducted to inform SME policy reform. Pro-SME reforms, based on this evidence, were recommended and included in the FY26 budget proposals.

Briefly describe the output’s activities and provide supporting narrative for the score.

The programme achieved transformative reforms in regulation, digitalisation, and institutional capacity, creating a more competitive and inclusive business environment—fully justifying the A+ score. The REMIT programme’s biggest achievement last year was improving the business environment through policy and regulatory reforms. A key milestone was establishing the legal foundation for regulatory modernisation via technical and legal support for the Asaan Karobar Act (AKA). This Act introduces a modern approach to business regulation and is expected to significantly improve the investment climate. REMIT also helped draft the rules under the Act.

The programme worked closely with the Special Investment Facilitation Council (SIFC) to implement reforms. These efforts have delivered tangible results, such as reducing medical device registration time from three years to three weeks, saving 23,000 labour hours annually on construction approvals, eliminating 600,000 export documents (saving PKR 1.3 billion annually), and modernising company legislation to spur innovation. Work is now underway to phase out subsidies in Special Economic Zones and develop cost-based incentive structures aligned with IMF recommendations.

Positive Feedback from SIFC
SIFC praised REMIT’s support, noting that the project provided access to expertise that government systems could not procure due to capacity and procurement constraints. However, weak capability within government institutions continues to affect reform implementation.

Regulatory Reform Achievements
ASI submitted 541 regulatory reform proposals to the Cabinet Committee on Regulatory Reforms (CCoRR), of which 465 were ratified. If implemented effectively, these reforms could reduce business costs and generate an estimated annual economic benefit of PKR 423 billion (£1.1 billion). ASI also mapped 346 business licences and permits across 27 ministries and 74 agencies, identifying 136 outdated or harmful to the business environment. The project proposed 117 reforms, which were approved for immediate implementation.

Company Law and Digital Tracking
ASI provided technical and legal support to review the Companies Act 2017, simplifying compliance for unlisted firms (over 90% of registered companies). This resulted in 231 reform proposals, endorsed by the government. A digital dashboard was developed to track reform implementation in real time, improving transparency and public accountability.

National Policy Support
The programme supported three major policies:
- National Industrial Policy
- New Energy Vehicles Policy
- Women Entrepreneurship Policy
All were approved and launched by the Prime Minister.

Investment Facilitation
REMIT facilitated Wise plc, a UK-based digital money transfer company, to begin formal discussions with the government and central bank to enter the Pakistan market. This move is expected to increase remittance flows through formal channels, particularly from the UK.

SME and Gender Initiatives
ASI supported the Small and Medium Enterprises Development Authority to train 200 women entrepreneurs on accounting and taxation. An online portal for women entrepreneurs is also being developed. However, the scale of this intervention is small and unlikely to have significant impact. Moreover, training entrepreneurs does not fully align with the programme’s core objective of economic reforms.

Describe any changes to this output during the past year, and any planned changes because of this review.

The output shifted from a broad focus on improving business environment indicators to a systemic, pipeline-based approach for regulatory reform. Key changes include tracking reforms ratified by CCORR and their economic impact (Output 4.1), supporting national policies such as NEVP, NIP, and WEP (Output 4.2), and introducing sector investment frameworks (Output 4.3). A permanent institutional mechanism for regulatory governance and digital tools for reform monitoring has been operationalised. Planned changes extend milestones to 2027 and prioritise institutional capacity, ownership, and sustainability of reforms.

The shift from broad business environment indicators to a systemic, pipeline based regulatory reform approach was necessary to make REMIT’s support more targeted, politically grounded, and sustainably embedded within Pakistan’s own reform architecture. By aligning reforms with CCORR’s ratification process and quantifying their economic impact, the programme can now demonstrate clearer attribution and strengthen the causal links between its activities and higher-level outcomes. Integrating support to national strategies such as NEVP, NIP, and WEP ensures reforms are anchored in real sectoral priorities, while sector investment frameworks focus efforts on constraints that most directly hinder growth and private investment. Operationalising permanent institutional mechanisms and digital tools addresses earlier weaknesses related to fragmented or short-lived reform efforts, improving ownership and long-term sustainability. Extending milestones to 2027 further reflects the time required for meaningful institutional change. Together, these shifts not only enhance programme effectiveness but also more closely align Output 4 with REMIT’s broader objectives of improving competitiveness, crowding in investment, strengthening institutional capacity, and contributing to more durable, higher quality economic growth.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Sr.	Recommendation	Progress
1.	Supporting NIP implementation through FCDO engagement with IMF: The implementation of the National Industrial Policy will require further stakeholder engagement to secure buy-in for the proposed reforms, including ensuring alignment with the ongoing IMF programme. FCDO should make sure that Industrial policy is a) fiscally prudent, b) creates level playing field, and c) avoids further capture by vested interests. The team should assess synergies between this policy and broader FCDO objectives and potentially support the messaging through its engagement with the IMF. (REMIT Investment lead, by August 2025).	Completed: The National Industrial Policy has been developed and aligned with IMF requirements. Stakeholder engagement is ongoing, and the policy is designed to be fiscally prudent, fair, and resistant to vested interests.
2.	Scaling up of targeted reforms in UK priority areas: The workplans of all implementing partners should have milestones related to deepening of work on four priority sectors; agriculture, information technology, livestock and minerals. The milestones can pick up targets from the investment frameworks and ideas from pitch decks to bring depth into the work already initiated by REMIT. (REMIT SRO, Implementing Partners’ Investment Climate Leads and FCDO’s Investment Climate Lead, June 2025)	Completed: Milestones and workplans have been established to deepen reforms in agriculture, IT, livestock, and minerals, utilising investment frameworks and pitch decks.
3.	Managing expectations on implementation: While the State Bank of Pakistan having made good progress on developing a draft green taxonomy for Pakistan with World Bank support, substantial work remains to be done on revising and vetting the draft and stakeholder consultation. In support of this process, FCDO-P should help manage expectations on the implementation timeframe of the policy through the steering committee. (REMIT SRO, by May 2025).	In progress: Progress on the green taxonomy is ongoing, with further revision and stakeholder consultation required. Expectations regarding implementation are being managed.
4.	Ensuring sustainability and continuity across FCDO programming: FCDO-P provides support for economic development and governance in Pakistan through a range of programmes. The REMIT team has been working collaboratively with other FCDO programmes to avoid duplication and take advantage of synergies. The REMIT team should continue the current collaboration with the SNG and SEED team on provincial level engagement to ensure federal reforms translate into impact. Going forward as REMIT ASI’s support on climate transitions to FCDO’s new CIFPAK programme, a similar coordination arrangement will be required with CIFPAK. (REMIT SRO, CIFPAK SRO by September 2025).	In progress: Collaboration with other FCDO programmes, including SNG and SEED, is ongoing to ensure synergy and avoid duplication. Coordination with CIFPAK is planned as REMIT transitions support on climate.

Lessons learned this year and recommendations for the year ahead
Over the past year, the programme learned that a systemic, government owned reform pipeline—anchored in strong institutions such as the CCoRR and supported by digital monitoring tools—is far more effective than relying on broad business environment indicators or fragmented, ad hoc reforms. The rapid scaleup from 150 expected reforms to over 541 submissions and 465 ratifications highlighted the importance of embedding technical work within a formal approval and tracking mechanism, which significantly strengthened reform credibility, attribution, and implementation discipline. The successful passage of the Asaan Karobar Act demonstrated that high impact reforms require early legal groundwork, consistent political engagement, and close coordination with central bodies such as SIFC, especially where technical evidence can compensate for limited government procurement and analytical capacity. Work on national policies (NIP, NEVP, WEP) showed that economic policies progress fastest when REMIT provides both technical drafting support and institutional strengthening, ensuring policies align with IMF requirements and reflect private sector needs. The experience with sector investment frameworks confirmed that sector specific reform pipelines are more actionable and better received by government than generic business climate interventions. Finally, implementation challenges—such as slow progress on the Green Taxonomy and uneven capability across ministries—reinforced the lesson that expectations must be managed proactively.

Recommendations
- Assess and consider the opportunity cost for the programme of providing support to SMEDA and whether this intervention is a good strategic fit with the rest of the programme. [REMIT Investment lead to lead by March 2026].
- Consider transitioning the work on training women entrepreneurs and supporting the organisational development of SMEDA to the upcoming JETPAK programme. [REMIT SRO and JETPAK SRO to do by March 2026].
- Propose to the Pakistan government to restructure the Board of Investment into a modern and autonomous investment promotion agency with specialist staff and to establish a dedicated regulatory authority for business and investment. [REMIT Investment lead and ASI consultants to do so by December 2026].
D: VALUE FOR MONEY

Key cost drivers and performance
The programme’s cost profile this year was driven primarily by direct technical assistance and the responsive policy fund. Together, these two categories accounted for £3.1m, or approximately sixty-five per cent of total spend between November 2024 and October 2025 for ASI delivered components. Operational costs related to training, workshops, missions, and stakeholder consultations formed the second tier of drivers constituting 35% percent of the total spend. Programme expenses represented about 6.9% of annual programme spend (£0.35m of £5.18m), a ratio that compares favourably with prior years and common practice for similar FCDO programmes.

VfM performance compared to the original VfM proposition in the business case
Against the business case’s VfM proposition, the programme has continued to convert relatively modest inputs into high‑leverage outputs and measurable outcomes, consistent with the theory of change tested in the previous annual review and strengthened this year. The shift to locally sourced design and development for digital systems has preserved the business case’s economy assumptions while improving contextual fit and speed of deployment. Efficiency gains are visible in the concentration of spend on high‑impact workstreams and the adaptive reallocation of effort to government priorities, particularly where reform windows opened. Effectiveness has improved in areas explicitly targeted by the business case, compliance risk management, regulatory simplification, and evidence‑led macro‑fiscal management, while equity considerations are now embedded more systematically in policy design and delivery, in line with the proposition’s commitment to inclusive growth and beneficiary reach. In short, the programme’s operating model continues to deliver the intended VfM balance, with stronger evidence this year of outputs translating into outcomes at portfolio level.

Economy: The programme maintained strong economy through competitive sourcing and localisation. Core systems were developed domestically at a fraction of international benchmark costs: the Compliance Risk Management tool at approximately £78,200, the domestic debt management analytics prototype at approximately £98,000, and the public–private dialogue platform at approximately £110,000. Comparable international systems of similar scope typically range from £200,000 to £400,000, with enterprise solutions higher still. The choice to procure locally delivered additional economic benefits, better contextual fit, reduced integration overheads, faster iteration cycles with government counterparts, and lower lifetime support costs. Average personnel costs rose relative to the prior year due to the required depth of expertise for scaled deployment and institutionalisation; however, these increases remained proportionate to scope, and the overall expense ratio for programme management stayed within prudent thresholds for FCDO delivery.

Efficiency: Efficiency improved through a tighter alignment of spend to impact weighted outputs and through adaptive management that prioritised deliverables with the strongest near-term payoff. Digital solutions were not only built cost effectively; they were also rolled out to end users, which reduced rework and idle asset risk. The CRM dashboards and intelligence scans now serve hundreds of tax collectors nationwide, and standardised manuals have begun harmonising field practices, reducing variability and administrative inefficiency. The concentration of sixty-five percent of annual spend in direct technical assistance and responsive policy funding reflects disciplined allocation to delivery rather than overhead. Compared with last year’s annual review, where several milestones were “partially met” due to procurement delays and shifting government priorities, the current cycle shows a greater share of milestones delivered or overdelivered, particularly in Output 1 (tax) and Output 4 (investment climate), indicating improved conversion of inputs to outputs without material cost overruns.

Effectiveness: Effectiveness strengthened across policy and systems. In tax administration, the CRM system has enabled early recoveries of PKR 1.2 billion during rollout and is projected to support further recoveries as risk-based case selection matures; the Digital Eye platform achieved ninety-nine point seven per cent accuracy in production monitoring across twenty-seven cement plants, providing reliable compliance data. In the investment climate, the regulatory reform programme submitted five hundred and forty-one reforms for Cabinet Committee consideration, with four hundred and sixty-five ratified for implementation and estimated annual business cost savings exceeding PKR 423 billion (~£1.1m) under the standard cost model. Macroeconomic governance saw the development of a domestic debt analytics prototype, adoption of public asset management guidelines, and institutionalisation of climate, gender and disaster budget tagging across more than forty federal entities, with provincial extension underway. Compared with the last annual review, where Outputs 2 and 3 were rated “B” due to stalled procurements and evolving government asks, the current period evidence substantive progress and institutional uptake in those same areas, while maintaining “A” or stronger performance in tax and investment climate. These changes indicate that outputs are now more consistently translating into outcomes at portfolio level and across counterpart institutions.

Equity: Equity is increasingly embedded as a design and delivery principle. The New Energy Vehicles policy reserves twenty-five per cent of subsidy for women, ensuring direct access to cleaner mobility at scale; early administrative data point to increased women’s participation among business leaders who acted following targeted campaigns. The Women Entrepreneurship Policy advanced through Cabinet submission processes and is positioned to benefit an estimated 3.2 million women led enterprises. Training and digital module handovers in partnership with TDAP have shifted from episodic workshops to sustainable, on platform learning, expanding reach to underserved locations and reducing time and cost barriers for women entrepreneurs. At the fiscal systems level, gender budget tagging provides a durable mechanism for tracking equity relevant spend in the chart of accounts, improving transparency and enabling evidence-based policy adjustments. Relative to last year, equity is now more systematically evidenced in both sector policies and budget architecture, not only in programme delivered trainings.

Assessment of whether the programme continues to represent value for money
On balance, the programme continues to represent strong value for money. Economy is demonstrated through consistent cost discipline and localisation that beats international benchmarks. Efficiency is reflected in the concentration of spend on delivery and in the rising share of milestones achieved across previously constrained outputs. Effectiveness is evidenced by tangible revenue recoveries, institutionalised tools and policies, and estimated economywide savings from regulatory reforms that materially exceed programme costs. Equity has moved from discrete activities to embedded policy and budget tagging, strengthening inclusive outcomes and accountability. The year-on-year comparison with the last annual review shows that earlier delivery frictions have been reduced and that the programme is now converting outputs to outcomes more reliably across pillars. Continued attention to analysis quality assurance, sustainability plans for digital systems, and transparent tracking of programme management cost shares will further enhance the VfM profile. Taken together, the evidence from this year’s progress reports, measured against the guidance in the VFM Smart Guide, supports the conclusion that REMIT’s current trajectory and operating model remain an efficient and cost-effective means of achieving the intended results for Pakistan and the UK taxpayer.

E: RISK

Overview of risk management
The programme risk rating remains Major, unchanged since REMIT’s launch. This reflects systemic vulnerabilities—particularly political economy resistance, reputational sensitivity, and funding uncertainty—that continue to pose material threats to reform momentum and delivery timelines, despite mitigation efforts. These factors largely sit outside REMIT’s direct control, justifying the retention of a Major rating. Risk governance remains robust: a live risk register tracks 11 risks across seven categories, and a risk escalation protocol agreed with partners is applied in quarterly and six-monthly reporting cycles. The British High Commission (BHC) Islamabad holds regular risk discussions with delivery partners. ASI and GCSI provide quarterly risk reports, while the World Bank has responded to last year’s recommendation by adding a dedicated risk section to its six-monthly report. The World Bank should provide more granular, REMIT-specific risk reporting to enable sharper programme-level analysis. [REMIT Programme PRO to ensure this is agreed and implemented by end of Q1 2026]

Political economy risks: Resistance from stakeholders with established positions posed a significant threat to tariff reforms, STPF implementation, and EDF restructuring. Mitigation included aligning reforms with IFI policy loans, close monitoring of the political economy, and sustained high-level advocacy. While these measures maintained momentum, residual risk remains Major, requiring stronger accountability and continued political economy analysis.

Reputational risk: Reputational risk persisted, with FCDO perceived as politically biased. GCSI’s strategic communications and ASI’s tariff policy reforms carried risks of misinterpretation. Mitigation focused on strong BHC oversight, clear technical framing, and strict adherence to REMIT outputs. Residual risk remains Major, requiring ongoing monitoring.

Delivery risk, Loss of institutional knowledge due to frequent civil servant rotations, flagged as Major last year, reduced to Moderate through improved handover processes, clear documentation, robust Terms of Reference, lobbying for continuity of key positions, and steering committee oversight. These measures proved partially effective, but sustainability remains fragile. Capacity gaps and coordination challenges affected programme coherence, with poor cross-government coordination leading to weak implementation and duplication. Regular working groups, a steering committee, and support from SIFC improved delivery, but sustainability remains fragile. Funding uncertainty and ODA cuts, including mid-cycle pauses, impacted timelines and increased pressure. Mitigation included BHC prioritising core activities and regular workplan reviews with partners. ASI built flexibility into its workplan and proposed expanded operational resources. These measures reduced residual risk to Moderate, though systemic vulnerability persists.

Safeguarding risks Global political instability, including the Ukraine war and Middle East crisis, affected programme ambition. Mitigation involved revising the logframe and prioritising stabilisation measures. Residual risk remains Moderate and largely outside programme control.

Recommendations:

While REMIT maintains dynamic risk registers and periodic reviews for monitoring and mitigating risks, further developing escalation protocols would help in future programming, particularly for political economy and reputational risks. Building contingency plans and prioritisation frameworks would safeguard critical activities during budget uncertainty. Enhancing REMIT team resourcing is critical to ensure that technical aspects of the programme are adequately quality assured by the BHC team; this should include additional expertise in trade policy and industrial economics, supported by monitoring and evaluation skills (Lead: BHC Economic Team with REMIT PRO; Timeline: resource plan by end Q2 2026, implementation in Q3–Q4 2026). Additionally, the World Bank should provide more granular, REMIT specific risk reporting to enable sharper programme level analysis, with the REMIT Programme PRO ensuring this is agreed and implemented by the end of Q1 2026.

Update on Partnership Principles

The BHC assessment of commitments made by the GoP are set in four principles of the Partnership Principles Assessment (PPA): (1) reducing poverty and progress towards achieving the Sustainable Development Goals (SDGs), (2) respecting human rights and international obligations, (3) strengthening public financial management and reducing the risk of funds being misused through weak administration or corruption, and (4) strengthening domestic accountability. No changes were made to these principles over the past year. UK ODA to Pakistan remained in line with PPA.

The change of the government in 2024 opened space for reforms, given GoP’s keenness to obtain IMF programme. REMIT has exploited the opportunity and should remain doing so. Shall the reform steam be sustained by the GoP despite political economy, it may stabilise economy and reverse the negative growth trend of recent years. This could in turn contribute to improving Pakistan’s PPA.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

REMIT delivery relies on four implementing partners: ASI, the World Bank, GCSI, and HMRC. Oversight and coordination have been managed through a mix of governance mechanisms, including the Programme Steering Committee, monthly reviews, and structured reporting. This year, collaboration between ASI and the World Bank has been particularly important for maintaining coherence across outputs. The BHC team has played a central role in driving this coordination, supported by sector-focused working groups that have improved communication and alignment. These efforts have contributed to tangible progress, such as tariff reform, demonstrating the value of integrated delivery. However, the level of coordination required continues to place a heavy management load on the BHC team, which remains responsible for technical oversight of ASI outputs, ensuring consistency in policy advice, and providing clarity on funding. While this oversight has ensured high quality outputs, achievement of KPIs, and cost efficiencies through streamlined activities and reduced duplication, the management burden remains significant. Suppliers have demonstrated flexibility in adapting workplans to onground challenges—including shifting political priorities and budget constraints—which has helped maintain delivery momentum. Recommendation: Strengthen reporting systems and embed longer term planning to sustain these gains and reduce the operational load, by instituting a lightweight efficiency and adaptive planning framework (quarterly portfolio review, KPI and quality dashboards, and pre-agreed change control triggers).

On financial management, all partners except HMRC (which is not funded by REMIT) track expenditure against forecasts, with ASI, GCSI, and the World Bank submitting monthly variance reports. Despite previous commitments, the World Bank did not meet the expectation of biannual reporting, providing only one report during the year due to their resource constraints. However, WB is adequately resourced and producing biannual reports. Gender representation in activities is monitored by all partners, but ASI is the only one actively assessing gender impact. A priority for the coming year is to generate evidence on the outcomes of REMIT-supported initiatives—such as the Women Entrepreneurship Policy, training for female exporters, and green taxonomy development—to better understand their impact on women and girls. The table below demonstrates the programme spend during the reporting period and to date across components.

Implementing partner / and status of formal agreement	Actual spent during AR period (£ million)	Programme spent to date / (£ million)
ASI -component numbers 300134-102,105,402 / (commercial contract November 2021 – Feb 2027)	5.18	12.9
Pak@100 Multi-donor World Bank Trust Fund – Component number 300134-103 (Admin Agreement signed in / December 2019	1.891	6.86
BHC managed TA from GCSI- – Component number 300134-104 (MoU)	0.557	0.819
Total	7.62	20.57

Implementing partner / and status of formal agreement	Actual spent during AR period (£ million)	Programme spent to date (£ million)
ASI / (commercial contract November 2021 – Feb 2027)	5.18	12.9
Pak@100 Multi-donor World Bank Trust Fund (Admin Agreement signed in / December 2019	1.891	6.86
BHC managed TA from GCSI (MoU)	0.557	0.819
Total	7.62	20.57

The commercial contract with ASI initially signed for the period covering 2021-2025. However, given the strong buy in from the Government of Pakistan (GoP), the programme itself was extended till March 2028. Therefore, for ensuring the consistency in delivery, the team decided to extend the ASI contract till February 2027. The total spend to date including forecast FY 24/25 is £ 12.9 million, which is 56% spend against the contract value of £ 23 million. The FY 25/26 allocation for ASI is £ £6.5m. ASI managed to maintain an overall variance of spend vs forecast within the range of 5% in the current financial year, but the 8% variance in the first quarter fell outside the threshold of 5%. This was a result of delays in the selection of the firm for the Airport Community Systems due to the complexity of the assignment. With firms having expertise in this area reluctant to work in Pakistan, ASI had to pivot to an alternative strategy resulting in delays and the higher variance. ASI’s relative inexperience in this niche area was mitigated by expertise in other thematic areas and the financial variance remained in line with targets, while also building in learning for delivery partners.

REMIT continued to contribute to the WB Trust Fund Pakistan@100 which started in December 2019. The total spend-to-date including forecast FY 25/26 is £ 6.856 million, which is 86% spend against the Administrative Agreement value of £ 8 million. The FY 25/26 allocation for WBTF is £ 2m. The financial reporting from WB needs some streamlining – WB shares monthly forecast against each output but does not provide activity level granular detail in line with the clauses of the Administrative Arrangement (AA).

The BHC team agreed Phase 2 of the Economic Reforms Communications Support project with GCSI, managed under an MoU for 21 months (Jan 2024–Sep 2025) with a value of £ 746k. The initial GCSI budget of £200k was increased by £74k to accommodate an additional workstream with the Ministry of Finance, resulting in a total budget of £ 820k and extending the delivery timeline to October 2025. The project was delivered with less than 1% budget variance. HMRC technical assistance is provided directly to FBR via a centrally funded MoU, with no cost to REMIT. This arrangement demonstrates high value for money and effective collaboration, delivering better results through coordinated support.

The BHC REMIT team conducts annual asset reviews, and ASI is the only partner that currently holds programme assets. The most recent verification confirmed that all furniture, office equipment, and assets transferred from the SEED and JSSP programme are properly tagged, well maintained, and in good condition, with no issues noted. Some assets transferred from the JSSP programme were assessed as no longer required for operational needs, including a generator, which will be disposed of in line with FCDO’s asset disposal policy.

Recommendations:

FCDO and the World Bank should work together to strengthen risk reporting for REMIT by introducing window-specific risk narratives in biannual and annual submissions. While the current reports provide an overarching view of risks, disaggregating risks by programme window would enable both parties to better understand exposure and mitigation strategies for REMIT. This collaborative approach would improve transparency, support joint risk management, and ensure alignment with FCDO’s framework, ultimately enhancing decision-making and programme resilience.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and evaluation during the review period focused on ensuring REMIT delivery remained aligned with objectives and responsive to emerging risks. Engagement with partners and stakeholders was maintained through quarterly reviews, virtual check-ins, fortnightly financial discussions, and consultations with government counterparts. Beneficiary feedback was captured indirectly through partner reporting and stakeholder workshops, informing adjustments to technical assistance priorities under the Revenue pillar. Although no formal field visits were conducted due to operational constraints, partners provided detailed evidence from in-country engagements to validate progress. ASI’s dedicated M&E team worked closely with FCDO to refine logframe indicators and strengthen data collection, including joint reviews of delivery chain maps and risk registers. The Annual Review drew on inputs from the programme team, FCDO economists, and governance advisers for a balanced assessment.

Evidence quality improved, with greater disaggregation by geography and institutional type, though further alignment with Inclusive Data Charter principles is needed. No major evaluation was completed, but preparatory work for a mid-term evaluation on fiscal impact and sustainability began. Learning was shared through quarterly reflection sessions, highlighting lessons on adaptive programming and risk management. Key gaps include stronger beneficiary engagement and better integration of gender and inclusion metrics. Looking ahead, priorities include commissioning thematic studies on revenue mobilisation, embedding inclusive data practices, and improving feedback loops to ensure evaluation findings inform future decisions. Potential actions include integrating gender-disaggregated indicators into the logframe or the commissioning of gender-focused studies, direct beneficiary constatations.

Date of last narrative financial report	ASI – Oct 2025 / WB – 30 June 2025 / GCSI – 22 Oct 2025	Date of last audited annual statement	ASI – 31 Dec 2025 / WB – 30 June 2025

Annexure A
                                      List of acronyms
Acronym	Meaning
ASI	Adam Smith International
BC	Business Case
BHC	British High Commission
BOI	Board of Investment
CIFPAK	Climate Investment Fund Pakistan programme
PAGs	Partner Across Government
CRM	Compliance Risk Management
DevTracker	Development Tracker
ET & NC	Excise, Taxation and Narcotics Control
FBR	Federal Board of Revenue
FCDO	Foreign, Commonwealth and Development Office
FY	Financial Year
GCSI	Government Communication Service International
GDP	Gross Domestic Product
GST	General Sales Tax
IMF	International Monetary Fund
MEL	Monitoring, Evaluation and Learning
MoC	Ministry of Commerce
MoF	Ministry of Finance
MoU	Memorandum of Understanding
ODA	Official Development Assistance
PPD	Public Private Dialogue
PRMI	Pakistan Regulatory Modernisation Initiative
PSW	Pakistan Single Window
RIA	Regularity Impact Assessment
SMEs	Small Medium Enterprises
SC	Steering Committee
SNG	Sub-National Governance
SRO	Senior Responsible Owner
TDAP	Trade Development Authority of Pakistan
VFM	Value for Money
WBTF	World Bank Trust Fund
ACS	Airport Community System
AI	Artificial Intelligence
AKA	Asaan Karobar Act
AK Act	Asaan Karobar Act
BISP	Benazir Income Support Programme
BRD	Business Requirements Document
CCORR	Cabinet Committee on Regulatory Reforms
CGBT	Climate, Gender & Disaster Budget Tagging
DGTO	Directorate General of Trade Organisations
EFF	Extended Fund Facility
EDF	Export Development Fund
ETAIP	Economic Transformation Agenda and Implementation Plan
HR	Human Resources
IPO	Intellectual Property Organisation
IRIS	Integrated Revenue Information System
KP	Khyber Pakhtunkhwa
LTO	Large Taxpayer Office
NFC	National Finance Commission
NEVP	New Energy Vehicles Policy
NIP	National Industrial Policy
OASIS	Objectives, Audience, Strategy, Implementation, Scoring (Communications Framework)
PAMG	Public Asset Management Guidelines
PKR	Pakistani Rupee
PRAL	Pakistan Revenue Automation Limited
PSDP	Public Sector Development Programme
RSF	Resilience and Sustainability Facility
SIFC	Special Investment Facilitation Council
SMEDA	Small and Medium Enterprises Development Authority
STPF	Strategic Trade Policy Framework
TA	Technical Assistance
TOR	Terms of Reference
TQA	Technical Quality Assurance
UAT	User Acceptance Testing
URAAN	Unified Reform Agenda for Accelerated National Development
VAPT	Vulnerability Assessment and Penetration Testing
WB	World Bank
Wise plc	Wise Public Limited Company (UK-based digital money transfer firm)