## SEED Annual Review 2024-25

Title: Sustainable Energy and Economic Development (SEED) Programme
Programme Value £ (full life): GBP 31.5 million		Review date: 18 July 2025
Programme Code: 300141	AMP start date: 08 October 2018	AMP end date: 07 October 2026

Summary of Programme Performance
Year	2019	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A+	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300141/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-300141/documents / https://iati.fcdo.gov.uk/iati_documents/90000015.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
The Sustainable Energy and Economic Development Programme (SEED) aims to improve provincial economic development, renewable energy, and energy efficiency (RE/EE) in Pakistan over a timeframe of eight years (2018/19 – 2026/27). It supports the province of Khyber Pakhtunkhwa (KP) to plan and finance the infrastructure and investment it needs for growth, jobs, and prosperity. The programme also contributes to addressing Pakistan’s energy crisis by providing innovative financial solutions to small and medium enterprises for the adoption of sustainable energy practices, as well as contributing to the UK’s International Climate Fund (ICF) commitments. The main components of the programme are as follows:
[note] SEED programme got a 1 year no cost extension in May 2024 to allow programme to deliver its commitments on ICF results committed through NRSP-CRCC and ability to fund new activities to improve quality of flood related spend in Sindh and undertake research to support economic reforms at provincial level.

Component 1 to 2: Providing targeted demand-led technical assistance (TA) to help the Government of Khyber Pakhtunkhwa (GoKP) plan, manage and invest its own resources in economic development more effectively. SEED, through Adam Smith International (ASI), is working with key provincial government departments, development partners, and the private sector to increase the level of, and returns to, public and private investments with the aim of supporting economic development. Key features of the TA focus on improving institutional capacity and the investment landscape to facilitate viable investments in the KP region.

Component 3: Enhancing Pakistan’s ability to access international climate finance (ICF) for selected projects. SEED, through National Rural Support Programme, Climate Resource Coordination Cell (NRSP-CRCC), provides targeted TA to concepts and projects nationally to help Pakistan access national and international financing for addressing and mitigating climate change challenges in Pakistan.

Component 4: Support to World Bank (WB) under the Monitoring, Evaluating and Following the Flow of Funds for Reconstruction (ME3F) - Pakistan@100 Administrative Arrangement (AA). SEED has signed an agreement with WB to have an umbrella trust fund under which an independent monitoring and evaluation process is set up to understand the impacts of the 2022 flood on communities and households and improve the quality of public spending for rehabilitating the affected population.

Summary supporting narrative for the overall score in this review:

The SEED programme has received an overall score of ‘A’, showing strong performance across all outputs despite working in a challenging environment. It met all its planned goals, especially in areas like improving government systems, attracting investment, and supporting climate-related finance.
Output 1 received an A+ because it went beyond agreed milestones. SEED helped the Government of Khyber Pakhtunkhwa (GoKP) put its Public-Private Partnership (PPP) system into action. This included the provincial cabinet approving key rules and setting up 16 dedicated units within different government departments, with the responsibility for managing Public-Private Partnership (PPP) projects. Fifty government officers were trained in PPP frameworks, and 23 earned international certification. SEED helped bring in USD 227.5 million (GBP 169.62 million) in private investment, slightly above the target. It also supported two major investment projects and prepared documentation for three more. A major success was helping register five hydropower plants for International Renewable Energy Certificates (I-RECs), which shall enable GoKP to unlock USD 34 million in long-term climate funding.
[note] I-RECs (International Renewable Energy Certificates) are tradable instruments that certify 1 MWh of electricity was produced from renewable sources and injected into the grid. They help organizations globally track and report renewable energy usage, especially where no local certification systems exist.
Output 2 received an A. SEED improved how public money is invested in KP. A key score measuring investment efficiency rose from 4.11 to 4.78, thanks to better planning and monitoring. A new road management system now covers 71% of KP’s roads and could save USD 24.6 million (GBP 19.96 million) each year, giving a strong return on SEED’s investment. SEED also helped ensure that all 59,544 newly hired civil servants joined a modern pension scheme. Older pension reforms are already saving PKR 13 billion annually, with total savings of PKR 39 billion (GBP 105.3 million) so far and PKR 148 billion (GBP 399.60 million) expected over 11 years. These savings allow the government to spend more on public services and infrastructure.
Output 3 scored a B, meaning it underperformed slightly on account of an unforeseen delay. This was mainly due to finalising an agreement for a climate project funded by the Green Climate Fund (GCF). Still, SEED achieved important goals, including approval of GBP 36.5 million for the Climaventures initiative and submitting two more project ideas. The partner organisation, NRSP-CRCC, hired 10 new staff and made progress on climate finance work. The score reflects that SEED kept moving forward despite delays caused by external checks on the fund manager.
Output 4 received an A, with all milestones achieved under the Monitoring, Evaluating and Following the Flow of Funds for Reconstruction (ME3F) initiative. SEED signed an agreement with the World Bank, finalised its results plan, selected firms, and began key surveys and audits. The programme is now collecting data to guide fair and transparent spending on reconstruction. Due to slow mobilisation, the 0.3% allocation, and portfolio streamlining, a reduction in ME3F disbursements is recommended.

Overall, SEED continues to deliver well, adapt to challenges, and make a real impact on institutions. Its success in attracting investment, driving reforms, and staying on track in a tough environment supports its overall A rating.

Major lessons and recommendations for the year ahead

Lessons Learned:
Institutional embedding is critical for sustainability: SEED’s success in operationalising the Public-Private Partnership (PPP) framework and RAMS demonstrates that embedding reforms within government systems through staffing, training, and ownership transfer is essential for long-term sustainability. However, the uneven uptake of tools such as modular designs and the Public Investment Management (PIM) Portal highlights the need for deeper institutional buy-in and continued capacity building.

Political economy dynamics shape reform trajectories: The Political Economy Analysis (PEA) matrix underscores how political transitions, leadership changes, and bureaucratic inertia can delay or derail reform momentum. SEED’s adaptive engagement strategy working across tiers of government and maintaining strong mid-level relationships has proven effective in mitigating these disruptions.

Value for Money (VfM) is strongest when interventions are targeted and demand-driven: The VfM assessment indicates high returns on investment in PPP transactions, PIM tools, and pension reforms. Interventions that align with government priorities and deliver tangible fiscal or investment outcomes such as AI-enabled tools for improved service-delivery, certifications for civil service employees, and pension savings yield the greatest impact.

Risk Management must be proactive, iterative, and complete: The programme partner’s risk register revealed that many risks particularly those related to political shifts, fiscal constraints, and institutional capacity are recurring. SEED’s structured mitigation strategies, including embedding, phased implementation, and stakeholder mapping, have helped reduce residual risk. However, continued vigilance and adaptive risk management remain essential. Furthermore, political instability and national-level economic volatility have significantly affected the provincial investment climate. A complete systems-level analysis of risk can ensure programme delivery was responsive to these broader contextual dynamics.

Designing for sustainability from the outset is essential. SEED’s experience reinforces that investment efficiency should be treated as a routine practice, not an exception.

Evidence-driven adaptation outperforms fixed delivery. Monitoring dashboards, revised VfM frameworks, and field observations enabled real-time adjustments that protected delivery timelines and improved targeting.

Recommendations:

Strengthen institutional capacity and governance: ASI should support the Energy Department in recruiting and selecting specialist staff to ensure that registered I-RECs can be translated into investment opportunities. This is particularly important after the conclusion of ASI support under the SEED programme to ensure long-term sustainability.

1. Clarify and codify Khyber Pakhtunkhwa Electric Power Regulatory Authority’s (KPEPRA) jurisdiction to avoid regulatory overlap: ASI should assist the GoKP in finalising a jurisdictional framework for KPEPRA that clearly defines its scope in line with the Constitution and NEPRA’s Act, to reduce legal ambiguity and mitigate litigation risks. The framework should address intra-provincial licensing for off-grid and embedded generation, establish KPEPRA’s advisory role on provincial tariffs (excluding tariff-setting), and ensure grid code compliance for provincial transmission infrastructure.
2. Embed RAMS into the budgeting process: Amend the PC-I template, and appraisal guidelines used by the Planning and Development (P&D) Department to require the Communication & Works (C&W) Department to submit RAMS-based maintenance priority lists with each road project proposal. These should include road condition scores, estimated cost of deferred maintenance and Highway Development and Management Model Version 4 (HDM-4) based cost-benefit ratios.

Convert the utility of the PIM portal and RAMS into enhanced transparency: Encourage Government of KP to publish RAMS-based road condition maps and prioritisation lists on the PIM portal. This will enable citizens and the media to better understand how and why public funds are allocated to specific road projects.

Close high-risk transactions with clear exit strategies: For transactions unlikely to reach financial close within SEED’s timeframe, develop clear handover plans with timelines and documentation to enable the GoKP or other partners to take them forward.

To consolidate VfM gains achieved through NRSP-CRCC’s transition: To keep the cost savings from NRSP-CRCC’s shift to doing work in-house, it’s important to keep training local staff and helping them learn from global climate finance practices.

Finalise procurement for fund manager services by Q2 2025–26: NRSP-CRCC should provide a clear timeline for onboarding a fund manager for Climaventure to ensure the timely operationalisation of the fund.

It is recommended that NRSP-CRCC strengthen its programme delivery through improved internal coordination, regular progress reviews, and enhanced mitigation strategies to ensure timely execution of project milestones and completion of key decision gates.

Devise a post-exit sustainability strategy for NRSP-CRCC: NRSP-CRCC should develop and share an organisational sustainability strategy by the end of Q2 2025–26 to ensure continuity of its functions post-SEED.

List of Acronyms
AA	Administrative Arrangement
AMP	Aid Management Platform
APMG	Association of Project Management Group
ASI	Adam Smith International
BHC	British High Commission
BOS	Budget Optimization System
CP3P	Certified Public-Private Partnerships Professional
C&W	Communication & Works Department
CDEL	Capital Departmental Expenditure Limit
CRCC	Climate Resource Coordination Cell
CRI	Climate Resilient Infrastructure
DCS	Defined Contribution Scheme
FAA	Funded Activity Agreement
FCDO	Foreign, Commonwealth & Development Office
GCF	Green Climate Fund
GESI	Gender and Social Inclusion
GHGE	Greenhouse Gas Emissions
GoKP	Government of Khyber Pakhtunkhwa
HDM-4	Highway Development and Management Model Version 4
ICF	International Climate Fund
IKI	International Climate Initiative
IP	Implementing Partner
ITZ	Integrated Tourism Zone
JV	Joint Venture
KPEPRA	Khyber Pakhtunkhwa Electric Power Regulatory Authority
MEL	Monitoring, Evaluation, and Learning
ME3F	Monitoring, Evaluating and Following the Flow of Funds for Reconstruction
MPHS	Multipurpose Household Survey
NEPRA	National Electric Power Regulatory Authority
NGO	Non-Governmental Organization
NRSP	National Rural Support Programme
NRSP-CRCC	National Rural Support Programme – Climate Resource Coordination Cell
OANDA	Currency exchange platform used for conversion rates
PC-I	Planning Commission Form I
PDA	Peshawar Development Authority
PEA	Political Economy Analysis
PETS	Public Expenditure Tracking Survey
PFM	Public Financial Management
PIMA	Public Investment Management Assessment
PIM	Public Investment Management
PPP	Public-Private Partnership
RAMS	Road Asset Management System
REMIT	Renewable Energy Market Integration and Transformation
RDEL	Resource Departmental Expenditure Limit
RFP	Request for Proposals
RMU	Risk Management Unit
SEAH	Sexual Exploitation, Abuse and Harassment
SEED	Sustainable Energy and Economic Development
SNG-II	Sub-National Governance Programme II
TA	Technical Assistance
ToC	Theory of Change
TORs	Terms of Reference
UK	United Kingdom
UNEP	United Nations Environment Programme
UPSCALE	Likely a successor programme; full form not defined in document
VfM	Value for Money
WB	World Bank

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The SEED programme’s Theory of Change (ToC) is built on the premise that improving institutional capacity, public investment efficiency, and enabling conditions for private investment, particularly in climate-resilient infrastructure will lead to increased public and private investment in KP, ultimately contributing to inclusive economic growth and improved service delivery.

The ToC logic remains valid and has held up well against implementation experience. The programme’s dual focus on (1) strengthening public investment management (PIM) systems and fiscal space, and (2) mobilising private and climate finance through policy reform and transaction support, has proven effective. This is evidenced by exceeding of key outcome indicators: a Public Investment Management Assessment (PIMA) score improvement from 4.1 to 4.78, and full enrolment of new civil servants in the Defined Contribution Scheme (DCS).

While the core outcomes and impact indicators have remained consistent with the original business case, targets were revised upward in 2023 to reflect SEED’s strong performance in the previous year. These adjustments were appropriate and aligned with the programme’s evolving capacity and contextual shifts.

Implementation experience has reinforced the ToC’s assumptions, particularly the importance of political buy-in, mid-tier bureaucratic engagement, and flexible, adaptive programming. However, challenges such as uneven uptake of PIM tools, delays in pension account activation, and limited cross-departmental coordination highlight the need for continued institutional embedding and ownership beyond SEED’s exit.

No new evidence fundamentally challenges the programme design. Instead, the experience has validated the integrated approach of combining upstream policy reform with downstream transaction support and capacity building. The ToC remains a robust framework for achieving SEED’s intended impact.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The SEED programme remains firmly on track to achieve its expected outcomes and impact by the revised end date of October 2026, with all output and outcome indicators either achieved or overachieved. For the period under review, SEED has achieved targets for all outcome indicators. On facilitating additional investment as a direct result of urban and economic development TA in KP, SEED facilitated USD 227.5 million in private investment (exceeding the revised USD 225 million target). On mobilising private finance for climate change purposes, SEED has mobilised USD 38.2 million (GBP 28.48 million) in private climate finance over-achieving the target of $22.5 million.
In the near-term, SEED’s work will benefit 208,980 citizens (117,980 rural and 91,000 urban). Communication & Works Department (C&W) is committed to secure funds for the remaining three out of ten projects on priority basis and then the overall beneficiaries will likely reach 224,480 citizens (Rural 133,480 and Urban 91,000).

On investment efficiency, PIMA score has increased from 4.1 to 4.78. This increase in PIMA scores is primarily attributable to various tools created which aim to directly and indirectly provide efficiencies in the way at least £500mn worth of provincial annual development plan is designed and executed – improving the quality of public development spend. Fiscal space has been expanded through full enrolment of over 52,000 new civil servants in the DCS.

The programme’s outputs are demonstrably contributing to intended outcomes. For instance, the operationalisation of the PPP framework and the launch of high-value transactions (e.g. Nowshera mega city, ITZs, PDA Blue Area) are directly linked to increased private investment. Similarly, the institutionalisation of PIM tools and the deployment of RAMS are enhancing public investment efficiency. However, while impact-level indicators such as provincial growth and employment remain below target, this is largely due to macroeconomic and security challenges beyond SEED’s control.

In the year ahead, SEED will focus on completing procurement for priority transactions, embedding PIM tools within the RAMS unit, finalising the pension audit, and handing over digital platforms to GoKP departments. NRSP-CRCC, as a key SEED component, has also made significant progress, mobilising GBP18.25 million from GCF for Climaventures and submitting nine additional proposals to global climate finance entities. These efforts reinforce the programme’s climate finance mobilisation objective and institutional sustainability.
[note] RAMS (Road Asset Management System) is Pakistan’s first AI-powered tool that helps monitor road conditions, plan maintenance, and manage budgets more effectively. It uses real-time data, smart analysis, and global software to improve how roads are maintained and funded.

Given current progress, the outcomes and impact are most likely to be achieved within the revised budget and timeline. No significant negative deviations have been observed in gender or inclusion outcomes; in fact, SEED has integrated Gender and Social Inclusion (GESI) considerations across interventions. Continued adaptive management and strong counterpart engagement remain critical to sustaining momentum and ensuring long-term impact.

SEED is on-track to deliver on its intended outcome, “Higher private and public investment and improved public investment efficiency” however, the relationship between the outcome and impact requires further investigation. Latest figure for provincial growth rate is from July 2024, where it fell short of target at 2.9% (target 4.1%). The target for % increase in average household income was 6.6% however latest figures are from 2019. In the absence of any evaluation conducted to assess these statistics, it is difficult to make an informed assessment on how effectively the programme’s outcome has translated into the desired impact.
Outcome Indicator	Target (June 2025)	Progress
Additional investment facilitated (US$m) as a direct result of economic and urban development TA in KP	$ 225m (cumulative) investment facilitated. / KPI1 12: Investment facilitated for at least $22.5m of private finance disaggregated by climate theme (i.e., adaptation / mitigation / both) / KPI-1. 133,000 individuals in rural areas and 91,000 individuals in urban areas supported to better adapt to the effects of climate change as a result of ICF.	Facilitated USD 227.5 million in private investment. / USD 38.2 million (GBP 28.48 million) mobilised in private climate finance. / 117,980 citizens in rural areas, and 91,000 urban citizens are expected to benefit from the 7 projects that have secured funding for FY 2026.
Effectiveness of PIM system in KP (PIMA)	4.70	4.78
Increase in fiscal space (PKR Billion)	100% of new employees subscribe to contributory pension scheme. Savings from legacy pension reforms remain on-track.	Achieved

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
The SEED programme has demonstrated strong performance and strategic relevance, justifying its continuation both on its own merits and within the broader FCDO portfolio. It has consistently delivered high-impact results in a challenging political and economic context, including facilitating over USD 227.5 million in private investment and achieving significant fiscal savings through pioneering pension reforms in Khyber Pakhtunkhwa. SEED’s adaptive approach, evident in its pivot to climate resilience post-2022 floods and its support for Pakistan’s access to international climate finance aligns with FCDO’s priorities on climate action, economic stability, and locally led development. The programme’s support to NRSP-CRCC has already mobilised GBP 18.25 million (out of GBP 36.5 million of total funding secured) from the Green Climate Fund and built a pipeline of climate finance proposals. Moreover, SEED’s integration of gender, disability, and climate considerations into public investment planning, and its institutional capacity-building across provincial departments, ensures sustainability and value for money. In the context of FCDO’s wider development objectives in Pakistan, particularly subnational economic growth, climate resilience, and governance reform. SEED remains a flagship programme with catalytic potential. Continuous support to programme partners will consolidate gains, enable delivery of climate finance outcomes already in motion, and inform the design of successor programming, making it a prudent and strategic investment.

## C. DETAILED OUTPUT SCORING

Output Title	Improved institutional capacity and better policy outcomes to attract investment and a viable investment pipeline, including climate finance
Output number:		01	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR.	No change

Indicator(s)	Milestone(s) for this review	Progress
Output 1.1 / Policy reforms and institutional support to attract private investments	Approval of Risk Management Unit (RMU) Guidelines (the last instrument in KP’s regulatory framework) / PPP Unit is fully staffed, PC-I for PPP Support Unit approved by PDWP and being implemented	Exceeded: / The RMU Guidelines have been approved by the PPP Committee. In addition, the Aasan Karobar Bill has been approved by the Cabinet and introduced in the KP Assembly for enabling business environment. / Achieved: / PPP Unit is currently fully operational and staffed with five permanent government officials. PC-1 for the PPP Support Unit has been approved by the PDWP, and its implementation is in progress.

Indicator(s)	Milestone(s) for this review	Progress
Output 1.1 / Policy reforms and institutional support to attract private investments	PPP Nodes notified in at least 6 departments, with regular meetings of PPP Nodes, PPP Unit and PPP Committee (30+ cumulative meetings since the start of program, including 10 meetings within 2023-24) / 45 middle-to-senior officers trained in PPP regime across 12 departments, with at least 10 enrolled in Certified Public-Private Partnerships Professional (CP3P) Foundation module.	Exceeded: / 16 PPP Nodes have been notified, with 54 meetings held by the PPP Nodes, Committee, and Unit (including 15 meetings held this year). / Exceeded: / 50 officers have been trained and 23 certified in CP3P foundation module.
Output 1.2 / Viable investment pipeline	Procurement initiated for at least 2 transactions (leading to contract award stage) / Documentation (or design) complete for 2 additional investment transactions or instruments / Carbon market project inventory for at least one sector finalized and being reviewed	Achieved: / SEED has initiated work on the procurement package for 2 transactions – Integrated Tourism Zones (ITZs) Thandiani and Ganool. / Achieved: / The procurement package is complete for 2 additional investment transactions (ITZ Mankiyal and PDA Blue Area). Transaction structure complete for Daraban Economic Zone. / Exceeded: / Carbon market project inventories have been finalised and approved for both the forests and renewable energy sectors.

Briefly describe the output’s activities and provide supporting narrative for the score.
During the reporting period, Output 1 delivered strong performance and remains on track to meet end-of-programme targets. SEED supported the GoKP in operationalising its PPP framework, including the approval of the final regulatory instrument (RMU Guidelines), notification of 16 PPP Nodes, and training of 50 officers, 23 of whom received CP3P certification. These institutional reforms have laid the groundwork for sustainable private investment mobilisation.

On the pipeline side, SEED advanced several high-value transactions. Procurement was initiated for ITZ Thandiani and Ganool, while documentation was completed for ITZ Mankiyal, Peshawar Development Authority (PDA) Blue Area Development, and Daraban Economic Zone. The Nowshera mega city transaction was concluded and ground-breaking is scheduled for July. SEED also facilitated a partnership between Pakhtunkhwa Energy Development Organization and Pakistan Environment Trust (PET) to register five hydropower plants for I-RECs, unlocking long-term climate finance. Additionally, carbon market inventories for both forest and renewable energy sectors were finalised and approved.

Cumulatively, SEED has facilitated USD 227.5 million in private investment, exceeding the revised target of USD 225 million. All Output 1 milestones were either achieved or exceeded. This including those related to climate finance and pipeline development.
[note] $143 million Swat Motorway 2, $50.30 million Nowshera Mega City, and $34.2 million worth of I-RECs for five hydro-power projects.

While the output initially faced some risks such as weak investor interest in certain tourism zones and delays due to land disputes, these were actively mitigated through legal due diligence, stakeholder engagement, and investor outreach. Overall, Output 1 is firmly on track and merits the ‘A+’ score, reflecting that it met expectations in full.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
During the past year, Output 1.1 was revised to reflect key support for the operationalisation of the PPP framework, with progress evidenced through staffing, regulatory approvals, and training. No major changes are planned as commercial contract with ASI is coming to a close in Oct 2025.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
With just a little over a year left of economic and investment facilitation related TA being delivered in KP, partners need to double down on their efforts to ensure sustainability of their investments and reforms work and either successfully close or hand over their investment facilitation work for selected projects. Where new projects are considered, this should be in tandem with a sustainability plan. Sustainability plans should focus on maximizing delivery against closing investment deals successfully, narrowing their focus where necessary to ensure deliverables are achieved. Interventions that may run beyond the contract end date need to be handed over to suitable partners to take forward	Completed: ASI revised and submitted a sustainability plan covering the investment portfolio, as well as other program initiatives in December 2024.
Significant focus and flexibility are needed to mitigate the risk that the uncertain political and macroeconomic context will negatively impact on achieving the programme’s objectives. Given the continuing uncertainty in the political and macroeconomic context, the programme should maintain its flexibility and focus on risk mitigation.	Completed: To maintain flexibility, ASI team revised and submitted its annual workplan and investment pipeline in November 2024. On risk mitigation, the team updated its risk register on quarterly basis to ensure its alignment with Outpu1 milestones. The ASI team continues to regularly scan for new risks on quarterly basis and reassess existing risks, in line with FCDO guidance on risk management.
Implementing partner (IP) to increase effort and put in adequate resources to bring the investment facilitation work, including projects with climate focus, back on track to deliver the targets missed in FY23/24. IP to provide monthly progress updates to FCDO.	Completed: The ASI team presented a robust stocktake on investment portfolio in November 2024 and agreed with FCDO on the way forward. The team was restructured with additional resources brought to bear on Output-1 targets, particularly those categorized as 'high-priority' transactions, which have considerably advanced since then. The ASI team continues to share quarterly updates to FCDO on investment mobilization progress.
In the coming year, the SEED programme should continue to engage with all Secretaries (most senior civil servants) of the GoKP to offer upskilling in PPP projects. The different secretaries have varying knowledge on PPP projects, which will affect the number of projects coming forward from different departments, disadvantaging those with less awareness/expertise. The programme should engage with these departments to ensure that there is a legacy of expertise and capacity relating to PPPs, enabling the investment landscape to improve across different sectors.	Completed: SEED provided PPP training to P&D officials and other prioritized departments (PPP nodes) under a PPP Capacity Building Plan, approved by P&D. Under this Plan, SEED has trained 50 individuals, including Special Secretaries, Chiefs of Sections, Chief Planning Officers, and other senior officials. The Association of Project Management Group (APMG) offers a globally recognized certification program for Certified Public Private Partnership Professionals (CP3P). This year, ASI has supported 23 trained officials to receive this global certification.

Overall, the recommendations from the last year have been met.

Key Lessons and Recommendations from this year:

Adaptive programming and visible government ownership have proven critical in catalysing private investment. SEED’s strategic pivot away from slower-moving transactions and its support for GoKP-led investor roadshows have significantly enhanced market confidence.

Tailored engagement strategies are more effective than broad-based forums. One-on-one consultations with departments advanced regulatory reforms more efficiently than multi-agency platforms, highlighting the importance of customised approaches.

The long-term viability of the PPP pipeline and identify mechanisms for post-SEED transaction support, ensuring continuity and sustainability of investment facilitation efforts will be a key lesson for the successor of the SEED programme.

Output Title	Improved PIM practices, especially for climate-resilient infrastructure, and policy/institutional reforms to increase fiscal space
Output number:		02	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR.	No change

Indicator(s)	Milestone(s) for this review	Progress
Output 2.1 / PIM practices developed/improved and embedded	Design and deployment of RAMS and inauguration of Bridge Code / Government officials trained in PIM tools through 6 workshops within the year (approximately each with 50 participants) / Fully functional PIM portal designed and deployed (with access to all tools and relevant material)	Achieved: / The Road Asset Management System (RAMS) has been designed and deployed, while the Bridge Code has been inaugurated by the Chief Minister, KP. / Achieved: A total of 7 workshops on PIM tools have been held during the programme year, with over 300 trainees from the C&W Department and PDA. / Achieved: / The PIM Portal has been fully developed and is now accessible at https://md.cwd.gkp.pk/.
Output 2.2 / Policy reforms and institutional support to create fiscal space	Four DCS Implementation Roadmap meetings held during the year with meaningful progress / External pension review initiated, and initial findings presented to Finance Department	Achieved: / Five meetings have taken place. A total of 52,000 employees is now enrolled in the new pension scheme, with an estimated 19,300 accounts opened. / Achieved: / The external pension review was concluded with both initial and final findings shared with the Finance Department.

Briefly describe the output’s activities and provide supporting narrative for the score.
During the reporting period, Output 2 delivered a strong set of results aligned with expectations. SEED successfully embedded and operationalised key PIM tools, including the launch of the RAMS and the formal adoption of the KP Bridge Design Code. RAMS is now fully functional, with a dedicated unit established in the C&W Department, and inventory data from six districts uploaded. The system is expected to significantly improve the efficiency of road maintenance and investment planning. Seven PIM training workshops were conducted, reaching over 300 government engineers and planners, and the PIM portal will provide centralised access to all tools and guidance materials.

On fiscal space, SEED supported the implementation of the DCS for civil service pensions. All 59,544 new recruits since June 2022 have been enrolled under the scheme, and five roadmap meetings were held to track progress. SEED also facilitated an external pension review, with findings submitted to the Finance Department to inform further improvements. These reforms are already generating fiscal savings, with PKR 13 billion (GBP 33.93 million) annually made available through legacy pension reforms. The programme also ensured sustainability by institutionalising digital platforms and embedding reforms within government systems.
[note] These reforms have resulted in cumulative savings of PKR 39 billion.

Given the full achievement of all Output 2 milestones, the output has met expectations and merits an ‘A’ score.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output 2.1 and 2.2 saw refinements during the past year to better reflect progress on infrastructure and fiscal reforms. Output 2.1 shifted focus from the notification of PIM tools to their practical deployment, including RAMS, Bridge Code, and the PIM portal, alongside extensive training. Output 2.2 was updated to reflect progress on pension reform through DCS roadmap meetings and an external review. As a result of this review, no major changes are planned, but emphasis will be placed on sustaining reforms, improving tracking mechanisms, and ensuring institutional ownership post-SEED exit.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
The wide scope and impact of the pension reforms necessitates a thorough communications plan covering both new civil servants, officials still on the legacy system, and the wider public to avoid misinformation and ensure transparency. A Strategic Communication Plan has been prepared and submitted to the Finance Department and is expected to be approved shortly. This should consider long term communication plans for each stage of reform.	Completed; The Strategic Communication Plan submitted to the Finance Department last year has been approved. Additionally, to further support the department and based on initial findings from the ongoing external review of the DCS, The ASI team developed a simplified communications plan for the department. The plan has also been included in the overall DCS implementation roadmap. The Finance Department is now implementing the plan with ASI’s team support.
IP and Implementing partner to have regular meetings with KP Planning and Development Department working alongside other concerned departments to track progress on number of people who have benefited from projects aimed at reducing the negative consequences of climate change. The target for FY24/25 should also be revised upwards in line with the additional beneficiaries identified as part of the project development.	Completed: The ASI team prepared a datasheet with estimated number of individuals who have (or will potentially) benefited from SEED's interventions on climate change. This was shared with FCDO in December 2024.
A fresh Public Investment Management Assessment needs to be undertaken to verify increase in PIMA scores and assess sustainability of reforms undertaken including flagging any risks and mitigation to avert reversal after SEED funding has concluded.	Completed: ASI initially planned to organize an external PIMA Assessment in April 2025. However, SNG-II was also conducting a Climate-PIMA or C-PIMA for GoKP at the same time. In line with FCDO steer, ASI team coordinated with SNG to ensure that the methodology was compatible with the one used by SEED and is now revising this assessment to reflect recent SEED milestones (including the RAMS). The report was completed by end-June 2025.
Capacity building material should be developed for all project levels of delivery. Lessons learned over the past programme year include providing sufficient support for the officials delivering the project at all tiers. For example, producing a capacity-building manual on Climate Resilient Infrastructure to be used by field engineers will support the development of the projects. This emphasis should be continued going forward to ensure sustainability of the reforms introduced.	Completed: ASI team has been regularly training C&W officials to deepen understanding and encourage use for PIM tools developed with ASI support. ASI has also developed a CRI Handbook to document best practices for developing climate-resilient infrastructure, which has already been approved by C&W Department. ASI will continue to prioritize capacity building as a cross-cutting theme, for all its interventions.

Overall, the recommendations from the last year have been met.

Key Lessons and Recommendations from this year:

- Designing for sustainability from the outset is essential. SEED’s experience reinforces that investment efficiency should be treated as a routine practice, not an exception.
- Tools such as RAMS and the Climate Resilient Infrastructure (CRI) Handbook have demonstrated the potential to shift infrastructure planning from ad-hoc decisions to systematised, lifecycle-based approaches.
- Achieving allocative efficiency, ensuring funds are directed to the right priorities requires deeper engagement with budget-setting processes and a strong understanding of political economy dynamics.
Output Title	BHC Managed Technical Assistance for Economic and Urban Development
Output number:		03	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR.	Yes, increased from 15% to 25%

Indicator(s)	Milestone(s) for this review	Progress
Output 3.1 / High quality climate focused engagement on economic and urban development nationally or in other provinces.	One funding proposal approved by the GCF. / Funded Activity Agreement (FAA) for the approved project signed / Up to two additional concept notes submitted to national and international financing entities.	Achieved: / Funding proposal approved by the GCF Board at the 40th Board Meeting. / Not Achieved: / In order to meet the legal requirements of the FAA, an extension of the deadline has been sent to GCF / Achieved: / Two concept notes have been submitted to International Climate Initiative, and Welcome Trust, with a project size of GBP 1.4 million each. Additionally, two concept notes are in different stages of development.
[note] GCF funding $ 25 million (GBP 18.25) also meets ICF KPI-11: Volume of public finance mobilised for climate change purposes as a result of ICF

Briefly describe the output’s activities and provide supporting narrative for the score.
During the reporting period, Output 3 made progress in strengthening NRSP-CRCC’s internal capacity to support its expanding climate finance portfolio. Ten new professionals were recruited across technical, GHGE, finance, communications, and M&E roles, and a comprehensive orientation and training programme was delivered to integrate these staff. These efforts have enhanced the organisation’s operational readiness and institutional maturity.

However, the output fell short of expectations due to delays in finalising the FAA for the GBP 36.5 million Climaventures initiative, which was approved by the GCF. Following the signing of an FAA with GCF, it typically takes an additional six months to make it effective due to legal arrangements such as subsidiary agreements, due diligence, bank account setup, and fund establishment. By conducting due diligence on the proposed fund manager ahead of signing, NRSP-CRCC has demonstrated strong risk management and proactively initiated fundraising efforts to support timely and smooth implementation. While NRSP-CRCC has submitted two additional concept notes and continues to develop a pipeline of proposals, while a key milestone was not met within the review period, these ongoing efforts reflect a clear commitment to progress and future performance.

During the reporting period $ 25 million (GBP 18.25 million) public finance has been mobilised for Climaventures which is contributing to ICF KPI 11: Volume of public finance mobilised for climate change purposes as a result of ICF

The score of ‘B’ reflects this moderate underperformance, while acknowledging that the delay in FAA signing was due to reasons beyond CRCC’

Describe any changes to this output during the past year, and any planned changes as a result of this review.
A no-cost extension was approved for NRSP-CRCC in Sept 2024. The approval is aimed at extending the current contract date for a further 19 months to achieve the intended results committed at the stage of signing the original Accountable Grant Agreement (AGA). The extension aligns with the already-approved no cost extension of SEED Business Case.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
NRSP-CRCC should complete current projects to ensure sustainability. NRSP-CRCC’s sustainability will depend on its perceived success in obtaining climate finance for its partners. Therefore, it should aim to bring bids to advanced stage as soon as possible given that the programme has now been extended to allow for this process to be wrapped up.	Completed: Of NRSP-CRCC’s various initiatives, Climaventures has successfully mobilised GBP 18.25 million of its total value of GBP 36.5 million, from GCF. Meanwhile the legal and other requirements are underway for the Funded Activity Agreement (FAA) signing, thus, ensuring NRSP-CRCC’s sustainability. / At the same time, various other initiatives are also being developed for direct climate finance mobilisation, with greater efficiency for time spent given NRSP-CRCC has developed its own expertise as well.

Overall, the recommendations from the last year have been met.
Key Lessons and Recommendations from this year:

Embedding flexibility and resilience in programme design is essential. NRSP-CRCC’s experience navigating delays caused by external due diligence processes highlights the importance of developing comprehensive risk registers and mitigation strategies that can adapt to unforeseen challenges.

The shift from ideation to implementation evidenced by the successful approval of the GBP 36.5 million Climaventures initiative and progress on Battery Swapping Stations, Early Warning Systems, and DairEase demonstrates the value of strong internal capacity and operational systems.

NRSP-CRCC’s ability to maintain momentum despite external delays reflects growing institutional maturity and adaptability, which are critical for long-term sustainability.

Output Title	Support to WB under the Monitoring, Evaluating and Following the Flow of Funds for Reconstruction (ME3F) - Pakistan@100
Output number:		04	Output score:	A
Impact weighting (%):		5%	Impact weighting (%):	5%

Indicator(s)	Milestone(s) for this review	Progress
Output 4.1 / Support to WB under the Monitoring, Evaluating and Following the Flow of Funds for Reconstruction (ME3F) - Pakistan@100	Administrative Amendment signed between FCDO and WB. / The result framework ME3F for has been updated and two components have been finalized. / Firms hired for MPHS in Sindh & RFP for Infrastructure Audit survey has been completed.	Achieved: / Administrative Amendment 08 signed for ME3F on 25 November 2024. / Achieved: / World bank shared updated result framework with FCDO. / Achieved: / The MPHS contract for Sindh was awarded to two firms. The Request for Proposals (RFP) closed at the end of June for the Infra Audit Survey.

Briefly describe the output’s activities and provide supporting narrative for the score.
Administrative Amendment No. 8 under the Pakistan@100 TF umbrella was signed with the WB on 25 November 2024, with a total value of GBP 4.19 million. This amount scheduled to be transferred in three tranches, with the first tranche of GBP 1.3 million was disbursed in February 2025. This was in line with the results framework, developed in close coordination with the WB, which was structured around two core components. The first focused on building evidence around the equity and transparency of reconstruction spending. This includes the Multipurpose Household Survey (MPHS), the Public Expenditure Tracking Survey (PETS), and a comprehensive infrastructure audit. The second component emphasizes community engagement and capacity building, aiming to enhance citizen participation, build community resilience, and ensure that findings are widely disseminated to civil society, NGOs, media, policymakers, and academic institutions.

For the MPHS, the WB has contracted two firms to carry out the survey in Sindh province. These firms are currently finalizing the design and programming of listing and village survey questionnaires. Fieldwork has commenced, beginning with pilot testing of the instruments. The Infrastructure Audit, which will assess reconstruction efforts in housing and farm-to-market roads, is progressing well. Following the completion of the Expression of Interest (EOI) process in January, the Request for Proposals (RFP) was issued. A total of 06 firms our of 12 were finalised. WB is awaiting disbursement under tranche no. 2 to finalise the procurement. Activities under Component 2 will be designed and implemented once the findings from Component 1 are available.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There have been no changes to the overall scope of this output. The only modification pertains to its repositioning within the SEED logframe from Output 5 to Output 4, following the closure of the previous Output 4 (Karandaaz Pakistan).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

 The previous AR recommendation has been achieved, and the detail are:

Recommendations	Progress
SEED team to work closely with WB project team to finalise the results framework and financing/disbursement strategy by 30 September to ensure robust implementation and review of the activities.	Completed: The result framework has been finalized in close coordination with world bank. The updated results framework, developed with the World Bank, includes two components: (1) building evidence on the equity and transparency of reconstruction spending through MPHS, PETS, and infrastructure audits; and (2) strengthening community engagement and capacity by promoting citizen participation, resilience, and broad dissemination of findings to civil society, media, policymakers, and academia. / AA No. 8, totalling GBP 4.19 million, was signed with the World Bank on 25 November 2024. The funds are to be released in three tranches, with the first tranche of GBP 1.3 million disbursed in February 2025.

Key Lessons and Recommendations from this year:

- The evidence generated through ME3F is expected to play a critical role in shaping future flood recovery strategies, ensuring that reconstruction efforts are equitable, resilient, and guided by principles of transparency and accountability.
- Given the slower pace of mobilisation, the 0.3% allocation announcement, and our ongoing efforts to streamline the portfolio, it is recommended that disbursements to ME3F be reduced this year.

D: VALUE FOR MONEY

Key cost drivers and performance
There is strong evidence of SEED and NRSP-CRCC delivering value for money (VfM) for the UK taxpayer. The programme adheres to the programme management guidelines and PrOF rule, underpinned by rigorous financial oversight and strengthened ME3F work. For ASI outputs, 76% of fees focused on investment facilitation, improving public investment management, and developing climate-resilient infrastructure. NRSP-CRCC reduced reliance on external consultants by building in-house expertise and secured over USD 25 million in climate finance, evidencing VfM through lower delivery costs, robust MEL frameworks, and increased leverage.

VfM performance compared to the original VfM proposition in the business case
Economy:

The SEED programme remains firmly committed to delivering value for money for UK taxpayers. It has maintained strong control over input costs while ensuring high-quality outcomes. A key element of this approach has been ASI’s decision to source 97% of technical work through local consultants, drawing on local knowledge that is critical for institutional reform. Less than 3% of the consultancy budget was allocated to international expertise, reflecting a disciplined, locally led strategy that delivers both cost savings and contextual relevance.

NRSP-CRCC has taken proactive measures to enhance efficiency and reduce costs. By transitioning away from high-cost, short-term consultancy and investing in in-house expertise across Data, Finance, and GHGE, it has achieved a reduction of nearly 80% in the average cost per proposal. This strategic shift not only delivers substantial savings but also embeds essential capabilities within Pakistan’s climate finance infrastructure, supporting long-term resilience and reducing dependence on external technical support. To further reduce operational expenditure, NRSP-CRCC undertook a thorough review of more than 15 properties before relocating to a more cost-effective office. This move has resulted in a 30% reduction in annual rent, while also providing improved facilities. By adapting the new space to host stakeholder workshops and technical sessions in-house, the programme has eliminated recurring venue hire costs.

Efficiency:
The SEED programme has demonstrated strong conversion of inputs into outputs, achieving significant financial leverage and operational optimisation. ASI has maintained high efficiency metrics, the total cost of developing the PIM tools, including RAMS which was developed and launched this year, amounts to £225,971. These tools have been applied to projects valued at £123 million, all of which were approved by the PDWP for the FY26 cycle. ASI also advanced climate-resilient investment by supporting the mapping of forest assets and progressing hydropower and renewable transactions with Pakhtunkhwa Energy Development Organisation. This groundwork positions the Government of Khyber Pakhtunkhwa to access significant volumes of carbon finance, with estimates indicating PKR 6.8 billion from renewable energy I-RECs and PKR 30 billion (GBP 1.76 million) annually from forest-based carbon credits.
NRSP-CRCC improved delivery efficiency by submitting all monthly, quarterly, and annual financial and programmatic reports on time, alongside completing audits. Its internal team now manages multiple complex proposals simultaneously, reducing dependency on sequential external studies. NRSP-CRCC also appointed a dedicated MEL expert to meet GCF and future funding partners’ requirements, laying the foundation for rigorous evidence-based delivery.
The ME3F partnership with the WB under Pakistan@100 AA contributed to efficiency by establishing critical evidence. The programme launched the MPHS in Sindh, initiated a PETS on roads, housing and hydraulic infrastructure, and advanced procurement for an infrastructure assessment to audit reconstruction quality. These procurements will collect data against previous floods in Pakistan will ensure that future climate-resilient investments are based on robust data, reducing inefficiency and waste. These findings are shared with stakeholders, including civil society, academia, and the media, to foster accountability.

Effectiveness:
SEED interventions have successfully translated into outcomes that advance Pakistan’s economic development and climate resilience. ASI over-achieved its milestone of facilitating USD 225 million (GBP 167.91 million) in private investment by June 2025, reaching USD 227.5 million (GBP 169.40 million). A further USD 344 million (GBP 256.72 million) remains in advanced stages, demonstrating the programme’s catalytic role in mobilising private capital for growth and jobs. KP’s institutional capacity has improved markedly, with its PIMA score increasing from 4.11 to 4.78, surpassing the benchmark of 4.7. This progress is directly linked to SEED-supported tools such as RAMS and updated PPP and JV frameworks, which ensure more rigorous appraisal and delivery of public investments.
NRSP-CRCC established Pakistan’s first climate-focused investment facility by securing GBP18.25 million through the GCF for Climaventures and an additional GBP 7.3 million for battery-swapping stations. Its submission of nine new proposals to the GCF, IKI, KfW, CCAC and Welcome Trust demonstrates an increasingly sophisticated climate finance pipeline. NRSP-CRCC’s carbon pilots, the Baghban Punjab agroforestry scheme and the Biochar Impact Initiative are enabling Pakistan to generate voluntary carbon credits, directly contributing to emissions reductions and creating new revenue streams linked to climate performance.
The ME3F component under SEED, by establishing baseline data and tracking systems through the MPHS, PETS and upcoming infrastructure assessment, strengthens the likelihood that future public expenditure on reconstruction and climate-resilient infrastructure will achieve intended development outcomes.

Equity:
Equity considerations have been integrated into programme delivery, although there remains scope to strengthen quantitative tracking. ASI embedded gender, disability and climate considerations into key regulatory reforms, notably within KP’s updated PPP and JV frameworks, to broaden participation in infrastructure and economic opportunities.
NRSP-CRCC’s transparent recruitment processes have diversified Pakistan’s climate finance talent pool. Its initiatives, such as the DairEase methane reduction pilot and the battery-swapping scheme, are also designed to benefit low-income groups including dairy farmers and three-wheeler drivers. However, there is a recognised need for more systematic disaggregation of beneficiary data by gender and vulnerability, to fully evidence inclusive impacts, consistent with FCDO’s Inclusive Data Charter commitments.

Overall VfM Assessment & Cost-Effectiveness:
The programme continues to deliver strong Value for Money, combining prudent cost control, substantial leverage of private and climate finance, and significant improvements in Pakistan’s institutional and climate investment landscape.

NRSP-CRCC transitioned from relying on fragmented short-term consultancy to building sustained local capacity by hiring local staff and embedding permanent expertise, ASI’s multiplier impact on private investment relative to advisory costs, and the ME3F under the World Bank, facilitates targeted and evidence-based data collection. To promote sustainability, future interventions by the Government of Pakistan and other donors could draw on these insights to guide strategic decisions around reconstruction and resilience-building.

Assessment of whether the programme continues to represent value for money.
This section has clearly demonstrated that the SEED programme continues to represent value for money through facilitating private investment with a cross-cutting focus on climate; improving fiscal space; and investing in improving access to climate finance to increase energy efficiency and the share of renewables in the energy mix. The programme has continued to achieve its outcomes and use its allocated budget efficiently.

Recommendation: To consolidate VfM gains achieved through NRSP-CRCC’s transition to an in-house model, continued technical training and exposure to international climate finance practices for local staff is recommended.

E: RISK

Overview of Risk Management
The SEED programme maintains an overall cautious risk rating, reflecting Pakistan’s enduring political, economic, and security context. Delivery partners ASI, NRSP-CRCC and WB continue to implement comprehensive risk management frameworks, with residual risks assessed quarterly and aligned to FCDO’s Risk Appetite Statement. Due diligence, safeguarding, gender and climate considerations are fully embedded across programme operations, and all partners are aware of and adhere to established risk escalation processes as par FCDO risk management framework guidelines

People
The overall risk appetite for this category remains ‘cautious’, while the programme overall residual risk is ‘moderate’. Following provincial elections last year, ASI navigated political transitions by intensifying technical engagement across multiple levels of the KP administration, ensuring continued buy-in for key economic and planning reforms. NRSP-CRCC mitigated staff capacity risks by recruiting ten additional specialists across technical, finance, communications and M&E, with formal orientation sessions reinforcing safeguarding and gender awareness. This approach maintained institutional continuity and ensured the programme remains compliant with SEAH and equality standards.

Financial & Fiduciary
The overall risk appetite for this category remains ‘cautious’, while the programme overall residual risk is ‘moderate’. Pakistan’s persistent fiscal pressures, high interest rates, and exchange rate volatility posed challenges to investment pipelines and financial structuring. ASI addressed this through revised financial models indexed to dollar revenues, protecting returns for planned investments. NRSP-CRCC diversified funding by submitting proposals to entities including the GCF, MAF, IKI and Wellcome Trust, thus spreading exposure and safeguarding climate finance inflows. Across partners, monthly financial reporting, AML/CFT checks, and quarterly reviews have maintained robust fiduciary oversight, reducing risks of mismanagement or compliance breaches.

Public Service Delivery & Operations
The overall risk appetite for this category remains ‘cautious’, while the programme overall residual risk is ‘moderate’. Security constraints continued to limit FCDO and partner access across KP, necessitating adjustments to operational modalities. ASI ensured high-level GoKP commitments to convene meetings in secure environments, sustaining momentum on public financial management and investment prioritisation. NRSP-CRCC embedded flexible workplans to absorb delays arising from political disruptions in Islamabad, enabling it to progress multiple concept notes and due diligence processes without major programme-level impacts. Climate considerations were actively integrated, with early warning systems and methane reduction initiatives addressing both operational resilience and Paris Agreement alignment.

Safeguarding (including SEAH and equalities)
The overall risk appetite for this category remains ‘minimal’. while the programme overall residual risk is ‘minor’. FCDO resources related to safeguarding hub and external guidelines for safeguarding were shared with programme partners last year, which is in line with the safeguarding country workplan. ASI conducted a three-day safeguarding workshop covering SEAH, with policies rigorously applied across all downstream contracts. NRSP-CRCC used social inclusion checklists during project development, reinforcing gender and disability lenses. The external GESI review commissioned this year led to updated programme frameworks, with gender-disaggregated indicators integrated into reporting, ensuring continued compliance.

Policy & Programme Delivery
The overall risk appetite for this category remains ‘cautious’, while the programme overall residual risk is ‘moderate’. Frequent political transitions and administrative changes risked slowing the reform agenda. ASI mitigated this by deploying an investment prioritisation matrix, safeguarding the pipeline of projects with the highest expected economic returns. NRSP-CRCC balanced ownership sensitivities in initiatives like the Early Warning Systems by adopting a facilitative role, aligning technical inputs with lead agency objectives while maintaining quality. This safeguarded policy traction and ensured that climate-focused interventions like Climaventures progressed despite institutional churn.

Strategy & Context
The overall risk appetite for this category remains ‘cautious’, while the programme overall residual risk is ‘moderate’. The broader economic landscape, combined with shifting political priorities, necessitated vigilant scenario analysis. NRSP-CRCC strategically positioned itself as Pakistan’s first dedicated climate finance facility, securing USD 25 million (GBP 20.25 million) under Climaventures with additional pipelines under negotiation, thus buffering longer-term contextual risks. Climate risk was systematically integrated, with proposals aligned to mitigation objectives across energy, agriculture and waste sectors, reinforcing Paris alignment.

Reputational
The overall risk appetite for this category remains ‘cautious’, while the programme overall residual risk is ‘moderate’. ASI’s support for sensitive reforms such as pension restructuring, tax systems and new climate financial instruments inherently carries reputational exposure. This was mitigated by transparent communication strategies, extensive joint review meetings with NRSP-CRCC alone conducting 48 multi-stakeholder sessions this year and adherence to international best practice. Strengthened MEL systems, including climate and gender metrics, further safeguarded programme integrity and reputational standing.
Progress on past DDA recommendations has strengthened partner systems, reduced identified risks and maintained assurances at a proportionate level to the programme’s scope.

Update on Partnership Principles
The UK’s development assistance within Pakistan is underpinned by an assessment of the government’s commitment to the four Partnership Principles: commitment to reducing poverty; respecting human rights; strengthening financial management; and strengthening domestic accountability. Our overall judgement is that the Federal Government of Pakistan is demonstrating a credible commitment to two of the four partnership principles namely: poverty reduction and financial management. There are however causes for concern in certain areas of human rights where the trajectory of progress has been downward. Domestic accountability to citizens in the areas of civic space and media freedom has also been constrained with no sign of improvements in the last year. On public financial management and anti-corruption, the direction of travel is broadly neutral, although some evidence indicates improvements particularly at provincial level. Substantial reform is needed in all partnership principles areas (especially on the implementation of commitments where these are in place).

At the provincial level, the BHC has built good relationships with the GoKP and there is confidence that there is broad commitment to build institutions, systems, and processes to support improved public financial management and service delivery. SEED plays a significant role in improving sectoral planning. SEED TA and interventions are improving the provincial government’s economic planning functions. This could contribute to improving Pakistan’s position in future assessments of the partnership principles. No SEED programme funds flow through government systems, but the TA will contribute to improved PFM outcomes.
Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Moderate (Cautious)
Specific assessment of corruption risk and direction of travel since last ASP	Moderate (Cautious)
Is a full FRA update required?	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The SEED programme has entered its seventh year of implementation. All Implementing Partners (IPs) continue to uphold robust financial and commercial management systems. The programme team conducts monthly and quarterly meetings with partners to review work plans, assess progress, and ensure alignment with agreed KPIs.

In collaboration with the finance team, the programme conducted financial spot checks on SEED’s IPs by verifying vouchers against actual expenditures, with a focused review of eligible and ineligible items in accordance with FCDO guidelines. Additionally, the programme team verified the asset registers of both ASI and NRSP-CRCC, confirming they are up-to-date and compliant with FCDO requirements. These checks were successfully completed and formally closed. Additionally, the team held separate meetings with programme partners to support the development of comprehensive risk registers and to encourage a realistic approach to risk appetite. Over the lifetime of the programme, SEED under ASI accumulated a portion of the fee budget amounting to GBP 514,442. These funds were paid and owed based on the KPI stream of the contract but remained unutilised. The disbursement was made in line with contractual obligations, and all KPIs were successfully met. To ensure effective use of these funds, SEED requested ASI to track the unutilised amount. A formal workplan was subsequently approved, and the funds were fully utilised against agreed programme deliverables by May 2025, in line with and approved from the programme’s Senior Responsible Owner (SRO).

During the reporting period, the programme team reviewed partner risk register, financial and programme reports to ensure compliance with FCDO guidelines, and as outlined in the respective funding instruments. BHC Islamabad team worked with programme partners to ensure they adhered to FCDO policies and PrOF rules. BHC Islamabad held compliance checks with ASI and CRCC to ensure they take full ownership of their risk register are up to date and in line with FCDO risk management policy. Additionally, a spot check was held with CRCC on safeguarding, a total of 47 questions were shared to ensure they are in compliance with FCDO safeguarding policy. This will result in partner being more compliant on fraud and safeguarding reporting in the future. Lastly, the latest communication policy and guidelines were shared with ASI earlier this year, which resulted successful deployment of three communications events in collaboration with FCDO.

Across all outputs, partners demonstrated effective financial and commercial management, timely reporting, and full compliance with FCDO framework. Continued oversight from BHC Islamabad programme management team has ensured delivery remains on track, within budget.

Financial compliance across the programme remains strong. Key indicators include maintaining budget variances within a 5% threshold, timely submission of financial reports, adherence to audit requirements, and clear categorisation of invoices by cost heads. The total allocation for the reporting period was GBP 4.45 million of which £ 4.43 million was consumed during the annual review period, ensuring we keep our variance between +/- 5% for the year. The distribution across all four outputs is as follows:

Outputs 1 & 2 (ASI): ASI continues to demonstrate strong delivery and financial discipline. The programme supports economic and urban development planning in KP through demand-led technical assistance. Cumulative expenditure stands till date stands at GBP 12.76 million, with 83% directed towards Output 1, reflecting strategic emphasis on private investment and transaction support. Output 2 focuses on strengthening public investment management.

Oversight by BHC Islamabad remains rigorous, with ASI actively participating in monthly management meetings, quarterly technical reviews, and investment stocktake sessions. These engagements facilitate KPI tracking, risk monitoring, political context analysis, and VfM assessments. ASI consistently meets compliance obligations, submitting KPIs and Means of Verification on schedule, with expense claims supported by detailed documentation and subject to SRO approval. ASI has been consistently sharing quarterly expense breakdowns; however, their current system generated format limits the programme team's ability to conduct timely and detailed analysis. To strengthen reporting and enable more effective cross-verification, ASI is encouraged to proactively provide comprehensive breakdowns of all cost heads, including staff timesheets, in a structured and accessible format such as spread sheets alongside quarterly submissions rather than waiting for specific requests from the programme team.

As the commercial contract concludes on 6 October 2025, ASI has to comply with FCDO’s contract closure guidance, including financial settlements, audit submission, asset transfer planning, and exit strategy development. Although ASI’s forecasting and spending have generally aligned well with expectations, more granular and realistic monthly forecasts for both KPIs and expenses would further strengthen financial planning.

Output 3 (NRSP – NRSP-CRCC): An AGA was signed with NRSP in December 2021 to establish the Climate Resource Coordination Cell (NRSP-CRCC). Expenditure of GBP 636,583 was aligned with approved workplans. NRSP-CRCC strengthened compliance by hiring dedicated staff. Quarterly reviews confirmed adherence to audit and reporting standards, with financial audit report demonstrated accurate forecasting and cost categorisation. NRSP CRCC exceeded its projected budget for the fiscal year 2024–25. While the actual overspend figures were not reported within the expected timeframe, the additional expenditure was subsequently carried forward and accounted for in the following fiscal year. Importantly, the overspend remained within the permissible threshold outlined in the Accountable Grant Agreement (AGA) for the fiscal year. BHC Islamabad team shared an up-to-date template with NRSP-CRCC team to ensure their programme reporting are aligned with FCDO requirements. The team also conducted dedicated meetings with the NRSP-CRCC team to ensure compliance with AGA reporting requirements, in line with FCDO guidelines on financial management, risk registers, safeguarding and programme management reporting. To strengthen financial management and ensure compliance, it is recommended that NRSP CRCC invest adequate time in annual planning and budgeting, as well as in quarterly and monthly forecasting. Any changes to financial projections should be promptly communicated to FCDO, accompanied by clear justification and a comprehensive value-for-money analysis. Furthermore, value-for-money considerations should be an integral part of NRSP CRCC’s financial reporting processes.

Output 4 [Old] (Karandaaz Pakistan): SEED concluded an AGA with Karandaaz Pakistan, valued at GBP 15.74 million, to support capital investments and technical assistance for the adoption of renewable energy and energy efficiency solutions. A total of £2.72 million was disbursed and fully utilised (RDEL £256,356; ICF-CDEL £2.47 million). Since the agreement’s inception, KRN successfully mobilised £17.2 million in private sector financing. As a Section 42 Special Purpose Vehicle, KRN Pakistan received full transfer of all physical and financial assets under the SEED programme, thereby concluding the Accountable Grant Arrangement in the previous year.

Output 4 (WB – PAK@100): Activities progressed across analytical and infrastructure planning streams. Contracts for the Multi-Purpose Household Survey (MPHS) were awarded, and RFP for Infrastructure Assessment closed by the end of June, with evaluations underway. Data for the Public Expenditure Tracking Survey is under analysis. The WB team maintained structured coordination with FCDO, aligning timelines with programme management and timely disbursement of tranches. Till date a total of GBP 1.3 million has been disbursed to WB under the Pakistan@100 AA. WB has fully committed this amount against the hiring firms for the MPHS workstream. The programme team has been facing ongoing challenges in producing accurate monthly forecasts with the World Bank under the ME3F fund, mainly due to the fund’s complex multi-donor structure. Contributions from other partners i.e KfW and UNDP into the trust fund have made it challenging to consistently isolate and monitor FCDO-specific financial data. To enhance financial clarity and streamline forecasting processes, it is recommended that SEED’s senior management initiate collaborative discussions with the World Bank. These discussions should aim to establish a shared understanding and identify practical, mutually agreed solutions.
Asset Management: The programme maintains an asset register at the partner level, and an annual asset spot check review was carried out on July 2025 of the reporting year for ASI and NRSP-CRCC. All assets were found to be in good condition and properly tagged. No major discrepancies were detected. The ASI commercial contract is approaching its conclusion. Accordingly, the ASI team has been advised to submit a clear and detailed plan for the transfer of assets to either the REMIT or UPSCALE programme, with a strong emphasis on demonstrating value for money.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring: Due to ongoing security risks in Khyber Pakhtunkhwa (KP), the SEED team was unable to conduct direct field monitoring since 2023. Instead, MEL activities focused on monitoring of the programme through implementing partners rather than projects directly, with partners conducting on-ground verification in their operational areas. Oversight was maintained through structured review of quarterly and annual partner reports, which were aligned to the SEED logframe, Value for Money (VfM) metrics, and gender-disaggregated indicators. Tools such as the Monitoring Dashboard, beneficiary’s datasheet, and the VfM tracker captured historical trends, ICF results and equity metrics, and delivery progress. FCDO held regular one-to-one programme and technical review meetings with ASI, reviewed risks against the programme risk register, and used investment stock-take sessions to integrate MEL data into decision-making.

Evaluation: During the programme’s inception phase, the BHC Islamabad team attempted to procure a supplier to develop a Monitoring and Evaluation framework. However, the procurement process was unsuccessful due to limited interest from potential suppliers, and no bids were submitted and the programme could not hire an independent MEL supplier. The situation was further constrained by the ODA funding pause in 2021, which impacted procurement efforts.

Learning: After-action reviews for BIU and the Peshawar Clean Air Alliance reinforced that early government engagement, sustained institutional alignment, and resourcing commitments are critical for uptake of technical reforms. CRCC’s iterative stakeholder consultations shaped its climate finance pipeline, while ASI’s external GESI review highlighted the need for clearer benefit pathways for women in PPP and public investment reforms. Programme-wide, MEL findings underscored that flexible, partner-focused monitoring structures can maintain accountability in restricted-access contexts but must be complemented by independent verification for robust impact assessment. Lessons also confirmed that institutional ownership, targeted technical capacity building, and integration of tools into government systems are essential for sustainability.
The absence of an independent programme-wide evaluation remains a risk to evidencing impact at closure, as current evidence is based on partner-led monitoring.

Recommendation: SEED should commission an independent impact evaluation before programme end to credibly assess contributions to public and private investment mobilisation, public investment efficiency, and institutional capacity in KP. This would provide robust evidence of programme achievements and strengthen accountability to FCDO and external stakeholders.
Date of last narrative financial report	NRSP-CRCC (July 2025) / ASI (July 2025) / KRN (July 2025)	Date of last audited annual statement	NRSP-CRCC: 30 June 2024 / ASI: 31 Dec 2023
[note] The financial audit for ASI runs between (Jan – Dec 2024. The audit for FY 2024-25 is still underway. The due date for completing external audit in the UK is September 2025 and they are in line with their statutory audit timelines. Source: Accounts and tax returns for private limited companies: Overview - GOV.UK