## Logframe Clean Version
Sustainable Energy and Economic Development (SEED)
Revised Version:05 March 2025
IMPACT | Impact Indicator 1 |  |  | Baseline | March - 2020 | July - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026 | Risks/Assumptions
Higher growth, jobs, and incomes | Provincial Growth Rate / % Increase in Average HH Income (PKR) (Khyber Pakhtunkhwa) |  | Planned | a) 3.73% b) 41813 | a) 3.73% b) 39539 | a) 0% b) 41813 | a) 3.73% b) 41813 | N/A | a) 0% b) 41813 | a) 1% b) 43904 | a) 0% b) 46099 | a) 1% b) 48404 | a) 3.7% b) 53244 | a) 4.1% b) 58569 | a) 4.1% b) 58569 | a) 4.1% b) 58569
|  |  | Achieved | [6 empty] | a) 5.2% | a) 5.01% | a) 0.08% | a) 2.16% | Data no available
Source: a) IMF estimates Frequency: Annual. b) Household Integrated Economic Survey (HIES). Frequency: Every second year.
a) For GDP growth rate, targets are set based on IMF’s projection of national real GDP growth rate, with 0.5 points less for KP than national average. For 'Achieved' row, the figure for Provincial Growth Rate figures are sourced from the KP Bureau of Statistics (KPBoS). b) The baseline for average HH income is taken from HIES 2018-2019 survey. For increase in avg. HH income, target has been set with the assumption that income (nominal) will growth by 5% from 2021 till 2023, and for later years it will increase by 10%. These assumptions align with the corresponding assumptions on growth rate and unemployment rate. Achieved figures will be added when the next iteration of HIES is conducted, which is expected in 2024-25, according to latest updates from KPBoS.
| Impact Indicator 2 |  |  | Baseline | March - 2020 | July - 2020 | Baseline |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June- 2025 | Oct- 2025 | June 2026 | Oct 2026
| Provincial unemployment rate (in %) (Khyber Pakhtunkhwa) |  | Planned | 7.16% | 7.16% | 7.16% | 7.16% | N/A | 7.16% | 8.8% Male: 7.13% Female: 15.65% | 7.7% Male: 6.8% Female: 14.9% | 7.3% Male: 6.4% Female: 14.1% | 6.6% Male:5.8% Female: 12.7% | 5.9% Male:5.2% Female: 11.4% | 5.9% Male:5.2% Female: 11.4% | 5.9% Male:5.2% Female: 11.4% | 5.9% Male:5.2% Female: 11.4%
|  |  | Achieved |  | 7.16% |  |  |  | 6.5% | 8.8% Male: 7.13% Female: 15.65% | Data not available | Data not available | Data not available | Data not available
Source: Pakistan Labour Force Survey. Frequency: Annual (Decreased by 5% till 2023, and by 10% from 2024 and onward)
The baseline is from Pakistan Labour Force Survey (LFS) 2017-2018. The figure for June, 2020 is based on the LFS 2018-19, as no survey was conducted in 2019-20. The figure for June,2021 is sourced from the LFS, 2020-21. The figures for June, 2022, 2023 and 2024 will be added when data from the next iteration of the Labor Force Survey is published, which is expected in 2024-25, according to latest updates from KPBoS. For year 2022 and 2023, target has been set for reduced unemployment rate by 5%; and for years 2024 and 2025, target has been set for reduced unemployment rate by 10%.
| Impact Indicator 3 |  |  | Baseline | June - 2019 | June - 2020 |  |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June 2025 | Oct- 2025
| Share of renewable energy in total installed capacity |  | Planned | 5%. | To be determined at inception | 4.5%. | 5%. | N/A | 4.50.% | 6% | 8% | 10% | 15% | >or equal to 20% | >or equal to 20%
|  |  | Achieved | [10 empty] | N/A
Source
http://gtf.esmap.org/country/pakistan.
OUTCOME | [17 empty] | Risks/Assumptions (Outcome-Impact)
Higher private and public investment and improved public investment efficiency | Outcome Indicator 1 |  |  | Baseline | March - 2019 | July - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026 | 1. It is possible to increase both the quantum and efficiency of public investment without significantly compromising either objective 2. Exogenous factors (including political instability and economic decline at the national level) do not significantly dampen growth 3. Growth enabled by SEED, GoKP and other donor programs will in fact create jobs and raise household incomes at targeted levels 4. Any increase in fiscal space will directly contribute to quantum of public investment as fiscal space is the only compelling constraint on public investment
| Additional investment facilitated (US$m) as a direct result of economic and urban development TA in KP (This could be a combination of multilateral, bilateral or private debt/equity/PPP/ other investment) - [KPI 12. Volume of private finance mobilised for climate change purposes]; Number of people supported to better adapt to the effects of climate change |  | Planned | Zero | 0 | 0 | Zero |  |  | 02 economically viable projects identified for additional investments. _______ KPI 12. N/A | i) At-least two (cumulative) improved PIM practices/ processes (relating to project design, appraisal, execution, monitoring, and completion) adopted and applied by the Government on projects (cumulative) with combined worth of PKR. 500M. ii) Data portal completed and launched, manual & training for BOS officials completed to use data portal to update and maintain provincial statistics iii) At-least four (04) departments trained on the use of the data portal for planning (project selection, design and appraisal) and policy formation. | $ 30m investment in advanced stages* KPI 12. Investment in advanced stages for at least $3m of private finance, disaggregated by climate theme (i.e., adaptation / mitigation / both) | $ 175m (cumulative) investment facilitated KPI 12: Investment facilitated for at least $17.5m of private finance disaggregated by climate theme (i.e., adaptation / mitigation / both) | i) $ 225m (cumulative) investment facilitated* ii) KPI1 12: Investment facilitated for at least $22.5m of private finance disaggregated by climate theme (i.e., adaptation / mitigation / both) ______ iii) KPI-1. 133,000 individuals in rural and 91,000 in urban areas*** | $ 225m (cumulative) investment facilitated* KPI1 12: Investment facilitated for at least $22.5m of private finance disaggregated by climate theme (i.e., adaptation / mitigation / both) ______ KPI-1. 133,000 individuals in rural and 91,000 in urban areas***
|  |  | Achieved | [6 empty] | PPP Project pipeline of 42 projects identified. Additional 2 projects identified (Koto HPP and Karora HPP) under PEDO Funding Strategy. No targets under KPI 12. | i) Exceeded expectations. Two improved PIM practices approved, adopted, and applied on 45 projects worth PKR 95.8 billion or £365 million) (against a target of PKR 0.5 billion or £1.9 million). 6 additional tools have been developed for approval in FY23. Online portal to improve access of PIM tools created and in use. Multiple training sessions held on use of 8 PIM tools. Plan for restructuring Urban planning and Policy Monitoring Unit developed and submitted to P&DD. New partnership with Peshawar clean air alliance aims to reduce air pollution and monitor air quality in Peshawar. ii) exceeded expectations. KP data portal approved and launched by ACS in April 2022; manuals developed and approved, and BOS official trained on data management and web hosting. Additions have been made in the data portal to allow use of night light data to estimate provincial GDP and extensions to the data portal have also been created to allow tracking price indices of key commodities in future. iii) Exceeded expectation. 8 against a target of 4 departments trained on the use of the data portal for planning. Additional targeted trainings have been provided to 35 GoKP officials from 12-line departments and a data landscaping exercise has been initiated. | $148 million to advanced stages during the review year 2022-23. Cumulative, transactions worth $335 million of private investment lies at advanced stages since the start of the programme. ______________________________ KPI 12. Against the target of $3m, transactions worth $62 million have reached advanced stages during the program year 2022-23 This included approval of feasibility studies on ITZs Ganool ($44m) and Mankiyal ($17m). | $ 143m (cumulative) investment facilitated and $355mn in advanced stages. . Milestone underachieved. No private climate finance transaction brought to investment facilitated stage. Milestone underachieved. | i) The cumulative investment facilitated by SEED since the start of the programme stands at US$227.5 million. ii) Cumulative private finance facilitated since the start of the programme stands at US$38.2 million. Please note: The ICF KPI 12 planned results has been revised in March and will be updated in cotober. iii) Seven PC-Is, potentially benefiting an estimated 208,980 individuals, have already secured funding, while the rest have been approved by the C&W department.
|  |  | Planned | [7 empty] | KPI 13. Level of integration of climate change in government planning assessed against the Scorecard by establishing baseline (process indicator). KPI 14. At-least 2 workshops held with the GoKP to finalise the baseline against KPI-14, and to improve knowledge of GoKP officials on CC mitigation, adaptation and best practices. |  | 45,000 individuals (in rural areas)* | NA
|  |  | Achieved | [7 empty] | KPI.13. Exceeded Expectations. Consultations held with P&DD, Finance, Agriculture, Local Government and Environment Departments to establish a baseline assessment against the ICF KPI 13 scorecard. The Baseline Report has been submitted to P&DD in June 2022. In addition to the baseline, a TA Roadmap was also developed; a Joint World Bank-SEED Climate Diagnostic Study was completed which is expected to lead to a new climate change programme by World Bank. KPI 14. Exceeded expectation. Baseline assessment concluded a score of 6.84 , followed by two capacity building workshops with up to 25 officials from 10 GoKP departments. Additional capacity building workshops were also held, and an online learning module created to improve capacity in assessing environmental and social impact of PPP projects. SEED also organised a climate working group convention on Carbon Markets to enhance the understanding and potential adaptation of voluntary carbon markets which has huge potential for generating revenues and private investment mobilisation. |  | PC-Is potentially benefiting 224,480 individuals accepted but awaiting approval by competent forum due to fiscal crunch. Milestone partially achieved. | NA
Source: Project reports and/or agreements, including a detailed SEED investment tracking sheet. USD 1= PKR 167.274. Source: www.xe.com. Exchange rate as of Aug 30, 2020. KPI 12 investment milestones are a subset of the total private investment facilitated. *The term 'advanced stage' means that the investment transaction has reached stage where preparation of investment work is complete, specifically: (i) completion of feasibility for solicited PPP project; (ii) submission of final proposal by private party in response to LOI for unsolicited PPP project; (iii) singing of terms sheet for CF/PF transactions; (iv) Reaching appraisal stage (initiation of PAD preparation) for multilateral investments. **The term 'investment facilitated' means that the investment transaction has reached a legally binding stage, specifically: (i) award of contract for solicited and unsolicited PPPs; (ii) signing of financing agreement for CF/PF transactions; (iii) Board approval of lender for multilateral investment. ***For 2024, the target denotes potential beneficiaries of PC-I projects which will be approved within the program year 2023-24. For 2025, the target denotes cumulative beneficiaries of PC-I projects approved within the program years 2023-24 and 2024-25ent.
| Outcome Indicator 2 |  |  | Baseline (2021) | March - 2019 | July - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June- 2022 | June - 2023 | June - 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026
| Effectiveness of PIM system in KP (PIMA) |  | Planned | 4.11 | TBD |  | 4.11 | NA |  | 4.11 | 4.11 | 4.2 | 4.6 | 4.7 | 4.7
|  |  | Achieved |  |  |  | 4.11 | NA |  | 4.11 | NA | The milestone has been exceeded with achievement of PIMA score of 4.60 which is higher by 0.49 than the target of 4.20 set for July 2023. SEED’s contribution to the improvement (of 0.49) in the score is approximately 0.31 (63%), mainly coming from its work on the PPP framework, technical appraisal checklist applied to all roads and bridges, bridge design code and developing monitoring and qualification testing protocols. | Potentially higher than 4.6 | 4.78
|  |  | Source | Source: Our own estimates through (new) PIMA Framework. Frequency: Annual
For assessing the relative strength of PIM institutions in KP, we have used the PIMA framework for the assessment and calculations. SEED engaged an independent expert to establish a PIMA baseline score for 2021, which was endorsed by GoKP. No PIMA assessment was conducted in 2022 and 2024 because no improvement was targeted. A PIMA assessment will be conducted in 2024-25 and the score will be updated accordingly.
| Outcome Indicator 3 |  |  | Baseline | March - 2019 | July - 2020 | Baseline |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June- 2025 | Oct- 2025 | June 2026 | Oct 2026
| Increase in fiscal space (PKR Billion) |  | Planned | Zero |  | N/A (baseline year) | Zero |  |  | 2 policy-reforms and/or institutional measures successfully adopted by government for increasing fiscal space. | PKR. 500 million of potential fiscal space identified as a result of SEED supported revenue mobilization and/or expenditure reduction initiatives. | 1 billion per annum, as a result of SEED's direct interventions (cumulative) - (Perpetuity Value: 12.5 billion) | 100% of new employees registered under the new contributory pension scheme* ii) Fiscal savings from legacy pension reforms on-track** | i) 100% of new employees registered under the new contributory pension scheme* ii) Fiscal savings from legacy pension reforms on-track** | i) 100% of new employees registered under the new contributory pension scheme* ii) Fiscal savings from legacy pension reforms on-track**
|  |  | Achieved | [6 empty] | 2 policy proposals adopted (Pensions reforms, STS roadmap). | Legacy pension reform complete with potential fiscal savings of PKR 148 billion to be realized over the next 11 years. | >Target for 2025 achieved by changes in pension rules > Early retirement age reform leading to savings of PKR 137 billion over next 11 years, starting from FY2022-23 > Now supporting contributory pension reform to gain potential fiscal savings = PKR 700 billion over next 29 years | 100% of new employees subscribe to contributory pension scheme. Milestone met Savings from legacy pension reforms remain on-track. | i) 100% of new employees (59,544) subscribe to the contributory pension scheme. Not only has SEED ensured that 100% of new civil servants are recruited under the new contributory scheme, but it has also supported several measures to make the DCS more efficient, reliable, and beneficial for the GoKP and its employees. ii) Savings from legacy pension reforms remain on track, as reported in the KP Budget White Paper (2025–26).
Source: Project reports substantiated by GoKP official figures. Frequency: Annual (June). *Excluding ad-hoc recruitments. This refers to Individuals recruited under the KP Civil Servants Act the Act 1973, after coming into force of the Khyber Pakhtunkhwa Civil Servants (Amendment) Act, 2022 (Khyber Pakhtunkhwa Act No. X of 2022); or an employee of the Government, regularized as civil servant through any legal instrument, issued after coming into force of the Khyber Pakhtunkhwa Civil Servants (Amendment) Act, 2022 (Khyber Pakhtunkhwa Act No. X of 2022), irrespective of the effective date of regularization. **Early retirement age reform leading to savings of PKR 137 billion over 11 years, starting from FY2022-23
| Outcome Indicator 4 |  |  | Baseline | June - 2019 | June - 2020 | Baseline |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025
| 'Additional commercial bank financing for renewable energy (% change in share of solar/wind in outstanding loans to private sector) |  | Planned | PKR. 43.62 billion (0.7% of total outstanding loans to private sector) in March 2020 |  | 2% | PKR. 43.62 billion (0.7% of total outstanding loans to private sector) in March 2020 |  | 2% | 2% | 2% | 2% | 2% | >$45 million
|  |  | Achieved |  |  | -15.43% |  |  | -15.43% | 0.63% | 0.59% | 0.9 |  | NA
Source: SBP - Credit Loans Classified by borrowers (https://www.sbp.org.pk/ecodata/index2.asp)
OUTPUT 1 | Output Indicator 1.1 |  |  | Baseline | March - 2019 | July - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026 | Risks/Assumptions (Output 2-Outcome)
Improved institutional capacity and better policy outcomes to attract investment and a viable investment pipeline, including climate finance Impact Weighting: 35% | Policy reforms and institutional support to attract private investments | TBD | Planned | PPP Act (not approved) No notified PPP rules available. No systematic PPD mechanism for policy discussion between GoKP and corporate sector |  | i) PPP diagnostic study conducted (August 2020) ii) Energy and housing sector diagnostics identify institutional weaknesses and areas of interventions for SEED | PPP Act (not approved) No notified PPP rules available. No systematic PPD mechanism for policy discussion between GoKP and corporate sector | 1.1 No. of high quality strategic economic development and urban plans supported in KP | . Technical assistance to GoKP fully mobilised for improved provincial urban, economic and spatial planning 2. Legal/policy reform or high quality strategic economic development and urban plans supported in KP. | i) Environmental and Social Management System (ESMS) approved for PPP. ii) KPK Power Sector Business Plan developed (Pakhtunkhwa Energy Development Organisation (PEDO) & KATGI). | i) At least one set of related/applicable PPP rules, policies, guidelines or strategies developed and approved (for example. PDF, VGF, JV rules for PHA/housing sector etc.) to mobilize private sector investments through strengthening PPP framework. ii) Three (03) public-policy dialogues (PPDs) (cumulative) held to bridge the gap b/w public and private sector in KP and recommendations submitted to government for uptake. iii) Work with at least 2 govt agencies underway for institutional debottlenecking (e.g. P&DD, energy, ST&IT, tourism, etc.) to mobilise private investment. | i) At least 2 policy and/or institutional bottlenecks removed/addressed to unlock private investment ii) Five-year PPP vision document firming up Government's long-term commitment submitted to the Government | i. PPP policy framework fully operational with regular meetings of the PPP Committee (at least 1) during the year. ii. Proposal for a new PPP Infrastructure Fund submitted to Government. iii. Implementation of comprehensive PPP Capacity Building Plan underway. | PPP institutional and policy framework nearly operational, as manifested by: i) Approval of RMU Guidelines (the last instrument in KP’s regulatory framework) ii) PPP Unit is fully staffed, PC-I for PPP Support Unit approved by PDWP and being implemented iii) PPP Nodes notified in at least 6 departments, with regular meetings of PPP Nodes, PPP Unit and PPP Committee (30+ cumulative meetings since the start of program, including 10 meetings within 2023-24) iv) 45 middle-to-senior officers trained in PPP regime across 12 departments, with atleast 10 enrolled in APMG’s CP3P Foundation module | PPP institutional and policy framework fully operational without SEED support on a sustainable basis, as manifested by: i) Fully notified legal and regulatory framework ii) PPP Unit operational with staffing plan rolled out iii) Regular meetings of PPP Nodes, PPP Unit and PPP Committee, as required iv) 45 middle-to-senior officers trained in PPP regime across 12 departments, with atleast 5 certified in APMG’s CP3P Foundation module |  |  | 1. PPP Unit can demonstrate sufficient value (e.g. through a track record of successfully concluded transactions) for the GoKP to financially absorb the cost of running the unit independently 2. Line departments gain familiarity with and confidence in the PPP process and PPP nodes become functional so that new projects are regularly identified 3. Early PPP projects do not run into common legal and/or financial difficulties which could become a bottleneck for projects further down the pipeline 4. Investors can cope with the rising cost of borrowing for PPP and other transactions being supported by SEED, which may invalidate certain assumptions in initial financial models 5. Prospective foreign investors can overlook declines in the investment climate brought about by the national fiscal crisis, deteriorating security situation and continued political instability 6. Institutional mechanisms developed by SEED i.e. VGF and PDF can help the GoKP replace technical expertise currently provided by SEED 7. The World Bank's funding window for the prospective climate finance program remains open and viable and there is no change in the Bank's relevant policies that might affect the inception or rollout of the program.
|  |  | Achieved |  |  | PPP diagnostic study and energy and housing sector diagnostics completed |  | Met: Programme team fully staffed in October 2018. Competition to procure the TA to efficiently source from pre-benchmarked suppliers was launched in June 2019 | A+: Output moderately exceeds expectations 1.1.1.TA contract signed in March 2020, full team recruited and mobilised. Extensive engagement with GoKP despite limitations imposed by COVID-19. 1.1.2. Two policy reforms supported and two contributions to GoKP’s economic recovery strategy. A pension reform plan and summary for the Cabinet was submitted to the Finance Department. The proposal has been endorsed by the Finance Minister and is expected to be presented for Cabinet’s approval. In addition, the draft pension reform bill has been shared with Finance Department. Additionally, SEED formulated the government’s SME and public infrastructure response as part of the post-COVID 19 Economic Recovery Plan Azm-e-Nau. The report has been approved by the Chief Minister. | Met. ESMS for PPP unit approved. ii) Met. Power business developed, approved, and published. | i) Selection of Private Partner Rules; Constitution and Function Rules; PDF Guidelines and VGF Guidelines developed and approved ii) 4 PPDs held on Pak-Afghan trade, Agribusiness, Tourism, and fiscal policy proposals. | I. Exceeded. 5 institutional bottlenecks removed/addressed to unlock private investment, including: 1) Viability Gap Funding (VGF) allocation increased from PKR 5bn (£14m) to PKR 9.3bn (£26m) to unlock investment for Swat Expressway-II; 2) Project Development Facility (PDF) allocation of PKR 500m (£1.4m) for FY 2023, out of which PKR 166m (£0.5m) have been spent to fund feasibility studies of 6 PPP projects; 3) Transfer of land parcel part of Pehur Hydel Power Project (HPP) from Irrigation Dept. to Energy Dept. nearly concluded to enable Corporate Finance Facility (CFF) for Pakhtunkhwa Energy Development Organisation (PEDO); 4) Risk Monitoring Unit (RMU) Guidelines developed and approved, and 5)KPCTA Business Plan approved by KPCTA II. Exceeded. Five-year PPP vision document was completed and submitted to GoKP in June 2023 | i. Not met: The PPP Policy Framework is fully operational and has already been used to process 8 PPP projects. The PPP vision document has also been approved by the PPP unit and P&D department. However, one meeting of the PPP Committee to review the pipeline could not take place. ii. Achieved: Proposal for a new PPP Infrastructure Fund was presented to the ACS, Planning and Development Department (P&DD) on the 6th of May 2024. SEED will now initiate support for implementation. iii. Achieved: PPP Capacity Building Plan was formally initiated in June 2024 through inauguration by the Chief Minister of the province. The plan was approved by the P&D department and implementation is underway. | i) The RMU Guidelines have been approved by the PPP Committee. In addition, the Aasan Karobar Bill has been approved by the Cabinet and introduced in the KP Assembly for enabling business environment. ii). Revised PC-I for the PPP Unit staffing has been approved, and the TORs for new positions have been advertised. PC-1 being implemented with recruitment underway. iii) 16 PPP Nodes have been notified, with 54 meetings held by the PPP Nodes, Committee, and Unit (including 15 meetings held this year). Milestone overachieved. iv) 50 officers have been trained and 23 certified in APMG’s CP3P foundation module.
Source: Project monitoring data, GoKP policy frameworks for energy and housing sector, P&D's documents. Frequency: Quarterly & annual
| Output Indicator 1.2 |  |  | Baseline | March - 2019 | July - 2020 | Baseline | June 2019 | June 2020 | June- 2021 | June - 2022 | June - 2023 | June- 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026
| Viable investment pipeline |  | Planned | No investment mobilization plan available in energy, housing or other sectors. Limited institutional capacity in energy sector to engage with banks/financers and private sector with no IPP complete. No capacity in housing department to undertake commercial projects in JVs No pipeline identified for PPP projects |  |  | No investment mobilization plan available in energy, housing or other sectors. Limited institutional capacity in energy sector to engage with banks/financers and private sector with no IPP complete. No capacity in housing department to undertake commercial projects in JVs No pipeline identified for PPP projects | 1.2 Number of pilot accelerator projects in focus areas agreed with the GoKP and DFID, and average achievement of planned deliverables for them against the workplan | The TA workplan includes sector assessments for downstream projects identification 2. Four sector assessment studies completed to identify downstream work | i) Initiate support on 2 priority projects in key economic development sectors. ii) PPP Unit supported to develop a project pipeline. iii) A comprehensive funding and corporate restructuring plan developed for PEDO’s hydel portfolio. KPI 14. Workshop held with 1-2 relevant Govt. departments to develop a plan for increasing institutional knowledge on climate change issues. (process indicator) | i) A comprehensive funding strategy developed for PEDO’s hydel portfolio. | i) At least 2 priority investment transactions, including at least 1 PPP project, have reached advanced stages* ii) Climate Investment Action Plan developed and LOI issued for at least 1 climate project | i. At least 1 priority investment transaction (PPP/climate) has concluded. ii. Feasibility completed and submitted to Government for KP’s first voluntary carbon markets transaction. iii. Transaction advisory support initiated for Daraban food processing zone for 2024. | i) Procurement initiated for at least 2 transactions (leading to contract award stage) ii) Documentation (or design) complete for 2 additional investment transactions or instruments iii) Carbon market project inventory for at least one sector finalized and being reviewed | i) Contract awarded (or legally binding stage reached) for at least 3 transactions since the start of the program (including 2 in the last year) ii) Procurement stage (or soft launch) reached for 2 additional investment transactions or instruments iii) Carbon market project inventory for at least one sector handed over to the Government
|  |  | Achieved |  |  |  |  | Met: Relevant stakeholders engaged and inducted on the programme. Ministry of Energy was supported with TA support through another programme to improve utilisation of royalties from natural gas, Planning and Development Department to discuss possible priority sectors for the TA support including special economic zones and mines and minerals. | A: Output met expectations 1.2.1. The TA workplan includes 10 sector diagnostic studies. 1.2.2. Nine sector diagnostics to identify SEED’s entry points were submitted for review to DFID team. Four of these will be finalized within the review period. Five are in the process of being revised. The tenth has been postponed in agreement with DFID. | i) Exceeded target. Support initiated for 5 projects. ii) Exceeded target. Pipeline of 42 transactions developed and approved by ACS. iii) Met. Funding strategy developed and approved. ICF KPI 14: | i) Funding strategy already developed in 2021. SEED provided investment advisory support on an initial investment mobilization pipeline of $120 million CF and PF transactions for PEDO ii) Worked with PEDO, P&D, Culture and Tourism Authority and ST&IT for institutional debottlenecking | I. Exceeded. A total of four priority transactions have reached advanced stage this year, instead of 2 as targeted for July'23. In addition, one priority transaction has reached ‘investment facilitated’ stage. II.Exceeded. Climate Investment Action Plan was developed, approved, and implemented with significant progress. Beyond an LOI for one climate/ solarisation project, SEED has made progress against 5 climate initiatives, including: (i) an RFP issued for Solarization of Economic Zones (ii) MoU signed and Concept Note developed for international climate finance; (iii) 2 projects on ITZs have moved to advanced stages; and (iv) Due diligence completed for CFF (v) MoU signed with CRCC. | i. Not met: PPP/climate transaction could not be concluded/delayed beyond June as the government was not willing to take any decision during the interim government period. However, progress is under way. ii. Achieved: Technical Feasibility Study completed during the year and submitted to the government. iii. Achieved: Transaction advisory support has been initiated and is well underway for finalisation in 2024-25 with the legal due diligence report and transaction structure report already submitted to government. | i) Procurement initiated for 2 transactions (ITZs Thandiani and Ganool). PEDO’s partnership agreement has also been signed with PET for I-RECs. ii) Procurement initiated for 2 transactions (ITZs Thandiani and Ganool). PEDO’s partnership agreement has also been signed with PET for I-RECs. iii) Carbon market project inventories have been finalised and approved for both the forests and renewable energy sectors.
Source: Project monitoring reports and government data. World Bank Reports/documents Frequency: Quarterly and annual. Priority investment transactions may simultaneously be developed/executed in PPP mode while also contributing toward climate mitigation and/or adaptation. Investment transactions that reach one or more of the advanced stages (examples provided) would meet the milestones for 2023, 2024 and 2025. *The term 'advanced stage' means that the investment transaction has reached stage where preparation of investment work is complete, specifically: (i) completion of feasibility for solicited PPP project; (ii) submission of final proposal by private party in response to LOI for unsolicited PPP project; (iii) singing of terms sheet for CF/PF transactions **Conclusion of transaction means that the transaction has reached a legally binding stage, specifically: (i) award of contract for solicited and unsolicited PPPs; (ii) signing of financing agreement for CF/PF transactions
OUTPUT 2 | Output Indicator 2.1 |  |  | Baseline (2019) | March - 2019 | July - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June- 2023 | June - 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026 | Risks/Assumptions (Output 1-Outcome)
Improved PIM practices, especially for climate-resilient infrastructure, and policy/institutional reforms to increase fiscal space Impact Weighting: 35% | PIM practices developed/improved and embedded |  | Planned | Deficient SOPs for project design, appraisal and execution Limited data organization integration, manipulability, and accessibility Poor air quality in Peshawar without adequate policy response from GoKP Baseline score for ICF-KPI 13: 7 Baseline score for ICF-KPI 14: 6.84 |  | i) P&D diagnostic study completed, and areas identified for improvement in the project cycle management. ii) BoS initial diagnostics conducted, and critical institutional gaps identified. | Deficient SOPs for project design, appraisal and execution Limited data organization integration, manipulability, and accessibility Poor air quality in Peshawar without adequate policy response from GoKP | Number of partnerships formed between Her Majesty’s Government (HMG) departments and Pakistani authorities | iNumber of partnerships formed between HMG departments and Pakistani authorities | i) SEED PIMA Roadmap developed and agreed with Government to strengthen government's related rules, SOPs, systems and processes. ii) Two technical briefs prepared on areas relating to PIM. iii) At-least one improved PIM practice/ process adopted by the Government (for example. SOPs, modular design for bridges, modular design for roads, improved AASTHO codes etc.) iv) Prototype of data portal for BoS developed and test run, paving way for wider availability of data/ evidence. v) Ensuring uptake of evidence-based policy/ planning as demonstrated by at-least one policy proposal/ study/ sector plan with actionable advice submitted to the Government for approval/ implementation. KPI 13. 1 action in advanced stage to integrate climate change considerations in provincial planning (process indicator) KPI 14. Workshop held with 1-2 relevant Govt. departments to develop a plan for increasing institutional knowledge on climate change issues. (process indicator) | i) At-least two (cumulative) improved PIM practices/ processes (relating to project design, appraisal, execution, monitoring, and completion) adopted and applied by the Government on projects (cumulative) with combined worth of PKR. 500M. ii) Data portal completed launched + manual & training for BOS officials completed to use data portal to update and maintain provincial statistics iii) At-least four (04) departments trained on the use of the data portal for planning (project selection, design and appraisal) and policy formation. KPI 13. Level of integration of climate change in government planning assessed against the Scorecard by establishing baseline (process indicator). KPI 14. At-least 2 workshops held with the GoKP to finalize the baseline against KPI-14, and to improve knowledge of GoKP officials on CC mitigation, adaptation and best practices. | i) PIM tools adopted and applied on at least 10% of new ADP projects ii) Atleast 01 demand-led suggestion resulting in public investment allocation or policy reform by the Government iii) At least 6 projects reviewed from climate resilience perspectives and improved/new project documents submitted | i) At least 6 (cumulative) new PIM tools notified by the Government ii) PIM tools embedded, verified through application on at least 30% of all infrastructure projects approved by PDWP | i) Design and deployment of RAMS and inauguration of Bridge Code ii) Government officials trained in PIM tools through 6 workshops within the year (approximately each with 50 participants) iii) Fully functional PIM portal designed and deployed (with access to all tools and relevant material) | i) A total of 8 SEED-supported PIM tools notified by the Government (including RAMS in the last year) ii) Government officials trained in PIM tools through 15 workshops since the start of the program (approximately each with 50 participants) iii) Fully functional PIM portal handed over to the Government (with access to all tools and relevant material) |  |  | 1. Application of PIM tools is wide enough across GoKP's infrastructure project portfolio to be able to raise public investment efficiency for the entire province 2. GoKP (particularly P&D & C&W) remains committed to implementation of PIM tools beyond SEED exit 3. GoKP will take ownership/ leadership on CC mitigation and adaptation issues, demonstrated by approval of SEED's CC interventions by Steering Committee. 4. BoS has the desired capacity (HR, mandate, etc.) to host, manage and update the data portal, while consistently expanding the database to include data from more departments 5. Public investment managers have the time, capacity and willingness to use BoS data for project identification and planning 6. ICF diagnostic work leads to innovative financing solutions i.e. financial instruments and mechanisms supporting climate change interventions. Also, Government is willing to understand the climate change priorities and the potential implications before any financial mechanisms and instruments are created. 7. Project proposals for climate resilience infrastructure initiatives are duly approved by the PDWP and included in the ADP in coming fiscal years 8. Future governments can withstand the political pressure associated with civil service pension reforms and there is no interruption, loss of momentum or reversal of SEED-supported reforms. 9. GoKP remains open to policy advocacy conducted by PCAA members 10. PCAA remains active in the absence of ongoing SEED support 11. BIU can provide demonstrable value (e.g. through increased revenues) for the GoKP to absorb its financial cost on an on-going basis 12. Adequate technical expertise can be found for the BIU for continued technical mentoring and quality assurance 13. Insights emerging from BIU experiments can be scaled up to realize potential benefits
|  |  | Achieved |  |  | P&D Diagnostic study and BoS initial diagnostics completed. |  | Met: ICED managed housing scoping completed and a final report is submitted | There were no milestones for the reporting period | i) PIMA Roadmap developed and approved by GoKP ii) 2 technical briefs prepared on 'Stimulating Urban Economy' and 'Use of nightlights 'Use of nightlight and satellite imagery data to estimate regional GDP iii) Technical Appraisal Checklists approved iv) Prototype of BoS data portal developed v) SEED pursuing policy proposal on Stimulating Urban Economy with GoKP and ensuring uptake through publications and webinars vi) Climate safeguards introduced in Technical Appraisal Checklists, and ESMS Guidelines for PPPs | i) Technical Appraisal Checklists notified by P&D and used to appraise projects worth PKR 98.bn. Standardized Modular Designs circulated by C&WD for use in project design. ii) BoS portal launched and BoS officials trained on data management and hosting iii) Officials from 8 GoKP departments trained to use data portal iv) FGDs conducted with GoKP departments to establish baseline for KPI 13 and develop Roadmap to improve score v) 2 workshops conducted with 10 GoKP departments to conclude baseline score for KPI 14 | I. Exceeded. PIM tools have been applied on 21% of the ADP which is more than double the 10% target for July 2023. II. Exceeded. 5 demand-led suggestions resulting in policy reform and public investment allocation. This includes new formal guidance on climate-risk appraisal of development projects (floods pivot) as well as the design of 10 new climate adaptation projects that respond to local public demands. PCAA-led advocacy influenced allocation of public investment for air quality improvement and prompted the GoKP to begin work on a Green Transport Strategy. III. Exceeded. A total of 24 new PC-IIs were submitted to government that will eventually lead to 24 climate-resilient development projects executed by GoKP (floods pivot), instead of only 6 as targeted for July 2023. Almost Rs 800 million have already been allocated to these 24 projects in the ADP 2023. | i. Achieved: 7 PIM tools have been developed and notified since the start of the programme. ii. Exceeded: PIM tools have been applied on 62% of all infrastructure projects (40% of all schemes) approved by the PDWP. | i) The Road Asset Management System (RAMS) has been designed and deployed, while the Bridge Code has been inaugurated by the Chief Minister, KP. ii) A total of 7 workshops on PIM tools have been held during the programme year, with over 300 trainees from the C&W Department and PDA. iii). The PIM portal was launched and is now functional, hosting access to all PIM tools developed with SEED support.
* Individuals recruited under the KP Civil Servants Act the Act 1973, after coming into force of the Khyber Pakhtunkhwa Civil Servants (Amendment) Act, 2022 (Khyber Pakhtunkhwa Act No. X of 2022); or an employee of the Government, regularized as civil servant through any legal instrument, issued after coming into force of the Khyber Pakhtunkhwa Civil Servants (Amendment) Act, 2022 (Khyber Pakhtunkhwa Act No. X of 2022), irrespective of the effective date of regularization.
Source: Project monitoring data; PIMA roadmap, periodic assessments; P&D's documents, ADP, notifications, PC-1s; government notifications. Frequency: Quarterly, Annually. With respect to Milestones for 2023, 2024 and 2025, different PIM tools apply to different types of projects at different stages in the planning cycle. The targets refer to the total value of projects on which any/all tools have been applied during the year.
| Output Indicator 2.2 |  |  | Baseline | March - 2019 | July - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 | Oct- 2025 | June 2026 | Oct 2026
| Policy reforms and institutional support to create fiscal space |  | Planned | Unchecked and unsustainable growth in civil service pension liabilities Limited exploration of options to mobilize additional revenue |  | i) Potential areas of policy reforms identified with the purpose to increasing provincial revenue, and reducing provincial expenditure. ii) Potential areas of institutional support identified with the purpose to increasing provincial revenue, and reducing provincial expenditure. | Unchecked and unsustainable growth in civil service pension liabilities Limited exploration of options to mobilize additional revenue | High quality engagement on economic and urban development nationally or in other provinces. | High quality engagement on economic and urban development nationally or in other provinces. | Scoping visit by Office for National Statistics (ONS) to assess scope and parameters of partnership with KP Bureau of Statistics (KPBOS) Climate change implementation unit agreed with Planning Commission and support in place by End-October | i) Two policy proposals (cumulative, carbon tax, health outsourcing, pension reforms - DCS reform strategy etc.) developed and presented to the government for implementation. ii) BI/Nudge Unit operationalized and KPIs agreed, with yearly plan and at-least one experiment initiated (with a focus on inclusive and gender-sensitive campaigns). iii) STS Delivery Lab/ Yearly Action Plan signed off by FM, and revamping of KPRA website supported. | i) Proposal (PC-I/SNE, etc.) for Pension Management Cell submitted to Government ii)BI/ Nudge Unit functional and at least one experiment completed iii) WB Diagnostic Study approved by the Government | i. Accounts of 10% of the newly recruited employees (40,000) are open and first contributions transferred into their accounts. ii. At least 2 experiments/ nudges (cumulative) completed by BIU. iii. Submission of comprehensive communications plan for sustainability of pension reforms to Finance Department. | i) Four DCS Implementation Roadmap meetings held during the year with meaningful progress ii) External pension review initiated and initial findings presented to Finance Department | i) DCS Implementation Roadmap fully operational and on-track manifested by: a) Regular meetings (at least 1 per quarter over the last five quarters) b) Meaningful progress against milestones reflected in meeting minutes ii) External pension review complete and relevant observations made part of the DCS Roadmap
|  |  | Achieved |  |  | Potential areas for policy and institutional reforms identified |  | Met: Covered as part of the existing TA ToRs published | A tender was launched on 18 Feb 2020 and completed on 17 March 2020. | Met. Virtual scoping workshop held on 8 June and ToRs of in-country scoping visit agreed, pending COVID-19 situation in Pakistan Met. Proposal for support received and on-track to begin implementation end-October | i) Four policy proposals submitted to GoKP in 2021. Three additional in 2022: Health Outsourcing, DCS reform and pension policy note were developed and presented to GoKP ii) BIU restructured and re-notified, 17 government officials trained, office premises secured and Advisory Committee active. Policy agenda and KPIs for BIU also approved and first experiment initiated. iii) STS Delivery Lab held with Yearly Action Plan for FY 22 approved. KPRA website revamped and relaunched | I. Exceeded. Proposal approved for the Pension Management Cell. Additionally, significant implementation progress was also achieved for the DCS reform including: i) Approval of DCS Rules; ii) Agreement with Asset Management Companies; iii) NOC for pension fund schemes; iv) and revised VPS Rules submitted to Finance Division for approval. II. Achieved. BIU is functional with dedicated in-house resources and a well-equipped office space within the Finance Department. One experiment is complete, and a second experiment has been initiated. III. Exceeded. The World Bank Diagnostic Study has been approved by the Cabinet and work has already started on developing a comprehensive climate project for KP. | i. Achieved: 24% of new employees have received their first contributions in their accounts. ii. Achieved: 3 nudges/experiments have been completed by BIU, but the result of only 1 study has been published during the review period. iii. Achieved: A communications plan was submitted to the Finance Department in June 2024 | i) A total of 5 DCS Roadmap meetings have been held during the year, with meaningful progress against Roadmap milestones. ii) The external pension review was concluded with both initial and final findings shared with the Finance Department.
* Individuals recruited under the KP Civil Servants Act the Act 1973, after coming into force of the Khyber Pakhtunkhwa Civil Servants (Amendment) Act, 2022 (Khyber Pakhtunkhwa Act No. X of 2022); or an employee of the Government, regularized as civil servant through any legal instrument, issued after coming into force of the Khyber Pakhtunkhwa Civil Servants (Amendment) Act, 2022 (Khyber Pakhtunkhwa Act No. X of 2022), irrespective of the effective date of regularization.
Source: Project monitoring data, Government notifications Frequency: Quarterly, Annual
IMPACT WEIGHTING ( 15%)
OUTPUT 03 | Output Indicator 3.1 |  |  | Baseline | June - 2019 | June - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 |  | June 2026 |  | Risks/Assumptions
BHC Managed Technical Assistance for Economic and Urban Development IMPACT WEIGHTING 15% | High quality climate focused engagement on economic and urban development nationally or in other provinces. |  | Planned |  | Housing scoping innitiated and a mid term report drafted | Tender process completed for technical assistance to the Ministry of Climate Change and Ministry of Energy on CC/RE |  |  |  | GBP 0.86 Million Principal SEED recruited. 2. Pipeline developed: | 1.)Unit fully staffed and operational. 2.) Project pipeline developed and work initiated on 5 specific concept notes 3.) Steering committee notified | 1) Upto three MOUs signed with partners to provide techncial assistance for proposal development 2) Two concept notes submitted to international climate funds 3) Upto two more concept notes finalised with partners for submission to access international funding opportunitie. | 1) Upto two full funding proposals submitted to GCF (incuding all annextures - Techncial and Financial feasibilities, Environmental and Social Safeguards, Gender Assessments and Action Plans, others). 2) No-Objection Letter (NOL) for upto two proposals recieved from the Government of Pakistan. 3) Board consideration date for approval by GCF recieved for at least one proposal. | i) One funding proposal approved by the GCF. ii) Funded Activity Agreement (FAA) for the approved project signed. iii) Upto two additional concept notes submitted to national and international financing entities. |  | 1) One funding proposal clears all pre-implementation requirements and implementation initiated. 2) Board consideration date for approval by GCF recieved for at least one proposal.
|  |  | Achieved |  |  | Tender process completed with no bids received |  |  |  | GBP1.02 Million Significantly Not Met i- Recruitment for Principal SEED in process ii- 10 deals under long list iii- EAD approval severely delayed. | Met. Unit established, fully staffed and operational. Project pipeline developed with 8 concept notes presented and discussion initiated with relevant stakeholders. Steering committee has not been notified due to change in government and key personal. | Achieved. Four MoUs were signed: i) MoU between CRCC, JS Bank and EXIM Bank for CRCC to provide TA in developing a programme for ‘Enhancing Green Export Capacity’ and accessing international climate finance. ii) MoU with GoKP for establishing a Carbon Facility. iii) TA Agreement between NRSP and JS Bank to collaborate on (re)accreditation iv) MoU with Karandaaz to support them in accessing climate finance. Exceeded. Concept Notes submitted to international climate fund - three concept notes submitted to GCF: i) Enhancing Green Export Capacity through Green Financing ii) Harnessing the domestic private sector ecosystem for climate action in Pakistan iii) ‘Electric 3-wheelers and battery swapping stations’ Achieved. Additional concept notes finalized with partners: i) Living Indus Initiative ii) Establishing Carbon Facility for GoKP | ii. Achieved. Two full funding proposals submitted to the GCF with all relevant annexure and required third party validations: a. Climaventures: Harnessing the domestic private sector ecosystem for climate action in Pakistan. b. ‘Electric 3-wheelers and battery swapping stations. Not only has this proposal been submitted to the GCF during the year with all the additional requirements, together with implementing partner it was submitted to Mitigation Action Facility (MAF) for co-financing with GCF. It has been selected among 300+ proposals submitted globally iii. Achieved. Following the national approval process, two no-objection letters have been secured from the Ministry of Climate Change for the two projects mentioned in (1) above. iv. Achieved. Subject to the Independent Technical Advisory Panel clearance (pre-requisite), the Fund has communicated the Climaventures proposal will be considered by the GCF Board at its 40th meeting, scheduled for 21 - 24 October 2024. | i). Funding proposal approved by the GCF Board at the 40th Board Meeting. ii).All requisite processing requirements including legal negotiations between NRSP and GCF timely concluded - document ready for signatures. However, as a risk mitigation measure, due diligence of IP was advanced to pre-signing stage, therefore signing of FAA was consciously delayed to include findings of due diligence. iii). Two concept notes have been submitted to International Climate Initiative, and Welcome Trust, with a project size of GBP 1.4 million each. Additionally, two concept notes are in different stages of development.
Source: GCF, CRCC reports
OUTPUT 04 | Output Indicator 4.1 |  |  | Baseline | June - 2019 | June - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 | June -2026 | Oct-2026 |  | Risks/Assumptions
Support to WB under the Monitoring, Evaluating and Following the Flow of Funds for Reconstruction (ME3F) - Pakistan@100 IMPACT WEGHTAGE 5% | AA amendment signed between FCDO and World Bank (WB) to initiate ME3F work |  | Planned | TBD | TBD | TBD | 0 | n/a | N/A | N/A | N/A | N/A | i. Amendment to Pakistan@100 agreement signed between FCDO and WB. ii. Review of ME3F work and formal submission approved from Chief Scientific Officer within team ‘FCDO Research and Evidence Directorate (RED) iii. Costed workplan, and results framework finalised with the WB team. iv. Budget allocated and finalised | i). Adminstrative Ammendment signed between FCDO and World Bank on ME3F. ii). Result Framework updated with World bank iii). firms hired by WB for MPHS & Infra audit surveys.
|  |  | Achieved | TBD | TBD | TBD | 0 | n/a | N/A | N/A | N/A | N/A | i. Achieved: Amendment 07 signed under Pakistan@100 AA to contribute to ME3F work. ii. Achieved: Submission approved by Chief Scientific Officer iii. Achieved: Workplan and results framework received, while disbursement schedule is being finalised to ensure effective financial forecasts. iv. Achieved: £5mn budget allocated for the intervention. | i)Administrative Amendment 08 signed for ME3F on 25 November 2024 ii).World bank shared updated result farmwork with FCDO. iii). The MPHS contract for Sindh was awarded to two firms. The Request for Proposals (RFP) closed at the end of June for the Infra Audit Survey.
Closed outputs
OUTPUT 3 | Output Indicator 3.1 |  |  | Baseline | June - 2019 | June - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 |  |  |  | Risks/Assumptions | Risk/Assumptions
Support for Renewable energy generation and energy efficiency in industry (Impact Weightage 10% | Successful closure of KRN SEED component |  | Planned |  |  |  |  | Number of policy and regulatory changes agreed with Government of Pakistan (GoP)/private sector and DFID; average achievement of planned deliverables for addressing them against work plan Mega Watts (MW) generated or saved through direct SEED support disaggregated by: - RE distributed/generation - EE energy efficiency Private investment leveraged by SEED for RE/EE purposes/ off-take of financing | Financial Close of KRN's investments for at least 2.25 MWs. 2. 15 entities receiving IFC advisory services and 8,000 MWh energy saved .£1.5 million of private investment legally committed 1. 5 additional staff members recruited for SEED programme; re-advertisement of position of Principal 2. Pipeline development: a. 15 deals under long list pipeline b. 3 transactions under internal review c. 2.25 MW transaction under preparation for submission to Investment Committee (IC) 3. Strategy paper updated and presented to IC and DFID on approach to RE/EE investments 4. Terms of Reference for monitoring and evaluation agreed . | Zero MWs | - 1.12MWs RE - Zero MWs (EE) L66 Investment Proposals to support up to 4.31 MWs of RE/ EE approved by the KRN-Board. GBP 2.66 Million 1. Pipeline developed: 6 deals under long list pipeline. 2. EAD approval received 3. Energy Audit of portfolio companies commissioned. 4. Draft SEED investment strategy developed 5. Procurement process of M&E firm initiated after seeking approvals from KRN Board. N65 | 7.27MWs attributable share Investment Proposals to support up to 12.91 MWs approved by the KRN-Board. £3.08m assumed leverage factor (1.5 x) I. Pipeline developed: 6 deals under long list pipeline II. Energy Audit of 8 portfolio companies successfully completed. | i. Closure of KRN SEED AGA in line with EAGR closure to ensure returnable capital with KRN is managed in equitable and accountable way. ii. Principal amount of £ 2.4mn fully disbursed. iii. KRN redeploys capital funds and ensure no unspent funds are left under SEED programme. iv. Funds disbursed within the remit and purpose of the original AGA. (KRN shares list of investors to which these funds will be disbursed). v. Karandaaz has sound corporate governance and board structure. Asset disposal in line with EAGR closure. | Closed
|  |  | Achieved |  |  |  |  | AA with IFC signed in Dec 2018. 2. IFC TF is partially staffed (see below) 3. IFC result framework not finalised Exceeded expectations: 1. Implementing partner identified, proposal, budget and AGA agreed in June 2019 2. Smart Rule 11 approval sought; received in June 2019 3. Head of Office approved the proposed signing of the AGA with KRN in May 2019 Met: Targets and methodology for leveraging agreed with KRN as part of their proposal | Partially Met Investment Proposal to support up to 2 MWs of RE (Solar) approved by the KRN-Board. .14 businesses receiving advisory services under the Resource Efficiency Project, 2 financial institutions receiving advisory under Sustainable Energy Finance project. 11,800 MWh energy saved reported by firms under resource efficiency project. Term Sheet Signed between KRN and Private entity committing £580k of Private Investment in RE. Additional $2.9 million private investment leveraged as a result of IFC energy efficiency interventions. 4 staff recruited, candidates for 2 vacant positions shortlisted. 2.3.2. Pipeline developed: a. 15 deals under long list pipeline b. 4 transactions under internal review c. Up to 2 MW transaction approved from IC 2.3.3. Strategy paper updated and approved by IC, Board of Directors and DFID. 2.3.4. ToRs for monitoring and evaluation agreed with DFID. | Progress Met Installation of 3.87 MW (KRN share 0.6MWs) RE project near completion. | Not Met: Installation of 3.86 MW Renewable Energy project successfully completed. KRN attributable share 0.65MWs No EE projects initiated Exceeded Target: 9.83 MWs (cumulative-KRN share only) of RE (Solar) approved under EBR and REON Financing facilities. Exceeded target: GBP 14.7 million Met: 1. 6 deals in the pipeline 2. EAD approval received. 3. Energy Audit of three portfolio companies successfully completed. 4. SEED Investment strategy developed and shared with FCDO. 5. Procurement for M&E firm approved by Board but process on hold on BHC Islamabad advice. | Exceeded. Installation of 57.83 MW RE project successfully completed. KRN attributable share 10.2 MWs cumulatively Not fully met.10.85 MWs (cumulative-KRN share only) of RE (Solar) approved Exceeded. £12.2m (PKR 4.42 bn) I. Achieved. 6 deals in the pipeline II. Achieved. 8 energy audits completed with results adopted by the portfolio companies. | i. Achieved. KRN closure in line with EAGR closure. FCDO PROF guidelines and policies followed during the closure process. ii. Achieved. Principal amount of £2.4mn fully disbursed. iii. Achieved KRN has redeployed capital funds under its green team. No unspent funds left under the programme. iv. Achieved. KRN funds to be disbursed with the original remit and purpose of the original AGA as agreed in the signed closure letter and signed certificate between FCDO and KRN. v. Achieved KRN has sound corporate governance and board structure. Long term governance framework and sustainability plan in place. Asset disposal in line with EAGR closure. | Closed
| MWs installed [KRN share only] through direct SEED support |  | Planned |  | 1.AA with IFC signed 2. IFC TF is fully staffed 3. Result Framework finalized | 1.Financial Close of KRN's investments for at least 2.25MWs. 2. Receiving advisory support services for IFC- 15 entities receiving advisory services and 8,000 MWh energy saved |  |  | 1.Financial Close of KRN's investments for at least 2.25MWs. 2. Receiving advisory support services for IFC- 15 entities receiving advisory services and 8,000 MWh energy saved | 0 MW | 1.12MWs RE - Zero MWs (EE) | 7.27MWs | NA - Project closed |  |  |  |  | NA - Project closed | Team to decide on the physical asset disposal under SEED component with KRN. Opportunity to disburse these assets to CRCC and ASI on priority bases.
|  |  | Achieved |  |  | Investment Proposal to support up to 2 MWs of RE (Solar) approved by the KRN-Board. 14 businesses receiving advisory services under the Resource Efficiency Project, 2 financial institutions receiving advisory under Sustainable Energy Finance project. 11,800 MWh energy saved reported by firms under resource efficiency project |  |  | Investment Proposal to support up to 2 MWs of RE (Solar) approved by the KRN-Board. 14 businesses receiving advisory services under the Resource Efficiency Project, 2 financial institutions receiving advisory under Sustainable Energy Finance project. 11,800 MWh energy saved reported by firms under resource efficiency project | Met Installation of 3.87 MW (KRN share 0.6MWs) RE project near completion. | Not Met: Installation of 3.86 MW Renewable Energy project successfully completed. KRN attributable share 0.65MWs No EE projects initiated | Installation of 57.83 MW RE project successfully completed. KRN attributable share 10.2 MWs cumulatively | NA - Project closed |  |  |  |  | NA - Project closed
Notes: These are targets for each year and not cumulative. We have assumed that financial commitment (KRN share only) of any year will result in 1/3 installation of MW in the same year and 2/3 in the following year. These targets are RE focused only. Targets for Energy Efficiency will be determined once a pipeline of EE projects is developed and a scoping study is conducted. Mov: KRN reporting, implementing partners self reporting and Third party validation.
| Output Indicator 3.2 |  |  | Baseline | June - 2019 | June - 2020 | Baseline |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 |  |  |  | 2025-08-01 | Risk/Assumptions
| MWs committed through direct SEED support [KRN share only] |  | Planned |  | 1. Implementing Partner identified, Proposal, budget and AGA agreed 2. Request for SR11 approval submitted 3. HoO aggreement with the AGA | Investment Proposals to support up to 1.12 MWs of RE (Solar) approved by the KRN-Board. |  |  | Investment Proposals to support up to 1.12 MWs of RE (Solar) approved by the KRN-Board | Investment Proposals to support up to 1.12 MWs of RE (Solar) approved by the KRN-Board. | Investment Proposals to support up to 4.31 MWs of RE/ EE approved by the KRN-Board. | Investment Proposals to support up to 12.91 MWs approved by the KRN-Board. | NA | NA - Project closed |  |  |  | NA - Project closed
|  |  | Achieved | [6 empty] | Not Met No MWs committed through direct SEED support approved during the year | Exceeded Target: 9.83 MWs (cumulative-KRN share only) of RE (Solar) approved under EBR and REON Financing facilities | 10.85 MWs (cumulative-KRN share only) of RE (Solar) approved
Notes: This is cumulative number for the project period, only for KRN share of the total capacity of each project. These targets are RE focused only.Targets for Energy Efficiency will be determined once a pipeline of EE projects is developed and a scoping study is conducted. Mov: KRN reporting, financing agreements, term sheets, IC/ Board approvals/ presentations.
| Output Indicator 3.3 |  |  | Baseline | June - 2019 | June - 2020 | Baseline |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 |  |  |  | Risks/Assumptions | Risk/Assumptions
| Private investment leveraged by SEED for Off-take of financing |  | Planned |  | Targets and Methodology for leveraging agreed with the delivery partner. | £1.5 million of private investment legally committted. |  |  | £1.5 million of private investment legally committted. | GBP 0.86 Million | GBP 2.66 Million | GBP 3.08 Million assumed leverage factor (1.5 x) | NA | NA - Project closed |  |  |  | NA - Project closed
|  |  | Achieved |  |  | Term Sheet Signed between KRN and Private entity committing £580k of Private Investment in RE. Additional $2.9 million private investment leveraged as a result of IFC energy efficiency interventions |  |  | Term Sheet Signed between KRN and Private entity committing £580k of Private Investment in RE. Additional $2.9 million private investment leveraged as a result of IFC energy efficiency interventions | Met GBP1.02 Million | Exceeded: 14.7 million | GBP 12.2 million (PKR 4.42 B
Notes: This is the amount of additional financing committed/ raised from other sources [partners, investors, shareholders, commercial banks, DFIs, etc.] each year. For target setting we have assumed a leverage factor of 1x in the 1st year i.e. for each £1M invested/ committed by KRN, additional £1M is committed/ raised from other sources, the leverage factor is gradually increased in subsequent years. These are targets for each year and not cumulative Mov: KRN reporting, financing agreements, term sheets, IC/ Board approvals/ presentations.
| Ouput Indicator 3.4 |  |  | Baseline | June - 2019 | June - 2020 | Baseline |  | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 |  |  |  | Risks/Assumptions | Risk/Assumptions
| Institutional capcity developed for effective management of the programme. |  | Planned |  | Targets and Methodology for leveraging agreed with the delivery partner. | i- 5 additional staff members recruited for SEED programme; readvertisement of position of Principal ii- Pipeline development: a. 15 deals under Long list pipeline b. 3 transactions under internal review of CIC c. 2.25 MW transaction under preparation for submission to IC iii- Strategy paper updated and presented to IC and DFID on approach to RE/EE investments iv- ToRs for monitoring and evaluation agreed |  |  | i- 5 additional staff members recruited for SEED programme; readvertisement of position of Principal ii- Pipeline development: a. 15 deals under Long list pipeline b. 3 transactions under internal review of CIC c. 2.25 MW transaction under preparation for submission to IC iii- Strategy paper updated and presented to IC and DFID on approach to RE/EE investments iv- ToRs for monitoring and evaluation agreed | 1. Principal SEED recruited. 2. Pipeline developed: 06 deals under long list pipeline. 3.All outstanding operational requirements are fulfilled and approvals from EAD received . | 1. Pipeline developed: 6 deals under long list pipeline. 2. EAD approval received 3. Energy Audit of portfolio companies commissioned. 4. Draft SEED investment strategy developed 5. Procurement process of M&E firm initiated after seeking approvals from KRN Board. | 1. Pipeline developed: 06 deals under long list pipeline 2. Energy Audit of 08 portfolio companies successfully completed. | NA | NA - Project closed
|  |  | Achieved |  |  | 4 staff recruited, candidates for 2 vacant positions shortlisted. Pipeline developed: 15 deals under long list pipeline 4 transactions under internal review Up to 2 MW transaction approved from IC Strategy paper updated and approved by IC, Board of Directors and DFID. ToRs for monitoring and evaluation agreed with DFID |  |  | 4 staff recruited, candidates for 2 vacant positions shortlisted. Pipeline developed: 15 deals under long list pipeline 4 transactions under internal review Up to 2 MW transaction approved from IC Strategy paper updated and approved by IC, Board of Directors and DFID. ToRs for monitoring and evaluation agreed with DFID | Significantly Not Met i- Recruitment for Principal SEED in process ii- 10 deals under long list iii- EAD approval severely delayed. | Met: 1. 6 deals in the pipeline 2. EAD approval received. 3. Energy Audit of three portfolio companies successfully completed. 4. SEED Investment strategy developed and shared with FCDO. 5. Procurement for M&E firm approved by Board but process on hold on BHC Islamabad advice. | I. 06 deals in the pipeline 08 energy audits completed with results adopted by the portfolio companies.
Notes: Long list pipeline shall include potential investment oppurtunity under the SEED program which are being evaluated by the team Mov: Pre IC Memo / Non disclosure agreement for pipeline development
Output 4 | Output Indicator 4.1 |  |  | Baseline | June - 2019 | June - 2020 | Baseline | June 2019 | June 2020 | June - 2021 | June - 2022 | June - 2023 | June - 2024 | June - 2025 |  |  |  | Risks/Assumptions | Risk/Assumptions
BHC Managed Technical Assistance for Economic and Urban Development IMPACT WEIGHTING 15% | Number of partnerships formed between HMG departments and Pakistani authorities |  | Planned | 0 | Need for scoping for the partnerships was made part of the ToRs for TA | to be determined at inception | To be determined at inception | Process and performance evaluation for Component 1 Independent validation of results and TA for methodology on monitoring key results for RE/EE component | Process & performance evaluation for Component 1 | Investment Proposals to support up to 1.12 MWs of RE (Solar) approved by the KRN-Board. 06 deals under long list pipeline. 3.All outstanding operational requirements are fulfilled and approvals from EAD received. | Agreement in place with ONS for partnership with KPBOS | Due to budget cuts, reprioritisation and security concerns of travelling to KP, any activities under this component were paused | Due to budget cuts, reprioritisation and security concerns of travelling to KP, any activities under this component were paused | NA - Project closed
|  |  | Achieved |  |  |  |  | Met: ToRs for an ESP for the TA component got fair rating from EQUALS and are tendered. Met: On track with agreement between DFID programme team and KRN on the scope for an independent monitoring firm, ToRs for procurement are being drafted. | Met expectations 4.1.1. Requirements for evaluation and clear split of roles and responsibilities agreed with ASI and reflected in the ToRs for the process and performance evaluation for output 1. 4.1.2. Procurement process for hiring an ESP re-initiated. This includes a procurement lead allocated and tender pack ready to be published. . | Not Met No MWs committed through direct SEED support approved during the year | Not met. Initial discussion took place with online scoping held, but agreement was not signed due to COVID, travel challenges to KP and ODA re-prioritisation. | N/A | N/A
Source
Scoping report
Note on L21: Enhanced public-sector capacity for public investment planning and management.
Note on N36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to revised downwards to accommodate the impact of increased interest rates, economic slow down and overall poor economic outlook including impact of floods 2022, Ukraine Russia conflict and ongoing political instability - Pakistan has averted a default.
Note on I40: Tahir Naeem: Output Indicator 1 in 2019: Improved provincial economic and urban development planning in KP
Note on K40: Reduced institutional, policy and transaction bottlenecks for private-sector and multilateral investments.
Note on J44: Improved Provincial Economic and Urban Development Planning in KP
Note on I48: Output 3 in 2019 DFID managed TA for Economic and Urban Development
Note on I53: Output 3 in 2019 DFID managed TA for Economic and Urban Development
Note on J53: Output 3 in 2019 DFID managed TA for Economic and Urban Development
Note on N67: Process Indicator as per FCDO guidelines and PROF rules on SPV.
Note on N73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where is this number coming from?
Note on N78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are these proposals coming from KRN? Are we not closing the contract?
Note on N83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are we not closing KRN?
Note on I88: Impact and effectiveness of TA to the GoKP and validation of the RE/EE results to the SMEs is measured
Note on J88: Output 04 in 2020 : Impact and effectiveness of TA to the government of KP